## Marshall Islands
MARSHALL ISLANDS
REPORT NAME | SECTORS | DATE | LESSONS | REPORT TYPE | REPORT RATING | LINK
Public Sector Program - Subprograms 1 and 2: Program Completion Report | Public Sector Management | 2014-01-10 | 1. Program context and government ownership. The intended program outcome of achieving fiscal sustainability was overambitious, given the historically slow pace of reforms in the Republic of Marshall Islands and in other countries facing fragile situations. Moving forward with the reforms needed to fully deliver the program outputs required approval of three key pieces of enabling legislation, but the program design did not take into account the likelihood of a lengthy parliamentary approval process and underestimated the political opposition such reforms might encounter. The program's design did anticipate the political sensitivity associated with some of the proposed reforms and supported a public consultation process to garner support and build ownership, but resistance has continued and is still delaying approval, which was initially expected to come by program completion. [Main text, para. 37] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform 2. Design and monitoring framework (DMF). The program's DMF was overambitious (para. 8) and, based on ADB guidelines for DMF preparation could have been correctly recast to make the outcome the intended impact and output 1 the intended outcome. The outcome and impact statements and indicators and targets in a DMF need to be realistic and take into account the country context. [Main text, para. 38] project cycle stage: Design Lesson Topics: 3. Policy actions: All Pacific developing member countries, including the Republic of Marshall Islands (RMI), have great difficulty implementing policies to support long-term adjustments. The program included several line expenditure conditions under output 2 that the government struggled to implement and monitor (para. 16). In the end, the government decided to make across-the-board expenditure cuts rather than the targeted cuts proposed under the program. The condition targets were related to budget estimates rather than budget outturns. Achieving these estimates requires a strong budgetary system, but the system in the RMI is weak. It may have been more appropriate to set conditions relating to budget processes and controls rather than estimates that proved difficult to execute. [Main text, para. 39] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Policy & Reform: Reform 4. On-the-ground support. Policy dialogue required on-the-ground support from ADB. Establishment of the ADB development coordination office in November 2011 played a key role in forging policy dialogue, although this was undertaken issue-by-issue (expenditure management, taxation, and state-owned enterprise reform) rather than through a holistic approach. Other development partners also provided substantial support for public sector reform in the Republic of Marshall Islands, but the coordinated dialogue with government that has been used successfully in programs elsewhere in the Pacific was missing. In the absence of a central foreign assistance unit or other aid coordination mechanism within government and if the proper channels for timely communication are not in place, risks of duplicated, excessive, or insufficient support in certain reform areas exist. [Main text, para. 40] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Policy & Reform: Reform Methodologies/Approaches: Policy dialogue | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/rmi-public-sector-program-subprograms-1-2-pcr
Skills Training and Vocational Education Project |  | 2006-11-15 | 1. In the case of a weakly performing, fragile, state (such as the Republic of Marshall Islands) - where governance is weak and institutional performance can also be expected to be poor - project design must pay far greater attention to examining the effective demand for any public sector improvement and the need to strengthen institutions and capacity development. [Main text, paras. 3, 53-54, 64(i)] project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Project Design: Project design Capacity Development: Capacity development Capacity Development: Institutional analysis Policy & Reform: Reform 2. National consultants should be preferred over international consultants where qualified, skilled, and otherwise competent national consultants exist. Greater attention should be given to consultants' terms of reference, so that this may complement local capacities. There is a growing cadre of Marshallese consultants in the field of economics and social development and ADB is increasingly employing them. [Main text, paras. 43, 46, 64(ii)-(iii)] project cycle stage: Appraisal Implementation Lesson Topics: 3. The engagement of a full-time, qualified accountant who is experienced in ADB loans can greatly assist project implementation. In this project, the accountant did an excellent job of tracking all orders. and ensuring timely payments to vendors and proper distribution of landed goods. [Main text, paras. 45, 64(iv)] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Project Management: Procurement Project Management: Project administration | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/skills-training-and-vocational-education-project
Ebeye Health and Infrastructure Project |  | 2004-12-15 | External management and privatization are critical for successful and viable operation of utilities in small island communities. The ongoing management contract with American Samoa Power Authority or ASPA (an external entity) was a key to the improvement of the operations of the power and water utility. ASPA's technical expertise, controls, and discipline in managing the operations - and its strict adherence to rules for revenue collection - helped to turn around the loss-incurring, government-owned public utility. Therefore, the appointment of a private sector operator to manage and control the utility for a minimum of 18-24 months as a condition of loan effectiveness was a key to project success. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Sector Related Issues: Energy planning/management Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Policy & Reform: Privatization Extra precaution should be taken in materials and equipment specifications to take into account the harsh external environmental conditions in the Pacific islands, such as high humidity, excessive salt content in the air and water, high temperatures, exposure to elements, etc. These conditions contribute to rapid and excessive corrosion of materials and equipment. project cycle stage: Implementation Lesson Topics: For projects of this size and in such a remote location, international competitive bidding often is not possible. Several bid attempts failed due to a lack of responsive bids, as few international bidders expressed interest in civil works that required even minimal mobilization. This caused much of the project's delay. A preferable approach would involve the use of domestic contractors (through local competitive bidding) where feasible, and negotiated bids with international contractors based on the island or with prior work experience in the Marshall Islands. project cycle stage: Implementation Lesson Topics: For proper collection and professional management of public utilities, strong controls, operating guidelines, and appropriate legislation should be in place from the start. This was done before the project began, which led to an immediate turnaround. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Sector Related Issues: Energy planning/management Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework Minimal implementation problems were encountered because (a) adequate consultations were undertaken with all stakeholders during project preparation; (b) a domestic project manager headed the project management unit (PMU); (c) the government, particularly the Office of the President, provided full support; and (d) ADB provided some flexibility in implementation to address the special circumstances of the project. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach Rehabilitation of equipment and completing unfinished buildings was significantly more complex than anticipated, and the main reasons for the 1-year delay in implementation. Given the isolation and remoteness of the location, an implementation period longer than 30 months should have been provided. project cycle stage: Feasibility, Appraisal Lesson Topics: Single-source procurement should be allowed in cases where, in rehabilitating old equipment, the only option for procuring spare parts is the original manufacturer of the equipment. project cycle stage: Implementation Lesson Topics: The inadequacy of the original hospital design, and non-compliance with health and safety standards, was not fully anticipated during project design. This was a unique situation, and such work in the future should be undertaken after more thorough investigation. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/ebeye-health-and-infrastructure-project
Fiscal and Financial Management Program |  | 2004-06-15 | Negotiations on the Compact [Compact of Free Association between the Governments of the Marshall Islands and the United States of America (US)], especially the extension of the economic assistance package, complemented and reinforced this reform program. The Compact Negotiation Office (CNO) became a partner and stakeholder in the reform process. The CNO helped champion many of the program reforms, and moved forward on many reforms when the executing agency (Ministry of Finance) was still lagging. In contrast, the government showed little support for the reform program during the Public Sector Reform Program (PSRP). The PCR for the PSRP recognized that lack of champions of reform within the government, which made reforms much more difficult to implement. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Policy & Reform: Public sector reform The implementation of the program provides a useful comparison with the difficulties faced during the implementation of the Public Sector Reform Program (PSRP). Many of these difficulties can be attributed to the fact that the PSRP involved severe, painful, and enforced reductions in the number of employees in the public service. Even so, it is interesting to note the differences that appear to have allowed for a smoother implementation of the program. Among the most notable differences was the improved dialogue between ADB and the government, which was willing to address reforms. The administration implementing the program was elected in 1999, and initially addressed the outstanding conditions of the PSRP. The new government then proceeded to implement the program with the assistance of ADB, moving forward on a number of reform fronts. The openness of the new administration made implementing reforms more realistic. Although some progress in fiscal policy has been demonstrated, some weaknesses endure. project cycle stage: Concept Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Loan Agreement: Covenants Modality: Program Policy & Reform: Policy matrix Policy & Reform: Public sector reform The improved design of the program can be attributed to a more consultative and participatory process than in the Public Sector Reform Program (PSRP). Meto 2000, created under a Pacific Islands Economic Report (PIER) TA, involvedwidespread consultation with the community about the impacts of the PSRP and the priorities for further reform. The recommendations of the Meto 2000 led to many of the reforms included in the program. When it came to implementing the program, Meto 2000 ensured a greater understanding of the reform process and the need for the reforms. However, the reforms under the program were less painful and less dramatic than those required under the PSRP. project cycle stage: Feasibility Lesson Topics: Modality: Program Modality: Technical Assistance Project Design: Project design Country Context: Prioritization Policy & Reform: Reform Methodologies/Approaches: Participatory approach The program was implemented without the coordination of a program steering committee, a noteworthy accomplishment. Good coordination between the executing agency (Ministry of Finance) and the Compact Negotiation Office (CNO) was a key to successful implementation. When problems arose, they were resolved through close consultation among key agencies - without resorting to a formal program steering committee. The CNO also needed to move forward quickly on some fronts due to the momentum of the Compact negotiating process. The result was that the program and the Compact negotiation process reinforced each other, leading to a greater impetus for reform. This situation, which is closely related to the need for champions of reform, shows how useful it can be to link reforms to parallel processes with similar objectives. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/fiscal-and-financial-management-program
Majuro Water Supply and Sanitation Project | Water and Other Urban Infrastructure and Services | 2004-03-15 | A single turnkey contract, while easier to implement, is not always the most effective and efficient way to implement a multiple component project. project cycle stage: Appraisal Implementation Lesson Topics: Applying the principles of full cost recovery and determining onlending rates must be properly evaluated, especially for small utilities with limited financial capacity. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Monitoring & Evaluation: Project evaluation Project Design: Appraisal Capacity Development: Capacity assessment Sector Related Issues: Health and sanitation management Better understanding of local conditions, the operational setup of the utilities concerned, and the cultural environment in which the project will operate, are vital to proper design and implementation. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Country Context: Cultural constraints For smaller communities, much greater analysis is required before designing tariffs, particularly when alternative sources of water are accessible. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial analysis Sector Related Issues: Health and sanitation management In the absence of an in-depth review and analysis, accepting the continuation of detailed design consultants to continue with supervision of construction must be made with much circumspection. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Project supervision In transferring water resources to other locations from areas where there are resource limitations, better understanding of political climate and in-depth consultations leading to proper agreements should be in place prior to project formulation. project cycle stage: Concept Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation Lack of adequate consultation at project preparatory stage and at design stage with the end user and other stakeholders can reduce the impact of a project. Consultations that cover type and level of proposed facilities, size, costs involved, probable tariffs, affordability, and willingness to pay are vital for the sustainability of the project. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Methodologies/Approaches: Consultation/Participation The assumptions on revenue growth and tariff increases must be based on social indicators that are not unrealistically high. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Indicators The project design and the consequent loan size must take into consideration the size of the utility and population of the project location. Over ambitious projects can become a burden of the government and the community. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Sector Related Issues: Health and sanitation management When designing future assistance, the selection of the reservoirs and other materials to be used should take into account local knowledge on atmospheric conditions (which is highly corrosive in locations like Majuro). project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/majuro-water-supply-and-sanitation-project
Health and Population Project | Health | 2002-12-13 | As for all the projects in the social sector in the Pacific islands, a 5-year implementationperiod is too short, particularly for the achievement of performance targets. Anupfront implementation period of 6 to 8 years appears more realistic. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Sector Related Issues: Education Sector Related Issues: Health and sanitation management Methodologies/Approaches: Targeting Due to the necessity of importing trainers for many of the skills required in the Pacific island developing member countries, outcomes depend to a large extent on the performance of the consultants. The selection of the consultants must be done carefully to ensure a project's success. The experience with consulting firms was particularly unsatisfactory in the case of this project. Strong monitoring to allow for early detection of poor performance and termination of the contracts, if required, must be built into both the contracting procedures and the project's management. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Project Management: Procurement Project Management: Project management Capacity Development: Capacity building Experience from this project, as well as from other health projects in other countries,shows that external sources of aid are often in too much of a hurry to press governments toagree on policy positions consistent with their own views and priorities, allowing too little time forthe necessary political process. Also, pressures to expand the agenda to include all of thefunders' favorite subjects can result in overly ambitious plans that do not necessarily reflect what islocally considered important to improve health outcomes. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Country Context: Prioritization Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework In common with other small island states, the Marshall Islands suffers from a lack ofsuitably trained staff who can substitute for colleagues attending training courses or programs.The amount of training planned to take place during the life of the project was probablyunrealistically high. In addition, other trainings continued taking place during implementation,placing an unsustainable burden on staff. A simple way of reducing the disruptive effect oftraining would be to establish manageable blocks of time, for example two periods of 6 to 8weeks each year, during which training can take place. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Human resources management The assistance provided to the Project Implementation Unit (PIU) for project implementation capacity proved of greatbenefit. However, it did not compensate for weaknesses in accounting. Where very limited accounting skills are available within the country, future projects must provide for additional capacities in this area. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial reporting Project Design: Project design Project Management: Project management Capacity Development: Capacity building The health education campaign has been less successful than anticipated because of the absence of a family health coordinator. The position has remained vacant in view of the inability to recruit a suitable candidate either locally or internationally. In general, as regards covenants requesting additional recruitments, they were in obvious conflict with the requirements of another ADB loan supporting the Public Sector Reform Program to decrease public service employment. Coherence has to be sought within ADB's programs and projects. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Design: Project design Project Management: Procurement Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Public sector reform The time budgeted for the consultants for the health financing and accountabilitysegment was obviously too short. Instead of one consultant for 8 person-months, twoconsultants for a total of 5 person-months were recruited. This did not allow enough time foreither of them to work along with local counterparts and implement any substantial change. Experience from other Pacific Developing Member Countries (PDMCs) has shown that a minimum of 1-2 years is required to obtainresults in this sector. However, most borrowers are reluctant to include long consultancies inprojects for economic reasons. Nevertheless, this concern must be balanced with the necessityof building long-term working relationships to obtain change and build capacity in smallcountries that lack skilled staff. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Corruption Finance & Financial Aspects: Financing Project Design: Project design Project Management: Consultants Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/health-and-population-project-0
Basic Education Development Project | Education | 2001-12-14 | All local training, especially that involving in-service teachers, needs to be continued and funded by the government after the conclusion of the project. Continued refresher courses are necessary to keep the teachers updated on the latest developments and changes in the curriculum. Similarly, continued government funding is necessary to provide adequate textbooks and materials to support curriculum implementation. Inadequate funding and lack of support will make it difficult to achieve any Basic Education Project (BEP) objectives. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Education As this was the first loan to the education sector, the executing agency had no prior experience with ADB procedures. The inception mission should have provided sufficient time and all necessary training and familiarization to the executing agency and the Project Implementation Unit (PIU). The Basic Education Project (BEP) design correctly called for the engagement of a consultant to establish the PIU, train the executing agency staff in ADB procedures, and prepare the implementation plan andschedules. The nonrecruitment of the advance action consultant contributed to the difficulties and delays in implementation. project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Project Management: Project supervision Capacity Development: Capacity building Sector Related Issues: Education In the design of educational projects in the Pacific, due consideration must be given to the lack of institutional capacity, weak management, and inadequate recurrent funding. Therefore, longer implementation periods should be considered. Implementation capacity needs to be assessed during appraisal. In this context, ADB should monitor education projects more closely, and missions should include an education sector specialist from time to time. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Human resources management Sector Related Issues: Education It is important that the executing agency and ADB be aware of ongoing and upcoming aid agencyactivities in the same sector to avoid duplication of efforts. All aid agency activities in a particular sector need to be coordinated to avoid difficult projects' working at cross purposes. project cycle stage: Appraisal Lesson Topics: Lack of provision for a qualified project accountant as part of the counterpart staffwas a major shortcoming of the project. Future project design should include aqualified project accountant in the Project Implementation Unit (PIU) funded under the loan. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Human resources management Providing curriculum development, training, and physical infrastructure can help,but are unlikely to produce significant improvements in student performance andachievement unless an appropriate overall educational environment isestablished. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Education Policy & Reform: Policy reforms/framework Since the education delivery system in the Republic of the Marshall Islands (RMI) is based on the US model, the consultants recruited should have been conversant with the US education system and should have had experience in the Pacific. Likewise, sequencing and overlap of consultants' engagement could have been better planned and coordinated. project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Project administration Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation The long lead times and lack of qualified local contractors in the Pacific must beconsidered in the design of civil works components and in the determination ofimplementation schedules. If local contractors and suppliers are to be used, moreextensive evaluation of capability must be carried out. Bid documents have to becarefully prepared and materials specifications clearly stated to avoidcomplications during civil works implementation. The flexibility to conductnegotiated bids should be given. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Procurement | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/basic-education-development-project