## Tonga
TONGA
REPORT NAME | SECTORS | DATE | LESSONS | REPORT TYPE | REPORT RATING | LINK
Integrated Urban Development Sector Project: Completion Report | Transport, Water and Other Urban Infrastructure and Services | 2015-09-18 | One of the significant lessons from the project is the positive impact of early fielding of PIA (project implementation assistance) consultants. During project preparation, the capacity of the executing agency, MOW (Ministry of Works), was assessed as insufficient, particularly for detailed design, construction supervision, and overall project planning, monitoring, and reporting. The project design therefore provided for PIA consultants to assist and support MOW. Recognizing the importance of the PIA team and its own unfamiliarity with ADB procedures for selecting consultants, MOW requested advance action and ADB's assistance for the recruitment. This is believed to have significantly reduced the risk of delays in recruiting the PIA consultants - which typically would result in slow project start-up and late implementation - and allowed for fielding of consultants within weeks of grant effectiveness. The project was implemented largely on time and on budget. project cycle stage: Design, Implementation Under a sector modality, core subprojects should only be included at project appraisal if detailed feasibility studies have shown them to be implementable. Under this grant project, a core subproject (Sopu drainage channel) had to be dropped in the implementation phase when detailed design and feasibility studies revealed huge and unfeasible land acquisition needs. project cycle stage: Design, Feasibility, Appraisal, Implementation ADB provided guidance and support throughout the project with frequent project review missions. Regular communication between MOW (Ministry of Works), PIA (project implementation assistance) consultants, and ADB allowed for continuous assessment of the direction toward attainment of the project's immediate objectives; review of institutional, administrative, organizational, technical, environmental, social, economic, and financial aspects of the project; assessment of the need to restructure or reformulate the project; and updates to the project's design and monitoring framework when necessary. Such regular tripartite interaction also allowed for good planning and implementation of additional, non-core subprojects to realize the benefits of savings from other project components, and also achieve completion of additional works within the fund utilization period. Although MOW went through a reform process during project implementation, close coordination between it and ADB prevented any major disruption to the project. project cycle stage: Appraisal, Implementation For projects where machinery and equipment are to be purchased from project funding, it should be ascertained during project design that the executing agency is making sufficient allocations to the operational budget in the year targeted for the procurement of the equipment, and the years to follow. Otherwise, the equipment is not used effectively for lack of operational budget in the first year. project cycle stage: Design, Implementation, Operation Allowing some NCB (national competitive bidding) packages in any project gives an opportunity to engage and test the ability of reputable local contractors. In this project it was noted that the local contractors for smaller NCB packages offered some very competitive rates and, with close supervision from the project team, were able to complete and deliver components in a timely manner. However, not every local contractor may be in the best position to handle larger ICB (international competitive bidding) contracts, as was seen in the poor performance displayed under an ICB contract won by a local contractor in joint venture with an overseas partner. The PMU (project management unit) acted swiftly to resolve the issues caused by the poor performance, and all activities under the component could be completed within the grant implementation period. project cycle stage: Implementation Proper engagement and communication with stakeholders is vital to ensure that the rationale and the objectives of the project are fully understood, and this helps during project implementation by speeding up important decisions. The good interaction between MOW (Ministry of Works), the PSC (project steering committee), and the PIA (project implementation assistance) consultants proved highly beneficial in completing this project on time. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/ton-integrated-urban-devt-sector-project-pcr
Strengthening Public Financial Management Program | Public Sector Management | 2014-08-01 | Single-tranche program. A single-tranche program operation can encourage up-front delivery of important reforms, particularly if launched as part of a programmatic, multiyear, policy reform effort where ongoing reforms are supported by several partners. This ensures reform sustainability. Limited but meaningful policy actions. In a single-tranche operation, those reforms selected for development-partner support should be few in number but large in potential impact. Technical assistance support should be available at program commencement. They should be clearly defined, widely owned, and have time-bound milestones that trigger financial support, either by ADB or by other partners supporting the government-led reform effort. A single, government-led policy matrix can enhance coordination and collaboration amongst development partners. The Joint Policy Reform Matrix has evolved into a highly consultative process around which development partners coordinate their budget support and technical assistance for reform. This process has helped the partners speak with one voice to the government and has created a situation in which line ministries actively compete to have reforms listed in the Joint Policy Reform Matrix. The Pacific Islands Forum Secretariat has identified the Joint Policy Reform Matrix as an international best practice in supporting government-led reform. Reforming large state-owned enterprises and complex regulatory reform. The impact of political sensitivities need to be factored into reform programs for major SOEs, particularly public utilities. Moreover, there may not be much legitimate appetite for foreign investment into distressed state-owned enterprises. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/tonga-strengthening-public-financial-management-program-pcr
Outer Islands Agriculture Development in Tonga (Loan 1412-TON) | Agriculture, Natural Resources, and Rural Development | 2006-07-31 | 1. As restructuring took much longer than anticipated, long-term resident consultants would have been more effective in maintaining progress than intermittent inputs. Since capacity constraints are significant in microstates, ADB must be sensitive to the need for ongoing support at times of significant change if it plans to encourage implementing agency restructuring. [Main text, paras. 61, 95] project cycle stage: Implementation Lesson Topics: Project Management: Consultants Capacity Development: Capacity assessment Capacity Development: Capacity building Policy & Reform: Reform 2. The scale of a technical assistance (TA) must recognize the size and strength of the recipient institution, and ensure general political support for the TA. Without such support, successful institutional change is impossible. The experience with the Tonga Trade TA exemplifies the difficulties of applying large-scale assistance to small and new organizations. Tonga Trade did not have the staff or financial resources to use the TA effectively, especially the training component, when it was provided. In addition, the continuing understaffing of Tonga Trade, as well as its subsequent changes in orientation, suggests that support for the organization s direction and role as specified in the RRP was not universal at higher levels of Government. [Main text, paras. 94, 96] project cycle stage: Design Appraisal Implementation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Ownership 3. When using commercially orientated organizations to achieve non-commercial objectives, ADB and the government should acknowledge possible conflicts and gear financial arrangements to realistic assessments of commercial outcomes. The telecommunications component was implemented efficiently, and has improved the target population s communications with the outside world. However, this phone system will be a cash drain to Tonga Telecommunications Corporation (TTC) for some time. Although TTC has contributed to the achievement of important development goals, its weak financial performance might conflict with its new corporate status. The new telephone system is connected only tenuously with the project objectives to increase agriculture productivity on the outer islands, reduce income disparities between households on different island groups, and stimulate agriculture exports. [Main text, paras. 73, 98] project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Executing/Implementing agencies Beneficiaries have appreciated the provision of agriculture access roads which have produced social and economic benefits. The provision of roads might be the most efficient way to stimulate economic growth in areas with agricultural land not served by roads. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Rural development The goal of privatizing within a short period was unrealistic. It did not reflect the limited size and strength of the agriculture export sector, which was expected to assume the major role in financing and directing the organization to be privatized. The expectations of the private sector far exceeded its ability to deliver. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Sector Related Issues: Private sector Policy & Reform: Privatization | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/outer-islands-agriculture-development-tonga-loan-1412-ton
Economic and Public Sector Reform Program |  | 2005-09-15 | Especially in situations where the government's capacity is poor, the design of the reform measures should be kept simple and extensive conditionalities should be avoided. The timeframe of the reform program should be realistic in balancing the government's need to rapidly establish a track record in relation to the external funding community and the broader public on the one hand, and the program's technical and political feasibility on the other. Moreover, providing sufficient resources for complementary institutionalchange and capacity building is indispensable. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Program Capacity Development: Capacity assessment Capacity Development: Capacity building Policy & Reform: Reform Measures that promise relatively rapid progress should be prioritized to facilitateeffective communication of success stories to the public. Effective communication of the reformprogram's rationale, objectives, and achievements is essential for maintaining public support,especially where an institutionalized participation mechanism does not exist. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Program Country Context: Prioritization Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Participatory approach The gap between domestic capabilities and skills requirements may be widened by theimportation of inappropriate techniques and technologies, so that reforms may not provedurable. At the same time, the involvement of strong, committed local consultants caneffectively help expand the government's capacities to manage and coordinate the reformprocess. project cycle stage: Implementation Lesson Topics: Modality: Program Project Management: Consultants Capacity Development: Capacity assessment Capacity Development: Capacity development Capacity Development: Technology/Technology transfer Policy & Reform: Reform The program has shown that strong government ownership of and commitment to aprogram with well-focused conditions can effectively support the reform process. By contrast,the program has also demonstrated the vulnerability of reform programs to the politicalenvironment, especially in conflict situations. This suggests that the level of commitment to aprogram loan is determined not only by the commitment of the government in power, but also byits ability to manage vested interests that wish to maintain the status quo (reform resistors) andthe overall political aspects of the reforms (for instance, displaced workers). Therefore, givensuch situations, carefully assessing and closely monitoring the political environment isimportant, including all supporting and resisting forces and the risks of a politically motivated interruption of the reform process, as well as assessing the capacity of the civil service and itsability to continue a reform program despite political upheavals. Extensive consultations amongpolitical factions and the broader public, including at the provincial level, are indispensable toensuring broadly based support for any reform program. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Ownership Country Context: Conflict/Post-conflict Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/economic-and-public-sector-reform-program