## Sri Lanka
SRI LANKA
REPORT NAME | SECTORS | DATE | LESSONS | REPORT TYPE | REPORT RATING | LINK
Support for Planning and Policy Formulation, Phase 1: Technical Assistance Completion Report | Public sector management | 2015-09-01 | The flexibility in design allowed ADB to accommodate a wide range of policy-related activities and respond quickly to government requests. However the outputs differed from what was anticipated during the design stage. A stronger commitment from government on the type of activities to support at design stage, at least for a larger component of funds, would have been helpful to design the performance indicators for the TA (technical assistance) more effectively. Some components, such as the training on PPPs (public-private partnerships) and the presentation on the PPP pipeline, should have had clearer paths for sustainability, either by linking to larger projects or further technical assistance. A tighter scope of the TA and streamlined set of players would have avoided much of the slippages in terms of time, however this must be balanced against the responsiveness factors noted above. The TA would also have benefited from closer involvement of topic experts, sector focal persons from ADB, industry representatives and experts from centers of excellence providing more practical orientation for technical aspects. Project cycle stage: Concept, Design | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/sri-support-for-planning-and-policy-formulation-phase1-tcr
Capacity Development for Non-Revenue Water Reduction: Technical Assistance Completion Report |  | 2015-08-01 | Updated and verified details of Colombo city water supply distribution network would have assisted the consultants in the redesign of the DMA (District Metered Area) with greater precision. A fully isolated and discrete supply zone with permanent boundaries should be established for the accurate measurement of baseline NRW (non-revenue water) figures and water balance assessments, through securing the hydraulic boundary and improving system input metering. The investment program has addressed these issues further. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/capacity-development-non-revenue-water-reduction-tcr
Colombo Port Efficiency and Expansion Project: Completion Report | Transport | 2015-07-29 | The project experienced substantial delays. These were mainly contributed by difficulties in securing sufficient public sector funding and approvals by various government agencies on the SHDP business plan and BOT concession agreement. However, ADB exercised flexibility in extending the TA loan, providing continued assistance to the government to implement the large-scale PPP project. Implementation delays was also attributed by the loan covenants on the ports sector reforms that could not be achieved as planned. Nevertheless, the spirit of these original loan covenants was fulfilled, which was beneficial in improving the operational efficiency at JCT. Although the ports regulator could not be established as planned, this was instead achieved by establishing an advisory committee to act as a grievance redress mechanism for such issues. For similar projects in the future, it may be beneficial to require reforms to be demonstrated as a project readiness criterion before project approval and implementation. Alternatively, if included in loan covenants, such institutional and regulatory reforms could be defined at a higher level - rather than as specific outputs - to allow the government more flexibility during implementation. project cycle stage: Feasibility, Appraisal, Implementation, Completion, Operation The decision to suspend the services of the MSC (main services consultant) from September 2005 to July 2006 with the consent of the MSC and approval from ADB was noteworthy. This approach not only resulted in financial savings, it ensured the success of the TA loan. Given that this is the first large-scale PPP project in the transport sector, the TA loan was effective in providing continuous support to government agencies, allowing them to carry out the necessary preparations for the PPP, including preparation of the procurement documents, bid evaluation, and BOT concession agreement negotiations. To minimize professional liability, the MSC was subsequently single-sourced to act as construction supervision consultants for the ensuing loan to implement the HIW works. project cycle stage: Appraisal, Implementation To mitigate the risk of lack of private sector participation, the selection of a private sector BOT concessionaire was a loan effectiveness condition for the ensuing loan. This ensured the selection of a credible private sector party to implement the BOT concession. project cycle stage: Appraisal The government had explored the possibility of setting up a special purpose vehicle to construct the breakwater using private sector financing, but this was found to be problematic for the following reasons: (i) the breakwater would not generate revenue, (ii) the construction skills required for building breakwaters and terminals are very different, (iii) revenues would only be generated from the operations of the container terminal, and (iv) it would be difficult to attract private sector investment for the breakwater. Hence the PPP landlord model was used, where SLPA (Sri Lanka Ports Authority) would be the landlord, and the breakwater implemented as a public sector component. project cycle stage: Feasibility, Implementation Although the completion of the TA loan was delayed by 6 years, the TA loan is still considered a success given its significant contribution in facilitating the development of the first large-scale PPP transport infrastructure project in Sri Lanka. The extensions in completion time allowed adjustments to be made to ensure successful of implementation. project cycle stage: Implementation, Completion, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/sri-colombo-port-efficiency-and-expansion-project-pcr
Colombo Port Expansion Project: Completion Report | Transport | 2015-07-27 | Project structuring. A key consideration was to draw an optimal balance of public and private sector participation. The government applied a PPP landlord port model whereby the public sector would deliver the basic breakwater infrastructure and private sector deliver two of the three container terminal facilities to be accommodated by the new breakwater. This approach has not only brought about significant efficiencies in delivery, it also resulted in tremendous financial leverage. project cycle stage: Design, Implementation Procurement. The project is very large scale and complex in nature, so it was important to bring in quality consultants and contractors. Continuation of services from the main design consultants to provide construction supervision not only reduced the time for procurement but also resulted in minimizing liability risks and disclaimers of responsibility. project cycle stage: Design Civil works packaging. Since the works were interrelated, the HIW (harbor infrastructure works) was packaged as a single contract. The large size of the contract attracted good quality and experienced contractors. project cycle stage: Design, Feasibility Loan effectiveness. Realization of the full project benefits was contingent upon the public and private sector components being well coordinated and implemented as planned. Implementation of the private sector component - and especially selection of the private concessionaire for the first container terminal - initially presented a major risk. This was mitigated by linking the progress of selecting a successful bidder for private concessionaire with implementation of the breakwater infrastructure (public sector component) as a condition of loan effectiveness. Although the loan effectiveness condition had to be amended to accommodate the commencement of breakwater construction and allow more time for selecting the private concessionaire, the condition ensured risk mitigation. project cycle stage: Appraisal, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/colombo-port-expansion-project-pcr
Southern Transport Development Project | Transport | 2014-08-01 | The success of the project can be attributed to a combination of solid government ownership and strategic vision; the long-term partnership between the government, ADB, and a number of development partners; the high level of advocacy of civil society groups; and a series of well-targeted technical assistance projects that bridged existing knowledge gaps. The Southern Transport Development Project is an invaluable source of lessons for mega road project planning and implementation. Planning and preparing a mega greenfield road project requires adequate allocation of resources and time to allow for timely and efficient commencement of civil works. The project implementation essentially focused on the concept finalization and detailed engineering in the first 4 years. For a country with no prior experience of expressway development, direct support from ADB on project conceptualization and detailed formulation is necessary to ensure project quality and final success. Even with such support, the finalization of engineering design took twice as much time as planned at project appraisal. ADB's lending instruments are now more diversified than they were in 1999. A recommended model is to use a technical assistance loan or a project design advance to assist the government in finalizing the engineering before the project loan proposal is submitted to the ADB Board. The impact of the lead time between the initial conceptualization and the commencement of services can be significant enough to change the feasibility of project alternatives and may result in a different preference. It was already envisaged in 1999 that the Southern Expressway would ultimately be a six-lane, high-capacity, limited-access express highway, and a stage-wise construction approach was adopted. However, the fast social and economic development in the southern region demanded a high-capacity highway earlier than the projection. The government, cofinanciers and ADB demonstrated great patience and flexibility to allow the further development of project concept during the early stage of project implementation, and finally ensured the relevance of project outputs. Managing the public relationship is an important part of successful project management. Even with the best ever compensation package in Sri Lanka, strong public protests were faced at the beginning of the project with regard to the land acquisition and compensation process. A proper project communication plan was not prepared during the project formulation and early implementation stage. To manage the public relationship, the Road Development Authority established a project communication plan in 2005 and ran a number of public awareness campaigns. Finally, the Road Development Authority gained strong support from stakeholders. Lastly, the implementation of mega projects can provide good opportunities for improving safeguard systems. Under the Southern Transport Development Project resettlement implementation plan, the mechanism of land acquisition and resettlement committee system was introduced to Sri Lanka for the first time. These committees were very popular among affected people as they played a very constructive role in redressing grievances. This mechanism managed a large number of cases which would otherwise have resulted in legal procedures, and thus significantly reduced implementation delays. The government also adopted the land acquisition and resettlement committee system in others sectors. It was also learned that the grievance redress system needed to be established as early as possible and stakeholders made aware of it. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/southern-transport-development-project-pcr
North East Community Restoration and Development Project | Agriculture, Natural Resources, and Rural Development, Education, Finance, Health, Industry and Trade, Water and other urban infrastructure and services | 2013-11-11 | 1. The North East Community Restoration and Development implementation structure, including the delegation of responsibility to a provincial project management unit and the inclusion of all stakeholders in the provincial project coordination committee subproject selection process, was effective in implementing restoration activities. It provided a model for coordination between central, provincial, district, divisional, and local government, and encouraged cooperation with other agencies and minimized duplication of agencies' work. project cycle stage: Lesson Topics: 2. Implementation is difficult in the fluid security conditions of conflicts and their aftermath. However, staff members were motivated by the evident need for their services, as well as by pressure from both sides in the conflict to address basic infrastructure in all areas. project cycle stage: Lesson Topics: 3. Most contracts were relatively small and within the competence levels of local contractors, especially relevant in the difficult conditions for access and supply that applied during and after the conflicts. Use of local contractors, instead of outside companies, strengthened local ownership and avoided aggravating community and ethnic tensions. project cycle stage: Lesson Topics: 4. Baseline data are important. During conflicts, data change: infrastructure is destroyed and people are displaced. Monitoring surveys are difficult to conduct because of restricted access. The project management unit failed to expand the management information system to assess subproject impacts, the absence of which made postproject evaluation difficult. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-east-community-restoration-and-development-project-pcr
Small and Medium Enterprise Regional Development Project | Industry and Trade | 2013-01-08 | 1. ADB's Financial Sector Operational Plan supports the market-based pricing approach and stipulates that projects involving credit lines need to be designed to strengthen the capacity of financial institutions intermediating the credits and such a project should comply with the Operations Manual (D6) to avoid undermining the commercial incentive for the participating financial institutions to competitively mobilize finances and distorting the credit and interbank market. As such, it is the norm to adopt the average weighted deposit rate (AWDR) as a local anchor for determining subloan interest rates for ADB financial intermediary loans. Adopting the AWDR is considered generally consistent with best practices. However, adopting a local interest rate anchor is not widely practiced by other development partners, which in many cases adopt fixed interest rates, often lower than prevailing market rates. There may be a need to promote a standard local anchor for interest rates, as it will bring assistance from development partners into conformity with the local environment and avoid market distortions. Project formulation missions need to be mindful of consistency with other projects with financial intermediary loans. If a significant discrepancy in the interest rate exists with projects funded by other development partners, there will likely be implications for disbursement. 2. Small and medium enterprises (SMEs) generally suffer capacity constraints and lack skills in business development, marketing, planning, human resource management, and other business skills, which makes them less bankable. Had it been done, the capacity development technical assistance would have provided necessary skills training and improved the capacity of borrowing SMEs. Sri Lanka's Credit Information Bureau also covers SMEs. Participating commercial bank (PCBs) reported that they accessed the bureau's credit information report to appraise the SME subloans to be financed under the project. Despite the existence of fairly adequate institutions for SME risk assessment, PCBs emphasized the need for stronger support institutions, including training institutions for SMEs, and reliable funding sources for SMEs. 3. Delay in ADB's internal business processes, including the disbursement of withdrawal applications, often frustrates smooth implementation progress. Timely disbursement is critical, especially for financial intermediation loans, because financial institutions set the subloan interest rate based on the relending rate from the government and approve subloans to final borrowers only after they receive refinance from the government. Project administration requires closer attention to efficient and timely disbursement and other internal business processes. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/small-and-medium-enterprise-regional-development-project-pcr
Fiscal Management Reform Program | Public sector management | 2012-11-01 | A sequence to reforms. A key consideration in sequencing is that legislative and regulatory reforms require changes in the capacity of institutions (policy and rules), organizations charged with implementation, and the competencies of responsible government officers to change their management practices. This cascade of legislation-institutions-organizations-people provides a strategic sequence for reforms. However, in practice this is not a linear sequence. Rather, people (officials and stakeholders) are involved from the outset of the reform process. As policy reforms are an iterative, negotiated process, attention needs to be given to developing and maintaining a broad consensus for reform, as this is one of the most difficult and important challenges in sustaining change management processes. It is important to note that developing and maintaining a broad consensus for reform was one of the hallmarks of the Fiscal Management Reform Program (FMRP) that ensured unwavering government commitment to the programï¿½s strong legislative and regulatory reform content. Capacity constraints and project complexity. In addition to appropriate reform sequencing, ambitious and complex programs and projects are more likely to succeed if significant attention is given to building the capability and ownership of a broad range of stakeholders. As a sector development program, the FMRP successfully tackled a wide range of issues within a short time frame, while also contributing significantly to human development in several key implementation agencies. Advisory services to government under the project were also effective in keeping the program on track, especially in technical areas where previous experience was limited. Developing ï¿½softï¿½ capacities. Institutionalizing change management practices among those charged with implementing reformsï¿½such as the efforts undertaken in the program to provide staff with technical skills to implement systems and procedures at the Ministry of Finance and Planning (MOFP) and the key revenue departmentsï¿½requires upgrading of technical and change management competency. It is necessary to enable government to sustain capacity development programs beyond the life of a program (for example, by providing training experts, particularly to develop soft capacities). | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/fiscal-management-reform-program-pcr
Tsunami-Affected Areas Rebuilding Project | Finance, Public sector management, Transport, Water and other urban infrastructure and services | 2012-11-01 | Reestablishing the identity papers and legal documentation of disaster victims is an essential and urgent necessity, and ADB's support to the government's program improved its delivery and effectiveness by ensuring sufficient funds. As highlighted in the performance audit, the mobile clinics facilitated legal documentation and proved to be an efficient mechanism for emergency situations. This can be adopted as a good practice for future interventions. For components B, E, and H, substantial time was required to mobilize community- based organizations and implementing-partner nongovernment organizations (NGOs) to reach hundreds of villages to be served under major disaster reconstruction programs. This resulted in delays at the start of implementing activities under these components, and support from NGOs was required. To avoid underutilization of newly built facilities, equipment, staff, and operations budgets should be identified and allocated by the responsible government agencies for activities involving rehabilitation and expansion of buildings and hospitals. The success of the women's rural development societies (WRDSs) involved in components B and H, and earlier in the North East Community Restoration and Development Project (NECORD) and NECCDEP (North East Coastal Community Development Project) projects, demonstrated that community-based organizations contribute to a sustainable mechanism for improving economic activities at the local community level while concurrently achieving aspects of the gender action plan by empowering women through increased income, confidence, and quality of life. Implementing ADB's requirement to incorporate strengthened building standards into the design of buildings and structures was not possible. It took the government 3 years to develop the revised standards, by which time most structures had been designed and many constructed. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/tsunami-affected-areas-rebuilding-project-pcr
Conflict-Affected Area Rehabilitation Project: Project Completion Report | Agriculture, natural resources and rural development, Education, Energy, Health, Public sector management, Transport | 2012-10-01 | At appraisal it was estimated that the project would be implemented over 4 years and be completed by December 2007. Due to the conflict, works could not be undertaken in the time envisaged, thus Loan 2043 was extended four times, to 31 March 2011, and Loan 2044 twice, to 31 December 2010. ADB needs to allow adequate time for planning, design, tendering, and construction of projects where a conflict is involved, as the incidence of security issues severely hampered the implementation of the project. Loan extensions cause extra work for the implementing agencies and ADB staff, and tend to discourage government agencies as they feel that their project is always behind schedule. In future, for similar projects under emergency or conflict situations, ADB needs to ensure that timetables are realistic. The appraisal estimate for component A was that 500 km of roads could be rehabilitated with double-bitumen surface treatment. As a result of the government's decision on national highways, the road surface was changed from double bitumen to asphalt concrete. This led to numerous contract variations and extensions. Therefore, rehabilitation of 500 km was reduced to 198 km. As for component B (power and electrification), it was fortunate that the Government of Norway agreed to cofinance it and that Japan Bank for International Cooperation (JBIC) agreed to undertake the Vavuniya-Kilinochchi transmission line, because otherwise the project would have had difficulty in meeting its objectives. In a major change in scope in 2006, funds released from component B thanks to the external assistance from Norway and JBIC were reallocated to component A. However, the scope of component A was reduced from 500 km to 300 km due to cost increases. Eventually, only 198 km of road could be completed. ADB needs to ensure that financial details, including cofinancing and assistance from other donors, are already in place at appraisal, as otherwise the possibility of not achieving project objectives becomes too high. The executing agencies did not always submit their project completion reports on time, and not always in the format requested by ADB. The reports also did not contain sufficient information on government counterpart funds, which forced the project completion review mission (PCRM) to spend considerable time on obtaining the data from each executing agency. In the case of Ceylon Electricity Board (CEB), this proved extremely difficult, as the agency did not have adequate records dating back to the start of the project. This has been a common problem in several previous projects, where the executing agencies did not seem to be aware of how much was spent from government funds to the level of detail necessary to undertake a project completion report. ADB needs to ensure that the executing agencies for ADB projects collect and supply all data required in the project completion report; otherwise a PCRM spends too much time chasing such information. In a project that involves several executing and implementing agencies, coordination between all agencies is of the utmost importance. While the national and provincial project coordinating committees (PCCs) did all that was possible to implement the project successfully, a more central unit for coordinating project activities would have improved implementation. The establishment of a dedicated project management unit (PMU) to facilitate the implementation and coordination with different government agencies should be considered for future projects of a similar nature, especially when they involve multiple sectors, multiple layers of governments, vast geographical areas, and other development partners. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/conflict-affected-area-rehabilitation-project-pcr
Secondary Education Modernization Project II | Education | 2012-02-07 | 1. Investment in information and communication technology (ICT) infrastructure requires additional resources and training to ensure that the facilities are adequately and appropriately utilized and maintained. These include (i) training for the school principal and ICT teacher on the effective use of ICT, (ii) a robust mechanism for providing funding to cover operating expenses such as electricity bills and internet access, (iii) a mechanism that would provide resources to schools (through provincial institutions) to maintain and update hardware and software as needed, (iv) improvement of the curriculum to integrate computer-assisted learning into the teaching of different subjects, and (v) parental education and involvement in encouraging students to enroll in ICT options at O- and A-level. The school visits conducted as part of the project completion report mission confirmed that the resources provided under the project are available in schools but are not being fully utilized, except where a particularly motivated school principal or ICT teacher is involved. Further, ICT infrastructure provided under various initiatives over the years (regardless of financing source) has become obsolete, and even when the hardware is still in working condition, the software has been rendered ineffective by viruses. [Main text, para. 61] project cycle stage: Lesson Topics: 2. Stronger monitoring and support from zonal facilitators is essential for ensuring effective use of interventions made in quality of learning. Although the project developed several good training modules on Program for School Improvement, school-based assessment, teaching learning methodologies and teaching learning resource development and use, the effective use of these modules cannot be sustained unless supported in schools and classrooms by a committed zonal facilitator. This individual is required to visit each school on a regular basis (at least once per month) to ensure that teachers and principals are supported in adopting new management and teaching techniques. With only four facilitators per zone, covering over 100 schools and many subjects in each, coverage is inadequate. It is important to ensure that a sufficient number of zonal facilitators are made available. Strengthening their role within the system and monitoring their performance to ensure delivery will be a key enabler for implementing future projects in school education. [Main text, para. 62] project cycle stage: Lesson Topics: 3. A general lesson learnt is that the sustainability of initiatives beyond the lifetime of the project rests heavily on the level of reinforcement provided by the Ministry of Education (MOE), in the form of circulars, training, and regular follow up by provincial and zonal staff. For example, initiatives such as school-based assessment and Program for School Improvement, which were supported and reinforced by the MOE (e.g. through circulars) have had better success than initiatives such as teaching learning methodologies and teaching learning resource development and useU, which did not enjoy the same level of support. Hence, in order for future projects and programs to be successful, ADB would have to closely align these with the government's Education Sector Development Framework and Program to ensure greater institutional ownership and support. [Main text, para. 63] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-education-modernization-project-ii-pcr
North East Coastal Community Development Project | Agriculture, Natural Resources, and Rural Development | 2012-01-08 | 1. A strong project management unit with qualified staff under a competent project director who remained throughout the project enabled implementation despite disruption from a tsunami and renewed conflict. [Main text, para. 63] project cycle stage: Lesson Topics: 2. The Gender Action Plan (GAP) provided a framework for gender-balanced activities but a project management unit gender specialist should have been included in the project design to manage the plan. Implementing the GAP separately through the rural development societies and the women's rural development societies gave women space for involvement but reduced opportunities for fully gender-balanced operations. [Main text, para. 64] project cycle stage: Lesson Topics: 3. Providing initial training for the government field staff, which had been weakened by the civil conflict, would have helped implementation. The capacities of the implementing partner nongovernment organizations were overestimated at the design stage and the project management unit spent a lot of time on guidance and training. [Main text, para. 65] project cycle stage: Lesson Topics: 4. No legal precedents for the special area management planning safeguards existed and no single agency was empowered to handle legal aspects of coastal resource planning. Implementation of coastal planning needed better interagency coordination and the Coast Conservation Department should have been included in the design as the implementing agency for component C to give a greater sense of ownership. [Main text, para. 66] project cycle stage: Lesson Topics: 5. Channeling credit through community organizations rather than individuals could reduce defaults through peer group pressure and lower administration costs. Credit lending terms should be consistent with the prevailing local microfinance conditions. [Main text, para. 67] project cycle stage: Lesson Topics: 6. Inclusion of an innovative process monitoring system enabled the correction of processes during implementation. This was especially important given the volatile and uncertain security conditions. Process monitoring helped in assessing the work of nongovernment organizations and modifying village planning, livelihood enterprise development services, and microfinance processes. [Main text, para. 68] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-east-coastal-community-development-project-pcr
Rural Finance Sector Development Program | Finance | 2012-01-05 | 1. Overly ambitious and complex projects are less likely to be successful. The Program objectives had a strong rationale and the design was technically sound. However, in view of the weak implementation capacity of the executing agency and the implementing agencies, the Program would likely have yielded better results with a more focused and prioritized set of policy actions and project activities. Moreover, the Rural Financial Sector Development Program was approved only three months prior to the April 2004 parliamentary election. While the election outcome and subsequent policy direction could not have been fully anticipated at the time, there was sufficient uncertainty regarding continued political support to warrant reconsideration of the timing of Board consideration. project cycle stage: Lesson Topics: 2. The program loan tranches were front-loaded, with $35 million of the total program amount of $50 million programmed for the first two tranches. The first two tranches were largely preparatory measures and intermediate steps. Had the program been back-loaded with relatively larger amounts allocated to the third and fourth tranches, it is possible that the authorities would have been more inclined to implement some of the more difficult reform measures. project cycle stage: Lesson Topics: 3. Timely project completion report (PCR) is important for maintaining policy dialogue and assessing the need for follow-up actions and future assistance. Project Administration Instruction No. 6.07A recommends that the PCR be prepared between 1-2 years after project completion. In the case of Rural Financial Sector Development Program (RFSDP) program loan, the second (and final) tranche was released in February 2006. The bulk of activities under Project 1 and Project 2 were completed in 2008. Given that considerable time has lapsed since Program implementation ended, and significant staff turnover in the executing agency and implementing agencies since, the authorities were not able to contribute meaningfully to Program assessment. PCR preparation would have benefited from the insights of officials directly involved in program implementation. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/rural-finance-sector-development-program-7
Sri Lanka: Road Sector Development Project (1986-SRI[SF]) | Transport | 2011-12-16 | 1. A sound and scientific methodology on road project selection (including expected social development impact as a criterion) reduces the exposure of the selection process to political influences. Further, having the necessary data (traffic counts and road condition) facilitates arriving at sound decision during the road project selection process. Evaluation noted the mechanics of the final screening and decision making of the implementing agency were not clear, nor was the relevance of the selected provincial roads to the objectives of the project. Selection of some road projects appeared to have been based more on political rather than economic and social considerations. [Main text, paras. 2,22,47-49,82] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Transport planning 2. More careful monitoring and supervision would have been required to review the progress of the program, to understand its key issues, and to propose alternative approaches where necessary. The design of the Reform Program with its numerous components was complex, so efforts on monitoring and guidance should have been made during project implementation. This was not done by ADB. Many targets of the Reform Program were not achieved, and neither ADB nor the implementing agencies reviewed the issues that prevented achievement. Almost all memoranda of understanding between the government and ADB, as well as monthly progress reports prepared by the consultants during project implementation, were not comprehensive and did not cover all targets of the Reform Program. Hence, the project completion reports of ADB, the Road Development Authority and the Ministry of Local Government and Provincial Councils (MLGPC) could not evaluate all the activities of the Reform Program. The main consultant was based in Colombo at the MLGPC and as such did not have much direct interaction with the four provincial road administrations, resulting in less effective monitoring of progress. With careful monitoring and attention, the number of successful targets and the quality of capacity building could have been greater and activities of the Reform Program could have been more user-oriented. [Main text, paras. 55,86] project cycle stage: Implementation, Completion Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project supervision Sector Related Issues: Roading Sector Related Issues: Transport planning Policy & Reform: Reform 3. The requirements, key issues, terms of reference, selection criteria including qualification of consultants, implementation structure, and understanding and ownership of the technical assistance (TA) by the implementing agencies should have been described carefully according to the requirements of technical assistance. If poor performance was observed, prompt action would have been required to minimize the loss of time and funds. The consultancy services for the detailed engineering design of national highways and TA 4075-SRI were incomplete due to poor performance by the consultants and did not provide significant outputs. The Road Development Authority also should have developed a well-maintained performance recording system. [Main text, paras. 3,19,76,87] project cycle stage: Implementation Lesson Topics: Project Management: Consultants Sector Related Issues: Roading Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/sri-lanka-road-sector-development-project-1986-srisf
Aquatic Resource Development and Quality Improvement Project | Agriculture, natural resources and rural development, Finance | 2011-12-01 | A single sector approach aids simplicity and a project's effectiveness. The strong project management office (PMO) with qualified staff and single project director effectively progressed the project, even if subsidiary implementing agencies lacked capacity. Key elements were seconding the implementing agency's staff, absorbing personnel contracted for the project to the PMO, and detaching the PMO from the executing agency's offices. For this project, engaging and training in-house or contracted staff of the implementing agency for social mobilization was more sustainable than recruiting outside nongovernment organizations (NGOs). Longer lead times (up to 2 years) should be allowed for the complex legal and administrative processes required to amend Acts of Parliament. Similarly, completing major civil works within 1-1/2 years is unrealistic. Regular review and updating of the DMF would have aided monitoring and evaluation. A design and monitoring framework (DMF) needs to follow ADB's standard format yet be dynamic. Credit line design needs to be based on studies of market demand. Given a profitable and properly regulated enterprise like culture-based fisheries, community-based organizations (CBOs) can be developed into sustainable, profitable businesses. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/aquatic-resource-development-and-quality-improvement-project
Distance Education Modernization Project | Education | 2011-12-01 | The project involved the establishment of an entirely new platform of learning, with investments in hardware and software and including creation of partnerships with institutions that were to develop their course content into online distance learning format. This constituted a major step toward a new concept of learning. There is a risk that the system will eventually collapse unless it is put on a sound business and strategic footing in the near future. In addition to the risk of dilapidation of equipment (which for now is still relevant and state-of-the- art), staff capacity that was sourced, developed, and placed to keep National Online Distance Education Service (NODES) and network access centers (NACs) operational risks being eroded as the highly skilled people begin to find alternative work in the market. One major lesson is that longer-term support could have been built into project design to enable more time for preparing a sustainability plan with concrete milestones, including adequate transition arrangements followed by approval of an institutional framework for the successor organization. Another lesson arises from the novelty and innovation of the projectï¿½a higher priority should have been placed on social marketing and awareness raising among potential partner institutions and students, to ensure broad-based demand and a strong supply of market- oriented courses. There is great potential for self-sustainability in this model if its management is outsourced or it is transformed into a corporate entity, but inclusion of social marketing will be key to its success. Also, mobilization of the private sector requires effective communication and a credible monitoring mechanism to ensure that matching grants are used effectively. An important lesson regards the nature of the courses that were offered and if they were the most appropriate ones for an online distance-learning platform. While the project was designed to create access to postsecondary (degree-level) programs for those A-level achievers who would not have an opportunity to enroll in traditional university programs, it may not have been suitable for students newly transitioning from secondary to tertiary education for whom distance learning was less desirable or appropriate, given the strong preference for more traditional modes of post-secondary education. Such a system may be of more relevance and therefore better used if it focuses on non-degree courses to supplement formal education, especially courses that help the employed broaden their skills or the unemployed making themselves more employable. This has deep implications for the future of NODES, as the ?new management? or policymakers consider how they want to develop and use it. Finally, an important institutional lesson arises from the need for better planning and coordination between all ministries and agencies that have a potential stake in a project's outputs. In the case of this project, NODES can be of relevance and use to the training and education programs offered and governed by various ministries and agenciesï¿½e.g., Ministry of Education, Vocational Training Authority. Already, several of these courses relate to vocational areas (hotel management; computer studies and/or software development; food and beverages; etc.) and their thrust is aligned with the government's priority goal of developing information technology (IT) and tourism as focus areas for investment in technical education and vocational training, supported by public-private partnership and an information and communications technology (ICT) platformï¿½all of which NODES offers. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/distance-education-modernization-project
Sri Lanka: Forest Resources Management Sector Project | Agriculture, Natural Resources, and Rural Development | 2011-12-01 | 1. Projects, which include enactment of legislations, should be provided ample implementation timeframes. The difficulty of enacting legislation in support of a project activity and within the timeframe of a project is often underestimated. The estimated implementation time of the Forest Resources Management Sector Project in Sri Lanka project should have considered possible difficulties faced by line agencies in pushing for the component legislation through the national parliament. [Main text, paras. 21, 24] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/sri-lanka-forest-resources-management-sector-project
Financial Markets Program for Private Sector Development | Finance | 2011-10-01 | The timing of a program is crucial to the effectiveness of its outputs and outcomes. Difficulties to obtain approvals of the numerous legislative actions in this program could be traced to the change of government (and the fact that the government did not hold a majority of seats in the Parliament). The program's achievements of performance targets benefited from the eventual improvement of the political and economic landscape from 2009 onwards. Therefore, to ensure the effective and pragmatic design of similar programs in the future, it is imperative that ADB be cognizant of potential changes in the country's political environment as well as factor in important variables (such as the internal conflict in this case) that could impact program implementation. Furthermore, it is prudent to minimize the number of legislative actions to ensure effective program implementation. The program had an excessive number of legislative actions that contributed to program implementation delays. In addition, a salient feature of this program is the transparent and effective approach to monitoring the restructuring of a bank. This feature can be applied to other similar entities. The key performance indicators that were embedded in People's Bank Strategic Plan 2009-2014 were rigorously reviewed on a biannual basis to ensure that the bank restructuring was on track. These key performance indicators were comprehensive and broad-based and encompassed major aspects of operational activities such as capacity adequacy, asset quality, management, earning, and liquidity. Finally, a key success of a reform program is the relevant design that incentivizes strong government ownership on institutional strengthening, in this case, by improving bank's operational management: supporting profitable business lines such as pawning, tightening credit reviews and recoveries to reduce nonperforming loans (NPL), and controlling overhead costs such as reducing headcounts to improve performance on a per employee basis. The fact that People's Bank continued restructuring and committed itself to performance indicators to improve bank operations over and beyond what was agreed to under the program underscored the success and sustainability of the ADB support. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/financial-markets-program-private-sector-development
Asian Development Bank's Assistance for Low-Income Housing Finance in Sri Lanka | Finance, Water and Other Urban Infrastructure and Services | 2011-08-31 | 1. Targeting poorer households could make the project welfare impacts more robust requiring flexible loan procedures and requirements. The project targeted households with incomes below the 55th income percentile (low income). As households were required to meet conventional standards of creditworthiness, including having loan collateral, the project was in effect not available to the very poor. Hence, most project beneficiaries were near middle-income households, whose labor force participation, school enrollment, and health conditions were already high. [Main text, paras. 60-63,66,68,72,76] project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Methodologies/Approaches: Targeting 2. For similar projects in the future, the design team can encourage flexibility in loan terms. The Impact Evaluation Study showed that in several cases, the impacts were larger and more significant in the case of longer-term loans. This supports the hypothesis that longer loan terms, with lighter repayment burdens, could increase household welfare. [Main text, paras. 53,60,78] project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/asian-development-banks-assistance-low-income-housing-finance-sri-lanka
Sri Lanka: Country Partnership Strategy 2009-2011 - Final Review Validation |  | 2011-08-28 | 1. The political economy of Sri Lanka required a more comprehensive understanding of the implementation time frame and greater appreciation of the need to inject policy reforms on a phased basis. The expectations of some of the interventions (e.g., restructuring of institutions, Aquatic Resources Development and Quality Improvement Project, Secondary Towns and Rural Community-based Water Supply and Sanitation Project, and fiscal and tariff reforms) were somewhat misplaced, not having been carefully planned in a phased manner with more realistic time frames to suit local conditions. Further, the design of some projects (e.g., Small and Medium Enterprises Regional Development Project and Forest Resources Management Sector Project) did not provide for strategic adaptations in respect of interventions such as credit components. project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Design: Project design Country Context: political economy factors Policy & Reform: Policy reforms/framework 2. Policy dialogue in the context of emerging economies beset with domestic complications is a long and arduous process that requires persistence, follow-up, and commitment to the achievement of end results. Policy-based lending encountered many constraints such as inadequate stakeholder partnership, political and trade union opposition, and absence of a comprehensive approach to policy dialogue by ADB, which would have necessitated a phased and programmatic approach to discussion of policy and sector reforms. project cycle stage: Implementation Lesson Topics: Modality: Policy-based lending Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Policy dialogue 3. Capacity development is a long and sustained undertaking that requires ownership, understanding, and support from within the country and should emerge in response to demand to develop and strengthen institutions for better delivery of services. Institutional capacity limitations were known and remedial measures were adopted through accompanying and stand-alone advisory TA to strengthen capacity. A total of 29 capacity development TA operations were approved during this period, but field visits suggested that more preparatory work should have been done before TA operations were approved, including consultations with stakeholders. The Umbrella Capacity Development Fund initiative for which TA was approved did not get off the ground despite the resident mission's interest and efforts. project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Capacity development Capacity Development: Ownership Other: Resident Mission 4. To ensure that outputs and outcomes can be continued, sufficient funding for maintenance, including policy level commitment for enhanced funding support, is crucial. This becomes all the more pronounced when civil conflict endangers people's participation and involvement. Insufficient funding for maintenance, such as in the case of the Road Maintenance Trust Fund, Ceylon Electricity Board, and National Water Supply and Drainage Board, and multiple agencies handling sector functions, such as in the transport and information and communication technology sector, led to lack of consistency in the approach to operation and maintenance. project cycle stage: Implementation Lesson Topics: | Country Partnership Strategy Final Review |  | http://www.adb.org/documents/sri-lanka-country-partnership-strategy-2009-2011-final-review-validation
Coastal Resource Management Project | Agriculture, natural resources and rural development | 2010-12-01 | One key lesson is the need to involve communities in project activities from inception to completion. Law enforcement alone cannot safeguard the environment. To ensure communities benefit, their involvement is important even in large infrastructure development and rehabilitation projects. Social awareness programs are important throughout project implementation and beyond to encourage community ownership of their resources. Even at the institutional level, a sense of ownership has to be developed early in the project. This can prevent delays during implementation and ensure continued operation and maintenance. Communication among stakeholders should be strengthened to convey correct messages and prevent misunderstandings. The project trained coastal communities in alternative livelihoods to prevent their over- exploitation of coastal resources. To ensure the sustainability of the alternative livelihoods, they should link to markets to generate income. If not, communities may return to their traditional activities. Delays in implementation ensue when components are clustered in a project. Further, clustering discourages ownership of project outputs. Combining harbor development with coastal conservation delayed project implementation considerably because the activities are not complementary. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/coastal-resource-management-project-pcr
Plantation Development Project | Agriculture, natural resources and rural development | 2010-12-01 | First, delays were avoidable if the project preparatory technical assistance (PPTA) financing percentages had been retained. During the loan appraisal and negotiation phase, the recommended financing percentages of the PPTA of 70% ADB-30% regional plantation company (RPC) for social amenities and 90% ADB-10% RPC for the social development programs were adjusted to 50% ADB-50% RPC, resulting in RPCs not participating. Given the weak balance sheets and the lack of profitability, the desire for greater ownership through increased financial contribution was inconsistent. The subsequent increase in ADB financing overcame the issues, and implementation proceeded rapidly over 3 years. Second, there was unnecessary design complexity and add-ons. The core project components relating to investment and social objectives were coherent and achievable. The inclusion of additional inputs for the development of Tea Association of Sri Lanka (TASL), marketing alliances, and demand-based public research were not client-driven nor demanded, lacked appreciation of the commercial and proprietary rights attached to market relationships, and research findings as contributing factors for achieving competitive advantage. Further, there were insufficient financial and governance benefits to merit insistence on an international fund manager when the size of the fund was extremely limited and the duration of funds available for investment short. In addition, project outcome and impact indicators were poorly defined in terms of sustainability and what this represented. There was inadequate consideration of sector financial risks, including wage inflation, and political risks relating to price escalation in the sector. A major cost item, the inflation adjustment formula for RPC leases, was not reflected in the institutional nor design framework. The use of a credit line was an effective implementation modality. Significant advantages from longer loan periods, grace periods, and fixed interest rates during a period of high and rising interest rates and markedly lower capital availability supplied a definite demand. The use of fixed interest rates during the current period of declining interest rates has, however, increased the requests for early repayment. THe Development Finance Corporation of Ceylon (DFCC), the Ministry of Finance, and Ministry of Plantation Industries (MPI) should consider the option of interest rate adjustment to outstanding loans. Similarly, the apex body agreement did not adequately cover for the recycling of early repayments, and, as such, interest earned and loan repayments can be retained by the apex body. Participating financial institutions (PFIs) are required to pass early repayments back to the apex body. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/plantation-development-project
Protected Area Management and Wildlife Conservation Project | Agriculture, natural resources and rural development | 2010-11-01 | Reference to international nongovernment organizations (NGOs) and public-private partnerships in the report and recommendation of the president (RRP) provoked local wildlife activists and politicians, resulting in project delays. This could have been avoided by wider pre-project public relations efforts. Launching a complex project through the Department of Wildlife Conservation (DWC), a small organization faced with structural reform, was overambitious. A two-phased approach (phase 1: capacity- building and restructuring; phase 2: implementation) would have been more appropriate. Loan covenant time frames underestimated the time required for the government procedures to amend the Fauna and Flora Protection Ordinance (FFPO) and for institutional reform. Heading the project management unit (PMU) with someone from outside the DWC was detrimental to engaging the department staff. Introducing large numbers of technical assistance (TA) consultants into the DWC that was understaffed resulted in inefficient use of consultancy expertise. Regular review and updating of the project framework would have aided monitoring and evaluation. The outreach program was made more sustainable by being implemented by the executing agency's own staff than it would have been by recruiting outside NGOs, who would have left when the project closed. Delegation of powers to the field enhanced pilot protected area (PPA) management but it also increased the importance of self-motivated PPA leadership. It was unreasonable to expect government officers to engage in commercial links and marketing initiatives with private enterprise in such a short time. A formal monitoring system should have been established by the DWC at the start of the project. Training for all PPA ranks and public awareness-raising were positive factors in improving conservation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/protected-area-management-and-wildlife-conservation-project
Sri Lanka: North East Community Restoration and Development Project | Public Sector Management | 2010-09-30 | It is noted that the project worked well with both sides in the conflict, and was well accepted in conflict-affected areas. Developing this type of rapport is important, and reflects well on the project implementers. The lessons should be relevant in other conflict or post-conflict situations.[Main text, page 8, section E(ii)] project cycle stage: Implementation Lesson Topics: | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/sri-lanka-north-east-community-restoration-and-development-project
Forest Resources Management Sector Project | Agriculture, natural resources and rural development | 2010-09-01 | Monitoring of production-related activities. A wide range of production activities were financed under the project new woodlots, the maintenance of old woodlots, clear-felling, and the replanting of mature plantations, for example. Detailed physical and financial information was not maintained at the individual enterprise level, however. This would have been best collected through regular stock assessments to estimate growth rates more clearly. The resulting information would have been valuable in two ways. It would have made it possible to more accurately determine the financial returns to beneficiaries at the household level. At the state plantation level, it would have informed policy decisions on investment in the sector. Institutional change process. The magnitude of loss in potential revenue because of its delay in introducing open competition in state plantation timber harvesting was demonstrated analytically to the government through a comprehensive plantation measurement and valuation system. This led to an increase in stumpage rates and provided an incentive for the Forest Department to take steps to review the mandate of the State Timber Corporation and make it more cost efficient. But much still needs to be done to enhance competitiveness in the sector. The process of achieving sustainable institutional change and strengthening organizations demands time, rigorous analysis, informed policy dialogue, and active engagement. Public response to project activities. Consultations, mass media campaigns, awareness workshops, and beneficiary involvement in conflict resolution meetings all contributed to a greater understanding of project interventions by key stakeholders. Implementation activities did not appear to have created significant public protest and generated no critical news reports, public interest litigation, or petitions. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/forest-resources-management-sector-project
Power Sector Development Program | Energy | 2010-01-12 | 1. A strong sector development program (policy and investment) entails a design that properly links and demarcates expected impacts, outcomes, and outputs. The Power Sector Development Program (PSDP) failed to coherently set out the objectives between its policy and investment components. Consequently, the lack of clarity between the two components in the PSDP framework contributed to the sector program's underperformance and poor design made it difficult to evaluate. Thus, in designing of such programs, proponents need to properly articulate linkage of impact, outcomes and outputs in various project documents. [Main text, paras. 40,69] project cycle stage: Design, Implementation Lesson Topics: 2. Advance procurement actions and decisiveness on the end of the Ceylon Electricity Board and ADB could have prevented procurement delays. The project completion report noted that the project was extended by 24 months to accommodate delays in procurement. [Main text, paras. 20, 71] project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/power-sector-development-program-0
Southern Province Rural Economic Advancement Project | Finance, Transport | 2010-01-12 | 1. The project was particularly effective in meeting the needs of the government. The project responded very effectively by repairing the damaged rural gravel roads and pedestrian bridges after the May 2003 floods. As requested by the government, the project also responded positively by changing its scope from gravel roads to paved surface roads. The responsiveness and flexibility demonstrated by the project was laudable, and the project provided a worthy example for the design and management of future projects. project cycle stage: Lesson Topics: 2. Since the project had two implementing agencies supervised by different agencies, project coordination was difficult. A more suitable arrangement involving dual implementation agencies may be through a region-based apex financial institution, which is also assigned responsibility for establishment and operation of enterprise development service support activities and works closely with the regional organization responsible for sustaining the enabling environment. During the design stage, project implementation arrangements and responsibilities of each agency should be clearly explained in the project administration memorandum. project cycle stage: Lesson Topics: 3. Future projects need to address issues associated with the financial capacity of pradeshiya sabhas to develop and maintain rural infrastructure through closer monitoring, obtaining greater commitments from provincial and local organizations, and the use of soft loans for capital works tied to user-pay financial plans for civil works such as rural markets, where a financing charges mechanism already exists. project cycle stage: Lesson Topics: 4. Future projects designed to address rural gravel road maintenance issues need to be more carefully designed through (i) identification of project roads during appraisal; (ii) identification of suitable gravel sources in proximity of the project roads; and (iii) prior commitment from each pradeshiya sabha to participate in the project, including prior establishment and commitment of funds to a road maintenance account. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/southern-province-rural-economic-advancement-project
Third Water Supply and Sanitation Sector Project |  | 2009-01-11 | 1. Demand-driven, community-based development requires a flexible design to accommodate community preferences. Accordingly, the project design team needs to ensure that sufficient time is alloted to overcome initial hesitation by communities. In this project, the overall success of delivering the investments can be attributed to sound planning and flexible design processes, particularly in mobilizing community participation in the initial stages of the Project. Participatory planning is an effective tool under the demand responsive approach to enable users to express their demands. [Main text, paras.7,43,52(i)] project cycle stage: Design Lesson Topics: Project Design: Project design Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation 2. Requiring cash and labor contributions and giving operation and maintenance responsibility to communities enhances commitment and ownership. project cycle stage: Implementation, Operation Lesson Topics: Project Management: Operation and maintenance Capacity Development: Ownership Methodologies/Approaches: Community approach 3. Handover of water supply to local communities requires continued support during the transition and follow-up periods. Ongoing capacity development efforts need to include operation and maintenance and financial management training. project cycle stage: Implementation, Completion Operation Lesson Topics: Capacity Development: Capacity development Sector Related Issues: Water resource management 4. Conducting groundwater investigations over a period of time sufficient to determine variations in yield and recharge rates can prevent water shortages. In future projects, shortages in groundwater experienced in some rural areas need to be identified as early as the feasibility stage planning. In Sri Lanka, depletion of the groundwater table is a common issue in dry-zone areas. Closely located agrowells were identified as a major cause of this, in addition to other natural and manmade hazards. Hence, in cases where groundwater was selected as the water source for pipe schemes, a safety factor was introduced to the actual possible yield from the well in calculating the probable extraction of water to allow for recharge and to avoid overextraction. In a small number of schemes, the implementing agency constructed additional boreholes or connected to nearby piped schemes to assist villages faced with shortages. [Main text, para. 52(iv), Appendix 9] project cycle stage: Feasibility, Implementation Lesson Topics: 5. Policy reforms, to be more effective, require a more careful assessment of political risks and upfront consultation with government leadership and various stakeholders. By project completion, expected sector reforms have been noted to be less satisfactory and only partially completed. For instance, a national water resources policy and act, included as one of the project covenants, was not achieved largely due to lack of political support. Government leadership and a more process oriented consultations are therefore critical in the policy formulation and broader stakeholder acceptance. [Main text, paras. 20-23,52(v)] project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Ownership Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation 6. Project preparatory activies needs to include an up-front capacity assessment of national procurement regulations and practices to avoid unnecessary delays. Accordingly, this needs to be reflected in the comprehensive procurement plan for new projects and used as a monitoring tool during implementation. Delays in procurement occurred due to government procedures in processing and approving contracts. After ADB intervention though, procurement procedures were improved by the Government. [Main text, paras. 34,52(vi)] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Capacity Development: Capacity assessment 7. Loan covenants for land acquisition needs to be strengthened to include provisions for preparing safeguard documents in case ADB's involuntary resettlement policy is triggered. Safeguards monitoring and reporting if not carried out effectively will lead to issues not addressed in time and appropriately. In this case, land acquisition has caused delays in some urban subprojects. Evaluation further noted that even after project completion, land compensation has yet to be completed for nine parcels of land. [Main text, paras. 15,32,52(vii); Appendix 10] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-water-supply-and-sanitation-sector-project
Secondary Education Modernization Project | Education | 2008-11-14 | 1. Implementation of the Project has shown that schools that are well managed implement project activities more effectively and efficiently. This strengthens the importance of champions for the success of any new initiative. Champions can be both identified and developed. [Main text, para. 72] project cycle stage: Implementation Lesson Topics: 2. Any project that attempts to bring about substantial systemic changes needs to be realistic about the goals including the timeframe for such changes. Due consideration for the sequencing and interdependence of project components as well as buy-in from stakeholders are essential in this process. As bringing about systemic change is an incremental and time-consuming process, continued support is crucial to its sustainability. The project completion report noted the lack of progress in career guidance, development of public-private partnership and school based management due to inadequate support from various stakeholders. [Main text, paras. 5, 21, 26-27, 64, 73] project cycle stage: Lesson Topics: Project Design: Project design Capacity Development: Ownership Capacity Development: Partnerships Policy & Reform: Reform 3. To bring about and sustain change, government ownership is crucially important. As a result of strong government ownership, many project components remain successful, or remain on the agenda for implementation. [Main text, paras. 59, 67, 74] project cycle stage: Concept Design Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Ownership 4. The potential of project activities cannot be maximized without effective monitoring and the commitment of officials trained in monitoring and evaluation. Project experience noted lack of attention given to monitoring and evaluation. Up until 2005 (almost five years into implementation), the project lacked systematic monitoring of its components and outcomes . [Main text, paras. 31, 76] project cycle stage: Implementation Lesson Topics: 5. The first computer procurement experience indicates that bidding documents need to always clearly specify instructions and requirements. Should there be doubts on the authenticity or completeness of bidders' submissions, the government needs to directly verify information with manufacturers. As noted in this education project, vague instructions in the bidding documents had caused misunderstanding on deliverables of contractors and this continued to be an outstanding issue at project completion. Lessons from this experience were incorporated in the succeeding contract awards. [Main text, paras. 48, 51, 53, 77] project cycle stage: Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-education-modernization-project
Tea Development Project | Agriculture and Natural Resources | 2008-03-03 | 1. The outcome of several project interventions was affected by changes in government policy during project implementation. The success of institutional reforms is closely linked to consistency in government policies. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Risks/Risk management Policy & Reform: Policy reforms/framework 2. To ensure implementation of institutional reforms, an agency or unit that has adequate mandate and power should be involved. A project management unit lacks the power to put pressure on the Government to enact policy reforms. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Institutional analysis Policy & Reform: Policy reforms/framework 3. A voluntary staff separation package program for streamlining an institution should use staff performance as an eligibility criterion. The voluntary early separationprogram under the Project did not achieve the expected results because it was not linked to staff performance indicators. project cycle stage: Design, Implementation Lesson Topics: 4. A plan for institutional reforms should be designed with due consideration for the effectiveness of the proposed actions. The reconstitution of the boards of the tea-related institutions was a reform intended to ensure the perspectives of the private sector and the tea smallholders were heard with respect to management decisions. Although the boards were reconstituted, their effectiveness did not increase as the role of the boards did not change, despite the inclusion of the new members. project cycle stage: Appraisal Implementation Lesson Topics: Capacity Development: Capacity assessment Capacity Development: Institutional analysis Sector Related Issues: Public-private partnership Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Policy & Reform: Reform Methodologies/Approaches: Participatory approach 5. A mechanism to continue and replicate successful activities after a project ends needs to be established prior to project completion. Despite the potential for continuity of the homestead development component, all activities ceased at the end of the Project and the increase in capacity relating to homestead development is not being utilized. project cycle stage: Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Crosscutting Issues/Themes: Sustainability Capacity Development: Capacity development 6. Consideration should be given to institutional sustainability after the project period, including coordination among related agencies and M&E of project benefits. Temporary arrangements for project implementation, such as the PMU and a steering committee, cannot continue their activities once a project closes. The stimulus for successful activities tends to disappear quickly upon project closure. project cycle stage: Completion, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Institutional analysis Project management should be given flexibility in modifying staff positions, especially for key technical positions. project cycle stage: Implementation Lesson Topics: Project Management: Project management Capacity Development: Human resources management The capacity of the entity that will be responsible for operation and maintenance of project facilities should be assessed carefully at appraisal. project cycle stage: Lesson Topics: Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity assessment Capacity Development: Institutional analysis The executing agency's firm commitment is essential to promote participation by the private sector in activities that could potentially be undertaken by public sector agencies. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Sector Related Issues: Private sector Sector Related Issues: Public-private partnership The record of fund utilization segregated by project activities is essential information for M&E, and adequate arrangements for financial management should be established early in a project, particularly when multiple implementing agencies are involved. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies The time and resources needed to finalize project accounts should be considered in preparing project implementation arrangements. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/tea-development-project
Second Perennial Crops Development Project |  | 2008-02-05 | 1. The experience of the pilot activity under the Project shows that potential exists in Sri Lanka for a gradual introduction of a fee-levying private extension service among commercial farmers with a better ability to pay, leaving scarce government resources to serve the poor and subsistence level groups of farmers more effectively. Commercial farmers need different kinds of services, including farm planning and budgeting, financial management, and post-harvest operations, in addition to the more traditional advice on production technology. They require need-based extension services with which they could reduce cost of production. Furthermore, user-pay services are accountable, collectively and individually stimulating service providers' performance and commitment related to demand. However, the process of introducing private sector service providers requires a clear policy framework and an effective framework for cooperation between the Government and private sector stakeholders. project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Project Design: Project design Sector Related Issues: Extension service Sector Related Issues: Public-private partnership Policy & Reform: Policy reforms/framework Methodologies/Approaches: Pilot project 2. To be profitable, private sector extension services need to be integrated into other commercial operations, such as sale of farm inputs. A company set up solely to provide extension services may not be viable in the long term. This is seen in the less than optimal scale of operations of the three service contractors. Contractors expressed views that (i) the financial benefits of input sales as setting off any operational losses in providing extension services, and (ii) the establishment of a reliable network of high-quality producers as of sufficient benefit to offset its operational losses in providing advisory services. Without such externalities, the operation may not be attractive. In fact, one of the contractors did not benefit from either input sales or output marketing. project cycle stage: Lesson Topics: Project Design: Project design Sector Related Issues: Extension service 3. An executing agency's firm commitment is essential to promote private sector participation in activities that could potentially be undertaken by public sector agencies, as government tends to be reluctant to take actions that broadly diminish its power and enhances the influence of the private sector. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Ownership Capacity Development: Partnerships Sector Related Issues: Private sector Sector Related Issues: Public-private partnership 4. The plan to use a short-term international consultant for M&E appeared to be inappropriate. When an assignment for consultants in a socioeconomic field is short term, national consultants are more appropriate than international consultants. project cycle stage: Design Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Capacity Development: Capacity development Capacity Development: Ownership After completion of projects, executing agencies do not have procedures and systems in place to build upon the knowledge gained by implementing the projects. This results in inadequate transfer of project knowledge to government institutions and staff. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Project Management: Executing/Implementing agencies Capacity Development: Capacity development Government institutions are in general not geared to working with the private sector and therefore have inadequate mechanisms to interface with it. project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity development Capacity Development: Institutional analysis Capacity Development: Partnerships Sector Related Issues: Public-private partnership Introducing new approaches requires public awareness campaigns at a project's outset to obtain stakeholders' support. Public understanding of proposed changes' rationale and expected outcomes can facilitate introducing new interventions. project cycle stage: Lesson Topics: Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach The multiplicity of government ministries and agencies involved in the agricultural sector poses serious challenges for coordination and synergy. project cycle stage: Lesson Topics: Crosscutting Issues/Themes: Public governance Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Institutional analysis The outcome of project interventions was affected by changes in the direction of government policies during project implementation. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Policy & Reform: Policy reforms/framework When procuring goods and services involves multiple agencies, each of them forms its own tender committee. Having several committees for procurement is extremely cumbersome. Despite the Government's having more flexible procurement guidelines for donor-funded projects, the executing agencies do not follow them. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Without specific activities for the most isolated rural areas, project investments remained biased towards suburban, more developed districts. project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Sector Related Issues: Rural development Sector Related Issues: Urban sector/development Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-perennial-crops-development-project
Skills Development Project | Education | 2008-01-30 | 1. Adding an additional component to a completed loan design requires thorough analysis to ensure congruence with the project goals, objectives, and methods. If additional input is required, the new requirements should be integrated into existing components in the original project design. project cycle stage: Design Appraisal Lesson Topics: Project Design: Project design Project Design: Subprojects 2. Complex projects involving multiple funding agencies, government agencies, institutions, and stakeholders require additional time at early implementation to establish operational policies and procedures. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project administration Methodologies/Approaches: Consultation/Participation 3. The sequencing of various implementation activities such as policy reforms, civil works, consultancy deployment, and equipment procurement must be logical and carefully planned to realize maximum investment efficiency and effectiveness. When project implementation relies heavily on policy change, the essential policy adjustments should be completed prior to consultant deployment. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement Project Management: Project administration Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/skills-development-project-1
Country Assistance Program Evaluation for Sri Lanka: Inclusive Development and Conflict Resolution: Major Challenges in the Future (2007) |  | 2007-08-31 | 1. Change management calls for an understanding of the reasons for resistance, and ways of overcoming impediments. Moreover, continuing efforts are needed to arrest the decline in the capacity of sector institutions to implement projects, mainly due to problems with recruiting and retaining qualified staff. An improvement in the incentive and reward system isimportant. project cycle stage: Feasibility, Implementation Lesson Topics: Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management 2. Policy-based lending requires a careful assessment of the reform environment and reform readiness. Country ownership and political will are fundamental. Policy reforms that are built on an apolitical process and a lack of understanding of the country's history are bound to fail. Policymaking is often complicated by elections. Certain calls for economic reforms may not be heeded, particularly during the rise to power of political coalitions that have differing agendas. A balance must be achieved between setting the pace of reforms and ensuring social and political stability. Thus, the vulnerability and sensitivity of policy reform must be understood in program design and implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Policy-based lending Project Design: Project design Project Management: Project management Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform A community-based approach to rural water supply systems can be effective in enhancing customer roles in project planning and implementation and in promoting greater ownership. Least-cost options for planning water supplyand sanitation projects should consider an integrated approach, including supply and demandfactors, to achieve more sustainable resource use. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Project management Capacity Development: Ownership Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Sector Related Issues: Water resource management Methodologies/Approaches: Community approach Methodologies/Approaches: Holistic approach A good understanding of political and legislative processes, including policy and regulatory environments, is a key requisite in project preparation and implementation. Monitoring changes in the macro context influencing a key sector is necessary, particularly the incentive environment for private sector participation. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project administration Project Management: Project management Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Assessing the institutional and management capacity of executing agencies is extremely important. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Benchmarking can be an effective tool for improving the operational performance of water supply service providers. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Sector Related Issues: Health and sanitation management Continued stakeholder support for policy reforms is essential to sustain the reform process. project cycle stage: Feasibility, Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Developing a project management and information system should be prioritized for effective project implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Management information system Project Management: Project management For vocational training graduates, support services must complement the provision of loans for self employment, and more tracer studies of graduates must be conducted for future planning. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Education Handover of management of water schemes to local authorities and community-based organizations requires continued support during the transition and follow-up periods to enhance the sustainability of such schemes. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Sector Related Issues: Water resource management Methodologies/Approaches: Civil Society Participation In distance learning, more awareness programs are necessary to promote readiness for online learning as well as to expedite the participation of nonstate agencies. A revolving fund will enable participants from non-affluent families to acquirecomputers for distance learning. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Education Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation In technical education and vocational training, more social marketing programs are necessary to change the negative attitudes of private sector employers, parents, and students toward state-run technical education and vocationaltraining institutions. While education policies have been gender sensitive, concomitant motivation programs to encourage women to enroll in technical training programs are crucial. Across the education subsectors, results-based monitoring andevaluation must be promoted to track achievements over time. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Managing for Development Results Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Human resources management Sector Related Issues: Education Sector Related Issues: Private sector In the context of sector reforms, country ownership and political will for implementing the reformagenda are requisites for which ADB assistance cannot serve as a substitute. Advancing policyand institutional changes requires champions and coherent support from within the country.Policy initiatives can take a long time to materialize, and such initiatives require sustainedsupport. project cycle stage: Feasibility, Implementation Lesson Topics: Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform Investing in awareness campaigns to improve beneficiary participation is vital. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation Power sector restructuring is a dynamic and complex process with enormous challenges. It calls for a deep understanding of the political economy; broad-based ownership of reforms; a comprehensive sector road map that recognizes pressing needs, such as least-cost power generation, other than reforms; and measures to knit reforms into a broader articulation of public interest. Conveying the costs and benefits of the reforms versus alternative measures isimportant. Work is necessary on all fronts, not only in putting in place a legal framework or animproved market structure, but also in building constituencies for reform. Where public andpolitical resistance is likely to hinder reform implementation, provision should be made forincreasing public awareness of the reform agenda and reaching a consensus on the means forachieving objectives. project cycle stage: Design, Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Project design Capacity Development: Ownership Sector Related Issues: Energy planning/management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform The complexity and diversity of a sector should be matched by flexible and robust projectdesigns that can meet evolving needs. project cycle stage: Design, Feasibility Lesson Topics: The rapid divestment of state-owned enterprises tended to sacrifice transparency and due diligence. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Policy & Reform: Privatization Policy & Reform: Public sector reform Without continuing commitment from the government, ensuring cost recovery and financial viability through ADB's loancovenants can be effective to some extent only. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Loan Agreement: Covenants Capacity Development: Ownership | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-sri-lanka-inclusive-development-and-conflict
Water Resources Management Project | Agriculture, Natural Resources, and Rural Development | 2007-01-11 | 1. During project preparation and implementation, there was overemphasis on achieving a product - a new policy and a new organization - but there was little time and insufficient resources to deal with the processes, the sociopolitical issues involved, and the overall institutional implications. The TA studies implemented prior to the Project analyzed the project environment with sufficient accuracy, but could not fully assess the political risks involved in establishing the National Water Resource Authority (NWRA) in place of the Water Resources Secretariat - creating a perceived threat within existing water sector agencies. Therefore, comprehensive analysis is needed on how the end product could be successfully achieved or a more process-oriented methodology could have been initiated during project preparation, including assessments of the risks associated with the establishment of NWRA, and resources required for the implementation of part A of the Project. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 2. Projects designed to support national policy, legislation, and sector reforms - including institutional development - should not be mixed with infrastructure development in selected geographic areas. Such diverse objectives, which require a complex mix of project staff and expertise, should have not been combined in a single project to avoid delays in project implementation. project cycle stage: Design Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform 3. In this Project, an attempt had been made to prepare and obtain approval of a comprehensive National Water Resources Policy that had too many contentious details, such as pricing of water, private sector participation, and regulation of groundwater. Since some political parties, even within the Government, had very different views on these aspects, the proposals reform attracted criticism at the outset. Only key elements of the policy (e.g., enabling the creation of a national agency with a mandate for overseeing water resources management and the key principles according to which water resources will be managed) were needed initially. The remaining policy elements could have been developed once the implementing agency was created and operational. Inclusion, without prior broad consultations, of complex issues - such as water rights, groundwater regulation, and water pricing - in the policy document eventually stalled the process. The policy could have been developed in a gradual manner, enabling wider consultations, to ensure acceptance by all stakeholders. Government leadership is critical in the policy formulation and consultation processes. project cycle stage: Implementation Lesson Topics: Sector Related Issues: Water resource management Policy & Reform: Policy reforms/framework Policy & Reform: Reform 4. Although the Project was designed to involve key stakeholders in a consultative process, the eventual effect was not favorable. The consultation activities have not been effective, as they could not reach grassroots stakeholders or they were not sufficient to present effectively the facts justifying the need for a National Water Resources Policy in Sri Lanka. Policy development and institutional reforms can be effective only when partner organizations and other stakeholders are all equally aware of their responsibilities and benefits. It is also essential that the proposed reform programs are clearly understood and eventually owned by all stakeholders. A strong political will to proceed with such reforms is a product of public confidence and the common acceptance of the proposed reforms. Adequate mechanisms are needed to produce that level of public awareness, confidence, and acceptance - initially by absorbing views of diverse interest groups and analyzing them in terms of program objectives, and finally adjusting the design of the programs to suit the majority views. project cycle stage: Design, Implementation Lesson Topics: Sector Related Issues: Water resource management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/water-resources-management-project
Upper Watershed Management Project |  | 2006-11-13 | 1. Project frameworks need to be dynamic, adopt standard procedures, and be constantly reviewed if they are to serve monitoring and evaluation needs. The Report & Recommendation of the President (RRP) framework was weak and was neither used nor updated. Having more than one outcome has also led to confusion during implementation. [Main text, paras. 9, 66(i)] project cycle stage: Feasibility Lesson Topics: 2. All land users should have been involved, as required by a holistic approach to watershed management. Tea estates were excluded despite their contribution to soil erosion. [Main text, paras. 9, 66(ii)] project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach 3. Translating policy into practice takes longer than the duration of a project. The National Watershed Management Policy (NWMP) has yet to be internalized within the government. Proposals to establish provincial watershed management units (WMUs) to continue the project approach, although welcomed at the local level, failed to materialize for lack of an overall institutional support agency. [Main text, paras. 50, 66(iii)] project cycle stage: Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Capacity Development: Capacity development Sector Related Issues: Water resource management Policy & Reform: Policy reforms/framework 4. A high degree of local community participation and contribution can lead to greater project efficiency. This was achieved in the Upper Watershed Management Project through the use of social mobilizers (SMs). The project management office directly engaged SMs as the interface between communities and implementing agencies. Community involvement in planning, implementing, managing, and maintaining field activities created greater transparency and ownership. This led to greater efficiency in procuring materials, construction, and ensuring plantation quality. [Main text, paras. 53, 66 (iv); Appendix 6, paras. 39-44] project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Rural development Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach 5. Given the major task of establishing coordination among many implementing agencies, devolved and not, an initial 12-month planning and preparation period should have been included. Pressure to commence field activities and meet targets adversely affected start-up operations and training. [Main text, paras. 26, 66(v)] project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Targeting 6. To facilitate assessment of effectiveness, systems to monitor and evaluate project benefits should be built into the implementing agencies' (IAs) systems. In this project, a computer-based system was designed but not applied nor adopted by the IAs. There was no midterm socioeconomic assessment undertaken. The project management office relied on less formal means of monitoring and depended on consultants for final evaluations. [Main text, paras. 45, 66(vi)] project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management 7. Sustainability of project benefits could have been increased by focusing on existing community based organizations (CBOs), registering new ones with the divisional secretariat, and giving CBOs full responsibility for use of their funds. The subsidy-dependent syndrome that remains engrained among beneficiaries will need to be reversed to self-reliance if participatory approaches are to become truly self-sustaining. [Main text, paras. 55, 66(iv)] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Methodologies/Approaches: Community approach Methodologies/Approaches: Participatory approach Management through a Project Management Office (PMO) engendered departmental independence and facilitated coordination of multiple implementing agencies (IAs), but the stimulus ceased on closure. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Project Management: Project management Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/upper-watershed-management-project
Private Sector Development Program Loan |  | 2006-06-15 | 1. Some measures, such as voluntary retirement schemes (VRS) for the involuntary termination of workers for state-owned enterprises (SOEs) that are to be divested, have significant budgetary implications. When including such measures in the policy matrix, it is important to ensure that the fiscal situation can support such measures and the necessary budget allocations are made. project cycle stage: Design Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Capacity Development: Human resources management Policy & Reform: Policy matrix Policy & Reform: Privatization Policy & Reform: Public sector reform In order to provide adequate flexibility, a program cluster should be designed as a set of single tranche subprograms, with each subprogram comprising clearly defined policy actions that are calibrated to be achievable within a relatively short time frame. project cycle stage: Appraisal Lesson Topics: Modality: Cluster operations Modality: Program Project Design: Project design Policy & Reform: Policy reforms/framework Proceeds received from the sale of state-owned enterprises (SOEs) are dependent on the economic environment and market conditions. A predetermined mandatory program for privatizations - with a quantified net asset value within a specified period to meet tranche release conditions - may not always optimize proceeds. Instead, it could result in underpricing of shares as demonstrated in the sale of Sri Lanka Telecom Ltd. and Sri Lanka Insurance Corporation Ltd., both of which were sold in order to meet tranche release conditions when the stock markets were plummeting worldwide and the Sri Lanka market was at a relatively low level. In addition, the regulatory authority must be operational to properly regulate the industry (i.e., Insurance Board of Sri Lanka) before a privatization takes place. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Market analysis Modality: Program Policy & Reform: Privatization Policy & Reform: Public sector reform Under the program cluster approach, other multilateral institutions may finance programs originally proposed to be included in future subprograms of the cluster loan. The Private Sector Development Program's (PSDP's) subprogram 1 and proposed follow-on (subprogram 2) were put in place before the World Bank's Poverty Reduction Strategy Credit was developed. The World Bank program overlaps some of the focus areas of PSDP's subprogram 2. Organizational restructuring within ADB also shifted responsibility for many of the components that were originally envisioned to be included in subprogram 2 to other departments, which are implementing them. Although the PSDP was structured as a cluster, only 1 of the 15 areas considered in the preparatory work for subprogram 2 were actually included in subprogram 2. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Cluster operations Modality: Program Sector Related Issues: Private sector | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/private-sector-development-program-loan-0
Science and Technology Personnel Development Project |  | 2006-06-15 | 1. The project was highly ambitious and complex, involving 16 semi-autonomous institutions, 4 different ministries; and activities that would take time to complete before they would have an impact. Therefore, the implementation period of 5 years was unrealistic. There was little room for flexibility in project implementation; with a longer-term view, and more of ï¿½processï¿½ approach, the project could have started at a smaller scale and gradually expanded as experience was gained and lessons were learned. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education Methodologies/Approaches: Process approach 2. One problem that will remain in terms of upgrading the qualification of academic staff is that some staff who go abroad for postgraduate studies, for example to the US or Australia, may not return, since they can there earn in a month what they would earn in a year at a university in Sri Lanka. Since Sri Lanka will need to continue to send science and technology and R&D staff abroad for higher science and technology qualifications, an option may be to send them to universities in the region in the first instance, and only to send them outside if the region cannot provide the required degree,. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Education 3. Underutilization of facilities has been and continues to be a problem in ADB-supported projects. Future projects need to assess carefully the needs and plans for such investments. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design 4. Gender aspects need more attention and action needs to be taken to increase female enrollment in undergraduate science and technology courses traditionally dominated by men. The obstacles women face undertaking graduate and postgraduate studies need to be analyzed. Support for gender studies, workshops for faculty at institutes, career guidance for women, and opportunities to meet successful female role models should be considered. In the case of the project, provision of a higher number of scholarship awards to females for postgraduate studies was the only input to promote gender equity. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Project Design: Project design Sector Related Issues: Education 5. Setting up a comprehensive scheme of accreditation, with continuous monitoring and periodic evaluation to maintain standards, is a long process, but a very important one if the required standards in response to global trends are to be maintained. In the case of the project, program quality at the 10 universities varies. The project provided inputs for accreditation of courses. Only a few courses received foreign accreditation, and no attempts were made to establish a local professional body for accreditation. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/science-and-technology-personnel-development-project
North Central Province Rural Development Project | Agriculture, Natural Resources, and Rural Development | 2006-05-15 | 1. Integrated Rural Development Projects (IRDPs), by nature, are multisectoral undertakings. Limited project preparation resources are therefore spread more thinly as the complexity of the design grows. It is therefore better to focus project activities on a core program, rather than trying to cover a wide array of potential activities. Extra care should be taken when including relatively new arrangements for line agencies, such as the devolution of powers to the Provincial Irrigation Departments (PIDs) and the Provincial Road Development Authorities (PRDAs). A period for building capacity through technical assistance may be required before the project, or, alternatively, special provisions may need to be made to ensure long-term institutional capacity building during the project. IRDPs require careful planning and coordination among all project partners. project cycle stage: Design, Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Irrigation management Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation 2. Projects that aim to expand emerging enterprises or help the establishment of new enterprises should provide more than credit. There is a need to support managerial, planning, record keeping, and marketing skills. Capacity building by qualified service providers (e.g., NGOs) or microfinance institutions is desirable. Proper targeting of beneficiaries at the design phase will help to determine the right microfinance option and to target poor beneficiaries who are often risk averse and cannot obtain credit from participating credit institutions (PCIs). The microcredit component of this integrated rural development project had very little impact on the poor (i.e., it has failed to target the poor, instead it has successfully encouraged entrepreneurship through training and/or credit provision among already established enterprises). [Main text, paras. 14-16, 62] project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Industry and Trade Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Targeting 3. The overall project objective was to reduce poverty in the province. The poorest of the poor might have benefited if the following approaches had been adopted: (i) the provision of microcredit and skill and employment training (rather than only the enterprise development approach that was finally adopted for the credit program); (ii) creative financing schemes to facilitate access to drinking water and rural electrification under the Village Advancement Program or VAP (e.g., through links to NGOs or microfinance institutions as is already being done elsewhere in Sri Lanka); and (iii) greater use of qualified NGOs that have the capacity to target and work with the poorest of the poor. This need not have required an overhaul of the Project Design, but could have been achieved with only minor enhancements. [Main text, para. 63] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building Crosscutting Issues/Themes: Employment Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Targeting 4. Better implementation planning would have ensured better phasing of project activities: (i) establishing the PMO office (staff, facilities, equipment, consultants); (ii) creating and integrating line agency capacities; (iii) a controlled pilot phase to introduce and learn from initial project works; and (iv) a scaling up of activities after a careful assessment of lessons learned from the initial pilot phase. BME is a critical part of planning and implementation, and should be established within the first year of the project. In the case of this integrated rural development project, poor planning has resulted to lack of cost control, poor quality work, and lack of program integration, among others. [Main text, paras. 26, 64] project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Project management Methodologies/Approaches: Pilot project 5. To foster greater ownership by local government, participation of local leaders and line agencies should be sought (i) in project preparation, and (ii) through routine and periodic planning throughout project implementation. The project did not achieve much transference to the provincial government or line agencies. It achieved little integration and significantly lacked involvement in and ownership of the project by the provincial government which threatens the likelihood of the project's sustainability. [Main text, paras. 52, 56, 60, 66] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Ownership Country Context: Decentralization Methodologies/Approaches: Consultation/Participation 6. Strengthening operation and maintenance (O&M) and looking into innovative mechanisms for participatory O&M should be a priority to ensure likelihood of project sustainability. Realistic post-project strategies, plans and budgets should be incorporated into the project for each sector. Serious attention to O&M issues at the design stage, and, where appropriate, a phased project implementation approach, with clear beneficiary understanding and formal commitment of the requirements for O&M is needed. If local government resources are limited, projects that require intensive O&M need particular attention in the country strategy and program and during the project design stage. One of the shortcomings in the project preparation of the integrated rural development project is the failure to incorporate enhancing O&M capabilities as a major component seriously reducing its relevance and likelihood of sustainability. [Main text, paras. 36, 60, 67] project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Cluster operations Project Design: Project design Project Management: Operation and maintenance Country Context: Decentralization Country Context: Prioritization Methodologies/Approaches: Participatory approach A participatory approach is critical throughout implementation of rural development projects and must be a high-profile activity. project cycle stage: Implementation Lesson Topics: Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach Technical and resource limitations should be documented when institutions are assessed in project preparation and programs prepared to overcome these. If the limitations cannot be addressed in project preparation, the components should be dropped, and the remaining implementation arrangements simplified. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Institutional analysis | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/north-central-province-rural-development-project
Southern Provincial Roads Improvement Project | Transport | 2005-09-15 | Any reassessment of a project is problematic where only limited field investigation has been carried out. A BME database management system must be set up for each project, right at the start of implementation. Using well-established scientific principles and techniques of experimental design would put BME for provincial roads on a more solid footing. Areas for improvement in future projects were identified, including: patchiness in both data collection and information safekeeping for BME since the time of appraisal; BME has often to be restrained and based upon a relatively small sample of road sections which needs to strike a balance between social and other demographic features; BME requires statistical coherence in the material collected and consolidated during the course of the project and in the years beyond; and road condition surveys should be geared towards the provision of consistent network-wide estimates of international roughness index (IRI), in particular, on all roads surveyed. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Design: Appraisal Project Management: Management information system Sector Related Issues: Roading Better consultation, coordination, and cooperation between public authorities would help reduce the incidence of problems related to relocation of utility services along roadways. The public service authorities were generally too slow to act on requests to relocate infrastructure that obstructed the project's road rehabilitation work although funds for such relocation were available through the project. When preparing projects in the future, other arrangements should be earnestly sought to ensure the timely relocation of such service infrastructure. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation Similar road projects in the future might more usefully be designed around local network effects than road classification. Existing and potential public transport routes, irrespective of the class of road used, might be a more appropriate starting point for design rather than a collection of dispersed short road segments, selected only because they fall within the purview of a single government authority. For the project, it was realized during appraisal that one of the risks was connected with the possible failure of the government to fully implement its plans to develop and maintain the primary road network serving the project area (Southern Province). Even now, after the project, some project roads are functionally connected to major class-B roads that are still in an indifferent state of repair. Where evident, this situation has tended to blunt the efficacy of the project. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Roading Sustainable road maintenance requires a continuing focus on the potential benefits available from effective and consistent budget allocation and expenditure. Funds must be allocated by the government to maintain infrastructure properly, and maintenance must be efficiently executed to obtain maximum benefit. Both of these requirements must be met as either one without the other will result in a deterioration of services. The project has contributed effectively towards ensuring that the latter requirement is met to the fullest extent, but the imbalance so far evidenced in the accomplishment of these two requirements, and the deleterious effects of this imbalance, should continue to be of major concern as a potential risk when preparing similar projects in the future. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Operation and maintenance Project Management: Risks/Risk management Sector Related Issues: Roading There are assured benefits to be gained by shortening as much as possible the response time between project preparation and implementation. Additional design and maintenance costs could be avoided, and economic performance and efficiency would improve. Borrowers and ADB together must ensure that the overall process is speeded up to the fullest extent possible. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Operation and maintenance | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/southern-provincial-roads-improvement-project
Plantation Reform Project | Agriculture, Natural Resources, and Rural Development | 2004-12-15 | Labor should be considered an investment, rather than a cost, and human capital and social development should be integral parts of regional plantation companies' (RPCs') corporate development strategies if the plantation sector is to be profitable. To be successful, social development programs should have a strong commitment at the management level and shouldbe driven by stakeholder demand. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Market analysis Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Industry and Trade Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Project experience underscores the commitment and political will required to implement policy reforms, such as privatization and market liberalization. This was the underlying factor in the privatization of 20 regional plantation companies (RPCs) during the project period's first half. The commitment and political will, however, did not last. When the privatization procedures were changed, the controlling interests in three of the 20 RPCs were bought by government entities. ADB did not consider the three RPCs privatized, and they were therefore not eligible for project funding. The three RPCs were eventually privatized, being sold to private entities. At project completion, another three RPCs were not yet privatized. Also, Janatha Estates Development Board (JEDB) and Sri Lanka State Plantation Corporation (SLSPC) estates and warehouses were not restructured and privatized. With continued political intervention on wages and the restrictions on marketing, an enabling environment was not created for the RPCs to improve their profitability, and, hence, achieve the full potential for long-term sustainability. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Capacity Development: Ownership Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Reform Success in privatization required a private sector willing and able to finance the acquisition of regional plantation companies (RPCs). Sri Lanka's financial system is well able to provide short-term funding for working capital purposes, but the limited development of sources of long-term loan funds would have prevented investors from using any gearing to achieve an acceptable cost of funds, forcing them to rely on equity alone. In the absence of Part A's long-term credit, there would have been no such funds available, and the pace and success of privatization would have been constrained. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Privatization The project's good performance was facilitated by the flexibility allowed in the non-credit component. This enabled the project to develop activities such as the tea sector strategy study and other programs to meet the industry's evolving needs. For example, the project provided regional plantation companies (RPCs) with training equipment, although this was not envisaged during appraisal. The training equipment provided was well used and served as an incentive for the expansion of field-level training. project cycle stage: Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/plantation-reform-project
Third Road Improvement Project |  | 2004-10-15 | Significant implementation delays were caused by the complex procurement procedures of the government. Improvements in government procurement procedures and the delegation of more authority to executing agencies need to be made. The lack of institutional capacity in the executing agency (Road Development Authority) for preconstruction processes, including land acquisition and relocation of utilities, also led to delays. Even though advance action wasapproved in December 1993, this action did not alleviate delays. As in previous projects, inadequate project maintenance was noted by the PCR Mission for the existing project roads. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Procurement Capacity Development: Capacity assessment Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Roading The government has difficulty complying with covenants related to broader budget allocation for road maintenance. The inconsistent management of the executing agency (Road Development Authority) is a serious problem and inhibits decision making. Due to these factors, ADB should focus on strengthening RDA and its project implementation capability. Although the project tried to develop the lack of capacity and inexperience of the domestic private sector in road construction and engineering and related services, considerable work still needs to be done. The broader lack of maintenance issues for the sector needs to be addressed through a reform program to improve the planning, execution, and financing of road maintenance. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Program Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity building Sector Related Issues: Private sector Sector Related Issues: Roading Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-road-improvement-project
Second Power System Expansion (Sector) Project | Energy | 2004-09-15 | Implementation delays due mostly to the government's complex procurement procedures became a major concern to ADB. Procurement procedures need to be improved, and more authority should be delegated to the executing agencies. Similarly, to avoid public opposition to future projects, and the resulting delays in project implementation, involuntary resettlement should be addressed, and the affected people should be consulted, as early as possible. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Executing/Implementing agencies Project Management: Procurement Methodologies/Approaches: Consultation/Participation The executing agency (Ceylon Electricity Board or CEB) should be given greater autonomy, and electricity tariffs should be set based on commercial, not political, grounds. Ideally, an independent regulatory body should set tariffs. If this cannot be achieved, tariffs should be raised according to a predetermined schedule. project cycle stage: Design Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Policy & Reform: Public sector reform The executing agency's (Ceylon Electricity Board's) compliance with loan covenants was not satisfactory, particularly in achieving an 8% rate of return. Based on CEB's performance, achieving this rate of return will be difficult.Loan covenants on rates of return should be set realistically in view of past performance. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Loan Agreement: Covenants Project Management: Executing/Implementing agencies | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-power-system-expansion-sector-project
Southern Province Rural Development Project | Multisector | 2004-03-15 | If an environmental assessment study was done for at least one saltwater exclusion and drainage (SWED) scheme during project preparation, the SWED implementation could have been launched earlier. This project highlights the importance of preparing a technically rigorous environmental assessment early in the business process. That would allow (i) the integration of safeguards into subProject Design, (ii) the appropriation of funds, and (iii) the provision of adequate institutional support as needed. ADB's suspension of SWED works until the Central Environmental Authority (CEA) approved the technical studies demonstrates the importance of monitoring safeguard compliance during project implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Capacity Development: Capacity building Sector Related Issues: Irrigation management In terms of closure and continuity, the project and other Integrated Rural Development Projects (IRDPs) typically employ an independent project management unit to coordinate activities and budgets during implementation. Upon completion, officers and staff frequently transfer and the project civil works are delegated - often to line agencies with inadequate O&M programs and budgets. The sense of continuity, commitment, and follow-through of the IRDP are generally casualties. project cycle stage: Completion Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Management information system Project Management: Operation and maintenance Project Management: Project management Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach The Project Benefit Monitoring and Evaluation (PBME) studies were partially satisfactory. The shortcomings were not necessarily in the execution of the PBME surveys by consultants. They were due partly to (i) inadequate ADB communication of its information and evaluation needs, and (ii) a lack of guidance to the local consultants conducting the surveys. To this end, more ADB contribution and guidance to these surveys is advisable if they are to provide useful input into ADB evaluations later. project cycle stage: Feasibility, Appraisal Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Post-evaluation Project Management: Consultants Project Management: Project supervision The project has not overcome the fact that lowland agriculture in the province generally is practiced on a subsistence basis, involving uneconomic-sized farms, land tenure and labor constraints, limited access to technology and inputs, and low levels of technical know-how. The project basically focused on upgrading infrastructure facilities. A more comprehensive approach to agriculture would include improving (i) farm practice and input use, (ii) input availability and product marketing, and (iii) crop diversification. This implies a higher profile for agricultural extension, farming systems, agribusiness and marketing, and policy assessment - areas less easily addressed in an integrated rural development approach. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Extension service Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Methodologies/Approaches: Holistic approach The project's management demonstrated an ability to achieve substantial disbursements and physical outputs for the province. However, the numerous sectors, activities, and implementing agencies were spread over a large geographic area. As such, the project did not achieve the focus and synergy that might be expected for an Integrated Rural Development Project (IRDP). This geographic spread stretched project management and limited the ability to focus on strategic issues, such as capacity building in implementing agencies, strengthening O&M, and ensuring sustainability. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Disbursement Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity building Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach The requirement of 10% farmer contribution to irrigation works was an obstacle to implementation. While this rate might be workable in high-performance systems, the appropriateness must be carefully considered when applied to subsistence agriculture. An alternative proposal for the future was half pay or food for labor. Under that proposal, poor farmers would have something to bring home at the end of the day, while simultaneously contributing to the irrigation works. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Irrigation management Sector Related Issues: Rural development While the project and other Integrated Rural Development Projects (IRDPs) have achieved some increases in rural income and employment, they generally have not resulted in a self-sustaining process of income growth to break the cycle of rural poverty. The projects typically have not provided rural inhabitants with the alternative skills, resources, and employment avenues required to move to higher levels of productivity. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Crosscutting Issues/Themes: Employment Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/southern-province-rural-development-project
Fisheries Sector Project | Agriculture, Natural Resources, and Rural Development | 2003-11-14 | One reason for the delay in implementing harbor and anchorage subprojects wasthe appointment of a single local consulting firm to conduct the coastalengineering studies. During project preparation and at appraisal, localcapacity should be realistically assessed before fixing the procurement mode(which, in this case, was local competitive bidding). Alternatively, recognizing thelimitations in local capacity, implementation schedules should be more realistic. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Consultants Project Management: Procurement Capacity Development: Capacity assessment Sector Related Issues: Rural development Some facilities built through the social infrastructure subproject are notmaintained well, because funding is inadequate. To ensure the sustainability ofsuch assets, beneficiary consultation should include (a) providing awareness tothe beneficiaries of the need for periodic maintenance, and (b) obtaining the user community's commitment to the funding of operating and maintenance (O&M)costs. Selection and design of such facilities should be within the communities'capacities. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Project Management: Operation and maintenance Capacity Development: Capacity assessment Capacity Development: Ownership Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation The benefit monitoring and evaluation (BME) interim evaluation noted that the Panadura site was not suitable technically, and that political considerations played a major role in the site selection. Although subproject selection is demand-driven, technical and financial or economic viability should be the overriding consideration in investment decisions. In addition, anadequate analysis should be made of risks and the robustness of assumptions. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Risks/Risk management The financial management consultants were appointed almost 38months into the project. The systems that the consultants recommended werenot implemented properly. Project data were not readily available. Data retrieval took time and effort, and was often incomplete. Project information systems should be set up within 6 months of implementation for efficient recording anddissemination of basic information. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Monitoring & Evaluation: Data collection and management Project Management: Consultants Project Management: Management information system Policy & Reform: Information dissemination/Public awareness | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/fisheries-sector-project-0
Fourth Development Finance Loan Project |  | 2002-10-15 | Project finance-oriented eligibility criteria such as financial internal rate of return (FIRR) and economic internal rate of return (EIRR) were not appropriate for lease applicants (mainly small and medium-sized enterprises or SMEs). A simpler return measure should be used. Owing to the revolving nature of short-term advances, overdrafts, and deposits, private domestic commercial banks (PDCBs) found the cash collection and debt service coverage ratios difficult to calculate. They should only be made applicable for term loan portfolios and term deposits and borrowings. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Sector Related Issues: Industry and Trade Protected industries should not be eligible for financing under future ADB credit lines to avoid, for example, nonperforming subloans and leases in textile manufacturing under the Fourth Development Finance Loan (DFL IV). Had appropriate economic pricing been applied in economic internal rate of return (EIRR) calculation, heavily protected subprojects would have been screened out. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Sector Related Issues: Industry and Trade The participating financial institutions (PFIs) should be required to maintain a computerized system for subproject benefitmonitoring and evaluation, which would facilitate quarterly reporting to ADB and preparation by the PFIs of their own completion reports, required under the Fourth Development Finance Loan Project. Otherwise, data on subprojectswould be difficult to retrieve, especially on those funded by leases, which, being generally 3-4 years, became inactive sooner than term subloans. After certain leases were fully paid, no active files on them were maintained and the old files could not be located easily. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Design: Subprojects Project Management: Management information system The Third Development Finance Loan Project (DFL III) PCR was completed almost 3 years after the Fourth Development Finance Loan (DFL IV) was approved, which prevented ADB from reflecting on the lessons of DFL III during formulation of DFL IV. It could have given more attention and resources to setting up a monitoring system to track the progress of policy reforms and to obtain subproject and participating financial institution (PFI) data required by ADB. Budgetary or technical assistance (TA) resources could have been allocated to sustain training of PFI staff in using the subproject benefit monitoring and evaluation worksheet model and system review, and to refine the model to enhance its usefulness. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Capacity Development: Capacity building Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/fourth-development-finance-loan-project
North Western Province Water Resources Development Project | Agriculture, Natural Resources, and Rural Development, Transport, Multisector | 2002-10-15 | A high level of efficiency, efficacy, and acceptance of credit lines can be achieved through client focus and specificity of the credit arrangements. However, this requires credit arrangements both to be worked out in sufficient detail with stakeholders and to be tested. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Pilot project Maintenance issues should have been more carefully analyzed during project formulation, as these were the reason for the rehabilitation. More attention should have been given to maintenance issues during the early stages of project implementation so that innovative arrangements could have been tested and proven to ensure their acceptability and sustainability. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Operation and maintenance Methodologies/Approaches: Pilot project Success factors and risks need to be comprehensively analyzed. The project objective of crop diversification was not achieved on the intended scale. Provision of water, extension services, and roads was insufficient to achieve crop diversification under the conditions of gravity irrigation systems found in the project area. Other factors of technical andsocial complexities of water management under tank irrigation systems, traditions, and risks must also be addressed. As farmer organizations (FOs) or farmer groups must jointly decide on crop changes involving water management, group-based approaches to training and extension using FOs as facilitators would likely have been more effective. A methodology was lacking to properly identify and prioritize problems and constraints associated with the intended crop diversification. Theanalytical process of project framework preparation, in use at ADB at the time of project completion and including situation, problem, objectives, and stakeholder analysis, would have been useful. Project experience indicates that, in addition, the comprehensiveness of the analysis including the analysis of the importance and sensitivity of success factors can be ofparticular import,i.e., the relevance of key success factors and the likely importance and efficacy of each to achieve targets must be viewed together. During implementation, performance of these factors should be monitored. If required progress is not achieved, timely design changes should be made. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity building Country Context: Prioritization Sector Related Issues: Extension service Sector Related Issues: Irrigation management Sector Related Issues: Roading Sector Related Issues: Rural development The design of the institutional development component should have been based on a more thorough diagnostic study of performance gaps, which should have included an analysis of the potential role that private service providers could have played. Investments should have been based on strategic institutional development plans and limited to sustained needs. Similarly, the project's substantial training efforts could have been more effective if they had been based on a morethorough needs assessment and strategic training planning process. Earlier provision of the project's required temporary services from the private sector could have been more efficient. The technical assistance (TA) could have been more relevant and effective if its objectives and scope had been aligned with those of the project. The TA's supervision could have been more effective as well. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Private sector | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-western-province-water-resources-development-project
Selected Advisory Technical Assistance to Social Sectors | Health And Social Protection | 2001-10-31 | A TA has maximum development impact when the government (i) feels a strong need for the TA, (ii) is very clear about the desired outputs, and (iii) provides leadership during design and implementation. These conditions result in the government having a strong incentive to use the TA outputs and implement itsrecommendations. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Impact evaluation Project Management: Executing/Implementing agencies Capacity Development: Ownership Arrangements for know-how transfer should become a standard design requirement for advisory TAs to ensure that government officials will have the capacity to use the TA outputs and reduce their reliance on consultants in the long run. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Given limited resources and time, a focused TA has several advantages over one with broad coverage, providing clear insights into the key factors underlying issues identified, detailed measures for ready implementation of its recommendations, and testing of selected recommendations when appropriate. The testing, if successful, may generate strong interest within the government in favor of the TA recommendations and, therefore, enhance its sustainability. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Management: Executing/Implementing agencies Methodologies/Approaches: Pilot project Sufficient time and budget need to be allocated for the later stages of TA implementation to allow consultants not only to produce reports but also to conduct in-depth discussions with government officials on the policyimplications of their findings, develop follow-up actions, and guide the actual implementation oftheir recommendations when appropriate. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Consultants To maximize a TA's impact on policy reforms, it is necessary to select an Executing Agency that not only has the ability to facilitate the required TA activities, but also the authority to implement the TA recommendations. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Policy & Reform: Policy reforms/framework Utilization of TA outputs should receive full attention in a TA design; whenever possible and appropriate, explicit arrangements for the dissemination of TA outputs to the general public and academic institutes should become a standard design requirement for advisory TAs. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Policy & Reform: Information dissemination/Public awareness | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/selected-advisory-technical-assistance-social-sectors
Kirindi Oya Irrigation and Settlement Project | Agriculture, Natural Resources, and Rural Development | 2000-12-31 | ADB has a special responsibility in approving projects. It should ensure that the optimal investment option has been selected. It must be transparent in explaining why major changes are made at appraisal relative to feasibility study analysis and when major assumptions are revised in subsequent economic evaluations. Substantial changes should not be made to costs or benefits unless supported by rigorous analysis. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design ADB must be able to challenge underlying assumptions and require that the proposed design reflects circumstances found in the target area. It should not be hurried into making politically driven decisions. project cycle stage: Design Lesson Topics: Getting the design correct from the beginning, including institutional aspects, is a necessary condition for project success. This is particularly true because neither ADB nor a government has a specific capacity to withdraw from a project if its design proves to be flawed. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity development Good record keeping is essential for management as well as facilitating the understanding of past developments. In particular, all details of economic evaluation should be electronically stored for greater accountability and future reference. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Management information system Particularly for schemes that are planned to utilize a significant proportion of total catchment water discharge, detailed analysis of catchment hydrology is essential, both at the time of design and thereafter at regular intervals. Improved stream gauging and rainfall recording may be required to support such analysis. Irrigation development must take a conservative view of future river flows, and recognize that water demand for all purposes is likely to increase over time. Schemes that use a high proportion of predicted seasonal or annual flow are inherently risky and should usually be avoided. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Settlement schemes can be highly charged politically. Major efforts are warranted to ensure that settlers move to their allotments to promote both social development and user management of irrigation and agricultural development. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development Where irrigation schemes include areas of existing irrigation, it is important to clarify existing formal and informal water rights, and to ensure that water allocation between new and existing users is equitable. The needs of existing livestock owners must also be taken into account. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management | Project/Program Performance Evaluation Report (PPER) |  | http://www.adb.org/documents/kirindi-oya-irrigation-and-settlement-project
Second Road Improvement Project (Loan 864-SRI[SF]) | Transport | 2000-06-30 | ADB should respond quickly to resolve tendering problems so as to avoid situations such as the expiry of validity periods, which happened under the project. Where the tender rules directly and clearly address the problem, there should not be any delay on the part of ADB. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project administration Both the government and ADB should ensure that monitoring systems are established and data collected as expected at appraisal. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal The experience of both the project and ADB s previous Trunk Roads Project highlights the difficulties in establishing quarries. Such difficulties may unnecessarily delay projects or cause contractors to submit higher tender prices because of the uncertainty raised. The problem of quarry establishment has been recognized, however, and the government now attempts to identify appropriate quarry sites and seek clearances prior to the opening of tenders. project cycle stage: Feasibility Lesson Topics: Project Management: Procurement Sector Related Issues: Roading The government recently acknowledged that it is inappropriate to rely upon its own Road Construction and Development Corporation (RCDC) to undertake all road maintenance works. Such an arrangement constrains road maintenance to the capacity of RCDC, which has recently reached its limit. Alternative arrangements that include force account operations by Road Development Authority and use of private contractors are now being used. The latter conforms to the original intent of the project. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Public governance Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Private sector Sector Related Issues: Roading The lack of success in the project s capacity-building efforts highlights two lessons. The first is that the design of capacity-building interventions should be based on real needs as defined by diagnostic studies. Such a review of the needs of the private road maintenance contracting industry would reveal the importance of continuity of work and access to working finance. Secondly, appropriate policies are required to support project capacity-building initiatives. When the government changed its policy concerning the implementation of road maintenance works, an important part of the project could no longer be achieved. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Private sector Sector Related Issues: Roading Policy & Reform: Policy reforms/framework The project suffered from a lack of realism in its formulation. Institutional capacities, the time needed for tendering and contract award, and postproject maintenance were substantially overestimated, whereas local currency price contingencies were grossly underestimated. While efforts have been made to improve the contract tendering and award process, such as through ADB-financed TA, projects will still need to consider the institutional constraints and high probability of inadequate postproject maintenance. The latter is of particular importance, and until maintenance planning, decision making, and funding are improved, both the design of roads and their evaluation should be done on the basis that maintenance will be inadequate. Local currency cost increases have historically exceeded those used in project appraisal, and more realistic estimates of price contingencies are also warranted. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Local currency Modality: Technical Assistance Project Design: Appraisal Project Design: Project design Project Management: Operation and maintenance Project Management: Procurement Capacity Development: Institutional analysis Sector Related Issues: Roading When preparing detailed designs for roads, greater consideration should be given to (i) hard surfacing road shoulders to save future maintenance expenditure rather than just graveling shoulders as done under the project; (ii) constructing bridges and culverts to the full width of the roadway, including shoulders; and (iii) providing road safety during construction. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Roading | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-road-improvement-project-loan-864-srisf
Second Water Supply and Sanitation Project | Water and Other Urban Infrastructure and Services, Multisector | 2000-01-08 | 1. To some extent, project facilities were expanded and repaired at the same time, adding significant benefits to the Project. In the interests of economy and efficiency, the Project should have been designed to cover less towns and to meet at least 10 years of demand so that expansion and rehabilitation works could have been further integrated. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 2. To avoid conflicts with other water users and to secure the water source, the availability of water should have been carefully examined, and its projected use coordinated with other users at the design stage. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 3. Inaccuracies in cost estimates for rehabilitation works contributed to the cost increase. Higher contingency funds should have been provided for such works. project cycle stage: Design Lesson Topics: 4. Unaccounted for water (UFW) could not be reduced on a sustainable basis only by repairing infrastructure. Institutional, managerial, and social measures were required in tandem with the rehabilitation works. As an institutional measure, a permanent operations unit was established in National Water Supply and Drainage Board (NWSDB) to carry out the program of reducing UFW in Greater Colombo and will continue the program even after the Project. The caretaker approach was adopted as a managerial measure. Standpost societies were mobilized to enhance ownership as a social measure, and metering and maintenance facilities were improved. project cycle stage: Implementation Lesson Topics: Capacity Development: Ownership Sector Related Issues: Water resource management 5. Tariff increases were effective in decreasing the water demand of high consumption households, but not enough to substantially reduce overall water demand. Other measures, such as public awareness, should be undertaken in parallel to control water demand. project cycle stage: Implementation, Operation Lesson Topics: Sector Related Issues: Water resource management Policy & Reform: Information dissemination/Public awareness 6. Before handing over the water supply distribution systems to local authorities, the Government and National Water Supply and Drainage Board (NWSDB) should allocate enough funds and staff to support local authorities in training staff and building capacity. project cycle stage: Operation Lesson Topics: Capacity Development: Capacity building Sector Related Issues: Water resource management 7. The involvement of beneficiaries in all aspects of development, implementation, and operation and maintenance can create a sense of ownership and improve the sustainability of the Project. The success of a community-based approach depends on local hydrogeological, socio-cultural, economic, and political conditions, and the capacities of local non-government organizations and community-based organizations. Therefore, a pilot project should be implemented to examine these conditions before introducing a full-scale project. project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Ownership Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation 8. To extend services for the urban poor, connection fee on concessionary terms and low lifeline tariff should be considered. project cycle stage: Operation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-water-supply-and-sanitation-project-0
Walawe Irrigation Improvement Project (Loan 695-SRI[SF]) | Agriculture, Natural Resources, and Rural Development | 1999-12-31 | Experience with irrigation system rehabilitation indicates that a different approach to irrigation project formulation, design, implementation, and operation is necessary to avoid (i) costly cycles of repeat rehabilitation soon after completion, (ii) resulting benefit shortfalls, and (iii) lack of overall sustainability. The optimal approach is a gradual and progressive process that focuses on institutional upgrading and participation by all stakeholders. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity development Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach Institutional support for participation at the highest levels in the implementing agency is essential if participation is to be institutionalized at the farm level. In some cases, participatory approaches may be seen as a challenge to traditional implementation methods and a threat to an institution's power base. Effort, therefore, is often needed to build support for participation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Policy & Reform: Reform Methodologies/Approaches: Participatory approach Mechanisms for beneficiary participation in the design of irrigation projects should be carefully planned; tackling participatory approaches on to a project during or after implementation is less effective. The involvement of farmers from the outset of irrigation system rehabilitation is needed to promote understanding of water management issues and general ownership of the irrigation system. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Participatory approach Participatory approaches are essential if system deterioration is to be prevented or minimized. Under the current fiscal climate it is seldom possible for irrigation authorities to assume full responsibility for system maintenance. project cycle stage: Feasibility Operation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Sector Related Issues: Irrigation management Methodologies/Approaches: Participatory approach Pilot projects can help define the best approaches to develop beneficiary participation. Such approaches must be utilized rapidly or much of the skill and knowledge developed can be dissipated. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Pilot project Resistance to change is often demonstrated by smallholders. It has proved difficult to change long-established and wasteful irrigation practices. project cycle stage: Implementation Lesson Topics: The establishment of sustainable participatory management approaches is time consuming and not well-suited to short-term TA inputs. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Methodologies/Approaches: Participatory approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/walawe-irrigation-improvement-project-loan-695-srisf
Secondary Towns Power Distribution Project II (Loan 870-SRI[SF]) | Energy | 1998-10-31 | The Appraisal Report was comprehensive but contained substantive underestimates of rehabilitation requirements for meeting the project's targets, namely, reducing system losses to 10 percent while at the same time meeting load growth for the full economic life of the project. It is noted that prior to approval of the project, the scope of rehabilitation had been reduced as a result of budgetary constraints; however the original loss reduction target had been maintained. Where the achievement of project objectives is a direct function of the level of inputs, the implications of reducing the project scope should be carefully assessed. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Sector Related Issues: Energy planning/management Methodologies/Approaches: Targeting As experienced under the project, a level of resistance and public enquiry not envisaged at appraisal, hindered implementation. With projects of this type, the design should include provisions to promote public awareness of the project benefits. project cycle stage: Design Lesson Topics: Project Design: Appraisal Project Design: Project design Capacity Development: Ownership Policy & Reform: Information dissemination/Public awareness | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/secondary-towns-power-distribution-project-ii-loan-870-srisf
Impact Evaluation of Bank Assistance to the Industrial Crops and Agro-Industry Sector in Sri Lanka |  | 1996-07-31 | ADB's assistance for projects emphasized raising productivity by improving factory processing and cultivation practices, and in effect attacked symptoms rather than the cause. The modernization of tea factories improved operating efficiencies and maintained operating margins, but it did not lead to a significant expansion in national production. There remains considerable scope for improving management and production efficiencies at the present scale of operations. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Project management Sector Related Issues: Industry and Trade Policy & Reform: Policy reforms/framework The development of industries within the sector has been suppressed by inappropriate regulations and fiscal policies. Under this operating environment, the record of success of postevaluated projects relative to targets at appraisal for these projects has varied and the operating performance of the sector has lost its competitive advantage and generally remained unsatisfactory. This has pointed to a need for a more market-oriented approach and in-depth project preparation in the sector. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework While many of ADB-financed projects improved technologies and cultivation practices, these improvements could not be sustained after completion of the projects, and the concepts introduced were not sustainable once the funds for projects had been utilized. For similar reasons, the factory modernization processes were not replicated or extended. An overriding constraint on development of the sector is the macroeconomic management of the economy. The government needs to focus on policies that further enhance the mobilization of capital, reduce inflation, minimize interest costs, and ensure more responsive exchange rate adjustments. There is a need for an analysis of the institutional framework, policy environment, and ecological implications of ADB's activities. project cycle stage: Feasibility Operation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Institutional analysis Capacity Development: Technology/Technology transfer Sector Related Issues: Industry and Trade Policy & Reform: Policy reforms/framework | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-bank-assistance-industrial-crops-and-agro-industry-sector-sri-lanka
Impact Evaluation Study of Bank Assistance in the Health and Population Sector in Sri Lanka | Health | 1995-12-31 | One of the reasons for the failed promotion of fuller integration of curative and preventive services is the apparent inclination of government doctors to devote more attention to hospital work (curative service) at the expense of preventive work, which also involves field visits. Hospital work serves to keep the doctors in touch with the types of services required in private practice. Alternatives to ensure that adequate medical personnel would be available for preventive health care will have to be studied to remedy the situation. project cycle stage: Feasibility Lesson Topics: The government needs to consider alternative financing strategies for health services as the increasing demand for these has not always been matched with increasing budget allocations. Given the welfare orientation of the government in regard to social services and the traditional political climate on such a sensitive sector as health, any cost recovery attempts may require considerable efforts. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Sector Related Issues: Health and sanitation management The installation of an appropriate BME system would have improved the efficiency of health care delivery system. In particular, it would have helped to monitor not only benefits during and after project implementation but would have also ensured that relevant benchmark data by which to quantify the impact of project intervention are compiled. It would have alleviated the data collection problems often encountered in any postproject assessment caused by transfers and nonavailability of relevant government officers who were intimately connected with the project and who could have provided reliable information. project cycle stage: Implementation, Operation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Sector Related Issues: Health and sanitation management | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-study-bank-assistance-health-and-population-sector-sri-lanka
Livestock Development Project (Loan 606-SRI[SF]) | Agriculture, Natural Resources, and Rural Development | 1995-11-30 | Although not envisaged under the project, the use of private inseminators and financial incentives for inseminators in the area covered by the project demonstrates that these measures can increase significantly the effectiveness of the artificial insemination field services. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Sector Related Issues: Rural development Crossbreeding to upgrade the productivity of dairy cattle and buffalo is beneficial. Artificial insemination is acceptable to livestock owners and provides a viable mechanism for introducing exotic genetic material. project cycle stage: Feasibility Lesson Topics: The concentration on infrastructure to improve government support services, such as those for animal health, without commensurate efforts to upgrade the operating systems may not generate the expected benefits. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Extension service Sector Related Issues: Rural development The importation of live animals to establish breeding herds for production of improved animals for distribution is expensive and risky, particularly in the case of the Sahiwal, where the sources and number of stock for making a selection are limited. The importation of semen or small numbers of bulls appears preferable. project cycle stage: Feasibility Lesson Topics: Project Management: Risks/Risk management Sector Related Issues: Rural development The inclusion of an office within the management structure for the project to collect data for monitoring and evaluation does not guarantee that useful information will be collected. It may be necessary for ADB to give specific support to ensuring that the office has expertise in developing appropriate data collection and monitoring systems. The need for this assistance should be assessed at an early stage of implementation in order that data collection activities are planned, funded, and conducted. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project management The promotion of successful cooperative societies is a lengthy process, requiring a comprehensive, well-executed development program, and may not be achieved within the timeframe of a project. This is evident by the lack of cooperative spirit and inability of many of the societies to prevent mismanagement of their business. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Cluster operations Methodologies/Approaches: Holistic approach | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/livestock-development-project-loan-606-srisf
Aquaculture Development Project (Loan 648-SRI[SF]) | Agriculture, Natural Resources, and Rural Development | 1995-08-31 | If preparatory work of the PPTA consulting team is poor, it is vital that ADB give greater emphasis on providing advisory input and guidance to the PPTA team to ensure that the project design is formulated in line with ADB's and the government's strategy frameworks, and that all detailed information is adequately presented for further analysis. This is especially important in projects involving the introduction of new technologies. Frequent monitoring and supervisory missions are needed. During the initial critical years of project implementation, ADB supervision needs to identify emerging problems at a much earlier stage and to react with appropriate assistance in a more timely fashion. Another important aspect is that review missions should carefully identify implementation constraints and review the appropriateness of project design and approach to ensure maximum flexibility to meet changing circumstances during implementation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project supervision Capacity Development: Technology/Technology transfer Policy & Reform: Policy reforms/framework In case of weak BME expertise both in the executing agency and local consultant capability, project design should give greater emphasis on designing a detailed BME program to enable the executing agency to execute the program. The BME program should specify key indicators by which the achievement of project objectives and the generation of outputs and provision of inputs are to be monitored. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Indicators Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Loan covenants should identify key milestones and ways to ensure that covenants are complied with in a timely manner. In this regard, implementation activities that can adversely affect the operational performance should not be allowed to proceed unless mitigating measures have been adopted in consultation with loan consultants and ADB supervisory staff. project cycle stage: Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Project Management: Consultants Project Management: Project supervision Project delay can be caused by inappropriate site identification because of water, land and/or soil constraints. Much time can be lost in finding alternative sites. Project preparatory teams should pay greater attention to devising appropriate site selection criteria and selecting suitable sites. In devising site selection criteria and subsequent site selection, detailed information pertaining to such factors as land availability and acquisition issues, soil suitability, beneficiary participation, and socioeconomic analysis of beneficiaries living around the proposed project sites should be collected as a basis for appraisal. Land availability and acquisition issues should be fully resolved prior to loan effectivity. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Methodologies/Approaches: Consultation/Participation That weak project management was not identified as a key issue in project preparation and appraisal contributed to the delay in staff and consultants recruitment. This and the cumbersome government procedures were the major reasons for the inefficient project implementation. Ineffective ADB supervision and failure to take firmer action to overcome the weak management during the early years of implementation also contributed to the major delay in implementation. Where weaknesses are identified in the executing agency, consideration should be given to the inclusion of advisory tehnical assistance to address these needs. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Modality: Technical Assistance Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Project supervision | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/aquaculture-development-project-loan-648-srisf
Sevanagala Sugar Development Project (Loan 369-SRI[SF]) | Agriculture, Natural Resources, and Rural Development | 1995-08-31 | Projects representing complex ventures integrating field production, factory and distillery performance, and management of smallholders and estates requiring social services, all in an isolated environment, require innovative management inputs to succeed. In that connection, several tested sugar development strategies are available. That of an integrated and closely managed and controlled mode has proved to be inadequate in many countries, as smallholders are particularly difficult to direct. An alternative approach relies on market prices as incentives to smallholders. It would thus appear essential for success that development strategies be subjected to thorough scrutiny at appraisal in the same way technical parameters are generally considered. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial benefits Project Design: Appraisal Project Design: Project design Sector Related Issues: Rural development Since sugar prices have historically been low, it is a prerequisite that price projections and variability are analyzed with care in order to assess realistically the level and likelihood of risks at appraisal and regularly during implementation to reorient a project, as required. In this regard, it would be necessary to prepare likely scenarios, related action plans, and needed resources. The opportunity cost of irrigation projects in situations of competition for water should be reflected in economic analysis and in action plans throughout a project's life, since such costs can often be large relative to the benefits. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Irrigation management Where a prospective executing agency has a consistently poor record of past performance on similar projects, it is desirable to strengthen the institutional framework in conformity with the requirements of the project (through privatization, for example). project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity building | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/sevanagala-sugar-development-project-loan-369-srisf
Plantation Sector Project (Loan 712-SRI[SF]) | Agriculture, Natural Resources, and Rural Development | 1995-02-28 | It should be necessary to assess the training needs of the project staff at different levels relating to accounting, auditing, reporting, and tendering. Training should be provided during the early stage of project implementation. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Procurement Project Management: Project reporting Capacity Development: Capacity assessment Capacity Development: Capacity building Projects that involve crops of long gestation periods and have longer-term benefits should consider the long-term interests of the participants, and rigorously assess the risks involved. The project design should provide for the periodic monitoring of government interventions and the macroeconomic environment affecting production and marketing. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Rural development The design and implementation arrangements and plans for projects of the plantation sector-type dispersed throughout the country should consider the views and experience of the potential participants. In particular, where a large number of producing and processing units dispersed in the countryside are involved, the project should take a realistic view and provide for a longer implementation period. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation The plantation estates complement the smallholder sector. Projects for the two subsectors, even if processed independently, should be coordinated but responsibility for implementation can be clearly demarcated and defined. This will ensure interaction of the estate factories with the neighboring smallholders supplying green tea leaf or rubber latex to the estates for processing. In this symbiotic relationship, the estates could provide the smallholders with various services, technologies, and inputs. Such an arrangement will, inter alia, lead to estate-village integration and harmony in the plantation environment. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development The strengths and weaknesses of state agencies owning and operating commercial enterprises should be examined in depth at the time of project appraisal. Project lending to them should proceed cautiously and include specific provisions to address problems that may be identified during implementation. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Capacity Development: Capacity assessment Capacity Development: Institutional analysis To be cost-effective, suitable, and maintainable, housing and other social welfare activities should have beneficiary participation in site selection, design and cost-sharing arrangements. project cycle stage: Design, Feasibility Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/plantation-sector-project-loan-712-srisf