## Viet Nam
VIET NAM, SOCIALIST REPUBLIC OF
REPORT NAME | SECTORS | DATE | LESSONS | REPORT TYPE | REPORT RATING | LINK
Enhancing Financial Stability (Scoping): Technical Assistance Completion Report | Finance | 2015-08-01 | For TAs (technical assistance) such as this one, the project team needed to take a one ADB approach by working with staff with expertise from other regional and non-operational departments. The pool of available consultants is very small for this type of TA so the project team should have started identifying potential experts at a very early stage, even straight after formal request from the Government. ADB acceptance of the TA request should have been conditional on identification of suitable consultants. Networks with other regional central banks also need to be leveraged through other resident missions and non-operational departments such as OREI (Office of Regional Economic Integration). Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/enhancing-financial-stability-scoping-tcr
Central Region Small and Medium Towns Development Project: Completion Report | Water and Other Urban Infrastructure and Services | 2015-07-31 | Executing agencies' recruitment of consultants remains time-consuming and was the main reason for start-up delays. This problem is not specific to the project but is common in all ADB-financed projects in Viet Nam. Delays in recruiting consultants result in delay of such project activities as detailed design, resettlement planning, environmental management planning, and preparing bidding documents. The delays in bidding and contract awards caused total project costs to rise and held back delivery of the facilities to the final recipients. project cycle stage: Design, Implementation The project substantially achieved the targeted outputs despite the start-up delays caused by the prolonged process of recruiting consultants. This demonstrated that the executing agencies at provincial level have the capacity for project implementation and the decentralized approach to project preparation and implementation is appropriate. project cycle stage: Feasibility, Implementation, Operation The result of efforts to increase tariffs varies among project provinces. Some provinces showed strong commitments in implementing the reform agenda set by the project (for example, Binh Thuan, Dak Lak, and Khanh Hoa provinces). Meanwhile, other provinces were reluctant to raise the wastewater tariff and solid waste collection fee to the required levels (Ninh Thuan and Phu Yen provinces). project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/central-region-small-and-medium-towns-development-project-pcr
Upper Secondary and Professional Teacher Development Project: Completion Report | Education | 2015-06-29 | Consistency in project documents between the government and ADB. Some inconsistencies and ambitious targets between the government's feasibility study report and the RRP (Report and Recommendation of the President) required discussions and formal agreements between the MOET (Ministry of Education and Training) and ADB, resulting in delays in project implementation. At the design stage, project targets should be more realistic and attainable. Intensive consultations among stakeholders are needed to avoid such discrepancies. project cycle stage: Design, Feasibility, Implementation Capacity of project management unit staff. Limited familiarity of PMU (project management unit) staff with ADB procurement and financial management guidelines and procedures contributed to delays in implementation, procurement of equipment, awarding of contracts of civil works, and disbursement. Moreover, PMU heads were nominated and approved by the MOET (Ministry of Education and Training) only after project approval, which further contributed to delays in project start-up. For future projects, the PMU and PIUs should be established before loan approval. Moreover, once these have been established, recruitment of PMU and PIU staff with prior experience in ADB projects should be immediately undertaken. Training of PMU and PIU staff by project preparatory TA start-up consultants, and by ADB if required, must be carried out and explicitly recommended in the loan covenants. project cycle stage: Design, Implementation Recruitment of consultants. The recruitment of consultants remains time consuming. This problem is not specific to the project but common in all ADB-financed projects in Viet Nam. Delays in consultant recruitment result in delays in implementing the entire project. In future, advance actions and project readiness filters should be applied to minimize start-up delays. project cycle stage: Feasibility, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/upper-secondary-and-professional-teacher-development-pcr
Preventive Health System Support Project: Completion Report | Health | 2015-06-26 | Consideration of local government fiscal capacity. The project originally required participating provinces to provide funds to upgrade the PPMCs (provincial preventive medicine centers), including their laboratories. While local government commitment to preventive health care is significant in Viet Nam, the fiscal situation of some provinces does not allow investments of the scale that was needed. ADB needs to carefully consider the local costs of such infrastructure projects and the fiscal ability of local governments to meet them before committing to an investment. project cycle stage: Feasibility, Implementation Phased approach. Implementing the project across almost four dozen provinces and such a wide geographical area led to challenges both in providing laboratory equipment in a timely manner and in ensuring that training was provided in the use of this equipment. A phased approach prioritizing provinces with stronger technical capacities would ensure a closer link between the provision of equipment and training thus increase efficiency. project cycle stage: Design, Implementation Need for market-based remuneration. The government's cost norm is too low and not competitive. Because of this, recruiting experienced senior national consultants (with the exception of retired government employees) remains a challenge. Training allowances are also too low. This also applies to its training allowances, which discourages participation by staff who must travel from where they live and work to take part. Future projects should include a clause that allows remuneration for consultants and allowances for staff training to be market-based. project cycle stage: Design, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/preventive-health-system-support-project-pcr
Support for Public-Private Development of the O Mon Thermal Power Complex Project: Technical Assistance Completion Report | Energy | 2015-06-01 | TA's (technical assistance) outcomes were achievable only with the condition that the gas sale and purchase contract can be materialized timely. However such a condition is an external factor to the TA and also beyond the controls of the TA executing and implementing agencies. In the TA's design, the 'inability to reach an agreement with gas supply partners and obtain economic gas supply agreement' was identified as a risk to the achievement of the outcome. However risk mitigation measures were not prepared. At the time it was considered that the likelihood of reaching gas sale and purchase agreement is very high given the intensive discussions and activities among the concerned stakeholders, and O Mon I was under construction. In the future design of a TA will have to take into consideration the factors that will have influences on the intended outcomes, such as fuel supply availability and correspondingly a list of measures to mitigate those risks will have to be prepared under the TA design. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/support-public-private-development-o-mon-thermal-power-complex-project-tcr
Water Resources Development in the Mid- and Northeast Red River Delta: Technical Assistance Completion Report | Agriculture, natural resources and rural development | 2015-06-01 | A programmatic approach to these types of water infrastructure upgrading investments, based on rigorous water balance assessments, could have provided a framework for more strategic selectivity of investments. This could have been more efficient instead of appraising the design of scattered individual subprojects only to find out much later on that water availability would become constraints. The subproject scope should have gone beyond water delivery to support changes in the irrigation system, as well as modernization and diversification of agriculture, which requires increased control of water and water delivery within the irrigation schemes. These considerations earlier in the PPTA (project preparatory technical assistance) could have provided insight into how the loan design could respond to the differing water demand needs of producers within and across the command area and within the context of diversification and modernization of production systems. The PPTA process could have been better phased to carry out screening on economic viability earlier in the process. A good practice from a previous successful ADB PPTA in the water sector in Viet Nam was to field a small team of individual consultants in the early pre-feasibility phase to do the economic and technical screening of the proposed loan. Recruitment of a PPTA firm did not commence until ADB was satisfied that the project had a very strong chance of being found feasible. Having said this, the processing time pressure for TA (Technical Assistance) 7926 would have posed a challenge to using such a staggered approach. Therefore, a better balance needs to be struck between processing in a short duration and using the phased approach. Project cycle stage: Concept, Design, Implementation | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/water-resources-development-mid-and-northeast-red-river-delta-tcr
Developing the Market Readiness Proposal for a Domestic Carbon Market: Technical Assistance Completion Report | Energy | 2015-03-01 | For implementation of future similar TA (technical assistance) on country MRP (market readiness proposal) development, we propose the following recommendations: (i) a strong emphasis on sector-wide consultation and consensus building mechanism around the proposed MRP components; (ii) Identify at the TA preparation stage one single leading agency, ideally the EA (executing agency); and (iii) Include in the TA package some individual consultancy to serve as technical advisor to the EA. The introduction of a carbon finance market does not follow the one-size-fits-all principle and considering that both MPI (Ministry of Planning and Investment) and MONRE (Ministry of Natural Resources and Environment) co-led this, a key lesson learnt is that not only is continuous dialogue enough but the comments and lessons learned from their outcome had to be reflected in the revised and final version of the MRP. With the number of stakeholders involved in the preparation of the final MRP, the importance of consensus-driven decisions to assess the strength of carbon pricing policies became highly evident. However it is recommended going for similar exercise, these types of efforts should not be co-led, rather there should one overall responsible agency. Also to promote stronger government ownership, hiring individual consultants to serve as advisors to the EA is beneficial. Another important lesson learnt is that there should be only one delivery partner for ease of efficiency since having two delivery partners implies more time for consultation and consensus building. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/vie-developing-market-readiness-proposal-domestic-carbon-market-tcr
Support for the National Target Program on Climate Change with a Focus on Energy and Transport: Technical Assistance Completion Report | Energy | 2015-03-01 | In the future, project design should emphasize in scope and resources the importance of establishing a credible evidence base from the outset. This would require a greater emphasis on modelling, geographic information system, and field survey activities as well as training to technical stakeholders in simple geographic information system assessment and database management techniques. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-national-target-program-climate-change-focus-energy-and-transport-tcr
Third Financial Sector Program Loan: Program Completion Report |  | 2014-09-30 | 1. Assessment of a program's success should be based on quantitative indicators and tangible results rather than whether policy actions have been met. Whileapproval of legislation and regulations can be considered a reform in the initial phase of a program, particularly subprogram 1, subsequent programs should assess the result of the implementation of the legislation and regulations. As an illustration of this, the issuance of circulars, which was heavily relied upon as having achieved the desired outcomes under the Third Financial Sector Program Loan, does not necessarily mean that the objectives of the circulars have been met, or even that the actions required by these circulars have indeed been carried out. Circulars are merely the medium through which the desired end results are to be achieved. Measurability of end results in the form of quantitative targets (including transitional targets) would significantly improve the grey assessment areas to the benefit of both ADB and the government. [Main text, para. 43(i)] project cycle stage: Completion Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Project evaluation 10. When a reform requires adoption of international standards, then both ADB and the government should communicate with the relevant international body responsible for the adoption of those standards. Where possible, a program specifically for Viet Nam can be designed and agreed. An example of this is the adoption of international financial reporting standards in close coordination with the international accounting standards board. [Main text, para. 43(x)] project cycle stage: Design Lesson Topics: Modality: Program Project Design: Project design Policy & Reform: Reform 2. Related to the point above, the design and monitoring framework should consist of indicators agreed between ADB and the government from the outset. These indicators should either already be present in the government's strategy or blueprint or, if they are not, then they should be included and approved by the highest level of authority of a particular organization. This would strengthen government ownership and accountability. These indicators then should be measured by both ADB and the government at the end of each year of the program. When the indicators fall short, corrective measures should be agreed on and included as a reform in the following year. [Main text, para. 43(ii)] project cycle stage: Design Lesson Topics: 3. These indicators should be linked to the policy matrix, as reforms should contribute to the achievement of these indicators. When a particular reform is delayed, then additional technical assistance resources will need to be provided to address the problem. When policy actions are not completely achieved orwhen they are assessed as either satisfactory or ongoing (as in the case of the two actions for the tranche 2 release of the Third Financial Sector Program Loan), then the subsequent subprogram should immediately focus on these actions at the design stage, so that they do not fall through the cracks between subprograms or even between clusters. The post-program partnership framework is important to maintain dialogue between program clusters. While the policy matrix and the design and monitoring framework are separate documents in form, they should be connected through a cause and effect relationship. [Main text, para. 43(iii)] project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Indicators Policy & Reform: Policy matrix Policy & Reform: Reform 4. Given the challenges of coordination in Viet Nam and the financial sector generally, when a policy action requires coordination between two or more agencies, ADB and the government must first ensure that the coordination mechanism and institutional infrastructure have been established and areworking as envisioned. In the initial stage, ADB staff, including those from the Resident Mission, should participate in meetings and discussions. This is to prevent the existence of a coordination mechanism only on paper. [Main text, para. 43(iv)] project cycle stage: Implementation Lesson Topics: 5. ADB and the government need to recognize that financial sector reforms are complex, have a medium- to long-term gestation period, and require proper sequencing that follows a step-by-step approach. This is especially important when new institutions, legal and regulatory frameworks, or standards are being introduced. Such a focused and phased approach may better accommodate capacity constraints, avoid delays, and enable a more accurate measurement of outcome and impact. [Main text, para. 43(v)] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform 6. Program loans should be focused and consist of targeted high impact policy actions in a few selected areas, which cumulatively lead to the desired outcome. This will increase government ownership of the program and thus avoid delays in implementation of the reforms. [Main text, para. 43(vi)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Program Capacity Development: Ownership Policy & Reform: Reform 7. There needs to be a balance between flexibility and achievement of results. A program cluster modality has in-built flexibility, particularly when designing indicative actions such as for subprogram 2. However, this flexibility is not a carte blanche for changes and should not be used to substitute uncompleted reforms just because they are difficult to implement. When making revisions or substituting policy actions, a careful assessment should be made as to how these revisions or substitutions will affect the achievement of outputs and ultimately the outcome of the program. In the case of Third Financial Sector Program Loan, the policy actions that were reformulated during subprogram 2 should be reassessed as part of future programs. [Main text, para. 43(vii)] project cycle stage: Design Lesson Topics: Modality: Program Project Design: Project design Policy & Reform: Reform 8. Financial sector reforms must be supported by sufficient technical assistance (TA) resources. The design of financial sector TA should be undertaken in close coordination with the relevant executing and implementing agencies and aligned to their work plan. TA projects should be focused, and targeted particularly at reforms that have been substantially delayed. [Main text, para. 43(viii)] project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Project design Policy & Reform: Reform 9. For capacity building, technical assistance grants are likely to be insufficient. An ad hoc approach to training is insufficient and can be counterproductive. Instead, ADB and the government should discuss the possibility of either a project loan to support capacity building or of Ministry of Finance earmarking a portion of the program loan to fund the capacity building initiatives of a structured medium-term program through the government budget process. Given its importance, this can be considered as a policy action in the policy matrix. [Main text, para. 43(ix)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Program Modality: Project Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development Policy & Reform: Policy matrix | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/viet-nam-third-financial-sector-program-loan-pcr
Agriculture Science and Technology Project: Completion Report | Agriculture, natural resources and rural development | 2014-09-01 | Ambitious project design including diverse technical and geographic coverage combined with innovative project procedures can delay implementation until all implementing agencies fully understand the process. Competitive bidding for agricultural research based on clear selection criteria that prioritize marginal areas and are formulated jointly by researchers and extension workers can lead to more user-responsive and demand-driven research, which also can be immediately extended to poor farmers. Preliminary impacts reveal more efficient use and more equitable distribution of public research funds. Competitive bidding for extension contracts based on demand-driven proposals generated at field level through a participatory process involving the poor can have a significant impact on (a) the timeliness and transparency of decision making, (b) the variety of extension messages delivered, and (c) the number and range of institutions and organizations providing extension services. Inadequate assessment during project preparation of implementing agencies' financial and human resources capacity, especially when introducing innovative implementation mechanisms, can lead to delays in project implementation. Unrealistic estimates of the time required for students to complete PhD programs can result in having to extend the project closing date. Insufficient or inappropriate design of consulting services, and delays in recruiting them, can cause problems early in project implementation and a failure to provide adequate support for key project activities in which project management has limited experience. Requiring the collection of gender-disaggregated data for all project activities is an effective means to improve gender mainstreaming in project implementation. Monitoring of and regular reporting on the participation of indigenous people in project activities can also lead to better awareness of special measures required for indigenous people. The lack of an effective project performance monitoring system risks undermining the success of a project by failing to properly report project outputs and outcomes. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/agriculture-science-and-technology-project-pcr
Viet Nam: Vocational and Technical Education Project | Education | 2013-04-26 | 1. Management of vocational and technical education requires extensive coordination among different stakeholders. For the project, there was little collaboration and sharing of lessons among donors. There were also overlapping responsibilities for technical and professional education between the Ministry of Labor, Invalids, and Social Affairs and the Ministry of Education and Training. [Executive Summary, page iv; Main text, para. 86] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Harmonization Sector Related Issues: Education 2. Outcomes need to be integrated with the national system for them to be effectively utilized and sustained. The General Department of Vocational Training adopted the new curriculum development method and implemented it nationwide. In contrast, the labor market information system, production units at key schools, and school industry partnership have become rather inactive as sustaining these outputs requires a lot of resources. [Executive Summary, page iv; Main text, para. 87] project cycle stage: Implementation Lesson Topics: 3. Strong management capacity should be a prerequisite to project implementation. The General Department of Vocational Training (GDVT) lacked experience and capacity to effectively implement the project. The GDVT is overwhelmed with an increasing number of vocational institutions, which may explain the delay in implementing the program accreditation system and technical certification system nationwide. [Executive Summary, page iv; Main text, para. 86] project cycle stage: Implementation Lesson Topics: Project Management: Project management Capacity Development: Capacity development Sector Related Issues: Education 4. Establishing a market-driven vocational and technical education (VTE) system is a long process and requires macro-level links with industry. Public vocational institutions are still financially and strategically dependent on the government. School industry relations remain adhoc. Many of the VTE graduates obtained jobs that were not in the same field as the training they received. The percentage of nonmatching jobs ranges from 10% to 45% across years and degrees. [Executive Summary, page iv; Main text, para. 88] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: 5. The quality of vocational and technical education (VTE) can be improved with more and broader participation of students. University degrees are still preferred over VTE. Many students who enter vocational institutions are low-performing and unmotivated. At the same time, access to vocational education can be more equitable. The system attracts relatively few disadvantaged students such as women, ethnic minorities, and the poor. [Executive Summary, page iv; Main text, para. 89] project cycle stage: Implementation Lesson Topics: Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/viet-nam-vocational-and-technical-education-project
Support the Implementation of the Poverty Reduction Programs IV and V |  | 2013-02-09 | 1. A program cluster approach with prior expected actions enveloped by a medium-term framework with flexibility built into its design is an effective approach to supporting government reforms. It promotes continuous dialogue with the government on reforms and allows for program changes to effectively and efficiently respond to new or worsening risks to the economy and shifts in government policy priorities. project cycle stage: Lesson Topics: 2. The breadth of the reform undertaking and linkages among policy actions across sectors called for a comprehensive approach to dialogue and support by development partners. Several development partners withdrew or reduced their development assistance to Viet Nam, in accordance with their aid practices for middle-income countries. The number of cofinanciers peaked at 11 for Poverty Reduction Support Credits (PRSCs) 6 and 7 and has fallen since, with some impact on the total level of financing under the PRSCs. Some switched their focus to more specialized policy-based operations as deeper reforms were identified in the PRSC policy dialogue. Development partners provided additional funding for budget support while providing technical assistance to the government to support the policy dialogue in highly technical and complex areas. This dialogue, in turn, helped strengthen the institutional capacity of the ministries or agencies concerned. project cycle stage: Lesson Topics: 3. The new series of programmatic development policy lending is taking this broad lesson into account, driven by a new Socioeconomic Development Plan report (2011-2015). Though focused on two of the four pillars of the last Poverty Reduction Support Credit series, policy coordination that reflects linkages in policy areas requires a strong analytical foundation to inform directions and specific decisions. Dedicated and adequate resources for analytical work and short-term technical assistance should enable the government and its partners to assess the potential impacts of related policy actions and help refine the proposals. project cycle stage: Lesson Topics: 4. The Poverty Reduction Support Credit (PRSC) series served as an effective framework for policy dialogue and interactions between the government and donors. The PRSC exercise also served as a common forum for donors to raise concerns with the government and provided the donors with broad access to a large number of ministries and agencies. The role of cofinanciers under the PRSC evolved from providers of financing to partners engaged in policy dialogue and the preparation of operations. Information flows from the government expanded as trust with the partners deepened, which reduced the transaction costs for the government ministries and agencies. project cycle stage: Lesson Topics: 5. In Viet Nam legislation is often comprehensive but implementation weak. Implementation required close monitoring on an annual basis and ensured continued relevance to the government's reform progress. While the Poverty Reduction Support Credit operations provided financial support for implementing the whole Socioeconomic Development Plan (SEDP), they disbursed against the upfront completion of a number of specific reform measures identified within the SEDP agenda by consultation between partners and the government, led by the World Bank. Implementation was also linked to supporting government systems, including synchronized timing to feed into the formal budget cycle. Lack of understanding of the effectiveness of policy implementation makes it difficult to link the impact of policy reforms to the SEDP indicators in the design, monitoring, and framework of this program. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/support-implementation-poverty-reduction-programs-4-and-5-pcr
Central Region Transport Networks Improvement Sector Project | Transport | 2013-01-10 | 1. The consultant's undertaking preparatory work for phases 1 and 2 were not the same as the construction supervision consultant's for all three phases who were also responsible for preparing Phase 3 subprojects. The construction supervision consultant's thus did not have any responsibility for the design of subprojects under phases 1 and 2. This became an issue after the consultant's that had done the preparatory work for phases 1 and 2 had completed their contract and left Viet Nam. Changed site conditions made it impossible for the contractors to follow the approved design, and so delays occurred. To ensure continuity, only one consultant both for supervision and design should have been selected. project cycle stage: Lesson Topics: 2. It was noted at appraisal: ï¿½preparation of documentation and commencement of civil works for phases 2 and 3 will follow sequentially as individual tasks are completed under Phase 1.ï¿½ This meant that delays and changes in some subprojects in phases 1 and 2, led to delays in subsequent Phase 3 subprojects. In future, this kind of conditionality should be avoided to prevent delays in implementation. project cycle stage: Lesson Topics: 3. In Phase 3, a total of three provinces were delegated full authority to implement subprojects in their provinces. This delegation included negotiations and signing of civil works contracts, approval of variation orders, changes to technical design, and approval of payments to the contractors. The time spent in solving changes in technical design and deciding on variations was significantly reduced, much to the benefit of the project. There was a feeling of local ownership to the subprojects in the delegated provinces. Delegated authority implied increased responsibility, which effectively put pressure on the provincial project management units to solve issues fast that otherwise could hamper the progress and/or negatively affect the quality of the subprojects. Delegation to more provinces could have improved the implementation of the project and avoided some delays. ADB should consider more delegation in future similar projects if provinces have sufficient capacity to handle ADB procedures. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-region-transport-networks-improvement-sector-project-viet-nam-pcr
Central Region Water Resources Project | Agriculture, Natural Resources, and Rural Development | 2013-01-10 | 1. When policies and views diverge, constructive dialogue is often more rewarding than confrontation. When Decree 115 was promulgated by the government, it directly impacted the loan agreement. While the ADB project team could have invoked the agreement and demanded that either the decree be withdrawn or the project suspended, it chose to conduct constructive dialogue, resulting in a workable compromise. This allowed the physical completion of the project works with its associated benefits. project cycle stage: Lesson Topics: 2. Participation in key decisions can have a major impact on the ownership of policies and institutional changes. Once proposed changes to the irrigation management companies and water user groups (WUGs) had been revised to take stakeholder views into account, they were enthusiastically taken up by government agencies, local administrations, and the intended beneficiaries themselves. The degree of ownership for the revamped institutions was tangible during field visits and interviews. This type of enthusiasm can only come from a participatory approach and a willingness to take into account all points of view as well as the actual field conditions. If an attempt had been made to push through the original revisions of the WUGs, results would have been far less promising. project cycle stage: Lesson Topics: 3. One of the project's major technical problems was the appearance of cracks in the Khe Ngang reservoir dam. This serious issue could have jeopardized a significant part of the project and could also have had further safety repercussions. The problem was resolved when the Ministry of Agriculture and Rural Development, with ADB assistance, mobilized a senior engineering team to inspect the dam and come up with an acceptable and viable technical resolution. This positive and cooperative reaction by ADB allowed the works to be successfully completed with only a slight delay in the implementation schedule. project cycle stage: Lesson Topics: 4. Critical decisions on project investments must be informed, careful, and judicious. At the time of the mid-term review mission in May 2009, contract awards were 8% of the total loan amount and disbursements were 5%. On the basis of such apparent poor performance it would have been possible to cancel the loan and shut down the project at that time. However, a full analysis by the review mission indicated that delays had been caused more by procedural problems than deficiencies in the capacity of the executing agency and that implementation was at the point of finally taking off. The adoption of a comprehensive analysis of the problems facing the project and the decision to continue with implementation allowed the project to be successfully completed. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-region-water-resources-project-viet-nam-pcr
HIV/AIDS Prevention among Youth Project | Health | 2013-01-10 | 1. Evaluation of the two nongovernment organization-implemented voluntary counseling and testing services demonstrated that population mapping, coordination between government agencies and the recruitment of suitable peers improved service targeting (particularly vulnerable populations). Setting optimistic testing targets that encouraged broad-brush recruitment of clients adversely affected testing results. project cycle stage: Lesson Topics: 2. Projects should be responsive to change; as the media environment altered, the project design should have been adjusted. project cycle stage: Lesson Topics: 3. Behavioral change communication, whether through mass media or interpersonal communication, is complex and specialized, and requires specialized expertise; a chief technical adviser should be provided throughout project implementation. project cycle stage: Lesson Topics: 4. Low cost norms made it difficult to attract competent, full-time staff for the central project management unit, resulting in project delays. There is a need to ensure proper staffing of the central project management unit. project cycle stage: Lesson Topics: 5. Project delays were mostly caused by lengthy administrative processes resulting from complex ADB and government procedures. project cycle stage: Lesson Topics: 6. Project monitoring was not systematic. An indicator list was prepared during the project's early stages, but the indicators were not adjusted and routinely reported as a result of weak monitoring capacity. project cycle stage: Lesson Topics: 7. A lack of exit planning resulted in no proper plan for continuation of activities and future use of information, education, and communication materials, including websites, interpersonal communication and training materials. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/hiv-aids-prevention-among-youth-project-viet-nam-pcr
Housing Finance Project | Finance | 2013-01-10 | 1. Careful poverty analysis, a proper demand and supply analysis for housing, better selection criteria, as well as more pro-poor loan procedures and flexibility in the loan size, term, and use would have enhanced the inclusiveness and beneficial impacts of the project. Given the targeted low-income segment and limited institutional capacity, such projects should not be overly complex in design and difficult to implement. Having a variable interest rate on the loan did not help. Fixed interest rates are more appropriate and preferred by low-income and poor borrowers. The spread levied by some of the participating financial institutions (PFIs) over their borrowing rate from the State Bank of Viet Nam (Housing Finance Facility) was high. The project's capacity building component provided for development of hedging instruments to enable PFIs to offer fixed-rate housing subloans. Hedging is practically nonexistent in Viet Nam. Further, given the weak institutional capacity, consulting support should be properly phased out over the implementation period of the project. Because consulting support ceased in 2006, component C was not fully utilized. More flexible instruments and such product design innovations as graduated-payment mortgages, flexible repayment arrangements, and multipurpose loans might be considered to suit such type of borrowers. In parallel, encouraging financial discipline among low-income borrowers is also important. project cycle stage: Lesson Topics: 2. There are perceptions among some government agencies in Viet Nam that the interest rate should be much lower than market rates and be subsidized. Rather than focusing solely on the financing side, the complex issue of housing for the urban poor also needs to be looked at from the viewpoint of supply side constraints and the willingness of lenders to consider this an appropriate business line. Targeted subsidies that are separate from financing also need to be considered. Again, access to credit is more important than is providing interest rate subsidies. In every part of the developed and developing world, housing for low-income and poor people includes subsidies in some form as part of national social policy. Such schemes together with interest rate subsidies are plausible so long as the lending institutions continue to receive subsidies from the government. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/housing-finance-project-viet-nam-pcr
Second Lower Secondary Education Development Project | Education | 2013-01-10 | 1. The recruitment of consultants by executing agencies remains time-consuming. This problem is not specific to the project, but common in all ADB-financed projects in Viet Nam. Delays in consultant recruitment result in delays in implementing the entire project. In the future, advance actions and project readiness filters should be applied to minimize start-up delays. project cycle stage: Lesson Topics: 2. The procurement capacity of the executing and implementing agencies, as well as the context of the project, needs to be considered when determining procurement methods. Their procurement capacity needs to be developed in order for them to implement procurement methods and accurately follow procedures and guidelines. Tracking of project implementation becomes difficult if procurement documentation does not follow requirements. project cycle stage: Lesson Topics: 3. The design of capacity building activities needs to be better structured with a model defining how knowledge and skills will be transferred and including pre- and post-training assessments to measure impact. Without a structure, capacity building activities are reduced to the number of persons trained. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-lower-secondary-education-development-project-viet-nam-pcr
Upper Secondary Education Development Project | Education | 2013-01-10 | 1. There was some concern that the feasibility study report prepared by Ministry of Education and Training (MOET), which was the official appraisal document on the government side, was not sufficiently consistent with the report and recommendation of the President. Considerable discrepancies between the two key documents, due to limited communication between MOET and the project preparatory technical assistance (TA) consultants, were observed. As government agencies, including the state treasury, preferred to use the feasibility study report in reviewing and processing documents submitted by the national project implementation unit, the inconsistencies often hindered timely implementation. TA consultants should be formally required to work out issues with the government before submitting any report to avoid such discrepancies. project cycle stage: Lesson Topics: 2. The project could have avoided some implementation difficulties had the project manager been appointed earlier and assisted with the design of project details. Compared with the size of the project, the consultant services package was too small. The national project implementation unit (NPIU) had to take on too much of the work. While this helped in its Capacity Development, the NPIU was observed at times to have difficulty finding technically qualified staff to implement project activities that were not fully supported by the loan implementation consultants because of their limited contracts. This problem was pointed out to the government and the latter has agreed to a larger consulting service input for recently approved loan projects to ensure their timely and high-quality implementation. The NPIU must also be structured better so that suitably qualified staff are identified and appointed earlier in the process and the timing of external consulting support is better matched with project timelines. project cycle stage: Lesson Topics: 3. Positive outcomes in terms of cost and quality were associated with using market prices in cost estimates for civil works and involving local communities in the management of works. This fact was appreciated by the government, which valued ADB's flexibility in this aspect of the project's operation. Escalation of civil works costs has been a major delaying factor in numerous ADB-funded projects in Viet Nam. In this project, however, Ministry of Education and Training and ADB had agreed from the start to use market prices in the cost estimates for construction contracts, so the national project implementation unit never encountered any unexpected overrun in civil works costs. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/upper-secondary-education-development-project-viet-nam-pcr
Central Region Urban Environmental Improvement Project | Water and other urban infrastructure and services | 2013-01-04 | 1. The recruitment of consultants by executing agencies remains time-consuming. This problem is not specific to the project, but common in all ADB-financed projects in Viet Nam. Delays in consultant recruitment result in delays of the entire associated project. In the future, advance actions and project readiness filters should be applied to minimize start-up delays. project cycle stage: Lesson Topics: 2. The loan covenants required compliance with most financial covenants within a certain number of months from the loan effectiveness date. It would be better to link the achievement of such covenants to the delivery date of project assets instead of the loan effectiveness date. project cycle stage: Lesson Topics: 3. Sanitation coverage indicators should be simplified by using nominal targets rather than ratios. Monitoring of coverage ratios requires that two independent parameters - physical outputs and population growth - be known. This is complicated by the continuing growth of the service areas under the control of the concerned utilities. project cycle stage: Lesson Topics: 4. The project provided sufficient resources to implement gender-focused design features. The provision of adequate resources is critical to both successful design and effective implementation of the gender action plan. The project was an excellent example of how attention to gender equality through a comprehensive and well-targeted gender action plan can lead to practical and strategic gender equality results. project cycle stage: Lesson Topics: 5. The calculation of the economic and financial internal rates of return at appraisal should be made in a manner that facilitates their re-evaluation at project completion. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-region-urban-environmental-improvement-project-pcr
Viet Nam: Small and Medium-Sized Enterprise Development Program Cluster (Subprograms 1 and 2) | Industry and Trade | 2012-12-17 | One significant lesson is the importance of monitoring the results of reform programs even after the financial closure of the program, ensuring that the government and its various implementing agencies develop a strong sense of ownership for the reform initiatives. As pointed out in para. 19, these types of small and medium enterprise reform measures would usually take much longer time to achieve real outcomes on the ground. [Main text, para. 37] project cycle stage: Implementation Lesson Topics: Monitoring &amp; Evaluation: Monitoring and evaluation Sector Related Issues: Industry and Trade | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/viet-nam-small-and-medium-sized-enterprise-development-program-cluster-subprograms-1-and-2
Viet Nam: Agriculture Sector Development Program | Agriculture, Natural Resources, and Rural Development | 2012-12-10 | Program experience demonstrates that accompanying investment projects in a sector development program loan matter. ADB, in selecting the sector lending modality as a broad-based lending instrument, should give careful consideration to the choice of accompanying projects intrinsically linked with the sector performance in all its dimensions. In this instance, greater benefits could have accrued by linking research and extension to some of the allied institutions such as land tenure, land use, land distribution and classification, marketing, agricultural credit, more extensive extension training, and human resource development than to small and medium enterprises, which in the end focused substantially on nonagricultural activities. [Main text, para. 27] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Harmonization Modality: Lending modality | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/viet-nam-agriculture-sector-development-program
Viet Nam: Teacher Training Project | Education | 2012-12-10 | Synergies between lower secondary education (LSE) curriculum development and LSE teacher training projects are important, as the new teacher training curriculum should be consistent with the LSE curriculum. [Main text, para. 30] project cycle stage: Design Lesson Topics: Capacity Development: Capacity development Sector Related Issues: Education | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/viet-nam-teacher-training-project
Emergency Rehabilitation of Calamity Damage Project | Agriculture, natural resources and rural development, Transport | 2012-10-01 | Project start-up. A look at previous and ongoing projects implemented by the Ministry of Agriculture and Rural Development (MARD) in Viet Nam shows a common pattern: slow initial start-up accompanied by delays, slow progress, and confusion followed by an intense pace of implementation from about the midterm of the project period, followed in turn by successful completion of the project scope, often at a higher level of coverage or output than originally conceived (see for example the project completion reports or PCRs for the Rural Infrastructure Sector Project or RISP and the Second Red River Basin Sector Project). This project has followed the same pattern. The obvious lesson from this experience is that the MARD and the provincial departments of agriculture and rural development are capable of implementing medium- to large-scale rural infrastructure projects, but there are some structural or institutional factors that constrain project start-up and initial implementation. As it is likely that the MARD will continue to be an executing agency supported by ADB in the future, it would seem worthwhile to expend some effort in determining what these factors are and identifying means to overcome or mitigate them. It is noted that since the PCR was completed, an effort has been launched by the resident mission and the MARD to try to reduce start-up delays by removing constraints to the government use of ADB's advance action procedures. ADB's disaster and emergency policy. A further lesson learned or at least hinted at by the experience of implementing this project is that, given the realities of the type of investment ADB is best adapted to support in view of its funding modalities, consultant recruitment procedures, and procurement regulations (i.e., generally capital-intensive infrastructure rehabilitation) and the level of supervision possible at field level (i.e., generally less intense than bilateral agencies or United Nations organizations), ADB's current policy on disasters and emergency assistance may be too restrictive. A preparation period of only 3 months may be inadequate to allow a full damage assessment and the design of rehabilitation and remedial measures. Moreover, if the disaster is weather related, rebuilding service infrastructure without improved design standards and protection from future severe weather is likely to be a waste of effort because the rebuilt infrastructure will still be vulnerable to future floods, typhoons, or storm surges. This will entail a longer period than the 2-year implementation period currently prescribed in the policy and in the operations manual. Provincially delegated projects. For projects that entail the delegation of design and implementation to provincial authorities, it is important to ensure that provincial implementation staff are fully briefed and trained on ADB safeguard requirements such as land acquisition and resettlement. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/emergency-rehabilitation-calamity-damage-project-pcr
Ho Chi Minh City-Long Thanh-Dau Giay Expressway Technical Assistance Project | Transport | 2012-10-01 | The local governments and parties concerned should have streamlined their decision- making process in a timely manner to avoid delays. In order to avoid delays, the project should have been planned more carefully. If so, there may not have been a need to change the scope during the project implementation. International consulting firms should have obtained ample information on potential difficulties in setting up the project office and other legal requirements on such issues. They should also have been informed in advance that unless they register the project office with local authorities, the executing agency will be unable to make payments. International consulting firms should have been made aware of the appraisal and approval procedures for the design documents, particularly when appraisal is carried out by a third party. It can be a time-consuming process, thus delaying payments to the design consultants. It is advisable to start procurement of an appraisal consultant (if required) early so that he or she is ready to be recruited as soon as the design work has started. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/ho-chi-minh-city-long-thanh-dau-giay-expressway-technical-assistance-project-pcr
Northern Power Transmission Sector Project | Energy | 2012-10-01 | ADB's appraisal of Component B of the project was inadequate. This oversight eventually delayed loan closing and caused the underutilization of the ADB loan. ADB should not approve funding for projects without independent evaluation and diligent review. The transmission and substation subprojects that had not been appraised prior to loan presentation took longer to process than planned and call into question the justification for the sector loan approach. All but one subproject had been identified during implementation, and problems that could have been tackled prior to approval led to significant delays and increased administrative effort during project implementation. ADB should closely review the use of sector loans to ensure that problems that could be addressed during project preparation are not being deferred for the sake of expediency. The delegation of loan administration to the Viet Nam Resident Mission improved ADB's ability to monitor project progress by allowing for more regular and informal meetings with project management staff in order to obtain information firsthand, rather than relying on quarterly reports, which were sometimes late and/or inadequate. The parallel cofinancing of part A with Agence Franc?aise de De?veloppement (AFD) worked well. The underlying reason was AFD acceptance of ADB rules and procedures for equipment procurement, which enabled consistent processing of ADB and AFD procurement packages. The leveraging of ADB's participation greatly assisted completion of the national power sector development program and the arrangements could be used in similar circumstances elsewhere. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/northern-power-transmission-sector-project-pcr
Health Care in the Central Highlands Project | Health | 2012-03-01 | 1. The selection of adjoining provinces in the Central Highlands had several benefits. First, these provinces have a large number of poor ethnic minorities and other residents with low health status and limited access to health services. As such, these areas align with both the government's policy of supporting disadvantaged groups and ADB's overarching objectives of tackling poverty. Ethnic minorities needed continuous targeting as their health status and sociocultural adverse health behaviour warranted project interventions. Second, the selection of adjoining provinces reduced travel times and administrative overheads for project monitoring and supervision. Third, selection of these provinces avoided overlap with other major development partners in the country. On the other hand, the lack of allocative criteria led to unequitable resource distribution among the provinces, though no significant variation in performance was found, as provinces used funding according to their internal technical and absorptive capacity. project cycle stage: Lesson Topics: 2. The Joint Annual Health Review, 2010 notes that a shortage of human resources continues in several fields, including preventive medicine, public health, pediatrics, infectious diseases, mental illness, forensics, pathology, tuberculosis and leprosy, food safety and hygiene inspection, medical technology, engineers specialized in medical equipment, health statistics, and hospital management. The provincial health departments identified postgraduate training in health specializations as a major project benefit, leading to more available district staff and specializations. However, lack of staff in the project areas continues to be a major constraint for service delivery and requires future support. The Ministry of Health has developed policies and has been actively supporting methods to develop training in disadvantaged regions, including direct recruitment of students for training without entrance exams35 using specific contracts between health institutions and training facilities. project cycle stage: Lesson Topics: 3. The considerable delays in implementation were due to complicated procurement regulations of both ADB and the government. These delays and price inflation resulted in the quality of civil works being compromised in some locations and some facilities deviating from the design. Delays in equipment procurement led to the purchase of inappropriate and out-dated equipment. Limited district administrative capacity resulted in delays in imprest accounts being replenished, which constrained progress. Current government per diem allowances for training courses are very low; this limited participation. Delays in procuring consultants, especially for the Health Care Fund for the Poor, delayed disbursement. project cycle stage: Lesson Topics: 4. Investment in civil works and equipment has recurrent budget implications. Monitoring of whether provinces are allocating greater resources to recurrent budgets is difficult as financial tracking is complicated in a devolved financial management system. User fees may help support the ongoing expenditure support for buildings and equipment in the curative sector, but the preventive system has limited capacity to mobilize resources outside of the state budget. Given these constraints, future projects must have investment allocations that reflect the limited capacity for increasing recurrent expenditure, and use appropriate technology that has manageable cost implications. project cycle stage: Lesson Topics: 5. The central project management unit and provincial project management units have monitored financial flows and activity progress as part of routine quarterly reporting. Limited attention was paid to project outcomes in the project framework; outcomes were not changed during the project. Similarly, measurement of the outcomes of the training programs appears to have been limited. Given ADB's results-based approach to Project Management, both the Ministry of Health and ADB should have given a greater focus to monitoring and evaluation. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/health-care-central-highlands-project
Second Red River Basin Sector Project | Agriculture, Natural Resources, and Rural Development | 2012-03-01 | 1. Project success almost always depends on simplicity of design and it is usually counterproductive to include superfluous components no matter how much they may reflect current development thinking or theories. project cycle stage: Lesson Topics: 2. Whenever possible, project design should target contiguous or proximate project areas with similar physical and environmental characteristics. project cycle stage: Lesson Topics: 3. To the extent possible and unless necessary, it is best to avoid making the implementation of one component of a project contingent on achievements of another component. project cycle stage: Lesson Topics: 4. Pursuing long-term institutional reforms through investment projects aimed at infrastructure development needs careful design and the full ownership of the borrower. project cycle stage: Lesson Topics: 5. Shortcomings in project and technical assistance design should be identified and acted upon early in implementation to avoid undue expense and a delayed accrual of benefits. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-red-river-basin-sector-project
Rural Health Project | Health | 2011-12-01 | Priorities for health sector development. One issue with health projects in Viet Nam is that the Ministry of Health (MOH) and the provinces typically give priority to upgrading facilities and staff. Provinces may be less focused on sector reforms and improving outcomes, perhaps as this is not seen as a role of projects, and the results are less understood and tangible. Provinces need to focus more on improving the quality of services and maintaining assets. Piloting reforms. While government ownership of project formulation was strong, proposed pilots were too ambitious given MOH constraints and the lack of detailed plans or technical support. On the other hand, the project flexibly responded to several policy changes and national developments by adjusting its scope, which counterparts appreciated. Demand-led programming improved project impact. Targeting. The project improved services for the poor and had a substantial focus on maternal care but provided less targeted support for ethnic minorities. Several of the interventions for ethnic minorities didn't materialize. The project evaluation study showed that the poor in general and ethnic minorities in particular benefited from the government support for commune health stations (CHSs) and health insurance, while ADB funding provided more general public support. More could have been achieved with better targeting for minorities, assuming MOH concurrence. Lengthy administrative processes. Implementation delays were largely caused by lengthy procurement and financial control procedures at all levels. While the project management unit (PMU) and provincial project management unit (PPMU) capacity was also an issue, the government's administrative procedures were time consuming. ADB administration was considered relatively efficient. Monitoring and evaluation. Data were regularly collected, and efforts were made not to create a separate monitoring system but use existing information. However, project monitoring was incomplete and insufficiently used as a management tool to achieve results. Substantive project evaluation was very useful. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-health-project
Third Provincial Towns Water Supply and Sanitation Project | Water and other urban infrastructure and services | 2011-10-01 | Appropriate monitoring indicators are required. A project framework or design monitoring framework should list SMART (i.e., specific, measurable, acceptable, relevant and time-bound) indicators that, as much as possible, are part of the specified agenciesï¿½ established monitoring program, such as number of connections, water produced etc. Introducing new indicators should be accompanied by a strong support program because if agencies do not see the benefit of monitoring certain indicators, they will be unwilling to pay for collecting the data, such as the health indicators in this case. Indicators should be specific as to what output, outcome, and impact is being measured, when this will be done, and by whom. The lack of sufficient resources and guidance has affected the quality of the public health awareness program's (PHAP) monitoring, and the absence of specific drainage indicators prevented assessing that outcome. Water supply and sanitation coverage indicators need to be simplified. Monitoring coverage ratios requires the monitoring of two independent parameters: physical outputs and population growth. Sometimes this is complicated by a change in delineating the service area of the utilities. Nominal targets are therefore easier to monitor than ratios and are equally functional for assessing achievements. Nonrevenue water (NRW) reduction indicators need to be versified. Expressing the NRW levels in liters lost per connection per day, demonstrates a large variation in results. The best performing systems in terms of NRW ratios--NRW reduction targets are defined as the ratio of unbilled production versus total input capacity in m3/day--are not necessarily the lowest in absolute terms. To get a fundamental idea on actual performance, NRW results should at least be reported in ratios and absolute terms. Sanitation credit scheme requires an exit strategy. The project foresaw the establishment of a sanitation credit scheme, financed by the project through a grant from the central government. However, it did not address what should happen with the grant money and potential revenues once the project was completed. This lack of clarity has made Provincial Viet Nam Womenï¿½s Unions (PVWUs) reluctant to continue the program by revolving the first batch of repaid credits and expanding it to other communities outside the original project area. In all provinces, the provincial peopleï¿½s committee (PPC) issued specific orders that PVWUs are in charge of the funds. The program may be continued after loan closing and initiatives may be extended outside the original project area. PVWU experience sharing is beneficial to effective implementation. Although guidelines were provided for the sanitation revolving fund, each PVWU had the flexibility to implement it differently. Sharing of experiences, especially at the beginning stages, could have contributed to a more streamlined and effective implementation of the community environmental sanitation improvement (CESI) program. Project outcome and outputs need resource allocation. The identification and procurement of small-scale sanitation improvements was not carried out through community participation as intended, but directly by provincial project management units (PPMUs). The strong investment focus and the PPMUsï¿½ lack of knowledge about community-based approaches should have been identified as risks and mitigated by the project design through resource allocation. Likewise, the introduction and enforcement of local regulations on sanitation and environment protection was not supported by the project nor included as a covenant. Although the introduction was still achievable, enforcement would need support from the project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/third-provincial-towns-water-supply-and-sanitation-project
Provincial Roads Improvement Sector Project | Transport | 2011-01-08 | 1. The bid value of the project consultant was found to be at lower side. Road design should have been the sole responsibility of the project consultant and he should not have been subcontracted and fully passed the task on to a less experienced and capable provincial consulting firms with low subcontract value. This resulted in poor quality of surveys and detailed design works and a need to correct the design during implementation but also in substandard designs at certain locations. Inadequate payment by the project consultant to provincial consulting firm meant that the proper and necessary engineering surveys were not done at all locations. project cycle stage: Lesson Topics: 2. The views of the provinces on requirements in the road classification and design - for instance, their preference for paved shoulders over earthen shoulders to better accommodate larger, two-way traffic - should have been adequately addressed at project conceptualization and or at project design and formulation stage. project cycle stage: Lesson Topics: 3. The project encouraged the involvement of small contractors but they lacked resources and expertise and their participation should not have come at a cost in quality and delays. While their involvement in construction was required because they were familiar with local conditions, they needed proper technical and financial support. project cycle stage: Lesson Topics: 4. Repackaging the road contracts to make them larger and more financially attractive to bidders was successful and made contract management easier for the provinces. project cycle stage: Lesson Topics: 5. The executing and implementing agencies believed that implementation of the EMDP should not have been their responsibility, was outside their area of expertise, and interfered with project implementation. They said that it should have been carried out through other more suitable agencies, such provincial committees on ethnic minorities or women's unions. project cycle stage: Lesson Topics: 6. Frequent ADB missions throughout the implementation period, particularly visits to provinces, had a positive effect and facilitated timely decision making. project cycle stage: Lesson Topics: 7. The traffic projections at the project preparation stage did not anticipate that heavy vehicle traffic would greatly increase on the project roads once they were improved. The result was an inadequate design, roads not built to withstand such heavy truck use, and greater than anticipated damage to some upgraded sections where this traffic has grown. This problem should be foreseen in future similar projects and tackled during design. project cycle stage: Lesson Topics: 8. The absence of official records on land ownership made it difficult and time consuming to pay compensation to and rehabilitate people affected by the project. The PDOTs should approach the responsible local administrations well in advance of this kind of project either themselves or through specialized agencies to ensure that records are available to implement resettlement when construction begins. project cycle stage: Lesson Topics: 9. The division of projects into many phases consumes additional time and resources and causes delays in project implementation. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/provincial-roads-improvement-sector-project
Kunming-Haiphong Transport Corridor-Noi Bai-Lao Cai Highway Technical Assistance Project | Transport | 2010-11-01 | The use of a technical assistance (TA) loan for project preparation rather than including project preparation in the investment loans is fully justified because (i) it enabled project costs, revenues, and social and environmental impacts to be more accurately assessed before preparation and signing of the investment loan; and (ii) it reduced the borrower's commitment charges caused by implementation delays of 20 months. The multitranche financing facility (MFF) mode was mainstreamed into ADB's financial operations in July 2008. (The MFF was introduced in August 2005.) TA and investment loans can be combined in an MFF as separate tranches. However, use of an MFF should not be recommended for large and complex projects such as the project highway because there is high risk of project cost overrun. The estimated total cost increased from $620 million at the TA loan appraisal to $1,216 million at the investment loan appraisal. The project cost would have considerably exceeded the maximum financing amount if an MFF had been used. However, if an MFF had been used the borrower could have benefited from the flexibility in timing of ADB financing and ADB's early commitment to the investment loans without incurring the commitment charges. Senior staff of both the Vietnam Expressway Corporation (VEC) and Ministry of Transport (MOT) had significant experience in implementing large- scale road development projects. Both agencies had sufficient capacity to carry out the project, and the capacity was further enhanced through the project. The delays in resettlement planning were mainly caused by low capacity of project provinces and districts but not of the executing or implementing agencies. The project provinces and districts should be involved from the early phases of resettlement and ethnic minority development plan (REMDP) preparation. Terms of reference for the consultant should be more realistic in predicting the project period, particularly for new infrastructure projects with considerable social and resettlement impacts, and multiple works procurements. In any project implementation, it is much more efficient to identify and correct problems in the initial part of the project period. The frequency of ADB review missions in the initial phase of the project achieved this efficiency and did a great deal to prevent further delays. The lesson is to have a higher frequency of review missions in the early phase of project implementation. In a fixed-fee services contract, inclusion of the value of the project contingency in calculation of the advanced payment should be carefully explained in the request for proposals. Similarly, the regulations applied to value-added tax (VAT) duties on national subconsultancy services should be clearly stated. The status of completion should be carefully examined before loan closure. In the event that there are outstanding activities, the contractual arrangements for completion should be carefully defined and committed before loan closure. It is a risk to assume that completion can take place under another loan with an unknown time frame and be dependent on a third-party consultant. Preparation of detailed design and bidding documents for the equipment packages should not have been included in the scope of the TA loan. The employment of an independent design appraisal consultant has been expedient and has avoided delays. Consideration should be given to the inclusion of an independent appraisal consultant in future large and complex design preparation projects with an underresourced implementing agency. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/kunming-haiphong-transport-corridor-noi-bai-lao-cai-highway-technical-assistance-
Vocational and Technical Education Project | Education | 2008-12-26 | 1. An adequate project management structure should be in place before the Project starts to minimize/avoid implementation delays. A key issue was the weak delegation of management and budget responsibility to the implementing agency and project implementing unit (PIU). It proved difficult to mobilize capable project staff before project effectiveness. Initial delays in project implementation were largely caused by the inexperience of executing/implementing agencies in Project Management, in spite of the advisory technical assistance for capacity building. The executing/implementing agencies were not fully involved in project preparation and therefore faced tremendous capacity constraints once the responsibility was transferred to them. The insufficient delegation of authority to the implementing agency, as well as to the PIU, made the submission of withdrawal applications to ADB very time consuming. The initial lack of staff experienced in procurement, especially in handling bidding at the PIU and sub-PIUs at key schools, might have been another reason for these delays. [Main text, paras. 24-26, 44] project cycle stage: Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building 2. The scope of project coordination work needs to be in line with the capacity of the implementing agency. The Project was cofinanced with three agencies - AFD (Agence Francaise de Developpement), JICA (Japan International Cooperation Agency), and NDF (Nordic Development Fund) - on a parallel basis, which made project coordination difficult. The administration of key schools belonging to different ministries and provincial governments required extra coordination, compounding the complexity of project management and implementation. It would have been better to limit the number of funding agencies and government agencies to match the capacity of the implementing agency and the project implementation unit (PIU). Despite initial difficulties in coordination and managing the subprojects under cofinancing, the PIU took corrective measures such as streamlining procurement procedures under the AFD-financed project. The implementing agency, on its end, is developing a new organizational structure to better manage donor-funded projects. [Main text, para. 45] project cycle stage: Design, Implementation Lesson Topics: 3. Future projects may consider setting aside an endowment from the loan and counterpart funds from government and employers for the operation and maintenance of school equipments and facilities. Schools should also be encouraged to generate additional funds to support their recurrent activities. In the Vocational and Technical Education Project in Vietnam, the lack of funds for repair and maintenance of equipment and buildings was a common concern among schools. [Main text, paras. 13, 46] project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Funding Project Management: Operation and maintenance | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/vocational-and-technical-education-project
Teacher Training Project | Education | 2008-01-12 | The project implementation unit (PIU) could have performed better had its composition included both technical and academic experts to effectively manage the logistics and establish a solid implementation framework and had there been information sharing from the project management unit of the project preparatory techical assistance. The project completion report of the Teacher Training Project in Viet Nam noted the PIU's weak implementation capacity due to its members' lack of involvement in designing the project and limited experience in project management. [Main text, paras. 57, 75(i,iv)] project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management When loan projects do not include advisory technical assistance projects for project implementation unit (PIU) capacity building, having a full-time, qualified staff for key positions (i.e., full-time project manager, financial and procurement unit heads) can facilitate implementation of project activities. The project's self- assessment has indicated the lack of full time qualified staff that contributed to its slow progress during the first half of the implementation period. [Main text, paras. 58, 75(ii)] project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/teacher-training-project
Lower Secondary Education Development Project |  | 2007-11-23 | The improvement of lower secondary education quality involves several factors. Teachers require time and support to change teaching methods. The textbook replacement training has caused some teachers (especially those in the remote and ethnic minority areas) to improve their knowledge and skills in teaching aids and equipment. Modern teaching methods require greater access to learning resources than traditional methods. The methods of student assessment need to be adapted to the new curriculum and teaching methods. The quality improvement process therefore requires efforts from both students and teachers and it takes longer - beyond the project period. In order to deliver the outputs and attain the outcomes, together with improved school facilities, it is important to increase the number of teachers from ethnic minority background and improve the quality of teachers through annual in-service training or refresher courses. The Project created a student-friendly learning environment and it encouraged the participation of the community in building more classrooms and school facilities. It became an example of socialization of education. ADB support plays a catalyst role in mobilizing funds from the community for the education of their children. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/lower-secondary-education-development-project
Second Provincial Towns Water Supply and Sanitation Project |  | 2006-12-15 | Advance action for land acquisition and resettlement should be required, as consultation and agreements with affected households can take a very long time. project cycle stage: Concept Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Methodologies/Approaches: Consultation/Participation Each procurement package should be established in such size that bidding will be competitive among qualified contractors, while also trying to minimize the number of contract packages to lessen the executing agency's workload for controlling contractors and suppliers. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Engaging two teams of consultants to manage implementation of a project is ineffective, even if project sites are geographically spread, as staffing will be duplicated in some positions (including that of team leader). project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Project management Capacity Development: Human resources management The consultants, including foreign experts, should be retained until the entire system is in operation and commissioning tests have been completed so that they will be held responsible for assessing the final outcome, including the quality of works, and for proposing corrective measures for defective works or shortages, if any. project cycle stage: Implementation, Completion Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants The project implementation schedule should be established taking fully into account the government's approval procedures that require approval of higher authorities for feasibility studies, project budgets, the bid plan, bidding documents, bid evaluation, and contract awards. At the time of project preparation, delegation of approval authorities for critical activities to the lower levels should be discussed and agreed. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project management Country Context: Decentralization The water supply companies (WSCs) that will be the end users of completed project facilities and responsible for repayment of the loan should be party to the contracts with contractors, such that the WSCs and provincial project implementation offices (PPIOs) are authorized to supervise or control the performance of the contractors and suppliers. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project management Project Management: Project supervision Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management Training workshops prior to project implementation are needed to familiarize staff of project implementation offices at local level with ADB procedures for selecting consultants, procurement, and disbursement. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Project Management: Consultants Project Management: Procurement Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-provincial-towns-water-supply-and-sanitation-project
Rural Infrastructure Sector |  | 2006-09-15 | 1. Collaboration among development partners through harmonization of processes and utilization of comparative advantages helped develop a comprehensive, strategic, and attainable reform agenda. The identification and sequencing of a comprehensive reform agenda covering a medium-term period requires strong analytical support. In Viet Nam's Poverty Reduction Support Credit (PRSC) program, this support was effectively provided by development partners in consultation with the government and relevant stakeholders (i.e., as evident, among others, in the joint analysis to identify appropriate policy actions and implementation arrangements for the first 5-year PRSC cycle and comprehensive analytical reports covering the three pillars of the Comprehensive Poverty Reduction and Growth Strategy such as the annual Vietnamese Development Reports). [Main text, paras. 7, 40] project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Harmonization Crosscutting Issues/Themes: Poverty reduction Modality: Program Modality: Technical Assistance Policy & Reform: Reform 2. The comprehensive nature of the Poverty Reduction Support Credit (PRSC) process led to a common realization among all stakeholders that progress in different sectors and among different measures within one reform agenda would be uneven. Under the commonly agreed comprehensive PRSC framework, development partners and policymakers have to harmonize their project process to identify and address those development areas requiring special attention. [Main text, para. 41] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Policy & Reform: Reform 3. The increasingly broad scope of the policy dialogue raises logistical challenges to the process hence requiring effective coordination mechanisms. Effective coordination mechanisms have continuously evolved over time in order for operations to be delivered on an annual basis. A high level of coordination and communication were required at various levels: among development partners, among government agencies, and between development partners and government agencies. Given the comprehensive nature of the reform process and the ever-growing number of cofinanciers, it became necessary to establish a unit responsible for coordination activities, to deal with the program agenda, including monitoring and reporting, awareness raising, capacity building and reform outcome dissemination. [Main text, paras. 25-27, 42] project cycle stage: Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Modality: Program Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Design: Project design Capacity Development: Capacity building Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy matrix Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation 4. Alignment of annual multisector programs (i.e., Poverty Reduction Support Credit or PRSC which outline development partners' framework) with the government's broader, medium-term socioeconomic development plan (SEDP) facilitates reform implementation and achievement of development goals. In Vietnam, this process required close donor coordination and common dialogue with the government focusing on the sequencing and timing of policy measures, instead of the policy measures themselves. By moving away from formal conditionality, PRSC operations became a tool for supporting the government in achieving its stated development goals and implementing its reform program. This coordinated approach reduced the transaction cost of both the government and development partners and enabled the latter to focus on their respective areas of expertise and comparative advantage. [Main text, para. 43] project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Alignment Crosscutting Issues/Themes: Harmonization Crosscutting Issues/Themes: Poverty reduction Modality: Program Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework 5. Program implementation would have been more efficient had the government's Comprehensive Poverty Reduction and Growth Strategy (CPRGS) and socioeconomic development plan (SEDP) been unified, as this would have eliminated the need for a dual reporting, monitoring, and implementing systems for the CPRGS and SEDP. The CPRGS was instead prepared in parallel to the SEDP 2001-2005, as the action plan to achieve development outcomes envisaged in the SEDP. The existence of CPRGS in parallel to the SEDP proved to be less efficient, as double reporting and monitoring tracks were unavoidable. [Main text, paras. 4, 44] project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting 6. Future poverty reduction support credit projects (Poverty Reduction Support Credit) may require exploring a new lending modality more suited to the nature of the PRSC framework. The Support to the Implementation of Poverty Reduction Program (SIPRP) was processed using an innovative lending modality that departed from conventional conditionality-type program loans. The SIPRP followed a program-based approach that was designed to be disbursed in a single tranche. The loan was disbursed upon loan effectiveness, because the SIPRP was formulated based on actual performance or prior actions that were complied with. Although it was a single-tranche program, the SIPRP was in fact part of a continuum multiple-tranche program loan, with emphasis on the feasibility of policy measures. The SIPRP design faced unavoidable challenges as it had to be classified under the existing lending modalities. [Main text, paras. 3, 45] project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Disbursement Loan Agreement: Covenants Modality: Lending modality Modality: Program Policy & Reform: Policy reforms/framework Methodologies/Approaches: Program Approach 7. The Resident Mission (RM) needs to be adequately resourced, both in terms of both personnel and financial resources, to ensure the quality of country coordination, dialogue, and research. Both the processing and implementation of intensive policy dialogue and coordination were most appropriately undertaken by ADB's Resident Mission. The coordination process could not be achieved through occasional missions from headquarters. The internal coordination and communication among ADB staff of the headquarters and of the RM are also important. As program (Poverty Reduction Support Credit or PRSC) operations are comprehensive in nature, the program officer will require input from all relevant sector specialists, and at times, consultants. [Main text, paras. 28, 47] project cycle stage: Design, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Project Management: Consultants Capacity Development: Human resources management Other: Resident Mission Policy & Reform: Policy matrix Methodologies/Approaches: Consultation/Participation 8. The Poverty Reduction Support Credit (PRSC) process is comprehensive and policy-oriented, without explicit technical assistance projects attached to a series of program loans. The Support to Implementation of Poverty Reduction Programs (SIPRPs) complement, rather than replace, other ADB initiatives, including sector-specific program loans, technical assistance projects, and sector-specific projects. Technical assistance from specialists based in ADB headquarters is important if ADB is to achieve maximum leverage in its sectoral operations in Viet Nam. In difficult areas of reform (e.g. banking and SOE reforms), however, there is a need to engage in analytical work beyond the conventional scope of the PRSC framework, and to engage influential local think-tanks or research institutions in in-depth studies, with the findings disseminated to decision makers. Ensuring that the PRSC process is integrated with other processes, such as projects, programs, and technical assistance undertakings supported by specific development partners, is therefore critical for achieving targeted development outcomes. The PRSC inputs to reform areas that are lagging therefore call for a concomitant involvement of sector or thematic specialists in such areas. [Main text, para. 48] project cycle stage: Design, Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Modality: Program Modality: Technical Assistance Policy & Reform: Policy reforms/framework Methodologies/Approaches: Holistic approach 9. Streamlining partnership group coordination by sector would improve the efficiency and effectiveness of donor harmonization efforts. There have been overlapping aid harmonization groups in Vietnam with multiple coordination groups by sector. For example, there are more than 20 sector-specific partnership groups that monitor Comprehensive Poverty Reduction and Growth Strategy (CPRGS) implementation, one of which is the partnership group of aid effectiveness (PGAE). Under PGAE, sector-specific subgroups duplicate the sector work carried out by some of the 20 PGAE-level partnership groups. There are also separate sector-specific groups within Poverty Reduction Support Credit (PRSC) operations. [Main text, para. 49] project cycle stage: Design, Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Capacity Development: Partnerships Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-infrastructure-sector
Support to Implementation of Poverty Reduction Program | Public Sector Management | 2006-09-15 | Advance recruitment of consultants can improve operational procedures and overall efficiency. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Procurement Capacity building is best affected by combining formal training and learning-by-doing in the presence of effective support from the central level. Further capacity building in construction monitoring and supervision is required to maintain the high quality of works. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project supervision Capacity Development: Capacity building Capacity building should be extended to public servants and private sector consultants when a project activity makes extensive use of outsourcing. Local consultant skills in the areas of social assessment, initial environmental assessments, and economic and financial analyses need to be further developed. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Private sector Counterpart contributions are difficult to collect in situations where a wide range of beneficiaries not necessarily from within the immediate impact area share project benefits. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design Flexibility in applying unit cost ranges is needed to accommodate situations where unit costs vary widely and depend on local conditions. project cycle stage: Implementation Lesson Topics: Implementation across several provinces (23 provinces) diminishes the support that a reasonably resourced central project management unit (CPMU) can realistically provide. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Project management Project procedural guidelines should be provided early during implementation and are particularly important where project management capacities are limited. project cycle stage: Implementation Lesson Topics: Project Management: Project administration Project Management: Project management Staff assigned to provincial project management unit (PPMUs) need to be seconded on a full-time basis, especially financial management and accounting personnel. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/support-implementation-poverty-reduction-program
Central and Southern Viet Nam Power Distribution Project Completion Report |  | 2006-07-14 | Both implementing agencies (power companies or PCs) significantly revised some targets in the project components. However, ADB staff who conducted six review missions (between 1999 and 2004) never updated the framework in their back-to-office reports (BTOR) and in the project performance report (PPR). The progress of each target in the framework was not properly monitored. Consequently, ADB and both PCs used different indicators in monitoring the project's progress. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Sector Related Issues: Energy planning/management Methodologies/Approaches: Targeting Lack of coordination between urban planning and the electricity network rehabilitation and extension also contributed to delays. For example, local authorities required changes in transmission line routes after changes in urban plans, even after the issuance of construction authorization and the near completion of pole foundations. These delays could have been avoided if the rehabilitation of the electricity distribution had been undertaken in parallel with urban planning. Lack of a standard national policy about the type of equipment to be installed on national networks proved a source of significant delay. Numerous technical specifications were drafted, corrected, amended, cancelled, and redrafted to satisfy many different designers. There were also numerous revisions to the detailed designs and delays in finalizing cost estimates and bills of quantity. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Sector Related Issues: Energy planning/management Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation More flexibility with regard to project scope is needed. In the case of the project, it could have been expanded to include additional cities to utilize loan savings had it been structured as a sector project. However, this was not an option during project preparation because of the difficulties involved with finalizing the feasibility studies/technical designs for additional towns/cities in a timely manner. It was also noted that some of the delays could have been avoided had the approval process for technical designs and the bidding documents been more streamlined. The procurement documents had to be approved by many layers at the implementing, executing and Borrower levels. project cycle stage: Implementation Lesson Topics: Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Energy planning/management Methodologies/Approaches: Sectoral approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-and-southern-viet-nam-power-distribution-project-completion-report
Power Distribution Rehabilitation Project | Energy | 2005-02-15 | Although the project implementation consultant (IC) finished working when the project was only 75% complete, the remaining work went ahead without the IC's involvement, with no apparent detrimental impact on the project's effectiveness. The utilities technical group had been, for some time, in the business of designing expansions to their medium-voltage and low-voltage systems, selecting construction contractors and implementing the work. The group picked up quickly on the improved standards of design for the systems introduced to them by the consultants. The effectiveness of the consultants apparently ended when the designs of the 110 kV (transmission lines and 110/medium-voltage substations) were complete and when procurement of the equipment and material for the project was complete. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement Sector Related Issues: Energy planning/management It is necessary to allow sufficient flexibility in the project design to cope with unforeseen circumstances. Significant aspects of the environment within which the project had to be implemented changed during the course of the project. Such aspects as the establishment of Electricity of Viet Nam (EVN) in 1995, revision of PC 1's (executing agency's) role with the presence of EVN, and the decision to remove Hanoi Power Company (HPC) and Hai Phong Power Company (HPPC) from PC 1 complicated and encumbered the approval process in a way that was not fully appreciated at the outset of the project. The difficulties with the compensation and resettlement aspects of the project were also not foreseen. These led to a significant delay in implementation. The unprecedented load growth in certain areas and the rapid urban development not foreseen at the design stage also affected the project implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Sector Related Issues: Energy planning/management Sector Related Issues: Urban sector/development Future projects should incorporate some form of amortization of up-front costs over a 12-month period (as in the Northern Area Rural Power Distribution Project in 2003). The cost of connection to the electric system for rural households was too high (ranged from $80-100) and resulted in fewer connections than envisaged at appraisal. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Sector Related Issues: Energy planning/management Sector Related Issues: Rural development If loan covenants are to be set, they need to be set realistically and on the basis of past performance. The executing agency could not comply with any of its financial loan covenants until the fifth year of project implementation. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Management: Executing/Implementing agencies Implementation delays could have been avoided if the executing agency and the consultants were familiar with ADB procurement procedures. Particularly, by using ADB's advance procurement procedures on recruitment of consultants, the executing agency and consultants can commence survey and design work soon after loan effectiveness, which could reduce the front-end period substantially. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-distribution-rehabilitation-project
State-Owned Enterprise Reform and Corporate Governance Program |  | 2004-12-15 | Clear understanding of the program by all stakeholders was essential. Successful and timely implementation of the policy decisions depended on the government's understanding and acceptance of the perspectives and approach that ADB envisioned under each condition. Program implementation showed that miscommunication and misinterpretation of the design and expected outputs of policy actions could delay implementation. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Modality: Program Project Design: Project design Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy matrix Program implementation reinforced the notion that the expected impact of a program loan is long term, particularly when the program scope and objectives are as broad and ambitious as that of the State-Owned Enterprise Reform and Corporate Governance Program. In Viet Nam, policy reform involves substantial learning and capacity building. It is difficult to predict the length of this process. Due to the large program scope, most policy actions were in areas over which the executing agency (State Bank of Vietnam) had no direct control. Therefore, the program depended highly on the performance of implementing agencies. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Capacity building Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform State-owned enterprise (SOE) restructuring is a sensitive area that requires political and institutional consensus on reform values, as well as acceptance of the resulting changes. Commitment from the government agencies in charge and SOEs themselves was necessary. SOEs' accurate understanding and acceptance of those policy decisions was critical to the program's success, particularly in Viet Nam, where SOEs continue the traditional domination in the industrial sector. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Industry and Trade Policy & Reform: Policy matrix Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/state-owned-enterprise-reform-and-corporate-governance-program
Population and Family Health Project | Health | 2004-11-15 | Cofinanciers should harmonize their requirements in advance, to the extent possible. project cycle stage: Appraisal Lesson Topics: Project design would have benefited from more preparatory sector work, including updated information on key indicators and detailed understanding of issues at field level. This would have allowed the planning of second generation reproductive health (RH) activities upfront. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Indicators Project Design: Project design Sector Related Issues: Health and sanitation management Project impact cannot be assumed based on a broad design, reflecting all major elements of the health system. Rather, it depends on participatory planning and strategy adjustments based on changes in health behavior and quality of care. The National Committee for Population and Family Planning (NCPFP) demonstrated flexibility to adjust the project as required. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management Methodologies/Approaches: Participatory approach The construction and maintenance of health centers was much better in locations where communities participated strongly. Communities should be involved in the planning of health centers, and agree with the authorities on the maintenance of the facility. The issue of medical waste should be addressed early in project preparation, included in loan covenants, and followed up during reviews. Health projects should provide clear guidelines, regular inspection,staff training, and community involvement for the handling of medical waste. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Methodologies/Approaches: Community approach The management structure made establishing a link to field performance difficult. However, the project demonstrated valuable lessons for good Project Management, including clear assignment of responsibilities, intensive coordination, and flexibility in implementation. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/population-and-family-health-project
Fisheries Infrastructure Improvement Project | Agriculture, Natural Resources, and Rural Development | 2004-10-15 | Covenants should be relevant and easy to implement in a localcontext. The Loan Agreement contained some ambitious covenants that couldnot be implemented. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Design should cater to future growth in demand, including phaseddevelopment, if necessary. Port design should be undertaken in discussion withintended users. Provisions should be made for small fishers, to the extentpermitted by efficient port operation. Equipment requirements should be moreclosely analyzed and related to specific needs. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Transport planning Methodologies/Approaches: Consultation/Participation Fisheries infrastructure projects need to ensure thatadequate processes are in place or established to monitor fisheries resourcestatus and exploitation. The project did endeavor to do this through establishingenvironment and resource management units (ERMUs), but this aspect of the project was modified due to the existence of aparallel project that, however, has not yet provided adequate data. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Rural development Sector Related Issues: Transport planning Fully effective waste management systems should beintegral to modern fishing port design. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Sector Related Issues: Transport planning Port selection should be based on detailed analysis of demand. Anadequate feasibility study on an individual port would, at the least, examine portrequirements over time, consider options, and assess economic and financialperformance. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Transport planning The difficulty of effecting change needs to be accountedfor in project design. At present, the provincial authorities do not appear to havemuch interest in introducing modern port management systems. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity development Sector Related Issues: Transport planning Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/fisheries-infrastructure-improvement-project
Ho Chi Minh City Water Supply and Sanitation Project | Water and Other Urban Infrastructure and Services | 2004-07-15 | Bidding documents specifications should be explicit, with provision of specific values and quantities that the contractors shall follow, to facilitate the authority to supervise the works. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Procurement Project Management: Project supervision Government project staff members should be given training prior to the implementation of a project, to familiarize them with various ADB guidelines and procedures for project implementation. project cycle stage: Design Lesson Topics: Project Management: Project administration Capacity Development: Capacity building Capacity Development: Human resources management Project implementation periods should be carefully examined and determined during appraisal, taking into account government regulations for preparation of detailed design and bidding, bid evaluation, and scope changes. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Procurement Qualified consulting firm and staff member selection are the keys for successful project implementation, and high priority should be given to the selection of consultants who are familiar with local rules and regulations related to project implementation. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Project administration Country Context: Prioritization Unaccounted for water (UFW) projection at 30% by December 1998, covenanted in the Loan Agreement, was too ambitious, given the increased water pressure after the project and the limited inputs to the improvement of distribution networks (rehabilitation of 65 kilometers of pipelines against a total length of over 1,800 kilometers). project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/ho-chi-minh-city-water-supply-and-sanitation-project
Irrigation and Flood Protection Rehabilitation Project | Agriculture, Natural Resources, and Rural Development | 2004-07-15 | Greater attention needs to be given to project preparation. ADB should have ensured, before loan approval, that the executing agency's implementation procedures were compatible with ADB's and that probable sources of delay were eliminated through mutual agreement. ADB also missed an excellent opportunity to provide capacity-building technical assistance (TA) to the executing agency. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Capacity Development: Capacity building Loan savings use, to carry out flood damage repairs in subprojects outside the originalproject area, was not cost-effective. The irrigation extension subprojects did not have clearobjectives or adequate needs and options assessments, and their selection criteria were notsufficiently rigorous to eliminate unsuitable schemes or works. These subprojects areconsidered unsuccessful, and they detract from the project's otherwise successful rating. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Design: Subprojects Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Many project implementation delays and performance-related difficulties can be tracedto the executing agency's lack of familiarity with ADB's project implementation guidelines and procedures. TheEA's need for capacity building should have been more carefully examined during projectpreparation, and appropriate technical assistance (TA) should have been included to complement physical works.Central Project Office's (CPO's) implementing capacity is limited, due to its low status within the executing agency (Ministry of Agriculture and Rural Development or MARD). CPO's role and status should therefore be strengthened, and CPO should be more effectively integrated into MARD. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Capacity Development: Capacity building O&M continues to be less than that needed to ensure the schemes' integrity. Irrigation management companies (IMCs)retained the practice of not providing maintenance to new infrastructure for a period of 3-5 years, thus setting the stage for ongoing cycles of capital reinvestment that water user fees do not cover. Currently, water fees pay for routine O&M but do not provide reserves for capital reinvestment. IMCs showed themselves to be effective implementers, but their capacity tomanage irrigation systems should be strengthened in all future projects. Most IMCs do not have O&M or business plans on which water fees and scheme performance can be based. A need also exists for greater accountability within IMCs for scheme performance. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Irrigation management The amount for resettlement required under the project far exceeded the appraisalestimate. Although the executing agency managed to resettle most affected people and compensate thosewho lost assets in a manner that increased well-being and produced little discontent, the lack ofa resettlement plan caused significant delays and increased counterpart fund requirements. Inaddition, project-gained experience was not applied to the irrigation extension subprojects.Resettlement planning should be integral to project preparation, including that for projectextensions. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Sector Related Issues: Irrigation management The executing agency did not understand the potential value of effective Benefit Monitoring and Evaluation (BME), and monitoring and evaluation during implementation were therefore sporadic. At project completion, no permanentBME unit existed for Hanoi dike or the irrigation subprojects. All future projects should give closeattention to establishing effective monitoring and evaluation functions, and making thesefunctions consistent with the Project Performance Management System and operational prior tocommencement of any construction activities. Attention should also be paid to the terms ofreference for monitoring and evaluation, to ensure that control areas are included and that theseare consistent with project-impacted areas. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Executing/Implementing agencies Sector Related Issues: Irrigation management The predominantly engineering approach failed to address constraints facing waterusers in irrigated agriculture. A wider systems approach that builds water user and water resource institution involvement would provide a more complete project formulation that is capable of achieving the stated goals. Future projects should include more effective involvement of primary stakeholders [farmer beneficiaries, water management groups, and irrigation (and drainage) management companies] in project design. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation The relief wells for the Hanoi dike subproject were a completely new technique in VietNam, and their design should have been based on detailed geological investigations carried outas part of project preparation. The technical difficulties, however, proved too challenging forsome local contractors. As a result, the number of installed relief wells fell short ofspecifications, and some wells have low efficiency. When new technical solutions areintroduced, greater care is needed to engage suitably qualified and experienced consultantsand contractors. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Design: Subprojects Project Management: Consultants Project Management: Procurement Capacity Development: Technology/Technology transfer Sector Related Issues: Irrigation management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/irrigation-and-flood-protection-rehabilitation-project
Second Road Improvement Project | Transport | 2003-11-14 | Many roads under the rural road component (RRC) did not meet the assumption at appraisal that they carry littletraffic. A tight budget also imposed limitations on the rehabilitation cost per kilometer, leading tounderdesigned rehabilitation work on some roads. The selection procedure should either haveensured selection of roads with low traffic volumes, or some of the excess funds should havebeen reallocated to the RRC to enable higher standards on roads with heavy traffic. Thereshould have been more interaction between ADB, the executing agency, and the consultant torespond to changing circumstances. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation Significant savings were realized in the course of project implementation, primarilybecause local contractors undertook construction rather than international contractors as wasexpected at appraisal. The savings enabled realization of additional project components thathad previously been abandoned for budgetary reasons. This has significantly improved theproject and contributes to long-term sustainability. The lesson learned is that flexibility isimportant during project implementation to ensure that opportunities for improvement can beseized. A flexible approach to unit cost constraints on the rural roads component (RRC) would have improved thesustainability of rural roads with heavy traffic. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Project Management: Procurement Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Process approach Small local contractors worked on the rural roads. Although these contractors hadtrouble finishing work on time, and required close supervision from Project Management Unit (PMU)-1 and the supervisionconsultant, the outcome was generally satisfactory. The lesson learned is that untested localcontractors can perform adequately, but ample time must be given to allow for the steeplearning curve and the many constraints facing such contractors. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project supervision Sector Related Issues: Roading Sector Related Issues: Rural development Viet Nam's bid evaluation process is complicated and time-consuming. For contracts above a certain size, the evaluationhas to be approved by the Ministry of Planning and Investment, and finally by the Prime Minister. The usage of advance procurement ensured that the contract with the supervision consultant and the four initial civil works contracts for the national highway component (NHC) were signed within 5 months of loan effectiveness, causing no major delays to implementation. Although initial project approval was lengthy, the executing agency acted swiftly thereafter, as seen in the floating of contracts for various project extensions. Until the systemic causes for initial delay are overcome, advanceprocurement action should always be considered for projects in Viet Nam. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/second-road-improvement-project-0
Rural Credit Project | Finance | 2003-09-15 | Institutional and policy reforms will be more effectively implemented if agreement between the implementing agencies (Vietnam Bank for Agriculture and Rural Development and Central Credit Fund) and the government is obtained at the start of the project. A time-bound action plan for implementing these reforms should be clearly described and agreed to, and the actions should be conditions for disbursement of the loan funds. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Loan Agreement: Covenants Project Management: Executing/Implementing agencies Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation Subject to appropriate loan appraisal and processing, there should be areasonable ceiling on the size of individual loans. It is impractical tospecify a subloan size of ï¿½up to $100ï¿½ for poor members. Also, specifying thatsubloans by People's Credit Funds (PCFs) should be short-term is inappropriate, as the objective is tofoster investment that would promote development. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Subprojects The amount of the imprest fund to be established under the loan should bespecified for each executing agency and the use of the fund should includefinancing of subloans. The ultimate objective of the imprest fund is to providequick access to funds for financing eligible expenditures. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Project Design: Subprojects Project Management: Executing/Implementing agencies The application of commercial interest on relending for noncredit components(i.e., strengthening of financial institutions), discouraged the People's Credit Funds (PCFs) from using the funds for institutional strengthening. Soft components such as training and software development should be provided at a concessional rate. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-credit-project-0
Saigon Port Project (Loan 1354-VIE[SF]) | Transport | 2003-03-31 | Developing member countries still in the nascent stages of administering ADB projects would benefit from more proactive project monitoring by ADB, strengthened particularly at the resident mission level. project cycle stage: Implementation Lesson Topics: Monitoring &amp; Evaluation: Monitoring and evaluation Project Management: Project administration Capacity Development: Capacity building Other: Resident Mission The approach of separating business planning from strategic development functions in the port sector adopted by the government, may also be appropriate for ADB's other developing member countries. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/saigon-port-project-loan-1354-vie-sf
Red River Delta Water Resources Sector Project | Agriculture, Natural Resources, and Rural Development | 2002-12-13 | Although the project's Benefit Monitoring and Evaluation (BME) program is being implemented successfully, it highlights (i) the desirability of commencing BME at an early stage of project implementation, (ii) the needto monitor control areas as well as benefiting areas, and (iii) the desirability of maximizing theuse of secondary data. It is important for future projects that BME is not seen as an end in itself,but rather as a valuable tool which can feed into the management of existing, and the design ofnew, subprojects. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Design: Project design Project Design: Subprojects Project Management: Project management For future projects, project planning should be based on a river basin development approach. It should also be undertaken within an overall system context and should address key constraints in an integrated manner. While the design of the project did not place any particular limit on the scale of subproject investments, in practice, central project office (CPO) and the design companies attempted to remain within the $3.0 million limit, above which subprojects had to be approved by ADB review missions. This resulted in a fragmented and truncated approach in the case of anumber of subprojects. Artificial cost limitations should not of themselves drive subproject selection. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Design: Subprojects Project Management: Project supervision Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach Future projects need to ensure that parallel downstream investments required from provinces, cooperatives, or farmers are made in a timely manner. In several of the project's subproject areas, investments in the secondary and tertiary canal systems have been less than optimal, resulting in lowered system performance and an inability to fully capitalize on project investments. project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Project Design: Subprojects Sector Related Issues: Irrigation management Getting the design of subprojects right is the key to project performance and impact. The project employed a traditional approach to subProject Design, focusing almost entirely on primary infrastructure. A more participatory and holistic approach to design should result in improved outcomes. Future project designs therefore should include extensive consultation with the primary stakeholders (farmers, water management groups, and irrigation and drainage management companies [IDMCs]). Examples of contributions that these stakeholders can make to system design include identification of investment needs in secondary and tertiary drainage and irrigation systems, alignment and level of canals and drains, location of major structures, and placement of spoil from excavations. project cycle stage: Design Lesson Topics: Project Design: Project design Project Design: Subprojects Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach Methodologies/Approaches: Participatory approach Since the management of most of the irrigation and drainage systems is under thejurisdiction of provincial governments, provincial stakeholders should take a lead role in upgrading and rehabilitating intraprovincial systems under future projects. Under the project, except for complex components such as large pump stations, and large outfall and intake sluices, implementation of several subproject components could have been delegated to the provinces with sufficient implementation capacity. project cycle stage: Design Appraisal Lesson Topics: Project Design: Project design Project Design: Subprojects Capacity Development: Capacity assessment Country Context: Decentralization Sector Related Issues: Irrigation management The project and the technical assistance (TA) were intended to assist in the development of Viet Nam's water resources institutions. In practice, their impact has been limited. The project and TA experiencehighlights the difficulties in encouraging institutions to adopt new approaches to planning andmanagement. A careful assessment is required during project and TA design of the agency'sreceptiveness to new institutional and operational concepts and the potential to operationalizethem. Furthermore, TA inputs should be planned in a phased manner so that in case ofinsufficient support and ownership on the part of the executing agency, the TA can bereformulated, rescheduled or, in the worst case, terminated. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity development Capacity Development: Ownership Sector Related Issues: Water resource management The project has shown that physical interventions do not necessarily lead to improved irrigation fee collection - one of the project's objectives. Specific activities need to be integrated in the project design to address cost-recovery issues, taking into account the role of the provincial people's committees in setting irrigation and drainage fees, the performance of the irrigation and drainage management companies (IDMCs) in providing irrigation and drainage services, and the role of the cooperatives and their water management groups. In-system irrigation and drainage conflicts also need to be understood and addressed. For future projects, inclusion of reform measures to improve theperformance of water sector institutions should be considered, besides the physical interventions. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/red-river-delta-water-resources-sector-project
Agriculture Sector Program (Loan 1340-VIE[SF]) | Agriculture, Natural Resources, and Rural Development | 2002-09-30 | A greater focus on policy outcomes rather than policy actions may be more appropriate for a number of reasons. This leads to the conclusion that ADB needs to adopt a more strategic and flexible approach in its policy-based lending. For flexibility to be a practical option, monitoring and evaluation systems must function effectively to provide the information on which decisions can be made, and dialogue must be frequent and in-depth. Given the reality of staff constraints, the appointment of a senior policy consultant should be considered for program loans to provide intermittent inputs throughout program periods. Given their short duration, monitoring and evaluation systems for program loans and the required skills and resources should be in place by loan effectiveness. project cycle stage: Appraisal Lesson Topics: Modality: Policy-based lending Modality: Program Monitoring &amp; Evaluation: Monitoring and evaluation Project Management: Consultants Capacity Development: Human resources management Policy &amp; Reform: Policy reforms/framework ADB s flexibility in providing an additional technical assistance (TA) and modifying (two) policy conditions also contributed to program success. This TA and the relatively frequent dialogue by regular ADB missions ensured that problems were rapidly resolved and did not become entrenched. The planned TA support also provided a good base of information for policy work, and in the case of another TA, a compelling analysis of policy options and outcomes. project cycle stage: Implementation Lesson Topics: Modality: Policy-based lending Modality: Technical Assistance Project Management: Project supervision Policy &amp; Reform: Policy matrix Policy &amp; Reform: Policy reforms/framework In future programs, local currency proceeds (counterpart funds) should be used for purposes that are consistent with, and contribute to reform. While fungibility is an issue, the government should be encouraged to provide incremental funding for certain activities or meet clearly identified restructuring costs, both of which can be tracked through a review of budgetary allocations. ADB s Operations Manual provides the basis for obtaining expenditure commitments from the government. project cycle stage: Appraisal Lesson Topics: Finance &amp; Financial Aspects: Counterpart funds Policy &amp; Reform: Reform Restructuring of bad debt of a lending institution must be accompanied by policy changes to ensure that the problem does not reemerge. project cycle stage: Feasibility Lesson Topics: Finance &amp; Financial Aspects: Financing Modality: Technical Assistance Policy &amp; Reform: Policy reforms/framework Technical assistance (TA) support to improve institutional capability is likely to require a reallocation of recurrent expenditure if new developments such as the rice market model and land information system are to be sustained. This needs investigation during TA design. project cycle stage: Design Lesson Topics: Finance &amp; Financial Aspects: Financing Modality: Technical Assistance Project Management: Management information system Capacity Development: Capacity development The project was also successful because it did not include any significant departures from existing policy. Whether policy programs should involve a degree of additionality and thereby risk being only partly successful or should they have a high degree of fit with existing policy probably depends on the context. In the case of the project, the reform pace was rapid and it made sense to reward past efforts and consolidate the progress made rather than attempt to further increase the pace. When the pace of reform is slow, it may be sensible to provide incentives to accelerate and deepen the reform, even if this means the program may not fully achieve its objectives. project cycle stage: Feasibility Lesson Topics: Project Management: Risks/Risk management Policy &amp; Reform: Policy reforms/framework The project was successful primarily because of genuine commitment and support for the principles it embodied by those in government with power and influence to make it happen. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Ownership The slow pace of achieving greater private sector involvement in agricultural trade is a concern. On the other hand, experience from the breakup of the former Soviet Union has shown that a too rapid privatization creates severe problems, which are very difficult to resolve. Viet Nam s steady approach has proven to be better although perhaps slower than necessary. What is clear is that the innovation and efficiency required to sustain agriculture sector growth and create off-farm employment through value-added activity will require a vibrant private sector operating at all levels. However, the private sector is unlikely to grow while a dominant state-owned enterprise sector retains competitive advantages. Measures are required to progressively withdraw state investment in commercial activities. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Employment Sector Related Issues: Industry and Trade Sector Related Issues: Private sector Sector Related Issues: Rural development Policy &amp; Reform: Privatization Policy &amp; Reform: Public sector reform Policy &amp; Reform: Transition economies | Project/Program Performance Evaluation Report (PPER) |  | http://www.adb.org/documents/agriculture-sector-program-loan-1340-viesf