## Sectors - ICT
Information and communication technology
REPORT NAME | COUNTRY | SECTORS | DATE | LESSONS | REPORT TYPE | REPORT RATING | LINK
Addendum to the Afghanistan Power Sector Master Plan: Technical Assistance Completion Report | Afghanistan | Energy | 2015-07-01 | Afghanistan, and the other countries in the region, have limited capacity to produce credible energy forecast. The Master Plan modeling was based on energy forecast data that were made available to the consultants by the different governments. In the case of Afghanistan the forecast was based on 22 months of incomplete data (March 2010 January 2011) from the regions grouped into the 34 provinces. The Master Plan and its addendum relied on the basic forecast data (best available data at the time). Capacity building needs to be an ongoing process and build into future projects. The conclusion of the study will improve as the underlying data quality improves. Project cycle stage: Implementation, Operation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/addendum-afghanistan-power-sector-master-plan-tcr
Security Plan for Project Implementation: Techincal Assistance Completion Report | Afghanistan | Public sector management | 2015-07-01 | The shift away from project security of the TA (technical assistance) in 2012?2014 was necessary to increase the protection of the AFRM (Afghanistan Resident Mission) compound to provide a safer and improved working environment for the international and national staff. During the same period, the executing agencies took more responsibility on project security along with APPF (Afghan Public Protection Force). Further, ADB provided funding within its projects for enhanced security. The bidding documents included provisions for developing and implementing project security measures appropriate to the location and site conditions. Even though Presidential Decree 62 was issued in August 2010, the lack of properly trained APPF personnel still remains a challenge for some projects. While the TA provided important assistance, contractors need to also be better informed during the bidding process about the security conditions so that project security costs may be properly estimated. Security incidents did occur on selected projects but were well-managed by the GOA (Government of Afghanistan) and the contractors. Improved security assessments and the inclusion of risk management firms could further improve project security. The community engagement aspect of project implementation is another important factor for project security. Involving the community, given the significant poverty and unemployment in many of the areas where ADB projects are being implemented, through construction jobs, community development, and discussions with local government and tribal leaders are an important factors to ensure project security. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/security-plan-project-implementation-tcr
North-South Corridor Project | Afghanistan | Health, Transport | 2013-02-09 | 1. Adverse security issues and project start-up delays are two main factors that have adversely affected and delayed almost all previous projects in Afghanistan, except those where these issues were carefully handled in advance. Furthermore, insufficient surveys during project processing, and major changes in the technical design parameters during project implementation, can also cause serious implementation delays and significant cost overrun. The project suffered security issues until the situation was fixed with the help of additional security arrangements. This caused about 12 months of delay as the project area was prone to major terrorist attacks. It also delayed the contractor's mobilization. Further, because the area was remote and insecure, the initial project design was done through geospatial analysis, eventually resulting in a significant design change and cost increases. Follow-on projects should carefully address these factors up front during loan or grant processing. Advanced contracting must be executed to avert start-up delays. Extensive security measures should be planned and budgeted for from the start. project cycle stage: Lesson Topics: 2. Scrutiny of contractors and consultants before their selection is critical to the success of any project. In particular, in projects like this, which draw minimum interest because of security hazards, lack of oversight may jeopardize project implementation. Therefore, in Afghanistan, specifically in projects like this, such risks may be averted by giving more emphasis to quality and the performance record of both the consultants and the contractors, and not just the lowest price. Afghanistan is a tough place to work, and picking a company that is not equipped to deal with the harsh geography, climate, and security environment can easily result in both cost and time overruns. The project completion report mission noted that the consultant had a cordial relationship with the local communities and government, which helped in the timely resolution of several implementation issues, given the tenuous security environment. project cycle stage: Lesson Topics: 3. In future projects, both the government and donors should prepare realistic project schedules by carefully taking into account (a) the security situation and the time and resources required to carry out remedial actions for the safety of project teams throughout the projects; (b) actual construction period available in a year considering the altitude of the project areas and inclement weather conditions; (c) probability of rebidding due to lack of interest, competition, or exorbitant costs (beyond acceptable limits) offered by some interested bidders; (d) delays in contractor mobilization; (e) longer-than-expected time spent by government agencies in procurement matters due to their limited capacity or lengthy internal approval procedures; and (f) possible flaws in the initial designs that may require additional surveys and increase the scope of the contract. project cycle stage: Lesson Topics: 4. In a project of this nature, where there are serious security risks, and a potential for contractors' or consultants' suspension of works, or expected contract variations due to type of terrain, prompt decision making becomes critically important. This can be achieved through exceptional involvement of donors. ADB provided enhanced supervision both from headquarters and Afghanistan Resident Mission (AFRM). Staff were closely involved in identifying and promptly resolving issues. Any matter requiring ADB's internal approval was expedited and funds releases were processed quickly. Furthermore, AFRM's site supervision, despite security hazards, helped in precisely assessing the field issues. All these factors contributed to the timely resolution of implementation issues and the completion of this challenging project. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-south-corridor-project-pcr
Hairatan to Mazar-e-Sharif Railway Project | Afghanistan | Transport | 2013-01-06 | 1. Experience on several ongoing and completed projects in Afghanistan has shown that project implementation is delayed due to two main factors: start-up delays and adverse security issues. Taking advance actions before grant or loan effectiveness can easily address these problems, as demonstrated on this project. Timely actions were taken to speed up implementation readiness, such as advance procurement of works and consulting services, award of contracts, site handover, and timely establishment of a fully staffed project implementation unit. These actions successfully avoided start-up delays. Furthermore, the provision of comprehensive security arrangements, with advance administrative approvals, resulted in an uninterrupted project implementation. Based on a careful assessment of the security arrangements, about 463 police personnel were deployed along the railway line and at about 62 check posts. project cycle stage: Lesson Topics: 2. For implementing large-scale and complex projects with a strict timeframe, the preferred form of contract can be engineering, procurement, and construction (EPC) turnkey. For this project, works were awarded under the EPC turnkey contract using a fixed-price and fixed-delivery schedule with penalties for nonperformance and a bonus for early completion. This provided reasonable economic stimuli for timely project completion. project cycle stage: Lesson Topics: 3. Combining the engineering, procurement, and construction (EPC) and operation and maintenance (O&M) into one package may yield more efficient and cost-effective outputs. On this project, this would have given all the parties a clear understanding of the requirements from the beginning, and risk-mitigation measures could have been built into the contract appropriately. The contractor would also have been particularly vigilant in ensuring the best quality of works during construction. In addition, the bidder would have had an opportunity to come up with more innovative ways of implementation and might have offered a more cost-effective bid. This combination could also minimize any additional due diligence required during the O&M contracting and would result in time savings. However, the concentration and performance risks would need to be mitigated through performance standards and deterrent contractual provisions. project cycle stage: Lesson Topics: 4. For projects where multiple government agencies are involved in decision making, it is important to establish coordination through an executive committee made up of representatives of the concerned agencies, chaired by a high-level government official and/or champion. Such a committee can facilitate the provision of overall guidance, ensuring expeditious approvals from various agencies, and in places where security is a major concern, could ensure that the project is implemented uninterrupted with sustained security arrangements. project cycle stage: Lesson Topics: 5. Implementing a project of this magnitude and in a strict timeframe was quite challenging. However, this can be achieved through exceptional involvement of donors. ADB provided enhanced supervision both from headquarters and the resident mission. Staffs were closely involved in identifying and promptly resolving issues. Any matter requiring ADB's internal approval was expedited and funds were released with fast-track processing. Furthermore, a fulltime implementation consultant was mobilized by ADB on site to provide coordination, implementation assistance, and independent reporting. All these factors contributed to timely resolution of implementation issues and completion of the project. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/hairatan-mazar-e-sharif-railway-project-pcr
Afghanistan: Andkhoy - Qaisar Road Project | Afghanistan | Transport | 2012-12-27 | Careful consideration should be given as to whether a project is really qualified for processing under emergency support modalities. In this case, the time saved from rushed preparation was subsequently lost in delays and other problems in implementation. [Main text, para. 32] project cycle stage: Design, Implementation Lesson Topics: Modality: Project Country Context: Emergency | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/afghanistan-andkhoy-qaisar-road-project
Afghanistan: Regional Airports Rehabilitation Project (Phase 1) | Afghanistan | Transport | 2012-12-27 | A lesson from project implementation is that special measures need to be taken with respect to timing, cost estimations, and availability of contractors in a difficult conflict environment. Lessons learned from the resettlement component needed to be included. [Main text, para. 22] project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Country Context: Conflict/Post-conflict | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/afghanistan-regional-airports-rehabilitation-project-phase-1
Country Assistance Program Evaluation Report for the Islamic Republic of Afghanistan | Afghanistan |  | 2012-10-19 | 1. ADB needs to formally recognize the facts and treat Afghanistan as a conflict-affected country rather than one in a post-conflict situation. This makes it possible for ADB to have a realistic assessment of the current and likely future security environment and to take proper approaches for Afghanistan. Afghanistan continued to be a weakly performing, conflict-affected country throughout the evaluation period, but ADB's programs and projects did not explicitly take into account the continuing conflict or the country's weak performance. The country assistance program evaluation findings highlight shortcomings in ADB's program in several areas including weaknesses in analysis in project formulation and design, in project efficiency due to delays and consequential cost increases, through insufficient supervision during project implementation, and in limited coordination with development partners. Many of these deficiencies were the result of concerns about the security environment. That the political, security, economic and social spheres are interdependent; failure in one risks failure in all others. This country weakness and the protracted military hostilities remain Afghanistan's most serious concern, and sustainability and risk management should be the priority. [Main text, paras. 167-168] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Risks/Risk management Country Context: Conflict/Post-conflict 2. Sector strategies necessitates analyses of industrial and agricultural demand and population's socioeconomic needs as well as linking ADB support in each sector and with those of development partners in other sectors to optimize use of resources. The evaluation finds an urgent need for ADB to adopt an approach to development in Afghanistan that is centrally and externally driven to one driven by demand. The bottom-up processes normally required were not fully executed and inadequate attention was paid to security aspects in project design and implementation. ADB's physical investment have not been clearly linked to other industrial and social demands or coordinated with projects of other development partners in industry, agriculture, and social services. Although the priorities in each of ADB's investment sectors are clearly stated, they are not supported by qualitative data assessment and have not yet been clearly linked to any substantive demands, especially in industry. If ADB support had been based on more substantial plans, coordination among development partners and sectors would have been more efficient. [Main text, paras. 171-172, and 175] project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Project Design: Project design Country Context: Conflict/Post-conflict Country Context: Prioritization 3. ADB needs to pay careful attention to country context and absorptive capacity in project design and use appropriate financing modalities. The design of ADB support did not fully capture the pervasive constraints to the government's absorptive capacity. Since 2007, ADB support to Afghanistan has been entirely in the form of grants. The government has preferred faster implementation to more careful implementation, even though this may mean inefficient use of the funds. Leaving civil works design and engineering tasks to a single construction contractor through design build contracts is an example of this, which constrains the government's ability to supervise civil works and to justify cost overruns. The Afghanistan government has been a missed opportunity for ADB to develop the capacity of the government to plan, design, and manage contract for civil works as well. The design build contracts also increased uncertainty about land acquisition and resettlement at the appraisal stage and limited the development of capacity in line agencies. Although these contracts are appropriate for simple civil works, they were used in large infrastructure projects without considering the two-step procedure that avoids conflict of interest by separating the design and construction functions. The design build contract should be used only selectively and must be fully justified. Several grants were provided in the form of multitranche financing facilities (MFFs), a modality that requires government capacity and a detailed road map and investment program to be effective. This may be a preferred tool for facilitating fast disbursement of funds, but it is likely inappropriate in Afghanistan, where there is insecurity and government absorptive capacity is weak. In addition, ADB has used some MFFs to cover cost overruns of ongoing projects that the government could not fund. Given the extraordinarily difficult environment under which projects had to be implemented and the inherent risk of cost increases, making the MFFs quasi-credit lines was imaginative but not defensible with respect to ADB principles of accountability. Instead, ordinary grant (loan) and supplementary financing for cost overruns should have been sought, with the necessary information provided to ADB's Board. [Main text, paras. 88-89, 173, and 174] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Lending modality Project Design: Appraisal Project Design: Project design Capacity Development: Capacity development Country Context: Conflict/Post-conflict Country Context: political economy factors 4. Operation and maintenance (O&M) budget stress exists and the international community needs to take a holistic approach for sustainability. During the country assistance program evaluation (CAPE) period, investments were made both to rehabilitate existing assets and to create new ones. The political imperative of the international community was to show progress through reconstruction and development. However, as a result, Afghanistan will need an estimated $1 billion $2 billion a year to meet the O&M costs of civilian assets. Without continued support from development partners, the government has neither the institutional nor the financial capacity to carry out operation and maintenance of its new and rehabilitated assets. Yet it will be under huge pressure to do so as international troops continue to withdraw and foreign assistance diminishes, forcing it to take on much greater budgetary responsibility for security, the delivery of services, and keeping assets in serviceable condition. Tax revenues may grow, but the International Monetary Fund has estimated that the government will achieve fiscal sustainability for operating expenditure only by 2024 2025. Weak public sector capacity compounds the problem. ADB support during the CAPE period did not systematically integrate a concept of sustainability in project design and implementation that took both financial and human resource requirements into consideration. [Main text, paras. 139 and 176] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Operation and maintenance Country Context: Conflict/Post-conflict 5. To develop the capacity of developing member countries (DMCs), especially DMCs in postconflict and fragile situations, there is a need for long term, sustained ADB support for capacity development. In Afghanistan, capacity development was a major goal but results frameworks as well as the design and monitoring of capacity development interventions were generally weak. Each set of policy reforms involved the need for new organizational and human capacity, and so prioritization and sequencing should have been seen as essential. A blend of training modalities was crucial to developing individual capacity. This meant that, while short-term internal and external training sessions were necessary, a simultaneous effort was needed to initiate sustained support for the development of trainers and to undertake long-term measures to develop training institutions. Exit strategies for project implementation units and international and national consultants were not defined at the beginning but should have been. Providing training abroad was an easy output to achieve but proved to be less effective when not twinned with hands-on application of learning on the job. [Main text, para. 178] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity development Country Context: Conflict/Post-conflict 6. A strong resident mission can make ADB more effective in capacity development and aid coordination, and can contribute to more expeditious project implementation. ADB s resident mission in Afghanistan did not have the numbers or the skills mix to cope with the task during the evaluation period. Although the portfolio grew, the number of international staff declined from six in 2006 to four in 2012. Positions have remained vacant for extended lengths of time. The human resources issue has other aspects in addition to staff numbers and skills at the resident mission (e.g,, number and skills of international staff working at ADB headquarters, the length of time they have spent in Afghanistan, and how often they visit and for how long). Staff specializations are also crucial to effectiveness. Having adequate procurement staff in the field is important, because long-distance procurement arrangements can be a significant source of delays in low capacity environments. [Main text, para. 181] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Project Management: Procurement Capacity Development: Capacity development Other: Resident Mission | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-report-islamic-republic-afghanistan
Afghanistan Investment Guarantee Facility Project | Afghanistan | Finance | 2011-12-01 | The availability of bankable political risk guarantee (PRG) cover for risks that are within the power of the government to mitigate is important to investors and their financiers. However, such targeted cover cannot address concerns about security and macroeconomic stability. Close collaboration with Multilateral Investment Guarantee Agency (MIGA), International Development Association (IDA), and Department for International Development (DFID) strengthened project design. It allowed for excellent exchange of experience with regard to PRGs, other insurance products, and how they can best be used to fill market gaps, especially in post-conflict countries. Responsibility for the project was spread out within ADB, causing coordination issues with MIGA and other cofinanciers. For future projects combining sovereign, nonsovereign, and cofinancing operations, having a single focal point within ADB would improve project implementation and prospects for success. The capacity of Afghanistan Investment Support Agency (AISA) to promote new investment in Afghanistan and the availability of PRG cover to support such investment was poor because of staff turnover and an inadequate incentive framework. This should have been anticipated and technical assistance could have looked at ways to address this problem. Modifications to project design, the monitoring framework, and the assessment methodology would help future projects using this or a similar PRG modality and projects that combine sovereign, nonsovereign and cofinancing operations. The assessment criteria did not easily accommodate the unique structure of the project or the modality used. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/afghanistan-investment-guarantee-facility-project
Fiscal Management and Public Administration Reform Program | Afghanistan | Public sector management | 2011-12-01 | Monitoring framework. How the design and monitoring framework (DMF) was prepared constitutes a major design and evaluation issue, and its lack of clarity made assessment of achievements across the program very difficult. The standards used in conceptualizing DMFs have evolved significantly since the programï¿½s approval, and the new practices should soon make it possible to design more effective assistance in Afghanistan and elsewhere. But it is also important to recognize that the nature of reforms in public fiscal planning and financial management reforms makes the adoption the new monitoring framework practices more complex; professionals with expertise in such work should develop more tailored approaches in this regard. Future assistance. Further assistance to the government, especially the Ministry of Finance (MOF), is crucial in order for reforms under subprogram 1 to become effective and be sustainable. But the approach to the provision of this assistance must also change. Instances have been highlighted in which high levels of technical assistance (TA) have constrained learning-by-doing on the part of local counterparts, and overwhelmed the incentives that normally underpin successful capacity development. Future ADB institutional reform programs in Afghanistan should include a specific and realistic strategy for capacity development that takes the following into account that: (i) In the absence of absorptive capacity in ministries, little technical skills transfer will occur. However, the level of fiscal resources needed to sustain hiring of more qualified staff to the civil service (to increase that absorptive capacity) is also affected by current development partner financing of externally-funded national staff (the so-called ?second civil service?), which is now hired on inflated terms. Coordination between these two dimensions is a priority if core government capacity is to be developed. (ii) In the absence of specific terms of reference for international advisors for on-the- job training, or if those are not strictly focused on the most technically challenging tasks, the availability of these experts to provide general support within the ministries will tend to crowd-out the inputs provided by, and the learning process of the local staff. Thus, experts should be given specific terms of reference that (a) require the provision of on-the-job training to local counterparts, and (b) limit their overall involvement to the most technically challenging tasks. (iii) Continuous recourse to resident international advisors may perpetuate the dependency of decision-makers on such experts. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/fiscal-management-and-public-administration-reform-program
Private Sector and Financial Market Development Program | Afghanistan | Finance | 2011-12-01 | Program Related Further action or follow up. Government implementation of outstanding policy and monitorable actions should be prioritized to maintain reform momentum. It may be possible to tap parallel ongoing advisory technical assistance (TA) projects if further TA is needed. The delays in program implementation by the government are mostly due to lack of expertise, and not to lack of willingness to reform. Additional assistance. The effectiveness of policy reforms under the program is ultimately determined by the competence of the different Afghan government agencies, which acquired new roles during the reform process. As a result, and in view of the pervasive capacity constraints that affect the government, the sustainability of the program requires substantial follow-up assistance. A second program focused on the implementation challenges created by the program should be considered, as that would also be in line with the current ADB country partnership strategy for Afghanistan. Timing of the program performance evaluation report. The impact evaluation of the program will be limited by the difficulties in building counterfactual scenarios. An evaluation of the relevance of the different program components could be undertaken between 2012 and 2014, and could address (i) how well commercial arbitration institutions are working, (ii) how sound the immovable property registry is perceived to be by the stakeholders the program intended to benefit, and (iii) how much use is done by the private sector of commercial arbitration mechanisms. General Similar institutional reform programs by ADB in Afghanistan should include a specific and realistic strategy for capacity development, taking into account the following: (i) without absorptive capacity in ministries, very little technical skills transfer will occur; (ii) sustained recourse to resident international advisors may perpetuate the dependency of decision makers on such advisors; and (iii) in the absence of specific terms of reference for international advisors, their contributions will tend to crowd out inputs provided by and the learning process of local staff. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/private-sector-and-financial-market-development-program
Regional Airports Rehabilitation Project Phase I | Afghanistan | Transport | 2011-12-01 | The main lesson learned through implementation of the project was that working with and supporting existing government structures helps develop the capacity of the executing agency to implement externally funded projects, especially in procurement and contract management. It also ensures better ownership of the various works and continued sustainability. Most other development activities are implemented off-budget in Afghanistan. Close coordination of the multiple development partners was important to ensure that works and programs were complementary, with no overlap or gaps in support. The project was able to incorporate separate but complementary programs from bilateral development partners, which helped the overall implementation and impact of the project. Senior provincial and district government officials and elders expressed gratitude to ADB for its timing and confidence in the implementation of the project. They hope that this will open the regions for future investments and improve governance in the regions. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/regional-airports-rehabilitation-project-phase-i
Andkhoy-Qaisar Road Project | Afghanistan | Transport | 2010-12-01 | It is important to conduct a sound capacity assessment of Ministry of Public Works (MPW) and adequate analysis of the local political context in the early stages of the project. Driven by the project's emergency nature, overemphasis on time savings during project preparation unfortunately resulted in delays coupled with cost overruns and implementation problems at a later stage. It is also highly desirable that emergency projects implemented in complex environments receive more frequent and comprehensive monitoring and supervision. Consultant quality at entrance is critical, as top international consultants and contractors are less interested in projects in Afghanistan. Emphasis during selection should be on quality and past performance record of consultants, as this can easily result in both cost and time savings, given the prevalence of price escalation, time extensions, and cost overruns for projects in Afghanistan. Frequent replacement of the supervision consultants' key staff members should be avoided or penalized. Projects that suffer from key staffing issues usually experience compounding delaying effects and cost overruns during implementation. The rapid turnover of the MPW staff, frequent changes in project officers and mission leaders, and the transfer of project administration from one ADB department to another were counterproductive. Afghanistan is a country with a long history of war, in which the usual rules do not work well in achieving development impacts. Appropriate adjustments, such as allowing procurement of bitumen from nonmember countries of ADB, proved to be beneficial for maximizing the project's development impact and economic efficiency. More effort should be made to gain compliance by the borrower and MPW with loan covenants, which helps strengthen the government's project ownership. Although difficult postwar conditions exist, ADB should use appropriate means including suspension of disbursements and cancellation of the loan if necessary and in the best interest of the project. The design-build contract adopted for this project is not a turnkey type of contract in which prospective bidders will need to conduct significant site reconnaissance in order to prepare competitive bids, but a measurement contract based on financial unit rates with design carried out by the contractor as the road is constructed. This type of contract was intended to overcome local design capacity constraints and expedite commencement of works. However, the result was mixed: the lead time required for project preparation was reduced, but the use of civil works contract documents without a finalized detailed design resulted in substandard implementation quality in terms of time, cost, and ease of implementation. The annual hiatus in processing withdrawal applications by Ministry of Finance (MOF) for the 3-month budget approval period (end of the financial year on 21 March until the end of June) causes cash flow difficulties for the contractors and consultants, as this period coincides with the peak construction season. A streamlined coordination among MPW, MOF, and ADB should be developed to minimize the adverse impact on project progress and avoid interest claims on late payments. The adequacy of security arrangements at project sites in Afghanistan determines the pace at which projects can be implemented. Ultimately, protecting construction crews and facilities and equipment storage areas will be feasible only if an effective grassroots outreach program is mounted to win the support and goodwill of communities who live near construction sites and secure the collaboration of local government officials and village leaders. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/andkhoy-qaisar-road-project
Afghanistan: Agriculture Sector Program [Loan 2083-AFG] | Afghanistan | Agriculture, Natural Resources, and Rural Development | 2010-11-30 | There is a need for closer ADB involvement in critical early stages and greater rigor in government reporting. [Main text, page 10, section E(ii)] project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project reporting | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/afghanistan-agriculture-sector-program-loan-2083-afg
Regional Power Transmission Interconnection Project (Afghanistan and Tajikistan) | Afghanistan, Tajikistan | Energy | 2014-06-01 | The Afghanistan component of the project demonstrated that importing relatively inexpensive electricity from Tajikistan, and elsewhere if available, can result in enormous economic benefits to Afghanistan and financial benefits to Da Afghanistan Breshna Sherkat (Afghanistan Power Utility). It would be prudent for the Government of Afghanistan and ADB to pursue further investments in the power sector to take advantage of surplus electricity in neighboring countries. Financial management assessments undertaken at appraisal need to fully assess the potential for executing agencies to provide the level of funding proposed in the project financing plan to avoid cancelation of project activities that may negatively affect project viability and sustainability. Although the economic and financial benefits of the project were substantial for Afghanistan, they would have been greater if investment in distribution had been undertaken in a timely manner to take advantage of the capacity to import electricity through the project transmission line. The transmission line is currently used at less than full capacity - about 200 MW. It is possible to energize it to transmit up to 600 MW of electricity. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/regional-power-transmission-interconnection-project-afg-taj-pcr
Infrastructure Sustainability Support Program: Technical Assistance Completion Report | Armenia | Public sector management, Transport, Water and other urban infrastructure and services | 2015-06-01 | Complex and integrated development challenges require integrated solutions and responses. The One ADB approach, as demonstrated under this TA (technical assistance) and the subsequent program loan, enables us to provide more fundamental, sustainable, higher-value products to ADB's clients. Project cycle stage: Design | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/infrastructure-sustainability-support-program-tcr
Rural Road Sector Project | Armenia | Transport | 2011-12-01 | At appraisal, ADB overestimated Armenian Roads Directorate (ARD's) capability to procure consultant services for subproject preparation and construction supervision. For future projects, a more detailed capacity assessment of the executing and implementing agencies is needed during project processing. Sufficient contingency is needed to cover cost increases. For future projects, design-build contracting can ensure better engineering and mitigate the risk of price escalation. An ADB review identified shortcomings on some road construction works and poor quality in engineer's cost estimates. These were caused mainly by inadequate designs or poor contractual works and materials. ADB needs to ensure strict compliance with contractors' contractual specifications. Contractors should be held accountable for poor contract performance or substandard materials before the defect liability period following the contract agreements. The roles and responsibilities of road network development and management are unclear. Stronger government commitment is needed to develop the road sector. During the surveys and preparation of road works design, more attention should be paid to the current and expected needs of pedestrians in road sections passing through villages. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-road-sector-project
Crisis Recovery Support Program | Armenia | Public sector management | 2010-12-01 | Lending Modality for Financial Crisis. ADB s Countercyclical Support Facility has been instrumental in supporting countries receiving loans financed out of ordinary capital resources. However, at present, ADB has no modality for a financial crisis response operation for Asian Development Fund eligible countries. The special program loan in the Program Lending Policy is limited to ordinary capital resources countries and can only used to address balance of payment crises. 21 Likewise, emergency assistance under the Disaster and Emergency Assistance Policy (DEAP) does not include financial crisis response. As such, the program had to use the standard program loan modality and develop the design of program actions to allow quick processing and disbursement. While program preparation was shorter than for typical program loans, preparation would have benefited from streamlined and abbreviated procedures similar to the countercyclical support facility and the DEAP, and would have been able to provide the support much earlier. During crisis episodes, while policy reforms are important, the government has urgent needs to quickly stabilize the economy, such as, providing urgent fiscal support to counteract the financial crisis. As such, crisis response operations should focus more on immediate responses to the financial crisis, such as maintaining critical social and safety net expenditures. However, as crises open opportunities for reforms, policy dialogue can be initiated for follow-up operations. But this should not delay the financial crisis recovery support. Success of a financial crisis response operation is highly contingent on the government s ability to quickly put together its own anti-crisis plan, which could be financed by ADB after exercising due diligence. In the case of Armenia, the government had an anti-crisis action plan and a crisis budget. Program Monitoring to be Improved. The program monitoring system should be improved for similar programs in the future. The government s monitoring system did not capture and produce the required data on indicators performance. In particular, the executing agency collected the information from other government agencies (Ministry of Labor and Social Issues, Ministry of Finance,, government reports on anti-crisis measures progress, and other official statistics) to produce its own project completion report. However, a specific indicator on the number of jobs created by the interventions in the construction area was not properly monitored and reported. Technical Assistance Support is Important for Crisis Programs. There was no technical assistance with the program. The absence made it difficult to monitor the outcome of the loan. A technical assistance (TA) would have been useful for monitoring budget execution in general, and monitoring of expenditures supported by the program in particular, including budget execution reports, expenditures in key programs for social protection (pension, family benefits, and unemployment insurance), social impact assessment, and financial flows and bank accounts related to regular and special safety-net programs. It would have helped track results and progress in achieving the targets and could have brought some advisory services to the government on fine-tuning the anti-crisis program as the implementation results emerged. The TA could have helped develop a second generation follow-up crisis recovery program in case the impact of the crisis had played out longer in the country. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/crisis-recovery-support-program
Power Transmission Enhancement Project: Completion Report | Azerbaijan | Energy | 2015-09-21 | The project demonstrated that Azerenergy is a capable implementing agency for power projects and that there is private sector capacity to undertake major construction projects related to augmentation and rehabilitation of power transmission and distribution networks. With proper planning, effective project monitoring mechanisms, and motivated and well-trained personnel, such projects can be successfully and expeditiously implemented. The government, with the assistance of ADB, should continue to upgrade and expand the transmission and distribution networks to ensure system losses are minimized, electricity supplies are reliable, and the growing demand for electricity in the country is met. project cycle stage: Design, Implementation There was some confusion in Azerenergy about the correct approach to use in calculating the debt - equity ratio and the DSCR (debt service coverage ratio). Financial ratios should be defined in loan covenants, particularly if they form part of the financial covenants of the loan. Moreover, ADB should more closely review these covenants during review missions to evaluate - and if needed initiate measures to ensure - compliance. project cycle stage: Design, Feasibility To enhance its operational and financial performance, Azerenergy is (i) streamlining its core business and transferring distribution networks assets and liabilities to Azerishiq, which will improve its financial performance and reduce administrative expenses; (ii) expanding power export to Georgia, Turkey and Russia; (iii) introducing enterprise resource planning, and enhancing internal audit and control to improve budgeting and planning functions; and (iv) accessing capital markets and diversifying financing channels (Azerenergy successfully obtained a corporate credit rating of BBB-/A-3 in February 2013). project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/aze-power-transmission-enhancement-project-pcr
Road Network Development Program (Project 2) | Azerbaijan | Transport | 2013-02-09 | 1. More robust due diligence is needed during project design and formulation to enable the closest possible cost estimates and to set aside enough resources to cover contingencies. This can save considerable time. The scope of the ADB-financed East-West Highway Improvement Project, approved in 2005, included two sections of the east-west highway: Gazakh-Georgian border section and Ganja bypass road, forming part of Yevlakh-Ganja section. However, during implementation, the project experienced unprecedentedly sharp increases in prices for fuel, utilities, and major road construction materials, which significant increased the cost of construction. Consequently, the scope of the East-West Highway Improvement Project was revised to exclude the Ganja bypass road. This delayed improving the Ganja bypass road, which was a muchneeded alternative to the existing highway. At cost estimation, prices of materials should be examined carefully and in relation to neighboring markets and the unit costs of similar items in previously awarded contracts. Contingencies should also consider the exceptional cost increases during implementation. project cycle stage: Lesson Topics: 2. Realistic estimation of project and contract duration is important. Inclement weather seriously hampered physical progress in project implementation, especially from August 2011 to February 2012. The contractor had difficulty coping with it, which significantly delayed the completion of works. A more realistic timeframe for implementing a road project should be formulated allowing for unpredictable local weather conditions and other contingencies so that resources can be deployed effectively and efficiently. project cycle stage: Lesson Topics: 3. The project constructed a two-lane road. Subsequent to the start of the project, the government decided to widen the road to four lanes by constructing another two-lane road alongside the project road. The widening works are scheduled for completion by December 2013. The ADB-financed two-lane road was completed in December 2012. At appraisal, project design needs to be properly formulated through much broader consultation with line ministries and other stakeholders, keeping in view future requirements and government plans so that administrative and operational issues are not encountered during the implementation and the facility can be made ready for the users in a timely way. project cycle stage: Lesson Topics: 4. The project experienced start-up delays, because the contractor mobilized slowly and was unable to tie up with suitable local subcontractors. The contractor was also unfamiliar with conditions in the country at the start, which caused implementation delays. The subcontractors contributed significantly, and without them it would have been difficult for the contractor to successfully complete the project. For future projects, the criteria for qualifying the contractor - and the disclosure of information on subcontractors and the contractual provisions related to contractor performance, such as mobilization, staffing, and the deployment of equipment and funds - need to be strengthened to minimize the risk of poor contractor performance. Moreover, the previous performance of the contractor in the project country should be taken into account when evaluating bids. The Ministry of Transport and Azer Road Service need to provide bidders with adequate local information at pre-bidding meetings, and to publish on its website information on the cost of locally available inputs such as materials, equipment, and labor, to enable bidders to submit sensible bids and implement the project successfully. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/road-network-development-program-project-2-pcr
Azerbaijan: Validation of the Final Review of Country Operations, 2000 - 2011 | Azerbaijan |  | 2012-11-06 | 1. A mechanism is required to secure government commitment to an ADB-supported forward program that is flexible in the context of shifting government priorities. ADB needs to adopt a flexible approach to its country program, in case the multi-tranche financing faciltiy (MFF) tranches do not materialize as envisaged. MFFs are generally approved for periods of up to 10 years, whereas country partnership strategies are approved for periods of 4 5 years. This flexibility could be either linked to updating the country operations business plan or defining a low-lending case or a base case scenario with results of support defined at entry for priority sectors. The evaluation period witnessed a shift in government's approach to economic growth from an early expeditious development of its oil and gas resources, to a more broad-based approach looking to long-term growth to reduce poverty and raise living standards. ADB initiated the shift in its strategic focus from direct support to internally displaced persons, agriculture and rural development, water supply and sanitation, and rural roads until 2006, to the transport, water supply and sanitation, and energy sectors starting from 2007. While ADB failed to secure commitment from the government for its planned full country and strategy program in 2006, it slowly and in an incremental manner developed its program in roads, water supply, and power. project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Country Context: Prioritization 2. A shift from investment program financing to provision of more knowledge services and technology facilitation is needed in upper middle-income country contexts. With the majority of the ADB-supported projects still ongoing, chances are high that most would be carried forward into the next country partnership strategy period. However, like Kazakhstan, another upper middle income country in the region, ADB needs to look beyond provision of investment program financing to knowledge services that add value. In the roads multitranche financing facility (MFF), efforts are ongoing to develop a study on a legal and regulatory framework and operational procedures for toll roads. Similarly, in the Urban Services MFF, a twinning arrangement is being finalized between Azersu, the executing agency and an international water utility for sustained institutional and organizational capacity development. ADB needs to build on these efforts to develop systematic policy advisory support and targeted capacity development in its sectors of engagement. Such an approach would enable continued ADB engagement in targeted sectors through a lowlending scenario, even if there were changes to the government's policy on external borrowing. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Finance & Financial Aspects: Financing 3. A focus on non-physical components, specifically Capacity Development, is essential to maximize the development effectiveness of investments in physical components. The capacity of the executing and implementing agencies has varied across ADB sectors of engagement, and capacity development efforts in the past have been part of ADB investments. Much of the previous focus has been on developing organizational capacity through, for example, preparation of manuals and training materials. In-country consultations highlighted that non-physical components, and especially Capacity Development, need to be given more attention through the forthcoming country partneship strategy period. The World Bank experience has included the use of funding pools earmarked for preparation and implementation of projects in priority sectors, in addition to individual capacity development components within sector investments. While, the former approach raises sustainability issues after closure of funding pool, the latter approach raises difficulties in reporting improvements at institutional, organizational, and individual levels. Predefined actionable indicators, which cover policy, regulatory issues (upstream), corporatization issues of service providers in the sector (mid-stream), and service delivery (downstream) are needed. project cycle stage: Design, Country Partnership Strategy Lesson Topics: | Country Partnership Strategy Final Review |  | http://www.adb.org/documents/azerbaijan-validation-final-review-country-operations-2000-2011
Urban Water Supply and Sanitation Project | Azerbaijan | Water and other urban infrastructure and services | 2011-12-01 | Understanding the sector environment in new member countries is important. When engaging in a new sector or country, understanding the key sector participants and their agendas, as well as developments in the sector is important. This will improve the project design and increase the likelihood that the project will have strong government support. Use phased reform programs. Radical reform programs, especially if they carry political risks, are likely to result in government resistance, unless the government strongly supports the concept. A phased long-term reform program is more likely to gain government support, especially if each stage is aligned with government objectives. Use conservative cost estimates and ensure sufficient funding. The funding allocation should be sufficient to cover project costs; if it is not, the project scope should be reduced or the funding allocation increased with no delay during implementation. Ensure the government understands the proposed project. Ensure that government agencies fully review and understand proposed projects. Reconfirmation with all relevant agencies is critical. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/urban-water-supply-and-sanitation-project
East-West Highway Improvement Project | Azerbaijan | Transport | 2011-11-01 | The project was the first of the ADB-assisted road projects in Azerbaijan. Many lessons were learned during project preparation and implementation. The main lessons are summarized below: Azerbaijan experienced sharp increases in the prices of fuel, utilities, and major road construction materials between project appraisal and detailed design. These led to significant changes in the project scope and financing plan. In future road projects, greater due-diligence needs to be undertaken during project design and formulation, which includes carrying out adequate cost estimations, setting aside enough resources to cover contingencies, and shortening the interval between appraisal and implementation. The contractor for the Gazakh-Georgian border section was perhaps not familiar with the country's situation at the start, and this caused mobilization delays and difficulty in finding suitable local subcontractors. In future road projects, the Ministry of Transport (MOT) needs to provide bidders with adequate local information at pre-bidding meetings, and publish information on the cost of locally available inputs (materials, equipment, and labor) on its website to allow bidders to submit sensible bids. The project was cofinanced by several external aid agencies. This modality proved to be suitable for financing the rapid development of the road subsector. In future road projects financed by multiple aid agencies, the Azer Road Service Open Joint-Stock Company (ARS) needs to strengthen its project management capacity in the aspects of financial accounts, project scheduling, and quality control. At appraisal, the project was designed to cover two subsectors: roads and customs. Projects of this type, covering different administration sectors, need adequate guidance and coordination. A project coordination office may be established at the central government to coordinate project management and implementation activities between the concerned government agencies. The implementation delay for the local roads component resulted in the shifting of this component to subsequent ADB-assisted projects. As local road development can efficiently bring project benefits to rural areas, especially to the poor, in future road projects more attention should be paid to the development of local roads, an integral part of the country's road network. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/east-west-highway-improvement-project
Second Capital Market Development Program: Completion Report | Bangladesh | Finance | 2015-09-08 | Several sustainability lessons from CMDP II (Second Capital Market Development Program) may be relevant to future interventions. A key aspect was following an integrated approach fostered through consultations. Policy coordination under CMDP II resulted in ensuring identification of responsibility and minimal replication of effort. In addition, CMDP II correctly understood the shortcomings in the government's response to the crisis, related to poor surveillance and failure to address the underlying causes in weak governance and incompatible incentives. At the outset, CMDP II proactively proposed remedies with proven records in addressing governance issues in the exchanges, especially demutualization. project cycle stage: Implementation An important aspect of CMDP II (Second Capital Market Development Program) was using a crisis as an opportunity to push reforms. This was reflected in CMDP II design that resulted in mutually reinforcing actions that simultaneously addressed the causes behind the crisis and expanded the financial sector to meet the needs of the real sector. In this regard, fundamental reasons for the crisis were the falsification of financial statements and the consequent exploitation of small investors. The accreditation system for auditors will help promote market information credibility. These actions provided mechanisms to restore investor confidence and encourage issuances and expanding products. However, the continuing weakness in the corporate debt market infers a lack of focus on issues related to market distortions and the absence of a recovery mechanism. Addressing these factors will fill gaps in the market and dovetail CMDP II achievements. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/second-capital-market-development-program-pcr
Second Rural Infrastructure Improvement Project: Completion Report | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2015-09-08 | Need for a high-level coordinating body. For a complex, multicomponent project, regular monitoring of implementation progress by the government through a high-level and active plenary body or steering committee is indispensable. Regular interaction among the borrower, stakeholders, consultants, contractors and suppliers, and ADB through the executing agency's PMO (project management office) contributed greatly to the success of the project. project cycle stage: Implementation Plan and coordinate preliminary activities well to minimize delays. The executing agency needs to pursue a set of well-planned and concerted actions to ensure timely completion of all critical activities for identification and appraisal of subprojects; government approval of the initial environmental examination, environmental management plan, and resettlement plan as appropriate; recruitment of consultants; streamlining the procurement of civil works contracts; and continuous cooperation among the executing agency and LGIs (local government institutions). The delay in project implementation is attributed mainly to protracted recruitment and fielding of the consultants and the consequent delays in preparing the SARs (subproject appraisal report). project cycle stage: Appraisal, Implementation Use advance actions. The project experienced delays of 24 months for several reasons. The absence of borrower's advance action largely contributed to these start-up delays and affected project implementation. ADB has been emphasizing this issue through its country and tripartite portfolio review meetings, and has included in most ADB-assisted projects provisions for advance action for selection of consultants, selection of subprojects, stakeholder consultation, and preparatory work for land acquisition and resettlement, if applicable. project cycle stage: Implementation Ensure sufficient consultation during project preparation. DFID's Department for International Development [United Kingdom]) decision to reduce substantial portions of its funding during project implementation indicated the need for greater consultation among cofinanciers, borrower, and other stakeholders during project preparation. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-infrastructure-improvement-2-pcr
Secondary Education Sector Development Program: Completion Report | Bangladesh | Education | 2015-09-08 | Implementing reforms under a project loan is generally difficult and less effective in accomplishing outcome than having a dedicated separate program loan meant for pursuing reforms. project cycle stage: Implementation The decentralization of DSHE (Directorate of Secondary and Higher Education) at all levels needs political will and supportive top level administrative decision to bring efficiency and transparency through bottom-up management. Without an effective and meaningful decentralization, DSHE may find difficulty in implementing the secondary education sector development plans in the future. project cycle stage: Implementation Where implementation delays are inevitable, advance actions, proactive project management, and effective progress monitoring are helpful to achieve timeline and targets. project cycle stage: Implementation Many project implementation support staff were recruited and trained. These staff gained valuable experience under SESDP (Secondary Education Sector Development Program) but could not be retained in the follow-up SESIP (Secondary Education Sector Improvement Program). Although it will benefit the education sector broadly, it is more efficient for the project to retain the trained officials. project cycle stage: Implementation Strengthening the role and capability of the head teacher as a mentor is a key to improving the school performance. project cycle stage: Operation Increasing the number of female teachers in secondary schools, particularly in the rural and especially in remote areas is difficult, but for quality of education, this is needed. project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/secondary-education-sector-development-program-pcr
Secondary Towns Integrated Flood Protection Project (Phase 2): Completion Report | Bangladesh | Water and Other Urban Infrastructure and Services | 2015-09-08 | The BWDB (Bangladesh Water Development Board) and LGED (Local Government Engineering Department) lacked the expertise to prepare tender documents and accurately survey, design, estimate, monitor, and supervise the construction of flood control and drainage structures. Thus, consultant services are needed to ensure the timely completion of all activities to a high standard. project cycle stage: Design, Implementation, Completion A design focusing on both physical and logistical issues and outputs and involving highly qualified experts was key to mitigate flooding and drainage congestions thoroughly and sustainably, improving living conditions in the towns as well as their economic. project cycle stage: Design Land acquisition in secondary towns can be a lengthy process and can cause significant delays in startup and implementation. Addressing the issue requires strong support from the relevant city corporations and district administrators, motivational campaigns, and adequate compensation packages. Advancing the preparation and approval of the Development Project Proforma to secure necessary funds for land acquisition early in project processing can reduce project startup delays. project cycle stage: Implementation Project implementation delays could be reduced reasonably through careful and efficient recruitment of consultants, early land acquisition and resettlement, proper surveys, and the motivation of city corporations. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/secondary-towns-integrated-flood-protection-project-phase-2-pcr
Road Safety Improvement Programs: Technical Assistance Completion Report | Bangladesh | Transport | 2015-09-01 | Road safety work in Bangladesh remains at the sidelines of operations of the concerned agencies. They are not properly coordinated, resourced, funded and empowered. In this regard, creation of an independent, well-resourced, funded and empowered NRSA (National Road Safety Authority) is critical. Should such body existed prior to the initiation of the TA (technical assistance), the uptake of TA recommendations could be much higher. Project cycle stage: Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/road-safety-improvement-programs-tcr
Small and Medium-Sized Enterprise Development Project: Completion Report | Bangladesh | Finance | 2015-09-01 | Definition of SME (small and medium-sized enterprise). The Ministry of Industries defines enterprises as cottage, micro, small, medium, and large enterprises, on the basis of'employment' and'fixed investment'. As SMEs, by definition, refers to small and medium-sized enterprises, the nomenclature is frequently misunderstood and used inappropriately to address cottage and micro enterprises as well. Surveys show that cottage and micro enterprises constitute 97% of all industries by number and employ 41% of the nonagricultural workforce. The SMEDP (Small and Medium-Sized Enterprise Development Project) financed 13,645 enterprises having on average 6.4 employees per enterprise, indicating that a vast majority of beneficiaries are cottage and micro enterprises. project cycle stage: Concept Data availability. There is no comprehensive, standardized, and updated database on the SME (small and medium-sized enterprise) sector that also includes cottage and micro enterprises. It is challenging to acquire reliable basic statistics, such as the number of SMEs and SME employment. The Sixth Five- Year Plan, 2011 - 2015 recognized the lack of data as a barrier to understanding the role of SMEs. In the absence of reliable key statistics, alternative inferential methods have been used extensively to assess the SMEDP's (Small and Medium-Sized Enterprise Development Project) performance parameters. The change in the definition of SMEs, incompatible presentations of data by various agencies, and complex definitions have complicated the understanding of the SME sector and its contribution to the national economy. project cycle stage: Concept, Implementation NBFIs (nonbank financial institutions) find the refinancing scheme more valuable. The funds disbursed through NBFIs increased to 48% of total facility for the SMEDP (Small and Medium-Sized Enterprise Development Project) compared to 20% for the previous SMESDP (Small and Medium Enterprise Sector Development Program). At the national level, banks and NBFIs disbursed SME loans at a rate of 87.8% and 2.2% in 2013. This disproportionate performance can be explained by the higher cost of NBFI funds as compared with banks, as the refinancing scheme provided them an opportunity to reduce their weighted average cost of capital. This indicates that NBFIs would be more interested than banks in any innovative interventions in the financial market. project cycle stage: Operation Women entrepreneurs. The SMEDP (Small and Medium-Sized Enterprise Development Project) disbursed 6.4% of the total facility to women-led SMEs, falling short of the target of 15.0%. Initial disbursements under this component were slow due to a lack of market awareness among women entrepreneurs. The target was also overly optimistic to comply with the provisions set out in the Refinance Scheme for Women Entrepreneurs of SME, given that the percentage of SME loans disbursed to women entrepreneurs was 3.4% - 3.9% during 2010 - 2013. The interest rate cap at 10.0% on loans to women-led SMEs might have also eroded PFI's (participating financial institution's) motivation for such lending, as PFIs usually lend to general SMEs at a much higher rate. project cycle stage: Concept, Implementation Subloan database. The reimbursement applications made by the PFIs (participating financial institutions) to the implementing agency were not standardized; the PFIs used different spellings in fields and the fields were different as well. This made analyzing the subloans for all 13,465 SMEs (small and medium-sized enteprises) (on the basis of location, industry, etc.) virtually impossible. The database would have been more effective if a standard reporting template with all required fields and their probable values had been prefixed. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/small-and-medium-sized-enterprise-development-project-pcr
Bangladesh-India Electrical Grid Interconnection Project: Technical Assistance Completion Report | Bangladesh | Energy | 2015-08-01 | The successful implementation of the first major grid to grid interconnection between India and Bangladesh has created opportunities for several more such interconnections in the region. South Asian countries have signed an energy trading framework agreement in November 2014 to facilitate development of energy generation resources to meet demand in the region. Institutions such as the Joint Steering Committee comprising the Power secretaries of the two countries and the Joint Working Group comprising power utility personnel played an important role in the timely design and implementation of the project. Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/bangladesh-india-electrical-grid-interconnection-project-tcr
Capacity Development for Bangladesh Bank: Technical Assistance Completion Report | Bangladesh | Finance | 2015-08-01 | A capacity development technical assistance (TA) is more likely to be effective when an executing agency has a strategic human resource plan in operations that aims at achieving well defined expected outcomes. In this context, the impact of the training is greatest when the selection of participants for training is based on objective criteria that can maximize the benefit from the training. Moreover, the effective dissemination of TA outputs can support the government to achieve a higher level of performance. Another important lesson is that in the discussions leading to the framing of the scope and components of TAs, governments should provide strong commitments and abstain from last minute changes to the agreed TA components including reversals of agreements?as was observed under this TA with the SRA and FSS (Systemic Risk Assessment and Financial Sector Supervision) re-allocation to another international financial institution?as these lead to inefficiencies and sub-optimal arrangements. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/capacity-development-bangladesh-bank-tcr
Chittagong Port Trade Facilitation Project: Validation of Completion Report | Bangladesh | Transport | 2015-02-10 | The PCR (project completion report) identified a few important lessons from the project. A more effective, high-level coordinating body needs to be established for a complex project of this nature, which comprised various groups of outputs. This could help regularly monitor a project's implementation progress. Planning and coordinating preliminary activities must be done well to minimize delays, including the use of advance actions. Sufficient consultation during project preparation should be undertaken in light of the CHC's (Customs House of Chittagong) decision during implementation not to use ADB funds for their automation program. project cycle stage: Implementation This validation offers a few lessons. During project implementation, constant follow-up is needed on the operationalization of the PPMS (project performance management system) and the conduct of baseline and other survey/data collection requirements that could be used in the PCR's (project completion report's) preparation. Likewise, the membership in the project coordination committee could have included a representative of the CCC (Chittagong City Corporation). While not directly implementing any component, the CCC could have expedited the implementation of activities within the Chittagong city proper and helped avoid delays. project cycle stage: Implementation | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/bangladesh-chittagong-port-trade-facilitation-project
Agribusiness Development: Project Completion Report | Bangladesh | Agriculture, natural resources and rural development | 2014-09-01 | Small enterprises should have been made more rewarding in terms of financial returns on investment and employment opportunities compared to medium and large enterprises. Due to improvement of technology; efficient use of increased capital cost, operating cost, and cost of labor; and ability to meet need for higher efficiency and demand for high quality standards of produce in the market, medium to large agribusiness enterprises are staying in the competition. The agriculture marketing subsector in Bangladesh is growing fast and requires public support for promotion, facilitation, legal and regulatory supports, and necessary infrastructure development and training. The future development of agriculture, agro-economy, and rural employment depends on the development of this subsector. There is a need for an appropriate and capable agribusiness development agency that can support future demand, which is now mandated to Department of Agricultural Marketing (DAM). The DAM has limited manpower, which needs to be strengthened at the district and sub-district levels. Through proper human resources management and capacity development of DAM staff through appropriate in-house and external training. Agriculture marketing associations are not well-organized and federated to meet the needs of the fast-growing domestic agriculture market of Bangladesh. The progress of value addition and supply chain development has been inadequate. The concept of value addition, supply chain management, and improved quality of products needs to be linked to export options, reduction of wastage, high quality standards, compliance with phytosanitary and public health standards, and an increased role of women at different levels of agribusiness development. There remains a need for continued support to women to enable them to diversify and scale up their enterprises, and gain access to upper levels of the value chain. The executing agencies should have had adequate capacity and experience in recruiting consultants to ensure timely availability of necessary consultant inputs. If necessary, advance actions should have been initiated to ensure the fielding of consultants in time. The participation of women improved project outcomes and gave them more opportunities in business, employment, skill development, marketing, and income generation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/bangladesh-agribusiness-development-pcr
Improvement of Capital Market and Insurance Governance TA Loan: Project Completion Report | Bangladesh | Finance | 2014-09-01 | Early proactive engagement with project stakeholders could have been done for readiness in critical areas. Although the project largely achieved its intended outcome and outputs and had significant impact on the capital market and insurance sector of the country, implementation began much later than scheduled because of delayed recruitment of consultants. Training component could be spread over the implementation period. The training component related to Investment Corporation of Bangladesh and Insurance Development and Regulatory Authority were not fully used because of time constraints and logistical problems. There appeared to a rush at the end of project period to find appropriate trainings. Commitment of stakeholders played crucial role to achieve success. Despite delay in recruitment of consultants, commitment and ownership of executing agency and implementing agencies played the vital role in achieving the intended results. Information could have been updated and stored in a better way. There have been difficulties in acquiring the project information needed to prepare the project completion report (e.g., a full set of consultant's reports). The underlying reason for the delay in consultant recruitment could not be discerned from the consultant recruitment and monitoring sheet because of the absence of detailed explanations for major delays. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/improvement-capital-market-insurance-governance-ta-loan-pcr
Second Urban Primary Health Care Project: Project Completion Report | Bangladesh | Health | 2014-09-01 | To minimize large variations in partner agreement nongovernment organization performance (PANGO), it is necessary to (i) evaluate, contract, and mobilize PANGOs within a specific time frame to avoid delays; (ii) critically evaluate budget proposals to ensure they are sufficient to deliver primary health care services; and (iii) set realistic selection criteria for evaluating the experience of PANGOs and their capacity to deliver services. Behavior change communication and marketing is important for expanding coverage of primary health care services delivery and raising awareness among partnership agreement area residents, especially women and children. Identification and targeting of the poor must be based on a simple set of criteria and supported by existing poverty maps or urban poverty mapping undertaken during project preparation. Eligibility requirements for obtaining red cards must be clear to households, and their application must be consistent across PANGOs and adhered to by providers in determining eligibility and distributing cards. To accurately measure health indicators and gather reliable data for evaluating project performance, it is necessary to regularly update the list of poor beneficiaries in order to effectively identify and track those who have left their respective partnership agreement areas and to collect data on unique individuals obtaining services at primary health care centers. Project management unit and project implementation unit staff must (i) have adequate capacity for procuring goods and services to avoid delays in contracting and awarding processes; (ii) ensure that tender documents contain bid criteria that are pertinent to the required works or consultancy services; and (iii) keep records of evaluation reports to enhance transparency and rigor, in line with undertakings under the ADB loan and grant agreements.69 For this purpose, the design of future projects should incorporate a dedicated procurement specialist to support the project management unit as well as training on ADB procurement and financial management guidelines and procedures for project management and implementation staff. Project management unit and project implementation unit staff must be trained (i) to proactively monitor funds flow, regularly update project accounts, and track loan and grant drawdowns in order to manage project funds effectively; and (ii) to regularly reconcile loan and grant accounts with ADB's records. To facilitate financial management, projects as complex as UPHCP-II should have an operational computerized financial management information system. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/bangladesh-second-urban-primary-health-care-pcr
Teaching Quality Improvement in Secondary Education: Project Completion Report | Bangladesh | Education | 2014-09-01 | Secondary school teachers, especially in nongovernment secondary schools, having relatively weak academic and teacher training background may not acquire enough teaching competency for quality teaching from one-time training; rather, they need repeated trainings. Cluster-based local training using indigenous training materials can ensure cost-effective teacher training. For secondary school teachers, expensive overseas study tours and training may not add appropriate skills and knowledge or represent good value for money. Training for inclusive education proved effective for creating an inclusive environment in schools, especially in remote and underserved areas. Inclusiveness is a common area of teacher training that demands mainstreaming. Continuous follow-up and support to school monitoring and supervision is critical for achieving desired school performance and quality standards. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/bangladesh-teaching-quality-improvement-secondary-education-pcr
Road Network Improvement and Maintenance Project II | Bangladesh | Transport | 2014-07-01 | Recruitment of supervision consultants and major civil works contractor was delayed by the Roads and Highways Department. This delay was further aggravated by problems with land acquisition and tree removals. In recent ADB-assisted projects in Bangladesh, advance work for land acquisition, tree removal and resettlement commenced before selection of civil works contractors. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/road-network-improvement-and-maintenance-project-ii-pcr
Chittagong Port Trade Facilitation Project | Bangladesh | Transport | 2014-06-01 | Complex projects need an effective high-level coordinating body. For a complex, multicomponent project, regular monitoring of the implementation progress by the government through a high-level plenary body or a steering committee is indispensable. Regular interaction among the borrower, the stakeholders, consultants, contractors and suppliers, and ADB through the executing agencies project implementation units contributed greatly to the success of the project. Plan and coordinate preliminary activities well to minimize delays. The executing agencies need to pursue a set of well-planned and concerted actions to ensure timely completion of all activities for land acquisition and resettlement, removal of utilities from rights of way, government approval of the initial environmental examination and environmental mitigation plan, and continued coordination with local government authorities. Delay in implementation of the Roads and Highways Department component was mostly attributed to delays in (i) procedures and decision making related to procurement, (ii) land acquisition and resettlement including removal of public utilities, and (iii) receiving clearance from Chittagong City Corporation on the construction of pier 19 of the flyover. Use advance actions. The project experienced implementation delays of about 42 months for several reasons. The absence of the borrower's advance action caused these start-up delays and adversely affected project implementation. ADB has emphasized this issue through its country programming review missions and tripartite project review missions, and has included in most ADB-assisted projects provisions for advance action for the selection of consultants, stakeholder consultation, and preparatory work for land acquisition and resettlement. Ensure sufficient consultation during project preparation. The Custom House of Chittagong's decision during implementation not to use ADB funds for their automation program indicated the need for greater consultation with the executing agencies and other stakeholders during project preparation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/chittagong-port-trade-facilitation-project-pcr
Power Sector Development Program (Project Loan) | Bangladesh | Energy | 2013-08-01 | 1. The Bangladesh Power Development Board corporatization target was a premature step, which underestimated the difficulties in the way of major reforms toward unbundling and corporatization in Bangladesh. The government has already changed its power sector reform agenda. Instead of corporatizing Bangladesh Power Development Board, it plans to restructure Bangladesh Power Development Board business functions into several generation and distribution strategic business units, which will operate under the existing legal structure and be functionally separate with more financial authority. The effectiveness of the strategic business units approach remains to be seen. 2. The construction of oil-fueled power plants by the public and private sectors increased Bangladesh Power Development Board's operational costs. The tariff increases by Bangladesh Energy Regulatory Commission in 2008-2012 were contrary to its tariff-setting methodology, which specifies at least a 10% return on assets. Rationalizing the tariff structure to provide an adequate margin to distribution entities can enable these entities to meet future financial requirements. 3. The cancellation of the Norwegian Agency for Development Cooperation funds and the delayed implementation of the Nordic Development Fund component affected consumer connection. A more reliable parallel financing arrangement has to be made to ensure the realization of designed project objectives. This matter needs to be addressed under ongoing and future loans16 for the power sector. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/power-sector-development-program-project-loan-pcr
Second Primary Education Development Program | Bangladesh | Education | 2013-02-09 | 1. Assessment of executing agency capacity is critical when embarking on an ambitious sector-wide approach and particularly so in a large, complex primary education system like that in Bangladesh with development partners cofinancing the project. The high number of vacancies and limited capacity of the Directorate of Primary Education were acknowledged during the design phase, which should have prompted a need to consider a preparatory phase to get minimum preconditions in place before beginning the implementation. In the Second Primary Education Development Program, the first 2 years prior to the midterm review mission became by default the preparatory phase for finalizing organizational arrangements and policies. project cycle stage: Lesson Topics: 2. A systemic approach to reforming the primary education system is required to address the complexity, complementarity and dependency of issues and organizations in primary education. To design such an integrated approach, a comprehensive subsector analysis to guide the scoping of the program and adopting realistic targets is necessary. The baseline study conducted by Directorate of Primary Education for the midterm review mission performed this function. project cycle stage: Lesson Topics: 3. Balancing the combined roles of development partners, as agency staff providing oversight on behalf of the agency and as experts providing technical advice, requires constant attention and reflection to ensure that the government remains in the lead during implementation and that development partners get sufficient information to exercise oversight. project cycle stage: Lesson Topics: 4. The use of consultant support with an evolving design requires flexibility. Therefore, packaging all consultant support in large lots through firms is not the best option. Institutional capacity development strategies should consider twinning between Bangladeshi and international institutions to developed capacity in the Directorate of Primary Education (DPE) and other local institutions. The international institutions can continue supporting the DPE after program completion. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-primary-education-development-program-pcr
Participatory Livestock Development II | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2013-01-10 | 1. Effective service delivery (of mobilization, training, credit support, technical services, and intensive monitoring) to a large number of rural poor spread over a wide geographical area is possible by establishing workable partnerships between partner nongovernment organizations and the government's service department. project cycle stage: Lesson Topics: 2. Livestock enterprises can be potential sources of an increase in income for the rural poor because of high demand for livestock products, the potential for high returns, and due to easy access of rural poor to livestock inputs and production techniques. project cycle stage: Lesson Topics: 3. The Department of Livestock Services field offices are able to provide improved technical services, e.g., artificial insemination, vaccination, de-worming, and treatment services for the sick animals to project beneficiaries through establishing effective coordination mechanisms and by ensuring capacity enhancement support. project cycle stage: Lesson Topics: 4. Selecting community extension worker from the local community, teaching them technical skills, supplying starter kits to them, and deploying them in the community worked well for service delivery and for establishing linkages amongst project beneficiaries and between the Department of Livestock Services field offices and non-government organizations. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/participatory-livestock-development-2-bangladesh-pcr
Jamuna-Meghna River Erosion Mitigation Project | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2013-01-07 | 1. Strengthen institutional capacity for adaptive and cost-effective design and implementation of riverbank erosion and management. The Bangladesh Water Development Board's (BWDB) institutional capacity has been strengthened for implementing cost-effective riverbank erosion mitigation. To this end, Guidelines for Riverbank Protection were developed under the project and approved by BWDB's management. This is treated as a knowledge product of ADB. The lesson from this has also been replicated regionally in a similar project funded by ADB in Assam, India. project cycle stage: Lesson Topics: 2. Improve disaster preparedness and risk management against flood hazards induced by riverbank erosion. A riverbank erosion prediction model was developed under the project, and is still in use by Bangladesh Water Development Board. Dissemination of information on predicted bank erosion from the model requires improvement. project cycle stage: Lesson Topics: 3. Strengthen community-based irrigation and water resources management through water management associations. ISC collection and timely operation and maintenance (O&M) activities require improvement, through motivational drive to pay irrigation service charge and improved O&M planning and timely allocation of funds. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/jamuna-meghna-river-erosion-mitigation-project
Road Network Improvement and Maintenance Project: Project Completion Report | Bangladesh | Transport | 2013-01-03 | 1. The project experienced substantial implementation delays of about 54 months. Protracted recruitment of detailed design and construction supervision consultants, delayed procurement of the major civil works contracts, delayed land acquisition and resettlement, and most importantly, underperformance by a major civil works contractor compounded the delays. Delays in procurement of the civil works contracts were mostly due to government delays in procedures and decision making related to procurement, land acquisition, and resettlement. The Roads and Highways Department's capacity to plan and monitor resettlement activities must be enhanced, with ADB's assistance. In the absence of any advance action prescribed by the project, recruitment of the detailed engineering and construction supervision consultants was inordinately delayed (by 23 months). This adversely affected the preparation of detailed engineering design and final selection of the road alignment, delaying land acquisition and awarding of civil works contracts. ADB highlighted this issue, through its country programming review missions, and has since included, in most ADB-assisted projects, provisions for advance action for selection of consultants, and preparatory works for land acquisition and resettlement. project cycle stage: Lesson Topics: 2. A contractor's ability and commitment to deploy resources for civil works in good time is key to overall performance. While ADB's standard prequalification and bidding documents are devised to ascertain the bidders' technical and financial capabilities, further clarification is sometimes required to support the information provided by the bidders. The bidding process therefore needs further streamlining, particularly through ensuring that sufficient clarification is obtained by the executing agency, to verify the bidders' capacity to comply with qualifying criteria on financial resources, equipment, and personnel. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/road-network-improvement-and-maintenance-project-pcr
Public Expenditure Support Facility Program and Countercyclical Support Facility Support Program | Bangladesh | Agriculture, natural resources and rural development, Finance, Industry and trade, Public sector management | 2012-10-01 | The program's implementation yielded important lessons. Most importantly, policy actions and reform measures need to be integrated into the government's own development agenda to ensure commitment and continuity beyond the program period. Additionally, effective coordination and high-level alliances will likely ensure the successful completion of a project or program. For this program, assigning the Ministry of Finance (MOF) as the executing agency and forming a steering committee chaired by the Finance Secretary were crucial steps that allowed for the efficient allocation of resources and the spearheading of diverse reforms across 10 ministries and agencies. Despite the presence of conditions (as in the public expenditure support facility or PESF), capacity constraints need to be taken into account to set an achievable target within the stipulated timeframe. Alternatively, the program should have included a piggyback technical assistance (TA) in areas where capacity was lacking and implementation weak. For better monitoring of implementation and evaluation of outcome, particularly for poverty reduction through social safety net programs (SSNPs), a TA for developing an instant poverty survey would have been more ideal than relying on the low-frequency (updated every 5 years) household income and expenditure survey (HIES) to establish poverty reduction achievements and SSNP coverage. The lack of a rigorous monitoring mechanism and dedicated survey to collect required information and data hindered a systematic measuring of program's impact on poverty reduction and gender equity. The program, in particular the countercyclical support facility (CSF), met all three core criteria for effective delivery of countercyclical measures: it was targeted, timely, and temporary. The program was directly targeted at the poor and the vulnerable whose livelihoods were affected by the global economic crisis. Income support and employment generation programs not only directly benefited the poor, but also increased aggregate demand through multiplier effects. The program also enabled the government to implement fiscal stimulus to support crisis-affected sectors and strategic sectors. In addition, policy actions under the PESF pinpointed sectors that could generate employment and higher growth, such as small and medium-sized enteprises (SMEs), the annual development program (ADP), and the private sector. The program was timely and was provided when it was most needed and when adverse impacts were widely felt. The government announced the countercyclical programs in June 2009 and requested ADB assistance in August 2009. The business processes were streamlined to ensure fast processing and quick disbursement. From Board approval to disbursement, the entire CSF and the first tranche of the PESF took only 3 weeks (from 13 October to 6 November 2009). Despite ADB having expedited the entire processes, capacity constraints in spending ministries and agencies caused delays in the effective and timely utilization of allocations. The CSF was a temporary, one-off lending instrument used to fund the government's key countercyclical measure. Its temporary nature was discussed with the government and it was therefore earmarked to support the quick disbursement nature of SSNPs. The temporary nature of the CSF is consistent with the process of fiscal consolidation in Bangladesh over the medium-term. In this regard, the CSF benefited from PESF support. Reforms made under the PESF helped strengthen the policies and public accountability mechanisms necessary for the more efficient use of public resources and a more sustainable budget. Both support facilities were critical to the crisis response of Bangladesh as no other development partners provided any crisis-related assistance or program support during the program period. However, the pricing (interest spread of 200 basis points above the London Interbank Offered Rate or LIBOR) and maturity (5 years) of the CSF loan makes it is less suitable for a poorer country like Bangladesh. While the higher pricing and the fixed 5-year tenor of the CSF took into account various considerations including containing the demand and rationalizing the allocation to each of the selected developing member country out of the limited CSF pool,17 it may be too hefty for Bangladesh with growing financing gaps and given the safety net nature of the program. A blend of higher borrowing costs to support policy actions that generate higher economic rates of returns on the supply side (such as SME development and public-private partnership or PPP investment) may be more desirable. Effective coordination between the Bangladesh Resident Mission and ADB headquarters and optimal delegation of responsibilities were important for achieving program outcomes. The resident mission, with its knowledge of local conditions and access to government and nongovernment agencies, contributed to effective monitoring and implementation, enabling the program outputs to be achieved. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/pesf-program-and-csf-program-pcr
Emergency Assistance for Food Security Project | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2012-02-07 | 1. Safety net programs are proven effective for mitigating critical food crises at times of price increases and natural disasters. Implementation of safety net programs requires experienced and committed human resources for food management, transparent identification of beneficiaries, and systematic and efficient distribution of food grains among beneficiaries. Finally, close monitoring oversight and evaluation are essential for improving the implementation and impact of safety net programs. A strong track record associated with strong institutional capacity and web-based stock management by efficient and skilled human resources is a prerequisite to success. [Main text, para. 53] project cycle stage: Lesson Topics: 2. Experience from the project demonstrates that prompt loan processing and disbursement is crucial to success of such budgetary support provided during a crisis situation. [Main text, paras. 10, 11, 54] project cycle stage: Lesson Topics: 3. For short-duration and emergency assistance projects, ADB should maintain better coordination with the executing agency throughout the whole project period and afterward to assess the project's impact in the next few years. [Main text, para. 55] project cycle stage: Lesson Topics: 4. As experienced in all past ADB-financed emergency assistance projects in Bangladesh, delegation of authority to the ADB resident mission in the borrower's country is essential for effective monitoring and immediate decision-making. [Main text, paras. 16, 29, 30, 56] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/emergency-assistance-food-security-project
Urban Governance and Infrastructure Improvement (Sector) | Bangladesh |  | 2012-02-07 | For a complex multi-component project, regular monitoring of the implementation progress and pourashava performance by the executing authority is indispensable. Regular interaction between the borrower and ADB, and ADB and the pourashavas through the projec management office contributed greatly to the success of the project. The use of a sector modality proved highly appropriate for performance-based allocation of funds among the competing pourashavas. This approach should be followed in all future ADB assistance to the pourashavas. However, when implementing a multi-component urban development project spread over a large geographical area, provision for strong consultant support, and advance action to select and field the consultants immediately after loan effectiveness is important to avoid startup delays. The government needs to put in place a powerful central monitoring system, preferably embedded in the Local Government Division, to regularly review and assess the progress and sustainability of urban development. Implementation experience suggests that secondary towns development projects generally require capacity building in the pourashavas and strong institutional support. [Main text, paras. 40, 41] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/urban-governance-and-infrastructure-improvement-sector
Second Small-Scale Water Resources Development Sector Project | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2012-01-08 | 1. Information campaigns through subproject fact sheets as part of the member education program, and the project newsletter proved more successful than the nongovernment organization facilitator. Bylaws were well drafted by the executive committees of the water management cooperative associations. [Main text, para. 60(i)] project cycle stage: Lesson Topics: 2. The project had significant positive impact through increased crop and fish production and through its micro-credit operations. [Main text, para. 60(ii)] project cycle stage: Lesson Topics: 3. Project delays could have been reduced significantly if the project director and other staff had been appointed on time, if competent consulting firms were managed for timely delivery and if the contracts had provided for price increases. [Main text, para. 60(iii)] project cycle stage: Lesson Topics: 4. The quality of subproject planning and design depended on the quality of the consulting firms and their staff. National consulting firms for the feasibility studies and detailed design should therefore have been better managed by the Local Government Engineering Department. [Main text, para. 60(iv)] project cycle stage: Lesson Topics: 5. the Local Government Engineering Department should have submitted withdrawal applications on time and ADB disbursements against the applications also had to be timely, to sustain the flow of funds. [Main text, para. 60(v)] project cycle stage: Lesson Topics: 6. The establishment of the Integrated Water Resources Management Unit (IWRMU) in 2003 to monitor completed subprojects further enhanced the commitment of Local Government Engineering Department to the sustainable management of small-scale water resources subprojects. The current frequency of staff transfers and re-posting at the IWRMU, on the other hand, diminishes initiative and commitment to work. [Main text, para. 60(vi)] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-small-scale-water-resources-development-sector-project-completion-report
Northwest Crop Diversification Project | Bangladesh | Agriculture, natural resources and rural development, Finance | 2011-11-01 | Project delays could have been reduced significantly by identifying and deploying qualified staff during project preparation, keeping those staff throughout implementation, obtaining early government approval for the project, and taking advance action on the recruitment of consultants before the loan agreement was signed. The issues of land ownership and operational responsibilities needed to be clearly settled between public ministries and departments before the project embarked on market construction. This was particularly important for revenue-earning infrastructure like markets. More time than was envisaged at appraisal was needed to form output-oriented farmers' marketing groups (FMGs) and to put them into operation. To ensure that the markets to be built under the project would be successful, the project needed to seek the participation and take into account the opinions of local stakeholders when selecting the sites for market construction. All project components should have been based on need assessment. This was particularly true of the activities for agribusiness credit piloting and infrastructure for marketing and the facilities at the horticulture training and demonstration centers (HTDCs). Failure to assess needs and conditions for these components adequately meant that the outputs were not used fully or successfully. Post-project monitoring and evaluation systems need to be designed for the project during the planning phase to ensure ongoing innovation and sustainability of the project impacts. The selection of capable nongovernment organizations (NGOs) was critical to ensuring effective delivery of services and for sustaining project activities. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/northwest-crop-diversification-project
Small and Medium Enterprise Sector Development Program | Bangladesh | Industry and trade | 2011-08-01 | Proper sequencing and program readiness. Proper sequencing of program activities is essential to ensure success. In the case of the Small and Medium Enterprise Sector Development Program (SMESDP), gaps in program readiness led to delays in its implementation. As discussed in para. 8, adoption of a two-step approach would have been more appropriate; first, the technical assistance (TA) loan to prepare the outputs needed and recommendations for implementation, followed by a second step of putting the SMESDP in place to implement the recommendations of the TA loan. The two-step approach might have taken a slightly longer time to implement, but it would have facilitated a smoother implementation of the program and ensured greater efficiency in achieving the program's outcome and outputs. In addition, a project readiness filter could have been put in place to ensure readiness to implement the SMESDP the moment it became effective. Compliance with the repor and recommendation of the president (RRP) recruitments. The requirements for goods and services as incorporated in the RRP and loan agreement need to be strictly followed while preparing the technical assistance project proposal (TPP) to ensure smooth TA implementation. Due to misunderstandings by the executing agency, the TPP prepared by the government was not able to meet the requirements; causing two problems. The first problem relates to the recruitment of consultants whose expertise did not match as mentioned in the RRP e.g., recruitment of two domestic consultants for rationalization of government assistance for small and medium-sized enterprises (SMEs) when the RRP specified that two international experts namely restructuring expert and SME strategic development specialist, were needed for that purpose. The selection of two domestic consultants instead probably compromised the quality of output and caused considerable delay in processing the rationalization measures for Bangladesh Small and Cottage Industries Corporation (BSCIC) and Small and Cottage Industries Training Institute (SCITI). The second problem relates to the need for making amendments to the TPP that involved time-consuming procedures and caused delays in the recruitment of the needed consultants. All these led to an overall delay of about 2.5 years in closing the TA and program loans, thus caused delay in releasing the second tranche of the program loan. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/small-and-medium-enterprise-sector-development-program
Emergency Disaster Damage Rehabilitation (Sector) Project | Bangladesh | Agriculture, natural resources and rural development, Public sector management, Transport | 2011-06-01 | For complex multisector projects, monitoring of implementation through a central project steering committee (PSC) at a plenary ministry of the borrower is indispensable. Regular interaction between the borrower and ADB through the PSC contributed greatly to the success of the project. The use of a sector approach proved highly beneficial in identifying eligible subprojects spread over a wide geographical area, and enabled reallocation of loan funds from one component/sector to another based on a final needs assessment and performance. Disbursement of funds through separate imprest accounts for the executing agencies handling the contracts also proved to be efficient. When implementing an emergency assistance project, provision for strong consultant support and advance action to select and field them immediately after appraisal proved important. In Bangladesh, the Local Government Engineering Department (LGED) and Roads and Highways Department (RHD) are still the two agencies that are reasonably capable of implementing ADB-assisted emergency projects. Implementation experience suggests that emergency assistance projects generally require adequate program for capacity building in the executing agencies, with strong institutional support regarding contract administration and fostering familiarity with ADB procedures for procurement and disbursement. This will help ensure timely completion of contractual works, submission of withdrawal applications, and liquidation of imprest accounts. Experience from the project demonstrated that the adoption of simplified approval procedures for procurement and other project activities is effective and enabled timely implementation of the project, and catalyzes early restoration of people's livelihood in the project-affected areas. As experienced in all past ADB-financed emergency assistance projects in Bangladesh, delegation of authority to ADB's resident mission in the borrower's country is essential for effective monitoring and immediate decision making. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/emergency-disaster-damage-rehabilitation-sector-project-1
Dhaka Clean Fuel Project | Bangladesh | Energy | 2011-01-04 | 1. Dependence on consultants for project preparation and implementation undermines the initiatives of executing agenciesï¿½ staff for implementing projects on time and for maintaining satisfactory standards. Therefore, executing agencies should build in-house capability to prepare and implement projects. project cycle stage: Lesson Topics: 2. Timely acquisition of land is a fundamental requirement for successful completion of a project. The acquisition process should start earlier, maybe before appraisal, so that possession of land can be achieved before loan effectiveness. project cycle stage: Lesson Topics: 3. The executing agencies should use the advance-action provision of ADB to their best. As a result, contracts could be signed immediately after loan effectiveness and the project could be successfully completed. project cycle stage: Lesson Topics: 4. The onlending facilities to the private sector through commercial banks worked well under the project. This modality may also be used in future for private sector financing. project cycle stage: Lesson Topics: 5. The loan covenants should be clearly set during project design so that they can be monitored properly during project implementation. project cycle stage: Lesson Topics: 6. The design and supervision consultancy contract should ensure that the supervision services are made available during construction even if the mobilization of construction work is delayed by a considerable period. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/dhaka-clean-fuel-project
Chittagong Hill Tracts Rural Development Project | Bangladesh | Agriculture, natural resources and rural development, Finance, Transport | 2010-12-01 | The project was initiated and prepared in 1999-2000, only 2 years after the signing of the Peace Accord, ending 25 years of insurgency and instability. Many high-risk incidents during project implementation could therefore be expected. The executing and implementing agencies had just been established, and their institutional capacity to implement projects was still being developed and strengthened. The unilateral withdrawal of a relatively large amount of cofinancing by Danida (around 50% of the total amount allocated for the rural access component) after project approval considerably delayed implementation and created difficulties in meeting project objectives and targets. The cofinancing was unfortunately a condition of loan effectiveness. The project was declared effective in October 2002, after the cofinancing condition was declared void. The withdrawal of cofinancing coincided with United Nations Development Programme's (UNDP) suspension of all missions to the Chittagong hill tracts or CHT (2001- 2002) due to the kidnapping of Danida experts, and project activities could start only in early 2003. The improvement of connectivity and access between rural and remote areas of the CHT, especially with the market centers, was crucial for development. The project directly and indirectly affected all aspects of rural life in the CHT. During the project completion review mission and earlier missions, villagers asked whether more livelihood projects would be provided in their area. When designing and implementing rural infrastructure in remote areas with indigenous populations as potential workers and beneficiaries, there must be a careful review of local habits and customs to understand how these can accommodate the common modalities of civil contracting. The original project schedule was too optimistic and did not leave enough time for careful review and adjustment. In such a case, a component that does not suit the needs of a specific target population could leave that population unserved or bypassed. For example, jhum cultivators did not benefit much from the project components except from the improvements in rural access. The rural roads improved under the project generally established all-weather connectivity between remote communities and growth-center markets and other important centers with economic, health, and educational facilities. Nongovernment organizations (NGOs) and other government service providers could also reach rural remote inhabitants more easily. The sustainability of several community development subprojects owned by beneficiary groups was considered an issue during implementation. However, except for a few specific technical support requirements, the beneficiary groups assumed responsibility for activities such as the maintenance of small irrigation and power tiller schemes. Besides, several group members also gained access to micro-credit through the project. The Palli Karma Shahayak Foundation (PKSF) or other NGOs may further expand their microenterprise activities in the CHT after the project. Before the project, microfinance was nearly absent in the rural areas of the CHT. The project introduced a relatively sustainable microfinance arrangement through local NGOs. Despite the existence of the other project providing grant assistance, the microfinance facilities under the ADB project are gradually expanding to meet demand in remote communities. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/chittagong-hill-tracts-rural-development-project
Rural Infrastructure Improvement Project | Bangladesh | Agriculture, natural resources and rural development, Transport | 2010-09-01 | Advanced Procurement Action. Early procurement for contract packages is absolutely essential to enable projects to meet their implementation schedule. In this case, the major civil works contract packages for year 1 were prepared by the Local Government Engineering Department (LGED) during the feasibility study before the project consultants were mobilized and the subproject appraisal reports (SARs) were prepared. Early recruitment of the consultants would have improved the performance of the project in the early stages. The recruitment process should be simplified to avoid delays. Subproject Appraisal Reports. Since SARs were prepared for each upazila, 96 SARs were produced. This was a huge and time consuming task that took almost two years to complete. It is recommended that future projects should produce SARs on the basis of districts or regions rather than upazila. This concept would have reduced the number of reports to 16 if prepared on a district basis or 2 if prepared on a regional basis. Drinking Water in Market Developments. The project has installed on a pilot basis a low-cost piped water supply system for drinking purposes at Haibatpur Growth Center in Jessore district, which is an arsenic-affected area. A water management committee within the market management committee (MMC) is managing the operation and maintenance of the system, and collects user fees. This approach to the supply of low-cost water in a growth center market (GCM) has proven to be feasible and may be replicated in future projects, while taking its shortcomings into account. For example, house connections could make it more viable. Women's Market Section (WMS). The project made an effort to include WMSs in all market developments to bring women more into the mainstream of the rural economy. However, women in some areas are conservative and not willing to run shops side-by-side with men. WMSs should only be included in market developments where project appraisal indicates that women are interested and available to participate in running the facilities; otherwise, the resources can be used elsewhere. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-infrastructure-improvement-project
Bangladesh: Road Maintenance and Improvement Project | Bangladesh | Transport | 2010-08-31 | There is a need to avoid including conditions in loans that depend on passing or amending legislation, or seeking high-level approval, such as from the Cabinet. This was the case in the road maintenence component that sought annual allocations in the budget for road maintenance. Projects that require legal or high-level administrative changes often experience major delays or fail to meet their objectives. [Main text, page 9, section E(ii)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/bangladesh-road-maintenance-and-improvement-project
Dhaka Power System Upgrade Project | Bangladesh | Energy | 2010-01-12 | 1. ADB needs to pay more attention to capacity assessment during inception. The executing agencies had insufficient capacity to carry out procurement, bid evaluation and other processes, resulting in significant delays. This capacity deficit within the executing agencies was not identified during inception. [Main text, paras. 39,45,62] project cycle stage: Design, Implementation Lesson Topics: 2. Caution is in order in concurring with major changes in project scope. The scope for Part C of the project changed from initiating preparatory work for launching a training and management institute at the Rural Electrification Board - to physically constructing the institute. Its implementation though has suffered from price escalation, scarcity of construction materials, and internal disputes among partners in the contractor's consortium. As a result, after more than eight years since ADB's approval of change in scope, the construction of the training institute remains to be completed. Such kind of major change in scope must be avoided. [Main text, paras. 26,63] project cycle stage: Design, Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/dhaka-power-system-upgrade-project
Bangladesh: Third Natural Gas Development Project [Loan 1293-BAN(SF)] | Bangladesh | Energy | 2009-12-31 | 1. The terms of reference of project preparatory technical assistance consultants needs to include obtaining project equipment prices in the open market and subsequent cross checking of prices with more than one supplier. Cost underruns were experienced for parts A (Bangladesh Gas Fields Company Limited) and D (Jalalabad Gas Transmission and Distribution Systems) of the project partly because equipment cost estimates were based on tied loan prices. [Main text, paras. 14,17,81] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Management: Procurement Sector Related Issues: Energy planning/management 2. The delays in procurement of materials under the project necessitated the resident mission to perform more rigorous and detailed follow-up of executing agency (EA) procurement action. Monthly estimate sheets were provided by the EAs to ADB to show progress and pinpoint where delays were taking place. This should become a fixture in future loans to the Bangladesh gas sector, and should be incorporated in project administration memorandums. [Main text, para. 82] project cycle stage: Implementation Lesson Topics: Project Management: Procurement Sector Related Issues: Energy planning/management 3. Whenever possible, selection of implementation consultants needs to be undertaken prior to project approval to avoid substantial delays in project implementation. All too often, ADB approves advance selection of consultants but executing agencies do not take advantage of this opportunity. Future loans to the gas sector of Bangladesh requires ADB missions to strongly encourage executing agencies to select consultants in time for project implementation and to take advantage of ADB s permission for advance recruitment of consultants. [Main text, para. 18,38,57,83] project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Sector Related Issues: Energy planning/management 4. It is more practical to hire a consulting firm rather than individual consultants as this gives the project greater flexibility in changing consultants as and when needed. The project engaged individual consultants through firms. The prolonged implementation period required changing of individual consultants, and the firms were able to provide suitable replacements when required. [Main text, paras. 38-40,84] project cycle stage: Implementation Lesson Topics: Project Management: Consultants Sector Related Issues: Energy planning/management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/bangladesh-third-natural-gas-development-project-loan-1293-bansf
Country Assistance Program Evaluation for Bangladesh (2009) | Bangladesh |  | 2009-10-31 | 1. A gradual approach to reforms and continuity in programming can facilitate sector efficiency and effectiveness. ADB's experience in the energy sector shows that, in an environment with weak institutions, a gradual approach to support reforms can limit risks to ADB-financed projects and maintain prospects for improvement. The evaluation of ADB's energy program showed that Bangladesh's energy sector has long needed major reforms; the sector has indeed been reforming, but only slowly. Despite the problems in the sector, ADB stayed involved in suitable ways without compromising its position or policies and contributed to the sector's progress. As a result, ADB has built a strong track record and relationship with the Government, and is in position to help the Government meet one of the country's top development challenges. [Main text, paras. 119-121,153,154,217] project cycle stage: Country Partnership Strategy Lesson Topics: 2. Continued Government ownership and commitment is an important factor in the success of reform programs. When future commitment is uncertain, a realistic, practical approach to reforms would be to, first, focus on reforms that can be solidly established within the Government's term; and second, beyond the Government's term, sow the seeds for future reforms, recognizing and accepting the reality and the risk that the efforts might falter. ADB's experience with the governance program loan is an example of how political risks affect the pace of reforms. The caretaker Government came to ADB for support in governance reforms. The caretaker Government was committed to those reforms, but the reform program extended beyond that government's term. The elected Government, while showing interest in reforms in some areas, is so far less committed to the program of the caretaker Government, and some key reforms supported by the governance program loan have started to falter. [Main text, paras. 218, Appendix 12] project cycle stage: Country Partnership Strategy Lesson Topics: Project Management: Risks/Risk management Capacity Development: Ownership Policy & Reform: Reform 3. Streamlined and efficient procedures, focused on outputs and results rather than process, can make joint work with other organizations more effective in creating synergies in country and sector programs. While joint work is likely to vary with every partnership, ADB should be able to identify essential internal procedures that it should maintain and work on identifying simpler, efficient steps, focusing on the output and results for the other procedures. ADB's experience on the sector-wide approach for primary education achieved one of its objective of cutting coordination costs on the part of the government, but resulted in higher costs for the development partners (since their procedures have not been harmonized). Similarly, in developing the 2005 Country Strategy and Program, ADB adopted an innovative approach of working with other development partners. While this strengthened program coordination, it also led to higher transaction costs for the development partners since ADB maintained its standard, internal, bureaucratic requirements for producing the country strategy (regardless of the relevance of the requirements). [Main text, paras. 54,122,219] project cycle stage: Country Partnership Strategy Lesson Topics: Capacity Development: Partnerships Sector Related Issues: Education Methodologies/Approaches: Sectoral approach | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-bangladesh-2009
Sundarbans Biodiversity Conservation Project | Bangladesh |  | 2008-02-06 | 1. Policy and institutional reforms imposed on an institution under a project need to be realistic and achievable, in view of the limited leveraging power of a project. The Project was ambitious in attempting to transform the management of the Sunderbans Reserve Forest (SRF) within the time horizon of a single project period, considering that the SRF had been managed for over a century by the Forest Department under a traditional command and control regime. The proposed ï¿½revolutionary' reforms should instead have been introduced in an ï¿½evolutionary' manner through a phased approach. project cycle stage: Lesson Topics: Capacity Development: Capacity assessment Capacity Development: Institutional analysis Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Program Approach 2. Policy and institutional reforms in challenging environments (i.e., marked by political patronage and authoritative civil service regimes) are more likely to succeed if they have sufficient ï¿½buy in' and have strong champions within the system. The Project demonstrated that such reforms cannot be enforced simply by dictum (i.e., imposed as loan covenants). The chances of success were also seriously jeopardized by attempting to circumvent the Forest Department on several occasions. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Loan Agreement: Covenants Project Management: Project administration Project Management: Risks/Risk management Capacity Development: Institutional analysis Capacity Development: Ownership Country Context: political economy factors Policy & Reform: Policy reforms/framework Policy & Reform: Reform 3. Institutional reforms that also have a direct bearing on project implementation should be addressed as project-readiness criteria and, to the extent possible, recommended as conditions for project approval rather than project effectiveness. For instance, establishment of the Sundarbans Management Unit and the were long-term institutional changes to the Forest Department but were also essential for smooth project implementation. They could have been addressed as project-readiness criteria prior to approval. project cycle stage: Design Appraisal Lesson Topics: Loan Agreement: Covenants Project Management: Project administration Capacity Development: Institutional analysis Policy & Reform: Public sector reform Policy & Reform: Reform 4. A risk assessment of the executing agency's capacity to undertake institutional and policy reforms should be conducted during the design phase, and specific corresponding indicators should be listed in the project design and monitoring framework. During implementation such indicators should be monitored by ADB through review of project performance reports. In the case of the Project, although the Sundarbans Management Unit, Sundarbans Stewardship Commission, and Stakeholder Advisory Council were established to comply with the effectiveness condition, there was no basis for assessing the effectiveness of these institutions. Therefore, for all practical purposes, the Project was implemented for several years without functional institutional arrangements. project cycle stage: Design Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project reporting Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Institutional analysis 5. Projects that involve complex implementing arrangements and challenging reforms require closer supervision. Such projects should be targeted for delegation to resident missions or for special joint supervision arrangements between headquarters and resident missions. However, resident mission staff assigned to such projects should be included as core members from the early stages of project design. project cycle stage: Design Appraisal Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Institutional analysis Other: Resident Mission Policy & Reform: Reform 6. A change in the officer responsible for a project during crucial stages (in this case soon after commencement of the project preparatory technical assistance and between project approval and effectiveness) should be avoided whenever possible. If unavoidable, the transition should be carefully managed to avoid a complete lapse of institutional memory (e.g., by ensuring the active participation of other team members, especially national officers). This can help to reduce unintended changes in project implementation arrangements (such as when the criteria for nongovernment organization participation in this Project were changed between the design and implementation phases). project cycle stage: Implementation Lesson Topics: Project Management: Project administration Project Management: Project supervision Capacity Development: Human resources management 7. Lessons from previous projects implemented by the Forest Department could have been incorporated more effectively into the project design. One such lesson was the Forest Department's poor assimilative capacity of technical know-how imparted by consultants under previous donor-assisted projects. Regardless, the Project included a front-loaded consultancy service package which was largely ineffective. Previous Forest Department projects had also encountered problems with Technical Assistance consultants not being accountable to the Forest Department but instead to ADB; however, the same problem was repeated in this project. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Project Design: Project design Project Management: Consultants 8. The administrative and financial management capabilities of the executing agency must be assessed as a ï¿½quality at entry' issue. For instance, the Forest Department did not have qualified accountants at the time the Project was approved. Furthermore, the Forest Department was implementing several other large donor-financed projects (including two other ADB-financed projects) when the Project was approved. The implications of implementing several large projects for the Forest Department's financial management and administrative staff were not assessed beforehand. Similarly, coordination between project executing agencies was undermined, in this case by having two project directors administering two separateproject proforma. project cycle stage: Design Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Human resources management Capacity Development: Institutional analysis | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/sundarbans-biodiversity-conservation-project
Secondary Education Sector Improvement Project | Bangladesh | Education | 2008-01-06 | 1. Reforms of any social development sector (such as the education sector) require a long implementation period, persistent pursuit of a reform agenda, and continued budgetary support to accomplish targeted improvements. In this case the project duration was considered inadequate to accomplish the many needed reforms. [Main text, paras. 44, 47, 67] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Funding Policy & Reform: Reform 2. School-based, hands on training support for teachers could have improved the utilization of new facilities and equipment. The project completion report noted that these provisions remain underutilized due to the teachers' lack of familiarity and skills, and the absence of requirements compelling their use. Poor maintenance of school equipment also remain a concern. [Main text, para. 68] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-education-sector-improvement-project
Khulna-Jessore Drainage Rehabilitation Project (Loan 1289-BAN[SF]) | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2007-11-30 | 1. A holistic analysis of the project area is required before determining the scope of a project (e.g., in this project, the drainage congested region in the southwestern coastal area). Evaluation noted that the project design often tends to be rushed and in the process several critical issues are overlooked or undermined. A project that involves the livelihood of a large number of people, particularly the disadvantaged groups, and stakeholders requires much time for robust consultation and full consideration of local indigenous knowledge systems to arrive at an acceptable solution. The design process should be owned by the stakeholders involved, and appropriate institutional arrangements and implementation modalities need to be worked out to ensure local ownership and sustainability. Due consideration should be given to nonstructural solutions wherever possible, and potential short- or long-term loss of income as a direct result of project activities also need to be factored in the design process. Balanced expertise, including a thorough knowledge of the local context, in the project design team is critical for the success of the project. Likewise, the planned project interventions need to be clearly sequenced. [Main text, paras. 57, 84] project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Crosscutting Issues/Themes: Sustainability Crosscutting Issues/Themes: Vulnerable groups Project Design: Project design Capacity Development: Human resources management Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach 2. The NGO/civil society groups fall broadly in three categories: (i) knowledgeable and sincerely committed to the cause and plight of poor and vulnerable people adversely affected by drainage congestion and flooding, (ii) looking for business opportunities or contract work, and (iii) capitalizing on the plight of affected people and seeking external recognition and personal benefits. It is crucial for a public institution like the Bangladesh Water Development Board (BWDB) to work with the first group and forge with them a strong development partnership for the benefit of local people. This would be possible only if the institution recognizes committed local organizations as genuine partners. This would have a positive impact on ADB s ongoing/new projects, including the Southwest Integrated Water Management Project and Command Area Development Project II. [Main text, para. 85] project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Vulnerable groups Project Design: Project design Capacity Development: Partnerships Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Civil Society Participation ADB and the executing agency (EA) need to have a more proactive role in complex public sector projects?by paying close attention and giving advice on the policy and institutional development process in the EA. This wouldimply provision of staff at ADB with the right skill mix. Similarly, the project steering committee needto be more proactive in guiding the project management. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Human resources management Policy & Reform: Policy reforms/framework Continuous operation and maintenance (O&M) is a necessary precondition to keep river and drainage channels open,and adequate provision for that must be built into national budgets, if not funded from othersources. However, leasing disputed government land for O&M is not a viable option.Furthermore, an active partnership between public institutions and local stakeholders is criticalto develop a sustainable O&M mechanism. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Operation and maintenance Capacity Development: Partnerships Sector Related Issues: Irrigation management The agreed-upon procurement plan and its updates should be followed and monitored toavoid processing delays, unnecessary splitting of large contracts into small ones, andprocurement of goods and works that are not identified for the project. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Procurement The project implementation arrangements in the Project Administration Memorandum (PAM)should be spelled out in detail, including roles and responsibilities of concerned stakeholders, apragmatic coordination mechanism, and accountability of the different parties including ADBHeadquarters, Bangladesh Resident Mission, executing agencies, implementing agencies, contractors, andconsultants. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project administration Other: Resident Mission Methodologies/Approaches: Consultation/Participation There is a need for an effective grievance redress mechanism so that the project-affectedpeople can voice their concerns without any fear of reprisal. Such a mechanism oughtto have transparent provision for providing fair compensation to the adversely affectedpopulation. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Project Design: Project design | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/khulna-jessore-drainage-rehabilitation-project-loan-1289-bansf
Command Area Development Project | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2006-11-15 | 1. In terms of social and institutional development, community livelihoods have improved significantly from the contribution of projects already implemented, but the institutions are weak in the collection of irrigation service charge (ISC) and participation in operation and maintenance (O&M). Local government institutions (union parishads, upazila parishads) have the scope to be involved in the O&M of infrastructure through mobilization of local funds and manpower. There is a need to further strengthen coordination and cooperation between the executing agency and other agencies involved, especially the local government department implementing infrastructure projects, at both the organizational and the field level. [Main text, paras. 67-70, 63, 72] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity building Capacity Development: Capacity development Country Context: Decentralization Crosscutting Issues/Themes: Employment Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation 2. Training should not be evaluated by the number of trainees but by its quality and effectiveness. While the project was able to meet its numerical target in training executing agency staff on participatory water management, the project completion report noted that the quality and effectiveness of these local training programs were unsatisfactory. [Main text, paras. 21-22, 72; Appendix 2] project cycle stage: Implementation, Completion Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity building 3. Problems brought about by technical inadequacies in planning, design and construction of irrigation infrastructure could be minimized by (i) locating flood-control, drainage, and irrigation investments in morphologically stable areas; (ii) paying special attention to smaller and remote canals of larger systems which often do not get adequate water; and (iii) using locally available knowledge. As reported during project completion, problems regarding the planning, design and construction of irrigation infrastructures contributed to irrigation coverage that is much lower than expected. [Main text, para. 16, 25, 43, 52, 72] project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management 4. Project sustainability depends on several factors including, among others, adequate funding for operation and maintenance (O&M), and well-functioning and effective water user organizations (WUOs). In this project, O&M activities generally received less attention and suffered from financial constraints. Beneficiaries were too dependent on the executing agency for O&M, while executing agency, as well as water management organizations were confronted with inadequate O&M funding. Given these, placing importance on collection of irrigation service charges, allocation of government funds and upfront capacity building of WUOs would contribute to improving sustainability of project benefits. [Main text, paras. 52, 64, 67, 69, 72] project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity development Locally available knowledge should be used in planning and design. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Project Design: Project design Smaller and remote canals of larger systems often do not get adequate water and hence, need special attention. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Strengthening Water User Groups (WUGs) and Water Management Associations (WMAs) should be undertaken up front, prior to starting physical works, and given sufficient time. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity development Sector Related Issues: Irrigation management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/command-area-development-project
Jamuna Bridge Railway Link Project | Bangladesh |  | 2005-11-15 | Advance planning and close coordination between Bangladesh Railway and the mine authorities and other major clients is necessary. The state of affairs confirms the urgent need for institutional reform of Bangladesh Railway, as covenanted in the Loan Agreement. project cycle stage: Feasibility Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Project Management: Executing/Implementing agencies Sector Related Issues: Transport planning Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Small amounts of cofinancing for vital components of a project should be carefully examined in advance. In this project, most of the delays in completion are attributable to the work and/or supply components procured, or envisaged to be procured, through separate contracts in accordance with the cofinancing agreements. The cofinancing to be provided by Export Development Corporation (EDC of Canada) for the rails needed for contracts 1 and 2 was only $7 million at appraisal. The failure of the supplier nominated by EDC caused most of the delay in completion of contracts 1 and 2. At the same time, the exclusion of the supply of rails from the scope of the main civil works contracts went against the spirit of the turnkey arrangement of the contracts. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Procurement The engagement of the construction supervision consultant (CSC) for day-to-day management of project implementation (which was done to strengthen Bangladesh Railway's project management capability) produced the desired results. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Project management Project Management: Project supervision Sector Related Issues: Transport planning The reform agenda should be pursued in stages with proper sequencing. In the case of Bangladesh Railway, preparatory work supported by substantial inputs of attached and/or stand-alone TAs, including the restructuring of Bangladesh Railway into lines of business as a first step, are needed before setting up a corporatized railway entity. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Design: Project design Sector Related Issues: Transport planning Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/jamuna-bridge-railway-link-project
Third Natural Gas Development Project | Bangladesh | Energy | 2005-11-15 | Fewer approval steps for procurement help with timely implementation of projects. The full financial authority now enjoyed by the gas sector entities helps accelerate project implementation. project cycle stage: Appraisal Lesson Topics: Project Management: Procurement Sector Related Issues: Energy planning/management Policy & Reform: Reform Reform-linked projects require follow-up projects to ensure implementation of reforms initiated in any sector. ADB assistance for series of projects is largely responsible for the substantial reforms in the power sector in Bangladesh which began in 1994. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Cluster operations Sector Related Issues: Energy planning/management Policy & Reform: Reform The nature of the consulting services should be commensurate with the implementation period of any project. For projects with long implementation periods that require intermittent intervention of consultants, the engagement of a firm to provide consultants with appropriate disciplines is better than engaging individual consultants. This allows the replacement of consultants whenever needed, at short notice. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement To avoid implementation delays, consultants whose services are required for design and supervision of project components should be selected before project approval. This approach has yielded positive results in some projects in the transport sector. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Project supervision Sector Related Issues: Transport planning | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-natural-gas-development-project
Coastal Greenbelt Project | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2005-10-14 | Delays in finalizing core implementation arrangement (e.g., engagement of TA consultants or partner NGOs) must be resolved promptly. The implications of prolonged delays should be assessed and, if necessary, certain project activities should be rescheduled to maintain the integrity of the project's overall intent. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Methodologies/Approaches: Civil Society Participation Essential implementation arrangements to be finalized during the project should be linked to disbursement of funds on related project activities to avoid the activities commencing before arrangements are in place. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Project design Greater emphasis should be placed on monitoring of implementation and benefits and on evaluation systems. In some instances, continuous monitoring and evaluation linked to specific project activities may be more efficient and sustainable than benefit monitoring and evaluation programs. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Monitoring and evaluation Methodologies/Approaches: Program Approach Participatory resource management projects involve complex arrangements between the beneficiaries, intermediaries (NGOs), and custodians (executing agency, etc.). Dynamics between parties, incentives for participation in project activities, and other such issues must be addressed in detail during preparation. Projects must also be flexible to accommodate changes, since the social dynamics between parties involved in such projects cannot be expected to remain fixed for long. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Methodologies/Approaches: Participatory approach Projects that introduce innovative approaches and implementing arrangements require close supervision by ADB especially during the first few years. The officer responsible for processing should remain involved during implementation at least during the first 1-2 years. Alternatively, such projects may be prepared with close, active involvement of Resident Mission staff, who would be assigned as project officer after loan inception. Regular and timely review missions during this period are essential to keep the project on track. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Project supervision Other: Resident Mission The government considers the project pro-forma (PP) as the guiding document for project implementation. The PP must therefore accurately reflect the project scope, implementing schedule and arrangements, breakdown of expenditure, and conditions and covenants. Ideally, executing agency staff involved with project preparation should have a role in preparing the PP, and should be finalized before project inception. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies The project could have encouraged greater private sector/community participation by outsourcing the production of plants under the executing agency's supervision and quality control. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Sector Related Issues: Private sector Methodologies/Approaches: Community approach | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/coastal-greenbelt-project
Southwest Flood Damage Rehabilitation Project | Bangladesh |  | 2005-09-15 | Adequate consulting support results in better executing agency performance in project preparation, monitoring, supervision, quality control of works, and timely utilization of loan funds. This is particularly relevant where a large number of small subprojects are implemented over a wide area. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project supervision Coordination and monitoring of project implementation through a central project steering committee (PSC) of the Borrower is very important for multi-sector projects that involve a large number of executing agencies. Regular interaction between the government and ADB through the PSC contributed greatly to the success of the project. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Methodologies/Approaches: Consultation/Participation Delegation of authority to ADB mission in the Borrower's country is essential for close monitoring and expediting decision-making processes. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Project Management: Project supervision Other: Resident Mission Disbursement of funds through establishment of an imprest account by each executing agency is vital for timely payment to consultants, contractors, and suppliers. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Larger contracts are more efficient in terms of monitoring, quality control, and timely completion of works, although they depend on the capacity of executing agencies concerned. Contractors must invest to purchase equipment and machinery, resulting in enhanced capacity and development of the construction industry. The issue has been reflected in several subsequent ADB loan agreements, with a minimum contract size included. project cycle stage: Implementation Lesson Topics: Loan Agreement: Loan Agreement Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity assessment Capacity Development: Capacity development Most executing agencies did not make adequate provision for maintenance funds, which are essential for long-term sustainability. ADB, together with other development partners, is seeking to assist the government establish a road fund to ensure a sustainable flow of maintenance funds for road infrastructure. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Sector Related Issues: Roading Procedural delay in recruitment of consultants and procurement of civil works contracts is the main reason for delayed project implementation. Timely completion of works requires streamlining of executing agencies' procurement and recruitment procedures, full implementation of newly-approved national public procurement guidelines, and further capacity building and training on contract administration and ADB procedures for procurement and disbursement. project cycle stage: Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Disbursement Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Capacity Development: Capacity building Provision for retroactive financing facilitates exploitation of first available working season to urgently rehabilitate damaged critical facilities. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Country Context: Emergency | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/southwest-flood-damage-rehabilitation-project
Participatory Livestock Development Project | Bangladesh |  | 2005-08-15 | Administering TA on a parallel basis using separate operational guidelines does not help smooth and timely implementation. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Project administration Assigning the executing agency a more regulatory role in the subsector will encourage increased private sector investment and provision of services. The continued provision of selected subsidized inputs from the executing agency acts as a disincentive to private companies. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Sector Related Issues: Private sector Policy & Reform: Reform Compared to the NGOs, the executing agency has limited outreach capacity. It is therefore advantageous to use the outreach capacity of NGOs to reach the poor with support services including microcredit. Establishing close ties between different implementing agencies and service providers at the field level are prerequisites for smooth project implementation and sustainability. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Extension service Methodologies/Approaches: Civil Society Participation Opportunities have been created to further expand the scope of livestock enterprises development by increasing production and involving a wider range of enterprises in the sector. Farmers and entrepreneurs are keenly interested in investing in other profit-earning enterprises like hybrid and broiler rearing beef, dairy, product processing, and input supply. The participatory planning process will help smallholder farmers access markets and ventilate theirideas and capabilities. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach The project demonstrated that it is possible to successfully deliver a large number of technically supported, microfinanced livestock improvement packages through the executing agency for the selection of NGOs and the disbursement of microcredit to beneficiaries and partner NGOs with technical support from the (lead) executing agency (DLS). Predetermined enterprises to some extent limited the beneficiaries' choice of enterprises to exploit local opportunities. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Sector Related Issues: Rural development Methodologies/Approaches: Civil Society Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/participatory-livestock-development-project
Secondary Towns Infrastructure Development Project II | Bangladesh |  | 2005-08-15 | Direct involvement of the urban municipality (pourashava) chairpersons and their staff in implementing the project activities might have played an important role in ensuring greater ownership of the facilities built. This is also important for supervision of works during construction and maintenance of physical facilities (bus terminals, markets, public toilets, and drainage). The new ADB-assisted Urban Governance and Infrastructure Improvement Project (UGIIP) was formulated in line with this lesson learned. The performance-based UGIIP approach is expected to result in significant change in practice and attitudes of the urban municipalities. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Public governance Project Management: Project supervision Capacity Development: Ownership Country Context: Decentralization Methodologies/Approaches: Consultation/Participation Regular monitoring of urban municipality (pourashava) performance by the agencies concerned was important. Newly elected representatives of the urban municipalities were generally not sufficiently aware of the project facilities and their obligations towards repayment of the loans after project completion. Lack of adequate skilled staff and transfer of trained staff resulted in deteriorating situations. However, the government recognized the overall situation of the urban municipalities and agreed with development partners, including ADB, to bring in necessary adjustments in the urban municipality ordinance (Pourashava Ordinance of 1977). It established a senior committee to review the reform proposals, and a central urban municipality performance evaluation committee chaired by a joint secretary of the Local Government Division (LGD). project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Public governance Monitoring & Evaluation: Monitoring and evaluation Country Context: Decentralization Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-towns-infrastructure-development-project-ii
Second Primary Education Sector Project | Bangladesh |  | 2005-07-15 | Although project interventions have improved quality, much more needs to be done to broaden the improvements in the quality of primary education in Bangladesh. The interventions expected under the Primary Education Development Program II (PEDP II) will contribute significantly to this objective, particularly through (i) organizational development and capacity building, (ii) quality improvement in schools and classrooms, (iii) quality improvement through infrastructure development, and (iv) comprehensive policy and institutional reform framework. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity building Sector Related Issues: Education Policy & Reform: Policy reforms/framework Annual increases in the government's budgetary allocation are essential for sustainable development of primary education. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Sector Related Issues: Education Parallel cofinancing without a firm commitment from the concerned donor(s) often creates problems in project implementation. project cycle stage: Appraisal Lesson Topics: Public-private partnerships for community-based routine and periodic maintenance of the primary school infrastructure are feasible, and appreciated by the community as an effective system. project cycle stage: Feasibility Lesson Topics: Project Management: Operation and maintenance Sector Related Issues: Education Sector Related Issues: Public-private partnership Methodologies/Approaches: Community approach To ensure sustainability, the formal transfer of incremental staff under any project to the government's recurrent budget should be completed well before project completion. Planned transfer of staff will reduce the hardships for project staff, as well as increase job satisfaction and commitment. The designs of future projects should address carefully the transfer of incremental staff to ensure maximum project impact and sustainability. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Human resources management To maximize the benefits from the renewed and redesigned curricula, full dissemination among classroom teachers and teacher educators is necessary. All classroom teachers must be provided with a teachers' guide. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Education Policy & Reform: Information dissemination/Public awareness | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-primary-education-sector-project
Road Overlay and Improvement Project in Bangladesh (Loan 1287-BAN[SF]) | Bangladesh | Transport | 2004-10-31 | Development partner coordination within the transport sector was beneficial. Working together avoided the duplication of efforts in institutional strengthening and policy development, with positive results in road maintenance. Similar coordinated approaches for addressing the remaining issues relating to road maintenance and to road safety and vehicle overloading would also likely prove beneficial. project cycle stage: Implementation Lesson Topics: Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Roading Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework Greater realism is required in using covenants and how they are worded. Achieving appropriate levels of maintenance funding has always been difficult. A realistic approach would have recognized the problem and, instead of relegating it to a loan covenant, might have established a series of steps toward achieving the desired outcome, in this case, funding of maintenance, so that the government s progression could be monitored and, where applicable, appropriately assisted. All will be difficult for the government to achieve and should not be left to broad loan covenants. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Funding Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Projects need to first consider the policy framework and political will prior to introducing expensive facilities aimed at creating fundamental change that affects the general public and institutional staff. This derives from the experience with the vehicle inspection centers, applicable to the situation with vehicle overloading, which is commonly addressed by providing weighbridge facilities. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Roading Policy & Reform: Policy reforms/framework The delays in the preconstruction phase of implementation show that advance action may not prevent such inefficiency from occurring. In the case of the project, hierarchical government bureaucracy and decision-making processes largely negated the advance actions for procurement of consultant services and civil works. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Project Management: Consultants Project Management: Procurement There is a need for detailed and pragmatic review of institutional capabilities when a relatively inexperienced executing agency is to be involved. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Institutional analysis Where new technologies and concepts are to be introduced, the amounts of consultant time for staff training and support with initial operations can be substantial and need to be realistically estimated. project cycle stage: Feasibility Lesson Topics: Project Management: Consultants Capacity Development: Capacity building Capacity Development: Technology/Technology transfer | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/road-overlay-and-improvement-project-bangladesh-loan-1287-bansf
Khulna-Jessore Drainage Rehabilitation Project | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2004-09-15 | Establishing close coordination within the different implementing wings of an executingagency and functional coordination among the different service providers at the field level arethe keys to the success of project implementation and sustainability of the facilities. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Project Management: Project management Methodologies/Approaches: Consultation/Participation For further improvement of water resources development and management, there is a need for (i) capacity development of the executing agency (Bangladesh Water Development Board) for mainstreaming participatory process addressingsocial and environmental issues, and capacity development of the Water Management Associations (WMAs) for sustainable O&M; (ii) effective local institutional mechanisms to coordinate and integrate water management; (iii) rigorous planning of O&M arrangements, including beneficiary financial contributions, and (iv) effective policy and regulations to support participatory water resources management. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity development Sector Related Issues: Water resource management Policy & Reform: Policy reforms/framework Methodologies/Approaches: Participatory approach Joint and coordinated efforts of the executing agency (Bangladesh Water Development Board) and water management organizations (WMOs) are essential for sustainable O&M of drainage systems, and efficient use of water resources. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation The design and implementation of development projects should recognize adequatelyand timely the wisdom, knowledge and practical experiences of the potential beneficiaries. Forexample, project implementation delays could have been reduced considerably if thebeneficiaries demand for the tidal river management (TRM) systems had been appreciated early. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Project Design: Project design Project Management: Project management Sector Related Issues: Water resource management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/khulna-jessore-drainage-rehabilitation-project
Jamuna Bridge Access Roads Project | Bangladesh | Transport | 2004-07-15 | Adequate services and inputs of a team of experienced international and domestic consultants are also indispensable in ensuring proper monitoring and management of large-scale projects. As the Project Completion Report Mission noted, one reason for the adequate and timely management of the project's high-value construction works, which were geographically stretched over wide and dispersed areas, was the provision of strong consultant support planned at appraisal and procured during implementation. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Management: Consultants Project Management: Procurement Project Management: Project management For large multicomponent infrastructure projects involving cofinancing by multiple development agencies, regular monitoring by ADB resident missions is essential from inception, due to resident missions' proximity to borrowers and rich country-specific knowledge. However, project design must include appropriate mechanisms to ensure effective coordination among cofinancing organizations, enabling them to address common implementation issues in a concerted and timely manner. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Other: Resident Mission Methodologies/Approaches: Consultation/Participation The project addressed road safety improvements comprehensively, instead of on an isolated and piecemeal basis, through countrywide road safety audits, to identify and prepare a comprehensive list of accident black spots. For effective axle load control that is designed to minimize the incidence of overloading on national and regional highways, adequate numbers of permanent weighbridges need to be installed up front, at strategic locations, to capture overloaded traffic. Including the procurement of axle weighing equipment in consultants' contracts is, however, not prudent, as this is not practicable, due to procedural complications. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/jamuna-bridge-access-roads-project
Small-Scale Water Resources Development Sector Project | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2004-07-15 | A good quality subproject needs to be carefully selected, with a feasibility study undertaken professionally. The subprojects must be designed based on good quality survey data, constructed by qualified contractors and well managed by labor contracting societies(LCS) under strict engineering supervision, managed by a well-developed water management cooperative association (WMCA) capable of good governance, and properly monitored by line departments. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management Project Management: Project supervision Crosscutting Issues/Themes: Employment Sector Related Issues: Water resource management Although relatively new in water resources management, the executing agency (Local Government Engineering Department or LGED) proved efficient and effective. Given the potential for development of many more small-scale water resources subprojects, LGED should further develop necessary in-house technical skills of its own and reduce dependence on external assistance. project cycle stage: Operation Lesson Topics: Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Water resource management Small-scale water resource development entails social, technical, financial, and management issues involving rural people of all levels. Therefore, its implementation requires a longer time than that for other types of projects. This requirement is already recognized in the longer project implementation period in the ongoing second phase project. Executing agency capability is important for setting physical targets for the subprojects. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Modality: Cluster operations Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Sector Related Issues: Rural development Sector Related Issues: Water resource management Methodologies/Approaches: Targeting The poor and disadvantaged, especially the landless and women, can benefit fromsmall-scale water resources facilities through earthworks and labor intensive agriculture and fishing activities. However, the formation of labor contracting societies (LCS) groups must be free from socio-political considerations to include only the poor and disadvantaged, especially destitute women. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Vulnerable groups Crosscutting Issues/Themes: Employment Sector Related Issues: Rural development Sector Related Issues: Water resource management The project proved the development of small-scale water resources as a feasible andsustainable means of poverty reduction as manifested in the implementation of the ongoing second phase. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Modality: Cluster operations Sector Related Issues: Water resource management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/small-scale-water-resources-development-sector-project
Second Water Supply and Sanitation Project | Bangladesh | Water and Other Urban Infrastructure and Services | 2004-06-15 | Instead of adopting a prototyped design, water treatment plants should be designed based on water quality, especially when the presence and concentration of iron, arsenic, and other harmful elements are factors. When water quality deteriorates from the increased presence of iron and or arsenic, operating costs and water losses due to frequent backwashing increase. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management The optimized use of potential water facility capacity was constrained by inadequate revenue collection, resulting from low water tariffs in project pourashavas. The 24-hour water supply pilot program at Faridpur could not be maintained, primarily for this reason. The pourashavas face a dilemma concerning 24-hour water supply. They can provide 24-hour water supply by either increasing or continuing existing low water tariffs. The latter option, however, while allowing leaders to remain politically favored, will result in supplying as little water as possible and earning low incomes. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Project Management: Operation and maintenance Project Management: Risks/Risk management Country Context: Decentralization Sector Related Issues: Health and sanitation management Methodologies/Approaches: Pilot project | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-water-supply-and-sanitation-project
Capital Market Development Program Loan | Bangladesh | Finance | 2003-08-15 | As noted during the formulation of the Capital Market Development Program (CMDP), a lack of cooperation by the parties involved in the program and their weak capacities were major risk factors. The government's ownership of the policy reforms was vital to the success of the program. Ministry of Finance (MOF), as the executing agency for the CMDP, and Securities and Exchange Commission (SEC), as the executing agency for TA 2913, provided strong support for the implementation of the program, contributing to significant progress in enhancing SEC's supervisory capabilities. However, the development of the supply and demand sides of the capital market progressed slowly. The lack of management and staff skills in the Privatization Commission (PC), inappropriate rules and procedures, and bureaucratic consultation impeded the privatization process. The insurance and pension and provident fund reform is a complicated and broad-based issue, requiring policy decisions by the government. The slow response from the government in evaluating recommendations related to insurance sector reform became an impediment to subsequent development. The scope of TA 2915 had to be refocused on pension and provident fund reform, but the Ministry of Commerce or MOC (instead of MOF) continued to be the executing agency. With more extensive discussion during program formulation, an appropriate implementation arrangement for the TA could have been designed. Staff and lack of skills in regulatory authorities hampered implementation of theCMDP and its attached TA activities. Transforming these regulatory bodies into independent self-funded organizations with greater flexibility in setting their own compensation scale is a delicate issue to be taken up with the government under ADB's future assistance program. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Modality: Program Modality: Technical Assistance Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Human resources management Capacity Development: Ownership Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Due to the prevalence of malpractice in the market when the Capital Market Development Program (CMDP) was designed, there was a strong need for increased transparency and disclosure and strengthened regulation and supervision of market players. However, the establishment of a disclosure-based system of regulation required several parallel reforms, including (i) a strong and independent but market-sensitive Securities and Exchange Commission (SEC); (ii) strong market players, including merchant banks; (iii) proactive exchanges willing and capable of self-regulation; (iv) the implementation of accounting and auditing systems to produce financial reports conforming to international standards; and (v) goodcorporate governance practices. Serious deficiency in any of these support reform elements makes it difficult to implement regulations based on full disclosure. The CMDP did not give balanced support to all these elements. Training and capacity building were heavily focused on SEC, almost to the neglect of other key capital market participants. Corporate governance, transparency, and adoption and implementation of accounting and auditing standards should have been given more priority. When brokers were barred from undertaking merchant banking functions, new merchant banks that were established did not have any experience and expertise. Accreditation should have been more selective, based on stricter criteria, and training on due diligence should have been provided. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Capacity Development: Capacity building Policy & Reform: Reform The tranche release conditions should have been more specific, thereby avoiding ambiguity in interpretation. For example, it could have been stated that the ï¿½private sectorï¿½ member of the Securities and Exchange Commission (SEC) board should have working experience in industry or business or in the financial intermediary or securities businesses. As regards the condition to ï¿½establishï¿½ a company or institution, it should have been made clear that this meant not just getting the company incorporated but obtaining a license and becoming operational. It is not clear if the phrase ï¿½new businessï¿½ in the Investment Corporation of Bangladesh (ICB Amendment) Law includes new transactions for existing clients. The tranche condition for the divestment of government's shares should have specified the minimum number of public and private limited companies to be divested and identified some of them. In many cases, the compliance status was assessed on the basis of the amendment of existing laws or the enactment of new laws, which were deemed to satisfy tranche conditions. However, enforcement of these laws in practice remained questionable. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Loan Agreement: Covenants Sector Related Issues: Industry and Trade Sector Related Issues: Private sector Weaknesses in corporate governance have been a pervasive problem. The quality offinancial reports and adequacy of disclosures of listed companies have to be improved to be inline with international norms. The privatization process lacked transparency and had seriousdeficiencies in policy, regulation, and valuation methods. Although reforms under the Capital Market Development Program (CMDP) have corrected many of these shortcomings, further improvement in corporate governance isimperative to foster investor confidence and attract capital flows. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Modality: Program Policy & Reform: Privatization Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/capital-market-development-program-loan
Nonformal Education Project | Bangladesh | Education | 2003-08-15 | A center based approach (CBA) is, comparatively, a more effective approach to nonformal education (NFE) delivery. Moreover, the cluster approach to selecting centers, as adopted by the project, is appropriate when ensuring total coverage, leaving no vacant spaces, irrespective of areas nearer to and further from upazila (subdistrict) headquarters. Provision of high-level committees is generally helpful in providing policy guidelines, but a council headed by the Prime Minister has proved to be unrealistic. Instead, committees that can meet frequently, as and when the project needs, and that are constituted with high-level and involved officials having the authority to formulate and implement policies are more practical and useful. Cooperation between the government and NGOs in delivering NFE, especially when using a CBA, is effective and a key to the success of NFE programs. Nonetheless, teachers' and supervisors' salaries are much less than enough to attract good teachers, and the center management fee is inadequate for getting suitable centers and properly managing them. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Education Methodologies/Approaches: Civil Society Participation Nongovernment organizations (NGOs) play a vital role in identifying target beneficiaries, selecting centers, recruiting and training teachers and supervisors, managing centers, delivering nonformal education (NFE), monitoring and evaluation, and financial management. Without a strong commitment combined with a significant amount of experience and sound financial and Project Management, it is difficult for any NGO to play its role. Moreover, in order to involve newly literate individuals in post-literacy and income-generating activities, participating NGOs should have a continued presence in the project area, even after completion. The study indicated that NGOs having existing programs inthe area could offer post-literacy and continuing education and livelihood support to newly literate males and females. As the role of NGOs is critical in the successful implementation of NFE programs, for quantity and quality, NGO selection should be transparent, and heightened importance should be attached to NGOs' track records; commitment; and presence in the area with similar programs, preferably microcredit and livelihood activities. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project management Capacity Development: Capacity building Capacity Development: Ownership Crosscutting Issues/Themes: Employment Sector Related Issues: Education Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Targeting The delay in activities such as land acquisition; recruitment of key staff, especially project directors and counterpart staff; and initial mobilization of counterpart funds are common in most projects. Therefore, provision for advance actions can partly help reduce implementation delays. Frequent staff transfer, especially of individuals that received specifictraining under the project, had some adverse impact on overall project implementation. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Counterpart funds Project Management: Project management Capacity Development: Capacity building Capacity Development: Human resources management The project targeted illiterate males and females between the ages of 15 and 24 who are considered to be more actively involved in income generation activities. The PCR study found that only 38.6% of all newly literate individuals are in this age group, indicating that a larger percentage of the illiterate population is in a higher age group. The study also found that90% of all target learners were poor, indicating a strong correlation between illiteracy and poverty. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education Methodologies/Approaches: Targeting Though monitoring and evaluation are fully acknowledged as important inputs for quality nonformal education (NFE) delivery, they are difficult to undertake without commitment on the part of the staff involved in pursuing the outputs of these and persistence on the part of management in doing the same. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Ownership Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/nonformal-education-project-0
Flood Damage Rehabilitation Project | Bangladesh |  | 2003-06-13 | For multisector projects that involve a large number of executing agencies (EAs), monitoring ofimplementation through a central Project Steering Committee (PSC) of the Borrower is very important. Monitoring by ADBthrough establishment of a Project Implementation Unit (PIU) at the Borrower's country level is also essential. Disbursementof funds through establishment of a separate imprest account by each EA also works well fortimely payment to the consultants, contractors, and suppliers, which is crucial for successfulproject implementation. The sector approach undertaken was also beneficial in identifyingappropriate subprojects scattered over a wide area. Adequate services of consultants are alsoessential. It was noted that consultant input was inadequate in several components. Where alarge number of small subprojects spread over a wide area are implemented, provision forstrong consultant support should be envisaged. Besides, it is an uphill task for the EAs tomanage a large number of widely dispersed small contracts with limited human resources. Inorder to ensure improved construction, supervision, and monitoring performance aimed atraising the quality of works, the number of contract packages should be restricted to a minimum,to the extent possible. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management Project Management: Project supervision Capacity Development: Human resources management Methodologies/Approaches: Sectoral approach In Bangladesh, the Roads and Highways Department (executing agency for roads component) and Local Government Engineering Department (executing agency for rural and urban infrastructure) are still the two agencies that are reasonably capable of implementing ADB-assisted projects. Other agencies including Bangladesh Water Development Board (BWDB), Bangladesh Railway (BR), Department of Public Health Engineering (DPHE), Dhaka Water Supply and Sewerage Authority (DWASA), Dhaka City Corporation (DCC), and Directorate of Secondary and Higher Education (DSHE) suffer from acute capacity constraints. Implementation experience suggests that civil works restoration projects generally require adequate programs for capacity building in the executing agencies (EAs) regarding contract administration and fostering familiarity with ADB procedures for procurement and disbursement. This will help ensure timely completion of contractual works,submission of withdrawal applications, and liquidation of imprest accounts. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Capacity Development: Capacity assessment Capacity Development: Capacity building Project experience confirms that the existence of, and familiarity with, a nationalstrategy for disaster management would have been helpful, especially if such a strategy alsocontained the method for early estimation of infrastructure damage and identification ofsubprojects. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Subprojects Country Context: Emergency Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/flood-damage-rehabilitation-project
Country Assistance Program Evaluation for Bangladesh (2003) | Bangladesh |  | 2003-01-31 | A multitude of development partners (DPs) have provided assistance to all aspects of transport, power, gas, and agriculture development. Much has been achieved in the last 2 decades. In some cases, however, the flow of concessional resources may have perversely undermined the perceived urgency for reform and domestic resource mobilization, as well as encouraged a deferred maintenance mentality. While these sectors will need external resources, these should be conditioned on a demonstrated commitment to improve institutional performance. This may suggest an increased use of theprogram approach by ADB, with solid agreement with the government on a wide range of policies, objectives, strategies, and expenditures. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Modality: Program Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity development Capacity Development: Ownership Sector Related Issues: Energy planning/management Sector Related Issues: Rural development Sector Related Issues: Transport planning Policy & Reform: Reform ADB's support for the development of a leasing industry, which principally took the form of a regional TA followed by policy dialogue leading to enabling legislation, is an example of how, in certain circumstances, TA can have a disproportionately positive impact even without any significant loan. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Modality: Technical Assistance Policy & Reform: Policy matrix All projects undertaken in the social sectors exhibit symptoms of less than complete ownership (delays in appointing key staff and in approving project proformas, and failure to take action on agreed policy initiatives are afew examples). Political commitment to institutional change needs to be strengthened, and more effective procedures and control mechanisms in the provision of public services introduced. project cycle stage: Design Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Project Design: Project design Capacity Development: Ownership Sector Related Issues: Education Sector Related Issues: Health and sanitation management Policy & Reform: Reform Before embarking on formulation of a future country strategy and program, more attention should be directed to how effective was the last COS. project cycle stage: Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Policy & Reform: Policy reforms/framework By setting its health goals purely in terms of human development indicators (e.g., reduced rates of infant mortality), the Partnership Agreement on Poverty Reduction (PAPR) is failing to provide an adequate guide for program formulation. This is because the achievement of such outcomes depends on so many factors and the performance of so many different actors that the indicators have little operational value. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Indicators Project Design: Project design Capacity Development: Partnerships Sector Related Issues: Health and sanitation management Certain types of loan projects may be at risk of failing to achieve their full potential impact because they are planned and implemented in isolation from complementary measures, which are required if the projects are to realize their theoretical benefits in addition to the institutional reforms that are so often a pre-condition of success. To ensure that the benefits are in fact realized will require ADB, in conjunction with concerned government authorities, either to structure its other sectorprograms to enable them to have complementary impact, or to act in concert with other development partners (DPs)and/or NGOs to a similar effect. The requirement to pursue such a holistic strategy will be all the greater to the extent that there is genuine involvement of local communities in determining project/program design. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Policy & Reform: Policy reforms/framework Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach Country strategies become much more relevant and operationally useful if there are specific monitorable benchmarks for policy reform and project outcomes. project cycle stage: Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Policy & Reform: Policy reforms/framework Experience suggests ADB's ability to achieve institutional reforms varies according to the degree of political significance of the sector in relation to the needs and interests of the ruling elite. This may be illustrated by the relative success in securing reform in the power subsector in contrast to the relative failure to date in respect of the railway subsector (and also to some extent in the gas subsector). In the latter cases, there is much less pressure to reform, less because the key vested interests are not threatened by the decline in performance that might result from the possible cessation of ADB support. project cycle stage: Feasibility Lesson Topics: Capacity Development: Institutional analysis Sector Related Issues: Energy planning/management Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework Policy & Reform: Reform Given the poor prospects for the ready made garment (RMG) industry, the country's lack of competitive advantage vis- -vismost other export markets, and its failure to attract foreign investment, enterprise, and employment growth that are central to poverty reduction, Bangladesh will have to continue to depend largely on indigenous enterprise, and be geared to supplying mainly the local or regional (South Asian) market. project cycle stage: Concept Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Market analysis Crosscutting Issues/Themes: Employment Sector Related Issues: Private sector In general, COSs underestimate the complexity and time necessary to bring about institutional change and capacity enhancement. Greater resource commitments and new TA modalities with a long-term focus are required. project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Capacity Development: Capacity development Managers and service providers in the health and education sectors are not held accountable to the communities that they serve. Government has been very good at 'campaign' activities, such as mobilizing communities, increasing school enrollment, vaccination, and contraceptive acceptance. It has been less able in bringing about systemic improvements needed to upgrade school quality or monitoring performance of actual health care provision. This means giving greater financial and managerial autonomy to local units within the country's administrative systems. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Country Context: Decentralization Sector Related Issues: Education Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Community approach Much more consideration should be given to the appropriate role of the public sector in the provision and maintenance ofinfrastructure. The private sector, both foreign and domestic, has a critical role to play in power generation and distribution, telecommunications, water and sewerage operations, ports, and all forms of transportation. Project success has been enjoyed, and sustainability enhanced, the closer the service providers are to the constituency that they serve. Local authorities and municipalities should be given more autonomy and managerial discretion in the investment and maintenance of certain infrastructure, particularly rural roads. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Operation and maintenance Country Context: Decentralization Sector Related Issues: Energy planning/management Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Sector Related Issues: Roading Sector Related Issues: Rural development Sector Related Issues: Transport planning NGOs play an important role in health and education, both in piloting innovative approaches and in the provision of services. The government has become increasingly supportive of NGOs over the past decade, and has accepted them aspartners in achieving national goals. Scope does exist for greater NGO/Government/ADB collaboration. There is also ample scope for private sector provision of social services and ADB needs to explore this further. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Civil society Capacity Development: Partnerships Sector Related Issues: Education Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Methodologies/Approaches: Pilot project Strategies should allow considerable flexibility to adjust the lending program in response to progress in identified key reform areas. project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Policy & Reform: Policy reforms/framework Policy & Reform: Reform The experience of ADB, together with all major development partners (DPs) and the government, in encouraging private sector tubewell development has dramatically increased agricultural production and reduced the incidence of waterbornediseases. However, it also likely contributed to the spread of arsenic-contaminated groundwater use for irrigation and domestic water supply. More rigorous analysis of groundwater conditions could have discovered and mitigated the problem at an early stage. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Project Design: Problem identification Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management Sector Related Issues: Irrigation management Sector Related Issues: Private sector Sector Related Issues: Rural development Sector Related Issues: Water resource management The government should progressively reduce its role as primary provider of services as contraceptive prevalence increases and phase out its retailing of family planning services. The NGOs and private providers should be encouraged to gradually fill the gaps. In family welfare and health, a more effective role for the government can also be defined, with a greater role for private providers that will increase the scope and variety of service alternatives available. In education, priorityshould be given to improving the quality of primary and secondary education. The role of the public sector in technical and vocational education should be limited, and programs that are developed should be undertaken in collaboration with private employers, with costs primarily borne by the employer and trainees. To increase accountability, schools should eventuallybecome the responsibility of reconstituted local governments, with teachers and administrators being employed by and responsible to these community-based administrations. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Civil society Crosscutting Issues/Themes: Public governance Project Management: Executing/Implementing agencies Country Context: Decentralization Sector Related Issues: Education Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Methodologies/Approaches: Community approach The public institutions supporting agriculture have proven to be resistant to change and service delivery performance has been poor. The positive achievements that have been made in the agricultural sector reflect the liberalization of input trade and greater private sector involvement in this trade. This has brought about significant technology transfer and suggests that in research and extension, which have been neglected in past assistance programs, public and private contributions are synergistic. Similarly, greater beneficiary participation, with local councils becoming involved in O&M of small flood control and drainage (FCD) schemes has had positive results. This should be expanded. project cycle stage: Design, Operation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Technology/Technology transfer Sector Related Issues: Private sector Sector Related Issues: Public-private partnership Sector Related Issues: Rural development Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation The validity and relevance of COSs is greatly enhanced by realistic assessments of the difficulties of achieving progress, which in turn makes the risk assessments more meaningful and expectations more realistic. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-bangladesh-2003
Eighth Power Project | Bangladesh | Energy | 2003-01-15 | For future ADB assistance to Bangladesh Power Development Board (BPDB) and Dhaka Electricity Supply Authority (DESA) as executing agencies (EAs), the design and implementation schedule should take into account the track record of procurement delays, and ways to speed procurement. Also, ADB should ensure that future EAs fully understand its procurement processes through training and explanation of the importance of timely and accurate procurement in the Project Administration Memorandum at project inception. Delegation of powers from higher authorities to the EA is critical to both recommendations. The corporatization of DESA and the reorganization of BPDB into corporate entities and profit centers, paving the way for further restructuring, seems to be a potential solution. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Energy planning/management Policy & Reform: Public sector reform There is a need to integrate the project design and implementation team, currently the Project Implementation Organization (PIO), with the unit that will eventually oversee day-to-day operations of the investment. Currently, the PIO oversees all project implementation. Upon completion, that responsibility will be handed over to the operating unit. This system does not allow the consultants and contractors to transfer experience and practices to the operating unit. Integration will make the transition of systems such as supervisory control and data acquisition (SCADA) and power station's financial management upgrade, much smoother. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Operation and maintenance Project Management: Project management Capacity Development: Technology/Technology transfer Sector Related Issues: Energy planning/management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/eighth-power-project
Second Aquaculture Development Project (Loan 821-BAN[SF]) | Bangladesh | Agriculture, Natural Resources, and Rural Development | 2002-12-31 | Channeling a credit line through the banking system requires a rigorous examination of the capacity of the participating banks to act as effective financial intermediaries. The credit line should provide flexibility to participating banks in setting their lending interest rates to reflect credit risks of the respective clients. An assessment of credit demand should be rigorous, taking into account analyses of lending risks, risk averseness of banks, and requirements for secured lending including collateral coverage and its implications on the targeted potential clients. The credit demand assessment should not be simply based on the estimation of financing gap of projected investments and the expressed interest of participating banks. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Management: Risks/Risk management Capacity Development: Capacity assessment Extension services for aquaculture development can be highly effective when supported with trained and adequately equipped staff to demonstrate improved aquaculture techniques to private farmers. Diffusion of information has been effective when the extension has relied on feasible, simple, and low-cost technology to improve aquaculture practices. Rather than compartmentalizing the funding for fisheries extension services through various project initiatives, the government should support the role and functions of the executing agency in such services by providing the necessary funds on a program basis. project cycle stage: Design, Feasibility Operation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Technology/Technology transfer Sector Related Issues: Extension service Sector Related Issues: Rural development Policy & Reform: Information dissemination/Public awareness Fish stocking is an attractive option for sustaining inland fish production, but effective arrangements for sharing of costs and benefits among users and stakeholders are required. Apart from technical feasibility, organizational, management, and social aspects of fish stocking should be addressed. Participatory processes should be followed that require the involvement of stakeholders including beneficiaries from the planning stage. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financial benefits Project Design: Project design Project Management: Project management Country Context: Cultural constraints Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach Food safety and hygiene are key requisites for sustaining exports. Appropriate legal instruments for and enforcement of environmental protection and sanitation, and harmonization of standards for food safety are essential for sustained aquaculture operations. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Legal system Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Risks of diseases and their potential devastating impacts on aquaculture production should be considered during project preparation. Aquaculture health and sanitation management, including issues concerning diagnostics, health certification, and quarantine, is equally important to minimize risks of epidemics. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Rural development The poor credit recovery generally reflects the current conditions affecting the banking sector which has suffered from inadequate capitalization and nonperforming loans. Although these systemic conditions were recognized during project preparation, the use of loan covenants to mitigate risks has not been effective. The targets specified in loan covenants were too ambitious given the systemic and far-reaching problems afflicting the banking sector. An aquaculture project cannot be expected to resolve such problems. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Management: Risks/Risk management Sector Related Issues: Rural development Methodologies/Approaches: Targeting The start of project implementation was delayed by premature loan effectiveness and protracted recruitment of consultants. As the project proforma is an administrative requirement of the government, future project preparation should promote strong country ownership with clear responsibilities for counterpart government agencies to provide administrative clearances or approval on a timely basis, including compliance with ADB s Guidelines on the Use of Consultants. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Capacity Development: Ownership There should be operating guidelines for the recycling of subloan repayments by the participating banks. The use of the credit facility for such recycling should be monitored to prevent uses for purposes other than those intended by the project. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-aquaculture-development-project-loan-821-ban-sf
Dhaka Integrated Flood Protection Project | Bangladesh | Agriculture, Natural Resources, and Rural Development, Water and Other Urban Infrastructure and Services, Multisector | 2002-09-13 | Dhaka City Corporation's (DCC's) financial performance was very disappointing. DCC's reassessment ofproperty values within the city is long overdue, as the last reassessment wasconducted in 1989 while normally in Bangladesh the reassessment is due every5 years. DCC also failed to increase the rate of conservancy charges and theirsolid waste management operation is currently not financially viable. At appraisal, an international consultant for accounting, financial analysis, and managementinformation system was provided for 12 month-input; however his input wasreduced to only 9 months. The government and ADB should have paid moreattention to DCC's financial performance and adequate consulting servicesshould have been provided to tackle the problem. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Management information system Land reclassification was one of the main requirements for cost recovery of theflood protection facilities and was covenanted accordingly in the LoanAgreement. Directorate of Land, Records and Survey (DLRS) was expected to carry out action for the land reclassificationfrom its own budget. However, DLRS did not have the financial or institutionalcapability to carry out the reclassification, and ADB agreed to finance the part of the costs for the reclassification. DLRS's capability should have been reviewedcritically at appraisal and necessary assistance could have been provided toDLRS from the beginning of project implementation. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Loan Agreement: Loan Agreement Project Design: Appraisal Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Sector Related Issues: Water resource management One of the causes of implementation delay was the time consuming clearance ofillegal settlers along the left bank of the Buriganga River. When the project was appraised in 1991, ADB had no resettlement policy established and aresettlement plan for the squatter clearance was not included in the projectappraisal. The resettlement plan, if prepared at appraisal, could have avoided the delay. Nonetheless the resettlement of project-affected people was carried out in accordance with ADB's policy. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Appraisal | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/dhaka-integrated-flood-protection-project
Secondary Education Development Project | Bangladesh | Education | 2002-09-13 | Some major loan covenants like the decentralization of the Directorate of Secondary and Higher Education (DSHE) management system, and privatization of textbooks printing and publication, etc., were not fulfilled. Such loan covenants should have been properly assessed before their inclusion in the project, keeping in mind the government's capacity to achieve them within the project duration. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Capacity Development: Capacity assessment Country Context: Decentralization Sector Related Issues: Education Policy & Reform: Privatization The revised teacher education curriculum would have given better output if all the teacher educators of all teacher training colleges (TTCs) had been reoriented on the revised curriculum. project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Education Policy & Reform: Information dissemination/Public awareness To ensure sustainability, the formalities regarding the transfer of facilities and staffunder any project to the government's recurrent budget should be completed well before theend of the project. This transfer will reduce the sufferings of the employees under the project.Moreover, it will increase the job satisfaction of the employees and will have a positiveimpact on the outputs. Any future project design should carefully address the issue ofsustainability. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Project management Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-education-development-project
Railway Recovery Program (Loan 1310-BAN) | Bangladesh | Transport | 2002-08-31 | The program demonstrates, in an adverse fashion, that policy-based lending cannot be successful without sustained commitment of the government and concerned institutions to reforms. ADB recognized this from the beginning and insisted that the government demonstrate its commitment by implementing some key reform measures before the program s approval. However, the commitment wavered or has not been passed on to the successive governments or EA management teams. While it is difficult to foster such commitment externally, a key difference between a reform-oriented organization and otherwise, among others, may lie in the number of change agents at all levels but particularly at the top. Future program loans should make an assessment of the strength of such change agents and, as a long-term task, ADB should actively engage in nurturing them through dialogue and training activities. Also, it is important to assess the long-term commercial viability of the operations that the program loans intend to assist. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Modality: Policy-based lending Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Ownership Policy & Reform: Policy matrix Policy & Reform: Reform There appears to be a considerable gap between the program objective of breaking even against working expenses and the policy and institutional reforms pursued in that the EA faces many additional inherent physical constraints, namely aging fleet, a two-gauge system, and lack of railway connection between the east and west zones. Unless these physical constraints are alleviated, the break-even objective is unlikely to be sustained even if it has been temporally achieved. In this regard, ADB developed in 1996 the sector development program Modality, which is designed to provide policy, capacity building, and investment support in a holistic manner. This modality generally has three components: program, investment, and TA. Had the modality existed at the time of the program s formulation, it may have been a better tool to address the policy and institutional constraints, and to focus physical investments on selected potentially commercially viable operations to overcome key physical constraints. It would also have provided more incentive to the agencies that carried out the reforms in the form of investments and capacity-building opportunities since program loan proceeds go to governments general budgets. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Program Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Holistic approach Though generally sound, the design of the program could have been improved in several aspects. First, it was essentially a blueprint, target-oriented approach in that all objectives, and policy and institutional reform measures were expressed in terms of targets. This blurred the distinction between the program objectives and the means and the outputs intended to achieve the objectives among some government and EA officials. Many felt that as long as the measures are implemented, the objectives should be considered achieved with no need to carry out further reforms. This was quite evident during the OEM wrap-up meeting at which some EA officials blamed ADB for the EA's deteriorating performance by arguing that they had implemented almost everything that ADB asked them to do under the program and other loans. Future program design should be more result oriented by focusing on accomplishing program objectives rather than on outputs. By doing so, the total number of conditions could have been reduced dramatically, perhaps to seven or eight. The result-oriented approach would be more input-intensive, involving fewer hard targets but more dialogue and joint assessments, by ADB and the government, of reform progress during implementation. Second, the program was approved well after the completion of the labor retrenchment program. As a result, the condition on providing counseling and information services to the retrenched workers was not enforced. Future labor retrenchment program design may consider dividing the total compensation package into lump sum and monthly payments, to avoid the situation in which many workers spend their lump sum payments in a very short time without success in starting a new career. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Loan Agreement: Covenants Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/railway-recovery-program-loan-1310-ban
Road Overlay and Improvement Project | Bangladesh | Transport | 2002-07-15 | A major cause of delay encountered during implementation of the road improvementcomponent was the breach of contract in the joint-venture agreement between an internationaland a domestic contractor. This serves once again to highlight the importance of screening suchparticipants during the prequalification phase. Accepting that this exercise was undertaken bythe host government, closer collaboration between the executing agency and ADB may have prevented suchdispute. Similarly, delays encountered in the recruitment of consultants for the vehicle inspection centers (VICs) may havebeen minimized by the timely intervention of ADB. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation Despite the absence of a Project Administration Memorandum (PAM), all three teams of consultants complied with the periodic reporting requirements. But these dealt primarily with the physical and financial aspects of the works. There was little reporting on benefit monitoring and environmental aspects, which have been significantly strengthened in subsequent ADB-assisted projects. Increased emphasis still needs to be given to the advantages of such activities, particularly benefit monitoring following project completion. For this project, such a requirement was not enforced. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial reporting Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Reporting Project Management: Consultants Project Management: Project administration Project Management: Project reporting Capacity Development: Capacity building Projects involving multiple contracts packages in diverse locations need additional resources for implementation. A Project Administration Memorandum (PAM) and project supervision procedures should be designed and implemented to address both the technical and administrative needs, as well as the reporting requirements of ADB and the higher authorities inthe government. Even with these aids, however, if such projects continue to be designed using the piecemeal approach, contract packages will remain small and difficult to supervise. As is the tradition in Bangladesh, both executing agencies (EAs) relied heavily on consultants for basic contract administration and construction supervision assistance. This meant that the opportunity for optimizing skills transfer was missed. Procurement by the EA is obviously still a problem as demonstrated by the EA's lack of success in acquiring some simple road maintenance equipment. Delegation of responsibility between consultants for producing the Borrower's Project Completion Region (PCR) is anotherinherent weakness in multicomponent projects. In this case, the requirement for the preparation of a PCR was overlooked. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Project Management: Project reporting Project Management: Project supervision Country Context: Decentralization Capacity Development: Technology/Technology transfer Technical skills training for Bangladesh Road Transport Authority (BRTA) operators in vehicle inspection and testing was insufficient, and in view of the lengthy delays in this component it was not possible to supplement the earlier training given. The training initially programmed may have been sufficient had a semiautomatic testing system been chosen as envisaged. The decision to install fully automatic diagnostic equipment meant, however, that the time needed for installation and operating skills development was totally inadequate. Clearly, the choice of equipment for theproject's vehicle inspection centers (VICs) was incompatible with the operating environment. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Sector Related Issues: Roading The project was intended to prolong the life of existing assets in the road sector byinvesting in periodic maintenance works, which had been deferred by the government due tothe paucity of funds. To this end the project was successful despite the difficulty of supervisinga large number of road sections scattered over a wide area, each with different initial conditionsand traffic volumes. Notwithstanding the need to prioritize, it would be prudent in the future tocluster subprojects within clearly defined geographic or administrative areas. This would affordmore meaningful impact on local road networks while easing construction supervision demands.Project implementation would also have been aided had the design called for a minimum size ofcontract packages. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Project Management: Operation and maintenance Project Management: Procurement Project Management: Project supervision Country Context: Prioritization Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/road-overlay-and-improvement-project
Second Rural Infrastructure Development Project | Bangladesh | Industry and Trade, Transport, Multisector | 2002-07-15 | An adequate number of experienced contractors is not available in rural areas.Providing repeated training for contractors is very effective in enhancing theircapability and improving the quality of their work. The lease rates ongovernment-owned construction equipment were fairly low, prompting somecontractors to just keep the leased equipment on site without using it. Theequipment would be far better utilized and maintained if owned by contractors. project cycle stage: Implementation Lesson Topics: Project Management: Operation and maintenance Project Management: Procurement Capacity Development: Capacity building Sector Related Issues: Rural development Due to lengthy government internal procedures, the initial delays in procurementof construction equipment and recruitment of consultants could not be avoided.The advance procurement action and retroactive financing under the loan tocover engaging consultants could not be used. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Consultants Project Management: Procurement Local people were not fully aware of the use of union market management committee (UMMC) office buildings.Involvement of local government institutions and local residents in project designand implementation is requisite to the sustainability of project facilities. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Project management Country Context: Decentralization Methodologies/Approaches: Consultation/Participation The involvement of labor contracting societies (LCS) groups and nongovernment organizations (NGOs) helped increase participation and users' responsibility in the construction and maintenance of rural infrastructure. This provided employment opportunities to destitute rural women and encouraged many of them to come out for such development work. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Project Management: Operation and maintenance Crosscutting Issues/Themes: Employment Sector Related Issues: Rural development Methodologies/Approaches: Civil Society Participation The trial program of various types of bituminous surfacing for type-B feeder roads (FRBs) suggested that otta seal is unsuitable. The 40-mm carpeting for roads with heavy traffic and both 25-mm carpeting and double bitumen surface treatment were recommended for roads with light traffic. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-rural-infrastructure-development-project
Railway Technical Assistance in Bangladesh | Bangladesh | Transport | 2001-01-31 | Prior to and during implementation, demonstrated and sustained client ownership is necessary which should be evidenced by the passage of enabling legislation, if applicable, combined with unwavering support from senior political and executing agency management levels who need to fully appreciate the TA benefits and become champions of change with the mandate and necessary political authority to develop and implement changes and enhance the likelihood of sustainability of benefits. project cycle stage: Concept Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Ownership Regular and periodic steering and management committee meetings are an important means to address advisory and implementation problems. It is important that senior management attend and participate fully in these meetings to support changes and new systems introduced under the TAs. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Methodologies/Approaches: Consultation/Participation TAs should have sufficient and specific provisions within their TOR for the development of sustainability of their outputs and the attainment of ownership by the EA particularly in terms of performance indicators that are viewed as the starting point of a management information system essential for a commercially viable service-based organization. Otherwise, next phases of reforms and future involvement of ADB and other aid agencies will be significantly constrained. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Monitoring & Evaluation: Indicators Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Ownership Policy & Reform: Reform When seeking political commitment to reforms needed for subsequent progress, the recommendations of preceding TAs or other relevant examples of best practices should be followed without compromise before subsequent TAs and loans are processed. Once opportunities for leveraging desired actions have been lost, future progress toward desired objectives will at best be time-consuming, but may also never be achieved within a reasonable time frame or withoutextensive additional cost and effort. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Capacity Development: Ownership Policy & Reform: Reform | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/railway-technical-assistance-bangladesh
Impact of Bank Project Preparatory Technical Assistance on the Agriculture Sector in Bangladesh | Bangladesh | Agriculture, Natural Resources, and Rural Development | 1998-12-31 | An effective project depends on local commitment and ownership. PPTAs resulted in projects having high priority in both the government overall priorities and the EAs forward plans. However, the plans tended to be no more than priority lists of projects rather than plans of the EAs under which programs are implemented and projects provide the design and capital input to develop the programs. Such a program focus in an EA's activities is essential if some defined outcomes are to be achieved. Moreover, there would be more commitment and ownership if EA operations are guided under a program. There is, however, conclusive evidence that the stated corporate intent of an EA has often been subservient to unstated but acted upon objectives. As a consequence, there is often not a very coherent relationship between government and EA objectives and the ensuing projects. The strategy and work program should aim to reduce discrepancies between strategic objectives and project design. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Methodologies/Approaches: Program Approach Development of an accepted ADB methodology to enhance the monitoring of PPTAs based on specific performance criteria would help improve project planning and design and allow objective PPTA evaluation. PPTAs should include development of a plan to integrate such indicators into existing management information systems. In some cases, technical assistance for evaluation capacity building would be required to assist in creating such systems. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation Project Design: Project design Project Management: Management information system Capacity Development: Capacity building Experience shows that the PPTAs transferred few skills to the EAs. A major reason for the low level of technical transfer was the EAs' token provision of resources to PPTAs. Marginal provision of counterparts to PPTA teams often meant desultory EA involvement in a project design and acceptance of a dependency relationship with consultants. This resulted in little technical capacity improvement or, in some cases, technical de-skilling of an EA. Whatever the case may be, there has been no stated policy to outsource such services to international consultants but that is nonetheless what has often happened. Consultants have generally replaced both ADB and EAs in effectively driving project preparation. There should be a conscious policy to transfer project preparation skills to EAs and domestic consultants. This requirement should be reflected in the TOR prepared for individual PPTAs. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Counterpart funds Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Methodologies/Approaches: Consultation/Participation For ownership and commitment to exist, the EA should drive the project from concept to completion. Sufficient evidence was elicited during the study to suggest in agriculture projects a compliant government is driven to some extent by aid agencies. The result is that projects become more related to the funding agency's own lending strategy and policy than the government's. Measures of who is a PPTA's driver include determination of the principal player in identifying a prospective project, designing the TOR, and determining the principal client of the consultants. The extent to which the fiction has been ritualized that the government identifies a project and approaches ADB to seek PPTA and project funding is shown in large differences of perception between ADB and other agencies and key individuals. One consequence of the apparent fiction that ADB seldom identifies projects is the insufficient investigation by ADB of the depth of EA commitment to a proposed project and particularly to its outcomes. Most EAs had strong commitment to construct infrastructure but focused significantly less on managing, maintaining, and sustaining it, and on supporting the beneficiaries in using the infrastructure. project cycle stage: Concept Design, Feasibility, Implementation, Completion Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Loan Agreement: Loan Agreement Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Ownership Sector Related Issues: Rural development It is critically important for a PPTA to assess the capacity of the EA(s) that will be accountable for the project the PPTA is to prepare. Overall, the study PPTAs paid extensive attention to the EAs capacity to produce the outputs required by the project design but only occasional attention to the overall capacity of the EAs to manage their business and support their customers. However, there remains a significant lack of comprehensive institutional analysis, either as specific studies or as part of PPTAs. In addition, PPTA teams have seldom included institutional specialists. These continuing deficiencies mean that ADB has generally had rather anecdotal evidence of the environment in which it has operated. The delivery of effective outcomes also depended on the way the PPTAs reported project risks without specifying the likelihood of risk occurrence. Experience has shown that some risks have been rather large. It follows that careful assessment of the likelihood of project risks and barriers to change is an area of major interest to ADB management, particularly as regards an EA's capacity. Such assessment enables management to (i) be confident that its decision to proceed with a loan project is taken with adequate knowledge of the risks, and (ii) specify what risks are to be monitored and at what frequency. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Risks/Risk management Capacity Development: Human resources management Capacity Development: Institutional analysis Projects prepared in the 1990s are more effective in meeting the needs of the customer. ADB has initiated an improvement process whereby beneficiaries are increasingly an integral part of the design process. The outputs and TOR of some recent PPTAs have reflected that many agriculture projects need to follow a participatory approach as they provide facilities or services that are for the eventual customer to use directly. In these cases, planning started with the premise that customers are in control of the PPTA and project process from the onset. In contrast, ADB's conventional project cycle, which is still in force for most PPTAs in the ANR sector in Bangladesh, start with the implicit proposition that ADB is initially in control of the PPTA and is replaced by the EA during project implementation. This approach is not particularly sensitive to customer needs and has a tight time schedule that constrains the process of customer participation. Responses suggested that participatory planning has not been well understood by EAs and consultants. They considered that designs were developed in a participatory way with end users given due consideration, despite structural problems. Actually, in most PPTAs some measure of consultation occasionally occurred from a small cross-section of potential end users. However, this is different from participatory planning that involves the users from an identification of their needs through the planning of interventions to implement the project. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Problem identification Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach Rather than adopting fixed budget limits in advance, the size of a PPTA needs to be based on what is known about the situation of a prospective project and the information available. Time and budget for the PPTA fact-finding mission need to clearly address this issue. A critical factor is that the mission members investigate their own areas individually and meet the people able to provide them with the needed information. Determining the time appropriate for a PPTA is essential to engaging the EA as a truly participating partner in design work. This requires that a distinction be made in a PPTA between process and design. The process needs to ensure an agency's commitment and capacity, as well as assessment of the project needs, so that the design itself becomes the residual part focusing on technical specifications. The design can then be outsourced without threatening the EA capacity or its commitment to or ownership of the project. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Technical quality and terms of reference (TOR) are major determinants of PPTA success. Technical quality relates mostly to consultants' competence. Other factors are also important such as the requirement to produce a realistic project design and a technical solution within the competency of an EA to implement and sustain, as well as the need for close PPTA supervision. Key elements of the TOR to ensure a greater likelihood of having an effective design and sustainable loan project include the following (i) analysis of beneficiary needs and capacities as well as opportunities for development; (ii) assessing whether there is a driving need for the project and commitment of the EA to its outcomes; (iii) requirement of close cooperation between the PPTA team and EA to secure full agreement and ownership, resulting in incorporation of the project in the EA program and the latter being supported by adequate funds; (iv) diagnostic analysis of the EA and identification of barriers to effective project implementation and O&M; (v) identification of constraints to project effectiveness and detailed strategies to address such constraints; and (vi) determination of a focused work program for the project based on deliverable outputs and realistic objectives with built-in flexibility to accommodate effective beneficiary participation. Effectively attending to these determinants of PPTA success will require as a minimum that objective criteria be set ADB-wide for evaluation of a PPTA and an EA's capacity to manage a project. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Modality: Technical Assistance Monitoring & Evaluation: Project evaluation Project Design: Problem identification Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Three major issues related to the way projects are processed have affected design quality. They concern (i) the overall project concept being determined before testing; (ii) the size of the project not being within the EA's capacity to manage; and (iii) the project design not being consistent with the EA's capacity to sustainably operate and maintain it. If a PPTA is started with a solution, alternatives are generally not considered, notably by ADB. In contrast, starting with a problem to be addressed or a desirable condition to be obtained would encourage a study to look at viable alternatives and choose the best. This implies that the TOR for a PPTA addressing a problem or desirable condition would specify the outcomes and the consultants would have to work out if and how these would be achieved. This approach would move ADB toward writing PPTA proposals with innovative ideas on how to achieve development objectives. In projects where risks appear high and tested solutions are few, designing big has its own risks. The solution-driven approach to agriculture PPTAs, requiring people to adapt to the demands of the design, often meets with little success, particularly in the larger projects. In contrast, a market-needs approach requires the project to be designed to meet the demand of beneficiaries, which in turn requires innovations to be first tested on a pilot basis. ADB mechanisms to that effect need to be strengthened for identifying and disseminating tested designs. Designs for infrastructure, particularly in PPTAs in the irrigation subsector, have often not been consistent with the availability of recurrent funds for O&M. When such projects fail for lack of maintenance financing, economic efficiency is reduced and significant numbers of people who would otherwise have the opportunity to work as farm laborers are deprived of work. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Modality: Technical Assistance Project Design: Problem identification Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Risks/Risk management Capacity Development: Institutional analysis Sector Related Issues: Irrigation management Methodologies/Approaches: Pilot project Thus far, ADB has not had a rigorous methodological framework to guide the development of an effective project design. This absence has led to projects having a design with (i) unclear objectives, (ii) provision of activities that do not contribute to project objectives and absence of activities that are required to produce an objective, and (iii) inadequate resources to deliver the objectives. The absence of a methodology also makes decisions about project viability much more difficult for management to make. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Project design | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-bank-project-preparatory-technical-assistance-agriculture-sector-bangladesh
Seventh Power Project and East Zone Thermal Feasibility Project (Loan 751-BAN[SF]) | Bangladesh | Energy | 1998-12-31 | There is need for ADB to enhance the basis of using financial covenants to strengthen institutional and operational performance and avoid loan suspension. project cycle stage: Appraisal Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/seventh-power-project-and-east-zone-thermal-feasibility-project-loan-751-bansf
Ganges-Kobadak Irrigation Rehabilitation Project (Loan 671-BAN[SF]) | Bangladesh | Agriculture, Natural Resources, and Rural Development | 1997-12-31 | In contrast to large new irrigation systems, rehabilitation can yield large economic returns. Rehabilitating existing irrigation schemes may affect their economic worth if the increased output turns a country from a food importer to a net exporter. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Project supervision from a resident office rather than from the ADB Headquarters is often more effective, particularly when it results in a better understanding of local problems and more judicious and timely reallocation of loan proceeds. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project supervision Other: Resident Mission The uncertainties in service delivery that characterize large irrigation schemes hinder cohesive water management at the farm level and reduce the farmer's willingness to pay irrigation service fees. The collection of service fees would be facilitated if such schemes become demand- or need-oriented, and if a level of service similar to that of private tubewells, for which farmers are prepared to pay in addition to capital and depreciation costs, were provided. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Uncertainty exists regarding the role and specific activities of BME units in large irrigation projects. Information systems geared to manage such projects may be more of a priority than the more traditional BME activities. There may be a case for strengthening the management information systems in such projects. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Management information system Country Context: Prioritization Sector Related Issues: Irrigation management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/ganges-kobadak-irrigation-rehabilitation-project-loan-671-bansf
Second Natural Gas Development Project (Loan 714-BAN[SF]) | Bangladesh | Energy | 1997-11-30 | The project highlighted the need (i) at project preparation to pay more attention to the technical risks and engineering evaluations associated with well development; (ii) at project design to implement procedures for fast-tracking, thus avoiding unnecessary delays in processing and administration of contracts and the timely availability of government funding; (iii) at implementation to ensure that transmission, treatment, and processing designs do not limit flexibility of operations, and/or reservoir management practices. Reflecting the current operational status of EAs, a continuing need exists to (i) pay more attention to improving the flexibility of sourcing gas supplies from different fields through unifying the management of transmission operations; (ii) improve institutional efficiency by strengthening monitoring capabilities at the different functional operations for well development, transmission, and distribution; (iii) reduce system losses at distribution; and (iv) enhance the financial performance of EAs through increasing end-user tariffs. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Risks/Risk management Capacity Development: Capacity building Sector Related Issues: Energy planning/management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-natural-gas-development-project-loan-714-bansf
Pabna Irrigation and Rural Development Project (Loan 378-BAN[SF]) | Bangladesh | Agriculture, Natural Resources, and Rural Development | 1996-12-31 | Assessment of future flood damage without embankments should not only reflect crop losses incurred during past floods, but should also consider changes - which would likely occur without the project - that would offset some crop losses. Even in the absence of a project, farmers continually improve flood strategies which increase crop output. Moreover, higher crop output often follows a flood. On the other hand, benefits from flood protection in sectors other than agriculture may be more significant, which should considerably influence project design. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development Overstating project benefits at appraisal must be avoided as it often affects design and leads to inefficient investment decisions. In designing projects aiming to increase crop outputs, the contribution of other means than the project to enhance production must be recognized. project cycle stage: Design Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Sector Related Issues: Rural development Project experience demonstrates that the costs and benefits of land acquisition in Bangladesh's increasingly densely populated rural areas need to be investigated during project preparation. Design decisions in that regard are particularly important in that they may lead to compromises largely defeating a project's purpose and sustainability. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Crosscutting Issues/Themes: Sustainability Project Design: Project design Sector Related Issues: Rural development Project experience highlights that the complexity, sophistication, and number of components of a project should match the level of socioeconomic development in a project area and the capacity of the implementing agencies. In poorer areas, projects need to be relatively straightforward with fewer components and simpler design to facilitate implementation and benefit generation at a lesser cost. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity assessment | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/pabna-irrigation-and-rural-development-project-loan-378-bansf
Northwest Rural Development Project (Loan 615-BAN[SF]) | Bangladesh | Agriculture, Natural Resources, and Rural Development | 1996-03-31 | In order for skills training of cooperative members to succeed, it should be preceded by a thorough survey of the demand for various trades and followed up with timely credit and marketing support to facilitate the development of entrepreneurship among the rural poor. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Capacity Development: Capacity building Sector Related Issues: Rural development Project reformulation could have been avoided if the preparation had included thorough assessments of geohydrological conditions in the project area and the need for types of minor irrigation equipment. If reformulation is to be undertaken, it should be carried out as soon as it is evident that the components as appraised are no longer relevant. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Strict screening measures must be established to ensure that only the target beneficiaries are allowed to gain cooperative membership. In addition, such membership should be kept small to encourage accountability and responsible credit behavior by the members. project cycle stage: Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Rural development Methodologies/Approaches: Targeting The project underscores the importance of fielding consultants in timely manner during implementation. The late recruitment of consultants delayed the implementation of the project. project cycle stage: Implementation Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/northwest-rural-development-project-loan-615-bansf
District Towns Water Supply Project (Loan 571-BAN[SF]) | Bangladesh | Water and Other Urban Infrastructure and Services | 1995-11-30 | Implementation should commence only after appropriate technically trained and experienced personnel ( either government personnel or consultants) are available to supervise contractors. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project supervision Regardless of the technology, any least-cost approach to water supply project planning and implementation will not achieve sustainable projects unless it is underpinned by sound financial and economic principles. Appropriate water tariffs must therefore be in place and be acceptable to potential household users prior to project implementation. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Water resource management The design of community sanitation programs should stress the importance of household hygiene, health standards, social maturation, and women's involvement. Particular emphasis should be given to the role of women in participating in the design of sanitation programs to reflect their views and allow for their responses to engineering designs that will be introduced into the home. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Gender Project Design: Project design Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation Where pilot schemes such as new sanitation programs are introduced to local communities, the schemes should be sufficiently flexible to accommodate as wide a range of technical options as possible. The pilot sanitation system introduced to the project involved only one sanitation design, which was found to be unpopular because of its size. Its lack of community acceptance could have been determined with fewer initial pilot units. project cycle stage: Design Lesson Topics: Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Pilot project | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/district-towns-water-supply-project-loan-571-bansf
Housing Sector Institutional Strengthening in Bangladesh | Bangladesh | Finance | 1995-11-30 | The likelihood of success of TA projects involving a wide range of interlocking agencies such as for the housing sector may be maximized when agencies fully support the objectives and adopt a position of mutual ownership of the outputs. This can be achieved when the terms of reference are mutually developed and refined, involving ADB, the agencies, and the consultants. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Urban sector/development There are a number of differing viewpoints to consider in defining housing financing, and different problems emerge with respect to the individual stakeholders involved. For households, the problem is access to affordable loans; for the primary government housing agencies, the problem is affordability; for the housing banks, the issue is how to expand the scope of financial services while maintaining a viable institution; for ADB and the DMCs' monetary authorities, the issue is to prevent financial instability and to maintain confidence in the financial system. Hence, any overview of housing finance in developing countries cannot be limited to a discussion of the availability of low-income housing finance. It must also consider the complex problems of developing effective financial intermediaries. To this extent, the TA was constrained in its scope from the outset, and thus the limited results achieved in relation to improved housing finance are not unexpected. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Sector Related Issues: Urban sector/development | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/housing-sector-institutional-strengthening-bangladesh
Flood Damage Restoration Project (Loan 892-BAN[SF]) | Bangladesh | Transport | 1995-08-31 | ADB should not expect the implementation of disaster rehabilitation projects to restore and repair transport infrastructure and achieve significant gains in technical, operational or economic efficiency. These objectives are usually not high priority for an executing agency responsible for restoring essential services such as railway operations after a disaster. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Country Context: Emergency Sector Related Issues: Transport planning For emergency projects, ADB should review (and if appropriate, revise) its requirements relating to reimbursement procedures to liquidate imprest accounts, specifically: (i) the categories of expenditure, and (ii) the minimum amount for each withdrawal application. project cycle stage: Implementation Lesson Topics: Project Management: Project administration Country Context: Emergency | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/flood-damage-restoration-project-loan-892-bansf
Serajgonj Integrated Rural Development Project (Loan 293-BAN[SF]) | Bangladesh | Agriculture, Natural Resources, and Rural Development | 1995-08-31 | Beneficiary participation is the best method of preempting unwanted beneficiary intervention and avoidable costs for acquisition of land or for repeated rehabilitation of facilities. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Operation and maintenance Methodologies/Approaches: Consultation/Participation Beneficiary targeting has to be more focused to ensure delivery of benefits to the relatively poor wherever practicable. Performance reviews by the government and ADB need to cover, among other things, structures and processes of decision making to ensure participation by the poorer groups, and accountability for the utilization of project facilities. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Targeting Flood control projects in deltaic areas should be conceived within a holistic assessment of the entire hydrological system and ecosystem. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach Other things remaining the same, the chances of the timely and successful implementation of agricultural and rural development projects are inversely proportional to their complexity, i.e., the multiplicity and diversity of their components and of their executing agencies. Further, in the case of large implementation agencies, project components that are physically and financially small do not generate a high level of commitment to a project in such agencies. Future integrated rural development projects should confine their objective to directly increasing production, with accompanying supporting services and groundwater irrigation as components as may be necessary. But flood control and drainage/irrigation projects and the provision of social services should be separately addressed, preferably under sector projects. There should be one overall executing agency for integrated rural development projects, with substantial components to be implemented by other relevant agencies. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Education Sector Related Issues: Health and sanitation management Sector Related Issues: Irrigation management Sector Related Issues: Rural development Project experience demonstrated that the collection of adequate, reliable data for project formulation is of fundamental importance. Where this is inherently difficult, as in the case of flow of rivers, risks must be minimized through a process approach. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Methodologies/Approaches: Process approach Project performance needs to be protected against adverse extraneous policy decisions: loan amnesty to agriculturists other than members of cooperatives has undermined the authority of those who recover cooperative credit, made members of cooperatives determined not to pay, and highlighted the poor mechanisms for rural credit recovery. Cavalier decisions on fiscal policy, especially if they are perceived as inequitable, can put governments in a difficult situation. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/serajgonj-integrated-rural-development-project-loan-293-bansf
Designing a Framework for the Asia SME Finance Monitor: Technical Assistance Completion Report | Bangladesh, Cambodia, China, India, Indonesia, Kazakhstan, Korea, Malaysia, Papua New Guinea, Philippines, Solomon Islands, Sri Lanka, Thailand, Viet Nam | Finance | 2015-09-01 | The ASM (Asia SME Finance Monitor) 2013 successfully drew the landscape of SMEs (small and medium-sized enterprises) and SME finance in Asia and the Pacific, which had been long lacking. Building partnerships with institutions in DMCs (developing member countries) for data collection was a key success factor for the ASM. We received a good sign from DMCs on this knowledge product for their use for policy discussions. Internally, ADB operations started thinking about SME projects, based on the findings from the ASM. Given the inaugurated project, the ASM team was coordinated and guided by ADB staff, and it took a long time to train consultants and make them understand the project concept and the data collection modality. To effectively manage overall workload for producing the ASM, ADB staff prepared the guideline on data collection and country paper review process for consultants who belong to the ASM team, which has been utilized for the on-going ASM second phase project (approved in 2014). Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/designing-framework-for-asia-sme-finance-monitor-tcr
ADB's Rural Credit Assistance in Bangladesh, Peoples Republic of China, Indonesia, Nepal, Philippines, Sri Lanka and Thailand | Bangladesh, China, Indonesia, Nepal, Philippines, Sri Lanka, Thailand | Agriculture, Natural Resources, and Rural Development, Finance, Industry And Trade | 2001-01-31 | A more focused targeting of the poor in terms of incidence, locality, priority and needs through a participatory process would need to be adopted to have a credible impact on poverty reduction which traditional rural credit projects do not effectively address. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financing Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach Methodologies/Approaches: Targeting As a whole, advisory TAs have been appropriate and useful as a mechanism for capacity building but should nevertheless be rendered in a sustained manner over a period of time rather than as isolated instances tomaximize their impact on capacity building. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Cluster operations Modality: Technical Assistance Capacity Development: Capacity building Besides mere provision of credit to clients, rural credit projects need to give due emphasis to the development of a sound and sustainable rural financial system that will provide an enabling environment and a range of financial services from sources other than the participating financial institutions, with focus on the poor. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financing Sector Related Issues: Rural development In the pursuit of a sustainable rural financial system, rural credit projects should be designed within the mandate and capacity of the participating financial institutions or EAs to avoid high administrative costs, implementation difficulties and inefficiency in the provision of capacity building and institutional strengthening assistance. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Sector Related Issues: Rural development Where foreign exchange risks are borne by participating financial institutions or clients, a foreign exchange risk mitigation mechanism which can be in the form of a fund built into the project loan, needs to be put into place to ensure that a rural credit project is not terminated prematurely as a result of losses incurred by the participating financial institutions or the clients. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Foreign exchange Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Sector Related Issues: Rural development | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/adbs-rural-credit-assistance-bangladesh-peoples-republic-china-indonesia-nepal-philippines
Selected Technical Assistance in Road Safety | Bangladesh, India, Indonesia, Kazakhstan, Pakistan, Papua New Guinea, Philippines, Singapore, Thailand | Transport | 2001-01-31 | Road safety should be accorded the priority it deserves through sufficient investments in projects, preparation of ADTAs on capacity building in road safety, the systematic undertaking of safety audits after completion of road designs and before commissioning of road projects, and through conduct of safety education for drivers and road users. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Roading Policy & Reform: Information dissemination/Public awareness | Technical Assistance Performance Evaluation (TPER) | Highly successful | http://www.adb.org/documents/selected-technical-assistance-road-safety
Reform of Pension and Provident Funds in Selected Developing Member Countries | Bangladesh, India, Indonesia, Thailand, Uzbekistan | Finance | 2003-12-31 | Continuity in the management of technical assistance - from design through implementation - greatly improves the likelihood that it will make lasting contributions and achieve its desired outputs. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Management: Project management The design of technical assistance must respect the specific needs, constraints, state of economic development, and human and financial capacity of the country it is intended to support. Overly ambitious designs for countries with low levels of institutional development are bound to fall short of expectations. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity assessment Capacity Development: Institutional analysis The effectiveness of technical assistance depends heavily on the quality and skills of ADB management. The institution requires staff with better developed skills and expertise in social policy issues in order to design and implement appropriate first or second pillar pension reforms. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Technical Assistance Project Management: Project management Project Management: Project supervision Capacity Development: Human resources management Policy & Reform: Policy reforms/framework Policy & Reform: Reform The provision of technical assistance in support of pension reform is most effective in cases where the government has expressed a strong appetite and commitment to the issue. It absolutely requires strong counterparts to champion the issue in the political arena. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Ownership | Technical Assistance Performance Evaluation (TPER) | Unsuccessful | http://www.adb.org/documents/reform-pension-and-provident-funds-selected-developing-member-countries
Impact Evaluation of Bank Assistance to Developing Member Countries for Benefit Monitoring and Evaluation | Bangladesh, Indonesia, Pakistan, Philippines, Sri Lanka | Agriculture, Natural Resources, and Rural Development, Education, Health | 1996-12-31 | Benefit monitoring and evaluation (BME) is looked upon in DMCs as an external imposition and ADB treats it as a mere project-specific technical requirement. Thus, there is a need to promote both the demand and supply side of ownership. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Capacity Development: Ownership BME should not be taken as a control mechanism but an information system which allows governments to exercise good management practices, namely, to take well-informed decisions and corrective actions whenever needed. This understanding has to be increased through discussions among government agencies on how to operationalize development management concepts in their national context, including the development of coordination mechanisms, regular exchange and pooling of information, and delineation of responsibilities. The government should continue to make policymakers appreciate the value of BME through an awareness campaign and encourage implementing agencies to publicize the BME success stories. project cycle stage: Operation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Management information system Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation Executing agencies should increase their understanding of their role in the context of development management. This requires an increasing awareness of the effects and impacts of goods and services they deliver to target groups, and a sharing of information on these aspects. In this context, BME indicators for specific sectors may be standardized in the interest of simplicity and efficiency and to allow proper assessment of project impact on the respective sectors. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Project Management: Executing/Implementing agencies Policy & Reform: Information dissemination/Public awareness Performance Management System (PMS) should be integrated to the entire project cycle, including sectoral and national impacts of project interventions. There is a need for an incentive framework which will encourage behavioral change and encourage the adoption of a performance management culture. Successful performance management requires a participatory approach; ADB and DMC counterparts should team up throughout the project cycle to agree on performance objectives, indicators, and accountabilities. Indicators should be simple, relevant and include a mix of both qualitative and quantitative measures. project cycle stage: Design, Feasibility, Appraisal, Implementation, Completion Operation Lesson Topics: Monitoring & Evaluation: Indicators Policy & Reform: Policy reforms/framework Methodologies/Approaches: Participatory approach Systematic and disciplined performance management is important and applies to the entire perspective of development efforts, from a project intervention to sector and institutional management, as well as to macroeconomic management. In this context, ADB needs to provide concrete assistance to DMCs to build their capacity for performance management and to strengthen its own capacity in this field. Likewise, within ADB, there should be broader ownership of PMS and a team effort to institutionalize it. project cycle stage: Country Partnership Strategy Lesson Topics: Capacity Development: Capacity building Capacity Development: Ownership The lack of BME integration to the agencies' MIS structure has prevented the sustainability of BME capacities in the study countries. ADB's past approach of assigning BME responsibilities to PIUs was flawed with design deficiency as such approach assumed BME system as project-tied activity resulting in a discontinuation of these activities after project implementation is completed. This did not contribute to institutional development. Similarly, overreliance for BME on external consultants and PIUs, which are coterminous with the projects, undermines the sustainability of capacity building efforts. Lack of expertise transfer, insufficient emphasis on skill building of EAs, inadequate budgetary provision, and flawed approach to BME assistance all contribute to limited sustainability and capacity building. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Project management Capacity Development: Capacity building Capacity Development: Technology/Technology transfer The practice of undertaking BME at individual project level is inadequate and there is a need to link it with the sector and eventually with the national level. The Project Performance Management Systems (PMS) is considered a better system. The PMS would focus on all levels of project performance: (i) project inputs; (ii) project outputs; (iii) immediate project impacts; and (iv) longer term impacts. For effective functioning of PMS, the following elements are important: (i) a clear set of measurable and monitorable performance indicators established for each level of results, and a process institutionalized for collecting data and reporting on these performance indicators as part of the project management and evaluation system; (ii) the identification of such performance indicators starting at project design stage; (iii) the monitoring of these performance indicators integrated into ADB's project implementation supervision processes, and into the executing agency's institutional performance monitoring and reporting; and (iv) the information from such monitoring used to actively manage the implementation process so as to ensure the more effective achievement of benefits. project cycle stage: Design, Feasibility, Appraisal, Implementation, Completion Operation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Monitoring & Evaluation: Reporting Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Project supervision There is a need to improve the BME activities both in the DMCs and in ADB including establishing a conceptual clarity and if necessary changing the terminology itself to suitably reflect the concept. The required BME system which would help carry out effective monitoring and evaluation has to be seen as one that would prove to be important to national planners, to line agencies, to executing agencies, to beneficiary communities, and to evaluators in the DMCs. It has to be equally useful to the development financing institutions. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Executing/Implementing agencies | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-bank-assistance-developing-member-countries-benefit-monitoring-and
Secondary Science Education Projects in Nepal, Bangladesh, and Pakistan | Bangladesh, Nepal, Pakistan | Education | 1998-12-31 | Determining the right mix and quantity of inputs cannot be done without a clear specification of the desired outcome and a thorough understanding of the process to produce such outcomes. In the case of the science education projects, this would have entailed taking pains in analyzing the teaching and learning process taking place in the actual classroom situation. Further, the analysis would have included the broader picture outside the classroom, particularly that science education is an integral part of the larger education system that in itself has a systemic quality problem. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education Implementation in all three project countries suffered significant deviations from the original implementation timetable. Besides the economic costs of the delay, another major adverse impact was the distortion of the logic in the sequencing of project components, e.g., teacher training came ahead of the new curriculum, thus reducing the potential impact of the project inputs. To help minimize delays in future projects, the following lessons from project experiences should be noted: (i) need for the prompt selection of the project director and other key positions, and avoiding frequent changes once they are appointed; (ii) within established guidelines, granting a certain degree of operational autonomy to regional/provincial units so that the more efficient units will not be adversely affected by the less efficient ones, a particularly important consideration in a federal setup such as in Pakistan; and (iii) training project staff in ADB financial systems and procedures, and familiarizing ADB staff with the project country's financial systems and procedures. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project administration Capacity Development: Capacity building Capacity Development: Human resources management One of the most glaring observations in all the project countries is the long period of inactivity following project completion, particularly of the newly established institutions. Activities were not sustained due to the failure to provide funds for continuing operation, suggesting lack of commitment. As a result, momentum was lost and the physical assets and human resources assigned to the project remained grossly underutilized. Subsequently, after a lapse of two to four years, a costly restart of activities ensued upon the implementation of a follow-up project. Future projects need to focus on the long-term nature of changes initiated, and a realistic and frank view needs to be taken of the executing agency's commitment to reforms and its financial capacity to sustain them. In the absence of sufficient local capacity for sustainability, ADB should consider whether it can undertake a sequence of projects as an approach to introducing sustainable improvements over an extended timeframe. project cycle stage: Completion Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Cluster operations Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity assessment Capacity Development: Human resources management Capacity Development: Ownership Policy & Reform: Reform Project management units were detached from what was going on in the classrooms. No data were available even on a periodic sampling basis indicating to what extent and how effectively the intended curriculum was implemented in the classroom and, if a significant portion was not implemented, to find out why. The absence of such real-time feedback deprived project management of the opportunity to effectively influence the outcome. It was a serious shortcoming. If management is to be in control, such an information gap must be filled or, in its absence, management must literally patrol the classrooms regularly. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management There is need for a balance in the establishment of new institutions science centers, teacher training institutes between flexibility and effectiveness of operations, on the one hand, and, on the other hand, operation within the mainstream of functional and administrative lines of authority of the government to ensure technical and financial sustainability beyond the project life. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Sector Related Issues: Education Throughout the project countries, there are secondary schools that stand out from the rest. Yet, they are just as exposed, as the others are, to the same constraints such as inadequate budgets, poor physical facilities, and political pressures. The critical importance of the process of choosing the head of an institution, new or old, cannot be overemphasized. Ordinarily, if the selection process is based on merit rather than mainly on political considerations, the results are invariably better. To the extent possible, ADB should actively influence the process of depoliticizing the selection of the project director as well as other key managers to increase the chances of success of its projects. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Human resources management Sector Related Issues: Education | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/secondary-science-education-projects-nepal-bangladesh-and-pakistan
Bank Assistance in the Health and Population Sector in Bangladesh, Pakistan, Papua New Guinea, and Sri Lanka | Bangladesh, Pakistan, Papua New Guinea, Sri Lanka | Health | 1997-11-30 | ADB should design and implement projects keeping in mind not only lessons learned from earlier interventions, but the need to reinforce the positive impacts of past successful projects. Lessened impact from cancellation, non-use, and implementation delay of project components could have been minimized with more thorough assessment of the constraints facing the sector. Other inadequacies, which include the absence of impact indicators and relevant baseline data at project preparation, poor monitoring at implementation, faulty design due to inadequate preparatory work, and minimal involvement of health care providers and beneficiaries throughout the project cycle, likewise indicate the need for an in-depth analysis of the sectoral and institutional issues prior to project formulation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Institutional analysis Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation The initial impact generated by ADB's assistance must be sustained. Sustainability of the benefits of the projects depend on the availability and operational efficiency of the facilities established under the projects. The lack of adequate budget provisions for O&M and related delays in making project facilities operational have significantly reduced the full potential impact of ADB's assistance. If user charges are imposed, the sums collected could contribute to minor maintenance expenditure. Given the welfare orientation of most governments in regard to social services and the traditional political climate on such a sensitive sector as health, any attempts at cost recovery require considerable effort. Yet the DMC governments need to consider alternative financing strategies because the increasing demand for health services are not matched by increasing budget allocations. To improve cost recovery, unit costing of services must be developed. Such information would help the governments to decide on the methods of cost recovery. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Project Management: Operation and maintenance Sector Related Issues: Health and sanitation management | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/bank-assistance-health-and-population-sector-bangladesh-pakistan-papua-new-guinea-and-sri
Impact Evaluation Report on the Development of Genetically Improved Farmed Tilapia and their Dissemination in Selected Countries | Bangladesh, Philippines, Thailand | Agriculture, Natural Resources, and Rural Development | 2005-10-31 | Multilevel partnerships and broad-based networks that are driven by common objectives and mutual commitments are highly valuable mechanisms for developing and disseminating genetically improved farmed fish strains, such as genetically improved farmed tilapia (GIFT). Public-private partnerships, moreover, have been instrumental in the sharing of resources, expertise, and information in support of tilapia breeding, seed production, and farming. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Capacity Development: Capacity development Capacity Development: Partnerships Capacity Development: Technology/Technology transfer Sector Related Issues: Public-private partnership Sector Related Issues: Rural development Policy & Reform: Information dissemination/Public awareness Systematic assessments of the performance of genetically improved farmed fish under diverse conditions must precede their commercial production. Multidisciplinary expertise is needed to assess the economic viability, social acceptability, environmental compatibility, and the overall impact of genetically improved farmed fish. It is important to develop the skills and provide adequate resources for these assessments. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Finance & Financial Aspects: Financing Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Project evaluation Project Design: Appraisal Project Design: Project design Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Rural development The development and dissemination of genetically improved farmed tilapia (GIFT) have shown that selective breeding is a feasible and cost-effective approach to the genetic improvement of tropical farmed fish. GIFT were developed without the need for any application of controversial biotechnology or genetic modification. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Rural development | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-report-development-genetically-improved-farmed-tilapia-and-their
Strengthening Royal Monetary Authority's Regulatory Capacity for Nonbank Financial Institutions: Technical Assistance Completion Report | Bhutan | Finance | 2015-09-01 | TA (technical assistance) administration can become complex and cumbersome with the recruitment of a number of individual consultants, as was the case under this TA. Given the required number of consultants and numerous outputs to be delivered under the TA, hiring under a firm selection process would have reduced the administrative complexity of handling individual consultants for better coordination and monitoring of TA outputs. Also, the RMA (Royal Monetary Authority) would have benefited more if the outputs were seamlessly integrated that would help determine gaps, future interventions, and strategy to further develop and strengthen the capacity building of NBFIs. Also, any future TA support of this nature covering too many financial subsectors should have needs assessments undertaken at the initial stages of the TA design to determine priorities and specific deliverables for better monitoring of TA outputs. This should include well considered indicators and targets for the outputs and outcome in the design and monitoring framework with clearly defined data source and collection approach, and a mechanism for monitoring the indicators. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-rma-regulatory-capacity-nbfi-tcr
Strengthening Audit Resource Management: Technical Assistance Completion Report | Bhutan | Public sector management | 2015-08-01 | The collaborative approach to software development by government officials and consultants can be replicated. Capacity development technical assistance (CDTA), if designed and implemented to properly encourage and strengthen government ownership, can help a small developing member country (DMC) to initiate important reforms even with a limited TA (technical assistance) budget. Linking up tangible TA achievements to a program loan serves to strengthen government ownership and provides potentially greater discipline to the implementing agency to ensure timely completion. Project cycle stage: Design, Implementation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-audit-resource-management-tcr
Strengthening Economic Management Program: Completion Report | Bhutan | Finance, Public Sector Management | 2015-07-31 | Active stakeholder consultations during both program inception and implementation are imperative for creating a strong sense of government ownership, and ensuring commitment by all stakeholders to achieving the required policy actions under ADB program loans. Policy actions must be thoroughly assessed, clearly defined, relevant, and achievable within the required time frame, in particular when quick release of funds is critical for urgent budget support in crisis situations. project cycle stage: Concept, Implementation, Operation Carefully aligning objectives and outputs of ADB program loans with related TA can help increase effectiveness and sustainability, and ensure efficient implementation of both ADB interventions and ADB TA recommendations. By incorporating related TA deliverables into the program design, the program helped ensure high-level government commitment to policy reforms and accelerate implementation of highly relevant TA recommendations, which may otherwise not have received the same level of attention and commitment. project cycle stage: Design, Implementation, Country Partnership Strategy Execution of pilot projects is valuable for (a) assessing ease of implementation, adaptability and potential for full-scale implementation; and (b) for identifying new potential bottlenecks and areas requiring further reforms. The successful pilot testing of a new property valuation method (PVM) demonstrated the potential for substantially increasing local revenues from property taxes as anticipated, but also contributed to potential revisions of the outdated tax laws. project cycle stage: Design, Implementation, Operation Policy-based loans can be successfully designed to provide an integrated approach to policy reforms by (a) leveraging constructive policy dialogue, (b) incorporating tailored policy interventions, and (c) ensuring implementation support and capacity development through TA project cycle stage: Design, Implementation, Operation Policy reforms are largely politically driven. The involvement and roles of government, stakeholders and politicians and the benefits to each party are important considerations in the design and implementation of policy-based loans. With a change in government in 2013, actions initiated under the program could have been altered, reversed or subject to delays or resistance. However, the program initiatives were fully endorsed by the new government, demonstrating that the program was well thought out and designed to transcend politics. project cycle stage: Design, Implementation, Operation, Country Partnership Strategy Financial crises may pressure a government to initiate policy reforms, and provide opportunities for development partners to introduce international best practices through policy-based loans. A key challenge in this context is to ensure that reforms introduced in response to emergency conditions are sustained in the post-crisis period. For the program, implementation of policy actions progressed as planned, and tranche 2 policy actions were achieved ahead of schedule, illustrating the broad political and institutional commitment to continued and sustainable reforms. project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-economic-management-program-pcr
Piloting the Design of e-Services Delivery Platform in Health Services: Technical Assistance Completion Report | Bhutan | Health, Information and communication technology | 2015-07-01 | Based on field study and survey, on a conservative estimate, this facility has helped at least two patients a day from making trips to the district referral hospital. Based on return, the savings, to patient of Tang BHU (basic health unit), of out-of-pocket expenditure annually, is about USD33,600. The intangible benefit includes (i) quality of data of patients, (ii) enhanced data analytics capabilities which will help in designing health policies specific to the locality, (iii) innovative solution for potential a scale up, (iv) patient's access to a qualified doctor through virtual means, and (v) opportunity costs associated with productivity of resources. This project piloted TV (television) white space as a last mile connectivity technology. The other forms of last mile connectivity such as leased lines, WiFi and Cellular can be evaluated separately and appropriate technology be selected depending on the context. While ICT (information and communications technology) based solutions for public service delivery enhances efficiency, it has to be implemented in an appropriate size to leverage economies of scale. This pilot has provided insights into the implementation challenges of such an intervention, and benefits of e-Health mode of service delivery in remote locations. It also provided insights to operational requirements related to purchase and installation of internet services, and configuration of IT (information technology) enabled equipment and cloud services. The operational requirements are related to allocation of spectrum for TV white space component, working out memorandum of understanding with stakeholders and remote management of maintenance of equipment. In one instance, the remote maintenance did not work effectively and a site visit was required as well as replacement of equipment. However, as mentioned before, generally sustainability of e-health solutions lies in large-scale implementation of such innovations within a national e-health framework as the scale allows optimization of resources, efficiency, cost reduction, and sustainability. Electronic records management, medico-legal, medico-ethical issues associated with such e-Health solutions, information security and data privacy associated with patient's data are issues that need to be addressed within broader national e-health governance policies. Also, sustained solution can be achieved by involving private sector partners. For example, India's primary health service delivery through e-health is implemented at some places by the private sector. However, before partnering with the private sector, it is important that a comprehensive e-health plan is in place and that health data is collected in a comprehensive national health information system and is not silo-ed. Further focused capacity building activities to the health professionals of the Government are required for sustaining efficient form of health service delivery. Project cycle stage: Concept, Design, Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/bhu-piloting-design-e-services-delivery-platform-in-health-services-tcr
Financial Sector Development Program | Bhutan | Finance | 2013-02-09 | Under the Financial Sector Development Program, the development and approval of key financial sector legislation was an important contribution to sector development. While the delays were inevitable, closer, longterm, in-country dialogue with the government would have been beneficial. This dialogue and close program monitoring will be enhanced by the establishment of a resident mission in Bhutan. ADB has been a long-standing partner of Bhutan's financial sector development since the beginning. A resident mission could better support monitoring of the ongoing financial sector reforms and provide timely assistance to address any systematic, institutional, and legislative deficiencies while continuously providing support for further strengthening the financial system. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/financial-sector-development-program-pcr
Micro, Small, and Medium-Sized Enterprise Sector Development Program | Bhutan | Industry and Trade | 2013-02-09 | 1. The tranche release criteria were clearly defined. They provided an impetus to achieve tangible objectives that motivated the involved agencies. project cycle stage: Lesson Topics: 2. The implementing agency should have been more involved in program design. The Ministry of Economic Affairs' Planning and Policy Division developed the program, but the Department of Cottage and Small Industry (DCSI) was responsible for implementation. The DCSI thought that some components could have been designed differently to improve their impact (e.g., the cost-sharing facility). project cycle stage: Lesson Topics: 3. The Bhutan: Micro, Small, and Medium-Sized Enterprise Sector Development Program included innovations that were new to Bhutan, so qualified local consultants were not available. Yet it was difficult to find foreign consultants who understood the Bhutanese context. The design and monitoring framework did identify ï¿½lack of qualified staffï¿½ as a risk. For future programs, however, ADB should further refine this risk to capture the tension between external expertise and local knowledge. project cycle stage: Lesson Topics: 4. ADB could have participated in the project steering committee. Without ADB's participation, the committee's decision making was constrained because its decisions were still subject to ADB's concurrence. project cycle stage: Lesson Topics: 5. Although delayed, the Micro, Small, and Medium-Sized Enterprise policy paper made effective use of consultations. Several white papers preceded it, and they solicited broad feedback that produced a strong final product. In addition, the paper included a tangible strategy and action plan that gives the Department of Cottage and Small Industry a clear work program. project cycle stage: Lesson Topics: 6. Instead of three tranches of $2 million, a better design might have been two tranches of $3 million. Regardless of the size, securing a tranche release has certain fixed administrative costs. If the tranches are small, these costs are proportionally higher and diminish the incentives to implement the preconditions for tranche release. project cycle stage: Lesson Topics: 7. The project had a much broader reach than merely providing credit to Micro, Small, and Medium-Sized Enterprises (MSMEs). It invested in their capacities and enabling environment (e.g., the cost-sharing facility, a coordinated government MSME policy, the collateral registry) so that banks could provide and MSMEs could employ credit more efficiently. This broader reach is especially important in frontier markets where these supporting elements are generally less developed. project cycle stage: Lesson Topics: 8. There was strong continuity between ADB's earlier support to establish a credit information bureau and this project's support for a central registry. There are natural synergies between the two initiatives that increase the effectiveness and sustainability of each. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/micro-small-and-medium-sized-enterprise-sector-development-program-pcr
Road Network Project | Bhutan | Transport | 2013-01-08 | 1. The project implementation was marked by substantial cost overruns. The detailed design put the cost for civil works about 35% higher than that estimated at appraisal. During implementation, the actual cost rose by about another 15%, including 6.7% for extra works and 8.2% for price escalation in construction materials. Such cost overrun caused three feeder roads packages to be removed from the project scope. In future, similar projects, this experience should be duly taken into account when estimating project costs as well as schedules. Additional costs and time were required due to unexpected amounts of rock needing to be excavated. This would have been difficult to detect in the design stage and could be found only during implementation. Therefore, it is recommended that sufficient contingencies be provided for similar projects. project cycle stage: Lesson Topics: 2. Implementation delays were mainly caused by slow and repeated procurements. Although, the project management office was retained from the previous ADB-funded project, most of its staff were newly recruited and not experienced with ADB Procurement Guidelines. For future projects, it is desirable to retain staff with ADB project implementation experience. Furthermore, adequate training on project management and implementation should be provided to relevant staff. In order to expose as many staff members as possible and provide repeated learning opportunities, on-site training by the consultants should be considered at an appropriate time during the implementation phase. Training design and resource should be appropriately incorporated and allocated during project design. The capacity of the executing agency to implement the road asset management system, including the data gathering, in particular, could have been better assessed at appraisal. project cycle stage: Lesson Topics: 3. The local competitive bidding adopted in the project provided an opportunity for domestic firms to learn international best practice under the supervision of an international consulting firm. Domestic contractors had weak capacity in management, technical staff, fund availability, and equipment, thus causing delays in project implementation. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/road-network-project-pcr
Bhutan: Basic Skills Development Project | Bhutan | Education | 2011-11-01 | 1. Sufficient knowledge of sector issues in developing member countries (DMC) during project formulation can help inform and uphold the relevance of project designs. Limitations on the design and formulation of the Basic Skills Development Project in Bhutan could have been avoided had there been a better understanding of the DMC's sector issues. Even when ADB was working with a development partner reputed to have sector expertise, it was still important for ADB to have sufficient understanding of the issues so that it can address the DMC's capacity problems. This is especially important during implementation when other development partners have departed from the scene. [Main text, para. 27] project cycle stage: Design, Implementation Lesson Topics: | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/bhutan-basic-skills-development-project
Asian Development Bank's Assistance for Rural Electrification in Bhutan - Does Electrification Improve the Quality of Rural Life? | Bhutan |  | 2010-08-31 | 1. A rigorous impact evaluation informs policymakers about attribution of outcomes and impacts more systematically. It helps to understand what works and what does not under a given condition. It is, however, not an exclusive decision-making criteria but the evaluation ratings can be used as an evidence to support resource allocation to relevant programs and activities. [Main text, para. 107] project cycle stage: Concept Completion Lesson Topics: 2. Country ownership is crucial for the project success. Rural electrification (RE) projects in Bhutan were successful as a result of (i) the government's social mandate to provide electricity for all by 2013, (ii) the government according top priority to RE coverage expansion, and (iii) the ability to coordinate with the five donors active in RE. The government's broad vision to harness hydroelectric power potential also played an important role in expanding RE throughout Bhutan. [Main text, paras. 21,102,108] project cycle stage: Implementation Lesson Topics: Capacity Development: Ownership Sector Related Issues: Rural development 3. Extra efforts are needed for boosting the demand for electricity and enable the shift from the use of fuelwood. Merely expanding the coverage of rural electrification (RE) is not sufficient. Although RE has expanded significantly since 1995, household electricity use has largely been limited to lighting, rice cooking, and water boiling. Although trends are emerging for other electric appliances, including televisions, the pace has been slow and largely concentrated in larger centers. Relatively assured access for fuelwood from forests at a nominal permit costs have been a disincentive for electrified households to migrate from fuelwood to electricity. People do not yet see electricity as a full substitute for traditional energy sources. As a result, an overwhelming majority of households still rely on fuelwood for cooking and heating purposes. [Main text, paras. 77,78,103,109] project cycle stage: Design, Implementation Lesson Topics: 4. The goverment's regulatory framework needs to be strengthened to ensure that energy efficient appliances and tools are used by households and businesses. Electric appliances are freely imported or brought into the country from various sources. There is no consumer information, guidelines, or regulations regarding safety and energy efficiency of such appliances. Most consumers end up purchasing less energy-efficient appliances because of lower initial costs. With adequate informed safety and efficiency measures, households can still enjoy greater benefits at a modest cost. There is substantial scope for mass awareness about safety and efficient use of electricity and associated appliances and tools, both by businesses as well as household consumers. [Main text, paras. 90,110] project cycle stage: Implementation, Operation Lesson Topics: Sector Related Issues: Energy planning/management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy reforms/framework 5. The use of electricity for income-generating activities has been very limited, but the potential to increase household income is quite high. Rural electrification (RE) is, of course, a necessary, but not sufficient, condition for expanding income opportunities. Unless substantive complementary investments in improving parallel infrastructure are made, such as access roads, market development, irrigation systems, skills development, and services, the demand for electricity is likely to remain below lifeline block in Bhutan in the foreseeable future for most of the households. project cycle stage: Design, Country Partnership Strategy Lesson Topics: Sector Related Issues: Energy planning/management Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework 6. Baseline data are crucial for properly evaluating impact of development intervention by any institution. Lack or loss of data is a major challenge in conducting impact evaluation studies and sustainability analyses of projects. Lack of a designated repository for collected data, loss of data during organizational restructuring, and no back-up for data collected by consultants, forced this study to opt for a quasi-experimental approach using a single-difference method. With proper advance planning and systematic recording, much richer databases could have been created and used for impact evaluation using a double-difference method. [Main text, paras. 5,22,114] project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/asian-development-banks-assistance-rural-electrification-bhutan-does-electrification
Country Assistance Program Evaluation for Bhutan (2010) | Bhutan |  | 2010-07-31 | 1. Long-term commitment, continuity, adequate resource levels, and a comprehensive and strategic approach to addressing binding sector constraints have been most effective in delivering satisfactory development results. ADB's strategic positioning in Bhutan ensured high consistency of country and sector strategies with the country's development needs and government priorities. Sector selectivity was evident in ADB's efforts to focus its operations strategically based on Bhutan's development needs and ADB's resource envelope, corporate priorities, and comparative advantage. ADB operations have also ensured logical sequencing and continuity of country assistance and coordination of strategies and interventions with other development partners. [Main text, paras. 29,33,35,83,103] project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Funding Capacity Development: Ownership Methodologies/Approaches: Holistic approach Methodologies/Approaches: Targeting 2. High level government ownership can result to better program outcomes. Government ownership was seen to increase given the consistency of ADB operations with evolving government development strategies thereby, contributing to good portfolio performance and positive on-the-ground results. [Main text, paras. 100,103] project cycle stage: Implementation Lesson Topics: 3. Country conditions need to be adequately reflected in project design. At the same time, it is important not to lose sight of established best practices. Evaluation noted that for a few projects, technical or policy solutions were not sufficiently cognizant of, or adapted to, country conditions. For instance, the design of ADB-financed road projects in Bhutan could have benefited from appropriate adjustments given the difficult and unusual terrain for road construction and maintenance. [Main text, paras. 37,41,103] project cycle stage: Design Lesson Topics: 4. A review of experiences from other sparsely populated countries or countries with similar topography might have benefited project selection and design for rural connectivity projects. While ADB has increased support for rural connectivity projects, the selection of interventions and project locations was not based on any in-depth analysis of relative poverty reduction effects, but rather responded to the government's desire to strengthen connectivity of and draw more rural areas into the mainstream of development. Working towards poverty reduction, rural connectivity projects need to be accompanied by programs in other sectors that help maximize their socioeconomic benefits. Such programs need not be financed by ADB, but require integrated planning and a certain level of coordination of implementation activities. [Main text, paras. 35,84,103] project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach 5. Policy dialogue needs to be based on adequate analysis, a good understanding of various policy options, and mutual agreement on the nature and underlying principles and objectives of individual policy actions to be effective. For instance, changes in foreign direct investment and foreign trade regimes as well as some of the commercial legislation under ADB policy dialogue did not address key sector problems and had little impact. While supported policy reforms had buy-in from the respective executing agencies, policy implications were often not well understood and/or underlying principles and objectives were not widely shared by all decision makers. [Main text, paras. 39,103, Appendix 7] project cycle stage: Implementation Lesson Topics: Policy & Reform: Reform Methodologies/Approaches: Policy dialogue 6. Capacity development should be addressed through sector-based institutional development strategies that take a comprehensive view of required policy and governance reforms to ensure that adequate incentives are in place for skills training and the application of new systems and processes. Although, some issues might not be sector-specific and must be addressed accordingly. For many ADB interventions, evaluation noted a narrow view of capacity development focused on short-term skills training, rather than on broader institutional capacity development. Even when assistance was provided for the design of institutional, legal, and policy reforms, it was usually not followed up with assistance for implementation. [Main text, paras. 100,102,103] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Methodologies/Approaches: Sectoral approach 7. Particularly in a low-capacity environment, the selection and supervision of project preparatory technical assistance (TA) consultants must ensure quality outputs. Evaluation noted a number of TA consultant reports to be lacking in quality. The management of TA consultants by ADB is an issue, as a number of government representatives feel that consultants are often paid regardless of whether expected services have been satisfactorily provided. [Main text, paras. 92,103] project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants 8. ADB can add considerable value through support for project design and implementation and the introduction of best practices for Project Management, procurement, and financial management. Based on the 2009 DER perception survey, government officials opined that ADB experience, support for project design and preparation, transparent procurement processes, and support for project implementation delivered the greatest benefits for their organizations. [Main text, paras. 97,103] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Procurement Project Management: Project management 9. There is a need to design practical resettlement frameworks/plan with feasible alternative arrangements in line with country conditions and the underlying principles of ADB safeguard requirements. Other underlying issues, such as poor title records and surveys that create uncertainty about land ownership, must also be addressed. While ADB safeguard policies were generally considered to be useful in minimizing social and environmental project impacts and permit projects to better safeguard environmental and social risks than government-funded projects, evaluation noted that many survey respondents felt that conflicts between national laws and ADB requirements were not always resolved in mutual consultation and understanding. For instance, the difficulty in achieving 100% concurrence for land pooling among hundreds of landowners has led to extensive delays and complaints from landowners. [Main text, paras. 56,87,103] project cycle stage: Design, Implementation Lesson Topics: | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-bhutan-2010
Basic Skills Development Project | Bhutan |  | 2010-03-18 | 1. To ensure proper sequencing and smooth coordination between components, the project implementation unit should have been responsible for the overall management of project components. The project provides for both software and hardware assistance as a comprehensive package. GTZ was financing the software side of the project and ADB provides for the hardware support. Since different departments in the Ministry of Labor and Human Resources managed the GTZ and ADB financed components, the sequencing of activities suffered. For example, equipment was selected ahead of the revision of curricula, and some equipment were inappropriate for the courses being offered. [Main text, paras. 33,42] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project management 2. A complete package of assistance should be provided to vocational training institutes (VTIs) to ensure the delivery of quality training. Taking into account existing resources, reducing the number of VTIs assisted could have been a better option vis-ï¿½-vis thinly spreading available resources to more VTIs. In some VTIs, for instance, a building was constructed or renovated but only minimal equipment was provided. Moreover, in some cases, only a limited number of VTI teachers were involved in listing the equipment to be procured under the project resulting in a mismatch between the procured equipment and training needs. These factors affected the delivery of quality training. [Main text, paras. 38,43] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project management 3. The project team should pay particular attention to selecting the top leadership of assisted institutions to the extent possible, and build in mechanisms to evaluate the performance of VTIs and award good performance to provide incentives. Given the same bureaucratic or external constraints, differences in performance of the VTIs can be attributed largely to differences in the quality of leadership. Furthermore, mechanisms (including incentives) can be established to evaluate and encourage good performance. [Main text, para. 44] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/basic-skills-development-project
Rural Electrification and Network Expansion | Bhutan | Energy | 2008-12-08 | 1. The provision of free house wiring kits under the project to some customers has been unsuccessful, in part due to concerns on targeting and consumer acceptance. Even with the village electrification kit, evaluation noted poor uptake among the poor and there remains potential consumers who are still without electricity. A project database would be helpful to relevant authorities as this would allow consumers who failed to connect to be readily identified and proactively supported. It would also be useful to examine alternative, more socially acceptable mechanisms for helping poor households install the internal house wiring needed before electricity can be supplied (e.g., provision of low interest loans that would be repaid in installments following energization). [Main text, paras. 23, 54] project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Management information system Project Management: Project management 2. The mission has noted significant variations in the assumptions made in various ADB reports regarding initial electricity consumption and consumption growth rates in newly electrified project areas. Individual consumption must be accurately measured for billing purposes, meaning actual consumption and growth rates in project areas could be directly measured though a project database linked to Bhutan Power Corporation's billing system. Given the strong link between electricity consumption and poverty alleviation, poverty impact assessments would benefit from greater reliance on data that can be accurately measured. Such data would also permit more accurate economic and financial analyses to be undertaken of both existing and proposed projects. Bhutan is unique in that almost all its electricity is generated from a renewable resource; encouraging the use of electricity as a substitute for traditional energy sources will have a positive environmental impact. Accurate data on electricity consumption in different project areas may assist relevant government agencies plan such initiatives. [Main text paras. 51-52, 55] project cycle stage: Design, Operation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Management information system Project Management: Project management Project Management: Project supervision | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/rural-electrification-and-network-expansion
Sustainable Rural Electrification | Bhutan |  | 2008-09-18 | 1. Projects that include the provision of photovoltaic lighting systems should be designed such that (i) appropriate beneficiaries are targeted, (ii) installation activities are recorded and monitored to ensure that the systems are correctly installed and operational at the end of the project, and (iii) processes are designed and implemented to ensure that the project is sustainable and that systems are properly maintained over time. The project completion report noted that with the availability of grid connections in some of the project areas, some of the solar systems installed have been relocated but their present location is not known. [Main text, paras. 22, 38, 55] project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Operation and maintenance 2. It is necessary to examine more socially acceptable mechanisms for helping poor households install internal house wiring before electricity can be supplied (e.g., provision of low-interest loans to be repaid in installments as part of a consumer's electricity account following energization). The provision of free house wiring kits under the project to some customers and not others has been unsuccessful due to two reasons: (i) the limited design capacity of these kits is seen as a barrier to possible future increases in a household's electricity consumption, and (ii) many beneficiaries do not like to be identified as poor and in need of charity. [Main text, paras. 24, 38, 54] project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Country Context: Cultural constraints | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/sustainable-rural-electrification
Urban Infrastructure Improvement Project | Bhutan |  | 2006-11-15 | 1. There is a need for more interministerial and intra-executing agency coordination to minimize delays in the scheduling of civil works (e.g., coordination between Ministry of Works and Human Settlement, Bhutan Power Corporation, and Bhutan Telecom in road diggings and cable relocation). In future projects, more effective use of the steering committee (or a coordination and decision-making body under it) would benefit project implementation. In this project, the steering committee met only twice. The design and supervision of civil works, especially for roads, was shifted from one division (or agency) to another, depending on workload at any given time. The Department of Roads (DoR) is responsible for maintaining roads once they are completed (and the responsibility shifts from the project management unit to the city corporation and then to DoR), yet it was not heavily involved in the design stage. [Main text, paras. 22, 24, 50(i)] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project supervision Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation 2. A critical assessment of the implementing agencies' (IAs) technical capabilities needs to be undertaken during project preparation both by the Government and by ADB. In this project, the absence of a detailed training needs assessment of the implementing agencies (IAs) has delayed implementation considering the IAs capacity constraints on detailed design of roads, bridges, and river training works. As such some staff were sent overseas to enhance their capacities on computer assisted transport infrastructure design. [Main text, paras. 26-28, 42, 50(ii)] project cycle stage: Design, Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Capacity assessment 3. Since city corporations have now become autonomous in revenue generation, there should be a structured system for budgeting enough operation and maintenance funds yearly, proportionate to the amount of the capital investment. The huge infrastructure investment needed demands a financial management plan for city corporations to generate enough revenues to sustain the maintenance of urban facilities and services. [Main text, para. 29, 44-45, 53(iii)] project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Project Management: Operation and maintenance Sector Related Issues: Urban sector/development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/urban-infrastructure-improvement-project
Health Care Reform Program | Bhutan |  | 2006-09-14 | 1. Success of the Bhutan Health Care Reform Program was due in part to strong ownership of program reforms by the government; stability of the tenure of key government stakeholders associated with program implementation; support for the reform program from major funding agencies; support for deepening of ongoing reforms (rather than entirely new reforms); and implementation of practical and achievable reforms. The overall impact of the reform program was noted to have been substantial with the achievement of equity in health service delivery, being on track to achieve all the health and poverty reduction-related MDGs, and ensured sustainable sources of financing, among others. [Main text, paras. 42, 44-58, 60(i)] project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Policy & Reform: Reform 2. A major challenge and barrier to the provision of emergency obstetric care in the South Asia region has been a severe shortage of anesthetists. Bhutan has addressed this issue to some extent by training and using nurse anesthetists. This is a significant option that other countries in this region may have to explore to address severe shortage of anesthetists. [Main text, paras. 32, 60(iii)] project cycle stage: Design, Feasibility Lesson Topics: Capacity Development: Capacity building Country Context: Emergency Sector Related Issues: Health and sanitation management 3. Sustainable financing of essential health services can be implemented through establishment of a trust fund. The Health Care Reform Program established the Bhutan Health Trust Fund (BHTF) with the objective of ensuring continued and timely supplies of vaccines and essential drugs. The BHTF has successfully mobilized $19 million which was used to finance vaccines and essential drugs in a sustainable manner. The establishment of BHTF (as well as the introduction of user charges) have led to some degree of sustainable financing for the health sector. [Main text, paras. 9, 60(iv)] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Sector Related Issues: Health and sanitation management Successful contracting of services to the private sector requires: (a) development of the capacity of the government agency for contracting services to the private sector; (b) establishment of good selection criteria for contracting private companies; and (c) assessment of the capacity of the private sector to provide efficient and quality services. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Procurement Capacity Development: Capacity assessment Capacity Development: Capacity development Sector Related Issues: Private sector Unlike most external social sector support programs, where committed liabilities are created through expansion of services due to significant inputs into capital expenditures, the program was designed to support consolidation and sustainability of health financing. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/health-care-reform-program
Country Assistance Program Evaluation for Bhutan (2005) | Bhutan |  | 2005-05-31 | Considerable scope remains for improving the participation of both government agencies and the private sector in designing and implementing projects, with a view to strengthening project ownership. project cycle stage: Design, Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Capacity Development: Partnerships Sector Related Issues: Private sector Methodologies/Approaches: Consultation/Participation Future Country Strategy Programs should take into account that adequate staffing with the correct skills mix is just as important as the establishment of project implementation units. project cycle stage: Country Partnership Strategy Lesson Topics: Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Human resources management Future Country Strategy Programs should take into account that frequent turnover of project managers adversely affects project implementation. project cycle stage: Country Partnership Strategy Lesson Topics: Future Country Strategy Programs should take into account that recommendations include the need to (i) enhance capacity of project implementation staff, especially with respect to ADB procedures and policies; (ii) enhance technical capacity of executing agency staff regarding sector knowledge, especially in the financial and energy sectors; (iii) better assessment of existing policy framework with implications for phasing and sequencing of sector reforms; (iv) adaptation to local conditions (road maintenance and management system); (v) improve coordination for cofinancing operations; (vi) ensure adequate financial resources for operations and maintenance, especially in the roads sector; (vii) address institutional weaknesses and build capacity thru long-term technical assistance commitment; and (viii) actively engage high-level government officials to ensure ownership and government commitment. project cycle stage: Country Partnership Strategy Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Institutional analysis Capacity Development: Ownership Policy & Reform: Policy reforms/framework Implementation of technical assistance, particularly in the financial and energy sectors, had been adversely affected by the lack of adequate counterpart support provided by the executing agencies (EAs) because of the lack of government ownership for the projects. Better coordination between ADB and EAs is needed to improve counterpart support. project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Ownership In a results-oriented Country Strategy Program, development effectiveness is improved if projects are designed and implemented in the context of the overall portfolio and other complementary interventions. The objective is to develop a strategy which has an impact that is greater than the sum of the parts. project cycle stage: Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Project Design: Project design Methodologies/Approaches: Holistic approach More government involvement during the process of recruiting consultants would ensure ownership as well as desirable outputs. ADB could seek informal involvement of the executing agency (EA) before short listing and during the evaluation of consultant proposals. project cycle stage: Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Public governance Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Ownership More time and resources need to be allocated to project preparation to identify possible bottlenecks and possible remedial measures. Public sector officials complained about the lack of sufficient project preparatory time and resources, and the fact that consultants are prone to rush the project preparation to meet ADB deadlines, rather than focusing on details and issues that would have saved time and reduced costs during project implementation. Adequate funding for project preparation is also needed. These are direct costs associated with poorly designed projects. ADB should focus on project quality and development effectiveness during project processing, rather than the date of Board approval of the loan. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Appraisal Project Design: Problem identification Project Design: Project design Project Management: Consultants On the institutional side of ADB's programs, ADB assistance has tended to underestimate the time needed for institutional capacity building. A longer-term view of capacity-building needs and implementation processes is required. Standalone capacity-building advisory technical assistances can be weakened when they target technical skills improvements at the individual level rather than broader institutional capacity building through improved management, operational, functioning, and budgeting systems. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Institutional analysis Methodologies/Approaches: Holistic approach Since ADB does not have a physical presence in the country, missions to monitor and review projects are essential to prevent implementation delays, poor contract award performance, and low disbursement performance. While this situation is similar in other countries, review missions are especially important in Bhutan because of the terrain and poor communications facilities, and because executing agencies (EAs) may be institutionally weak, have few qualified project staff, and be familiar with ADB policies. ADB needs to continue supervising and monitoring projects more closely than in other countries. The assessment of project performance under a project performance rating should be a joint effort between ADB and the EAs. project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Project Management: Project supervision | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-bhutan-2005
Rural Electrification Project (Loan 1375-BHU[SF]) | Bhutan | Energy | 2003-12-31 | Bhutan Power Corporation (BPC) technical personnel should be closely involved in all aspects of the design of rural circuits and the specified equipment. BPC personnel are aware of many lessons learned during the implementation of previous projects and must be able to impart these to any international consultants in future. Since availability of private domestic technical consultants are limited, this may require substantial participation of BPC personnel in the preparation of feasibility studies to ensure that (i) aspects unique to Bhutan (e.g., terrain, weather) are considered; and (ii) technology is effectively transferred. With the appropriate transfer of technology and design methods, BPC personnel should be enabled to perform rural electrification (RE) system design in-house in the future. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Consultants Capacity Development: Technology/Technology transfer Methodologies/Approaches: Consultation/Participation For first ADB loan in a sector, more attention should be paid by both ADB and the executing agency regarding the consultant s understanding of the country specific context. In cases where the consultants do not have sufficient experience in similar terrain, adequate time needs to be given during the feasibility stage for them to become familiar. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies System expansion of the rural electrification (RE) system should be pursued only after a detailed system analysis by computerized load flow techniques is performed and all existing system electrical parameters are determined and entered into a computerized database. project cycle stage: Feasibility Lesson Topics: Project Management: Management information system Sector Related Issues: Energy planning/management Sector Related Issues: Rural development Various precautions can be introduced to improve procurement of supplies and shipping to a landlocked country like Bhutan, which is not familiar to many suppliers. Future procurement packages have to be designed for maximum manufacturer participation from all member countries. Equipment warranties of a minimum of 12 months following receipt at the project site should be required for all major equipment items. Prices for and guaranteed availability of spare parts for a reasonable number of years following delivery should be required for this equipment. To minimize the impact of shipping delays after the supplier has submitted the letters of credit, bank guarantees from suppliers should be required. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/rural-electrification-project-loan-1375-bhu-sf
Financial Sector Intermediation Facility | Bhutan | Finance | 2003-12-15 | All of the policy actions except one were implemented on time - mainly due to the government's strong commitment and ownership, in particular from the Ministry of Finance (MOF) and the Royal Monetary Authority (RMA) - but implementation experiences underscores the need for strong government commitment to enact required laws and policies. To facilitate this process, policy dialogue on structural reforms needs to be extended from the government to the financial and private sectors, as well as concerned government agencies including the National Assembly and the Council of Ministers. Strongownership was also a result of ADB's extensive, in-depth discussions with government officials on project design. There is still a need for broader consultative process and greater accessibility of policy issues so that implementation is hastened and potential resistance is minimized. Simplification ofcomplex reform jargon is desirable so that the discussion is well understood. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Private sector Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation Program implementation revealed the deeply entrenched problem of lack of transparency in business practices and lack of a governance structure in the financial sector. While the executing agency has undergone some important initial changes, there remains a question of its independence. Maintaining governance among market participants should remain a top priority in program lending. ADB TA 3905 has recommended a framework for corporate governancefor financial institutions based on generally accepted best practices. As the financial sector develops and economic integration accelerates - raising both the volume and scope of financial transactions - there is a greater need to establish clear procedures for solving problems. Speedy bankruptcy procedures and recourse for financial institutions in recovering loans should help the cost of borrowing to fall. Over the last few years, a number of regulatory acts have been passed to address these issues. These acts should be implemented quickly. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Modality: Program Modality: Technical Assistance Project Management: Executing/Implementing agencies Country Context: Prioritization | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/financial-sector-intermediation-facility
Institutional Strengthening and Policy Support to the Power Sector in Bhutan | Bhutan | Energy | 2003-10-31 | Accounting software requires customization to meet an organization's specific requirements. Accounting knowledge and skilled information technology support are required on an ongoing basis as many problems are not apparent immediately after system installation. project cycle stage: Implementation, Completion Operation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Management information system Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Before installing new accounting software, the governments should agree that the new accounting system, when operational, can replace the one currently in use. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Technology/Technology transfer Given the limited time available in the technical assistance (TA), solutions developed elsewhere were used to meet the government's perceived requirements. Time allowed for counterpart feedback was also inadequate, and the government had little sense of ownership for much of the work. In the end, much of the scope of the terms of reference (TOR), such as the development of a hydropower policy and preparation of technical standards, will be redone under future ADB-funded TAs. In the design of future TAs, ADB will need to be sensitive to such issues as the 'pressure cooker' approach and be realistic in designing the TOR with respect to the time and resources available. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Government departments usually focus on cost. Prior to corporatization, they need assistance with the implementation of systems that focus on revenue collection, rather than a new computerized accrual accounting system. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial management Project Management: Management information system Capacity Development: Capacity building Policy & Reform: Reform More attention should be paid to local characteristics and conditions at technical assistance (TA) formulation and during implementation. Further, the results indicate the importance of counterpart involvement at the senior management level during TA formulation and implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Country Context: Cultural constraints | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/institutional-strengthening-and-policy-support-power-sector-bhutan
Technical and Vocational Education and Training | Bhutan | Education | 2002-01-15 | Capacity building of key implementation staff should be provided prior to the commencement of a project or during its early phase to avoid unnecessary implementation delays. This would have been useful particularly in the areas of ADB's disbursement and procurement procedures. Therefore, human resources development needs assessment should be given more attention during the design stage of a project. Likewise, project design at appraisal need to outline performance indicators, which wouldhelp assess the qualitative aspect of project inputs. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Monitoring & Evaluation: Indicators Project Design: Appraisal Project Design: Project design Project Management: Procurement Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Human resources management Where cofinancing is involved, preparatory activities for cofinancing should beundertaken and finalized as early as possible to avoid any implementation delays, as experienced in this project. project cycle stage: Appraisal Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/technical-and-vocational-education-and-training
Highland Livestock Development Project (Loan 808-BHU[SF]) | Bhutan | Agriculture, Natural Resources, and Rural Development | 1998-12-31 | Careful attention to benefit monitoring and evaluation (that is, a project performance management system) is essential for the proper evaluation of project performance and impact. Sustained technical support from external and local resources is needed to ensure that the project performance management system is institutionalized in the EA. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Project evaluation Project Management: Executing/Implementing agencies Capacity Development: Technology/Technology transfer Consideration of cultural and other special circumstances is a major factor in the design of appropriate components. Livestock projects should be realistic in assessing the prospects for culling of animals where religious sensitivities mitigate against it and in considering the incentive structure for pasture development where there is competing land use. Integrated components in a project s design serve to reinforce one another and contribute to a greater chance for project success as a whole even when there are shortcomings in individual components. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Country Context: Cultural constraints Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach For government entities to be successfully privatized requires appropriate monitoring, provision of a proper policy environment, and a regulatory framework that ensures that the privatized entities are sustainable and will contribute to the development of a more competitive market. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Monitoring and evaluation Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Greater impact can be derived from extension activities if they are focused on meeting the special needs of farmers rather than on fulfilling a set curriculum. The delivery of technical packages requires a closely supported, supervised, and accountable extension delivery mechanism. The mechanism should provide for follow-up of field activities by senior staff and the strategic support of subject matter specialists. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project supervision Sector Related Issues: Extension service Projects are likely to have a better chance of success when there is strong commitment and enthusiasm from the EA and where staff transfer is kept to the minimum. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Ownership Tender and procurement procedures should take into consideration the peculiar circumstances of a country and should be managed to ensure the delivery of high quality goods in a timely manner. The award of tenders to the lowest evaluated bid (that is, based on past performance and other considerations besides price) rather than the lowest priced bid, together with the proper specifications for quality, will prevent delays in project implementation due to supply of inferior and ineffective equipment and materials. However, award of tender on lowest evaluated bid may not be possible at all times especially in countries that accept the lowest priced bid to avoid any impression of malpractice. project cycle stage: Implementation Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/highland-livestock-development-project-loan-808-bhusf
Institutional Strengthening of the National Budget and Aid Coordination Division of the Ministry of Finance in Bhutan | Bhutan | Public Sector Management | 1998-12-31 | The lack of institutional analysis and performance criteria impeded the design and effectiveness of the technical assistance (TA). To address the complexity of public expenditure management, ADB would have been well advised to analyze rigorously existing capacities for public expenditure management and apply a phased approach that provides assistance over the medium to long term. This would have provided ADB with a better understanding of capacity building requirements, and established a framework for assistance. A phased plan would have ensured sufficient flexibility because at the end of each TA, progress could have been reviewed and follow-up TA revised, if necessary. Such an approach could have corresponded to developing the computerized system in a modular way, and could have extended assistance to other areas than computerization. It would have increased the significance of the series of ADB TAs by providing a framework for assisting the EA and other government agencies, and to guide and coordinate interventions of other external funding sources. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity assessment Capacity Development: Institutional analysis Capacity Development: Ownership | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/institutional-strengthening-national-budget-and-aid-coordination-division-ministry-finance
Preparation of Energy Efficiency Policies and Guidelines for Bhutan and Nepal: Technical Assistance Completion Report | Bhutan, Nepal | Energy | 2015-09-01 | Countries like Bhutan and Nepal can learn from others considering that countries like India and Sri Lanka are advanced in their energy efficiency and conservation policies and have been successfully implementing them. They have dedicated institutions for the promotion of energy efficiency and conservation that have successful energy efficiency and conservation programs under implementation for some time. Considering that energy efficiency and conservation cut across many sectors, it is important that a nodal agency responsible for the subject is established to coordinate the related activities in the country. In this regard lessons from the India and Sri Lanka experience will be useful. Bureau of Energy Efficiency in India and Sustainable Energy Authority of Sri Lanka have been in operation for more than 10 years and have successfully executed many energy efficiency programs such as energy labeling programs for compact fluorescent lamps and refrigerators among others. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/energy-efficiency-policies-and-guidelines-for-bhu-and-nep-tcr
Second Power Transmission and Distribution Project: Project Completion Report | Cambodia | Energy | 2016-04-01 | There were implementation delays during the initial period of the project, especially in achieving loan effectiveness, recruiting implementation consultants, and awarding contracts. These delays occurred even though advance procurement action had been approved. To minimize delays in achieving loan effectiveness, it is recommended that the practicalities of achieving all proposed loan effectiveness conditions are reviewed and discussed with the borrower and the executing agency during appraisal. To address start-up issues, ADB should assist the executing agency with the implementation of project start-up tasks such as consultant recruitment and the preparation of comprehensive feasibility studies and detailed engineering designs. The delegation of project administration responsibilities to the resident mission during the project helped facilitate close working relationships between ADB staff and key government and EDC officials. The experience EDC gained from this project and the relationships that have developed between the resident mission and government counterparts should greatly benefit any future project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/cam-second-power-transmission-and-distribution-project-pcr
Strengthening Development Partner Coordination in Cambodia: Technical Assistance Completion Report | Cambodia | Public sector management | 2015-10-01 | Supporting the development of government national and development coordination strategy and aligning ADB country strategy with national strategy has been essential for effective ADB country operations, which requires additional resources, besides existing ADB staff capacity. The S-CDTA (small-scale capacity development technical assistance) has been instrumental for CARM (Cambodia Resident Mission) in this respect, despite the fact that Output 5 was not achieved. One related lesson emerging from implementation of the S-CDTA, which equally applies other ADB TAs (technical assistance), is that project scope and complexity should be carefully calibrated to available resources. Project cycle stage: Design, Feasibility, Implementation, Country Partnership Strategy | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-development-partner-coordination-cambodia-tcr
Support for Public-Private Partnerships in Cambodia: Technical Assistance Completion Report | Cambodia | Public sector management | 2015-08-01 | The S-PATA (small-scale policy and advisory technical assistance) has been part of a phased ADB program of assistance for PPPs (public-private partnerships) to the government. Upon establishment of enabling conditions, additional ADB assistance for capacity building, and to finance a PDF (project development facility) and prepare a series of pathfinder projects has been scheduled. Significant delays in approval of the Policy Paper, however, have derailed the sequence of PPP interventions, with TA 8773-CAM Capacity Development for Public Private Partnerships, which aims to build the institutional capacity of government's agencies involved in PPPs, approved in November 2014. Approval of the Policy Paper and establishing the enabling conditions for PPPs ahead of implementation of the capacity building activities under TA 8773 would have been desirable to enhance the effectiveness of related capacity building activities. The sequence of PPP projects should therefore have been more carefully planned, taking into account government capacity constraints to proceed with the PPP reform agenda. The timeframe and expected results of the S-PATA in a highly complex policy area, including recruitment of expertise, should have been estimated more realistically in line with government capacity and availability of expertise at prevailing ADB consultancy rates. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-public-private-partnerships-cambodia-tcr
Strengthening Knowledge Solutions for the Cambodia-ADB Partnership: Technical Assistance Completion Report | Cambodia | Public sector management | 2015-07-01 | Supporting the development of government strategy and aligning ADB country strategy with national strategy is essential for effective ADB country operations. Providing and disseminating sustained knowledge products and services (KPS) to government requires additional resources, besides existing ADB staff capacity. The S-PATA (small-scale policy and advisory technical assistance) has been instrumental for CARM (Cambodia Resident Missions) in this respect, despite the fact that output 4 was not achieved. One related lesson that emerges from implementation of the S-PATA is that project scope and complexity should be carefully calibrated to available resources. Project cycle stage: Feasibility, Implementation, Country Partnership Strategy | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-knowledge-solutions-for-cam-adb-partnership-tcr
Road Asset Management Project: Completion Report | Cambodia | Transport | 2015-06-30 | Capacity building (planning). Road Data Collection and Management Unit staff are still unable to complete a road maintenance planning report with solid budget recommendations, which needs to be improved. project cycle stage: Implementation Capacity building (implementation). The overall institutional setup for asset management, construction supervision and quality assurance and/or quality control, still needs improvement to be practically usable. In addition, the project completion review mission agreed with MPWT's (Ministry of Public Works and Transport) recommendation for further training of RAMO (Road Asset Management Office) staff as necessary in International Federation of Consulting Engineers-based contracts; the English language; technical reporting; procurement activities; road safety; and social and safeguards aspects, including gender. project cycle stage: Implementation, Completion, Operation Road safety audits. Similarly, the project completion review mission found the need for road safety audits to be undertaken as part of the pavement design process, with additional work to solve problems with ineffective lane markings. project cycle stage: Design, Completion Road maintenance funding. Sustainable funding was not an objective of the project. Also, sustainable road asset management was not given a sufficient focus by the government, with adequate annual budget allocation for road maintenance. These issues need to be explored in the proposed future project to achieve sustainability of the MPWT (Ministry of Public Works and Transport) road maintenance regime. project cycle stage: Operation Project coordination and project readiness. Where multiple cofinanciers are involved in interventions, careful selection (and attention to transparency in collaboration) of co-financiers during project design is required, to enable close and effective coordination during implementation; this is especially the case for parallel cofinanciers. The project design should focus on project readiness, including climate resilient design of pavements (flooding has become more frequent than it was during project design). project cycle stage: Design, Feasibility, Implementation Privatizing force accounts. The failure to privatize force accounts remains an issue to be resolved during the proposed future project. MPWT (Ministry of Public Works and Transport) reported that the privatizing activities are now ongoing, although there has been no successful bidding process to date project cycle stage: Operation Priority operating cost. POC was a confusing process for MPWT (Ministry of Public Works and Transport) staff, which was implemented with delays, and it is recommended that a similar approach not be used for future intervention. project cycle stage: Implementation, Operation HIV prevention program. Although HIV prevention program was implemented as designed, the budget allocated by IDA (International Development Agency) at project design was insufficient. Better project design with more detailed focus on an HIV prevention program is needed for future interventions project cycle stage: Design, Implementation Independent procurement agent. This modality was not successful, and is not a good example to follow in future interventions, as shown by the issues that MPWT (Ministry of Public Works and Transport) faced with the IDA (International Development Agency)- funded IPA (independent procurement agent). project cycle stage: Implementation Project management. RAMO (Road Asset Management Office) staff were not located in a single area, but scattered across their respective offices. This meant the project director could not supervise them in the course of day-to-day activities project cycle stage: Implementation Robustness of cost estimates. Some cost categories were fully used and others insufficient (such as for the HIV prevention program), and more careful cost estimates are needed. project cycle stage: Design, Feasibility Link between cost estimate and financing arrangements. There should be a stronger linkage between cost estimates and financing arrangements to achieve the project scope as designed . However, this may have been possible only given sufficient ADB financing, ideally close to that provided by IDA (International Development Agency). project cycle stage: Design, Feasibility | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/road-asset-management-project-pcr
Northwest Irrigation Sector Project | Cambodia | Agriculture, natural resources and rural development | 2014-06-01 | It is easy to overestimate the capacity needed to implement a project that is largely undertaking pilot activities and which also involves significant reforms. At all levels of involvement - executing agency, service providers, contractors, farmers' water user community members - capacity constraints affected project performance. In these circumstances, the project design was both overambitious (e.g., by not focusing on fewer subprojects from the outset) and not rigorous enough (in its analysis of the risks and assumptions inherent in many operations). While appropriate and necessary interventions to support capacity development and training were included in the project scope, the dependence of farmers' water user community gaining experience with improved physical works and for farmers undertaking improved and diversified agriculture upon the completion of civil works was not brought out fully as a project design characteristic - again, partly because the risks and assumptions were not fully thought through. Had the project implementation schedule been largely as intended, sustainability based on effective farmers' water user community functioning would have been likely. A realistic understanding of local procurement practices and an ability to engage with executing agency staff on a daily, face-to-face basis can greatly facilitate implementation. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/northwest-irrigation-sector-project-pcr
Cambodia: Education Sector Development Program | Cambodia | Education, Multisector | 2012-12-27 | 1. The overall design of a sector development program should be well considered to ensure that outputs will lead to the intended outcomes, and that the design is based on a realistic assessment of the government's capacity to meaningfully implement the entire reform agenda. [Main text, para. 30(a)] <!-- project cycle stage: Design Lesson Topics: Project Design: Project design Methodologies/Approaches: Sectoral approach --> 2. The adequate coordination, supported by an appropriate mix of program loan, project loan, and advisory technical assistance from ADB, is needed for the effective implementation of sector-wide approaches. [Main text, para. 30(b)] <!-- project cycle stage: Implementation Lesson Topics: Modality: Program Modality: Project Modality: Technical Assistance Methodologies/Approaches: Sectoral approach --> 3. Effective program loan implementation requires political stability, strong ownership and commitment on the part of the government to implement reforms in education. [Main text, para. 30(c)] <!-- project cycle stage: Implementation Lesson Topics: Capacity Development: Ownership Policy &amp; Reform: Reform Methodologies/Approaches: Program Approach --> | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/cambodia-education-sector-development-program
Cambodia: Commune Council Development Project | Cambodia | Public Sector Management | 2012-12-10 | 1. This validation adds the finding of mission reports that hospitals, Buddhist monks, employers, teachers, as well as community-based volunteerism could be tapped to influence more people to register. [Main text, para. 24] project cycle stage: Implementation Lesson Topics: Country Context: Decentralization Methodologies/Approaches: Community approach Methodologies/Approaches: Participatory approach 2. Lesson relates the importance of securing sustained government resource support for the mobile civil registration activities (to finance supplies, transport, food, and water for registration teams) more so than project-financed allowances and incentives that affect the motivations of recipients after project completion and possibly even the enthusiasm of nonrecipients. [Main text, para. 24] project cycle stage: Implementation, Operation Lesson Topics: Finance & Financial Aspects: Funding Country Context: Decentralization | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/cambodia-commune-council-development-project
Greater Mekong Subregion Transmission Project | Cambodia | Energy | 2012-11-01 | There were implementation delays in the initial period, especially in achieving loan effectiveness, recruiting implementation consultants, and awarding civil works contracts. These delays occurred even though advance procurement action had been approved. The formation of a new government following loan approval was a major factor in this respect, as was the time taken for a new executing agency to climb the learning curve on use of ADB procurement procedures. To facilitate project start-up, it is recommended that ADB should extend the services of the procurement consultant financed under the project preparatory technical assistance project until loan consultants are fielded. The devolution of project administration responsibilities to the resident mission during the project helped facilitate close working relationships between ADB staff and key officials. The experience Electricite? du Cambodge (EDC) gained in this project and the relationships that have developed between the resident mission and counterparts should greatly benefit any future project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/greater-mekong-subregion-transmission-project-pcr
Second Education Sector Development Program | Cambodia | Education | 2012-01-06 | 1. Policy reforms require monitoring beyond disbursement of the final tranche and closure of the program loan. A number of the Education Sector Development Program II policy initiatives may have lapsed since implementation, but without proper independent monitoring these are difficult to track. [Main text, para. 56] 2. Strong construction supervision and monitoring systems are vital in education projects that emphasize civil works. The quality of school construction and furnishings was a continual concern during project implementation, stemming from inadequate monitoring and enforcement of quality standards. Lower secondary school construction relied on a community participation modality manual prepared by Ministry of Education, Youth and Sport, but there was no orientation or training for community members that enabled them to monitor the construction process. There was a lack of continuous quality assurance from the executing agency site engineers during construction (they were responsible for a large number of sites), which in turn led to weaknesses in documentation. Compounding these issues was the lack of continual input by a team leader in overseeing these construction quality issues. This lesson will be particularly relevant for the proposed Third Education Sector Development Program. [Main text, para. 57] 3. Supervision of procurement could have been stronger. ADB's project procurement-related review cited potential conflicts of interest, inappropriate prequalification, misleading and incomplete contract documentation, payments not accompanied by adequate documentation, lack of proper evidence and onsite inspection reports accompanying progress payment claims, and poor retention of contract documentation by the school support committees and school construction committees. [Main text, para. 58] 4. Providing for continuous consulting team leadership, by an international team leader along with a national deputy team leader, is advisable for efficient project management. The lack of continuous leadership under Education Sector Development Program II to some extent hindered the effective implementation of some project activities. [Main text, para. 59] 5. Extending project closing dates can result in stronger outcomes. The final review mission agreed to the use of bank guarantees so Ministry of Education, Youth and Sport (MOEYS) could issue contractor checks for work extending beyond loan closing, including payments for amounts withheld during the defects liability period. With some activities occurring after project completion, there was a lack of adequate oversight by MOEYS, resulting in quality issues in building construction and finishing. The delays also contributed to poor management of some SRCs because of inadequate training of staff. It would have been more prudent to allow for a project extension for the adequate completion of these activities. [Main text, para. 60] 6. The inclusion of a gender and ethnic minority action plan (GEMAP) in the project design does not guarantee its implementation, even when GEMAP monitoring is included in consultant terms of reference. Without reporting systems and designated focal persons the GEMAP does not get fully implemented. Good practice would have been to report in detail against GEMAP targets with gender-disaggregated data in all projects reports, including quarterly and annual progress reports, with any follow-up issues flagged for the next mission. The ADB resident mission gender specialist should develop a GEMAP orientation program at the start of implementation for all project consultants and executing agency staff. [Main text, para. 61] | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-education-sector-development-program-pcr
Tonle Sap Sustainable Livelihoods | Cambodia | Agriculture, Natural Resources, and Rural Development | 2012-01-06 | 1. Project experience demonstrates that it is possible to improve natural resource-based livelihoods in a decentralization context, but that doing so is institutionally complex. More in-depth institutional analysis at all levels (e.g., regarding ownership by executing and implementing agencies, the commitment to basin-wide planning, the role of coordinating institutions, and the capacity development needs of communal service providers) could have overcome some of the problems encountered during implementation, and this is an essential design requirement for any future development interventions of this kind in the Tonle Sap. Use of the sustainable livelihoods approach may be insightful, but alone does not guarantee design rigor. [Main text, para. 58] project cycle stage: Lesson Topics: 2. Although the project appears relatively efficient against its own delivery expectations, the extent to which such institutional complexity potentially adds to overall investment delivery costs remains unknown in the absence of reliable quantified benefits data from the project itself that would allow a comparison of different approaches. In institutionally complex projects such as this, implementation and eventual output delivery are especially likely to be affected (both positively and negatively) by circumstances not always foreseeable at design. Allowing for flexibility in implementation within such project designs is likely to be essential for later performance success. [Main text, para. 59] project cycle stage: Lesson Topics: 3. The project's design: (i) did not anticipate the scale and nature of change in implementation arrangements that would arise from choosing the Ministry of Interior as the executing agency; (ii) underestimated coordination difficulties between government agencies - notably between the executing agency and Council for Agricultural and Rural Development (in its role as chair of the project steering committee) and between the Tonle Sap Biosphere Reserve Secretariat, Fisheries Administration, and Ministry of Environment for output 2; and (iii) overestimated the appetite for change in fisheries management. Lack of advance action to recruit implementing consultants severely reduced the effective implementation period. [Main text, para. 60] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/tonle-sap-sustainable-livelihoods-0
Agriculture Sector Development Program | Cambodia | Agriculture, natural resources and rural development | 2011-12-01 | Program Related Technical assistance (TA) inputs. The implied assumption of the TA work plan (with its heavy emphasis on early TA inputs) was that the policy and institutional reforms would be achieved quite early on and that the remainder of the time would involve just monitoring and evaluation of implementation. Policy reforms take time, and continued monitoring and effort are required from the TA, the counterparts, the government, and ADB throughout the program in order to effect policy and institutional change. Local ownership of process. It was not until the establishment of working groups for each of the tranche conditions in late 2005, under the initiative of the program support unit (PSU), that ownership of the process became more localized. There were delays in the development of work plans and budgets, and the consequent disbursement of funds to the working groups caused a delay in meeting tranche conditions. However, resolving difficulties and obstacles was made easier by empowering the working groups to come up with their own ideas and solutions through internal processes. Commitment to change. This is an important issue and lesson learned from the program loan activities. Although there clearly was a commitment to change in relation to most tranche conditions, there was back-tracking on the initial commitment to divest state-owned enterprises. However, after considerable reflection and reconsideration of options over the program period, all state-owned enterprises were successfully divested, and the benefits of thisï¿½significantly better operations and financial performance of the ongoing enterprises, and cost savings for those wound upï¿½are increasingly appreciated. Resettlement plans. At appraisal, the social and cost implications of the resettlement plans required in connection with the divestment of the state-owned rubber estates (SOREs) were not fully anticipated. This was a key reason for the 2-year delay in the release of the second tranche of the program loan. The scope and cost of resettlement plans needs to be clearly recognized at the time of project design, since they are time-consuming to prepare and costly to implement. Project Related Funding constraints. The uptake of some project activities was constrained by the lack of funds (or credit) for necessary capital expenditure items (e.g., costs of establishing greenhouses, chicken-raising facilities). This was accentuated by the project's deliberate policy of seeking to involve a substantial proportion of the rural poor, who lacked cash or access to credit. Future projects should include adequate funds for such purposes or seek involvement of a nongovernment organization with funding available for such items. Value of diffusion and informal extension services. Budgetary constraints mean that once the project ends, follow-up provision of provincial and district extension services from Ministry of Agriculture, Forestry, and Fisheries (MAFF) staff is limited. This highlights the importance of developing the informal farmer-to-farmer and input-supplier-to-farmer extension services. In particular, the village extension worker (VEW) program introduced late in the project's life has trained a number of farmers who will continue to disseminate their knowledge to neighboring farmers. Some farmers have become involved in the production of inputs to new technologies (e.g. fingerlings, chicks, and vaccinations) and are therefore motivated to encourage other farmers to also become active participants in the new technologies. Profitability of new farming technologies. New activities such as vegetable growing, mushroom growing, pig fattening, chicken raising, and fish farming are more profitable than traditional paddy production and have had high adoption rates. However, for most of the targeted farmer households these new activities will be supplementary to paddy cultivation rather than a substitute for it. This is because most smallholders' paddy production is for own consumption rather than for sale. For household food security reasons, paddy will continue to be grown given the perceived risks associated with nontraditional agricultural activities. Decentralized training. The project targeted a large number of districts (18) in four different provinces. The geographical spread meant that a decentralized training model was essential. Project staff deployed in the provinces and districts needed to be skilled to a level commensurate with the requirements of the projectï¿½i.e., agricultural commercialization and diversification. MAFF provided this training and skills development centrally but enabled provincial and district extension staff to provide training and back-up support to the farmer households. Farmer-based agroenterprises. The project found very few agroenterprises in the target districts. Toward the end of the project, the focus switched to providing agribusiness skills to the higher-performing farmer households that had already been trained in the new technologies. A number of examples emerged where these farmer households moved along the production chain and got involved in the production and/or sale of farm inputs to other farmersï¿½e.g., chicks for chicken farming, fingerlings for fish farming, chicken feed, vaccines. A positive side-effect of this process was the commercial incentive for these farm input suppliers to conduct extension services free, or for a small fee, to promote the sale of their farm input supplies. These were generally non- poor farmers with sufficient resources of their own to develop these activities. However, the project also benefited poor farmers to a significant extent. Monitoring and evaluation. Monitoring and evaluation is an important part of any project and the Agriculture Sector Development Program and Project (ASDP) was fortunate to have monitoring and evaluation officers in the PCU and in the provinces and districts. The adoption, diffusion, and cost/production surveys were an important part of the monitoring and evaluation system and helped provide information on the value of the project. This aspect of the project was particularly well implemented. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/agriculture-sector-development-program
Tonle Sap Rural Water Supply and Sanitation Sector Project | Cambodia | Agriculture, natural resources and rural development | 2011-12-01 | The Second Rural Water Supply and Sanitation Sector Project (RWSSP2) is being implemented in a much more focused geographic area, and in a more holistic manner, covering all villages in each selected commune and aiming at 100% water supply coverage and 75% sanitation coverage in order to achieve the intended collective health benefits; To maximize cost effectiveness, the first emphasis of RWSSP2 is the rehabilitation of wells in disrepair; RWSSP2 will only support the rehabilitation of non-functioning community ponds, rather than the construction of new ponds; To offer a more consistent, harmonized approach to nongoverment organization (NGO) support, the Ministry of Rural Development (MRD) has engaged one NGO to provide support for all provincial teams, instead of hiring individual NGO teams to support each provincial department of rural development (PDRD); Recognizing the low capacity and high level of effort required for monitoring and evaluation (M&E), an international M&E firm has been engaged under RWSSP2 to work alongside MRD M&E officers to develop systems and build capacity; and Subsidies for household sanitation will be offered, but will be very strictly and transparently targeted at those households measured as ï¿½poor level Iï¿½ and ï¿½poor level IIï¿½ using the Ministry of Planning's national Identification of Poor Households targeting mechanism. This is a proxy means test that measures easily observable household characteristics and assets and is implemented in all 24 provinces. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/tonle-sap-rural-water-supply-and-sanitation-sector-project
Greater Mekong Subregion: Cambodia Road Improvement Project | Cambodia | Transport | 2011-11-01 | Match covenants with jurisdictions. One covenant required government approval of the road law and transport policy. However, the formulation of the road law and transport policy that was expected under the project was delayed. The requirement should not have been a loan covenant because the Ministry of Public Works and Transport (MPWT) did not have jurisdiction over rural roads and thus lacked the ability to comply fully. Loans should not include covenants that impose requirements on an executing agency that lacks full jurisdiction to meet them. ADB teamwork. ADB needs to have better teamwork approach between its operational support divisions for activities, such as consultant recruitment where support divisions have more authority over approvals. The project completion review mission observed that absence of internal coordination created the initial delay in the consulting selection process. Faster disbursement process. Disbursement was slower than specified in the conditions of contracts. In addition, local funds were disbursed much later than ADB funds. The government needs to reduce the time for disbursement of funds to improve cash flow of the contractors. Better planning of vendor relocation. Planning for relocation of roadside vendors in projects such as this needs to pay careful attention to the viability of new market area sites and to involve close consultation with the affected individuals. Moving vendors from a roadside to proper market facilities does not guarantee that they will earn the same income as before. A new marketplace housed in a linear building running parallel to the road and provided with service lanes could give better access to relocated vendors. Closer ADB watch on environmental issues. Closer ADB supervision through regular submission of environmental monitoring reports by MPWT, along with regular safeguard reviews, will help avoid or minimize adverse environmental impacts due to project implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/greater-mekong-subregion-cambodia-road-improvement-project
Cambodia: Tonle Sap Environmental Management Project | Cambodia | Agriculture, Natural Resources, and Rural Development | 2011-09-30 | 1. For a project with interrelated components funded from separate sources, it is important that a coordination mechanism is set in place to integrate and optimize outputs and impacts. For example, coordination between the ADB-funded components 1 and 2, and the Global Environment Fund-funded, United Nations Development Programme-administered component 3 was lacking in the Tonle Sap Environmental Management Project in Cambodia. While the its design was well conceived with three separate but interrelated components, parallel financing arrangements and the creation of a separate Tonle Sap Conservation Project appear to have made it difficult to coordinate and integrate the project components. ADB's internal procedures somehow reinforced the notion that these were two separate projects. In addition, the project completion report team did not have complete information on the activities and disbursements of component 3. [Main text, paras. 26, 29] project cycle stage: Design, Implementation Lesson Topics: 2. Inferior project frameworks, e.g., characterized by the lack of clearly identifiable performance indicators, prevents the conduct of robust evaluations. The validation report on Tonle Sap Environmental Management Project in Cambodia indicated that empirical results linking activities, outputs, and outcomes on socioeconomic and environmental conditions were lacking. Its design did not have a rigorous monitoring plan and needed an improved quantitative set of indicators to measure results. [Main text, paras. 29, 31] project cycle stage: Design Lesson Topics: | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/cambodia-tonle-sap-environmental-management-project
Cambodia: Small and Medium Enterprise Development Program [Loan 2129-CAM] | Cambodia | Industry And Trade | 2010-12-31 | 1. It is crucial to the success of a policy-based program to undertake proper pre-appraisal preparatory work to identify correctly the concerns and issues that needed to be addressed under a reform program to facilitate program implementation and accomplish the envisaged outcome and outputs (a pre-assessment was done in this case using an ADB funded technical assistance). [Main text, page 7, section E(ii.a)] project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Modality: Policy-based lending Modality: Program Project Design: Appraisal Policy & Reform: Reform 2. It is essential to provide technical assistance (TA) for capacity enhancement and program implementation to make a success of a reform program (2 TAs were provided in conjunction with the Program in this case). [Main text, page 7, section E(ii.b)] project cycle stage: Design, Implementation Lesson Topics: Modality: Program Modality: Technical Assistance Policy & Reform: Reform 3. It should be understood that enactment of new laws (financial leasing law in this case) which would take time particularly in countries faced with capacity constraints is necessary. [Main text, page 7, section E(ii.c)] project cycle stage: Implementation, Completion Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/cambodia-small-and-medium-enterprise-development-program-loan-2129-cam
Health Sector Support Project | Cambodia | Health | 2010-12-01 | The success of nongovernment organization (NGO) contracting of health services under the project provided the foundation for Ministry of Health's (MOH) introduction of new contracting arrangements (internal contracting) based on the government's Policy on Public Service Delivery (2006) and adoption of MOH's procedures and guidelines on contracting arrangements. Many innovative features first developed under NGO contracting have been, or are in the process of being, adopted for internal contracting, including performance incentive schemes, monitoring indicators, monitoring and evaluation (M&E) approaches and tools, and supervision arrangements. The internal contracting arrangements include performance agreements between MOH and provincial health departments (PHDs), and service delivery contracts between PHDs and operational districts or referral hospitals; and are drawn directly from the NGO contracting implemented under the project. The success of NGO contracting has thus proved to MOH that internal contracting is feasible, cost- effective, and equitable; and can materially increase the extension of health benefits to the poor. Building on lessons from the Basic Health Services Project, the project gave greater emphasis to close monitoring and supervision by MOH to ensure that civil works were closely coordinated with the supply of equipment and drugs under minimum package of activities (MPA) and complementary package of activities (CPA) guidelines. However, efficient planning, a well-executed plan, and close oversight by MOH would have allowed timely completion of civil works and avoided cost overruns. To improve the quality of civil works, implementation arrangements should incorporate closer supervision and monitoring at all levels. In support of MOH's sectorwide management strategy, ADB's participation in the sectorwide management approach along with other partners in a jointly administered project proved the benefits of close collaboration among health partners. While the Health Sector Support Project (HSSP) was cofinanced by different donors and implemented through an integrated project implementation arrangement under the sectorwide management approach, the project was administered by each donor agency with different implementation schedules. The ADB funded activities under HSSP were closed in 2009 while the World Bank portion of HSSP has been extended to complete all the activities including construction of health facilities. This resulted in different reporting arrangements including project completion reports. The sectorwide management approach significantly helped the government improve planning and coordination in project implementation, avoided duplication, and provided the basis for a broader sectorwide approach. However, the process of harmonization and coordination of various activities among the partners has challenged and slowed implementation progress. Considerable time and effort was spent on the process. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/health-sector-support-project
Tonle Sap Environmental Management Project | Cambodia | Agriculture, natural resources and rural development | 2010-06-01 | The project can point to the setting up of community fisheries organizations (CFOs) and the empowerment of local communities as huge successes in the short and medium term. However, in the long term, the CFOs may come under considerable pressure from outside interests without technical and moral support from the Fisheries Administration (FiA) provincial teams in the field. Cross-ministerial implementation of projects brings complications beyond just day-to-day technical issues. Experience shows this to have been the case with other projects. The Tonle Sap Environmental Management Project (TSEMP) experienced many delays caused by having to obtaining agreement and approval across departments. Alternative livelihood programs, while functioning satisfactorily, were focused on individual households, with little built-in capacity for extension. Small-scale livelihood activities must be appropriate to the situation. TSEMP has shown that the most successful small-scale activities are those that people themselves can sustain, given their income, time, and material constraints. Training is a necessary part of livelihood work, particularly if the participants have no previous experience. Overall, the project outcome appears successful. However, an important opportunity was missed. The project did not establish a recognized baseline with pre- and post-project comparisons to demonstrate to ADB, the government, and key stakeholders the natural resource management, environmental, community, and economic benefits. It would have been possible to provide well-documented evidence that the project had achieved its primary goal. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/tonle-sap-environmental-management-project
Country Assistance Program Evaluation for Cambodia: Growth and Sector Reform (2009) | Cambodia |  | 2009-09-30 | 1. Overall development strategy involves risks. Cambodia has pursued an effective development strategy of an open economy, linked to global and subregional markets, and private sector-led growth. There has been a consequent increase in incomes and reduction in poverty. While past ADB country strategy was successful, the future strategy involves external risks of a too-narrow economic base and reliance on foreign markets and investment; and internal risks from poor quality services, low standards of public sector management, difficulties in natural resource management, and reduced returns through corruption and weak rule of law. Continued improvements in addressing the external and internal risks will still take time and require considerable support. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Regional cooperation Country Context: political economy factors Sector Related Issues: Private sector 2. Early, continued and responsive involvement in a country's development process places ADB in a good position to ensure achievement of program/project results. Through its early and sustained involvement, and by delivering responsive projects and programs that generated clear and meaningful national and subregional results, ADB has built up a substantial level of trust with the Government. This puts it in a good position to effect some changes in the program, some of which are already under way. [Main text, paras. 46,56-58,121,125] project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Program Modality: Project Modality: Technical Assistance 3. Realistic designs can facilitate program implementation and contribute to positive outcomes. Cambodia's multiple transitions have required a complex set of reforms mounted on several fronts all at once. One of the keys to ADB's success has been its ability to help the Government plan and sequence a series of reforms at the sector level over a decade or more. ADB experience have shown that this required solid diagnostic work, practical grounding in sector investment realities, a good understanding of and working relationship with key line ministries and sector agencies, and an ability to tailor advice and recommendations to the Cambodian setting. [Main text, paras. 70,126] project cycle stage: Design Lesson Topics: Project Design: Project design Country Context: Transition Policy & Reform: Reform Methodologies/Approaches: Sectoral approach 4. Synergies among operations, even in the same geographic area, do not evolve naturally and need to be generated. Line agencies, local governments, and partners may be reluctant to see ADB focus its operations if this means that funding and partnering opportunities in any particular area are diminished. The cost of spreading limited resources over too many interventions, however, is declining project size, reduced focus on interventions of core ADB competence, lower cost efficiency as more resources are used for project administration, and a heavy aid management burden. A concerted effort is required to focus ADB' s assistance where the direct and catalytic payoffs are the greatest. [Main text, para. 74,112,127] project cycle stage: Country Partnership Strategy Lesson Topics: Capacity Development: Partnerships Methodologies/Approaches: Targeting 5. ADB's support to a wide-ranging reform and capacity-building effort have met with most success when there was high level political support and a clear demand for advice and capacity building; when assistance went beyond augmenting skills to improving institutions; and when the tasks were designed, sequenced, and staffed appropriately. For instance, well sequenced reform framework, strong government ownership of and commitment to future reforms were exemplified by the performance of loan operations in the financial sector. [Executive Summary, Main text, paras. 70,98-102,128] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Ownership 6. There is a need to continue advancing agriculture and rural development (ARD) in Cambodia considering that this is at the center of the country's poverty reduction effort. Continued support to ARD requires better diagnostic work and simple implementation arrangements. Rising inequality and current capacity limitations of traditional sources of growth (i.e., boosting rice yields) threatens to undermine the country's poverty-reduction efforts. ADB's past experience suggests that it is possible to identify, design, and implement ARD projects with a strong positive impact on economic growth and poverty reduction through interventions across a broad geographic area using simple implementation arrangements. Institutionally, ADB intends 80% of its operations to be in its core areas by 2012. However, it also acknowledges that support for agriculture is an underlying component of an inclusive growth strategy, mainly through rural infrastructure development; natural resource management; and regional cooperation and integration, such as agricultural trade and investment in the Greater Mekong Subregion. [Executive Summary, Main text, paras. 90,129] project cycle stage: Design, Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Sector Related Issues: Rural development | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-cambodia-growth-and-sector-reform-2009
Education Sector Development Program | Cambodia | Education | 2009-06-30 | 1. An effective monitoring and evaluation framework would have allowed better assessment of project outcomes. A key weakness in the Education Sector Development Program was that too little emphasis was placed on establishing baselines for output and outcome indicators at project start-up and ensuring that output and outcome data were available. There was no effective monitoring of progress of output and outcome indicators, and the achievement of a number of output and outcome targets could not be assessed for the project completion report. [Main text, paras. 45, 61] <!-- project cycle stage: Design, Implementation, Completion Lesson Topics: Monitoring &amp; Evaluation: Data collection and management Monitoring &amp; Evaluation: Indicators Monitoring &amp; Evaluation: Monitoring and evaluation Monitoring &amp; Evaluation: Project evaluation --> 2. The program could have benefited from sharper prioritization including better selection of performance indicators. Though the policy reform program had significant achievements, it was ambitious and not aligned with Government's capacity to fully undertake the reforms. The policy matrix covered too many areas and a significant number of performance indicators required specific data collection that was never undertaken. [Main text, para. 62] <!-- project cycle stage: Design Lesson Topics: Policy &amp; Reform: Policy matrix Policy &amp; Reform: Policy reforms/framework --> 3. To improve the quality of the civil works, implementation arrangements should be explored that allow closer supervision and monitoring at all levels, including assigning fulltime engineers in the provinces. Penalties for delinquent contractors and negligence in supervision should be strictly enforced to ensure both quality and timely completion and as a deterrent visible to other contractors. In some instances, performance in civil works was unsatisfactory due to weak oversight by the school communities, low bids submitted by the contractors, and, in a number of cases, deliberate noncompliance with specifications and written instructions. The delinquent contractors were penalized, and, where warranted, their contracts were terminated and they were barred from bidding for future civil works. These issues are also being addressed in the Second Education Sector Development Program. [Main text, paras. 41, 67] <!-- project cycle stage: Design, Implementation Lesson Topics: Project Management: Project management Project Management: Project supervision Sector Related Issues: Education --> 4. Guidelines on the use of learning resource centers is important in ensuring the facilities' efficient utilization and maintenance. While most of the facilities provided under the project are being used as planned, the teacher training and resource centers provided in 14 provinces are not being fully used. The lack of clear direction and responsibility regarding the use and maintenance, particularly for the science laboratory equipment and computer laboratories, has resulted in the very limited use of only the general spaces. Because they are rarely used, buildings are not properly maintained. [Main text, para. 69] <!-- project cycle stage: Design Appraisal Implementation Lesson Topics: Project Management: Operation and maintenance Project Management: Project management Sector Related Issues: Education --> 5. Contracting small, scattered civil works in remote, rural areas through local communities is the most effective procurement method for Cambodia's educational facility development. It empowers communities, raises awareness and ownership, and allows better quality through closer supervision. It enhances the capacity of the local builders. However, adequate time and resources need to be allocated for community orientation and periodic training during implementation. While communities are very keen to participate and take responsibility, they often lack simple technical and procedural knowledge. Making community contracting effective requires more intensive training in the beginning and midway through construction. [Main text, paras. 22,65] <!-- project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project management Methodologies/Approaches: Community approach Methodologies/Approaches: Participatory approach --> 6. Efficient planning and implementation are required for the timely completion of the education sector's investment component. Efficient planning, a well executed work plan, and strong oversight by the education ministry's senior management and the team of consultants resulted in the timely completion of civil works, which avoided cost overruns. [Main text, paras. 55,66] <!-- project cycle stage: Design, Implementation Lesson Topics: Modality: Project Project Design: Subprojects Project Management: Consultants Project Management: Executing/Implementing agencies --> Before handing over completed school facilities, communities and school authorities need to be trained in preventive and recurrent maintenance, and resources need to be allocated in the school budget so that school buildings are adequately maintained. <!-- project cycle stage: Lesson Topics: --> No technical assistance was provided to support policy reforms. The Government received support from other development partners, but it was neither comprehensive nor well coordinated, placing a burden on the Government that was in some instances beyond its capacity. <!-- project cycle stage: Lesson Topics: --> | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/education-sector-development-program
Provincial Power Supply Project | Cambodia | Energy | 2008-05-08 | 1. Preparing complex turnkey bid documents during the project preparation stage and using advanced procurement actions could reduce the risks of late project start-up and implementation delays. Although all project components were successfully implemented as envisaged, implementation delays have acted against the project's viability. There were lags in recruiting the implementation consultants and procuring two major turnkey contracts. These contracts were awarded about 18 months behind schedule. [Main text, paras. 16-17, 28-29, 52] project cycle stage: Design, Implementation Lesson Topics: Project Management: Procurement Project Management: Project management 2. The risk of investing in long-term transmission and distribution assets, with their degree of natural monopoly and mature technology, is far less than that of investing in competitive generator assets where energy conversion efficiency is relatively low. Future investments should be better made on distribution or transmission assets rather than on generator assets. [Main text, para. 50-51, 53] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Market analysis Sector Related Issues: Energy planning/management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/provincial-power-supply-project
Primary Roads Restoration Project | Cambodia | Transport | 2006-11-15 | 1. A contractor's ability to commit physical resources to a contract is crucial to project performance. In the Primary Roads Restoration Project, the contractors' performance varied. Scheduling development and maintenance works, contracts for tender, and prequalification of civil works contractors facilitated a more regular construction work flow and commitment of proper resources. However, given the project's experience on contract implementation delays and noncompliance to contractual obligations, an improved process can be achieved with rigorous prequalification process, establishment of effective measures to discipline noncomplying contractors, shorter periods for bid assessment, and timely payments to contractors. [Main text, paras. 18-20, 37-39, 54] project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Disbursement Project Management: Procurement Project Management: Project supervision 2. To prevent emergence of resettlement and environmental concerns, thorough safeguards monitoring is needed during project implementation. In this project, a resettlement audit was conducted due to allegations of inadequate compensation of affected persons during implementation. It was also noted that environmental problems were experienced as contractors failed to carry out environmental impact mitigation measures during civil works implementation. [Main text, paras. 38-39, 49, 52, 55-56] project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Project Management: Procurement Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/primary-roads-restoration-project-0
Emergency Flood Rehabilitation Project | Cambodia |  | 2006-01-13 | 1. The consulting services can contribute significantly to overall efficiency and play a critical role in ensuring the quality of works programs. Civil works projects generally require associated capacity building within implementing agencies for contract administration and addressing ADB procurement and disbursement procedures. In that respect, consultants greatly assisted management units to achieve timely completion of works, submission of withdrawal applications, and liquidation of imprest accounts. The impartiality international specialists brought to contract administration and quality assurance greatly assisted in achieving desired outcomes. [Main text, paras. 33, 43, 44(vii)] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building 2. Close monitoring of adherence to selection criteria for subprojects is necessary to ensure that resources are channeled appropriately. While the agreed criteria were generally followed, there were cases when external influences affected prioritization of proposed subprojects. For instance, a road alignment, which was rehabilitated and significantly upgraded, was outside the flood-affected area and not in full conformity with the agreed selection criteria. [Main text, paras. 16, 27, 44(iii)] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects 3. Given the complex multisector context and sector modality of implementation, the project benefited from the project monitoring and coordination unit's (PMCU's) efficient monitoring and coordination within the executing agency. Evaluation noted the PMCU's timely handling of coordination and monitoring of implementation issues. Monthly PMCU meetings was an important feature to identify implementation constraints and determine mitigating measures. [Main text, paras. 15, 24, 33, 44(i)] project cycle stage: Implementation Lesson Topics: Modality: Lending modality Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation Close monitoring and quality control of construction by an independent individual or organization is needed if design quality standards are to be achieved. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants Even if standard designs for common structures (roads, buildings, and irrigation) have already been established, each new project tends to promote its own design. Efficiencies are available through standardizing certain designs, and the government should assess the relative merits of the available alternatives. project cycle stage: Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Roading Procedures for prequalifying contractors can take as long as 6 months (including ADB approvals). In an emergency, it is expedient to draw on short-listed contractors from ongoing or recently completed internationally funded projects with a similar scope of works to avoid selecting contractors by bid price alone. Post-qualification procedures might be used to speed up procurement. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Country Context: Emergency Technical capacity building initiatives were not part of the design, but counterpart staff benefited significantly from working alongside international specialists. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Capacity Development: Capacity building Capacity Development: Technology/Technology transfer The emergency demanded a rapid response. Short-term expedience to accelerate processing was necessary but had some repercussions on the operational efficiency of loan disbursement. Accepting disbursement arrangements in the original design that incorporated neither interest during construction nor project monitoring and coordination unit (PMCU) operating costs was an oversight. It loosely grouped disbursement accounts (loan categories) into one for each part (component), covering all items from those with predominantly foreign exchange costs to those that were mainly local costs. Insufficient attention to such details during the design stage has resulted in considerable confusion among the IAs and their management units, as well as for project analysts within ADB and Ministry of Economy and Finance (MEF). This has resulted in the Government's eventually making a reduced contribution to the cost of civil works than was envisaged at appraisal. The Government made no counterpart contributions in the first 12 months of implementation. While this did not slow the rate of progress (it may in fact have helped, as counterpart funds were slow to be released), it was clearly not the intention when the Loan Agreement was negotiated. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Foreign exchange Finance & Financial Aspects: Local currency Loan Agreement: Loan Agreement Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Country Context: Emergency When unnecessarily lengthy and complex, procedures for the endorsement of interim payment certificates and payment of counterpart funds can provide opportunities for individuals to seek advantage from the system. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Corruption Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Disbursement While the government is understandably reluctant to spend loan funds on foreign consultants, depending exclusivelyon domestic specialists would have significant repercussions for engineering design (particularly in complex areas of hydrology where limited reliable data is available) and in the supervising works. During consultations with the PCR Mission, the IAs, without exception, considered international consultant inputs as a necessary part of the project on both counts. While good technical expertise is being developed in the line agencies and the emerging private sector in each of these fields, technical skills require further development. In terms of quality assurance, the IAs also recognize that the position of government monitors, especially junior staff, is easily weakened by influential contractors. The impartiality international specialists brought to contract administration and quality assurance greatly assisted in achieving desired outcomes. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Private sector Sector Related Issues: Water resource management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/emergency-flood-rehabilitation-project
Basic Skills Project in Cambodia (Loan 1368-CAM[SF]) | Cambodia | Education | 2005-09-30 | Focused institution building can bring dividends in a post-conflict situation. A positive lesson is that a project with clearly defined and focused outputs and outcomes that are well executed is appropriate in a post-conflict situation. <!-- project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity building Country Context: Conflict/Post-conflict --> Informal endorsement of health staff working in the private sector may begin to undermine government policies on ensuring equitable access to health care services, as staff increasingly prefer to work in private clinics in urban areas. <!-- project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Employment Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Sector Related Issues: Urban sector/development --> Informal endorsement of revenue-raising has been positive in assisting short-term sustainability of operations previously funded under the project. <!-- project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance &amp; Financial Aspects: Financial management --> Insufficient regulation of public/private partnership constitutes a risk to sustainability of project benefits. <!-- project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Risks/Risk management Sector Related Issues: Public-private partnership --> The effectiveness of the executing agency's human resources management information system may be undermined by unresolved organizational issues. The system established under the project has contributed to registration of health staff and workforce development planning, including quantitative and qualitative aspects. However, its potential may be undermined unless the coordination issues with personnel management functions, which fall under a separate department, are resolved. <!-- project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity development Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation --> The executing agencies and beneficiaries have highlighted how exposure to modern overseas institutions, along with learning English and computing, has been critical in confidence building and capacity development. <!-- project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity development --> Training demand and trainees willingness to pay may decline as areas of the job market become saturated. Government budget provision to cover critical areas with lower market demand (e.g., technology degrees) is critical. <!-- project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance &amp; Financial Aspects: Financing Finance &amp; Financial Aspects: Market analysis --> | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/basic-skills-project-cambodia-loan-1368-camsf
Rural Infrastructure Improvement Project | Cambodia | Multisector | 2005-07-15 | As a result of floods, standard bridge designs should be modified to incorporate piling and scour protection to withstand the impact of flooding in this complex hydrological environment. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Roading Decentralized selection, prioritization, and implementation of infrastructure rehabilitation are effective provided the technical skills are available to supervise and monitor works programs. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project supervision Capacity Development: Capacity assessment Country Context: Decentralization Country Context: Prioritization Funds available for provincial initiatives need to be matched withprovincial contracts awarded and amalgamated nationally to ensure efficient use of loan funds. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Procurement Integrated rural access planning is an effective tool for prioritizing rural infrastructure. This is essential for rural roads, markets, and other larger public civil works, wherethe vision from the village, commune, and districts needs to be widened and a more strategic planning and development approach adopted. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity development Country Context: Prioritization Sector Related Issues: Roading Sector Related Issues: Rural development Involving local communities and stakeholders in the identification and prioritization of project activities is critical to develop their sense of ownership and prepare them for future maintenance obligations. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Problem identification Project Management: Operation and maintenance Capacity Development: Ownership Country Context: Prioritization Methodologies/Approaches: Community approach Screening of individual consultants in bids should be exhaustive; where uncertainties arise, individuals should be replaced within the winning bid at negotiations. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement The quality and compaction of road base and alternate surface options are important to minimize recurrent maintenance obligations. The capital cost of rehabilitationshould not be the only criteria used to prioritize rural roads for rehabilitation because of its implications for recurrent obligations. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Management: Operation and maintenance Country Context: Prioritization Sector Related Issues: Roading Sector Related Issues: Rural development The timely release of counterpart funds ensures no undue implementation delays. Executing agencies should not use the imprest account to pay government's share under civil works contracts because of delay in the government release of counterpart funds. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Disbursement Project Management: Executing/Implementing agencies Using subcontracted labor-based appropriate technology (LBAT) works programs rather than force account paymentarrangements provides significant cost advantages and has implications on the need to maintain an inventory of equipment in the public sector. project cycle stage: Feasibility, Appraisal Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-infrastructure-improvement-project-0
Phnom Penh Water Supply and Drainage Project | Cambodia |  | 2005-05-13 | During project preparation, consultants should carefully assess conditions in project areas that are likely to be encountered during construction which can affect the achievement of more realistic time schedules and durations. Consultants must monitor closely the performance of contractors, and advise the PMU early if corrective measures are needed to prevent construction delays. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants Project Management: Procurement Project Management: Project management Government staff assigned to a project should be trained before implementation to familiarize them with ADB guidelines and procedures for project implementation. project cycle stage: Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Capacity Development: Capacity building The accountability and autonomy of the executing agency, together with its strong leadership, were critical to the success of the water supply component of the project. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management The lines of authority and responsibilities of concerned agencies in project implementation must be clearly defined. The project participants (Borrower, EA, IA, PMU, contractors, and consultants) must be made aware of them at the startof a project. Appropriate authority for decision-making should be delegated to the project management unit (PMU). project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management The track records of consultants and contractors should be evaluated and checked carefully to verify their ability to mobilize qualified staff and sufficient equipment and other resources to undertake contracted works well and within thespecified duration. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/phnom-penh-water-supply-and-drainage-project
Siem Reap Airport Project (December 2004) | Cambodia | Transport | 2004-12-15 | Direct selection is the easiest way to engage consultants, but strong justification is required to secure transparency and ensure performance of the selected consultant. One of the reasons that the executing agency failed to recruit individual consultants for establishment of a National Airport Authority was unfamiliarity of methodology and requirements for the standard consultant selection procedure. When ADB is requested to consider the direct selection of consultants, very careful examination is required. Direct selection should only be used with a strong justification, and ADB should carry out a careful review of the minutes of contract negotiation meetings and the contract document. It is not appropriate to apply direct selection for the purposes of time savings only. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Project Management: Consultants Project Management: Executing/Implementing agencies Sector Related Issues: Transport planning The number of contract packages should be minimized as much as possible in order not to spend much time in preparing bidding documents, reviewing the bidding documents, evaluating technical and financial bids, and solving issues which can be detrimental to project implementation. It is adequate to procure highly technical packages separately. project cycle stage: Implementation Lesson Topics: Under a substantial change in the executing agency's function, the loan covenants and due compliance should have been revised as appropriate, and additional loan covenants should have been agreed with the Borrower as a conditionality to continue project implementation. Further, to strengthen government organizations and undertake sector reform, it is important to reserve sustainable funds. It is highly recommended that an airport development special account be set up in the country. The technical assistance consultant for establishing the National Airport Authority (NAA) found that only about 25% of the aeronautical revenue is being used for the civil aviation sector and the remaining 75% is transferred to the government general account, and pointed out that financial sustainability of an NAA is highly questionable under the current financial mechanism. The loan covenants should have included establishment of an airport development special account, prior to setting up an airport authority. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Transport planning Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/siem-reap-airport-project-december-2004
Basic Health Services Project | Cambodia | Health | 2004-03-15 | Contracting health services to nongovernmental entities is feasible, cost-effective, and equitable and effectively targets and benefits the poor. This innovative approach has rapidly provided services to more people, and reduced infant, child, and maternal mortality. The contracting out model was preferable to the contracting in model. The contracting model could be applied to (i) outreach services, (ii) health centers and referral hospitals and their catchment areas, (iii) a district or districts in a province, and/or (v) entire provinces. In addition, appropriately designed and managed user fees systems can increase utilization by the poor and decrease their out-of-pocket expenditures on health care. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Project Management: Procurement Sector Related Issues: Extension service Sector Related Issues: Health and sanitation management Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Targeting Decentralization of health service management to provincial levels is crucial where small but adequate amounts of resources are provided to enable the management and supervisory systems at the district levels to implement managerial decisions and address problems identified. project cycle stage: Feasibility Lesson Topics: Country Context: Decentralization Sector Related Issues: Health and sanitation management The development of health care facilities, particularly referral hospitals, requires clear operational policies at the planning and design stages. Design should incorporate site works, utilities (including power and water supply), and adequate cost estimates. The construction, which should be coordinated with the supply of equipment, drugs, and trained personnel, should be monitored closely. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/basic-health-services-project
Country Assistance Program Evaluation for Cambodia (2004) | Cambodia |  | 2004-01-31 | Development effectiveness can be achieved through long-term commitment. The successful experience of ADB's assistance in the education sector demonstrates the value of long-term, comprehensive, well-integrated lending and nonlending programs through the adoption of the sector wide approach (SWAp). Other long-term modalities adopted in other sectors/subsectors also have good promise. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Lending modality Modality: Program Modality: Technical Assistance Capacity Development: Ownership Sector Related Issues: Education Methodologies/Approaches: Holistic approach Development effectiveness can be reduced by a narrow approach to institutional strengthening. Since many of the stand-alone, capacity-building advisory technical assistance projects narrowly focused on improving technical skills at the individual level, institutions as a whole have remained weak in terms of the management, operational, functioning, and budgeting systems. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Technical Assistance Capacity Development: Capacity building Development effectiveness can be reduced by weak aid coordination. Ineffective aid coordination reduced the institutional development impacts of many advisory technical assistance projects. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Development effectiveness can be reduced by weak governance. The lack of a clear strategy and substantial efforts to reform the public sector and improve governance early lessened the institutional development impacts of many advisory technical assistance projects. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Public governance Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Difficulties in evaluating the country assistance program (CAPs) performance are due to the lack of intermediate sector outcome indicators linked to the country operational strategy (COS) objectives. Without an established set of such indicators in the CAPs, it is difficult to evaluate the CAPs performance as many project and technical assistance completion reports (PCRs/TCRs) tended to rate projects/TAs as successful, based mainly on achievement of outputs rather than outcomes. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Policy & Reform: Policy reforms/framework | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-cambodia-2004
Selected Technical Assistance for Development Planning and National Statistics in Cambodia | Cambodia | Public Sector Management | 2003-09-30 | Approving almost $4 million for a technical assistance (TA) with four major components in a fluid situation with likely governmental changes after a landmark election and rapidly changing external agency involvement asks much of supervision from ADB, especially in cases where there is no resident mission. The implementation of such TA also needs to take into account that postconflict situations attract fewer consultants. A smaller TA, with fewer components, may be easier to implement in such situations. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Project supervision Country Context: Conflict/Post-conflict Other: Resident Mission If a ministry undergoes major organizational and functional changes, a thorough institutional assessment should be included to review the need for ongoing and new support. Support for such assessment from the government side is essential. project cycle stage: Feasibility Lesson Topics: Capacity Development: Institutional analysis Capacity Development: Ownership Policy & Reform: Public sector reform In transition economies and postconflict situations where local capacity is very limited and certain essential government outputs need to be rapidly produced, it may be useful to employ separate technical assistance (TAs) for substitution of local capacity with external capacity to produce these outputs on the one hand, and for training to produce local capacity on the other. If the two are combined, a risk is run that capacity substitution will quickly have the upper hand since it yields the quickest returns. In addition, a pattern may set in regarding the funding of operational activities by external agencies, to which the government may become accustomed. In Cambodia, this has led to habitual provision by TAs of salary supplements, allowances for attending training courses, vehicles, and allowances for field trips. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Country Context: Conflict/Post-conflict Policy & Reform: Public sector reform Policy & Reform: Transition economies | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/selected-technical-assistance-development-planning-and-national-statistics-cambodia
Agriculture Sector Program (Loan 1445-CAM[SF]) | Cambodia | Agriculture, Natural Resources, and Rural Development | 2003-07-31 | Earmarking the use of counterpart funds for reform purposes contributed to continued implementation after loan closing, and ensured that funds were used in accordance with the reform objectives. project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Counterpart funds Policy & Reform: Reform Identifying key sector issues is necessary but not sufficient for the design of a program loan. The program needs in-depth analysis of the various factors underlying the issues identified, as well as clear causal links among the sector issues, underlying causes, proposed policy interventions, and expected outcomes. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Policy & Reform: Policy reforms/framework Overstatement in program objectives may lead to less favorable rating of program performance, which needs to be evaluated against expectations specified in the Report and Recomendations of the President (RRP). Appraisal teams should be encouraged to limit themselves to realistic estimations; review of draft RRPs should remove ambitious statements. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Project evaluation Project Design: Appraisal Project Design: Project design Promotion of agricultural technologies should not be based solely on their potential to raise productivity without considering marketing limitations. The promotion is best driven by market demand identified by the private sector instead of by government agencies. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Management: Executing/Implementing agencies Capacity Development: Technology/Technology transfer Sector Related Issues: Private sector Sector Related Issues: Rural development The attached technical assistance focused on short-term implementation and used consultants to implement reform measures for the government. This resulted in the achievement of all program measures but not program objectives. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Policy & Reform: Reform The importance of proper sequencing in the design of policy interventions should be highlighted. Since it is impossible for one program loan to remove all sector constraints, interventions should focus on the most binding obstacle(s), and the remaining constraints should be explicitly identified as risks or assumptions. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Project Management: Risks/Risk management Policy & Reform: Policy reforms/framework The success of the Land Law can be attributed to the full participation of the government in the reform process, as well as extensive consultations with stakeholders. The long duration (4-5 years) of this process was justified: it produced a law accepted by all primary stakeholders, strong government ownership has led to continued reforms, and institutional capacity was developed through this process. In contrast, an unrealistic time frame for formulating strategies and policies generated undue pressure on the government to use consultants to merely meet reform requirements on time without benefiting from reform process. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Ownership Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/agriculture-sector-program-loan-1445-cam-sf
Power Rehabilitation Project (Loan 1345-CAM[SF]) | Cambodia | Energy | 2003-07-31 | A systematic needs analysis could well have identified the need for a customer billing system, and the requirements of such a system, and eventually could have led to a less complex implementation. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design On hindsight, a project design weakness was the absence of policy components that address broader sector issues such as high tariff and reliance on oil-fired power generation, which resulted in the failure of medium-size and large businesses to use the project facilities to the fullest potential. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Energy planning/management Policy & Reform: Policy reforms/framework Providing ongoing consulting support after project completion as well as before and during project implementation is very important. While this can often be difficult due to budgetary and time constraints, failure to provide such support can lead to suboptimal project outcomes. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Consultants The consulting services to support the introduction of a commercially based accounting system were inadequate. The transition from a manual system to the use of a computerized state-of-the-art accounting system required a major cultural shift, which necessarily must take a significant time to implement and establish. Furthermore, the end result is critical to the ongoing management and control of the organization and, once in place, requires the full commitment of staff and management. However, all work to implement the accounting system was done in seven months, which is an inappropriate level of involvement in circumstances where a major organizational change or cultural shift is required. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Consultants Project Management: Management information system Capacity Development: Ownership Country Context: Cultural constraints Policy & Reform: Reform The lack of involvement of the consultants over the final 2 years of the project is apparent from the utilization summary included in the project implementation consultant s completion report. It has led to the executing agency's inability to utilize the simulator provided in the project. While no further information is provided, it is possible that the consultant was unable to verify that the equipment operated correctly since he could not connect it to the power supply. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/power-rehabilitation-project-loan-1345-cam-sf
Basic Skills Project | Cambodia | Education | 2003-07-15 | Much of the project's success can be attributed to good leadership at various levels of the organization: Department of Technical and Vocational Education and Training (DTVET), formal technical and vocational education and training (TVET) institutions, provincial training centers (PTCs), Human Resources Development of the Ministry of Health (MOH), Ministry of Health (MOH), National Institute of Public Health (NIPH), Technical School of Medical Care (TSMC), regional training centers (RTCs), and Project Implementation Unit (PIUs). Differences in physical appearances of the institutions, enthusiasm, andquantity and quality of outputs can be traced to the effectiveness of leadership. Some notable traits of effective leadership are: (i) a clear vision of technical and vocational education and training (TVET) subsectors, manifested by development of long-term plans, (ii) openness to new ideas, (iii) willingness to take risks, perseverance in going around bureaucratic rules in order to get achieve results, (iv) concern and care for the staff, providing the training and logistical support to enable to perform better, and (v) giving constant recognition for good performer through verbal appreciation or financialincentives. <!-- project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management Sector Related Issues: Education --> | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/basic-skills-project
Basic Education Textbook Project | Cambodia | Education | 2003-03-14 | Most of the staff development activities under the project were implemented on the job,and on a short-term or intermittent basis by international consultants to keep abreast with theprogress of reorganization and systems development in the Publishing House and later in itssuccessor, PDH. This arrangement effectively minimized staff absence from the implementationsites, which is often caused by longer term off-the-job training programs that may lead toimplementation delays, and it has reduced the implementation cost compared with the formaloff-the-job training programs. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Capacity Development: Capacity building Capacity Development: Human resources management The project has addressed the importance of textbook distribution, which most of theprevious textbook projects seem to have overlooked. This focus on delivery mechanism is a keyto the project's sustainability, and, therefore, needs to be incorporated in future ADB operationsdealing with social services and provision of public necessities. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Sector Related Issues: Education Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/basic-education-textbook-project
Gender and Development in Cambodia | Cambodia | Multisector | 2003-02-28 | A TA can result to a loan project proposal that is well matched to country needs for skill development and employment promotion but be not feasible, if it is premature in relation to the political and institutional environment at the time it is proposed. Recognizing this can avert project failure. project cycle stage: Concept Lesson Topics: Modality: Technical Assistance Project Design: Problem identification Project Management: Risks/Risk management Capacity Development: Capacity assessment Country Context: Conflict/Post-conflict ADB and other aid agencies should consider a multipronged approach in which (i) continued support is given to the executing agency related to its priority areas in gender issues and its role as facilitator; (ii) technical assistance is provided to line ministries to build sector capacity for gender mainstreaming; and (iii) sector projects are designed with mechanisms for gender mainstreaming, accompanied by budgetary provisions. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Gender Finance & Financial Aspects: Financing Modality: Program Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity building Methodologies/Approaches: Holistic approach With (i) early identification of the key constraints; (ii) early, objective analysis of achievable goals and revision of the objectives; and (iii) responsive, efficient, and participatory management by the mission leader and team leader, a technical assistance design, although ambitious, after revision could be successful and achieve beyond its objectives. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Problem identification Project Management: Project management Methodologies/Approaches: Participatory approach | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/gender-and-development-cambodia
Institutional Strengthening in Transport Planning and Administration in Cambodia and Viet Nam | Cambodia | Transport and Communications | 2001-08-31 | Government ownership is necessary for full achievement of TA objectives and may be improved through (i) greater involvement of the recipient governments in TA formulation and consultant selection; and (ii) making strong efforts to identify practical solutions suitable for the needs of developing member countries, which may be pilot tested before wide-scale application. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Ownership Methodologies/Approaches: Pilot project Overly ambitious in scope, unfocused and low cost-effective TAs prove that sound design is a necessary first step for a successful TA. Second, close ADB supervision of all TAs, particularly those related to institutional strengthening, is clearly warranted to address unanticipated issues as they emerge. Third, the current guidelines for TA evaluation by operational departments need to include adequate provision for preparation of analysis on TA effectiveness. project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Management: Project supervision Capacity Development: Capacity building To maximize training effects, a long-term cost-effective strategy for capacity building should adopt the well-tested approach 'train the trainers' by involving research institutes and universities, or if this is not possible, should try to reach the widest target recipient base possible. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building Sector Related Issues: Education | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/institutional-strengthening-transport-planning-and-administration-cambodia-and-viet-nam
ADB's Program of Subregional Economic Cooperation in the GMS | Cambodia, China, Lao PDR, Myanmar, Thailand | Energy, Industry and Trade, Transport | 1999-12-31 | ADB provided very limited additional staff resources and has not made institutional changes to reflect the differentneeds and issues that arise with subregional initiatives. No formal networks or areas of joint responsibility between projects and programs departments have been established for GMS activities. The lack of formal institutional arrangements and the explicit recognition of a flexible, pragmatic, and results-oriented approach to cooperation have provided the GMS with a major comparative advantage in generating tangible results. There are advantages in designing subregional initiatives that avoid the need for diplomatic niceties by focusing on flexible, pragmatic objectives. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Project Design: Project design Capacity Development: Capacity development Capacity Development: Human resources management Methodologies/Approaches: Process approach An important area of comparative advantage for ADB is its capacity to provide a comprehensive package of support including assistance to reach agreement on priorities; in project preparation; to resolve software issues (e.g., cross-border agreements); and in securing financing for projects. ADB involvement in subregional initiatives can be useful in ensuring more equitable negotiating positions for the smaller, less developed countries. This has been important in accelerating agreements on key infrastructure projects. The cost of undertaking the consultation needed to build ownershipgreatly increases the broader the focus and the greater the number of countries involved. In the longer term, ADB should focus more on helping develop partnerships rather than being the promoter of initiatives and ownership. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Finance &amp; Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity building Capacity Development: Ownership Capacity Development: Partnerships Country Context: Prioritization Methodologies/Approaches: Consultation/Participation An important role for ADB in subregional cooperation is to act as facilitator in providing neutral technical and economic advice and secretariat support. The commitment of individual ADB staff to increasing economic cooperation has been seen as an important factor in bringing member countries together and in building trust. Continuity in committed national officials and ADB staff has also assisted in building trust and confidence that has facilitated decision making and implementation. project cycle stage: Concept, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Capacity Development: Human resources management Capacity Development: Ownership By focusing on practical changes needed to successfully implement specific projects, the GMS subregional program has helped break down administrative and institutional barriers to developing subregional infrastructure and trade and tourism. The GMS has shown that subregional approaches to development cooperation and planning can work and generate benefits that otherwise would not have been achievable. This supports ADB's charter rationale for supporting regional cooperation, for such cooperation generates economic growth in the region and enhances peace and stability. Regional cooperation can generate benefits from economies of scale, reduce transaction costs, and improve resource mobilization and opportunities for investment. project cycle stage: Feasibility Lesson Topics: Effective subregional cooperation requires attitudinal changes at all levels. Subregional initiatives generate widespread interest, and there are real dangers that the lack of systematic approaches to information dissemination can result in a considerable degree of misinformation. Strategies for the regular dissemination of information should be included in subregional initiatives. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Project Design: Project design Capacity Development: Capacity development Policy &amp; Reform: Information dissemination/Public awareness Subregional initiatives can provide economically viable opportunities to develop some of the poorest areas of member countries. The viability of national-level investments in poverty reduction can be substantially enhanced through subregional cooperation, as evidenced by the east-west corridor development. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Regional cooperation Project Design: Project design Sector Related Issues: Roading The key to effective implementation of subregional initiatives is sustained commitment and leadership from within the subregion and ADB. The process of reaching agreements and commitment to key priorities requires major commitments of time by senior subregional leaders. Such commitments will only be forthcoming if officials are convinced of potential benefits and there is a real sense of ownership of the initiative. The commitment of all members to the GMS process is reflected in the unprecedented and sustained level of ministerial participation in key meetings. An important factor in the GMS success is that participation in the individual activities is voluntary. There is no requirement that all countries agree with and/or participate in each initiative. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Capacity Development: Ownership Country Context: Prioritization Methodologies/Approaches: Consultation/Participation There are sometimes major differences in the distribution of the costs and benefits of subregional infrastructure developments. There is need for considerable innovation in the financing of subregional projects to ensure more equitable distribution of costs and benefits. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Finance &amp; Financial Aspects: Financing Project Design: Appraisal Project Design: Project design | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/adbs-program-subregional-economic-cooperation-gms
Promoting Renewable Energy, Clean Fuels, and Energy Efficiency in the Greater Mekong Subregion: Technical Assistance Completion Report | Cambodia, China, Lao PDR, Myanmar, Thailand, Viet Nam | Energy | 2015-05-01 | Compared to the power sector cooperation under the GMS (Greater Mekong Subregion), the expanded energy cooperation through SEF (Subregional Energy Forum) faced constraints and difficulties due to (i) lack of understanding of the opportunities for common efforts at the policy level and non-existence of underlying regional interconnection concept for RE (renewable energy), CF (clean fuels), and EE (energy efficiency); (ii) relatively limited capacity and diverse roles of ministries and agencies responsible for RE, CF, and EE; and (iii) relatively weak institutional setup of SEF in GMS energy cooperation. Project cycle stage: Implementation | Technical Assistance Completion Report |  | http://wcm.adb.org/projects/documents/promoting-renewable-energy-clean-fuels-and-energy-efficiency-gms-tcr
Southeast Asia Regional Energy Efficiency Sector: Technical Assistance Completion Report | Cambodia, Indonesia, Malaysia, Philippines, Thailand, Viet Nam | Energy | 2015-07-01 | National energy-savings targets have been identified by countries across Asia, but concrete action to meet these targets is still in the initial phase. Despite the increased level of interest, actions taken by policymakers, available market opportunity, and actual implementation EE (energy efficiency) projects remain deficient. While the TA's (technical assistance) awareness campaign has been effective in highlighting the significance of EE projects, there needs to be continuous effort, on the regional and national levels, in accelerating EE investments to help meet EE targets. During stakeholder consultations, access to financing was identified as one of the primary barriers to EE investments. To address this issue, programs tailored for financing institutions should be available to build their capacity in structuring and monitoring EE loans, understanding the technical nature and economics of EE projects, and marketing EE financial services to develop their EE project pipeline. With respect to the implementation delay due to political activities in Bangkok, it could not have been anticipated as the locale was relatively stable during the initial TA design. The workshops could not have been relocated without significantly impacting the success of outreach in the prioritized Thai market. ADB appreciated the consultants' flexibility to regroup and rearrange to make sure the target audiences were reached once circumstances returned to normal. Project cycle stage: Concept, Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/se-asia-regional-energy-efficiency-sector-tcr
Establishing a Regional Knowledge Sharing Platform for Resource Revenue Management: Technical Assistance Completion Report | Cambodia, Kazakhstan, Lao PDR | Public sector management | 2015-09-01 | It is appropriate to engage in the review of important current issues with relevant countries through knowledge forums. However, country ownership is critical for the success of such programs to generate better outcomes. It is important that production of knowledge products by knowledge departments should be at the request of ODs (operations departments) to ensure full ownership. Moreover, there is a need to ensure optimal coordination between knowledge departments and ODs for better delivery of knowledge services to client countries. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/establishing-regional-knowledge-sharing-platform-for-resource-revenue-mgt-tcr
Promoting Gender Equality in the Labor Market for More Inclusive Growth: Technical Assistance Completion Report | Cambodia, Kazakhstan, Philippines | Health | 2015-01-01 | One handicap in Kazakhstan was finding local consultants who had English speaking and writing skills as well as substantive skills in the area under study from a gendered perspective. Although economists could be found, it was difficult to find lawyers and gender specialists who had sufficient depth and understanding of the substantive content required. Despite the lack of a quality study from the Kazakhstan consultants, the international consultants were able to fill this lacuna and produce a quality regional synthesis and publication with relevant data from all three countries. In the end there were no gaps in information from Kazakhstan. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-promoting-gender-equality-labor-market-for-more-inclusive-growth-tcr
HIV Prevention and Infrastructure - Mitigating Risk in the Greater Mekong Subregion: Technical Assistance Completion Report | Cambodia, Lao PDR, Myanmar, Viet Nam | Health | 2015-06-01 | Designing and monitoring high quality intervention is an expensive and slow process. The design and monitoring framework should include measureable and quantitative indicators with interim and end-line targets, accompanied by documentation on how targets based on national policies were determined. HIV mitigation in infrastructure project should be more standardized and systematically included in all ADB supported infrastructure projects, particularly for vulnerable groups (ethnic groups, migrants, and mobile sex workers). Comprehensive administrative arrangements (7 firms/NGO or nongovernment organization packages and 23 individual consultants) posed a significant administrative burden to the implementing division (SEHS or Southeast Asia Department-Human and Social Development Division). However through these complex arrangements, the RETA (regional technical assistance) designed and implemented 11 innovative interventions in 4 countries which were documented as best practices in the field. Key lessons learned from the RETA served as essential inputs to the development of 7 ADB supported RETAs and projects on HIV, malaria, and GMS (Greater Mekong Subregion) health security. Among these were the engagement of NGOs as implementing partners to ensure post-project sustainability, the effectiveness of cross-border collaboration initiatives, and strengthening local capacity for project management and implementation. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/hiv-prevention-and-infrastructure-mitigating-risk-gms-tcr
Greater Mekong Subregion: Phnom Penh to Ho Chi Minh City Highway Project | Cambodia, Viet Nam | Transport | 2008-09-01 | 1. The prequalification of firms that do not have the capacity to undertake the civil works in a timely manner not only results in delays but extends the period of the construction supervision consultants. There was no effective measure to ensure that bidders who passed the prequalification and won the contract had the required equipment, working capital, and management staff at the project sites as stipulated in the documents. The prequalificationprocess needs to be more rigorous to avoid delays caused by the incorrect choice of contractors. project cycle stage: Design, Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement 2. There were several areas where resettlement issues affected the completion of the civil works, especially in Cambodia, where a resettlement audit became necessary. The resettlement audit was instrumental in improving the Ministry of Finance's understanding of proper resettlement practices and has improved overall resettlement practice in Cambodia. In future, ADB needs to undertake a careful analysis of the legal and policy framework in a country inrelation to ADB's policy, which may help to anticipate and address potential resettlement risks. The management structure for planning and implementing resettlement needs careful thought and planning to avoid conflicts of interest and to ensure efficient implementation. In Viet Nam, some residents were not satisfied with the resettlement payments and would not move until they were compensated at higher than market rates. Civil works cannot be continually delayed because of individuals attempting to receive additional benefits. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Resettlement Project Design: Project design Project Management: Risks/Risk management Capacity Development: Institutional analysis Sector Related Issues: Roading Policy & Reform: Policy reforms/framework 3. Environmental problems caused by contractors not taking an active role in protecting the environment could be avoided by more active monitoring. One way of doing this would be to withhold payment from contractors if they have not carried out environmental mitigation measures. Implementation of environmental mitigation measures should be included in tender documents and contracts, and where possible separate cost estimates for mitigation measures should be made. An environmental management action plan should also be prepared for project implementation. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Disbursement Project Management: Procurement Project Management: Project supervision | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/greater-mekong-subregion-phnom-penh-ho-chi-minh-city-highway-project
Developing a Legal System for the Credit Market: Technical Assistance Completion Report | China | Finance, Public sector management | 2016-05-01 | It is important to clearly align the expected outcome and outputs with the objectives of the executing agency and the government's objectives. Strong support from the counterpart was experienced and also vital in the success of the TA (technical assistance). Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/prc-developing-a-legal-system-for-the-credit-market-tcr
Public Finance Development Strategy 2020: Technical Assistance Completion Report | China | Public sector management | 2016-01-01 | The cancellation of the high-level dissemination event suggests that the authorities are cautious about the wider dissemination of ADB policy advice in key structural reforms, and prefer to limit discussion and dissemination on these topics to technical level meetings. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/prc-public-finance-development-strategy-2020-tcr
Wuhan Wastewater and Stormwater Management Project: Completion Report | China | Water and Other Urban Infrastructure and Services | 2015-09-07 | The project experienced significant delay in implementation and in delivering the project outputs. This was mainly caused by the construction delay of the Huangpu Road WWTP, which was completed in August 2015, 1.5 years after the loan closing. The delay of constructing the Huangpu Road WWTP attributed mainly to (i) delay in securing domestic approval for the required flooding control permission, which took 4 years from the loan approval in June 2006 to the certificate issuance in June 2010, and (ii) prolonged procurement of the plant equipment, which took 3 years from the preparation of the bidding documents to the contract approval. project cycle stage: Appraisal, Implementation The lessons from delayed construction of the Huangpu Road WWTP showed necessity of securing domestic approval in advance, prior to the loan effectiveness. If flooding control permission had been approved earlier, construction of the plant could have been completed on schedule and thus the overall project output could have been delivered completely. The lessons learned from procuring the design, supply, and installation contract for the Huangpu Road WWTP were meaningful for improving procurement efficiency in similar projects and contracts. The lessons include: (i) the contract type should be thoroughly justified by considering necessary technical factors - for example, the treatment process in this case - during project preparation; (ii) domestic approval for land or other administrative permissions should be coordinated closely with the detailed engineering design to ensure consistent and organized implementation; and (iii) expert support is needed when preparing the bidding documents, particularly in formulating technical specifications. project cycle stage: Design, Appraisal, Implementation The project cost overrun is another major lesson learnt. Regardless of common factors, such as Chinese yuan appreciation and raise of labor and material prices, inadequate project preparation and insufficient engineering design contributed directly to the project cost increase because they resulted in costs underestimate at appraisal and frequent contract variations during implementation. Lessons from the project cost overrun suggest the great importance of sound engineering design that can (i) support more accurate cost estimates, (ii) preclude or minimize contract variations during construction, and (iii) secure a more reasonable implementation schedule. project cycle stage: Design, Feasibility, Appraisal, Implementation The potential close-down and reconstruction of the Erlangmiao WWTP was totally unanticipated. ADB was not notified of this matter until the project completion review in December 2014. This indicates the lack of thorough and serious policy dialogue with the executing agency. If WMG notified ADB early of its urban plan updates related to the activities (e.g. Erlangmiao WWTP in this case) under the project, such low effective subproject could have been avoided through a scope change. In this regard, more effective policy dialogue with the executing agency should mainstream into the whole process of the project and the preparation of the new projects in the same project area. project cycle stage: Design, Implementation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/wuhan-wastewater-and-stormwater-management-project-pcr
Central Yunnan Roads Development Project: Completion Report | China | Transport | 2015-09-02 | The land acquisition and resettlement costs should be budgeted adequately during project preparation. The resettlement costs for the project increased by over 300%, mainly because of the significant increase in land compensation rates resulting from the nation-wide resettlement policy reform in 2008. When budgeting for resettlement cost, the project team should assess whether the existing resettlement policies are outdated and compare the policies with the market prices to assess whether the policies are reasonable. Based on a detailed measurement survey and cost assessment, the project team should then budget adequately for resettlement costs to ensure that the implementing agency has adequate funds to pay compensation to the affected people. project cycle stage: Design, Feasibility When establishing the project implementation team, it is better to mobilize staff with experience in ADB-financed projects under the same executing agency or implementing agency. The project was the fourth road project supported by ADB in Yunnan and YPDOT (Yunnan Provincial Department of Transport) was the executing agency for all previous projects. Unfortunately, only three working level staff of WKEC (Wukun Expressway Company Limited) had worked in the previous ADB-financed projects. Although the project implementation was successful, the overall performance of the project implementation could have matched that of the previous projects. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/central-yunnan-roads-development-project-pcr
Emergency Assistance for Wenchuan Earthquake Reconstruction Project: Completion Report | China | Transport | 2015-09-02 | This is the first emergency assistance loan to be processed for the PRC under ADB's Disaster and Emergency Assistance Policy. The project comprised more than 363 subprojects in 23 counties in two provinces, including reconstructing and upgrading rural roads ranging in length from 3 km to 32 km and rebuilding 12 schools. The PMOs (project management offices) and implementing agencies had no experience in implementing ADB projects. Their relatively weak capacity in managing many subprojects resulted in implementation lagging during the first 2 years. The TA (technical assistance)-supported training strengthened the project management capacity and knowledge of ADB policies of the staff of the PMOs and implementing agencies. A special review mission was conducted in both Sichuan and Shaanxi provinces in 2010 to fully coordinate the major reconstruction works and identify the bottlenecks that impede construction progress and resettlement implementation. Further, procurement and disbursement arrangements were also facilitated to ensure timely approval, award of contracts and disbursements. project cycle stage: Concept, Implementation The project engagement of external monitors in both Sichuan and Shaanxi enabled timely response to any involuntary resettlement impact during project construction and ensured full compensation and income restoration of affected villages. The emergency loan adopted a framework approach for resettlement safeguard management, i.e., a resettlement framework was prepared during loan processing, and during implementation detailed resettlement plans were prepared for all subprojects with adverse impacts. In general, this approach worked well for the emergency project with minor to moderate resettlement impacts to achieve streamlined loan processing. The environmental management practices during construction were implemented well by contractors and public participation was solicited effectively with public awareness campaigns on environmental protection and public health and well integrated with operations and maintenance of completed roads and education facilities. This approach facilitated project implementation and in the future can be adopted taking into account the emergency nature of components. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/emergency-assistance-wenchuan-earthquake-reconstruction-pcr
Nanjing Qinhuai River Environmental Improvement Project: Completion Report | China | Water and Other Urban Infrastructure and Services | 2015-09-02 | Land Acquisition and Sludge Disposal. Potential land for use by the project was secured and confirmed at appraisal and confirmed before loan effectiveness. However, land issues related to sludge disposal still arose during implementation, resulting in the cancellation of Component E. Sensitivity in site selection, careful assessment of land acquisition issues, and consultation with stakeholders during preparation are therefore essential. project cycle stage: Design, Appraisal, Implementation Implementation Arrangements. The project management office serves a critical coordinating function in executing projects that involve several implementing agencies. The NPMO's (Nanjing project management office's) strong leadership and good communication skills proved to be crucial for the efficient implementation of the project. In addition, the establishment of databases and monitoring mechanisms by each implementing agency during the early stages of the project was very useful. Assurance of a good partnership among implementing and oversight agencies is essential. project cycle stage: Implementation Loan Reallocation. To optimize the utilization of the loan, cost savings identified during implementation can be reallocated to other components during the midterm and final reviews. Under the project, NMG (Nanjing Municipal Government) was able to reallocate the proceeds from the cancellation of component E to the other components, resulting in optimum utilization of loan proceeds. project cycle stage: Implementation Flexibility in Project Design. Changes in the design of the project during implementation should be considered in order to achieve a better outcome. For instance, the cancellation of the Jiangxinzhou WWTP (wastewater treatment plant), because of the introduction of new technology to use the sludge to co-incinerate at a power plant, has provided a cleaner form of power generation and is good practice for recycling waste. Likewise, Mount Fenghuang was cancelled due to LAR (land acquisition and resettlement) issues, and sludge co-incineration was used instead, which resulted in a better outcome. project cycle stage: Design, Implementation Wastewater Tariff Revision. NMG (Nanjing Municipal Government) should continue to regularly review the tariff level, monitor and ensure that the wastewater tariffs are capable of meeting full cost recovery, covering the O&M (operations and maintenance) costs, interest, depreciation, debt repayment, and a reasonable profit margin. project cycle stage: Operation Operation and Maintenance (O&M). In Nanjing, management responsibilities for O&M of river systems, drainage systems, WWTPs (wastewater treatment plants), and sewerage systems were fragmented between Nanjing Qinhuai River Construction Company and Nanjing Municipal Water Company (under NCIC or Nanjing Urban Construction Investment Holding [Group] Company Limited), NDMD or Nanjing Drainage Management Department (under NMUMB or Nanjing Municipal Urban Management Bureau), water resources bureaus, and the district governments. This resulted in considerable confusion and inefficiency. However, certain institutional reforms (with a simpler division of responsibilities) introduced by the NMG (Nanjing Municipal Government) during project implementation, have helped to streamline O&M functions. project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/nanjing-qinhuai-river-environmental-improvement-project-pcr
Gansu Baiyin Urban Development Project: Completion Report | China | Energy, Transport | 2015-09-01 | The project helped develop the EMS (environmental management system) to enhance environmental management of the SBIZ (Southern Baiyin Industrial Zone). This enabled the BHTIP (Baiyin High-Tech Industrial Park) to become an environmentally friendly industrial park demonstrating'ï¿½circularâ€ economic development. The three-layer institutional setup, integrated environmental management platform, and early warning system help ensure that the environmental protection targets are met, potential environmental risks identified in advance, and actions and measures taken immediately to respond to emergencies. Following on this success, the Gansu Baiyin Integrated Urban Development Project will develop a more sophisticated EMS for another industrial park in Baiyin. project cycle stage: Operation As one of the first batch of comprehensive urban development projects in the PRC (People's Republic of China), lessons were learned with respect to LAR (land acquisition and resettlement) : (i) LAR impacts for urban projects usually are larger due to the high population density in urban or semi-urban areas; (ii) compensation rates could rise during implementation due to increased value of land and affected persons' property; and (iii) LAR implementation is influenced by the pace of urbanization rather than the schedules for individual projects, and that may result in delays which are beyond the project's control. BMG (Baiyin Municipal Government) had to reprioritize its urban infrastructure construction plan including the roads construction plan to better handle the large LAR impacts resulting from the city's rapid urbanization. As a part of the reprioritization, construction of some road sections was removed from the project scope so that LAR impacts would be reduced and the project could be completed within the extended loan period. Despite the reduced LAR impacts, the total LAR cost have increased by 60%. This was mainly due to higher compensation rates resulting from rapid urbanization and increase in land value. BMG had to mobilize additional counterpart funds to cover the cost increase. project cycle stage: Design, Implementation Procurement of civil works should take full consideration of LAR (land acquisition and resettlement) progress. Otherwise, even if procurement is completed quickly, it may not be possible to commence contract execution. Furthermore, disputes may also arise if land cannot be acquired and transferred to contractors on time. project cycle stage: Implementation Engineering design works could be further improved with more detailed on-site survey and adequate geological exploration to minimize contract variations during implementation due to unexpected geological conditions and missing items in the bill of quantities. project cycle stage: Design, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/gansu-baiyin-urban-development-project-pcr
Guangdong Energy Efficiency and Environment Improvement Investment Program - Tranche 3: Completion Report | China | Energy | 2015-08-19 | Project management. Strong government ownership was critical to successful project implementation. Creative and practical implementation arrangements ensured the investment program was soundly managed. Under the MFF, a distinctive financial intermediary modality was adopted, and a third party was selected to conduct energy savings M&V for each subproject. Furthermore, the executing agency issued and updated management handbooks for the investment program on procurement, financial management and energy savings M&V that ensured smooth and sustainable project implementation. project cycle stage: Implementation Financial intermediary. The financial intermediary loan modality was an effective mechanism to support implementation of energy efficiency projects. Evaluation of the financial viability of the candidate subborrowers was conducted independently by the GFTC to assess the financial status of each subproject. The project's revolving funding mechanism is operational, and proceeds from the loan repayments of earlier subborrowers are being rolled over to provide loans to new subborrowers that meet the eligibility criteria. The relending of subloan funds that have been repaid with interest will allow compound growth in the energy savings produced by the project during the ADB loan repayment grace period. project cycle stage: Feasibility, Appraisal, Implementation, Operation Energy saving estimates. The actual energy savings achieved by the tranche 3 project are much higher than anticipated at appraisal. More accurate methods of estimating energy savings should have been used at appraisal. The key is to establish an accurate baseline and design a customized M&V method to verify energy savings achieved from the outset. It is also important to use the same methodology for pre- and post-project energy saving calculations. project cycle stage: Implementation, Operation Measurement and verification. Third-party M&V agencies ensured accurate assessment of subproject energy savings and emissions reductions, which enabled the energy efficiency benefits and achievement of the overall project to be accurately calculated. project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/guangdong-energy-efficiency-and-environment-improvement-investment-t3-pcr
Xinjiang Municipal Infrastructure and Environmental Improvement Project: Completion Report | China | Energy, Transport, Water and Other Urban Infrastructure and Services | 2015-08-19 | Extensive, participatory consultations were conducted during project design and implementation. The needs and requirements of the beneficiaries and affected people, mostly ethnic minority groups, were incorporated into the design. As ADB's first loan for urban development in XUAR, the project prioritized promoting inclusive growth and sustainable development in the region through introducing a new urban development perspective, which addressed social benefits, environmental protection, and public participation. The project has a demonstration effect and provides lessons on planning and managing sustainable infrastructure development to other similar border cities and land ports with tourism potential in the region. project cycle stage: Design, Implementation Capacity building was emphasized in the project design and during implementation. A comprehensive training program was developed and implemented to strengthen the executing agency and implementing agencies' capacity in project management and O&M. Training was conducted to introduce ADB's policies and procedures in implementation and the experiences and best practices in urban development. This ensured that Xinjiang PMO, with strengthened institutional capacity, could continue to take the lead in managing subsequent ADB urban projects in XUAR. project cycle stage: Design, Implementation The project implementation arrangements were effective. The Xinjiang PMO executed clear division of responsibilities among different institutions. Through coordination efforts of Xinjiang Housing and Urban-Rural Development Department, close communications were maintained and issues were solved quickly. project cycle stage: Implementation The estimate of financing charges during implementation, $18.1 million and capitalized in the ADB loan, was too large compared to the actual interest during construction of $1.9 million. The large surplus could result in loan proceeds cancellation if no proper usage could be found before project completion. project cycle stage: Design, Implementation, Completion | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/xinjiang-municipal-infrastructure-and-environmental-improvement-project-pcr
Railway Safety Enhancement Project: Completion Report | China | Transport | 2015-08-10 | The radical change in scope of the project after the MRM on 8 May 2007 deserved more consideration, especially with respect to the economic rationale of emergency equipment. The economic evaluation at appraisal should have been carefully reviewed to eliminate the calculation mistakes made. project cycle stage: Design, Feasibility Although the delay in implementation was caused for justified reasons, i.e., a careful review of the required specifications of the second batch based on progressive understanding of actual needs, the project scheme could have allowed for a longer implementation period. project cycle stage: Design, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/prc-railway-safety-enhancement-project-pcr
Beijing Sustainable Urban Transport Project: Technical Assistance Completion Report | China | Transport | 2015-08-01 | The TA (technical assistance) provided a good communication and coordination platform between ADB, BMG (Beijing Municipal Government), and related agencies for supporting and preparing the travel demand model and TDM (travel demand management) measures. Good rapport among ADB, GIZ (Deutsche Gesellschaft fuer Internationale Zusammenarbeit GmbH) and the consultants ensured smooth TA implementation. The factors for successful implementation of the formulated demand management strategies were (i) strong political will of the municipal government, (ii) appropriate analytical and simulation outputs gleaned from the model, and (iii) strong collaboration and stakeholder participation in identifying the TDM strategies for implementation. Settling the claims by the national firm and closure of the contract and TA account encountered major delays. The national consultant's ability to manage its contract was overestimated. It overlooked the contract terms and conditions and had difficulties to claim accurately and on time with the required supporting documents. Project cycle stage: Implementation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/beijing-sustainable-urban-transport-project-tcr
Capacity Development of Partner Banks in Microfinance Wholesale Lending: Technical Assistance Completion Report | China | Finance | 2015-08-01 | Although the S-CDTA (small-scale capacity development technical assistance) helped the candidate banks establish and improve their risk appraisal system for MCC (microcredit company) lending, slow implementation of MWLF (microfinance wholesale lending facility) led to delays in the S-CDTA. Such a linked S-CDTA could usefully consider the implications of delays or changes in the main loan project, and prepare measures to mitigate delays. In this case, it would have been useful to provide for alternative outputs such as expanding potential candidate bank pools and providing additional training based on the demand and circumstances of the banks. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/capacity-development-partner-banks-microfinance-wholesale-lending-tcr
Management of Uncontrolled Landfills: Technical Assistance Completion Report | China | Water and other urban infrastructure and services | 2015-08-01 | Good timing and relevance. The TA (technical assistance) was carried out when many cities in the PRC (People's Republic of China) faced serious challenges of the disposal of vast amounts of municipal solid waste in uncontrolled landfills thus making the TA highly relevant. Strong leadership and realistic outputs. Throughout the TA, the executing agency showed strong ownership and leadership in refining its priority objectives, namely on the focus given to the guidelines and the reduction of the number of pilot cities. Nevertheless, more realistic outputs should be defined at the processing stage of the TA. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/management-uncontrolled-landfills-tcr
Managing the Water Resources of Boyang Lake: Technical Assistance Completion Report | China | Agriculture, natural resources and rural development | 2015-08-01 | The significant socio-economic growth in the watershed is being driven by four overarching national urbanization and economic policies: (i) the Rise of Central China, a national policy aimed at accelerating development of the central provinces of Anhui, Henan, Hubei, Hunan, Jiangxi, and Shanxi (e.g. development of the China Central Triangle); (ii) east to west transfer and connectivity, which promotes the relocation of industries from the more developed eastern coast of PRC (People's Republic of China) to the less-developed central and western regions; (iii) eco-economic development, which emphasizes balancing the goals of development and ecological conservation; and (iv) coordinated development, emphasizing development of key cities of the Boyang Lake urban belt radially around the provincial capital of Nanchang, and careful integration of urban and rural development to strengthen peri-urban economies. There are different priorities or interests between agencies in terms of how to manage water resources in Boyang Lake watershed. Against this backdrop, a multi-stakeholder approach was critical to achieving inter-departmental support for the action plan of integrated lake basin management strategy. In this regard, the TA (technical assistance) has successfully engaged the key water-related stakeholders in the process. As sustainable water management is a broad agenda beyond the local water department's mandate, securing the development and reform commission's ownership is key for successful multi-stakeholder approach. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/managing-water-resources-boyang-lake-tcr
Performance Evaluation Model for the Urban and Rural Subsistence Security System: Technical Assistance Completion Report | China | Public sector management | 2015-07-01 | (i) ADB involvement in the field of PRC (People's Republic of China) social protection arose from a sequential series of TA (technical assistance) employing individually recruited consultants. However, recent expansion in PRC social sector TA has brought heavy and competing demands for these pioneering PRC individuals and created some availability delays. It is important that ADB not only deliver effective individual TA but also help to nurture domestic consulting capacity in this important field. Heavy work demands on MOCA (Ministry of Civil Affairs) staff and a change in MOCA TA focal point made capacity and continuity of consultant inputs particularly important. Selection of a pilot site close to Beijing facilitated involvement of MOCA and Beijing City Civil Affairs and supporting field workers. This also resulted in TA savings due to lower travel and logistics costs. It is suggested that ADB identify and work with more diverse institutions and consultants and explore means for pairing national junior level researchers with more experienced research partners; (ii) Rapid pace of PRC policy creation and revision during Reform means that TA interim outputs or particular findings may have significant and timely policy contributions whereas the impact of larger, final study findings may take longer to materialize. This also requires timely information from client agencies. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/prc-performance-evaluation-model-urban-and-rural-subsistence-security-system-tcr
Songhua River Basin Water Pollution Control and Management Project: Completion Report | China | Water and Other Urban Infrastructure and Services | 2015-07-01 | Long-term vision and strategic planning. Strategic prior ADB TA (technical assistance) contributing to the preparation of the SRBPCMP (Songhua River Basin Water Pollution Prevention and Control Master Plan), which was approved by the State Council in March 2006, and ongoing ADB involvement and long-term partnership with local governments in the SRB (Songhua River Basin) is a model for replication. Key inputs to the SRBPCMP through ADB TA established a solid framework for policy and governance reforms and capacity building for pollution control, sustainable urban development, and integrated river basin management. The TA also developed a strategic prioritized portfolio as the basis for future investments by the government, ADB and other development partners, and the private sector. This was featured in the project design and implementation, and was fundamental to ensuring project relevance, and sustained future regional and local-level pollution control actions. In particular, following project preparation, phases 1 and 2 of Songhua River Basin Water Pollution Control and Management Project Private Sector Facilities provided an equity loan to Longjiang Environmental Protection Share Company to complete the project investments by upgrading wastewater and sludge treatment facilities in the SRB. Finally, one key aspect of the strategic planning was to identify cities where ownership and commitment were high, which is very important in situations involving a large number of cities and stakeholders. project cycle stage: Design, Implementation, Operation, Country Partnership Strategy Project coordination. The large scale and scope made project design and implementation challenging. Implementation succeeded because key stakeholders were involved in achieving the project goals, from the design stage through implementation. ADB missions served as catalysts to develop strong coordination and commitment between the two provinces and among the project counties and cities. Finally, the very good cooperation between agencies - and especially between provincial development reform commissions and finance bureaus - was essential for this type of project. project cycle stage: Design, Implementation Clear cost-recovery mechanism. National regulations on water and wastewater tariffs formulated and promulgated with ADB TA (technical assistance) require full cost recovery; all towns and cities nationwide must implement the regulations. Some project cities and counties have not yet reached full cost recovery, but they are making progress in a phased manner. Effective and sustained policy dialogue on cost recovery and tariff reforms is essential, and must be undertaken first nationally, to support and facilitate tariff reform in towns and cities. ADB's successful policy dialogue with the government on cost recovery and tariff reforms, and TA to prepare national water and wastewater tariff regulations, helped establish an enabling environment for private sector participation. This helped prepare market conditions for the Longjiang Environmental Protection Share Company and introduce the company for the Private Sector Operations Department-financed project, which contributed to important SRB pollution control objectives. project cycle stage: Operation | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/songhua-river-basin-water-pollution-control-and-management-project-pcr
Building a Framework for Regulation and Policy Support System for Eco-Compensation in Gansu: Technical Assistance Completion Report | China | Agriculture, natural resources and rural development | 2015-06-01 | Based on ADB's observations, this TA (technical assistance) was particularly successful due to the following reasons: (i) high ownership of the TA outcome and outputs by the relevant sector agencies; (ii) high preparedness of the sector agencies prior to review missions, which enabled them to extensively engage in discussions; (iii) strong leadership by the provincial finance and forestry departments; (iv) highly dedicated consultants who engaged extensively with key stakeholders and villagers; (v) decisions at the central government level during project implementation that supported the objectives of the project; and (v) prior experience of the executing agency in implementing ADB projects. During TA implementation (December 2013), the State Council approved the 'Master Plan for Establishing Integrated Experimental Zones in Gansu Province as the National Ecological Security Shield'. This decision further emphasized the urgency to strengthen the eco-compensation legislation and policy framework in Gansu, and proved to be an important factor in promoting stronger inter-agency collaboration in achieving the TA outputs and outcomes. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/building-framework-regulation-and-policy-support-system-eco-compensation-gansu-tcr
Highway Safety and Information System Development: Technical Assistance Completion Report | China | Transport | 2015-06-01 | The TA (technical assistance) demonstrated that a thorough study of advantages and disadvantages of systems and new technologies presented in a policy note can help policy makers evaluate which technology can be applicable for the country. Good cooperation between the international and national consultants has made project implementation smooth. Knowledge sharing through articles in magazines and newspapers to inform the public of the benefits and findings of the TA may be useful and fast to disseminate within the TA implementation schedule. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/highway-safety-and-information-system-development-tcr
Improving Energy Efficiency and Reducing Emissions through Intelligent Railway Station Buildings: Technical Assistance Completion Report | China | Transport | 2015-06-01 | The original TA (technical assistance) schedule significantly underestimated the time needed for (i) consultant recruitment; (ii) a detailed field investigation; (iii) in-depth comparison between the status of the PRC (People's Republic of China) and the best practices in the developed countries; (iv) organization of the workshops and overseas study tours; and (v) settlement of the consultant's claims, particularly the out-of-pocket expenses. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/improving-energy-efficiency-and-reducing-emissions-through-intelligent-railway-tcr
Operational Capacity Building and Value Addition: Technical Assistance Completion Report | China | Public sector management | 2015-06-01 | Experience under the TA (technical assistance) showed that the demand for capacity building significantly exceeded original expectations. The demand for in-depth and sophisticated technical solutions goes beyond general knowledge of project management. Capacity building projects should be flexible to correspond to this evolving demand. The inclusion of a pool of trainers for capacity building should have been carefully reviewed from the perspective of sustainability and effectiveness. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/operational-capacity-building-and-value-addition-tcr
Pilot Implementation of the Drought Management Strategy: Technical Assistance Completion Report | China | Agriculture, natural resources and rural development | 2015-06-01 | Drought risk is more properly managed at local levels, since such a management is intrinsically connected to water use and control which are parts of local water management. Since resources and capacity are often limited at local levels, there is a need for higher level organizations to take on a greater role initially, and greater effort need to be put into developing capacity at local levels and developing local drought management plans. Project cycle stage: Operation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/pilot-implementation-drought-management-strategy-tcr
Study on Eco-Compensation Regulations: Technical Assistance Completion Report | China | Agriculture, Natural Resources, and Rural Development | 2015-06-01 | The integration of the TA (technical assistance) interim workshop into the international eco-compensation conference, ensured a wider participation from stakeholders, and enhanced the results of the TA. The key lessons learned from the study were the importance for the national eco-compensation regulation to create a long-term eco-compensation mechanism that: (i) differentiates eco-compensation for individual ecosystem types and activities; (ii) is primarily funded through government financial transfer payments; and (iii) is supplemented with market-based schemes. Lessons learned from the studies of eco-compensation in different ecosystem types provided guidance on specific issues the national eco-compensation regulation should address. Many of these lessons are related to issues for which the National Main Functional Area Development Plan--a development zoning plan and the People's Republic of China's blueprint for regulating environmental protection and sustainable development approved in 2010 by the State Council--requires supporting measures. Incorporating provisions based on these lessons into the draft national eco-compensation regulation would contribute significantly to the implementation of the National Main Functional Area Development Plan. The TA findings also confirmed that regulating eco-compensation can be challenging as it requires fundamentally re-thinking the existing economic development mode and educating people to create a resource- conserving and environmentally-friendly society in all parts of the country. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/study-eco-compensation-regulations-tcr
Biodiversity Strategy and Action Plan for Yunnan Province: Technical Assistance Completion Report | China | Agriculture, natural resources and rural development | 2015-05-01 | A multi-stakeholder approach was critical to achieving inter-departmental support for the action plan. A key risk identified at the outset of the TA (technical assistance) was differing priorities or interests between agencies for conservation activities, which might result in reduced acceptance of the action plan. Such differences arose during the TA but inter-departmental consensus was reached through the transparent ranking process and rounds of discussion. The climate change analysis was an added value of the TA (not part of the original YEPD or Yunnan Environment Protection Department proposal) and illustrated to local agencies the importance of including climate change in natural resource planning. The CSOs (civil society organizations) noted that the action plan would help focus their conservation and research programs. CEP (Core Environment Program) involvement promoted regional collaboration, improved the technical quality of the TA materials, and strengthened the sustainability of the TA by supporting some of the follow-up actions. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/biodiversity-strategy-and-action-plan-yunnan-province-tcr
Recycling Waste Coal for Power Generation: Technical Assistance Completion Report | China | Energy | 2015-02-01 | The TA (technical assistance) delegation to the Shanxi Provincial Finance Bureau consumed longer time than expected to recruit the consultants and complete the payments. The transaction cost for both the Shanxi Provincial Finance Bureau and ADB was unnecessarily high. The key lesson is that initiating a new action such as delegated TA should be complemented by appropriate capacity development. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/prc-recycling-waste-coal-power-generation-tcr
Dali - Lijiang Railway Project: Validation of Completion Report | China | Transport | 2015-01-30 | The PCR (project completion report) listed a few important lessons drawn from the project, such as the need for sufficient consultations with stakeholders to promote ownership and responsibility. Likewise, there is a need for continuous process of adaptation to the latest construction and operation technology and more environmentally friendly solutions. The PCR also indicated the need to have careful estimation of the costs of construction materials and more realistic traffic forecast. project cycle stage: Feasibility, Implementation This validation offers three additional lessons. First, before implementing any additional works or contract variation, there should already be agreement on the works to be done and the commensurate costs. While this is an accepted project management practice, it may not have been the case in this project, which resulted in significant delays in loan closing due to the negotiations on pricing for additional works or variations. Second, while work on the land acquisition and resettlement seemed to have progressed well, the executing agency - the WYRC (West Yunnan Railway Company) - should have been provided more assistance in its implementation given its inexperience with both PRC (People's Republic of China) and ADB practices. As such, ADB assistance, through more frequent missions during the implementation period, could have provided the guidance needed for land acquisition and resettlement. A third lesson was the need to constantly follow-up with the executing agency on the implementation of the PPMS (project performance and monitoring system). It is surprising to note that this loan condition was not readily achieved, although its compliance was considered as ongoing. project cycle stage: Implementation | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/people-s-republic-china-dali-lijiang-railway-project
Guangxi Nanning Urban Environmental Upgrading Project: Validation of Completion Report | China | Agriculture, Natural Resources, and Rural Development, Water and Other Urban Infrastructure and Services | 2015-01-30 | The PCR (project completion report) gave several lessons upon project completion. This validation agrees with these lessons: (i) institutional arrangementsï¿½PMO's (project management office's) strong leadership and awareness of its critical role in the coordination process, experience with ADB procedures, and good communication skills are desirable; (ii) consultant recruitment and procurementï¿½early recruitment of consultants and national competitive bidding can reduce project delays; and (iii) resettlementï¿½the PCR noted that allocating commercial land to affected persons is a good practice for maintaining long-term income sources for affected persons; and can be replicated in other ADB projects. project cycle stage: Implementation, Completion | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/people-s-republic-china-guangxi-nanning-urban-environmental-upgrading-project
Hunan Roads Development II Project: Validation of Completion Report | China | Transport | 2015-01-30 | The PCR (project completion report) identified three lessons: (i) early preparation and readiness, and achievement of key milestones contribute to timely project completion; (ii) the importance of an appropriate traffic survey; and (iii) the importance of early completion of the resettlement plan. This validation agrees that a sound traffic survey is the heart of a preparatory study for road projects. An understanding of the assumptions used in the forecast and the methodology employed would have made this lesson more meaningful. This validation also notes that poverty incidence declined in the project areas as more jobs were created for local residents, including the ethnic minority groups. project cycle stage: Design, Feasibility, Implementation, Completion | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/people-s-republic-china-hunan-roads-development-ii-project
Hunan Roads Development III Project: Completion Report | China | Transport | 2014-09-01 | To minimize the cost for rehabilitating local roads, some existing bridges were not included in the project for reconstruction or reinforcement. The improved road network together with the construction of other expressway projects in the area triggered a significant increase in traffic volume, which resulted in damage to Changyishao Bridge in Huayuan-Fenghuang. In June 2012, serious safety problems were detected that subsequently stopped vehicle traffic on the bridge. A temporary access road was later built to meet the demands of local traffic; bridge reconstruction commenced in December 2013 with expected completion by December 2015. Careful detection and assessment of existing bridges should be conducted at the design stage for future projects involving the rehabilitation of local roads. Meanwhile, the generated traffic by the improvement of local roads and construction of adjacent expressways must be considered. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/hunan-roads-development-3-project-pcr
Kunming Qingshuihai Water Supply Project: Completion Report | China | Water and Other Urban Infrastructure and Services | 2014-09-01 | Strong commitment from the executing agency and the implementing agency is critical for successful project implementation. Yunnan provincial government and Kunming municipal government strongly supported the project. Additional CNY260 million counterpart funds were provided, and the provincial and municipal governments committed to share partial ADB loan repayment to help release Kunming Water Supply Group Company Limited (KWSG)'s financial burden. Kunming municipal government approved the Kunming Qingshuihai Water Resources Protection Regulations to promote watershed management as planned, and provided production assistance and livelihood subsidies to the affected farmers to mitigate the potential impacts. KWSG established a strong project implementation unit with adequate and capable staff, which is a fundamental reason for the successful project implementation. Engineering design was completed before ADB approved the loan, and advance procurement was applied which expedited the project implementation. Although it is an enterprise, KWSG demonstrated strong social responsibility. Additional input was provided for the land acquisition and resettlement implementation so that the affected people not only restore their livelihood quickly but also enjoy better living conditions in each of the four resettlement sites. In addition to the physical works, a water quality online monitoring system was established under the project. The system will be integrated into the management information systems developed by KWSG which, as the central water supply monitoring and control platform, will play a significant role in supervising and monitoring the overall supply of reliable, safe and clean water to the city in the future. The project facilitated the following corporate governance reforms of KWSG: (i) capacity development on reservoir management, safety and operation, and online water quality protection; (ii) improved corporate and business planning; (iii) enhanced financial management; (iv) assignment of two independent directors to represent water users on the board of directors; (v) strict enforcement of ï¿½one household, one meterï¿½ policy; (vi) substantial reduction in water loss from 38% to 22%; (vii) expanded distribution networks to connect more industries; and (viii) reduction of industries' groundwater use by 86%. All of these will contribute to more efficient, reliable, and safe water supply in Kunming. Procurement could have been improved. Civil works for conveyance works could have been grouped in bigger packages to attract contractors with good reputation, higher qualification, stronger financial resources, and more experience with large civil works contracts. This will reduce the risk of contract implementation as well as reduce the cost for managing the large number of contracts. The cost estimates at appraisal are conservative as they are based on the preliminary design with limited geological investigations. The potential cost increase due to complex and difficult terrain and geological conditions was not fully taken into account. Although Kunming municipal government and Yunnan provincial government provided additional counterpart funding for the project and committed to share a big portion of the ADB loan repayment, KWSG undertook a heavy financial burden resulting from domestic commercial loans for the project (about 44% of the total project cost) and the associated water plants and distribution works (100% of the total cost). The audit review conducted by National Audit Office on KWSG in 2012 concluded that the provincial and municipal governments should take more responsibility for such large public facilities investments. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/kunming-qingshuihai-water-supply-project-pcr
Western Guangxi Roads Development Project: Project Completion Report | China | Transport | 2014-09-01 | Special features. The inclusion of special features in project design should have been supported by careful formulation within the existing institutional context and allocation of sufficient funding to ensure adequate implementation and achievement of expected results. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/prc-western-guangxi-roads-development-pcr
Xinjiang Regional Road Improvement Project (Korla - Kuqa Section): Project Completion Report | China | Transport | 2014-09-01 | The 299.7 km four-lane expressway was constructed along the existing two-lane class II national highway (G314) and about 85.0 km of the existing highway was intermittently utilized as a part of the expressway. The advantages of using the existing road were the low cost of construction and less land acquisition and resettlement. However, there were disadvantages. First, using the existing road resulted in higher maintenance costs. Destruction of the existing road will be accelerated as traffic volume increases, since the existing road was built with a lower design standard for structure and pavement. Thus, major maintenance or reconstruction of the existing road will need to be carried out much earlier than for the newly built sections, which will increase maintenance costs and cause disturbance to road users. Secondly, using the existing road resulted in inconvenience to the local residents, especially for short distance travel. The national highway had served as the main road for local residents, which was free and easy to access. After construction of the expressway, local residents now have to travel longer distances since the expressway is enclosed and can only be entered at interchanges, and no alternative road was provided parallel to the expressway. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/xinjiang-regional-road-improvement-project-korla-kuqa-section-pcr
Anhui Hefei Urban Environment Improvement Project | China | Transport, Water and other urban infrastructure and services | 2014-08-01 | Private sector participation in utility operation has been mutually beneficial for government, private sector, and consumers benefitting from reliable service at competitive prices. With adequate implementation arrangements, projects can strengthen interagency coordination and cooperation, as this project has done. Additional potential synergies among components and associated benefits should be planned during project preparation to enhance project outcome. Projects with wastewater treatment plant components should be careful using health or water quality indicators, as many other factors influence these indicators outside the control and contribution of the project. The project demonstrated how well-scheduled feasibility design, detailed design, and the use of advance contracting can accelerate project implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/anhui-hefei-urban-environment-improvement-project-pcr
Hebei Zhanghewan Pumped Storage Project | China | Energy | 2014-08-01 | A strong technical and economic rationale for the project ensures its success even if the institutional arrangements for its implementation change. Significant changes to the power sector in Hebei Province and to the implementation arrangements of the Zhanghewan Pumped Storage Hydro Power Plant (ZPSHPP) did not affect implementation of the ZPSHPP, as it had strong technical and economic relevance to the needs of the Hebei power system. The overall financial strength and institutional capability of the sector are important to ensure the successful implementation of large infrastructure projects which require a significant amount of counterpart financing. The ADB loan contributed 21% of the cost of the ZPSHPP and 15% of the total project cost; the remaining financing was mobilized from domestic banks, shareholder financing, and local government financing. Establishing a dedicated entity for the design, construction, and operation the ZHSHPP contributed to the smooth implementation of the project and its subsequent operation. The core staff of Zhanghewan Pumped Storage Company (ZPSC) has been involved in the project from its inception, so the Company has a strong sense of ownership and institutional memory. Competent implementation supervision consultants are important to ensure the quality of the technical design and the performance of contractors for complex infrastructure projects. ZPSC highly appreciated the contribution from implementation consultants for the smooth implementation construction of the project within the original schedule. Affected households should be provided with full information regarding their entitlements, livelihood options, and access to other services; and to secure their agreement for proposed resettlement sites as early as possible. The project owner should proactively engage in the consultation process, without delegating the responsibility for managing the resettlement to local government agencies. Consultations with the affected people were not effectively conducted by the local government, which caused significant delays because of lack of consensus on the resettlement sites. This could have been avoided if ZPSC had played a more active role in managing the resettlement program. Obtaining the agreement of affected people to the proposed resettlement sites and entitlements is also significant. Selecting relocation sites near an economic center provides better access to employment opportunities, and public services (such as schools and hospitals) help in obtaining the agreement of the affected people. Providing better housing conditions with basic infrastructure (such as piped water, electricity, internet, and telecommunications) modernized the lifestyle of the affected people, compared with old villages in mountainous areas. In addition, a combined monitoring method - with direct inspection through the missions and regular monitoring - is highly effective for sensitive resettlement cases. The project design and monitoring framework included components that are not directly related to the project. The implementation arrangements for these components were different from ADB-financed ZPSHPP, and ZPSC did not have any role in implementing these components. This prevented effective monitoring of the implementation of these components by ADB review missions, and confirming their efficacy in achieving the outcomes. Furthermore, the indicators to measure the poverty alleviation impacts were poorly defined as a result these could not be monitored during review missions. ADB should have required Hebei Electric Power Corporation to establish a coordinating mechanism to supervise the implementation of different project components and insisted on more information about these components to be included in annual progress reports and safeguard monitoring reports and inappropriate indicators should have been appropriately revised The relevance and rationale for including an institutional strengthening component to promote power sector reforms is questionable given the uncertainty over the government's strategy for power sector reforms. It is necessary to ascertain the government's vision and strategy for far-reaching sector reforms before committing resources to implement these reforms in lending projects. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/hebei-zhanghewan-pumped-storage-project-pcr
Central Sichuan Roads Development Project | China | Transport | 2014-06-01 | The project was formulated to minimize the potential technical, safety, economic, financial, and resettlement risks. The main technical risks were associated with 25 tunnels (41 km in total length) and 270 bridges (91 km in total length). To mitigate the risks, national and international consultants reviewed the project design and construction methods and incorporated solutions based on advanced technologies and international prevailing practices. During construction, monitoring and contract management information systems were set up and implemented to identify technical problems and implement corrective measures on a timely basis. Given the safety hazards associated with large and high bridge works and long and deep tunnels, the contractors were required strictly to enforce working safety rules and measures and Sichuan Yaxi Expressway Company Limited closely supervised all key construction activities through supervision engineers. In term of the lessons leant from resettlement implementation, the adequate budget, recruitment of qualified external monitor, and earlier planning and construction of resettlement sites are deemed essential. One of most complex mountainous expressways in the PRC, the project expressway passes through the most difficult and complicated geo-technical terrain. In coping with various technical difficulties and challenges, Sichuan Provincial Transport Department and Sichuan Yaxi Expressway Company Limited initiated 32 technical research and development studies associated with the project's design, construction, and operation. Application of these technical findings has generated significant social and economic benefits. For example, based on a study of operation safety control technology for expressway spiral and small radius tunnels, the project expressway alignment executed a climb of 350 m in a V-shaped valley 2.9 km long by reducing the longitude slope. The study also optimized the number of ventilation fans compared with the preliminary design, thereby halving the power consumption. This study was awarded a prize by the China Highway Association. Other knowledge achievements and breakthroughs include a key-technology study on deep and super-long tunnel design and construction, a comprehensive technical solution for truss-beam and steel-column concrete for medium-span bridges, as well as design and construction of higher-pier and long-span bridges in serious seismic areas. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/central-sichuan-roads-development-project-pcr
Eastern Sichuan Roads Development Project | China | Transport | 2014-06-01 | The project cost is within the approved cost estimate, which can be attributed to accurate preliminary and detailed designs. Contingencies envisaged at appraisal sufficiently covered all routine variations. The Sichuan Provincial Transport Department and Sichuan Dashaan Expressway Company Limited started preliminary and detailed designs during the project processing stage, and results of both designs were incorporated in the project design, contract packaging, and preparation of the procurement plan. According to prevailing project design process for the infrastructure sector, it was optimal and beneficial to project implementation to procure works packages on the basis of the preliminary design or preferably the detailed design, which were completed during loan processing. The connection road between Chengkou County of Chongqing and the project expressway serves as an example on how to spread project benefits among neighboring provinces. Improving access to poor remote areas should not be limited to project areas within the project province, but should be extended to broader areas. This wider coverage of project influence areas may be considered at the project design stage and supported through commitment and coordination from national authorities. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/eastern-sichuan-roads-development-project-pcr
Guangdong Energy Efficiency and Environment Improvement Investment Program - Tranche 2 | China | Energy | 2014-06-01 | Project Management. Strong government ownership was critical to the successful implementation of the project. Creative and practical implementation arrangements ensured the investment program was soundly managed. Under the multitranche financing facility, a distinctive financial intermediary modality was adopted, and a third party was selected to conduct energy savings measurement and verification for each subproject. Furthermore, the executing agency issued and updated management handbooks for the investment program on procurement, financial management and energy savings measurement and verification that ensured the smooth and sustainable project implementation. Financial intermediary. The financial intermediary loan modality was proved an effective mechanism to support implementation of energy efficiency projects. Evaluations of the financial viability of the candidate subborrowers were conducted independently by the Guangdong Finance Trust Company to assess the financial status of each subproject. The projectï¿½s revolving funding mechanism is operational, and proceeds from the loan repayments of earlier subborrowers are being rolled over to provide loans for more new subborrowers that meet the eligibility criteria. The relending of subloan funds that have been repaid with interest will allow compound growth in the energy savings produced by the project during the ADB loan repayment grace period. Energy saving estimates. The actual energy savings achieved by the tranche 2 project are much higher than anticipated at appraisal. More accurate methods of estimating energy saving should have been used. The key is to establish an accurate baseline and design a customized measurement and verification method to verify energy savings achieved from the outset. It is also important to use the same methodology for pre- and post-project energy saving calculations. Measurement and verification. Third-party measurement and verification agencies ensured accurate assessment of energy savings and emissions reduction for subproject, which enabled the energy efficiency benefits and achievement of the overall project to be accurately calculated. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/guangdong-energy-efficiency-and-environment-improvement-investment-program-tranche-2-pcr
Guangxi Nanning Urban Environmental Upgrading Project | China | Agriculture, natural resources and rural development, Water and other urban infrastructure and services | 2014-06-01 | Institutional arrangements. The project management office serves a critical coordinating function in executing urban development projects that involve implementing agencies from several sectors. A project management office with strong leadership, experience with ADB procedures, and good communication skills is desirable. The establishment of databases and monitoring mechanisms by each implementing agency early in the project is important. Placing a monitoring specialist and project performance monitoring system within each implementing agency allows for consistent monitoring throughout the project period. Consultant recruitment and procurement. Recruitment of consultants through the use of the quality- and cost-based selection method can take 9-10 months, reducing the time allowed for project preparation. In addition, managing a large number of contracts can increase the coordination challenge for the project management office. The ADB threshold between requiring national competitive bidding and requiring international competitive bidding is very easy to exceed, and international competitive bidding is time-consuming, taking 6-9 months. The international consulting company recruited by the project management office provided consulting services at the early stage of project implementation. It ensured successful procurement, implementation, and payments, as well as timely report submission. In project procurement, bidding document preparation, bidding, bidding evaluation, and contract award progressed smoothly. Early recruitment of consultants and national competitive bidding for contracts can reduce project delays. Resettlement. Although some delays occurred in land acquisition and resettlement, a good consultation process and transparent information disclosure mechanisms helped to build trust and understanding between the different stakeholders. In 2008, Nanning municipal government updated the resettlement regulations, which made the compensation more acceptable to affected persons. The practice of providing commercial land for livelihood restoration based on these regulations was successful and left the affected persons highly satisfied. Allocating commercial land for tertiary industry to affected persons is a good practice for maintaining long-term income sources for affected persons that can be replicated where local regulations permit. The installation of some sewer networks under the Kelijiang River subproject was planned to coincide with the construction of roads scheduled to be built with government financing. The inability of the government to carry out the planned road construction on time due to resettlement problems forced a change in the project's scope. This showed that to avoid scope changes and delays, the risks of undertaking project components whose timely implementation and design are dependent on the schedule and design plans of non-ADB projects should be carefully evaluated during project preparation, and the actual progress on and potential changes in these non-project activities should be carefully monitored. Solid waste tariff covenant. The solid waste tariff increase required for cost recovery was estimated accurately at appraisal, and the increase was made part of a covenant to assure the Nanning Shixi Solid Waste Treatment Companyï¿½s financial autonomy. While the tariff was raised in 2007 and 2011, it remained below that set in the covenant and insufficient to ensure cost recovery in the solid waste management operations. The failure to execute the necessary tariff increase was due to the lack of support from relevant government agencies and Nanning municipal governmentï¿½s concerns about social reaction, affordability, and willingness-to-pay in light of inflation. Cost recovery has not been achieved, Nanning Shixi Solid Waste Treatment Company operations are therefore subsidized by Nanning municipal government budget, and further policy dialogue on the tariff increases is needed to realize full cost recovery and sustainability for solid waste services. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/guangxi-nanning-urban-environmental-upgrading-project-pcr
Shandong Hai River Basin Pollution Control Project | China | Water and other urban infrastructure and services | 2014-06-01 | Water reuse. Water reuse was included in the project design, which contributed to water conservation and efficiency. For commercial use of reclaimed water, identification of suitable industrial users is critical. Lingqing and Gaotang municipal wastewater management subprojects identified two existing paper mills close to the wastewater treatment plants as potential users at appraisal, and started providing treated wastewater upon operation of wastewater treatment plants to generate revenues. The Binzhou subproject failed to commercialize water reuse as the major potential industrial user relocated. Clean Development Mechanism program for small-scale landfills. The Clean Development Mechanism program has been implemented successfully in large-scale landfills. With strong support from ADB and Shandong Provincial Government, the Zouping solid waste management subproject was successfully registered as a Clean Development Mechanism project under the Kyoto Protocol. The implementing agency, Zouping County Domestic Solid Waste Limited Liability Company, signed a carbon purchase agreement with the Asia Pacific Carbon Fund. This subproject provided the first pilot of a small-scale landfill and actively contributed to global greenhouse gas reduction. ADB's technical support and commitment from local governments to achieve more environmental benefits are critical for Clean Development Mechanism program implementation. Cost recovery scheme for solid waste management project. In the PRC, tariff setting and collection for solid waste management generally lags behind other public services. In small cities or counties where solid waste management services are being extended to rural residents to promote integrated urban-rural development, the situation is even worse. For most solid waste management projects, local governments provide subsidies for their operation, in particular the solid waste collection and transfer. Although the situation is improving, it may take longer than expected to increase the tariff to cost recovery levels. For future projects, a more realistic cost recovery scheme or partial cost recovery scheme shall be considered. Flexibility to optimize project design during implementation. This flexibility, which is critical to enhance effectiveness of project outcomes, enabled the project to use loan savings to expand the municipal wastewater management and solid waste management subprojects' service areas and improve project facilities' operation efficiency. On the other hand, when the urban plan of Shanghe County was updated, the design of the Shanghe municipal wastewater management subproject was changed to a two-phase construction plan to avoid overcapacity of the wastewater treatment plant, which has been an issue according to prior ADB-financed projects. In addition, local governments leveraged further financing to expand infrastructure, such as sludge treatment and disposal facilities in municipal wastewater management subprojects and the wetland in Binzhou to further purify the wastewater treatment plant effluent for landscaping works use. These measures enhanced outcome effectiveness and sustainability of the project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/shandong-hai-river-basin-pollution-control-project-pcr
Taiyuan-Zhongwei Railway Project | China | Transport | 2014-06-01 | Although the final cost of the project was much higher than the appraisal estimate, the increase was largely due to the unrealistic cost estimate at the feasibility study stage, which is evident even when other factors, such as price increase of construction materials, modification to the original design, and the addition of facilities, are considered. The completion review noted that many cost items in the original estimate were based on outdated cost quotas that were far below market prices. This significant underestimation of the project's cost also affected the financial and economic evaluations made during project preparation. The component for institutional strengthening was not implemented. The main reason was the change in the operational arrangement for the railway. The executing agency was unable to identify alternative areas for institutional strengthening. This affected the realization of value addition of ADB's assistance. The executing agency needs to identify its priorities in the sector, as well as the project company that can benefit from the expertise of international or national consultants. The project budget did not include adequate resources for resettlement and social impact monitoring. This resulted in difficulties in complying with the requirements for timely monitoring reports and reports on the project's benefits and impact during the construction stage and after project completion. Although generally sound, the project framework and the project performance management system designed at appraisal contained some impractical indicators, and the information required to monitor their achievement was not available from the executing agency's normal reporting system. In addition, due to limited budget available, the project benefits and impacts were not reported adequately during implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/taiyuan-zhongwei-railway-project-pcr
Fuzhou Environmental Improvement Project | China | Water and other urban infrastructure and services | 2013-09-01 | 1. Project management and schedule. Urban development projects are inherently complex, involving various sectors and agencies, numerous infrastructure works, and significant safeguard impacts; thus they require tight coordination among all stakeholders. Considering the sector and institutional complexities, sufficient time should be allowed to scope, design, and implement urban projects. While the project management setup and implementation arrangements were generally relevant and effective, the interagency coordination necessary for the project was at times inadequate. In view of the rapid urban development in Fuzhou, which caused frequent changes in project design as well as land acquisition and resettlement difficulties, project implementation could have been improved if there had been adequate staff resources with a mixed skills set within the project coordination institutions, careful risk assessment and mitigation planning, and a more realistic implementation period. 2. Institutional arrangements. A careful institutional assessment and well-targeted capacity development program would help strengthen institutional capacity and promote sustainable management of urban services. There were discrepancies between the actual institutional arrangements and those stipulated in the loan and project agreements concerning responsibilities for investment and operations and maintenance in wastewater services and inland creek rehabilitation. These discrepancies made some of the loan covenants inoperable and caused the project's capacity building program to be mistargeted. Although institutional arrangements were realigned through a change in scope and implementation arrangements and subsequent amendments to the loan and project agreements, institutional strengthening objectives of the project were achieved to a lesser extent. 3. Resettlement. The rapid urbanization and transformation of cities in the PRC means that resettlement safeguards are a critical element of urban projects throughout project preparation and implementation. This is particularly complex in the eastern coastal cities, such as Fuzhou, that experienced unplanned housing development. While the rapid urbanization and a changing urban master plan were the primary reasons for implementation problems, the project was affected by consequential resettlement difficulties from which the following lessons can be drawn: (i) Project design and resettlement planning should be carefully sequenced with the government's development plan using a realistic implementation schedule. (ii) The government's land acquisition plan should be prepared well before project approval so that all preparatory administrative procedures are completed ahead of physical implementation of projects. (iii) Projects that are intermingled with domestically financed development projects should be avoided. Many cities have elaborate local land acquisition and resettlement regulations that often make it difficult for ADB projects to implement land acquisition and resettlement independently from the other development projects. In the case of Fuzhou, the ADB-financed project and the domestically financed projects affected the same villages, and this caused some confusion and dissatisfaction in the affected villages. (iv) Alternative design options to avoid or minimize house demolition and resettlement should be explored thoroughly during detailed design and project implementation, particularly if the project is located in a rapidly urbanizing area. In the Fuzhou project, design options were largely limited by technical parameters such as flood discharge flows and gradients. (v) Public announcement of the resettlement cutoff date and its notification to affected villagers should be supported by robust evidence of the established cutoff date such as unambiguous aerial photographs. Local authorities should also try to prevent people from building illegal structures and should rigorously enforce the cutoff date. (vi) Extra attention and resources should be allocated to projects involving displacement of unregistered or illegal properties. (vii) Sufficient budget and institutional coordination should be available to minimize the transition period between the completion of resettlement housing and demolition of structures, and relocation of affected persons to their new residences. (viii) Affected persons should not be displaced before they have signed compensation agreements. This was strictly applied in Fuzhou and is now a national regulation. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/fuzhou-environmental-improvement-project-pcr
Facility-Type Technical Assistance in the People's Republic of China | China | Multisector | 2013-04-26 | 1. Introducing facility-type TA in middle-income country contexts increases goodwill for the wider ADB country portfolio. In the PRC, the view of knowledge as a product, and the consciousness of the costs embedded in knowledge production, enhance the prospects for the further development. ADB should consider formalizing a discussion on knowledge products and services strategy in the annual country programming review exercises. However, success in introducing this facility in other developing member countries, including middle-income countries, would depend on government ownership, in-country institutional strengths, and capacity to manage. [Executive Summary, page v; Main text, para. 139] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Modality: Technical Assistance Capacity Development: Ownership Country Context: Middle Income Country 2. Improved quality assurance of facility-type TA projects is resource intensive, but a must for their success. Proper quality assurance imposes high demands on ADB staffing and time allocated to facility-type TA. Close involvement of ADB staff members is also needed to keep subprojects from degrading into routine activities of implementing agencies, and to preserve the merit base of consultant selection. Some of this quality assurance work could perhaps be funded through the TA itself, and done through international consultants kept on a retainer basis, and used on request for peer review. [Executive Summary, page v; Main text, para. 140] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Project Management: Consultants Capacity Development: Human resources management 3. Value addition by ADB on substantive issues is crucial to the eventual success of facility type TA operations. This starts with active ADB involvement in the screening of proposed subprojects and the appointment of senior ADB staff members as task managers who actively engage with implementing agencies during subproject implementation and are involved in the preparation of periodic sector and thematic assessments to build institutional knowledge. [Executive Summary, page v; Main text, para. 141] project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Project Design: Subprojects Capacity Development: Human resources management | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/facility-type-technical-assistance-people-s-republic-china
Dali-Lijiang Railway Project | China | Transport | 2013-03-06 | 1. Having sufficient consultation and participation with stakeholders helps to promote ownership and responsibility. During implementation, a great number of consultation meetings were conducted on the design, construction, safeguards, job opportunities, ethnic minority culture protection, gender, and social mpacts. These included hundreds of participants including representatives of local governments, nongovernment organizations, potential customers, ethnic minority groups, and women's federations at town, county, and city levels. Continued extensive consultations during project implementation promoted participants' sense of ownership and responsibility for the project, and helped to further improve the project design. project cycle stage: Lesson Topics: 2. There has been a continuing process of adaptation of the project to the latest construction and operation technology and more environmentally friendly solutions. This has demonstrated that such innovation and reform can improve cost effectiveness, efficiency, safety, and sustainability. project cycle stage: Lesson Topics: 3. The costs of construction materials were underestimated. The price for some construction materials, such as cement, steel, stone, and sand increased substantially during project construction. Although there was a price escalation clause in the contracts, price negotiations and contract variations and approval of the variations took considerable time and caused delay in the financial closure of the project. project cycle stage: Lesson Topics: 4. The traffic forecast at appraisal was optimistic regarding the first few years after project completion, particularly for freight traffic. Traffic increase assumptions should be carefully reviewed in future projects. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/dali-lijiang-railway-project-pcr
Fujian Soil Conservation and Rural Development II Project | China | Agriculture, Natural Resources, and Rural Development | 2013-03-06 | 1. Subproject selection criteria guided the selection, but the Fujian provincial government's active role in subproject selection contributed to the project's success. Most subprojects made significant progress during project implementation despite the global financial crisis in 2008. project cycle stage: Lesson Topics: 2. Private enterprises played an important role in advancing the agriculture sector through branding and marketing of farm produce, introducing quality standards and technology, investing to improve farm infrastructure, and providing extension services. Farmers also benefited from advice on agricultural inputs, credit services, and increased farm gate prices. project cycle stage: Lesson Topics: 3. The holistic approach for rural development was not sufficiently emphasized in the project document. The original project design involved a large number of subprojects across 50 counties. This may have overextended loan resources. Reduced and focused geographic coverage would have eased project management pressure at the provincial level and amplified the effect of this holistic approach. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/fujian-soil-conservation-and-rural-development-ii-project-pcr
Gansu Roads Development Project | China | Transport | 2013-03-06 | Roadside stations were introduced to promote community development along the local roads covered by the project by linking the roads with local community activities. However, in the current institutional arrangement, the Gansu Provincial Transportation Department (GPTD) does not have enough resources, including staff and funds, to operate the roadside stations. This brings their sustainability into question. Keeping in mind the poorly maintained and underused roadside station built under a previous donor-funded project in the project area, GPTD sought to design multipurpose roadside stations to be constructed and managed by the private sector. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/gansu-roads-development-project-pcr
Ningxia Roads Development Project | China | Transport | 2013-03-06 | 1. Careful and adequate analysis of properties of collapsible loess at project site is necessary, because different types of collapsible loess behave differently while some treatment methods are more effective than others for certain types of loess. project cycle stage: Lesson Topics: 2. For projects that encounter collapsible loess, sufficient budget should be allocated to design of foundation treatment and its construction, which is much more economical than to remedy deformation of road when inappropriately treated loess settles at a later stage. project cycle stage: Lesson Topics: 3. If possible, pavement layers should be constructed after one year or more of settlement of earthwork, depending on the type of treatment of collapsible loess. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/ningxia-roads-development-project-pcr
Sanjiang Plain Wetlands Protection Project | China | Agriculture, Natural Resources, and Rural Development | 2013-01-10 | 1. Performance targets and indicators for impact, outcome, and outputs should be realistic and measurable through local efforts, particularly when a target or an indicator has a global perspective. Baseline indicators and targets for project performance, including environmental management, should be developed during project preparation. project cycle stage: Lesson Topics: 2. Monitoring methods and frequencies need to be defined and agreed upon by the government and ADB at the beginning of a project, and followed during implementation by the executing or implementing agencies, to ensure the reliability and replicability of the monitoring data and the effectiveness of the project completion evaluation. project cycle stage: Lesson Topics: 3. To protect and restore wetlands, strong political support, including funding for nature reserves, is important. To disseminate lessons learned more widely and to help high-level decision making, executing agencies must publish policy briefs. project cycle stage: Lesson Topics: 4. The most successful elements of the project were those that had been discussed with the relevant authorities at an early stage so that plans developed under the project could feed into government plans. This provided a lasting and replicable impact from the project. Examples are the work with the water authorities on water allocation for the nature reserves, and the work with the tourism authorities on ecotourism development. project cycle stage: Lesson Topics: 5. The steering committee established under the project effectively acted as an inter-agency working committee, with authorization from and representation across various sectors such as land, water, fisheries, and agriculture to coordinate wetland protection efforts. To ensure coordination on inter-sector activities in future projects, such a committee or similar agency should be established before project start-up. project cycle stage: Lesson Topics: 6. The consulting services for project implementation designed during project preparation did not meet the needs during implementation. This usually happens because needs change over time. To avoid having to undertake contract variations to correct this balance, an approach used in European Union contracts would have allowed greater flexibility; bidders for consulting services are typically evaluated on a small number of long-term key experts; while short-term expertise is not defined in the bidding but decided upon during implementation based on agreed work plans and government demands. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/sanjiang-plain-wetlands-protection-project-peoples-republic-china-pcr
MFF: Guangdong Energy Efficiency and Environment Improvement Investment Program - Tranche 1 | China | Energy | 2013-01-08 | 1. The financial intermediary loan modality was adopted, and the loan proceeds were relent to support implementation of more energy saving and emission reduction projects. Separate evaluations of technical feasibility of the subprojects and the financial viability of the candidate subborrowers were conducted by the efficiency power plant project management office and Guangdong Finance Trust Company independently to ensure that the technical merits and financial status of each subproject were assessed. project cycle stage: Lesson Topics: 2. The actual energy savings achieved of the tranche 1 project are much higher than the anticipated energy savings at appraisal. More elaborate methods of energy saving estimates should have been used. The key is to establish an accurate baseline and design a customized measurement and verification method for verifying the energy savings achieved at the outset. It is also important to consistently use the same methodology for ex ante and ex post energy saving calculations. project cycle stage: Lesson Topics: 3. Measurement and verification. ADB Independent Evaluation Department's report noted that the Guangdong provincial government had incorporated appropriate measurement and verification (M&V) of energy savings for the multitranche financing facility investment program implementation. Third-party M&V agencies ensured fair assessment of achievements of energy savings and emission reduction. The measured and verified results of each subproject provided a solid basis for computing the energy efficiency benefits and achievement of the project. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/mff-guangdong-energy-efficiency-environment-improvement-investment-program-t1-pcr
Gansu Heihe Rural Hydropower Development Investment Program - Project 2: Dagushan Hydropower Project | China | Energy | 2013-01-04 | Strong government ownership is critical to the successful construction of the project and important to facilitate effective implementation and delivery of development results in ADB-financed projects. The Dagushan Hydropower Company (DHC) was consistently proactive and took initiative in solving problems, including the provision of design documents, timely delivery of equipment, approach to dealing with issues, and other areas. DHC's initiative guaranteed appropriate procedures and timely action for key tasks. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/gansu-heihe-rural-hydropower-development-investment-program-project-2-dagushan-hydropower-pcr
Peoples' Republic of China: Yellow River Flood Management (Sector) Project | China | Agriculture, Natural Resources, and Rural Development | 2012-12-27 | The requirement, under ADB's formula for sector lending, of early approval by all parties of a completed feasibility report for each ADB-supported subproject, has additional merit, at least in the People's Republic of China experience, of creating opportunity and incentive for perfecting design and introducing savings before actual implementation. [Main text, para. 27] project cycle stage: Design, Feasibility Lesson Topics: | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/peoples-republic-china-yellow-river-flood-management-sector-project
Coal Mine Methane Development Project | China | Energy | 2012-03-09 | 1. Major changes in scope were undertaken during implementation. The coal-bed methane/ coal mine methane (CBM/CMM) subproject was revised, two subprojects cancelled, and another two subprojects added, although these did not affect the project outcome. While minor changes in scope and implementation arrangements are inevitable during project implementation, major changes in project scope involve additional inputs and resources from both the government and ADB in undertaking due diligence. Prudent prescreening of subprojects is thus essential during loan processing, especially where the subproject (like the CBM/CMM Development Component) depends on contractual agreement with a third party. [Main text, para. 60] project cycle stage: Lesson Topics: 2. Deviations between the final project costs and the appraisal estimates were small. The results were achieved through coordinated efforts made by all parties involved in project implementation. Properly administered bidding processes were vital in obtaining advantageous bid offers. Proactive Project Management, both in equipment procurement and construction, enabled capital cost savings and ensured the quality of construction and equipment supply. The effectively adopted external supervision mechanism also played an important role in improving the quality of the project. The selection and hiring of competent international and national consultants ensured that the quality standards required for projects were met. [Main text, para. 61] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/coal-mine-methane-development-project-pcr
Heilongjiang Road Network Development Project | China | Transport | 2012-03-09 | 1. The use of available modern technologies to capture hazardous methane gas, when considered carefully and implemented properly, can produce attractive returns to project developers while addressing the issues of climate change, energy security, and safety of mine workers. The project also demonstrated the strong willingness of consumers to switch to cleaner energy sources once these are provided reliably and at affordable rates. [Main text, para. 48] project cycle stage: Lesson Topics: 2. The strong commitment and ownership of the project proponents is critical to the success of a demonstration project that uses the latest technologies for the first time in a country. Similarly, some flexibility in project design is needed to strengthen key aspects of the project. In this case, the drilling of 80 additional coal bed methane wells ensured methane gas supply to the power plant and other users, resulting in better-than-anticipated results. [Main text, para. 49] project cycle stage: Lesson Topics: 3. The project clearly demonstrated the ability of ADB to design and formulate projects even in a traditionally polluting industry such as coal mining to provide large greenhouse gas mitigation and environmental benefits and contribute to a shift in a country toward a cleaner and sustainable energy pathway. [Main text, para. 50] project cycle stage: Lesson Topics: 4. Changes in regulations not anticipated during project design and approval can adversely affect the project. Contingency provisions that will allow for such unanticipated changes during project implementation should have been considered during project planning and design. [Main text, para. 51] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/heilongjiang-road-network-development-project-pcr
Jilin Water Supply and Sewerage Development Project | China | Water and other urban infrastructure and services | 2012-03-09 | This project confirmed that the Heilongjiang Provincial Department of Transport (HPDT) has sufficient capacity to implement large-scale road construction projects to a high standard and in compliance with domestic and ADB's social and environmental safeguards. However, the HPDT is less prepared for piloting private sector participation in road operation and maintenance (O&M), and this capacity limitation was not fully addressed in the project design. The proposed concession mechanism for O&M of class I roads, where tolls provide the revenues to finance a concession for highway maintenance, remains a feasible option for improving road O&M arrangements in Heilongjiang and merits further policy dialogue with the provincial transport sector management. [Main text, para. 63] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/jilin-water-supply-and-sewerage-development-project-pcr
Liaoning Environmental Improvement Project | China | Energy | 2012-03-09 | 1. The project experience reinforces conclusions on water (and wastewater) tariffs in the ADB water operational policy. To raise tariffs to allow cost recovery is essential for financial sustainability. Since the water tariff adjustment follows official procedures and is beyond the water company's control, consumer groups and government officials should be made aware of the necessity of the tariff increases before they are imposed. Further, since the official procedures for approving tariff increases are long and complicated (public hearings are included), regulations should allow for an annual increase to cover actual cost increases, plus some allowance for capital cost, instead of significant increases in the tariff every several years. According to social surveys, if improved water supply can be provided throughout the day, beneficiaries are willing to pay higher water tariffs. [Main text, para. 58] project cycle stage: Lesson Topics: 2. Non-revenue water (NRW) management, corporate governance, and enterprise reform are long-term objectives of ADB's Water Operational Plan, and were also special features of the project. The application of these concepts is expected to go through a learning curve. The lessons learned during the project may be relevant in other, similar projects: (i) the NRW consultant should be involved in developing an action plan for the water company from the early stages of the project to have enough time to implement and adjust the plan for better results; and (ii) corporate governance and enterprise reforms should be given emphasis and should start when the project is first implemented. [Main text, para. 59] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/liaoning-environmental-improvement-project-pcr
Henan Wastewater Management and Water Supply Sector Project | China | Agriculture, Natural Resources, and Rural Development, Water and other urban infrastructure and services | 2012-01-08 | 1. At the beginning of project implementation, three local governments tried to adopt build-operate-transfer (BOT) modality and contracted private companies to construct the wastewater treatment plants (WWTPs). However, the local governments had inadequate capacity to conduct due diligence, and the contracted companies could not provide adequate counterpart financing. The unsuccessful introduction of BOT modality also showed that the capacity of individual WWTPs was too limited to ensure commercial viability. The BOT modality for WWTPs should have been carefully assessed during subproject appraisal. [Main text, para. 57] project cycle stage: Lesson Topics: 2. Self-supply groundwater wells have not been closed completely as envisaged at appraisal and still exist in Qingfeng and Puyang counties. As a result, the actual operational capacity of three water supply plant (WSP) subprojects is lower than designed. The self-supply groundwater wells also caused difficulties in collecting the wastewater tariff. Although the local and provincial governments subsidize water companies to guarantee operation of wastewater treatment plants and WSPs, the existence of self-supply groundwater wells has become a major constraint for water companies in achieving better financial performance and a viable water supply service in the longer term. Henan Provincial Government has considered the issues and will push ahead closure of groundwater wells effectively. [Main text, para. 58] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/henan-wastewater-management-and-water-supply-sector-project-pcr
Yichang-Wanzhou Railway Project | China | Transport | 2012-01-08 | 1. Three years after loan approval, the government made the decision to double track a section of the Yichang-Wanzhou Railway which connects to the subsequent ADB-financed Chongqing-Lichuang Railway. During project implementation, the Ministry of Railways made the investment to increase the capacity of the congested alternative railway routes, which changed some key assumptions made at appraisal. This highlights the importance of incorporating the overall planning of the sector into the appraisal of a specific project. Moreover, the actual freight traffic in the initial years of operation was significantly lower than the appraisal estimates. Similar to several other completed railway projects in the People's Republic of China, the appraisal estimates for freight traffic were overestimated, while passenger traffic was somewhat underestimated. This is mainly because local manufacturing and mining industries, as the main sources for generated freight traffic, take longer time to develop and adjust their shipping patterns. [Main text, para. 45] project cycle stage: Lesson Topics: 2. A few factors contributed to the success of the project in mitigating the diverse environmental impacts of the highly complex and challenging construction. A strong institutional establishment ensured effective implementation of the project environmental management plan. Sound environmental management practices were adopted throughout the Project Design, construction, and operation. For example, shock absorbers were installed on the Yichang Extra Large Bridge to minimize the vibration impacts of railway carriages on the aquatic habitats of the Chinese sturgeon. Long spans were adopted for bridges over the Yangtze River to minimize the number of piers, so that construction impacts were minimized. The design was also improved to control gas emissions by adopting solar or electric boilers at stations. [Main text, paras. 7, 46] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/yichang-wanzhou-railway-project-pcr
Hunan Roads Development II Project | China | Transport | 2012-01-06 | 1. The project expressway was implemented in an efficient and effective manner and was opened to traffic on 18 December 2008, which coincided with the completion date estimated at appraisal. The timely completion of the project was mainly due to early project preparation and readiness, including the completion of preliminary design in March 2003 and the detailed design in December 2003, as well as advance procurement of key civil work contracts and project implementation consultants. The achievement of key milestones of the project contributed to timely completion of the project expressway, despite some delays at the commencement stage. project cycle stage: Lesson Topics: 2. Based on the actual traffic recorded in 2009 and 2010, the traffic forecast at appraisal was unrealistically high for both the project expressway and parallel G319. The lower traffic and increased project cost have negatively impacted on the project financial reevaluation compared to appraisal. It is, therefore, suggested that a road traffic origin-destination survey be conducted in an appropriate manner, including timing and locations for survey, detailed information on the local and through traffic, accurate information on vehicle categories, and validation of traffic results. project cycle stage: Lesson Topics: 3. The project encountered common resettlement issues, and timely measures were taken: (i) early completion of the major land acquisition resettlement activities 1 year prior to the commencement of civil works allowed adequate time for resettlement implementation as well as completion of civil works; (ii) instead of concentrated resettlement sites, allocation of individual housing plots ensured that the affected households moved into new houses in a timely manner, but this approach has to be prudently decided upon based on the local context; (iii) a good relationship was built with the local communities through appropriate assistance in the improvement of local community facilities such as schools and access roads; and (iv) adverse impacts caused by construction activities should be identified during the project design stage. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/hunan-roads-development-ii-project-3
Gansu Heihe Rural Hydropower Development Investment Program: Erlongshan Hydropower Project | China | Energy | 2011-12-01 | The successful construction of the project resulted from the strong government ownership and provides a valuable lesson on the importance of this factor in facilitating effective implementation and delivery of development results in ADB-financed projects. The Erlongshan Hydropower Company (EHC) always took the initiative in solving problems, including in the provision of design documents, timely delivery of equipment, approach to dealing with issues, and other areas. The owner's initiative guaranteed appropriate procedures and timely action on key tasks and when problems arose. The external supervising mechanism was also effective and played an important role in improving the quality of the project. The selection and hiring of competent international and national consultants ensured that the quality standards required for the project were observed. Procurement. Properly administered bidding processes were vital to obtaining cost- effective bid offers. Strict adherence to such processes, both in equipment procurement and onsite construction, facilitated savings on capital costs and ensured quality construction and equipment. The engagement of an experienced procurement agent proved to be a key factor in facilitating efficient procurement. Counterpart financing. The project funds comprised international funds and domestic funds. For smooth project implementation, the timely availability of counterpart funds is a key issue. For the project, the actual ADB financing was $22.0 million and the counterpart funds mobilized from stockholders and local banks was $35.9 million, all of which was provided in a timely manner that ensured smooth project implementation and early project commissioning. Carbon revenue. The project was successfully registered as a clean development mechanism (CDM) project and was able to source significant amounts of revenue from the sale of carbon credits, thereby making it financially viable. This offers valuable lessons as a successful demonstration project for other clean energy developers in the region. Social development. The project has contributed to regional sustainable socioeconomic development, poverty reduction, and community development in the project area. The good practices of the project include (i) the formulation and implementation of the community development plan, which greatly promoted the development of local communities and enabled the local people to enjoy the benefits from the project in harmony with their traditional values and customs; and (ii) the great importance given to social issues by the Erlongshan Hydropower Project (EHP) throughout project implementation and subsequent operation of project works to strengthen its relationship with local communities. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/gansu-heihe-rural-hydropower-development-investment-program-erlongshan-hydropower
Guangxi Roads Development II Project | China | Transport | 2011-12-01 | The difficulties encountered in implementing the intercounty road were attributed to the low capacity of local counties in project implementation. The officers in the Baise Communications Bureau and Baise Highway Administration Bureau had no experience in implementing multilateral development bank-financed projects, particularly in procurement, disbursement, and project management. The lesson is that proactive efforts and timely actions should be undertaken to build the capacity of officers in local counties when they are responsible for local road components. These efforts could include (i) conducting pre-project implementation training for the relevant officers on ADB's procurement guidelines, disbursement procedures, and safeguards policies; (ii) providing on-the-job training to the implementation team on procurement, disbursement, and contract management; and (iii) conducting frequent review of local roads implementation to identify potential problems at an early stage and then take timely action to resolve issues. In addition, frequent communication with project management offices is crucial to ensure that local roads construction is completed according to the plan and implementation schedule. The other lesson learned from the project is that the award of contracts to low price bidders can result in contract management difficulties and implementation delays. To win a contract, the bidders, who are not familiar with Fe?de?ration internationale des inge?nieurs-conseils (FIDIC) contract and contract management in ADB-funded projects, offer low prices and take it for granted that the contract amount would be increased through contract variations during implementation. The low price bidders usually are not able to provide sufficient resources to implement the contract, thus resulting in slow progress in implementation. The incidence of offering low prices to bid for ADB-funded projects has decreased in recent years in the People's Republic of China (PRC), since contractors have become more familiar with contract management practice of the World Bank and ADB. However, at the county level, the problem is still widespread among local contractors. For future local roads bidding, a mandatory site visit could be arranged for all potential bidders before bidding documents are issued and a brief introduction to FIDIC contracts for the bidders could be carried out at that time. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/guangxi-roads-development-ii-project
Songhua River Flood Management Sector Project | China | Agriculture, natural resources and rural development | 2011-12-01 | Flood Management Related The project provides useful lessons on the process of changing institutional and policy making mindsets, in this specific instance in relation to flood management. Prior to the project, flooding was often perceived solely as an agent of damage and disruption to human settlement and socioeconomic activities, and even a cause of human casualties in the People's Republic of China (PRC). People, however, now realize that floods (in particular more frequent and smaller freshwater floods), sustain ecosystems and the services that ecosystems provide. The benefits of floods also include recharging ground water, maintaining river courses, making soil more fertile, purifying water, and sustaining natural habitats. The old belief that floods should be fought and controlled by construction of dams, dikes, and bypass channels was misleading. Furthermore, continuously strengthening and extending structural flood defenses is unsustainable economically, environmentally, and in terms of social equity. The flood management approach accepts that certain parts of the landscape will occasionally be flooded and seeks to reduce the ultimate cost to society. This includes taking measures to prevent floods from becoming disasters, anticipating worst-case scenarios, and identifying opportunities for conveying the resultant flood wave through the river system in a safe and largely predictable manner. The approach incorporates structural measures, but only as part of a larger strategy that includes: (i) flood proofing important structures and implementing land use controls; (ii) establishing flood forecasting, risk assessment, and warning systems; (iii) preparing emergency responses and flood recovery measures; and (iv) creating financial incentives such as flood insurance and eco-compensation. Risk assessment is essential for flood management, and the project significantly improved the Songliao Water Resources Commission's (SWRC) capacity for flood forecasting and risk assessment through the development of the Songhua River Basin Flood Management System. The concept of integrated water resource management and the river basin management approach were recognized and put into practice by the PRC as adaptive processes. The government took steps to achieve such change. The Songhua River Basin Flood Management Master Plan was prepared first, and then the Songhua River Basin Comprehensive Plan was formulated. In regard to policy implementation, the flood forecasting, risk assessment, and warning systems were completed first, and the actions on flood retention area and flood insurance development are still ongoing. The project advanced these reforms and helped to develop a new way of thinking about floods and their broader ecological significance in the Songhua River basin. The government agencies involved in the Songhua River basin have shifted their approach from only structural measures for flood control to a balanced approach using both structural and non- structural measures. However, there remains room for improvement in the development of different types of non-structural measures. In the next phase, basin flood management needs to evolve into integrated flood management, which not only aims to reduce the human and socioeconomic losses from flooding but also to increase the social, economic, and ecological benefits from floods and the use of floodplains. Project Management Related The lessons learned in project design and implementation include: (i) complicated implementation arrangements for future projects should be avoided to reduce challenges and increase efficiency in project implementation; (ii) domestic approval procedures and timelines for subprojects should be carefully reviewed and adequately factored into project schedules so that the schedules can be adhered to; and (iii) in addition to the training on consultant recruitment, ADB should also provide executing agencies (EAs) with adequate training in consulting service contract management to ensure cost effective and quality consulting services. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/songhua-river-flood-management-sector-project
Wuhan Wastewater Management | China | Water and other urban infrastructure and services | 2011-12-01 | Wastewater tariff. The required tariff was accurately estimated at appraisal and was made a loan covenant to assure the Wuhan Urban Drainage Development Company's (WUDDC) financial autonomy. During project implementation, the tariff was adjusted but was still insufficient to achieve the goal set for the WUDDC. The delay in the tariff increase was not only due to lack of support from relevant government agencies, but mainly because of the Wuhan municipal government's (WMG) concerns on social stabilities caused by inflation and overall prices increases in recent years. As the top concerns of the central and local governments, the governments in most cases subsidize wastewater treatment plants (WWTPs) from the government budget to ensure the operations of the WWTPs. The objective of a tariff increase has not yet been achieved to date, so there is a need to further strengthen policy dialogue on the tariff increases for the future achievement of full cost recovery for wastewater services. Land acquisition and resettlement. Because of land use changes in updated urban development programs, the Luobuzui WWTP was relocated after the issuance of the land-use permit. Resettlement impacts were consequently different from those anticipated in the resettlement plans, and identification of a new WWTP site caused implementation delays and difficulties. The change mandated the adaptation of the associated wastewater collection system, which made resettlement more difficult. To ensure smooth project implementation, such changes should be anticipated during project preparation or recognized at an earlier stage of implementation. Schedule for implementation and financing. The WMG should have increased the wastewater tariff to raise the required funding instead of requiring the WUDDC to borrow more from domestic banks. The WUDDCï¿½s audited financial reports indicate that its short-term indebtedness is much higher than the typical for such an enterprise. The more timely reallocation of unused loan proceeds could have achieved full utilization of the loan proceeds including savings on interest during construction. The finance department of the WUDDC should have monitored and controlled the implementation schedule and financing plan to minimize commitment charges. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/wuhan-wastewater-management
Xi'an Urban Transport Project | China | Transport | 2011-12-01 | For the third ring road (TRR), there were several variations caused by design changes or differences between the engineering designs and actual field conditions, which included (i) addition of a pump station to the subgrade package due to an exceptional design change, (ii) rapid expansion of the urban areas, (iii) inaccurate preliminary design and engineering designs, (iv) emerging urban infrastructure demands during project construction. A more accurate detailed design based on a well-coordinated inter-agency strategy would have helped to avoid unexpected variations as well as increased resettlement costs. Better preparation and coordination would have been of great value to the design of interchanges, grade separations, pedestrian bridges, and traffic safety measures along the TRR and its connector roads. The project consisted of several components implemented or administered by various agencies. Xi'an Municipal Urban and Rural Construction Commission (XMURCC), Xi'an Third Ring Road Construction and Development Company (XTRRCDC), and the government offices concerned made enormous efforts in coordinating and harmonizing project implementation activities, particularly in obtaining necessary government clearances during procurement and operation. A streamlined institutional arrangement will ensure a solid foundation for smooth project implementation. Further, complicated domestic processing requirements related to equipment procurement it took a long time to obtain domestic clearances from the agencies involved before submission to ADB for review and approval caused delays. The government needs to simplify cumbersome domestic procedures to speed up project implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/xian-urban-transport-project
People's Republic of China: Capacity Building to Combat Land Degradation Project | China | Agriculture, Natural Resources, and Rural Development | 2011-11-30 | 1. It is important to establish not just a properly functioning monitoring and evaluation (M&E) system but a monitoring system that enables measurement of global environmental impacts. Without such an M&E system, it will not be possible to verify the impact of PRCï¿½GEF partnership interventions with respect to combating land degradation, reducing poverty, and conserving biodiversity. [Main text, para. 20] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design 2. Technical assistance (TA) activities that are well integrated into the overall project can result in more effective provision of guidance to achieve project outputs. This reiterates the importance of effectively timing TA interventions when supporting investment projects so as to maximize value addition. In the case of the Capacity Building to Combat Land Degradation Project in the People's Republic of China, the TA played a catalytic role in strengthening interagency and multisector cooperation and collaboration for integrated ecosystem management (IEM), including the collection and sharing of IEM-related data and information among policy decision makers, legislators, planners, private sector, and communities. The consultants served as lead resource persons and technical support in (i) various training activities, (ii) completion of IEM strategies and action plans, (iii) formulation and revision of 33 local laws and regulations, and (iv) implementation of 18 pilot sites. [Main text, para. 21] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Technical Assistance Project Design: Project design | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/peoples-republic-china-capacity-building-combat-land-degradation-project
Southern Sichuan Roads Development Project | China | Transport | 2011-10-01 | As a pioneer in Sichuan Province in applying software to manage road projects, Sichuan Panxi Expressway Company Limited (SPECL) developed a construction management and administration system as the main tool managing major project implementation activities. Under the system, tripartite management of project fund application, disbursement, and supervision was established between the employer, contractors, and the local commercial bank. With the assistance of the system, SPECL could remotely supervise the implementation progress of each package in terms of quality control, adherence to schedule, and accuracy in cost control. Meanwhile, SPECL could administer and monitor the status of disbursed funds flowing between the bank and the contractor to ensure the disbursed funds were utilized for the intended purpose. The system is now being replicated and applied in other domestically financed road projects in Sichuan Province. The project cost amounted to CNY7.162 billion, which is CNY1.272 billion less than the CNY8.434 billion approved at appraisal. Project contract management was effective and efficient, focusing on key contract items including key personnel, equipment, scheduling, construction quality, safety, environmental protection, and avoiding corruption. Accumulated knowledge and experience were shared and disseminated. SPECL dispatched regular and special inspection missions during construction and issued orders, regulations, and special notices to contractors as needed. Contractors strictly followed the contract, mobilizing and fielding competent and diligent project managers responsible for implementation. Under a strict contract management system, contractors and national supervision engineers performed as required and stipulated in contracts, which ensured satisfactory outputs. As the first mountain-traversing expressway in Sichuan Province, the project expressway crossed geo-technically difficult and complicated terrain. To cope with various technical difficulties and challenges, Sichuan Provincial Transportation Department (SPTD) and SPECL initiated 14 technical studies associated with the project expressway's construction. Of the 14 studies, two were awarded state patents and eight were acknowledged as achievements at the provincial and ministry level. The application of these technical research products in the project expressway's construction generated significant social and economic benefits. For example, technical innovations in the study of road construction on Xigeda stratum has been widely used in constructing other road projects, allowing significant cost savings. Other ongoing road projects also benefitted from these studies. The initiation and wide application of the knowledge products are commendable. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/southern-sichuan-roads-development-project
Western Yunnan Roads Development Project | China | Transport | 2011-01-02 | 1. Proactively treating geological hazards before cutting and excavating the earthworks proved to be more effective and cost-efficient than reactively handling the issue when excavation had been completed. project cycle stage: Lesson Topics: 2. Plantation and landscaping work for slope protection immediately taken after earth excavation proved to be an effective practice to ensure water conservation and environment protection. project cycle stage: Lesson Topics: 3. The 11 escape ramps built by the project to deal with the over 30 km of continuous decline of the expressway proved to be an effective safety feature. project cycle stage: Lesson Topics: 4. To effectively utilize consulting services, a clear and specific terms of reference for each consultant needs to be prepared with the expected outputs before consultants' mobilization to the project. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/western-yunnan-roads-development-project
People's Republic of China: Harbin Water Supply Project [Loan 1995-PRC] | China | Water and other urban infrastructure and services | 2010-12-31 | 1. The commitment shown by ADB and the municipal government was fundamental to the project s success. Careful assessment and project design during loan processing, detailed procurement and implementation planning, and timely availability of counterpart funding and decision making ensured smooth implementation and commissioning of the project about one year ahead of schedule. [Main text, paras. 67-68, 72] project cycle stage: Design, Implementation, Operation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Appraisal Project Design: Project design Project Management: Procurement 2. The government recognizes that water resource problems in the People s Republic of China (PRC) are related to various economic, technical, regulatory, and other developmental issues, and that an integrated and comprehensive approach is required to ensure that adequate volumes of water of requisite quality are available on a sustained basis. Such an integrated approach includes protection of upstream water sources, watersheds, rivers and other water bodies, and includes but is not limited to (i) alleviating risk of pollutant contamination from point and non-point sources of pollution; (ii) treating wastewater before discharge into such water bodies; (iii) monitoring and analyzing water quality; (iv) developing alternative sources of water supply; (v) setting up an institutional framework and strengthening the institutions; and (vi) establishing a regulatory framework that provides the right incentives for implementation of such measures. The success achieved by the project and the progress made so far in improving the Songhua River s water quality attests to the benefits of such a comprehensive approach. [Main text, paras. 30,73] project cycle stage: Design, Implementation Lesson Topics: Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach 3. While price setting in a tightly regulated market is often an act of balancing a large number of concerns, it is important to give due consideration to the long-term sustainability of the water utility, including investment in its modernization and expansion. If tariff income falls short of requirements (assuming normative operational efficiencies), government support is required. However, as ADB may not be in a position to influence water tariff levels and structures, ADB should review the merits of including tariff setting-related covenants in the loan and project agreements, or seeking assurances on this matter. [Main text, paras. 53,74] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Sector Related Issues: Water resource management 4. Project covenants affected by institutional changes need to be closely attended to, especially if these are crucial to the attainment of project outcomes. The project design was based on the premise of achieving full cost recovery and this was reflected, among others, on the project financial covenant on water pricing. However, the institutional set-up of the Harbin s water sector has changed since the project s appraisal which made the financial covenant difficult to meet. Certain project covenants could have been revised to ensure that the Harbin municipal government can continue to follow up on some aspects of water pricing. [Main text, paras. 71,75] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Loan Agreement: Covenants Sector Related Issues: Water resource management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/peoples-republic-china-harbin-water-supply-project-loan-1995-prc
People's Republic of China: Tianjin Wastewater Treatment and Water Resources Protection Project [Loan 1797-PRC] | China | Water and other urban infrastructure and services | 2010-12-31 | 1. Adequate consultation and better communication with affected people for projects experiencing resettlement issues can reduce implementation delays. Delays in the implementation of the resettlement subcomponent of this project could have been mitigated if lessons from past projects have been taken into account. These included executing and implementing agencies ensuring closer consultation and resettlement impact is better communicated with local officials, village committees and affected peoples, and proposing reasonable resettlement or fishpond removal scope and compensation policies. The villagers would then be able to better understand the objectives and importance of projects, and would be more receptive to the resultant land acquisition and resettlement activities. [Main text, paras. 77,84] project cycle stage: Design Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Methodologies/Approaches: Consultation/Participation 2. Further improving project sustainability requires the involvement of communities in environmental improvements. For similar projects, it would be helpful to have a community participation and self-management booklet prepared by villagers themselves under the guidance of the social specialist at the project preparatory or implementation stage. Significant environmental improvements, and ecological protection works are continuously being implemented by the Tianjin municipal government to further improve water quality. Environmental improvements have also been extended to 68 villages. While current assessment indicated a high sustainability rating for the project, further improvements can still be achieved through community participation and self-management since these are effective gateways into sustainable implementation and operation. [Main text, paras. 69,85] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation 3. Bringing in private sector experience yields efficiency in project operations.The eventual full participation of Tianjin Capital Environmental Protection Company (TCEPC) in component A was a good demonstration of private sector participation, particularly in bringing about the required expertise in running a wastewater treatment plant. Aside from the Beicang wastewater treatment plant, TCEPC is also responsible for the operations of three other large-scale wastewater treatment plants in Tianjin. Prospects of private sector participation in component B should have been explored with other private groups or entities, particularly in enhancing ecological works around the Yuqiao Reservoir, which is currently financed by municipal funds. This could be a showcase to invite interest from private enterprises, particularly in the growing concern for the environment. [Main text, paras. 14,86] project cycle stage: Implementation, Operation Lesson Topics: Sector Related Issues: Water resource management Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation 4. Complementarities of projects and donor coordination could improve operational efficiency. The full capacity of the wastewater treatment plant for this project has not yet been reached, pending the completion of the World Bank-funded sewerage system. Sewerage construction needs to be fully addressed in the early stage of the project, particularly as it affected the implementation of wastewater treatment operations. It is, thus, essential that when such interlinked projects are implemented by different funding institutions, inter-donor coordination needs to be ensured so that project operations and targeted completion are not compromised. [Main text, paras. 16,26,88] project cycle stage: Implementation, Completion Operation Lesson Topics: 5. A two-pronged approach focusing on developing institutions and training is needed to strengthen executing (EA) and implementing agencies (IAs) in the water supply sector. While various trainings were provided to these agencies, emphasis on developing the institutions, such as review of the overall organization structures and terms of reference of management and staff, would also be helpful in further strengthening EA and IAs (i.e., creation of the Tianjin Water Affairs Bureau, a first step in overseeing the continued development of water-related IAs, and commercialization of operations through the involvement of Tianjin Capital Environmental Protection Company). [Main text, paras. 28-29,89] project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Capacity development Sector Related Issues: Water resource management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/peoples-republic-china-tianjin-wastewater-treatment-and-water-resources-protection-project
Capacity Building to Combat Land Degradation Project | China | Agriculture, natural resources and rural development | 2010-12-01 | Acceptance and application of integrated ecosystem management (IEM). The IEM approach is highly relevant to combating land degradation in the People's Republic of China (PRC) and is a significant departure from traditional practices and therefore, requires time to become fully accepted. Good progress to date suggests that the full 10-year period, as originally designed, will be required. Moreover, with numerous central and provincial agencies involved in programs to combat land degradation and alleviate poverty, mainstreaming of the IEM concept and approach into central and provincial policies and plans requires sustained reinforcement to prevent stakeholders from reverting to agency-based approaches for combating land degradation. Integrated approach to achieving long-term success. International experience demonstrates that an integrated approach is appropriate to achieving long-term success in combating land degradation that is mostly caused by interacting socioeconomic factors (e.g., overexploitation of natural resources, poverty, and population pressure). Participatory and science-based IEM approaches are essential for successfully combating ecosystem degradation, including in dryland areas. IEM concepts and principles have been demonstrated to be effective in influencing the ways in which people use natural resources and how they benefit from viable ecosystems. IEM has also been effective in addressing the poverty-resource degradation cycle at the grassroots level, as it generates solutions from the stakeholders that are directly and most affected by land degradation. Institutional capacity building for establishing an enabling environment. For IEM to be effective and successful, cooperating and collaborating institutions and sectors must be supported by IEM knowledge and skills for policy making, planning, legislation, and joint management of the environment and natural resources. Joint and effective management of environmental and natural resources requires improving the capacities of cooperating and collaborating with government institutions for combining top-down and bottom-up approaches. The legitimacy of the joint management system within the provincial and autonomous regional government structure may be enhanced through the guidance and assistance of lead expert and advisory groups. The pool of experienced local experts trained by such groups, as well as the members of these groups, play an important role in providing guidance for future land degradation prevention and control in other provinces and autonomous regions. Interagency cooperation and collaboration in policy and planning. Improved institutional coordination and harmonization of land degradation policies, legislation, programs, and budgets is needed. Interagency cooperation and collaboration in policy and planning of IEM strategies and plans ensure that complex problems related to land degradation control are addressed following a participatory approach and that government agencies, private sector agencies, and local communities have a clear understanding of their delineated tasks and responsibilities. A consistent legislative, regulatory, and planning framework for land degradation control must likewise be created to ensure efficient coordination of land degradation prevention and control projects funded by various government and donor sources, and cost- effective use of funds. Importance of awareness building. Strong awareness among stakeholders, especially the public, on the state of the environment and natural resources is important for gaining support for government plans and strategies for land degradation control and for overall environmental and natural resource management in general. Disclosure of government plans for management, and conservation and protection provides a solid foundation for cooperation in planning and implementing IEM plans and strategies. Important decisions, plans, and proposed investment projects should be disclosed through public media for soliciting public opinion. Awareness building should be complemented by an effective information-sharing multimedia system. Importance of a database system and information-sharing mechanism. Clarification on the institutional role of each agency regarding IEM and land degradation control provides a clear basis for defining the type and level of data to be collected by each participating agency in the joint and collaborative management of environmental and natural resources. For information sharing to be effective and useful, the institutional value of data should be recognized and access to data should be made available for all government agencies in a timely and practical manner. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/capacity-building-combat-land-degradation-project
Efficient Utilization of Agricultural Wastes Project | China | Energy | 2010-12-01 | Simplify grant disbursement arrangements. The flow of Global Environment Facility (GEF) funds was slow and tedious and delayed implementation. This was due partly to the lack of an imprest account in the provinces. These disbursements arrangements need to be simple. The government has drawn lessons from the project and has now agreed to the establishment of imprest accounts in provincial departments of finance to receive grant funds directly from ADB. Such an arrangement is expected to accelerate the disbursement of the GEF grants in future GEF- cofinanced projects and ensure the effectiveness of the fund uses. Government ownership key. The project objectives were in line with the government's national policy on environmental improvement, renewable energy development, and poverty reduction in rural areas. The project activities were also well integrated with the existing institutional system, which involved rural energy offices and extension service stations in the counties and villages. The government demonstrated a strong ownership of and commitment to the project by increasing its counterpart contribution to the construction of infrastructure in the project area and the issuance of relevant laws and policies during project implementation, which made the project successful and sustainable. Training crucial to sustainability. A well-designed, well-executed capacity development program assures that a project will be sustainable and can be replicated. The sound planning of this project's training programs was one of the keys to its success. The training combined courses on biogas systems and agricultural production, giving farmers an opportunity to use new technology, knowledge, and ideas to improve their incomes and living standards. It was also broad and flexible, allowing the family members who are often the final users of the biogas to take part. This ensured that the type I and II systems would remain operational. The project also trained technicians in service centers and stations in the counties and villages, helped establish service networks in the project areas, and ensured the availability of maintenance services in rural areas. Providing training in the year after construction of the biogas digesters was also effective since this was when project farmers needed to learn about operation and maintenance (O&M) for their new equipment and how to make use of the slurry and sludge from the digesters in agricultural production. The project also established an institutional mechanism linking contractors with extension service stations and the farmers, which is critical in promoting further development of rural household biodigesters. The training program has created ripple effects in the participating provinces. The implementing agencies have started replicating the project's biodigester-cum-livelihood design and training in other areas, using the training materials and extension services established by the project. Climate and location important. Local weather conditions can affect the success of technology, as they did in the case of the type I system. The sustainability of type I systems, which include a greenhouse, could be marginal in Shanxi Province where the annual average temperature is low and they can only function properly for about half the year. The province's harsh weather also means that the greenhouses deteriorate faster and need more intensive maintenance. Understanding the geography of farmers' lives is also important in designing projects such as this. The systems were constructed on the farms and were usually far from farmers' houses. This limits the benefits of using the biogas to cooking one or two meals a day when farmers are at work in their fields. Due diligence critical before using new technology. The technical and economic viability of a new technology, such as the straw gasification technology in the project, must be examined carefully before its inclusion in a project. This is particularly important to poverty- focused projects as poor stakeholders would have less capacity in managing risks of project failure. The cancellation of type IV gasification plants at midterm review mission over the concerns about their technology immaturity and economic viability avoided project failure and was a sound decision. However, it also showed a lack of proper due diligence regarding these factors at the appraisal. The supplementary appendix A of the report and recommendation of the President (RRP) indicated that the technology was only beginning to be tried. The fixed bed gasifier had been installed only by one company and had not been widely adopted. The other equipment type, a fluidized bed gasifier, had not received certification from Chinese authorities at the time of the project appraisal. The project design was unclear about the type IV systems' implementation arrangements and investors. This was especially risky because the majority of the project beneficiaries were to be farmers with limited skills, and the beneficiaries and implementing officers would both need capacity development in basic biodigester construction and O&M. The type IV system technology would have been too complicated for farmers to operate and maintain. It might well have failed if the 28 units had been set up as planned. Enterprise ownership lacking. The lack of ownership and commitment on the part of the project enterprises to the preparation of the project design document (PDD) might cause the Clean Development Mechanism (CDM) pilot bundling project to fail. In the case of the pilot CDM project in Henan Province, the provincial government may need to change its role from direct involvement in the CDM project development to technical support. The government should also seek direct involvement by the enterprises to enhance their ownership and understanding of the CDM process. The enterprises considered carbon financing as an easily accessible fund and were not aware of the commitment and efforts that would be required from them to avail of the carbon credit. The absence of direct involvement in preparing the CDM pilot project and lack of full understanding of the process may lead to the failure of the pilot bundling project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/efficient-utilization-agricultural-wastes-project
Yellow River Flood Management (Sector) Project | China | Agriculture, Natural Resources, and Rural Development, Public Sector Management, Water and Other Urban Infrastructure and Services | 2010-12-01 | For the village flood protection component, local governments committed funding for constructing infrastructure and houses for poor people. However, their revenue fell with the abolition of taxes on agriculture. Local governments' capability to raise funds should have been carefully investigated, taking into account possible risks. As democratization develops in the People's Republic of China (PRC) and individual autonomy increases, the formulation and implementation of projects that require voluntary resettlement, such as the village flood protection component under this project, need careful consideration. The government's approval process and processing time should have been carefully assessed during project preparation and reflected in the project schedule. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/yellow-river-flood-management-sector-project
Hebei Province Wastewater Management Project | China | Water and other urban infrastructure and services | 2010-11-01 | Sludge treatment. Proper handling of sludge has been an issue for most wastewater treatment plants (WWTPs) operating in the People's Republic of China (PRC) since traditional landfill options have become problematic. The government and WWTPs must find alternative solutions for sludge treatment. More sustainable sludge treatment methodologies may need to be considered during project preparation. Tangshan and Baoding are piloting the composting of sludge for fertilizer; however, this solution may not be sustainable without clear safety measures, due to increasing health concerns. Sewer construction. For the Tangshan component, construction of a fully functioning sewer system should have been adequately addressed during the planning stage. The construction delay had a negative impact on the project. Technical preparation needs to be enhanced, as does overall coordination of project implementation among government agencies. Reclaimed water development. The government has not recognized the tariff issues related to recycled water, although 30% of treated wastewater is being recycled as of 30 June 2010. The government needs to streamline the tariff system for recycled water, including tariff setup, charging standards, and collection mechanisms. Land acquisitions and resettlement. Most of the compensation rates for resettlement were higher than those in the resettlement plans. However, according to the data provided by each municipal sewerage company (MSC), the total resettlement costs for permanent land acquisition, temporary land use, building demolition, and associated items on the ground were lower than those estimated in the resettlement plan. The huge reduction in the resettlement costs was the result of waivers or significant reduction of land taxes or administration fees, large-scale reduction of temporary land use, and avoidance of house demolition through the use of the pipe-jacking construction methods rather than open-cut sewer construction. Coordination among municipal governments to increase the compensation rate but reduce the overall resettlement cost is a good lesson learned. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/hebei-province-wastewater-management-project
People's Republic of China: Acid Rain Control and Environmental Improvement Project [Loan 1890-PRC] | China | Energy, Industry and Trade, Water and Other Urban Infrastructure and Services | 2010-09-30 | 1. The Anhui Provincial Government and ADB should ensure that the executing agency and/or project management office staff has the capacity to carry out the procurement in accordance with ADB guidelines before project procurement starts. This requirement should be made integral to the outputs of the project preparatory technical assistance and recorded in the report and recommendation of the President. [Main text, page 9, section E(ii.b)] project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement 2. ADB should obtain a stronger commitment from executing agencies to institutional strengthening and provide stronger monitoring and evaluation to meet that commitment. [Main text, page 9, section E(ii.b)] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Capacity Development: Ownership | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/peoples-republic-china-acid-rain-control-and-environmental-improvement-project-loan-1890-p
Shaanxi Roads Development Project | China | Transport | 2010-07-01 | Bidding of expressway civil works took place in early 2002 and the government approved the detailed design in mid-2002. Thus, among other factors, bidding which was not based on detailed design resulted in some significant variations for large structures with complicated geotechnical situations. Based on this experience and similar experience in other road projects, it would be appropriate to conduct in-depth detailed geotechnical investigations before finalizing bidding documents. The Ministry of Transportation (MOT) now requires that detailed designs are completed before procurement of expressway civil works. The cost estimate of the toll system was overestimated at appraisal, and the actual cost was about one-third the appraisal estimate. The main reasons for this difference include (i) the network-based toll system arrangement resulted in cancellation of unnecessary equipment; and (ii) the cost estimate was made in 2000 and procurement was conducted in 2004, during which time the availability of more advanced information technologies contributed to a lower and more competitive actual cost. Close follow-up on information technology development and the toll capacity demands means that a precise cost estimate of a toll system is now possible. During the project preparation stage, it was anticipated that the project expressway would generate significant local socioeconomic development impacts. The expressway served not only as an important section of the transport corridor, but also as a vital link between Weinan and Xi'an and other neighboring regions. With growing traffic volume, it was observed that toll collection capacities at some exits were limited, which periodically caused long queues. It is necessary to consider increasing toll collection capacity and efficiency by increasing the number of toll lanes and applying advanced technical measures. The inclusion of 70 additional local roads for improvement was proposed and approved during the later stages of the original project implementation. Local road improvement has produced very positive impacts. However, it led to loan extensions of about 3 years. An integrated approach to combining improvement of local roads and the project expressway during project processing would ensure a more effective and efficient outcome. The impacts of land acquisition and resettlement were not well estimated in the resettlement plan, which led to a 30% increase in the amount of land acquisition and a 187% increase in house demolition area. This was mainly due to impacts induced by connection roads and service stations, as well as temporary buildings that had not been included in the resettlement plan. The project was processed in early 2000, but updating the resettlement plan has since been made a standard requirement stipulated in loan covenants. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/shaanxi-roads-development-project
Harbin Water Supply Project | China | Water and other urban infrastructure and services | 2009-11-06 | 1. Fundamental to the Project's success were the commitment of both the Government and ADB. This ensured careful assessment and project design during loan processing, including cost estimates, financing plan, and clear and detailed procurement and implementation plans, which helped speed up project development. [Main text, para. 32, 33, 61] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Design: Project design Capacity Development: Ownership 2. Strengthening financial sustainability in the provision of clean, safe drinking water requires imposition of tariff levels that would recover costs fully or meet cash requirements in the near future, and eventually generate a reasonable return of equity over the life of the Project. If Harbin Water Supply and Drainage Group Co., Ltd. (HWSDGC) is not able to raise tariffs sufficiently to pay for full maintenance costs, it may cause the deterioration of the supplied water quality and service, which will reduce the project benefit. Failure to raise tariffs steadily to cost recovery levels is counterproductive unless a specific subsidy regime is put in place. During project processing and implementation, the Harbin municipal government (HMG) could have revised tariffs in phases to ensure consumer affordability and willingness to pay. As the required water tariff increase will likely evoke a negative consumer response, heightened awareness among consumers, consumer groups, and government officials on the importance of the tariff increase before its imposition would be beneficial. [Main text, paras. 21, 24, 40, 45, 56-58, 63] project cycle stage: Implementation Lesson Topics: Sector Related Issues: Water resource management Policy & Reform: Information dissemination/Public awareness | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/harbin-water-supply-project
Gansu Clean Energy Development Project: Project Completion Report | China | Energy | 2009-08-16 | 1. The successful project construction resulted from the high ownership of the project as promoted by the Government throughout the country. The Xiaogushan Hydropower Company (XHC) always took the initiative in solving problems in the provision of design documents, the timely delivery of equipment, the approach to dealing with accidents, and other areas. The owner's initiative guaranteed appropriate procedures and timely action. [Main text, paras. 24,42] project cycle stage: Design, Implementation Lesson Topics: 2. The external supervising mechanism, effectively adopted, played an important role in improving the quality of the project. The selection and hiring of competent international and national consultants ensured that the quality standards required for projects with high investment costs were observed. [Main text, paras. 20,43] project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project supervision 3. roperly administered bidding processes were vital in obtaining advantageous bid offers. Following these processes, both in equipment procurement and in site construction, enabled savings in capital cost and ensured the quality of construction and equipment supply. Deviations between the final project costs and the appraisal estimates were noted to be marginal. [Main text, paras. 10,11,19,44] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Procurement Project Management: Project management 4. For smooth project implementation, the required funds must be available on time. The availability of counterpart funds was a key issue, as the funds could not be secured until the project launching. ADB staff must carefully scrutinize counterpart fund arrangements and availability during project appraisal. [Main text, para. 45] project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Appraisal 5. Comprehensive training in ADB procedures and guidelines and project administration for the project management staff at the start of and during project implementation helped improve project performance. The Project Management, financial management, and performance management capacity of the implementing agency was strengthened through domestic training, overseas study tours, and consulting services. [Main text, paras. 9,16,46] project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Project administration Capacity Development: Capacity development 6. The delegation of project administration to the resident mission resulted in more efficient communications between the executing agency, the implementing agency, and ADB. Thereby, resolving more efficiently various implementation issues. The PRC resident mission, among others, provided clear guidance and action plans for resolving key issues in financial management, environment and resettlement monitoring, benefit monitoring, and reporting. [Main text, paras. 22,47] project cycle stage: Implementation Lesson Topics: Project Management: Project management Other: Resident Mission 7. Land acquisition and resettlement were generally implemented well. Besides cash compensation for grassland acquired for the project, the implementing agency has provided annual fodder subsidy to households that were seriously affected. The special subsidy has largely helped to mitigate the loss of fodder from the acquired land. This is good practice and can be applied in future projects where the situation is similar. However, an area that would require improvement is the adequate cost estimation of land acquisition and resettlement (including government fees and resettlement monitoring cost); hence, ensure sufficient budget allocation particularl for future projects. [Main text, paras. 34-35,48(i); Appendix 13] project cycle stage: Design, Implementation Lesson Topics: 8. The implementation of the community development plan has greatly promoted local community development and enabled the local people to share harmoniously in project benefits. The community development plan, implemented by Xiaogushan Hydropower Company (XHC) and the local governments, covered local roads improvement, education, health, religious protection, electricity supply, water supply, telecommunications, technical training, and job opportunities. The plan was drawn up during project preparation and the early stages of implementation to ensure the development of local communities in harmony with traditional values and customs. Such a plan may be needed in other similar projects in the PRC; in which case, it should be included in the project budget. [Main text, paras. 36-37,48; Appendix 14] project cycle stage: Design, Implementation Lesson Topics: 9. An effective regime of ecological management for areas with construction projects can contribute to successful implementation of conservation measures in project reservoir area. In this energy project, soil and water conservation measures were implemented effectively in the reservoir area. Five percent of hydropower company's annual tax payments to the municipal government (Zhangye) go into a special fund to be used to finance projects, and maintain and improve ecological functions in the reservoir area and the Qilian Mountain Nature Reserve. Projects were implemented jointly by the municipal forestry bureau and the local county or township government. The municipal financial bureau has issued financial management regulations specifically to manage the funds collected. A long-term project plan has also been prepared for the use of the special fund for works and projects in the reservoir protection area. Such institutional arrangements have provided a very effective financing instrument for the sustainable support of ecological conservation in the long run. [Main text, para. 48; Appendix 12, para. 12] project cycle stage: Design, Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/gansu-clean-energy-development-project
Shanxi Road Development II Project | China | Transport | 2008-08-28 | 1. Key lessons learned from the Project include the need for (i) timely government approval of preliminary design, procurement documents, and overseas training activities, (ii) improving government's traffic data information and management system; and (iii) more prior discussion to establish what authority will comply with loan covenants that are not directly related to the project company. Evaluation noted delays in approval of design, prequalification documents and trainee candidates; missing information on destination traffic and accident data; and noncompliance on the covenant on private sector financing. [Main text, paras. 19, 24, 46; Appendixes 13&15] project cycle stage: Design Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Management information system Project Management: Procurement Capacity Development: Capacity development Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Policy dialogue 2. In the future, more discussions should be held to identify the local road component of similar projects to ensure the local roads originally selected are implemented. In the case of this project, the government would have constructed the local roads with or without ADB assistance. Three of the original six roads selected at appraisal were built using other sources of financing. [Main text, para. 7, 46] project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Transport planning Methodologies/Approaches: Policy dialogue 3. Complementary interventions and partnerships in improving connectivity can further advance development outcomes. The integration of local roads to the expressway was able to maximize development impacts by further stimulating local economic transformations and social development. Local governments were also able to strengthen the development process spurred by the project by promoting the establishment of enterprises and by providing programs and funds to support technological services. [Main text, paras. 33, 39, 43-44, 47-48; Appendix 18] project cycle stage: Design Lesson Topics: Project Design: Project design Capacity Development: Partnerships Sector Related Issues: Roading Sector Related Issues: Rural development Sector Related Issues: Urban sector/development Methodologies/Approaches: Community approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/shanxi-road-development-ii-project
Country Assistance Program Evaluation for the People's Republic of China: Success Drives Demand for More Innovative and Responsive Services (2007) | China |  | 2007-04-30 | 1. The enhanced accountability resulting from beneficiaries being responsible forrepaying a portion or most of the loan has been a powerful instrument to ensure that a project is welldesigned and implemented. This might be the primary factor differentiating the PRC's strong projectperformance from other DMCs. In many other countries, repayment obligations are assumed by thecentral authorities, while the beneficiaries are at the local level. This separation of who benefits fromwho repays blurs the incentives for accountability. On the other hand, the beneficiary-must-payprinciple also restricts project selection by discouraging the use of loan financing for social andtargeted poverty programs where the beneficiaries are often too poor to assume repaymentobligations or are difficult to identify. A decade ago, the PRC's financial position and the difficulties incontrolling potential waste in external assistance meant that this external borrowing strategy was apractical position. However, the country's financial and monitoring systems are now more developed,and some flexibility in this regard would be appropriate for projects that offer the potential forparticularly innovative solutions to address social and poverty problems. project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial management Modality: Lending modality Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Education Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development 2. The ADB-People's Republic of China (PRC) partnership has the potential to determine the future path of regional cooperation and economic prosperity in Asia. Because of the rapid rise and size of its economy, the PRC presents a great opportunity for sustained growth and prosperity in Asia and throughout the world. Among others, the PRC provides a dynamic market, a new source of demand, foreign aid, investment, and a vehicle for skills and technology transfer. As an honest broker with a regional focus and expertise, ADB can support the PRC in continuing with a multilateral approach,which has served it well, while intensifying efforts in other areas of regional cooperation. In infrastructure, ADB can support the PRC's active participation to improve connectivity in Asia by investing in roads, railways, air transport, and gas and oil pipelines. In trade and investment, ADB can facilitate consolidating trade agreements (particularly free trade agreements), reduce nontariff measures, and improve trade in energy and commodities to harness neighbors' comparative advantages. In money and finance, ADB can help the PRC play a notable role in developing capital markets and financial institutions, undertake regional investments, and enhance exchange rate management. Finally, in terms of regional public goods, the PRC can be an active player in developing and financing programs to mitigate natural disasters and tackle crossborder issues, such as the spread of disease and environmental concerns. If ADB and the PRC work together to exploit synergies, the gains for the PRC and Asia would certainly be greater than otherwise. project cycle stage: Concept, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Regional cooperation Finance & Financial Aspects: Financing Finance & Financial Aspects: Foreign exchange Finance & Financial Aspects: Market analysis Country Context: Emergency Capacity Development: Technology/Technology transfer Sector Related Issues: Energy planning/management Sector Related Issues: Industry and Trade Sector Related Issues: Roading Sector Related Issues: Transport planning 3. While individually most projects and TAs are rated as successful or better, the efficiency of ADB'soperations has generated widespread concerns relating to cumbersome procedures, excessivedelays, and inadequate core project-related services. More systemic issues revolve around ADB'soperational reliance on consultants, with its frequently cited negative consequences. Reforms at the institutional level are needed to achieve fundamental changes. For this to happen, ADB must restructuremanagerial and staff incentives to be more responsive to client needs. Two observations are offered here. First, change will occur only if the system is under pressure to do so and the easiest way to make that happen isto move to a more radical model of decentralizing staff resources and authority to the field office.Placing more staff and authority closer to the client will generate strong momentum for moreresponsive services, and will cause ripple effects for change in the system. Second, incentives needto shift in favor of providing a more balanced mix of advisory and lending services. Promotion andgrading policies, which reward technical and advisory skills as much as processing and managerialexpertise, are vital to sending the right signals. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Project administration Capacity Development: Human resources management Country Context: Decentralization Other: Resident Mission Policy & Reform: Policy reforms/framework 4. Although the vast majority of the ADTAs are rated assatisfactory, many clients feel that this instrument is not being used to its full advantage. This isalso an ADB-wide concern. Important principles are involved here, not just procedural matters.One relates to whether ADB is willing to delegate implementation responsibility to the client. Thestrong sense from the CAPE is that the PRC has the capacity and commitment to take on thisresponsibility. Transferring responsibilities to the PRC does not mean that ADB would shirk itsresponsibilities in selecting topics for support, shaping the methodology, and selecting consultants.Rather, its role would be the same as for projects, which is advisory in some stages and clearancein others. Such approach may free off ADB staff resources, which could be deployed in projectsupervision or in any innovation initiatives and knowledge transfer. Second, the criteria for judgingthe success of ADTAs should be based more on its impact than the quality of the documents orthe completion of a forum. Having an exit plan might be another important consideration in ADTAstrategy. Moving toward a results-oriented assessment would shift incentives toward how tofollow-up on recommendations and beyond just completion of a polished written product. Thiswould require recalibrating expectations. Building capacity, providing new analytical insights, anddeveloping feasible reform options are inevitably high-risk activities with significant failure rates.However, such endeavors also offer potentially high rewards. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Crosscutting Issues/Themes: Managing for Development Results Modality: Technical Assistance Monitoring & Evaluation: Impact evaluation Project Management: Project administration Project Management: Project supervision Project Management: Risks/Risk management Capacity Development: Capacity building Country Context: Decentralization Policy & Reform: Reform Institutions that thrive on providing services to others are at risk if their clients change faster than they do. ADB has been sensitive to this concern in developing new lending vehicles and restructuring its operations to be more responsive to the PRC's needs. Nevertheless, ADB's systems have not evolved quickly enough to fit the PRC's circumstances. The country portfolio review (CPR)process and portfolio monitoring indicators are still based largely on the traditional project cycle rather than client service standards and achieving outcomes. The consultant-based operating system means that institutional knowledge on many issues is not retained or easily made available to other clients. Capacity gets substituted than built. Approval processes, which were fine when communications and sharing of information was slow and methodical, are no longer acceptable in a world where speed requires more delegation of authority downward. While specific actions in each of these areas can help, a culture change at the institutional level is needed for this to add up to something greater than the sum of the parts. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Lending modality Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Management: Consultants Project Management: Project administration Project Management: Risks/Risk management Capacity Development: Capacity development Country Context: Decentralization It must be recognized that if the government's strategy and policies seem to be working, ADB should draw on its comparative advantages and skill mix to develop programs and provide services where it can add the mostvalue within the government's framework. However, a delicate balance must be struck betweenrelying excessively on client preferences and providing alternative views and options that mightchallenge current thinking. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Project Design: Project design Capacity Development: Ownership Policy & Reform: Policy reforms/framework | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-peoples-republic-china-success-drives-demand-more
Shen-Da Power Transmission and Grid Rehabilitation Project | China |  | 2007-03-05 | 1. Designing and implementing projects in sectors that are undergoing major restructuring involves several uncertainties. These include policy and institutional uncertainties that cannot be fully foreseen at appraisal. To cope with these, close coordination between ADB, the Government, and the EA during project implementation are needed at the sector level, as opposed to the project level. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project management Policy & Reform: Policy reforms/framework 2. A well-designed project, an experienced EA with a strong sense of project ownership, and a committed project implementation office staff is a formula for success. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Ownership 3. Projects in a sector that is undergoing structural reforms require some flexibility in loan covenants to ensure that they remain practical and relevant. In the project, the EA saw its asset base and business scope reduced significantly, yet the original financial covenants remained in place. This led to an unrealistic assessment of compliance with the loan covenants. project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management 4. A practical approach should be adopted when formulating covenants. Some difficulties were noticed in two covenants in the project. First, the time-bound tariff action plan is a sector, rather than a project, issue. Second, the required household level of efficiency improvement was beyond the mandate of a grid company, given ongoing structural reforms. project cycle stage: Design Lesson Topics: Loan Agreement: Covenants Project Design: Project design 5. The project provides a good example of land acquisition and resettlement plan (LARP) implementation at geographically dispersed project sites. However, the amount of permanent land acquisition more than doubled from the appraisal estimate., with a proportionate increase in the cost. This suggests, that, because of the preliminary nature of the project design that was available at appraisal, there should have been a larger contingency built into the LARP budget. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/shen-da-power-transmission-and-grid-rehabilitation-project
Technical Assistance Performance Evaluation Report for Selected Technical Assistance Projects in Public Administration in the People's Republic of China | China | Public Sector Management | 2006-12-31 | Given the scale of in-service training and the financial limitations of the technical assistance (TA) Modality, TA support should focus on strategic interventions including new approaches such as the use of distance education methods to in-service training. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Technical assistance (TA) can provide effective support for capacity development if appropriately designed toward realizable outcomes and output levels. Consideration should be given to ensuring that draft TAs are translated into the national language such that goals, timing and implementation arrangements are shared. The design and monitoring framework is a tool for gaining clarity about development issues and proposed solutions as outlined in the scope, assumptions, risks, and implementation timeframe of the TA. The design and monitoring framework should be used as intended in the design of the TA, rather than as a matrix to be completed when preparing the TA report. project cycle stage: Design Lesson Topics: The following features are common to highly successful TA implementation: (i) realistic design and relevant risks identified, (ii) active involvement of the executing agency from start of the TA to implementation and evaluation of the TA results, (iii) consultants who are respected for both their technical knowledge and their style, and (iv) training manuals provided in formats that encourage updating and revision. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Institutional analysis Policy & Reform: Public sector reform The Peoples Republic of China (PRC) has adopted some innovative approaches to managing procurement, including the creation of tendering agencies and one-stop procurement and contracting trading centers (tangible markets). ADB should make more of an effort to facilitate the transfer of successful PRC practices to other countries in transition from planned to market economies and for fragile states where government capacity is limited. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Procurement Capacity Development: Capacity development | Technical Assistance Performance Evaluation (TPER) | Highly successful | http://www.adb.org/documents/technical-assistance-performance-evaluation-report-selected-technical-assistance-prc
Shanxi Environment Improvement Project | China | Water and other urban infrastructure and services | 2006-09-15 | 1. A key factor in the success of the project was the strong commitment of the project proponents. All concerned parties demonstrated ownership of the project. Through the dedication of the executing agency, the local governments, and the three project implementing agencies (PIAs) to achieving target outputs, the implementation met project objectives with close adherence to guidelines and procedures. Project implementation was undertaken through effective supervision, monitoring, and cost control. [Main text, paras. 40, 60] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Ownership Country Context: Decentralization Methodologies/Approaches: Targeting 2. Adequate planning and preparation are key elements of the smooth and timely execution of a project. Timely availability of the required funds is also important. The project experienced delays mainly due to problems arranging local financing (withdrawal of funding commitment by domestic banks delayed the approval of the project feasibility reports, and extended loan signing and effectiveness), change in scope (reallocation of loan funds since some infrastructures became unnecessary), and contract administration (delayed contract awarding). [Main text, paras. 12, 23-26, 61] project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design 3. Responsiveness to significant changes in prevailing parameters could improve project design and benefits. Although the original design did consider the more efficient heat source, it was not firmed up at the time of formulation. The appropriate changes were made when the opportunity presented itself. [Main text, para. 16, 62] project cycle stage: Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Energy planning/management 4. A properly administered bidding process, supported by detailed technical design and bid specifications, can generate advantageous bids. Selection and recruitment of competent international and national consultants have ensured quality standards. [Main text, paras. 12, 38, 63] project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/shanxi-environment-improvement-project
Shanxi Road Development Project | China |  | 2006-09-15 | For efficient Project Performance Management System (PPMS) data collection and analysis, it is crucial to involve national consultants in addition to international expertise. During both the project processing stage and the inception stage, in-depth discussions of the PPMS should be conducted to ensure that the PPMS serves its intended purpose. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Project Management: Consultants Methodologies/Approaches: Targeting In order to comply with ADB's resettlement policies, the executing and implementing agencies should demonstrate that implemented compensation standards for cultivated land are based on the actual annual average output value of the land in the 3 years before land acquisition. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Executing/Implementing agencies Project administration arrangements, such as, the team leader in place during project processing continues to administer the project for at least 1 year, and if a successor is needed, he or she is selected from the project team - which can direct on time information flow amidst major scope changes, need to be applied. During administration of this project, ADB detected a major scope change - the design change from four-lane highway to six-lane highway - only in the latter stages of expressway construction. The executing agency should have reported the design change in accordance with the Project Agreement. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Sector Related Issues: Roading Resettlement monitoring reports should include more data, including data on resettlement organizations, compensation standards, factory and institution resettlement, and infrastructure restoration. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Since resettlement plans are used as the main guiding documents for actual land acquisition and resettlement activities, resettlement plans based on preliminary design should be revised upon completion of the detailed design of the civil works. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/shanxi-road-development-project
Shenmu-Yanan Railway Project | China | Transport | 2006-08-15 | 1. Though not funded by the project, link roads were a very important related facility. They were not clearly defined in a manner that allowed road development to be monitored, however. The specific locations and end points should have been specified in detail at appraisal to allow the construction and finalization of all roads to be monitored and evaluated during implementation and at project completion. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Sector Related Issues: Roading 2. The selection process for domestic consultants to monitor land acquisition and resettlement should ensure that the selected consultants have sufficient experience and clearly understand their role and reporting requirements. The issues concerning resettlement found at completion might have been alleviated, had a more experienced and thorough consultant been engaged. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants As with past ADB railway projects in the PRC, the appraisal estimates for freight traffic were somewhat high. Appraisal passenger traffic estimates were also considerably higher than the traffic now being realized. In both cases, the actual traffic would be considerably higher with the allocation by the Ministry of Railways (MOR) of additional wagons and passenger cars. With respect to land acquisition and resettlement, estimates at appraisal (land taken, persons affected and houses demolished) were considerably lower than the actual figures. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Market analysis Project Design: Appraisal Sector Related Issues: Transport planning The ADB loan was repaid in full by the EA in 2003, as the cost of the ADB loan was much higher than the interest rates prevailing in the market at that time. After the repayment of the loan the EA had no communication with ADB until the fielding of the consultation mission in October 2005. When a loan is repaid in full, ADB's ability to gain compliance with covenants, such as timely submission of the EA's PCR, is compromised. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Management: Executing/Implementing agencies Project Management: Project reporting Project Management: Project supervision | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/shenmu-yanan-railway-project
Fangcheng Port Project in the People's Republic of China (Loan 1427-PRC) | China | Transport | 2006-03-31 | 1. The project experience points to a need to improve traffic demand forecasts for expressways. While the total number of vehicles on the expressway is not far from that expected, the mix of vehicle types is. In particular, the growth in truck traffic and the expressway s ability to attract cargo from the railway, was overestimated. Perhaps fortuitously, urban development and growing affluence near the port has stimulated a compensatory, but unexpected, growth in light vehicle traffic. The Project s preparation is not unique in incorrectly estimating traffic growth as shown by a number of recent project completion reports for other ADB-financed expressway projects. [Main text, paras. 35-39, 79] project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Sector Related Issues: Roading Sector Related Issues: Transport planning 2. ADB should take greater care to store baseline information and records so that these can be used for project reviews at a later date. ADB has not been very careful in storing records concerning the project as reports or materials, which were the basis of traffic projections and calculations of economic and financial rates of return, could not be found. [Main text, paras. 61, 74, 80] project cycle stage: Feasibility, Implementation, Completion Operation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Post-evaluation Project Management: Project reporting | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/fangcheng-port-project-peoples-republic-china-loan-1427-prc
Southern Yunnan Road Development Project | China | Transport | 2006-02-15 | 1. There needs to be adequate and timely funding for resettlement and closer supervision, earlier identification, and resolution by ADB of potential resettlement issues. A main concern in the implementation of resettlement in the Southern Yunnan Road Development Project was the lack of funding, which delayed compensation payments. Compensation was paid in a timely manner for house demolition and reconstruction, but payments for land losses were delayed by 1 to 2 years. [Main text, paras. 46, 51(i)] project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Project Design: Project design A basic monitoring framework needs to be formulated and baseline values for the indicators established, where available, during project preparation and updated at project inception. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design There needs to be sufficient geological investigations for projects that are in difficult, mountainous terrain to ensure more accurate assessments of designs and costs. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Sector Related Issues: Roading Traffic projections for the initial years of operation need to be more conservative. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/southern-yunnan-road-development-project
Anhui Environmental Improvement Project for Municipal Wastewater Treatment and for Industrial Pollution Abatement in the People's Republic of China (Loans 1490/1491-PRC) | China | Water and Other Urban Infrastructure and Services | 2005-12-31 | At the program (strategic level), achieving the synergy between environmental benefits and financial benefits is the best possible scenario, as the latter is the basis for sustainable achievement of the former. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental benefits Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial benefits At the project level, the project preparatory technical assistance (TAs) had little impact on the actual design of the project due to a series of reasons including poor timing of the TAs and cost considerations. ADB needs to reassess its project preparatory TA program in the People's Republic of China (PRC). project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Project Design: Project design The project implementing agency (PIA) should not be forced to choose between environmental benefits or financial benefits. Improvement of technologies or processes is often more economical than adopting end-of-pipe treatment in pollution abatement. ADB s policy of not supporting industrial efficiency improvement projects at the time of appraisal imposed a great deal of pressure on the appraisal team to justify the project on its environmental merits. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental benefits Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial benefits Project Design: Appraisal Project Design: Project design | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/anhui-environmental-improvement-project-municipal-wastewater-treatment-and-industrial-poll
Hunan Lingjintan Hydropower Project in the People's Republic of China (Loan 1318-PRC) | China | Energy | 2005-12-31 | At appraisal, ADB should emphasize the need for the executing agency and implementing agency to cooperate with ADB in preparing the project completion reports and project evaluation reports. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Project reporting Major changes in contracts, and particularly costly additions should be evaluated in terms of the overall economics of the project, as well as the technical merits. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project administration Project Management: Project management More diligence in establishing prequalification criteria and evaluating prequalification submissions should improve the likelihood of success of a project. project cycle stage: Appraisal Lesson Topics: Of prime importance in water resource projects is expert review of hydrology. project cycle stage: Feasibility Lesson Topics: The ADB project staff should obtain data from the executing agency and implementing agency immediately after the project and before loan closure. This would ensure the availability of accurate and reliable information, and make use of the institutional memory of staff who were responsible for project implementation. project cycle stage: Completion Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management The common practice in the People's Republic of China (PRC), and at times in other developing countries, of restructuring government and executing agencies during implementation and operation should be anticipated during appraisal so that lengthy deliberations are avoided and separate evaluations of the capabilities of the new entities, and subsequent modifications of loan and project documents, would not be necessary. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Executing/Implementing agencies Policy & Reform: Public sector reform Using ADB's international bidding procedures, and an experienced executing agency and consultants, was important, and deputizing procurement specialists who were familiar with ADB's procurement guidelines was useful in preparing and implementing a successful project in a developing country. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/hunan-lingjintan-hydropower-project-peoples-republic-china-loan-1318-prc
Suzhou Creek Rehabilitation Project | China |  | 2005-09-15 | Strong capacity to implement resettlement activities was essential for smooth implementation of the large-scale urban resettlement activities under the project. Clearly defined functions and responsibilities of the Project Preparation Department established within the executing agency and resettlement companies ensured close coordination between resettlement activities and construction activities to prevent delays and maintain orderly relocation. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation The executing agency actively utilized the ability of the private sector in project implementation and management. Tendering companies were engaged to manage tendering works, resettlement activities were coordinated and managed by resettlement companies, and operations of some of the facilities improved and/or constructed under the project were contracted out. This approach was effective for such a large, complicated, and multifaceted project. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Procurement Project Management: Project management Sector Related Issues: Private sector The government's strong political commitment and management capability was key to the success of the project. As the project focused on comprehensive environmental rehabilitation and comprised many components, strong leadership to bring in all related agencies of the government (Shanghai Municipal Government) was required throughout the planning and implementation of the project. To exercise its leadership, the government carefully designed and established project implementation arrangements to allow it to coordinate related agencies effectively, provide guidance at the highest level when necessary, keep to schedules, and adhere to procedures. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Project Management: Project management Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Wastewater projects in the future should exercise caution in estimating revenues derived from water supply sales and forecasts. Where possible, price elasticity of demand should be explicitly considered or only growth from increased coverage should be incorporated. In this project, estimates of wastewater revenues were overstated because the volume of water sold was overestimated. This is a recurring problem in similar projects in the PRC particularly where the water and/or wastewater tariff has increased substantially. On the other hand, this is a successful case of water conservation through the introduction of a market mechanism. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial analysis Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/suzhou-creek-rehabilitation-project
Guizhou Shuibai Railway Project | China |  | 2005-08-15 | As with past ADB railway projects in the PRC, the appraisal projections for freight traffic in the project area were unrealistically high and, conversely, the passenger traffic projections were extremely low and have already been significantly exceeded. Coal production projections at appraisal were significantly below current projections. Also, in land acquisition and resettlement, projections at appraisal were significantly lower than the actual figures. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Market analysis Project Design: Appraisal Sector Related Issues: Transport planning The service/access roads and link roads connecting the railway stations to population centers were two important components of the project, and yet they were not clearly specified in the appraisal. These should have been specified in detail at appraisal to allow the construction and finalization of all the roads to be monitored and evaluated during implementation and at project completion. The project was designed to give more emphasis to coal transport and less to passenger transport. But later on, the focus on passenger transport increased significantly, and the project was flexible enough to accommodate the increased demand for passenger transport. Without such flexibility, the project would have been less successful. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Project management Sector Related Issues: Transport planning | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/guizhou-shuibai-railway-project
Yunnan Dachaoshan Power Transmission Project | China |  | 2005-08-15 | A well-designed project, an experienced executing agency with a strong sense of project ownership, and a committed project management office staff is a formula for project success. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Ownership Designing and implementing projects in sectors like the power sector that are undergoing major restructuring involves several uncertainties. These include some policy and institutional uncertainties that cannot fully be foreseen at appraisal. To cope with uncertainties and unexpected developments, close consultation between ADB, the government, and executing agencies during project implementation should be held at the sector level, as opposed to the project level. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Greater attention should be paid to project cost estimates at appraisal. However, the project has demonstrated the benefits of prompt cancellation of loan savings to the executing agency. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Management: Executing/Implementing agencies Projects in a sector that is undergoing structural reforms require some flexibility in loan covenants to ensure that they remain practical and relevant. In the project, the executing agency saw its asset base and business scope reduced significantly, yet the original financial covenants remained in place. This led to an unrealistic assessment of compliance with the loan covenants. project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Project Management: Executing/Implementing agencies Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/yunnan-dachaoshan-power-transmission-project
Second Industrial Energy Efficiency and Environment Improvement Project in the People's Republic of China (Loan 1436-PRC) | China | Energy | 2005-06-30 | ADB should know in a timely manner whether the subproject enterprise is making adequate surpluses and whether it is capable of sustaining a project financially. Considering the depth of financial analysis required and quantum at stake in this kind of situation, more staff time and expertise are needed during the review missions for thorough financial analysis and recommendations. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financial analysis Project Design: Subprojects The periodic submission of audit and progress reports of the subprojects and financial statements of the enterprises to ADB has been unsuccessful, since available subproject information was all in Chinese, and proper and timely translation into English became difficult for most executing agencies. A standard reporting format applicable to all projects is not very helpful in the case of the People's Republic of China, where English is not widely used. It would be useful to prepare and provide a project-specific benefit monitoring format in English prior to implementation. project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Project Management: Executing/Implementing agencies To determine the financial health of subproject candidates, especially the health of state owned enterprises (SOEs), all supporting documents relating to counterpart funding commitments from local banks and counter guarantee letters from local governments should be carefully reviewed in parallel with the usual financial ratios analysis. project cycle stage: Feasibility, Appraisal Lesson Topics: Capacity Development: Capacity assessment Country Context: Prioritization Policy & Reform: Reform To make loan covenants more legally credible, any waiver or modification should be agreed upon between the executing agency and ADB and formally documented. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Policy-based lending Capacity Development: Ownership Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-industrial-energy-efficiency-and-environment-improvement-project-peoples-republic-c
Beijing Environmental Improvement Project | China |  | 2005-06-15 | Closer attention should be paid to details during the project preparatory TA stage to avoid delays during project implementation. Greater scrutiny of the market and financial situations, customers' affordability levels, assumptions, and risks could have identified unfeasible components, which could have been removed from the project at the outset, thereby not holding up implementation overall. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Modality: Technical Assistance Project Design: Project design Project Management: Risks/Risk management For project components that are based on the feasibility studies conducted by other institutions, mandatory reviews should be undertaken prior to inclusion in the ensuing project loan. This can bring out critical issues at the outset and improve project design. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Problem identification Project Design: Project design Greater attention to supervision of resettlement activities should be observed during project review missions so that the quality of reports submitted by the project implementing agencies (PIAs) can be improved and their compliance to their social obligations can be better assessed. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project reporting Project Management: Project supervision Slow mobilization of domestic loan funds accounted for some initial delays. Timely availability of the required funds is important and should be given adequate attention. Up-front confirmation of the funding source should be secured and arrangements for possible shortfalls during implementation should be in place. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Appraisal Up to now, knowledge of critical supply sources and proper planning and preparation are key elements in suitable project design and smooth and timely execution.The substantial increase in project cost was due to the expansion in scope and some technical difficulties encountered during construction, which were not anticipated at the design stage. While, to a large extent, the expansion in scope enhanced project benefits, the implementation period could have been shortened by accurately envisaging the scope at the outset. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/beijing-environmental-improvement-project
Hebei Roads Development Project | China |  | 2005-06-15 | A projection of demand for parking zones at the roadside stations was not done at appraisal, which resulted in insufficient space to meet rising demand. Parking zone projections should be conducted during the design stage to avoid potential traffic congestion. Overseas training for the toll, communications, and traffic surveillance systems should be included as part of the terms reference of the consultants at appraisal. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Management: Consultants Capacity Development: Capacity building Sector Related Issues: Roading The expressway design and traffic forecast should be thoroughly assessed during appraisal to reflect actual traffic demand, and to ensure the appropriate number of lanes. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Design: Project design The use of participatory rural appraisal (PRA) techniques should be associated with a better monitoring process, and the Report and Recommendation of the President should provide clear guidance to the executing agency to facilitate implementation of the project. A resettlement plan for the connector roads should be included as part of the expressway resettlement plan, and the cost should be identified and included as part of the project cost. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Management: Executing/Implementing agencies Sector Related Issues: Roading Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/hebei-roads-development-project
Xiamen Port Project | China | Transport | 2005-03-15 | Active involvement of ADB in problem solving and design enhancement was essential in ensuring the successful completion and operation of the project's facilities. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Project Management: Project supervision Well-formulated advisory technical assistance contributed significantly to the implementation of the policy reform action program and successful operation of the project's facilities. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Operation and maintenance Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/xiamen-port-project
Tangshan and Chengde Environmental Improvement Project in the People's Republic of China (Loan 1270-PRC) | China |  | 2004-12-31 | ADB could have done more in terms of preventing the incidents from happening through, for example, providing advice to the project implementation agencies (PIAs) on the potential risks of advancing procurement by a year in order to avoid paying import tax, or helping the PIAs to identify the right type of expertise to install the equipment once the incidents occurred. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Risks/Risk management In contrast, the PIAs visited by the OEM were clearly much more concerned about the financial returns. For future environmental improvement projects, ADB should not try to de-emphasize the importance of achieving economic benefits in the process of achieving environmental improvement. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Successfully implemented subprojects appear to share one common trait: strong participation by project implementation agency's staff. For example, in the case of Subproject 7, the Chengde Iron and Steel Company dispatched 600 engineers for training before and during the construction of the subproject; they have subsequently formed the backbone of the operating entity. project cycle stage: Implementation Lesson Topics: Project Design: Subprojects Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation The selection of an untested technology for producing high-quality porcelain, which was to be the second such production line in the world, was one of the main reasons for its failure in commercial production. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Consultants | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/tangshan-and-chengde-environmental-improvement-project-peoples-republic-china-loan-1270-pr
Chengdu-Nanchong Expressway Project | China |  | 2004-12-15 | A detailed resettlement plan, which should be updated after a measurement survey, is necessary to assess if adequate provisions and cost adjustments were made. ADB should supervise resettlement more effectively to stay informed of the progress and to ensure that the implementation is in compliance with the resettlement plan. More attention should be given to resettlement monitoring and submission of monitoring reports on time. Systematic data collection requirements should be established so that basic data about resettlement is collected in time. This would enable a more comprehensive review and assessment of resettlement during project completion review. project cycle stage: Feasibility, Implementation, Completion Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Management: Project supervision The international consultants and the executing agency (Sichuan Provincial Communications Department) cooperated well during the implementation of the project. The international consultants were sensitive to the local needs and practices. They also acted as a communication bridge between ADB and the executing agency, explaining ADB's procedures and requirements, especially in procurement. The approach adopted by the international consultants in their working relationship with the executing agency under this project can be taken as a worthy example. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement The preliminary design document was used in the bidding documents. The detailed design used during project construction included significant variations that increased project costs. Based on this experience, and similar experience with some of the previous road projects, ADB had been suggesting conducting more detailed geological investigations before finalizing bidding documents. Now both ADB and domestic financed projects start bidding after detailed design is completed. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/chengdu-nanchong-expressway-project
Anhui Environmental Improvement Project for Industrial Pollution Abatement | China | Agriculture, Natural Resources, and Rural Development | 2004-10-15 | Technical assistance (TA) that is suitably designed, properly targeted, and appropriately timed can providesynergies to a loan project and enhance its overall impact. The advisory TA associated with theproject was directly relevant and well timed, which enabled formulation of an Integrated Environmental Management Plan (IEMP) and enhanced the executing agency's institutional capacity for enforcing stricter environmental compliance. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity development Methodologies/Approaches: Targeting The phased implementation of the coke oven plants construction was not fully assessedduring Project Design, resulting in an unrealistic implementation schedule for the Hefei Iron and Steel Corporation (HISC)component of the project. ADB staff should fully assess and anticipate environmental versuseconomic/financial objectives of the industrial enterprises in future projects. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial management Project Design: Project design Sector Related Issues: Industry and Trade The suitability of a full-time and adequately resourced Project Management Office (PMO) in project implementation fora multicomponent project was proven through efficient implementation and coordination of theproject activities. The PMO approach continued to keep the executing agency's (Anhui Provincial Government's) focus on the project. ADB should continue to encourage APG to set up a similar PMO for all multicomponent projects. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Timely availability of required funds is essential for smooth project implementation. Inthis project, availability of counterpart funds was a key issue, because they could not besecured in a timely manner. ADB staff must carefully scrutinize counterpart fund arrangementsand availability during project appraisal. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Appraisal ADB should play a more active role in resettlement supervision and monitoring to ensure that (i) the resettlement plan would be implemented as agreed between government agencies and ADB, and (ii) actions could be formulated and implemented to address the concerns of the affected people. Also, it is essential to ensure that independent agencies monitor the social impact of the resettlement activities during implementation and evaluate the results for at least 2 years thereafter. Such monitoring would assist the executing agency and ADB to prepare a comprehensive resettlement completion report. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project supervision While specific access roads were not identified at appraisal, local roads were constructed and upgraded. Poverty areas along the expressway benefited from the expressway, with improved accessibility to transport facilities, making it easier for farmers to transport their products to market. There is a need to include a specific local road component in the project scope to ensure maximum access to the expressway by the rural population and thus maximize poverty reduction and regional economic development. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Appraisal Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Rural development Sector Related Issues: Transport planning | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/anhui-environmental-improvement-project-industrial-pollution-abatement
Changchun-Harbin Expressway Project (Hashuang Expressway) | China |  | 2004-10-15 | ADB should play a more active role in resettlement supervision and monitoring to ensure that (i) the resettlement plan would be implemented as agreed between government agencies and ADB, and (ii) actions could be formulated and implemented to address the concerns of the affected people. Also, it is essential to ensure that independent agencies monitor the social impact of the resettlement activities during implementation and evaluate the results for at least 2 years thereafter. Such monitoring would assist the executing agency and ADB to prepare a comprehensive resettlement completion report. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project supervision While specific access roads were not identified at appraisal, local roads were constructed and upgraded. Poverty areas along the expressway benefited from the expressway, with improved accessibility to transport facilities, making it easier for farmers to transport their products to market. There is a need to include a specific local road component in the project scope to ensure maximum access to the expressway by the rural population and thus maximize poverty reduction and regional economic development. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Appraisal Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Rural development Sector Related Issues: Transport planning | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/changchun-harbin-expressway-project-hashuang-expressway
Chongqing Expressway Project | China | Transport | 2004-09-15 | A detailed geological survey should have been completed to avoid major cost differences brought about by major changes in design and frequent contract variations. A more conservative traffic projection, particularly for the initial years of operation, should be used to ensure more robust financial performance of the expressway operator. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Procurement Before the expressway is completed, a road safety campaign should be actively promoted among people living in the area of the new road to avoid unnecessary traffic accidents. In this project, many of the recorded traffic accidents involved unauthorized road crossing by local residents. Many fencing sections have been removed by unauthorized persons to gain access to the expressway. Underpasses should be designed so that they are centrally located and have good natural drainage to encourage their frequent usage by local residents. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Roading Policy & Reform: Information dissemination/Public awareness Publicizing the resettlement plan and compensation rates to all people affected by a project is essential to ensure good support and provide detailed information on the basis of compensation. Relocation within the same village helps to maintain social ties. For those who need to supplement their income through new employment, appropriate skill training should be provided. Periodic monitoring of resettlement activities by an independent panel is essential to ensure timely corrective actions on resettlement problems. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity building Crosscutting Issues/Themes: Employment Policy & Reform: Information dissemination/Public awareness | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/chongqing-expressway-project
Hainan Agriculture and Natural Resources Development Project | China | Agriculture, Natural Resources, and Rural Development | 2004-09-15 | A strong sense of ownership is an important factor in effectively implementing a project,which is reflected in the sustained support and guidance that the executing agency provides tothe Project Management Office (PMO). To ensure that the PMO remains effective throughout projectimplementation, it should be (a) provided with a team of full-time and permanentstaff, (b) allocated an independent budget for operations and monitoring of fieldactivities, and (c) fully familiar with ADB loan administration procedures. Withoutsuch support, the PMO will be ineffective. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project administration Project Management: Project management Capacity Development: Human resources management Capacity Development: Ownership ADB should have been more proactive in offering assistance and remedial measures to the executing agency in resolvingcritical issues that caused protracted delays in project implementation, such as the collateral issue. An appropriate monitoring system at the beginning of project implementation is crucial to obtain adequate information needed fortaking timely corrective measures when required. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Project supervision In general, the Provincial Financial Bureau (PFB) may not be the appropriate channel to onlend ADB funds to privatecompanies, because it may not have the technical expertise, particularly in risk assessment. A major improvement in the financial sector is needed, so that this task could be assigned to commercial financial institutions - the appropriateconduit for onlending of development funds from multilateral institutions. In the absence of an alternative, some basic requirements must be satisfied to continue utilizing PFB's services: (i) strong technical support and partnershipwith the Project Management Office (PMO) to guide onlending decisions, (ii) an appropriate risk-sharing mechanism, and (iii) a strong sense of project ownership by the provincial government that is reflected in the provision of adequate financial and staff resources. In the ADB-financed Fujian Soil Conservation and Rural Development Project, these requirements were satisfied, and PFB successfully played the role of financial conduit. In that project, the risk was shared by the FujianProvincial Government and the participating town and district governments. The local governments guaranteed the repayment of disbursed loan funds. In case of repayment default, the provincial government would deduct the repaymentamount from the annual town and district governments' public budget. As a result, the local governments had a strong incentive to partner with successful private, commercial agricultural companies to onlend ADB loan funds. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Human resources management Capacity Development: Ownership Capacity Development: Partnerships Country Context: Decentralization Sector Related Issues: Private sector Sector Related Issues: Rural development In line with the Provincial Government of Hainan's (PGH's) support for thedevelopment of private companies, the project design depended on new privatecompanies that had little or no experience in agricultural production or processingto implement the project. The performance of the private companies falteredwhen they were assigned (a) a complex set of tasks that did not elicit stronginterests from them and were outside their core business competencies - requiring specialist commercial and technical knowledge of crop production,processing, and marketing that they did not possess; and (b) the taskof promoting agricultural and rural development, which did not interest them.Furthermore, the assumption that attaching a technical assistance (TA) for capacity building wouldsolve the severe capability weaknesses of the implementing agencies (IAs) was wrong in this case. Thesupport provided by the PGH did not have the expected impact on the IAs due totheir lack of adequate experience. In hindsight, a more thorough andcomprehensive analysis of the institutional capability of the IAs, and the risks ofusing such inexperienced companies, would have averted the problems underthe project. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Capacity building Capacity Development: Institutional analysis Sector Related Issues: Private sector Sector Related Issues: Rural development Overly ambitious fixed targets set at appraisal precluded a flexible approach to achieve the overallgoal, making the project supply-driven instead of market-driven. Thedesign of future ADB projects should adopt a flexible approach to targetedoutputs, and should be sensitive to changes in market demand and productprices. Moreover, the designation of, and dependence on, a sole implementing agency (IA) could beavoided if a sector approach is adopted. This could decrease the risk of projectfailure. A sector approach for similar projects would be more appropriate. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Methodologies/Approaches: Sectoral approach Methodologies/Approaches: Targeting The project needed the support of a strong steering committee to provide leadership and guidance to the Project Management Office (PMO), with a high-level executing agency official as chair to provide direction and ensure the success of the project. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/hainan-agriculture-and-natural-resources-development-project
Qitaihe Thermal Energy and Environmental Improvement Project | China | Energy | 2004-09-15 | A strong commitment by the project proponents, and efficient management and execution of experienced and well-trained project implementation staff, consistently have been the primary success factors in most projects in the PRC. Selection and recruitment of competent international as well as domestic consultants have ensured observance of the quality standards required for projects with high investment costs. project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Consultants Project Management: Project management Capacity Development: Human resources management Capacity Development: Ownership Properly administered bidding processes were key to obtaining advantageous bid offers. Deviations between the final project costs and appraisal estimates were small. But the contingencies in foreign currency cost items, at almost 20% of the base cost, were too high. Consultants and ADB staff must carefully review the status of project feasibility studies to arrive at reasonable contingencies in project costs. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Foreign exchange Monitoring & Evaluation: Project evaluation Project Design: Appraisal Project Management: Consultants Project Management: Procurement Technical Assistance (TA) that is suitably designed, properly targeted, and appropriately timed can provide synergies to a loan project and enhance its overall impact. Both TAs associated with the project were directly relevant and well timed, which enabled smooth unbundling of the Heilongjiang Electric Power Company or HEPC (the executing agency) and transition of plant's ownership to China Datang Corporation (CDT). project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Sector Related Issues: Energy planning/management Policy & Reform: Reform Timely availability of the required funds is essential for smooth project implementation. In this project, availability of counterpart funds was a key issue, because they could not be secured until project launching. ADB staff must carefully scrutinize counterpart fund arrangements and availability during project appraisal. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Appraisal | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/qitaihe-thermal-energy-and-environmental-improvement-project
Yunnan-Simao Forestation and Sustainable Wood Utilization Project | China | Agriculture, Natural Resources, and Rural Development | 2004-09-15 | Commercial projects need to be financed with reasonable debt-equity ratios.Equity should be paid in as a condition for ADB Board consideration of the loan. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Sector Related Issues: Private sector Commercial projects of this type require greater flexibility in design, and moreproactive and timely responses by ADB to key emerging issues duringimplementation. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Project supervision Sector Related Issues: Industry and Trade Sector Related Issues: Private sector For a project of this type, the forestry component should start well in advance of pulpmill construction so that the first harvest coincides with the mill start-up. Long-term guarantees of access to an adequate timber supply are needed fromspecific plantation land or leases on government timberland. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Industry and Trade Sector Related Issues: Rural development For future projects of similar type, a thorough and complete capacity analysisshould be conducted during the feasibility study to ensure long-term economicand financial viability of the enterprise. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Capacity Development: Capacity assessment Sector Related Issues: Rural development The forestry component involved technology transfer related to the introduction of new forest management, planting, and harvesting techniques. Due to theserious financial constraints faced by Jinggu County Forestry Bureau andpotential risks associated with introducing new technology-related activities, the executing agency(Yunnan Province) decided not to implement the forestry component as designed. Such a component needs to be designed carefully in the context of localknowledge and practices. Recommendations for new technologies require fulllocal ownership. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Knowledge Management Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Ownership Capacity Development: Technology/Technology transfer Sector Related Issues: Rural development The government should give more attention to the need for experienced foreignconsultants when new technologies and equipment are imported. The loanprovision for consultants was intended to ensure that the equipment met thepurchase criteria and that construction and start-up was executed smoothly. Thisprovision was only partially utilized. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Capacity Development: Technology/Technology transfer Timely and complete training of operating staff that is specific for the technology and equipment is essential for smooth start-up and operation. Yunnan Yun-Jing Forestry and Pulpmill Company (YFPC) required 4 years to achieve a steady operating rate and consistent product quality. A provision for international training was included in the design, but never utilized. project cycle stage: Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Human resources management Capacity Development: Technology/Technology transfer Sector Related Issues: Private sector | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/yunnan-simao-forestation-and-sustainable-wood-utilization-project
Fujian Mianhuatan Hydropower Project | China | Energy | 2004-08-13 | As was the case with other power projects approved about the same time, the expected tariff increase did not materialize. The government controls the tariffs for power sales and purchases. As a result, electricity transactions were determined more by the government directives than through commercial negotiations between the seller and the buyer. This made it difficult for the executing agency to comply with the loan covenants on the signing of a sound Power Purchase Agreement (PPA). In the context of competitive power markets in the near future, other commercial arrangements in addition to PPA may deserve consideration during project design phase. project cycle stage: Feasibility Lesson Topics: Loan Agreement: Covenants Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Resettlement of large populations in a hydropower project needs prudent and thoroughexamination. ADB closely monitored the resettlement work during project implementation, andpromptly identified deficiencies. ADB's intervention helped improve implementation of the Resettlement Plan (RP),including the provision of increased resettlement budget. Continuous monitoring of restoration ofthe resettlers' income is essential to evaluate the implementation status of the RP. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Energy planning/management The actual project cost was only 60.7% of the appraisal estimate. The main reasons for this significant cost reduction were vigorous competition in the bidding process of equipment and materials, changes in the market conditions, and the substantial reduction in the cost for interest during construction due to government's policy changes towards taxes and interest rates. While the latter was difficult to predict, the other factors could have been given greater weight in estimating the project costs at appraisal. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Management: Procurement The project demonstrated a successful model for a joint-investment between the central and local governments. Local governments' participation in the project enhanced their ownership, and thus helped implement the project smoothly. The local governments also played an important role in obtaining a reasonable power tariff for the project. Establishing a project company (FMHDC) to exclusively construct and operate the project proved to be an effective practice, which should be pursued to the extent possible in future projects. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Project Design: Project design Project Management: Project management Capacity Development: Ownership Country Context: Decentralization Policy & Reform: Public sector reform Methodologies/Approaches: Consultation/Participation The successful completion within the revised implementation schedule, the stringent budget control, and the high quality of the project's facilities demonstrated the project entities' high competence in hydropower design, construction, and operation. Future Project Preparatory Technical Assistance (PPTA) studies for hydropower development projects may focus more on the aspects pertaining to compliance withADB safeguard policies. Similarly, the scope and the terms of reference (TOR) for implementation supervision consultants may be strengthened to mainly cover these areas. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Resettlement Crosscutting Issues/Themes: Vulnerable groups Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Project supervision Sector Related Issues: Energy planning/management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/fujian-mianhuatan-hydropower-project
Zhejiang-Shanxi Water Supply Project (Phase I) | China | Water and Other Urban Infrastructure and Services | 2004-08-13 | A key element in the project's success, particularly for the physical components, was the government's strong commitment. This ensured that schedules were kept, procedures adhered to, and guidance at the highest level was given when necessary. Project preparation involved extensive consultation between various departments, bureaus, and offices of the government and ADB. Implementation was planned in detail and undertaken through effective supervision, monitoring, and cost control. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project supervision Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Generally, the resettlement implementation was carried out successfully, which was due to various reasons: strong commitments and efforts from local government; preferential treatment of the affected people; and following an income restoration strategy that took advantage of rapid economic growth in one of the project cities. The resettlement was carried out with a relatively modest budget. This was possible by sharing the burden with the host population. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Financing Capacity Development: Ownership Country Context: Decentralization Greater care in drafting covenants would help prevent potential misunderstandings. Terms and phrasing in financial covenants were in some instances found to be vaguely defined or ambiguous. For example, the term ï¿½net revenueï¿½ was used without definition. References to general cash reserve balances and the retention and debt service accounts were difficult to understand. The nomenclature for certain reserve fund accounts implied funds for construction and maintenance, while they were in fact meant to finance ongoing resettlement efforts. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Financial management Loan Agreement: Covenants Several financial covenants were highly prescriptive. For example, financial covenants stipulated how cash reserves should be managed to ensure adequate debt servicing. However, such requirements cannot be effectively monitored as they concern operating decisions and actions that occur after project completion, and did not effectively improve ADB's capacity to enforce good financial management practices in the implementing agency (Shanxi Economic Development Company). The other example relates to having a fixed tariff at completion. Calculations of a tariff should be based on many factors including water demand and consumption, projects cost, implementation period, and government policy on tariffs. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financial management Finance & Financial Aspects: Market analysis Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/zhejiang-shanxi-water-supply-project-phase-i
Fuzhou Water Supply and Wastewater Treatment Project | China |  | 2004-07-15 | A commitment charge to undisbursed loan funds makes it important for ADB missions and the executing agency to closely monitor changes in project costs and to take actions to cancel or use loan savings. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project supervision Delegation of authority from the executing agency (Fujian Provincial Government) to the Fuzhou Municipal Government (FMG) enabled the project management office (PMO) to closely manage and coordinate with the implementing agencies (AWDD and YLWWTP) in day-today implementation activities. Project ownership and dedication of all concerned parties has resulted in achieving all targeted outputs with close adherence to guidelines and procedures. The project took 9 months more than the 48 months scheduled at appraisal. A 5-year implementation period would have been more realistic, considering the project's scope. FMG's ability to raise counterpart funds from state and provincial sources in a timely manner was important for smooth project implementation. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Ownership Country Context: Decentralization Methodologies/Approaches: Consultation/Participation Failure to increase water and wastewater tariffs to meet targets for cost recovery and to cover weak implementation of tariff policies could significantly jeopardize financial sustainability. Although residents normally object strongly totariff increases, the executing agency (Fuzhou Municipal Government or FMG) has supported measures for cost recovery and tariff reviews, and has implemented increases regularly. The financial risk of not increasing wastewater tariffs to meet full costs has been incorporated in preparing the new ADB-funded project. A corporate development plan for one of the project implementation agency (Yang Li Wastewater Treatment Plant Company or YLWWTP) is included in the project design. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Health and sanitation management Project Performance and Management System (PPMS) is a relatively new practice whose benefits are not fully appreciated by government and implementing agencies. The executing agencies do not feel that much of the information that ADB staff request is directly relevant to their operations or day-to-day decision making. Thus, they are not willing to spend the money necessary to collect the data. Experience from the project indicates a need for more policy dialogue with government and project staff on preparing practical and functional PPMS. Project targets should be linked to project activities. Methods to monitor achievement of these targets should be based on readily measured indicators. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management Policy & Reform: Policy matrix Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/fuzhou-water-supply-and-wastewater-treatment-project
Ping Hu Oil and Gas Development Project | China | Energy | 2004-05-14 | A properly administered bidding process, supported by detailed technical design and bidspecifications, can obtain advantageous bid offers. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project administration Adequate planning and preparation are key elements to the smooth and timely execution of a project. Timely availability of the required funds is also important (availability of funds though was not an issue in this project). project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design Project Management: Project management The issue of detailed information regarding the onshore gas transmission and distribution component of the project (Part B), for which loan proceeds were not utilized, could have been avoided with a more binding provision in the Loan Agreement and closer monitoring during project implementation. project cycle stage: Appraisal Implementation Lesson Topics: Loan Agreement: Loan Agreement Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Energy planning/management The successful implementation of projects with huge investment costs and associatedrisks requires a strong commitment and preparedness by the project proponents, as well as theinvolvement of experienced and well-trained project implementation staff. The expertise ofcompetent international consultants ensured accurate evaluation of the risks involved, adoptionof appropriate technical design and reasonable cost estimates, and observance of theapplicable safety and operating standards. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Project Management: Consultants Project Management: Project management Project Management: Risks/Risk management Capacity Development: Human resources management Capacity Development: Ownership | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/ping-hu-oil-and-gas-development-project
Hebei Expressway Project | China | Transport | 2003-12-15 | The Office of the General Auditor's (OGA's) review missions revealed control weaknesses and indicators ofpotential risks in relation to the misuse of loan funds and made recommendations for variousparties involved in project implementation. Following the recommendations, the National AuditOffice has strengthened its audit procedures. The Ministry of Finance agreed to coordinate withMinistry of Communications (MOC) to improve their overall project monitoring procedures and conduct periodic site visits.Effective and regular communication among and monitoring by ADB and national governmentagencies was essential to ensure that any significant changes in project implementation werediscussed and comments and feedback from relevant agencies were sought in advance. Forexpressway projects, resettlement should be evaluated during the midterm review. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation A properly administered bidding process has been a key factor in obtainingadvantageous bid offers. However, the significant savings in project costs have cast doubt onthe integrity of the cost estimates. The degree of deviation between the final project cost and theappraisal estimates bolsters the PRC's view that project cost estimates adopted in ADB projects tend to be overly conservative. In light of the PRC's track record in generating cost savingsunder this project and others, the project preparatory consultants and ADB staff must carefullyreview the assumptions developed at appraisal. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Procurement A strong commitment by the project proponents, and efficient management andexecution of experienced and well-trained project implementation staff, consistently have beenthe primary success factors in most projects in the People's Republic of China. Selection and recruitment of competentinternational as well as domestic consultants have ensured observance of the quality standardsrequired for projects with high investment costs. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Project management Capacity Development: Capacity building Capacity Development: Human resources management Capacity Development: Ownership Detailed technical design and adequate planning and preparation are vital to the smoothand timely execution of a project. Timely availability of the required funds is also essential.Under this project, availability of funds was not an issue as firm commitments on disbursementrequirements were secured beforehand. project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Disbursement Project Design: Project design Recommendations to amend the power purchase agreement (PPA) to incorporateinternational practices have not shown much progress. While the PRC's power sector is movingtoward competitive pricing governed by independent market mechanisms, achieving market-basedpricing still could take time. In the interim, the approved tariff levels provided in the PPAshould support the requirements for basic operations and debt repayments. On the other hand,the recommendations to include international practices in the PPA would have received awarmer reception in a more open and mature power market. In the PRC's power sector, thereality is that the seller and buyer of electricity are state-owned, and PPA contract provisions areset by the state. As a result, the executing agency and implementing agency have found it difficult to comply with ADB'srecommendations. The prevailing institutional constraints in implementing commercialcontractual provisions have to be recognized and considered upfront to avoid making thempersistent contentious issues during the review of project implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Institutional analysis Sector Related Issues: Energy planning/management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/hebei-expressway-project
Northeast Power Transmission Project | China | Energy | 2003-12-15 | For timely completion of physical works, and the smooth processing of withdrawal applications and disbursements, strong coordination by the Project Management Office (PMO) is essential. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Management: Project management Methodologies/Approaches: Consultation/Participation Implementation experience suggests that the use of international project management specialist consultants who are familiar with ADB procedures for (i) subproject selection, (ii) eligibility of particular expenditures for loan financing, and (iii) procurement and disbursement will assist with the timely implementation and monitoring of major projects in the People's Republic of China, although the executing agencies (EAs) and implementing agencies (IAs) involved with this project have now gained this experience themselves. Also, emphasis should be placed on training EA and IA staff by consultants. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management Capacity Development: Capacity building The absence of a project framework and lack of Benefit Monitoring and Evaluation (BME) data, coupled with poor monitoring by counterpart staff, affects the monitoring of project performance. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration The capability of, and availability of counterpart funds at, municipal government implementing agencies (IAs) in the People's Republic of China (PRC) have proven to be sufficiently high for this large and complex multisector project to be implemented to a generally high standard. Despite the largely disaggregated implementation structures and initial unfamiliarity with ADB procedures and documentation, the various IAs and executing agencies (EAs) were able to formulate, design, and implement a series of subprojects, which met their own priorities, but within the selection criteria agreed with ADB at appraisal. Adopting this sector loan approach appears to be well suited for emergency loans to the PRC. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Modality: Lending modality Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project administration Country Context: Decentralization Country Context: Emergency Country Context: Prioritization | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/northeast-power-transmission-project
Second Yantai Port Project | China | Transport | 2003-12-15 | A well-designed project, an experienced executing agency with a strong senseof project ownership, and a committed project management office staff make upa formula for project success. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Ownership Designing and implementing projects in sectors that are undergoing major restructuring,such as the power sector, involves many uncertainties. These may include policy andinstitutional uncertainties that can not fully be foreseen at appraisal. To cope with uncertaintiesand unexpected developments, close consultations between ADB, the government andexecuting agencies during project implementation should be held at sector level, as opposed toproject level. Coping also calls for flexibility on both sides when dealing with unexpecteddevelopments. project cycle stage: Implementation Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Risks/Risk management Sector Related Issues: Energy planning/management Policy & Reform: Public sector reform Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach Methodologies/Approaches: Sectoral approach Government and executing agencies should advise ADB prior to any institutionalchanges resulting from sector restructuring, particularly changes that will impacton project implementation. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Policy & Reform: Public sector reform There is a need to pay greater attention to project cost estimates and the size ofADB loan at appraisal, to avoid subsequent loan savings. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Appraisal There is a strong emphasis in the People's Republic of China (PRC) on project technical issues. The government and executing agencies need to pay greater attention to project financial issues, including the financial viability of projects. ADB review missions need to pay more attention to financial issues. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/second-yantai-port-project
Xi'an-Xianyang-Tongchuan Environment Improvement Project | China | Energy | 2003-12-15 | Port construction materials should not be procured in one large package ordelivered in one bulk shipment. This type of procurement cannot meet thedemand for change arising from the alteration or optimization of civil worksdesign and construction schemes. Procurement of this kind also can lead tofurther expenses, unnecessary storage areas, and possible rust and deterioration of some equipment that is needed at later stages. Construction materials shouldbe procured under small batch-by-batch procedures, as required, or under astaggered delivery schedule. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Sector Related Issues: Transport planning | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/xian-xianyang-tongchuan-environment-improvement-project
Dalian Water Supply Project (Loan 1313-PRC) | China | Water and Other Urban Infrastructure and Services | 2003-11-30 | A commitment by the local government is the most important factor contributing to the success of water supply and sanitation projects. The project also was implemented against a backdrop of an escalating water supply crisis in Dalian, providing a strong incentive for all concerned to perform effectively. project cycle stage: Appraisal Lesson Topics: Country Context: Crisis/Post-crisis Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management Consumers accept and understand the need for higher tariffs, but only if the water supply services are adequate and reliable, as in the project. project cycle stage: Implementation Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Highly successful | http://www.adb.org/documents/dalian-water-supply-project-loan-1313-prc
Hunan Lingjintan Hydropower Project | China |  | 2003-11-14 | Assumptions for future tariff increases tend to be unrealistic. Greater prudence should be used in developing assumptions regarding tariff increases, which may lead to setting unrealistic project benefit targets. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Methodologies/Approaches: Targeting Certain recommendations for power purchase agreement (PPA) revision to include international commercial practices would have been more appropriate in a more open and mature power market. Realities of PRC's power sector - where both the seller and the purchaser of power are state-owned enterprises, and where higher authorities set contract standards instead of negotiations - have made it difficult for the executing agency and implementing agency to comply with ADB's recommendations. Certain institutional constraints in implementing desirable contractual provisions should be recognized up-front to avoid their becoming persistent and contentious issues during implementation. project cycle stage: Feasibility, Appraisal Lesson Topics: Loan Agreement: Covenants Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Institutional analysis Sector Related Issues: Energy planning/management Policy & Reform: Public sector reform Resettlement of populations that were displaced by the reservoir, in densely populated areas of the People's Republic of China (PRC), continues to be a difficult challenge for the restoration of income. Although the impact of resettlement was not great by PRC standards, ADB needed to review the resettlement implications more closely to identify problems and issues at an early stage, and recommend appropriate measures. Contracting of an external monitor to provide independent feedback on these issues, which ADB could then have raised with the Wuling Hydropower Development Corporation (WHDC), would have been helpful. This would have required a resettlement specialist on review missions. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Project Design: Problem identification Project Management: Project supervision Capacity Development: Human resources management Sector Related Issues: Energy planning/management The ADB project staff should obtain data for the project completion report (PCR) preparation from the executing agency and implementing agency immediately after project completion, and before loan closure. This would ensure the availabilityof accurate and reliable information, and the ï¿½institutional memoryï¿½ of staff who were responsible for project implementation. project cycle stage: Completion Lesson Topics: Monitoring & Evaluation: Data collection and management Project Management: Executing/Implementing agencies Project Management: Project management The common People's Republic of China (PRC) practice of creating a separate entity for project implementation and operation should be anticipated during appraisal. That might help avoid lengthy deliberations and the need for separate evaluations of the capabilities of the new entities, and subsequent modifications of loan and project documents. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Project management Capacity Development: Capacity assessment The use of international bidding procedures effectively generated highly competitive bids. Proper administration of the bidding process, supported by clear and detailed bid specifications are important. Deputizing procurement specialists who were familiar with ADB's procurement guidelines was also useful. project cycle stage: Appraisal Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/hunan-lingjintan-hydropower-project
Second Industrial Energy Efficiency and Environment Improvement Project | China | Energy | 2003-10-15 | Significant cost underruns were noted due to the overestimation of costs at appraisal as well as lower equipment costs brought about by keen competitive bidding. The appraisal missions should carry out separate cost estimates using the most recent available contracted prices for equipment. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Management: Procurement The engagement of a domestic agency to assist the executing agencies (EAs) in procurement proved to be wise, particularly as the EAs were not familiar with ADB's Guidelines for Procurement. The useof a procurement agency to provide expertise in preparing bidding documents ensured smoothand timely procurement and enabled valuable experience to be passed on to the new EAs. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building The financial performance of each project enterprise was generally weak because inputcosts were higher-than-expected and market prices for the products were lower-than-anticipated.The use of more conservative price and cost assumptions should be considered infuture projects to provide an adequate cushion for potential downside risks, particularly in lightof the emerging global competition. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Project Management: Risks/Risk management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-industrial-energy-efficiency-and-environment-improvement-project
Fujian Soil Conservation and Rural Development II Project | China | Agriculture, Natural Resources, and Rural Development | 2003-09-15 | Local governments should select the locationof agricultural markets on the basis of long-term land use and developmentplanning. Changes in land use have been detrimental to the financial condition ofthe Sangjie market in Fuzhou City. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Country Context: Decentralization Sector Related Issues: Industry and Trade Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Market demand changes, and subsequently the price of outputs,are sensitive. Selection and approval of agroprocessing subprojects should takeinto account the capacity and flexibility that allow quick response to changes inmarket trends. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Subprojects Capacity Development: Capacity assessment Sector Related Issues: Industry and Trade Sector Related Issues: Rural development Public-private sector participation was well integrated in the project and played amajor role in ensuring the project's successful outcome. Contractual arrangementswith farmers and enterprise shareholding facilitated innovative risk-sharing throughinvestment-sharing with individuals, management contracts, or partial ownershipthrough shareholdings. The government's role in promoting the enablingenvironment and the effective policy of ï¿½Dragonhead Enterprisesï¿½ are noteworthyfactors in the success of public-private partnership and participation. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Public-private partnership Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation Since repayment collection is recorded only for subborrowers oneadministrative level lower, nonperforming loans are difficult to detect and timelyremedial action was not emphasized. Local financial bureaus should systematicallyorganize and monitor financial information to identify loan amounts due andpayment delays, and be proactive in assessing nonperforming loans. In the samemanner, economic enterprises operating in highly competitive markets should havea sound accounting and financial management information system for monitoringtheir productivity and efficiency, and be required to submit financial statementsregularly to the Provincial Project Management Office (PPMO). project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Management: Management information system Project Management: Project management The project was implemented using primarily existing government structure and staff without hiring consultants or contractual staff. This measure not only reducedproject cost, but also ensured sustainability after project completion. The use offinancial bureaus at provincial and county levels was necessary to overcome theunwillingness of financial institutions, and worked well due to strong ownership andconviction at the very high level of provincial government. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Ownership Country Context: Decentralization The use of the imprest account helped in expediting project implementation andpromoted efficiency in disbursements by reducing the number of withdrawalapplications. A reduced number of loan categories would also help Project Management Offices (PMOs) toimplement them more efficiently. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Project Management: Project administration Project Management: Project management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/fujian-soil-conservation-and-rural-development-ii-project-pcr
Selected Environmental Advisory Technical Assistance in the People's Republic of China (2003) | China | Agriculture, Natural Resources, and Rural Development | 2003-08-31 | Although a technical assistance (TAs) theme may be broadly compatible with the government's goals, the specific scope of the TA can be stretched to yield a different but less relevant focus. Compatibility of the TA objectives and the government's goals appears to be a necessary condition for a TA's success. project cycle stage: Feasibility Lesson Topics: Although most executing agencies (EAs) indicated that they had reviewed the technical assistance (TA) report and terms of reference for consultants and provided comments, it was clear that ADB drafted the documents and played a more dominant role in designing the TA. This echoes a key problem identified in the Resident Mission report, which was limited involvement from EAs in TA design. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Other: Resident Mission Methodologies/Approaches: Consultation/Participation Clusters may only be appropriate where there is very clear synergy between various subprojects. project cycle stage: Feasibility Lesson Topics: Modality: Cluster operations Project Design: Subprojects Perhaps more so than for a regular technical assistance (TA), the recruitment of consultants and their performance are instrumental for the success of a TA cluster. The single-firm approach has the advantage of saving time and effort in procuring consultants for different subprojects, easier coordination between different subprojects, and better utilization of findings from earlier subprojects as inputs to the subsequent projects. However, the disadvantages include difficulties in maintaining a high level of commitment and strong efforts from the consultants, and ADB getting stuck in terms of difficulties and reluctance in recruiting different consultants when the incumbent ones were not performing to a satisfactory standard. A single consulting firm may also find it difficult or may not have the capacity to simultaneously carry out project works for two or more subprojects, which may be required by circumstances. In general, by 'putting all eggs (subprojects) in one basket (the winning consortium/firm),' the single-firm approach is more risky and less flexible than the multiple-firm approach. ADB needs to carefully evaluate the pros and cons of the approaches on a case-by-case basis for future TA clusters. project cycle stage: Appraisal Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Project Design: Subprojects Project Management: Consultants Project Management: Procurement Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation The thematic selection of ADB's advisory technical assistance tends to be 'ad hoc' and is often 'supply driven', which addresses concerns more important to ADB than to the government. project cycle stage: Feasibility Lesson Topics: Timescale is a particularly crucial factor for the success of a technical assistance (TA) cluster and work should be ideally completed over a relatively short period, such as 2-3 years. There should be some or significant overlap in the timescale between the start of one subproject and the completion of another to maximize the potential for one subproject to feed into another, and to maintain the momentum of the overall TA within the designated timeframe. Since delays are very common for ADB TAs (more than 2 years in this case), the delays may cause a more adverse impact on a cluster TA than on a regular TA due to the former's relatively long time span and the chain effects of delays rippled across different subprojects. project cycle stage: Design, Feasibility Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Project Design: Subprojects Project Management: Risks/Risk management To improve the potential efficacy of the cluster approach, there should be a single overall coordinating agency within government for a cluster technical assistance (TA), and ADB should pay particular attention to ensuring that this coordinating body is fully engaged in all formulation processes leading up to the TA and during its implementation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation Two key related factors (among others) for a relatively successful implementation of a technical assistance are: (i) an international consultant team leader who is experienced and knowledgeable about the subject country, and (ii) a significant role for enthusiastic and knowledgeable domestic consultants who would also have access to information and ability to influence decision making. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Consultants While training activities should be clearly encouraged, the cost effectiveness of the training program should be explicitly assessed through comparing different options. For those executing agencies (EAs), particularly those at the central level that have had substantial international exposure, future technical assistance (TAs) may gradually move away from the more costly international study tours or limit their scale. Other innovative yet more cost effective approaches, e.g., secondment of selected EA staff to a foreign agency for a prolonged period of time, should be given priority. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity building Country Context: Prioritization | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/selected-environmental-advisory-technical-assistance-peoples-republic-china-2003
Anhui Environmental Improvement Project for Municipal Wastewater Treatment | China | Water and Other Urban Infrastructure and Services | 2003-03-14 | Extensive training under the project and associated technical assistance (TA) led to the establishment of a training center in Hefei Sewage Treatment Company (HSTC), which has contributed to effective transfer of knowledge among the executing and implementing agencies and to wastewater treatment plants (WWTPs) in other cities in the province. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Sector Related Issues: Health and sanitation management The executing agency (Anhui Provincial Government) and the governments of the implementing agencies (Governments of Hefei and Chao) have supported the cost recovery measures and tariff reviews and increases have been implemented regularly and in close consultation with local residents. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Executing/Implementing agencies Policy & Reform: Public sector reform Methodologies/Approaches: Consultation/Participation The most important factor was strong commitment from the executing agency and implementing agencies (Anhui Environmental Protection Bureau, Hefei Sewage Treatment Company and Chaohu Wastewater Treatment Engineering Company). Project ownership by all concerned parties and dedication to achieving target outputs resulted in implementation within the original schedule, close adherence to guidelines and procedures, and close coordination among the provincial government, local governments, and the utility companies. The ability of the local governments to raise counterpart funds in a timely mannerwas also an important factor for smooth project implementation and on-target completion. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Management: Executing/Implementing agencies Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation The project was designed with a clear goal, objectives and outputs that are in line with government policies and ADB's country and sector strategies. Implementation was planned in detail and undertaken through effective supervision, monitoring, and cost control. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project management Project Management: Project supervision | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/anhui-environmental-improvement-project-municipal-wastewater-treatment
Laiwu Iron and Steel Company Modernization and Expansion Project (Loan 1162-PRC) | China | Industry and Trade | 2003-01-31 | More attention should be given to investigating market conditions during project preparation to avoid significant changes of scope during implementation, resulting in significant changes in project components and costs, as well as delays in completion. project cycle stage: Feasibility Lesson Topics: Finance &amp; Financial Aspects: Market analysis Project Design: Project design The project is a model for modernization of the steel industry and reform and privatization of state-owned enterprises, with other enterprises following both in the steel industry and other sectors. The timing was certainly significant, as was the choice of the company and the support the project received from all levels of government. project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Private sector Policy &amp; Reform: Privatization Policy &amp; Reform: Reform | Project/Program Performance Evaluation Report (PPER) | Highly successful | http://www.adb.org/documents/laiwu-iron-and-steel-company-modernization-and-expansion-project-loan-1162-prc
Jing-Jiu Railway Technical Engineering Project (Loan 1305-PRC) | China | Transport | 2002-12-31 | Although the land acquisition and resettlement were generally carried out in accordance with laws and generally accepted practices, several aspects call for further improvement. These include (i) lack of basic documentation, at ADB and EA of resettlement activities (e.g., written resettlement plan, and lists of persons and entities affected); (ii) greater participation by persons and entities affected in designing a resettlement program and transparency in compensation distribution; and (iii) better monitoring of resettlement implementation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation The executing agency reported frustration with the high costs and long waiting time for procuring spare parts from some foreign suppliers. The EA also stated that, under the project, ADB imposed a maximum amount of spare parts that could be procured with new equipment. After these spare parts are used up, it is expensive and difficult to purchase replacements. For the computer-based hump control system, lack of spare parts has threatened shortening its service life from 15 years to 7 8 years. Fortunately, in this particular case, a domestically produced system, perhaps less powerful, is available at much lower cost. For similar projects in the future, adequate amounts of spare parts should be procured with the equipment. Requests for such procurement should be included in the procurement packages prepared by executing agencies for ADB s approval. In addition, the costs of additional spare parts and quality of after-sale service should be taken better account of in evaluating bids. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement The People's Republic of China has long been known for its centralized project management style. The construction of Jing-Jiu railway best exemplifies the advantages of such a model in terms of speedy execution of complex projects. The transferability of such a model to other developing member countries is debatable. However, an important lesson here is that strong commitment at the very top is necessary to deliver a complex project on time. project cycle stage: Design, Implementation Lesson Topics: Project Management: Project management Capacity Development: Ownership Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/jing-jiu-railway-technical-engineering-project-loan-1305-prc
Fertilizer Industry Restructuring Project | China | Industry and Trade | 2002-11-15 | A more conservative approach should have been used to estimate the demand for urea. The projected urea price ofCNY1,700 per mt for estimating the FIRR at appraisal was overly optimistic. The fertilizer enterprises' assessment of market risk in an open economy was grossly inadequate, particularly with respect to the likely impact of price deregulation and changes in farm practices on the subprojects' financial viability. While the primary and secondary objectives of the project were largely met, the financial performance of the assisted enterprises has not improved and the reevaluated FIRR (and EIRR) is lower than appraisal estimates. This has made all the assisted enterprises virtually dependent ongovernment financial assistance to fulfill their loan repayment obligations. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance &amp; Financial Aspects: Financial analysis Finance &amp; Financial Aspects: Financing Finance &amp; Financial Aspects: Market analysis Project Design: Appraisal Project Design: Subprojects Sector Related Issues: Rural development Policy &amp; Reform: Reform Design for industrial projects in an open economy should incorporate flexibility infeedstock and product mix to the extent possible, so that projects can take advantage ofchanging market conditions to switch to cheaper feedstock and produce higher value-addedproducts. A subproject manufacturing a single product under rapidly changing conditions may have difficulty sustaining its operation if the projected demand for and/or price of its product arenot realized. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance &amp; Financial Aspects: Market analysis Project Design: Project design Project Design: Subprojects Sector Related Issues: Industry and Trade The delay in project start-up and implementation was due mainly to a shortage ofdomestic funds, compounded by the increase in project costs. To ensure timely project implementation all required funding should be confirmed upfront and contingent arrangements made for cost overruns. project cycle stage: Appraisal Lesson Topics: Finance &amp; Financial Aspects: Financial analysis Finance &amp; Financial Aspects: Financing Finance &amp; Financial Aspects: Local currency The gross underestimation of project costs during appraisal resulted in the subsequentdeletion of an approved subproject, which along with difficulties in mobilizing additional domesticfunds reduced the project's financial and economic viability. Cost estimates prepared byborrowers, particularly for new technology, should be verified for accuracy through crosscheckingwith similar projects in other developing member countries or by a short-terminternational expert. project cycle stage: Appraisal Lesson Topics: Finance &amp; Financial Aspects: Financial analysis Finance &amp; Financial Aspects: Local currency Project Design: Appraisal Project Design: Subprojects Project Management: Consultants Capacity Development: Technology/Technology transfer The monitoring of reforms and compliance with loan covenants became difficult after the disbanding of the executing agency (Ministry of Chemical Industry). In hindsight, senior government officials should have been alerted to the need to ensure that stipulated commitments and obligations were fully honored when this unanticipated reorganization took place. project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Monitoring &amp; Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Policy &amp; Reform: Public sector reform Policy &amp; Reform: Reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/fertilizer-industry-restructuring-project
Fangcheng Port Development Project | China | Transport | 2002-09-13 | ADB involvement to speed up loan effectiveness and monitor project progress isan integral part of ensuring successful operations. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Management: Project supervision The port construction materials should not be procured in one large package.This procurement could not meet the demand for change, arising from alterationor optimizations of design and construction schemes of civil works. This alsowould lead to allocation of further expenses, unnecessary storage areas, andpossible rust and deterioration of some of the equipment, which is needed atlater stage. Construction materials should be procured under small batch-by-batchprocedures and as required. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Sector Related Issues: Transport planning Methodologies/Approaches: Process approach The project suffered some delays due to the inability of some suppliers to deliver timely services and unfamiliarity of the executing agency with ADB requirements. These problems could have been addressed through disqualification of incompetent contractors and advance training on ADB guidelines, procedures and policies for executing agency staff, respectively. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/fangcheng-port-development-project
Tangshan and Chengde Environmental Improvement Project | China |  | 2002-09-13 | The engagement of a domestic agency to assist the executing agencies (EAs) in procurement proved to bewise, particularly as the EAs were not familiar with ADB's Guidelines for Procurement. Thearrangement in which the procurement agency provides expertise in preparing biddingdocuments ensured smooth and timely procurement and also enabled valuable experience tobe passed on to the new EAs. However, when selecting prototype equipment whoseperformance has not been assured and when equipment is delivered ahead of the required timeas in the cases of subprojects 4 and 5, appropriate safeguards such as a higher performancebond and a larger retention fee should have been considered during contract negotiation toprotect clients against non-performance of suppliers' obligations. project cycle stage: Implementation Lesson Topics: Project Design: Subprojects Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building The financial performance of the project utility entities is basically weak because the lowutility tariffs approved by the regulatory board are insufficient to cover operating and capitalcosts. The low tariff has affected the financial viability of four subprojects, namely, subprojects1, 2, 6, and 7. Unless utility tariffs are increased to a level allowing for full cost recovery, theproject entities may have a problem in sustaining their operation without some form ofgovernment assistance. Unless tariffs are reviewed and adjusted yearly on a regular basis, ADBshould in the future consider mechanisms for automatic tariff adjustments. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Project Management: Operation and maintenance Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/tangshan-and-chengde-environmental-improvement-project
Guangdong Tropical Crops Development Project (Loan 1175--PRC) | China | Agriculture, Natural Resources, and Rural Development | 2002-05-31 | Income-generating opportunities were not equitably distributed when the financial viability of an operating entity itself was at stake. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financial analysis Crosscutting Issues/Themes: Employment Investment in protected sectors delayed restructuring by operating entities and preserved inefficient institutional arrangements. project cycle stage: Feasibility Lesson Topics: Privatization measures to improve efficiency were ineffective where workers shareholding participation was not accompanied by incentives for higher productivity, or where enterprises were not financially viable. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial analysis Policy & Reform: Privatization Policy & Reform: Public sector reform The lack of realistic market demand projections for commercial operations led, in some cases, to overinvestment and lower returns. project cycle stage: Feasibility Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/guangdong-tropical-crops-development-project-loan-1175-prc
Shenyang-Jinzhou Expressway Project (PRC) | China | Transport | 2002-04-15 | The design and distribution of vehicle weigh bridges and environmental equipment should be determined well in advance, preferably before project implementation, so that procurement and installation could be completed before expressways are fully operational. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Project Management: Procurement Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/shenyang-jinzhou-expressway-project-prc
Second Agricultural Bank of China | China | Finance | 2002-01-15 | Subloan selection should be focused and clearly emphasize the developmentimpact on the entire province selected and on selected areas within the province. The amount of subloans should be based on the optimal requirement of selected priority subprojects. Setting a maximum limit of $5 million for one subloan maynot be a good approach as indicated by lessons drawn from many ADB Development Finance Institution (DFI) projects, where the greater the number of subprojects, the less the focus and the greater the risk. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Project Management: Risks/Risk management Country Context: Prioritization The evaluation of small, rural projects has to be strengthened. Smallmultisectoral subprojects should be evaluated on the basis of their economicimportance and the development impact on the entire project area. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Project evaluation Project Design: Subprojects Sector Related Issues: Rural development The project put a good deal of effort into providing the subprojects with creditfacilities and strengthening the development finance institution's (DFI's) institutional capability in managing thefunds. However, the project made less effort to enhance the capability of the borrower of thefunds which was crucial to the success of the project. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Subprojects Capacity Development: Capacity building The technical assistance (TA) provided to the executing agency could also have addressed the fundamental issues ofits banking reform and helped it improve its financial status in areas such as reducing its nonperforming loans. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Executing/Implementing agencies Policy & Reform: Reform To assure consistency, certain compromises have to be considered in settingtargets for possibly conflicting factors, such as poverty reduction and job creationversus a high project financial internal rate of return (FIRR) and economic internal rate of return (EIRR) and job creationversus technology upgrading. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financial analysis Crosscutting Issues/Themes: Employment Capacity Development: Technology/Technology transfer Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/second-agricultural-bank-china
Urban Development Advisory Technical Assistance to the People's Republic of China | China | Multisector | 2001-12-31 | ADB needs to ensure that sufficient resources are allocated for meeting the requirements of the TA terms of reference, for the supervision of TA implementation, and for translation services. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance TAs need to be more thoroughly prepared such that data availability is adequately assessed to enable the appropriate selection of areas for in-depth study. project cycle stage: Feasibility Lesson Topics: TAs that serve as demonstration or pilot projects should include in their design mechanisms to disseminate the results and findings to a wider audience in the country. project cycle stage: Design Lesson Topics: | Technical Assistance Performance Evaluation (TPER) | Unsuccessful | http://www.adb.org/documents/urban-development-advisory-technical-assistance-peoples-republic-china
Heilonjiang Expressway Project (Loan 1324-PRC) | China | Transport | 2001-08-31 | Project experience underscored the need for more rigorous reviews of design features at appraisal and during implementation so as to identify early and/or avoid technical and safety design deficiencies. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Project administration Sector Related Issues: Roading There is need for more rigorous attention to elucidating the project rationale, purpose, targets, and how these will be realized, so that there is a clear basis for monitoring and evaluating benefits. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/heilonjiang-expressway-project-loan-1324-prc
Shenyang-Benxi Highway Project and Jilin Expressway Project (Loans 1168/1262-PRC) | China | Transport | 2000-10-31 | In future expressway projects, noise should receive more attention in project design and construction. Suitable antinoise mitigating measures should be considered before project construction. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Sector Related Issues: Roading Pavement cracks and ice slab formation inside tunnels, which have occurred in the two project expressways, should call attention to improved and adapted road pavement design when an expressway project is located in northern areas with low temperatures. As a minimum, expansion joints installed on the expressway pavement would be required to correct for thermal shrinkage during periods of severe cold weather. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Roading The need for a proper appraisal methodology initially in the Shenyang-Benxi Highway Project constitutes an important lesson that was rectified in an ensuing TA. project cycle stage: Appraisal Lesson Topics: There should be standard indicators for evaluating project economic and social impacts. For example, there were no indicators of railway traffic data either at project appraisal or at project completion, for both Changchun-Siping Expressway and Shenyang-Benxi Highway; nor was there any socioeconomic baseline survey against which to gauge discernible impacts on the welfare of beneficiaries attributable to the expressways operation. project cycle stage: Feasibility, Appraisal Completion Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Monitoring & Evaluation: Project evaluation Project Design: Appraisal Project Design: Project design Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/shenyang-benxi-highway-project-and-jilin-expressway-project-loans-11681262-prc
Shanghai Nanpu Bridge Project (Loan 1082-PRC) | China | Transport | 1999-11-30 | A comprehensive and participatory approach to project preparation, taking into account beneficiary needs, appears to have been an important factor in the success of the project. The benefits of a planned and well-coordinated housing and business resettlement scheme with adequate prior consultation withaffected parties and installation of all necessary public services before relocation of residentsand firms likewise contributed to successful resettlement. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Methodologies/Approaches: Participatory approach Although reliable forecasts of traffic volumes are difficult to achieve, more realistic forecasts could have helped planners anticipate the design limitations to meet traffic volumes, As the economic costs of underdesign can be significant, there is a need for a more professional approach to forecasting traffic volume and understanding of the implications forecasting has on the engineering design of infrastructure projects. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Transport planning In view of the siginificant costs of TAs and the lack of tangible impact, strengthening the follow up reporting systems on advisory TAs would help enhance their effectiveness. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/shanghai-nanpu-bridge-project-loan-1082-prc
Country Assistance Program Evaluation for the People's Republic of China (1998) | China |  | 1998-12-31 | Although the TA ratings determined by ADB have been good, ADB staff resources devoted to TA have been inadequate to perform the required supervision during implementation. On average, less than ten days of staff time are spent per TA per year on supervision. There is a need to increase staff input for supervision to improve the effectiveness of ADB's TA operations. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Project supervision Capacity Development: Human resources management Projects financed by ADB in the PRC were mostly identified and formulated by the government. The government has been not just the owner but author of its projects. The EAs took pride in their capability and sometimes entertained little or no intervention in their project designs. This is a reflection of strong ownership that ADB has often advocated. This study provides a first insight into the development outcome for projects that were approved and completed during the formative years (1986-1990) of PRC operations. This outcome was generally less than satisfactory (60 percent success rate). This should be a signal to the PRC planning authorities that weaknesses exist in their project formulation and planning processes. That the government is aware of this, is demonstrated by the recent creation of an inspectorate within the State Development Planning Commission. The mission of the inspectorate is to ensure and improve project quality. This will open an avenue for ADB to pursue active policy dialogue with the PRC planning authorities and enable ADB's involvement in the early project formulation phase rather than at the postfeasibility study stage. project cycle stage: Country Partnership Strategy Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Policy & Reform: Policy matrix The COS responded well to the internal needs of ADB, although the initial COSs were too broad to be operationally effective and measurable. The COS documents were perceived by the PRC as ADB-driven without much relevance to the PRC reality. This explains the frequent inconsistency between the COSs and the CAPs, based largely on projects selected by the PRC authorities. The COS document should conform to the objectives of the PRC or be more transparent about the difference in strategic views. This would provide the basis for identifying the instruments available to ADB to achieve its strategic objectives. The COSs and the CAPs should more adequately analyze the range of action parameters available to ADB, including distribution between lending and nonlending operations, lending by sector and region, and TA and ESW operations. The COSs should also develop indicators to monitor long-term development objectives and prepare action plans to correct deviations from those objectives as they occur. In defining the strategic objectives, there should be frank discussion with PRC authorities as to their feasibility in view of ADB constraints and the PRC policies. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Lending modality Modality: Technical Assistance Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Problem identification The PRC's need for financial institution building, resources, and policy reforms is enormous, and ADB's assistance program is relevant in the sense that it can contribute to the needs of the country. However, ADB's resources are limited and have been scattered thinly over many sectors and regions without creating a critical mass for significant impact. ADB should aim at identifying niches for itself, taking into account its limited resources and staff constraints, rather than trying to meet the PRC's needs over a wide spectrum. project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Capacity Development: Capacity building Policy & Reform: Policy reforms/framework Methodologies/Approaches: Targeting The strategic objectives outlined in COS 1991 and COS 1997 tend to be too inward looking to gain operational support of the PRC planning authorities. The CAPs, which present the multiyear rolling programs of loans and TAs, are often a reflection of the decisions made by the PRC about their investment programs and their allocations to the aid agencies, with little linkage to the strategic objectives of ADB. The CAPs embodied the borrowing program of the PRC rather than operationalization of the COS. There is a need to realistically assess the constraints faced by ADB's operations in the PRC and resolve the differences of views between ADB and the PRC. Operations should focus more sharply on specific strategic issues where ADB has a comparative advantage, for example, the environment and fiscal policy reform areas. The CAP should in turn more fully reflect the strategic directions of operations agreed between ADB and the PRC. This requirement is more adequately met by the 1997 and 1998 CAPs. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Public governance Modality: Technical Assistance Policy & Reform: Policy reforms/framework The TA program is an important nonlending instrument that could improve project quality, strengthen institutional capability, and contribute to policy reforms. The TA program was found effective in areas such as environment sector and fiscal policy reforms and less effective in other areas. In general, the TA resources have been scattered over a large number of operations with inadequate coordination and supervision. There were also no strategic objectives formulated for the TA operations, and many TAs were supply-driven to satisfy ADB's own internal needs. There is inadequate ownership on the part of the PRC's EAs for many TAs implemented. The lesson of experience for the PRC is that TA resources can be very effective instruments to bring about capacity building and policy reforms. The ways and means of using ADB's TA resources more effectively should be considered more fully in COS and CAP documents. Cluster TAs to assist the long-term development of niche counterpart agencies should be defined. For better management of TA resources, the staff in project departments should be involved more fully in TA programs. There is also a need to consider how TA funds could be used more effectively to assist staff in designing and implementing TA projects. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Public governance Modality: Cluster operations Modality: Technical Assistance Monitoring & Evaluation: Project evaluation Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Ownership Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation There is a need to formulate a more focused TA program supporting clearly defined strategic objectives. COS documents should incorporate a section on TA strategic objectives. Future CPMs should make concerted efforts to focus the TA program to link directly with the strategy objectives of COS and the lending program of CAP. project cycle stage: Country Partnership Strategy Lesson Topics: | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-peoples-republic-china-1998
Hexian Pulp Mill Project (Loan 937-PRC) | China | Education | 1998-12-31 | A different ownership structure would have helped ensure both the financial commitment and the managerial and institutional involvement in project planning and execution. The project proponent did not seem to have been aware of the financial implications of the project and the fatal consequences of delayed allocation of owner s equity. Commercial projects should be supported only if an entity exists that can financially and managerially back the proposal. The project s focus on building technical expertise for operating the mill was useful, but inadequate because on the managerial side, it focused on project implementation capacities and neglected the need to develop adequate managerial capacities for mill operations. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Technology/Technology transfer A project in a technically sophisticated field such as pulp making requires that the consequences of technology choices on production cost, output and its prices are considered at the design stage. The Appraisal Report lists equipment items without detailed technical specifications, which, however, would have been needed to accurately estimate the cost of these items. The absence of this information and the approach to average out cost estimates indicate that implications for technology choice and subsequent operating parameters were ignored. In addition, the choice of technology affects the layout and cost of civil works, so the lack of specificity may have had an effect on the cost of this component as well. As a result, scope and choice of technology had to be altered. This experience indicates that technical design specifications ought to be determined prior to setting budget ceilings. project cycle stage: Design Lesson Topics: Project Design: Appraisal Project Design: Project design Capacity Development: Technology/Technology transfer The project design unsuccessfully tried to combine a number of conflicting factors. While the mill size of 50,000 t/yr was considered below the economic scale of production, price assumptions made in the economic and financial analyses indicated the project was viable. The Appraisal Report foresaw an expansion of the mill in the late 1990s to 100,000 t/yr or 150,000 t/yr. However, it did not consider whether available wood resources would be adequate to support such a mill size, although the preparatory TA consultants had raised doubts that they would be. In addition, the layout of the mill does not lend itself to the suggested expansion, which raises the question whether plans for such expansion had been considered at the local level during the design stage. It seems that the project did not have a consistent long-term concept for the mill, and, even less, one that would be conducive to addressing the project objectives. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/hexian-pulp-mill-project-loan-937-prc
Selected TAs for the Development of Financial Intermediation in the People's Republic of China | China | Finance | 1998-12-31 | EAs and the government have expressed general concerns about potential negative effects related to heavy reliance on a single consulting firm. TA performance improves when (i) ADB has a medium/long-term relationship with a concerned institution/subsector; (ii) key officials and agencies have wide-ranging and in-depth involvement in the TA; and (iii) TAs have practical, action-oriented outputs. project cycle stage: Implementation, Completion Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation To further improve accountability of TA operations in the financial sector, ADB could (i) strengthen monitoring of overall sector developments, while ensuring that it has a full grasp of the financial and operational performance of the targeted institution and/or subsector; and (ii) standardize financial terms used across similar TAs, adopt performance benchmarks and refer to those benchmarks during reviews. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Modality: Technical Assistance Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation With respect to country-specific knowledge and client orientation of international consultants, ADB will want to (i) put sufficient weight on country experience in consultant selection, ensure an effective use of domestic consultants, and use a fully participatory approach in TA conceptualization and implementation; and (ii) introduce some enhancement measures towards more active communication between the EAs and consultants, and disincentive measures against excessive 'in-and-out' and turnover of consultants during implementation. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Procurement Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/selected-tas-development-financial-intermediation-peoples-republic-china
Shanxi-Xiaoliu Railway Project (Loan 948-PRC) | China | Transport | 1998-03-31 | Realistic traffic forecasts are essential, and should have a sound basis. Where traffic forecasts are contingent on developments outside the control of the project operating authority, an effective project management system should be established to monitor their progress. The initial analysis should carefully review the firmness of such external developments, and this should be taken into account in risk assessment. Traffic forecasts for railway projects should invariably include a computerized probability risk assessment . Passenger traffic forecasts should take into consideration the low quality of service of a predominantly freight railway compared with possible alternatives like road transport. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Project management Project Management: Risks/Risk management Sector Related Issues: Roading Sector Related Issues: Transport planning Methodologies/Approaches: Targeting The railway is only one source of economic development in the area and it is difficult to isolate any adverse effects that the railway operation alone may have had on the local environment. However, the railway and related operations will further burden the assimilative capacity of the already polluted surroundings. Instead of focusing on the impacts of the railway, it is likely to be more effective to improve the assimilative capacity of the environment by promoting pollution reduction efforts in the most cost-effective manner. These efforts need to include not only project-specific measures, but also more general considerations such as reducing subsidies on fuel, encouraging cleaner and more efficient technologies, and promoting public awareness and participation in environmental protection. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial management Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Transport planning Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation There is a need to establish, early in the project planning stage, a fully functional executing agency responsible for both construction and operation of a railway, and to ensure that the institutional structure is appropriate for such operations. If construction is to be undertaken by a separate agency, the operating company still needs to be in place, involved in both planning and construction. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Transport planning To prioritize pollution control efforts and to evaluate the cost-effectiveness of pollution control instruments, it is essential to compare the reduction in the pollution with relevant costs of abatement and improvement in health indicators. Further efforts are needed to integrate environmental information (pollution from point sources, costs of abatement, environmental quality data) with socioeconomic data and health indicators, not only to properly evaluate the most cost-effective pollution control instruments, but also to measure the progress made from past interventions in environmental management. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Monitoring & Evaluation: Project evaluation Project Design: Project design Country Context: Prioritization Sector Related Issues: Health and sanitation management Where a project generates traffic that also travels over non-project lines, the handling capacity of such lines should be assessed at loan appraisal, with any necessary improvements to them incorporated in the project evaluation. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation Project Design: Appraisal Sector Related Issues: Transport planning Where economic benefits of avoided road improvements are included in a railway project EIRR, future road development and upgrading plans should be confirmed by the local planning offices and highway authority. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Transport planning Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/shanxi-xiaoliu-railway-project-loan-948-prc
Selected Environmental Advisory Technical Assistance Sector to the People's Republic of China (1997) | China | Multisector | 1997-12-31 | A clear strategic vision on the part of ADB, and pursuing it with determination, can result in a series of TAs going beyond the immediate stated objectives of each to become a catalyst for broader action. These TAs provided the opportunity of a dialogue for the revision of existing EIA regulations to harmonize EIA procedures in the country and multilateral development banks, and the establishment of new policies for managing EIA. They also brought the climate change issues to the forefront in the country's environment policy agenda, resulting in the adoption of a practical strategy to reduce GHG emissions. A series of TAs can thus be used to provide policy advice to further the government's agenda. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Modality: Cluster operations Modality: Technical Assistance Policy & Reform: Policy reforms/framework Clearly defined criteria and milestones for measuring institutional progress can ensure accuracy in defining objectives and scope of the TA, ease monitoring, and increase the effectiveness in measuring implementation progress. The absence of such a criteria allowed the provision of an MIS under the garb of an EMIS. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Management: Management information system Capacity Development: Capacity building High levels of ownership and commitment to TAs, appropriate and collaborative counterpart staff, proper selection of trainees and their keeness to learn, effective marketing of training to decision-makers by assimilating them into the training, and selection of good international consultants and their close and effective interaction with best available local consultants make a good recipe for TA success. The capacity of the EA is also a determining factor for TA success. A combination of local and international consultants can help overcome the limitations of both. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Human resources management Capacity Development: Ownership Learning from the experience of the early TAs, it is important to recognize the usefulness of needs assessment TA when ADB embarks on helping a new sector in a country. This would enable ADB to visualize a cluster of TAs in an appropriate sequence. Each TA within the cluster can be narrowly focused and adapted to the capacity of the EAs and yet be sufficiently flexible to learn from the previous ones. project cycle stage: Feasibility Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Capacity Development: Capacity assessment Capacity Development: Capacity building | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/selected-environmental-advisory-technical-assistance-sector-peoples-republic-china-1997
Supporting Policy Analysis in the Ministry of Finance in the People's Republic of China | China | Public Sector Management | 1996-12-31 | Technical assistance (TA) must provide appropriate levels of financing for the inputs required. Matching TA inputs and outputs to a predetermined figure does not make for optimal results. project cycle stage: Design Lesson Topics: | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/supporting-policy-analysis-ministry-finance-peoples-republic-china
Jiangxi Expressway Project | China | Transport | 1996-11-19 | A road safety campaign should be promoted among affected persons and drivers before expressway completion to avoid unnecessary traffic accidents along the expressway. Many of the recorded traffic accidents involved drivers who were not familiar with road conditions and traffic signs and unauthorized road crossing by local residents, who preferred to cross directly rather than use the underpasses nearby. Many sections of the fencing have been removed to gain access to the expressway. Underpasses should be designed so that they are centrally located and have good natural drainage to encourage their frequent use. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Roading Policy & Reform: Information dissemination/Public awareness More conservative traffic projections, particularly for the initial years of operation, should be used to ensure more robust financial performance of the expressway operator. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Sector Related Issues: Roading While the land prices and resettlement compensation rates paid to affected persons were in line with Land Administration Law of the People's Republic of China, the government has revised rates upwards on a number of occasions since the resettlement plan was completed. Many of the relocated households had either used up their lifetime savings or borrowed from relatives and friends in order to construct better and bigger housing. This created dissatisfaction among 24% of the relocated persons, who said that cash compensation for housing should be sufficient to build bigger and better housing. More frequent dialogue with affected persons and clearer explanations on compensation entitlement would have minimized their dissatisfaction. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/jiangxi-expressway-project
Fishery and Coastal Marine Resources Management and Development in East China Sea in the People's Republic of China | China | Agriculture, Natural Resources, and Rural Development | 1995-08-31 | TA evaluation confirmed that a project framework approach is essential during the TA design stage so that verifiable input and output indicators could be specified and monitored. Such approach will also assist in TA implementation, supervision, and evaluation. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Indicators The TOR for the TA should provide some degree of flexibility to enable midterm modification of project design and approach, if necessary. In this respect, ADB supervision missions to provide guidance and advice to the consulting team during the inception and midterm stages are crucial for effective TA output. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Project supervision | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/fishery-and-coastal-marine-resources-management-and-development-east-china-sea-peoples
Qingdao Tire Development Project (Loan 897-PRC) | China | Industry and Trade | 1995-08-31 | In projects involving expansion of capacities, equal attention should be given to monitoring of compliance with environmental standards by existing production plants and appropriate covenants on such compliance should be included in the loan agreement. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Loan Agreement: Covenants Loan Agreement: Loan Agreement Monitoring &amp; Evaluation: Monitoring and evaluation Project experience shows that in preparation of realistic implementation schedules, proper consideration should be given to the degree of familiarity of local agencies with ADB's operational procedures especially in cases when local agencies are being engaged for the first time to implement ADB-financed projects. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration There is a need, during implementation of a project, to monitor carefully not only the procurement of ADB-financed facilities and equipment, but also that financed by the borrower or executing agency to ensure that only equipment and facilities having the required capacity are included in the project. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/qingdao-tire-development-project-loan-897-prc
Water Supply and Sanitation Projects in Selected Developing Member Countries | China, India, Indonesia, Malaysia, Philippines, Sri Lanka | Water and Other Urban Infrastructure and Services | 2002-12-31 | ADB needs to give serious attention of implementing effective sanitation, hygiene, and health promotion programs in its WSS projects. project cycle stage: Design Lesson Topics: Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness An effective demand-side management (DSM) program is a simple and cost-effective alternative to supply expansion, particularly in water-scarce areas. DSM succeeds with political support and appropriate campaigns to promote customer awareness of the need for conservation, as observed in Dalian. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Capacity Development: Ownership Country Context: Prioritization Sector Related Issues: Water resource management As drinking water requirements account to 2 3 liters per capita per day, they do not have to be met only through a piped water supply. Potable water from water treatment plants, as well as smaller quantities from shallow groundwater, may be better delivered when distributed in bottles, either by the water supply company (WSC) or through public-private partnership. Most tropical areas of DMCs are endowed with sufficient annual rainfall for shallow groundwater to be the most accessible and sustainable source of potable water. project cycle stage: Design Lesson Topics: Sector Related Issues: Public-private partnership Sector Related Issues: Water resource management Most water supply and sanitation (WSS) projects experience significant delays in implementation. These delays result from an interplay among institutional, design, policy, and administrative factors that include institutional and capacity constraints commonly encountered in DMCs, overly complex project designs, proliferation of policy requirements of both external funding agencies and recipients, administrative procedures that are not always well understood, and cumbersome domestic procurement procedures and decision-making processes. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project administration Project Management: Project management Project preparation documents should specify a program of feasible and cost-effective tasks, tailored to the situation at hand, that have a high likelihood of reducing NRW to 'reasonable' levels of about 25% 30%, or lower if the situation permits. Leak detection is only one of many options that should be considered. The caretaker approach, currently under development by ADB, is a useful tool to apply coupled with benchmarking the performance of water utilities. project cycle stage: Feasibility Lesson Topics: Stakeholders' roles in planning, implementing, and operating water supply systems have been limited in the projects reviewed in the IES. Perhaps the greatest obstacle to successful participatory development is convincing institutional players that it is indeed possible. Maximizing stakeholder involvement in project decision-making and implementation goes against the institutional culture in some DMCs. Success stories from Malaysia and the Philippines show that often just one committed person can lead the way and achieve customer participation. Consistent with ADB policies that specify the importance of such participation, project designs should make a more concerted effort to realize this objective. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Country Context: Cultural constraints Sector Related Issues: Health and sanitation management Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation Support for implementing these processes, as in the two tariff study TAs in the PRC, would increase the likelihood of WSCs meeting financial targets and achieving long-term sustainability. project cycle stage: Feasibility, Implementation Lesson Topics: | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/water-supply-and-sanitation-projects-selected-developing-member-countries
Deposit Insurance Establishment: Technical Assistance Completion Report | China, Mongolia | Finance | 2015-08-01 | Efforts to support a DIS (deposit insurance system) must consider the added time needed to obtain strong and broad support from government, the banking sector, and other stakeholders. Movement from a 'no fee' implicit guarantee system, to a premium-based transparent scheme, can confront political economy constraints that must be overcome. These hurdles should be considered within the project timeframes and outputs. Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/deposit-insurance-establishment-tcr
People's Republic of China and Mongolia to Support Municipal Finance Reforms: Technical Assistance Completion Report | China, Mongolia | Public sector management | 2015-08-01 | The design of the TA (technical assistance) responded to the considerable interest within the PRC (People's Republic of China) and Mongolia in the public finance issues, and helped ensure that ADB was an active participant in dialogue on public finance issues in Mongolia. But the TA was too small to fully meet the demand in the PRC, and other sources of support from ADB were preferred by the PRC authorities. Larger TAs with clear backward and forward linkages to other ADB support are likely to be more effective and efficient in the PRC. Project cycle stage: Design | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/prc-and-mongolia-support-municipal-finance-reforms-tcr
Strengthening Carbon Financing for Regional Grassland Management in Northeast Asia: Technical Assistance Completion Report | China, Mongolia | Agriculture, Natural Resources, and Rural Development | 2015-02-01 | The TA (technical assistance) concluded that carbon financing in the grassland and livestock sector is feasible, and can provide an incentive for sustainable grassland management. Sustainable grassland management results in improved incomes while improving environmental quality and reducing desertification leading to dust storms. Carbon markets are constantly evolving; and although the current pricing is low, government support and buy-in makes the use of carbon financing feasible. The PRC (People's Republic of China) is currently developing its own national carbon markets, and the Mongolian government supports the use of carbon finance. Project cycle stage: Feasibility, Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-strengthening-carbon-financing-regional-grassland-mgt-northeast-asia-tcr
Economic Recovery Support Program - Subprograms 1 and 2: Completion Report | Cook Islands | Finance, Health, Public Sector Management | 2015-09-15 | The provisions of funds under a program loan will generally only have an immediate impact on the overall level of economic activity if a pipeline of projects is in place when the funding becomes available. This was not the case when the ERSP (economic recovery support program) subprogram 1 loan was disbursed, but the delay in capital project construction to ensure more sustainable and beneficial projects were implemented was desirable. The Cook Islands governance of infrastructure projects had improved by the time of the release of subprogram 2 funds with project priorities and planning further advanced, providing a number of potential projects that could immediately use the ERSP funding assistance. The program modality is beneficial in that it enables the recipient government implementing agency to maximize the use of local suppliers of goods and services through appropriate project selection and contract package sizing. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/coo-economic-recovery-support-program-subprograms-1-and-2-pcr
Asset Management for Sustainable and Improved Infrastructure Services Delivery: Technical Assistance Completion Report | Cook Islands | Water and other urban infrastructure and services | 2015-08-01 | The scope of work in this S-CDTA (small-scale capacity development technical assistance) was fairly extensive. Within the space of just over a year, the S- CDTA undertook to introduce and implement asset management in 3 SOEs (state owned enterprises), which from industry experience can be a two to five year process. While the SOE's fully embraced the concept of asset management, organizationally they were not ready for it. A better approach may have been to spread the components of the S-CDTA over a longer timeframe and incorporate a change management component in the scope to prepare the SOE's organizationally, for the introduction and commitment to asset management. It is envisaged however, that the Ports and Power (Te Aponga Uira) Authorities will likely advance more quickly and hopefully they can help the other organizations to advance their asset management practices. While the Cook Islands was ready for and needed a new AMIS (Asset Management Information System), the quality and state of the asset data available was not sufficiently developed for use in the AMIS. A significant amount of time and effort was required to complete the datasets. The Cook Islands have quite a commitment ahead of them to ensure good quality data is input and maintained within the AMIS. Project cycle stage: Design, Implementation, Operation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/coo-asset-management-sustainable-and-improved-infrastructure-services-delivery-tcr
Avatiu Port Development Project: Completion Report | Cook Islands | Transport | 2015-06-29 | A major lesson stemming from the project is its inadequate preparation at appraisal, which caused problems by requiring supplementary financing, which was necessitated by exchange rate fluctuations and cost underestimation. About 55% of the increase in costs was attributable to exchange rate movements, and 45% to an underestimation of the cost. Cost estimates at appraisal were based on an exchange rate of NZ$1.00 = $0.67, whereas the revised cost estimate was based on the prevailing rate of NZ$1.00 = $0.76. More time needs to be taken at appraisal to thoroughly assess costs, especially in an isolated location such as the Cook Islands. At the supplementary financing stage it appears that the economic reevaluation took for granted that the benefits were as envisaged at appraisal, and no reexamination was made of the benefits on which the appraisal was based, despite the rapid decline in the number of cruise ship visits, and the fact that ships were not docking in Avatiu Port. Instead it was assumed that the benefits calculated at appraisal would continue. There were a total of three reallocations following the supplementary financing. This shows a lack of attention to detail when the project was designed and allocations made to different loan categories. It is essential that ADB carefully examine possible cost increases during project design. project cycle stage: Design, Feasibility, Appraisal | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/avatiu-port-development-pcr
Waste Management Project | Cook Islands |  | 2005-12-15 | Delay in the adoption of revenue generation measures will affect the sustainability of waste management infrastructure. The capacity and funding for O&M should be carefully assessed for all future infrastructure projects. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity assessment Land acquisition remains difficult and should be avoided and minimized. Where land must be acquired from customary landowners, the acquisition process, including compulsory action, should be started as early as possible. project cycle stage: Feasibility Lesson Topics: Project management assistance, provided as an integral part of a project, can enhance the executing agency's implementation capability. A strong project management unit and project steering committee and the active involvement of the implementing agencies was key to the project's success and similar arrangements should be part of future projects. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/waste-management-project
Education Development Project in the Cook Islands (Loan 1317-COO[SF]) | Cook Islands | Education | 2004-07-31 | ADB s inception mission of any future project should allow sufficient time and include staff from other concerned divisions in ADB. project cycle stage: Concept Lesson Topics: Project Design: Problem identification Methodologies/Approaches: Holistic approach Assessment of the executing and implementing agencies implementation capacity should be done during project formulation. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment For any education sector project, a sector strategic and action plan should be developed to provide future directions of overall sector development. project cycle stage: Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Education Methodologies/Approaches: Targeting If significant training is provided in any future project, particularly international training, prospective trainees should be required to sign an agreement for returning to work in the trained areas for at least a few years. project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity building Capacity Development: Human resources management If the attached technical assistance of any future project cannot provide the outputs (e.g., preparation of a strategic and action plan) as planned, ADB review missions should adjust the project scope to do it. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Project management In any small-island country, with a limited pool of people having project experience, establishing a separate project implementation unit (PIU) for every new project might not be efficient. A permanent, single pan-government PIU should be established, comprising experienced permanent staff in key positions. For each new project to be implemented, one or a few subcontracted specialists in that particular sector can be added to the PIU team. project cycle stage: Feasibility Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project administration | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/education-development-project-cook-islands-loan-1317-coosf
Third Cook Islands Development Bank Project | Cook Islands | Finance | 2003-10-15 | Appraisal of the Third Cook Islands Development Bank Project (CIDB III) underestimated the consequences of the layoff program advocated under the Economic Restructuring Program (ERP). Instead of retrenched public servants investing their funds locally to start up their own businesses, most chose to emigrate. Accordingly, some of their loan accountswith CIDB went into default. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Social protection Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Policy & Reform: Public sector reform Methodologies/Approaches: Program Approach As evident after the merger, being directed and controlled by the government did not prepare the Cook Islands Development Bank (CIDB) and Cook Islands Savings Bank (CISB) well for the transition to Bank of the Cook Islands (BCI) and operating in a competitive and aggressive banking environment. CIDB was not accustomed to a performance-based or market-oriented culture. BCI should import the services of an experienced international expert to implement change management and manage BCI into a profitable institution. In some respects, the postmerger management structure strayed from the original blueprint contained in the consultant's report. project cycle stage: Completion Operation Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Consultants Capacity Development: Capacity development Policy & Reform: Reform Policy dialogue under the Economic Restructuring Program (ERP) altered the rationale and implementation plan of TA 2404, which was processed in conjunction with the Third Cook Islands Development Bank Project (CIDB III). The project benefits expected to accrue to CIDB were lost to the Small Business Enterprise Center (SBEC), resulting in an unsustainable training program and loss of credit advisory support. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity building Policy & Reform: Policy matrix Policy & Reform: Public sector reform Methodologies/Approaches: Program Approach The loan of US$3.0 million equivalent was considered ambitious, bearing in mind the fact that the Second Cook Islands Development Bank Project (CIDB II's) US$1.5 million equivalent was only 87% used and the remaining balancecanceled. Except for the merger exercise, a higher amount would have been canceled, due to the low rate of use resulting from the depressed investment demands and sluggish economic growth experienced between 1996 and 2001. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-cook-islands-development-bank-project
HIV/AIDS Prevention and Capacity Development in the Pacific | Cook Islands, Kiribati, Marshall Islands, Micronesia, Nauru, Palau, Papua New Guinea, Samoa, Solomon Islands, Timor-Leste, Tonga, Tuvalu, Vanuatu | Health | 2011-12-01 | There are several lessons from the project. First, even if a project is aligned with regional strategies, designs need to incorporate sufficient national consultation and consider country absorptive and technical capacity and commitment. Second, efforts to strengthen routine surveillance and laboratory capacity will achieve only limited success where health information systems and laboratory services are weak. Third, an executing agency's ability to implement project activities within set timeframes is diluted where there is limited PMU capacity, a lack of experience with ADB procedures, and inadequate executive oversight. Fourth, establishing a project steering committee is challenging where separate development partner committees already exist to oversee arrangements for Pacific countries. Fifth, national M&E remains a challenge due to lack of capacity and minimal regional support to assist participating DMCs. While regional evaluations of some activities have taken place, they need to focus on impact or outcome indicators rather than on the process of implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/hiv-aids-prevention-and-capacity-development-pacific
Third Road Upgrading (Sector) Project: Completion Report | Fiji Islands | Transport | 2015-09-18 | A lack of data and documentation was noted throughout project implementation. The project procurement-related audit noted this, and, as determined by the project completion review mission, data is unavailable within the executing agency. For example, there are no traffic counts after 2009, only two benefit monitoring evaluation reports were available, and the project completion report lacks important information. ADB needs to ensure during project implementation that data requested is provided by the executing agency. project cycle stage: Implementation, Completion The consultant supervision costs were the responsibility of the executing agency. As was previously noted, the delays in civil works resulted in increasing consultant supervision costs and the executing agency decided to terminate the consultants and recruit individual consultants. The consultants were paid by the executing agency and the change was made over ADB's objections. For future projects, it would be better for ADB to pay for consultant supervision, as more control will then be available for implementation of the project and, if necessary, consistency will be obtained by extending the consultant supervision contract. project cycle stage: Implementation One of the contracts issued that was declared misprocured by ADB because the bidder failed to meet minimum post-qualification financial threshold requirements, and which was then paid for by the executing agency, was completed successfully and within budget by the national company. That work was of high quality. Though appointment of national contractors for civil works was one of the project's key goals as a means of encouraging development of the private sector for future work, this was a case in which ADB's procurement guidelines blocked the loan financing of a national contractor who, as it turned out, was capable of doing the job. It is recommended that, for future contracts, means be found to introduce greater flexibility into the post-qualification financial criterion in conjunction with a close review of the company's past experience. In such cases, the criterion might be flexibly adjusted prior to contract award through close consultations between the executing agency and ADB. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/fij-third-road-upgrading-sector-project-pcr
Fiji Ports Development Project (Loan 1902-FIJ) | Fiji Islands | Transport | 2011-12-19 | 1. The project could have benefited from more careful preparation through a small-scale project preparatory technical assistance (PPTA). The project was prepared through a sequence of four processing missions, without the benefit of dedicated PPTA. Evaluation noted weaknesses in the project design such as poor formulation of the design and monitoring framework and methodological shortcomings in the EIRR calculation. The unexpected long delay between the end of the last processing mission and the project s approval following the political instability during 2000 2002 provided ample opportunity for a more complete preparation. [Main text, paras. 8-9,28-31,70-73,95] project cycle stage: Design, Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design 2. A more rigorous risk assessment during project processing could have led to better project design as well as better monitoring of key assumptions during implementation. Among other activities, the project processing missions could have effectively consulted key project stakeholders and carefully reflected key impact and output assumptions that could affect project performance. For example, decrease in the port service charge by 50% in 2009 and its elimination by 2010 was cited as a project benefit, but this would have required agreement of the shipping agents and companies to implement. This was a key impact assumption overlooked during the project preparation. The same applies to the Lautoka reclamation component, which should have been undertaken only after commitment by project stakeholders had been obtained. This could have been highlighted as a key output assumption for sustainable utilization of the reclamation area. [Main text, paras. 29,71,94,96-97] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Methodologies/Approaches: Consultation/Participation 3. Higher priority in ensuring that baseline data was collected and reported during project implementation could have ensured a more robust evaluation. The lack of baseline data hampered analysis for both the self- and independent project evaluation. Subsequent to the project completion report, Fiji Ports Corporation Limited, and Ports Terminal Limited have introduced a more systematic performance management system, but port statistics provided to the independent evaluation mission were still insufficient. The absence of these baseline data targets made independent evaluation of the project considerably more difficult. [Main text, paras. 34,36,98] project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/fiji-ports-development-project-loan-1902-fij
Low Income Housing Development Project (Loan 1005-FIJ) | Fiji Islands | Finance | 1999-12-31 | Access to affordable land, with title, remains an essential element of meeting the housing needs of low-income families. Unless provided with affordable housing, such families will establish informal housing characterized by inefficient spatial arrangements and substandard services that will require costly measures to correct at a later stage. project cycle stage: Feasibility Lesson Topics: Care is needed in defining target groups to avoid having too broad groupings. Overly broad definitions can result in some parts of the group being left out even if the project achieves its physical targets. Such missed segments would normally be the more difficult to help, and perhaps the ones in greater need. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Methodologies/Approaches: Targeting Care is needed in preparing projects to avoid situations where project outputs depend on policy changes that are also to be generated under the project. Where substantial policy change is required and is expected to be incorporated into investment components, it would seem prudent to initiate the policy development prior to embarking on the investments. This may mean dividing development into two phases, with the policy work in the first phase and investment in the second. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Policy & Reform: Policy reforms/framework Public sector-provided housing is more expensive and less efficiently provided than that built by individuals or through NGOs. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Private sector Sector Related Issues: Urban sector/development Methodologies/Approaches: Civil Society Participation The growth in informal housing highlights the difficulties of the lower income group in acquiring formal housing, and points to the need to lower subdivision and housing standards. project cycle stage: Feasibility Lesson Topics: The project experience where the achievement of development objectives was not given much attention during implementation highlights the appropriateness of ADB s newly implemented project supervision arrangements that require specific attention to development objectives along with implementation issues. project cycle stage: Implementation Lesson Topics: Where entities in authority are expected to operate in a commercial fashion so as to recover costs and achieve financial performance targets, they may not then be appropriate for maintaining an overview of the sector and operating the monitoring system. Such a role requires an entity that is removed from commercial considerations and can focus on national objectives. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Policy & Reform: Reform | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/low-income-housing-development-project-loan-1005-fij
Sigatoka Valley Rural Development Project (Loan 781-FIJ) | Fiji Islands | Agriculture, Natural Resources, and Rural Development | 1997-11-30 | A careful analysis of institutional capacity and arrangements is indispensable for integrated rural development projects where coordination among different government agencies is critical. Where weaknesses are identified, the project design should include strategies and project interventions to directly address these weaknesses. project cycle stage: Feasibility Lesson Topics: Project Design: Problem identification Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Institutional analysis Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach Preparation of projects based on unfounded assumptions in the absence of rigorously collected data can spell disaster for certain project components. Assumption of groundwater availability is an avoidable error, as that of the inclusion of a large-scale cold storage capacity near the valley. The disproportionate public sector intervention for the cold storage facilities indicated a tendency towards allocation of public funds without consideration of their opportunity costs. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Data collection and management Sector Related Issues: Irrigation management Sector Related Issues: Water resource management The formulation of integrated rural development projects is a complex process requiring substantive consultation with all stakeholders to adequately identify all constraints, aspirations, and developmental potential, and to develop effective implementation and coordination mechanisms. Differentiated consultation with beneficiary groups requires time and resources, but can be a good investment in terms of improved project design and more efficient project delivery. Where data are scarce, the project preparatory technical assistance study could be conducted in two phases: the first for the collection of technical data and the second one for participatory project preparation. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Project administration Project Management: Project management Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach The project management team should be located within the project area, and mechanisms for regular contact with farmer beneficiaries (extension activities, focal farms, and training) should be provided. Such an arrangement would give project management the opportunity to better understand beneficiary constraints and aspirations, and to adjust project components and implementation arrangements as required. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Capacity building Sector Related Issues: Extension service Where basic assumptions concerning important project components are found to be no longer valid, the need for formal reformulation of the scope and the nature of project interventions should be seriously considered. This should also be done where major policy reforms are implemented after project formulation. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/sigatoka-valley-rural-development-project-loan-781-fij
Agriculture Diversification Program (Loan 906-FIJ) | Fiji Islands | Agriculture, Natural Resources, and Rural Development | 1996-11-30 | Agricultural diversification was an important objective and the urgency of providing the program loan to meet the structural adjustment support may have made it impractical to undertake detailed sectoral work. However, this should not have prevented ADB from having a more definitive plan of action for follow-up activities, apart from the intentions to continue policy dialogue. Likewise, ADB should have stressed the need to have effective coordination mechanisms. project cycle stage: Implementation Lesson Topics: Modality: Program Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation It is recognized that many policy reforms require time to have a demonstrable impact. The 1996 Fiji agricultural sector study states that 'the transition to private sector led (development) has not been easy. The private sector has found itself faced, sometimes with reluctance, with unfamiliar responsibilities. Deregulation means that the private sector (farmers, processors, and exporters) has to lead the way and set the course for the sector (which crops, which markets). The role of the government and its ancillary organizations is still, however, important in facilitating private sector efforts'. A longer term program for sector development is, therefore, necessary in many cases. ADB needs to pay greater attention to sector issues and sector development programs and establish a pragmatic time-frame for policy reforms to make their impact. project cycle stage: Country Partnership Strategy Lesson Topics: Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework The commitment of the government is critical for successful implementation of the policy reform agenda. However, the effectiveness of the implementation of policy reforms and results therefrom (even where there is strong commitment and ownership) demands thorough assessment of the linkages between the reforms pursued and the goals to be achieved. There should also be priorities set to ensure attention to critical issues, particularly when there are large numbers of reforms pursued. There is a strong need to establish performance indicators to monitor progress and make suitable adjustments during implementation. Therefore, policy-based loans should have a policy matrix (logical framework). The policy goals (or expected impacts) should be related to quantifiable and time-bound targets. This will allow effective monitoring and give the opportunity to make mid-course corrections in the pace and scope of the program. It would also provide a benchmark for subsequent evaluation of the impact. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Ownership Country Context: Prioritization Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/agriculture-diversification-program-loan-906-fij
Road Maintenance Sector Project (Loan 912-FIJ) | Fiji Islands | Transport | 1995-06-30 | In small economies, where there is a small number of suppliers, the storage of spare parts of a variety of manufactures is uneconomical, and standardization of equipment should be promoted. In such countries, a package of essential spare parts should be included in the original equipment purchase contract. This would ensure that the new equipment could be operated without major interruptions for at least three years. project cycle stage: Implementation Lesson Topics: Investment in road maintenance has proven to be economically worthwhile and has yielded high returns. Therefore, sufficient funds should be provided through budgetary allocations to ensure that road maintenance is carried out on a sustained basis. project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Operation and maintenance Sector Related Issues: Roading Project experience indicates that the sector loan modality is suitable for road maintenance projects. Under the sector lending arrangements, the appraisal of subprojects can effectively be carried out by the executing agency provided that the selection criteria and the methodology for appraisal including model for economic evaluation are clearly established at the design stage. project cycle stage: Feasibility, Appraisal Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/road-maintenance-sector-project-loan-912-fij
Bank Assistance to the Power Sector in the Pacific Developing Member Countries | Fiji Islands, Kiribati, Samoa, Solomon Islands, Tonga | Energy | 1998-12-31 | ADB provides loans to finance investment costs (procurement, installation, and commissioning of an asset), and not recurrent costs. While financial covenants are normally included in loan agreements to help ensure that resources will be available to cover recurrent costs and to provide for future development (e.g., tariff increases, self-financing ratios, debt service covenants), the utilities often do not have the financial and political autonomy to undertake the steps necessary to meet these conditions. This lack of autonomy has been particularly important in respect to authority to adjust the tariff as required to meet financial targets. In addition, governments often require utilities to support social or political objectives such as extending power to unprofitable rural areas or even providing services in nonpower sectors without a compensating government subsidy. Often, governments restrict tariff increases even as social service responsibilities and their costs are imposed, without direct subsidy. Where noncompensated costs are imposed or where tariffs are restricted below full cost recovery, or both, utility cash flow becomes increasingly restricted, covenants are not complied with, maintenance expenditures decline, performance declines, and project benefits are undermined. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity assessment Sector Related Issues: Energy planning/management Methodologies/Approaches: Targeting Closely allied with institutional strength is the priority (or lack thereof) that a utility places on staff training. As with maintenance, the nature of training is anticipatory in that it supports future development as well as current operations. Effective training requires appropriate budgeting and financial control, planning capability, and capacity to monitor staff performance. Over time, training raises the capability of the utility to deal with operational problems, monitor performance, and undertake measures to improve it, thus ensuring higher returns from given assets. The utilities that have consistently devoted resources to staff training were seen to operate successful projects. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Capacity Development: Capacity building Capacity Development: Human resources management Country Context: Prioritization Difficulties experienced at the start-up of projects related in varying degrees to procurement delays, slow response to and completion of administrative responsibilities by the utility, poor performance by consultants, and technical problems related to poor design or poor contractor performance or both. Some of the problems could have been avoided, or minimized, by closer involvement of ADB in project monitoring during implementation and post commissioning, and greater attention to implementation problems in project design. In general, the Pacific DMC utilities, in which project management skills are especially scarce, will benefit from a higher level of ADB assistance in project implementation. After commissioning, utility financial performance and compliance with loan covenants could be improved through closer monitoring and assistance provided by ADB , especially in the procedures of financial reporting and the techniques for measuring performance and compliance. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Loan Agreement: Covenants Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants Project Management: Procurement Project Management: Project administration Project Management: Project management Project Management: Project supervision Capacity Development: Technology/Technology transfer Sector Related Issues: Energy planning/management Strong institutional capacity, with the utility exhibiting sufficient technical, managerial, and financial depth, is essential for project success. Adequate preventive maintenance in itself is a hallmark of a strong and well-managed institution, as it signifies awareness of corporate long-term interests rather than a focus on immediate needs. It requires a capacity to budget properly to ensure that tools, spare parts, and manpower are available when maintenance must be performed and to keep tools and working spaces in good order. Above all, good maintenance requires skills to monitor technical performance and to understand what the technology needs and to anticipate problems. Good record-keeping systems, essential to system monitoring, are usually allied with good maintenance practices. In general, Pacific DMC utilities tend to be weak in all of these areas, but there are wide differences. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Management: Operation and maintenance Capacity Development: Capacity development Capacity Development: Institutional analysis Capacity Development: Technology/Technology transfer Technical robustness, simplicity of design, and consequent minimization of maintenance requirements are key factors in achieving efficient performance and ensuring asset survival. The clearest differences in this regard show up in a comparison of hydro and diesel projects. Diesel engines require nearly continuous monitoring and preventive maintenance to operate at peak efficiency and with expected reliability. Temperatures, pressures, fuel quality, and a host of other parameters need to be continually monitored to detect problems early and to take corrective action before a breakdown occurs. The effects of inadequate maintenance appear quickly in the form of higher operating costs and increasing down time. In comparison, a hydro power station is almost free of routine maintenance requirements, apart from regular checking of the water intakes, and requires far less manpower for operation than does diesel. Not all PDMCs have hydro as an option, but technical simplicity is preferable even when diesel technology is the only practical option, as in atoll countries. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Operation and maintenance Capacity Development: Technology/Technology transfer Sector Related Issues: Energy planning/management Sector Related Issues: Water resource management | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/bank-assistance-power-sector-pacific-developing-member-countries
Georgia Investment Forum: Technical Assistance Completion Report | Georgia | Industry and trade | 2015-07-01 | More rigorous oversight of comparable surveys to ensure greater feedback should be undertaken for future events as the percentage of Forum attendees who responded to the Forum survey was only 10%. Visa restrictions introduced by the government of Georgia in 2014 hindered participation from several of ADB's developing member countries. While the government has revised visa regulations to streamline these processes going forward, this aspect requires close follow-up for future events. The quality of panel discussion during the Forum was linked in large part to advance planning and having skillful and articulate moderators. Participation of JICA (Japan International Cooperation Agency) in the Forum outreach activities was not planned during the design stage of the TA (technical assistance). However, JICA significantly contributed to the success of the Forum by identifying the Japanese companies interested to participate in the Forum and facilitating their travel and accommodation. Such partnerships will be valuable and should be actively sought. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/georgia-investment-forum-tcr
Developing a Geospatial Urban Water Supply and Sanitation Utility Management System: Technical Assistance Completion Report | Georgia | Water and other urban infrastructure and services | 2015-03-01 | The basic infrastructure asset mapping is essential and can be considered an integral part of urban planning while designing for any major urban infrastructure investments. It is better to adopt a holistic approach by advance identification of various utilities to be mapped and how the database can be used by various service providers. This would involve dialogue at various levels in different government departments before designing such initiative, and the consulting firm should be engaged only after clarity on such issues. It is equally important for the utility staff to understand importance of such exercise and engage from the beginning of the TA (technical assistance). This would help the staff to have clarity on the outputs, which would be required to be updated on continuous basis for its effective use, based on future investments in the assets creation or rehabilitation. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/geo-developing-geospatial-urban-wss-utility-management-system-tcr
Road Corridor Investment Program - Project 2: Project Completion Report | Georgia | Transport | 2014-09-01 | Need for adequate resource allocation to preparatory works for new projects. The cost overrun of the civil works component was a primary reason for the cancellation, and was caused by inadequacies in the investment program appraisal with respect to safeguards, engineering design and the cost estimate. The project preparatory TA was conducted with very limited resources - only about $0.75 million was allocated to complete a comprehensive feasibility study for the investment program within 8 months, which was insufficient for a country that had become an ADB member country only one year before the TA's commencement, and for construction of roads in a greenfield site. The budget and implementation duration should have been carefully examined and discussed in depth with the government prior to the project preparatory TA's implementation. ADB currently has a different financial modality to provide project preparatory support to its developing member countries, called as project design advance, that involves more robust funding for needed studies and detailed advance design, with greater government ownership. Need for comprehensive due diligence in safeguards and technical aspects. The cost overrun had two major causes: (i) an insufficient safeguard assessment during appraisal, and (ii) an inaccurate cost estimate. A comprehensive safeguards impact assessment during appraisal could have avoided the later realignment. Detailed analysis of alternative alignments and their associated potential safeguards impacts, both of environmental and social, should have been conducted as well. The original alignment was to be located in the vicinity of the protected wetland area, which should have been examined together with the cost for environmental mitigation measures to be implemented. Several factors contributed to the inaccurate cost estimate, including market volatility. The estimates were prepared in 2009, when global construction activity was low. ADB has discussed with the government the need to minimize the risk of estimation errors or design changes in future projects. As a first step, the government and ADB agreed to plan robustly and execute preparatory work with more attention to detail, especially with regards to engineering designs, safeguards, procurement and cost estimation. The government will also explore value-engineering and non-traditional project delivery methods such as design-build to mitigate the risks the project encountered during implementation. Furthermore, the critical cost factors and the technical parameters of roads to be improved in future projects should be examined, with allowance for price and quantity adjustments for uncertainty, and including adequate contingencies to minimize the risk of cost overruns. Need for the government's continuous capacity enhancement in project preparation. The government should have conducted its own robust due diligence prior to processing new projects, particularly in terms of engineering and safeguards. Further, international financial institutions, including ADB, should continue providing technical support, including institutional and capacity development programs, to enable the executing and implementing agencies to independently prepare projects with sound technical inputs. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/road-corridor-investment-program-project-2-pcr
Georgia: Validation Report of the Final Review of Country Operations, 2008 - 2012 | Georgia |  | 2013-11-14 | 1. Project designs and cost estimates should be carefully validated by ADB and the government. Projects are more appropriately designed and costed when there is close oversight of preparatory technical assistance outputs. Government participation in the early stages of project preparation is important because of the knowledge of local conditions, and it is essential that the government validates designs and cost estimates prepared by consultants during the project preparatory phase. This ensures that an adequate level of financing is allocated to the project, and cost overruns are avoided (particularly in large infrastructure investments). [Main text, para. 109; Executive Summary, page ii] project cycle stage: Design Lesson Topics: Project Design: Appraisal Project Design: Project design Methodologies/Approaches: Consultation/Participation 2. Project investment should be complemented by policy reforms. The interim operational strategy final review points out that ADB's policy reform, knowledge service, and innovative pilot project support were too limited compared with the size of the lending program. Investments undertaken so far have been implemented in an inadequate policy environment. Therefore, it is critical to augment project investment with policy reforms that address the broader spectrum of sector issues. [Main text, para. 110; Executive Summary, page ii] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Policy & Reform: Policy reforms/framework Policy & Reform: Reform 3. A stronger focus on inclusive growth is needed to ensure that rural population benefits from ADB support. Inclusive growth is crucial in a country with 50% of the population living in rural areas and high youth unemployment. A focus on economic growth, where investments are primarily geared to infrastructure, is insufficient to address the issues of poverty and unemployment in rural areas. [Main text, para. 111; Executive Summary, page ii] project cycle stage: Design, Country Partnership Strategy Lesson Topics: | Country Partnership Strategy Final Review |  | http://www.adb.org/documents/georgia-validation-report-final-review-country-operations-2008-2012
Municipal Services Development Project - Phase 2 | Georgia | Transport, Water and other urban infrastructure and services | 2013-03-06 | 1. Proactive consultation with municipal governments by the Municipal Development Fund to ensure prompt selection of subprojects created a momentum that was maintained during project implementation and contributed to completion of physical works ahead of schedule. project cycle stage: Lesson Topics: 2. Considering there were some shortfalls in the road subproject detailed design work (such as drainage and ditch cover, sidewalk, and traffic safety provision), Municipal Development Fund (MDF) technical staff, local consultants and contractors need training on technology and workmanship in order to reach international standards. MDF and ADB need to ensure timely recruitment of construction supervision. project cycle stage: Lesson Topics: 3. On-the-job training activities alone are less effective than actual training courses in terms of capacity development. The capacity of the municipal governments remains weak; all lack a filing and database system to store their asset inventories, which will be essential for planning, improvement and operation and maintenance of municipal infrastructure and services. project cycle stage: Lesson Topics: 4. Issues regarding legal and/or technical aspects of operation and maintenance (O&M) planning and funding, measures for cost recovery, tariff collection, and the metering system should be properly studied by consultants to mitigate the risk associated with inadequate O&M of project water supply system facilities. project cycle stage: Lesson Topics: 5. The management information system proved to be an efficient means to provide all project information and data and helped Municipal Development Fund monitor implementation of the project in a timely manner. The same system should be used other projects. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/municipal-services-development-project-phase-2-pcr
Municipal Services Development Project | Georgia | Water and other urban infrastructure and services | 2012-10-01 | The Municipal Development Fund (MDF) consulted proactively with the municipal governments to ensure prompt selection of subprojects. It created a momentum that was kept during project implementation and contributed to physical completion ahead of schedule. The United Water Supply Company of Georgia (UWSCG) could not be fully involved in project implementation because it was created in 2010, after the project started. Since the facilities had already been completed when transferred to UWSCG, UWSCG could not be accountable for their design and construction. Similarly, MDF and the municipal governments are no longer accountable for the completed water supply and sanitation (WSS) facilities. Future projects should involve all the parties concerned from preconstruction to completion. The quality of civil works for road pavement and watertight structures, such as the underground water reservoirs, has achieved the required national standards. However, local civil works contractors need further training on technology and workmanship for cement concrete pavement and the construction of water supply facilities, in order to reach international standards. No consultant was engaged to address issues regarding legal and/or technical aspects of operation and maintenance (O&M) planning and funding, measures for cost recovery, tariff collection, and the metering system. This poses a risk associated with inadequate O&M of project WSS facilities. MDF has a management information system (MIS) installed under the World Bank assistance program. The MIS is efficient in providing all project information and data, which helped MDF monitor implementation of the project in a timely manner. The same system should be used for future and ongoing projects. Capacity development of municipal governments has been partly addressed through on-the-job training activities only and has not been as effective as actual training courses. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/municipal-services-development-project-pcr
Social Services Delivery Program | Georgia | Education, Finance, Health, Public sector management | 2011-09-01 | Socially responsible budget. Rapid disbursements into a budget that is socially responsible and sound in macroeconomic terms provide an efficient channel for supporting sustainable and inclusive public spending, including social sector financing. Loan size determination. The projected budgetary financing requirement provides the rational for determining the loan size for budget support attached to a policy reform agenda, and it rests on unfunded fiscal ï¿½adjustmentï¿½ costs of reform, including both recurrent and capital expenditures. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/social-services-delivery-program
Emergency Assistance for Post-Conflict Recovery | Georgia | Finance, Health, Public sector management | 2010-12-01 | Lending Modality: Having an appropriate modality is critical. ADB's Disaster and Emergency Assistance Policy together with Achieving Development Effectiveness in Weakly Performing Countries provided a ready framework for Emergency Assistance for Post-Conflict Recovery (EAPCR). Monitoring and evaluation framework. The overall success of the EAPCR could have been greater had the DMF been better designed. The impact statement could have been closer to the outcome, and assumptions about investor and consumer confidence should have been more realistic. The impact statement could have focused on maintaining sustainable and inclusive public sector spending rather than to restore the Georgian economy to the pre-war trajectory of growth and social development. A more realistic assumption could have been formulated in line with the government's commitment to give priority to social expenditures. The output targets could have been defined according to existing data and definitions. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/emergency-assistance-post-conflict-recovery
Growth Recovery Support Program | Georgia | Public sector management | 2010-12-01 | Socially responsible budget. Rapid disbursements into a budget that is socially responsible and sound in macroeconomic terms provide an efficient channel for supporting public spending, including social, infrastructure, and countercyclical stimulus. Lending Modality: The crisis in Georgia, triggered largely by exogenous shocks, has underscored the need for a suitable modality that will enable ADB to provide quick support. While ADB has a program lending policy, there is no special modality for a financial crisis response operation for Asian Development Fund countries. The special program loan in the program lending policy is limited to ordinary capital resources countries (OCR). ADB's Countercyclical Support Facility (CSF) helped disburse anti-crisis support quickly to OCR eligible countries. In 2008, ADB invoked its Disaster and Emergency Assistance Policy, together with Achieving Development Effectiveness in Weakly Performing Countries, to support Georgia through the Emergency Assistance for Post-Conflict Recovery Project. However, the approach adopted under the Growth Recovery Support Program has demonstrated that ADB can quickly mobilize support for its developing members countries (DMCs). Yet, somewhat protracted internal discussions over the application of the program lending policy slowed down ADB's response in the absence of clarity on the flexible application of that policy for crisis situations such as the one faced in Georgia. ADB business procedures. While program preparation was shorter than for typical program grants and loans, streamlined and abbreviated business procedures for processing crisis response programs could allow the response to be more timely. Monitoring and evaluation framework. The overall success of the program could have been greater had the design and monitoring framework (DMF) been better designed. The impact statement could have been closer to the outcome and assumptions about investor and consumer confidence more realistic. The impact statement could have focused on maintaining sustainable and inclusive public sector spending rather than to restore the Georgian economy to the pre-war trajectory of growth and social development. A more realistic assumption could have been formulated in line with the government's commitment to give priority to social expenditures. The output targets could have been defined according to existing data and definitions. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/growth-recovery-support-program
Madhya Pradesh Power Sector Investment Program (Tranche 2): Project Completion Report | India | Energy | 2016-05-01 | DISCOM-East was proactive in solving problems in the development of design documents, procurement, the timely delivery of equipment and in resolving the numerous issues and problems normal to project implementation. Lessons for future ADB projects include the need for capable and committed implementing agencies. DISCOM-East demonstrated that; (i) open communication and willingness to deal with stakeholders - and particularly contractors - are helpful in resolving complex technological and economic issues leading to better resolution in a timely and cost efficient manner, (ii) a properly administered procurement process will lead to improved bids with lower prices and better quality of equipment and workmanship of contractors; (iii) ability to adjust project scope due to actual field conditions and to apply technical optimization will improve project implementation and outcome; and (iv) assignment of experienced and sufficiently ranked technical managers with autonomy to plan, design and implement the project, will lead to better project implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/ind-madhya-pradesh-power-sector-investment-program-t2-pcr
Kolkata Environmental Improvement Project: Completion Report | India | Water and Other Urban Infrastructure and Services | 2015-09-11 | Fully staffed PMUs (project management units) and complete involvement of the executing agencies from the outset are necessary to create ownership and commitment. project cycle stage: Implementation, Country Partnership Strategy Project timelines need to take into account implementation complexity, the experience of the executing agency, consultants and contractors, and the available working seasons. project cycle stage: Design, Feasibility, Implementation Use of innovative practices like electronic measurement books and advanced technologies like trenchless technology for pipe laying can help improve implementation efficiency. project cycle stage: Implementation Access to transport facilities at resettlement sites is key to protect the livelihoods of resettled people, especially women and the differently-abled. It is necessary to protect sites from which people are relocated, from squatting. project cycle stage: Implementation Secondary displacement due to land acquisition and resettlement always needs to be included in resettlement plans. project cycle stage: Design, Implementation For projects with a canal rehabilitation component, a component to integrate bank protection and maintenance with community involvement can support sustainability. project cycle stage: Design, Implementation, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/kolkata-environmental-improvement-project-pcr
Madhya Pradesh State Roads Sector Project II: Completion Report | India | Transport | 2015-09-11 | Implementation delay. The project implementation initially experienced delays mainly due to slow mobilization by the civil works contractors, even though the pre-construction activities were carried out in a timely fashion by MPRDC (Madhya Pradesh Road Development Corporation). Subsequently, the termination of a poorly performing contractor and procurement of a new contractor for completing the balance of works, and the addition of three new subprojects in 2009 - 2010 further affected the implementation schedule. Nonetheless, ten civil works packages were completed before original loan closing date, whilst the others were completed about 8 months before the extended loan closing date. This was achieved by close coordination between MPRDC and ADB in identifying issues and preparing action plans to expedite the implementation and recoup time lost. Consequently, the contractors improved their planning and mobilized additional resources. The supervision consultants closely monitored the progress achieved by the contractors on the action plan. The recouping of time lost was facilitated by MPRDC through early decision-making and fast processing of payments. Timely identification of the issues, formulation of suitable action plans and close monitoring of progress helps improve project implementation. project cycle stage: Implementation Performance of contractors. Despite reiterated requests and financial support from MPRDC (Madhya Pradesh Road Development Corporation), one civil works contractor continued to perform poorly and the contract had to be terminated. Incorporating additional evaluation criteria in the bidding document on past poor performance or terminated or abandoned contracts would facilitate identification of such contractors in future procurement activities. project cycle stage: Implementation Financial management. Based on observations of financial auditors, ADB recommended MPRDC (Madhya Pradesh Road Development Corporation) to strengthen internal audit system with regard to nature and scope of verification, timely preparation of audit reports, and to improve fund management. These measures together with regular and robust assessment of financial sustainability would facilitate better financial management. project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/madhya-pradesh-state-roads-sector-project-2-pcr
National Highway Corridor (Sector) I Project: Completion Report | India | Transport | 2015-09-11 | Underestimation of costs. The project encountered a significant cost overrun due to underestimation of costs at the time of processing of the original loan. To enable quality completion of the project, ADB approved a supplementary loan and the government provided additional counterpart funds. For future projects using the sector loan modality, consideration may be given to setting appropriate level of cost contingencies, taking into account the uncertainties caused by (i) the unavailability of designs and detailed estimates, and (ii) higher price escalation due to a longer gap between the processing of the loan and the actual time of subproject appraisal, approval, and contract award. project cycle stage: Design, Feasibility, Implementation, Completion Performance of the contractors. During implementation, significant delays in mobilization and completion of contracts were caused by weak capacity and poor performance of some contractors. For future projects, the criteria for qualification of contractors and for the award of multiple contracts should be strengthened. The contractual provisions related to contractor performance, such as mobilization, staffing, and deployment of equipment and funds, need to be strengthened so that poor performance by contractors is discouraged. project cycle stage: Implementation, Completion | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/national-highway-corridor-sector-1-project-pcr
Chhattisgarh Irrigation Development Project: Completion Report | India | Agriculture, Natural Resources, and Rural Development | 2015-09-03 | Where principles and approaches proposed under a project are innovative in the context of the prevailing institutional framework, capacity building of implementing agencies should be undertaken in advance to ensure ownership of those principles and the capacity to implement projects dependent upon them. Effective ADB supervision can help to overcome limitations in implementing institutions' capacity. project cycle stage: Implementation Project preparation should consider the capacity of local civil works contractors and ensure that eligibility criteria for bidding are not so prescriptive that they preclude participation by all but large contractors who may not be interested in smaller-scale works. project cycle stage: Appraisal Some form of incentive may be necessary to attract staff to project management units and new units or sections within executing agencies specifically established for project activities. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/chhattisgarh-irrigation-development-project-pcr
Assisting in Framework Development for Mainstreaming Public-Private Partnerships: Technical Assistance Completion Report | India | Public sector management | 2015-09-01 | The outputs and key activities under the TA (technical assistance) have contributed to the PPP (public-private partnership) enabling environment. It helped enhance and streamline the PPP processes, guidelines and frameworks for catalyzing PPPs. Some of the documents developed under the TA may, however, require a long standing effort to ensure adoption and integration into practices and processes. Accordingly, the government would need to continue with the efforts beyond the TA period. In light of this, indicators and performance targets for the outputs in the design and monitoring framework (DMF) should be well considered at the time of TA design so that they are realistically achievable within the TA period. Further, the DMF should have one clearly defined outcome statement with carefully selected indicator(s) to avoid any attribution issues. Project cycle stage: Design, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/assisting-framework-development-mainstreaming-ppp-tcr
Capacity Building for Government Agencies Supporting ADB Operations in India: Technical Assistance Completion Report | India | Public sector management | 2015-09-01 | (i) Change management was a big challenge during designing, developing and implementation of the website as new functionalities were added periodically. The important lesson learned is that while developing a website, it is very important to agree on the functionalities and stick to these to make the website development more predictable in terms of resources and; (ii) Web-based systems would be completely successful only when paper based file system is discarded and use of web-based system is made mandatory. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/capacity-building-government-agencies-supporting-adb-operations-india-tcr
Introducing Best Practices for Septage Management: Technical Assistance Completion Report | India | Water and other urban infrastructure and services | 2015-09-01 | The lessons learned under the TA (technical assistance) that can help improve formulation and implementation of similar TAs in future are: (i) Need for simpler implementation arrangements: The staff experienced difficulties in supervising and monitoring of TA activities in two geographically distant states of India. The delays in one state contributed to the overall delay in TA implementation. Even though the TA was able to achieve its objectives, it is suggested that such geographical spread be avoided for future TAs. This will help staff to monitor and implement the TAs in an efficient manner. (ii) Requirement for funding opportunities for implementation of successful pilots designed under the TA: There were requests from the DUD (Department of Urban Development) and UDPAD (Urban Development & Poverty Alleviation Department) for funding opportunities to implement the pilots prepared under the TA. While funds could be made available for pilots at Mizoram from Tranche 2 of ADB's ongoing program for North Eastern Capital Cities Development Investment Program3, the same could not be made available for pilots of Himachal Pradesh. It is suggested that for future TAs, the scope of funding for pilots be linked with existing ADB's financing program in the country. Project cycle stage: Design, Implementation, Country Partnership Strategy | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/introducing-best-practices-septage-management-tcr
West Bengal Development Finance Program: Completion Report | India | Public Sector Management | 2015-08-14 | The sustained commitment by the GOWB ensured that reforms transcended short-term political considerations. For a policy-based program to be successful, sufficient resources must be devoted to cultivate dialogue with all stakeholders and institutionalize ownership of reforms. project cycle stage: Implementation, Operation Policy-based programs targeting fiscal consolidation should not sacrifice economic growth by insisting on rapid and drastic fiscal adjustment in the short-term. Instead, fiscal space must be created gradually through carefully sequenced and multifaceted reforms that promote a sustainable fiscal trajectory along with economic growth. To achieve this balanced approach, revenue collection should be augmented with more efficient tax administration and an expansion of tax base instead of tax rate increases, which might hinder economic growth. Expenditure rationalization should complement revenue reforms by substituting the fiscal savings generated through streamlining current expenditures with growth-enhancing capital outlay in infrastructure and critical social sectors. To promote economic growth, private investment must be encouraged at the same time, especially through PPPs in public service delivery, which reinforces the rationalization of public spending and improvement in the quality of services. Finally, accompanying social programs embedded in the MTEFs are necessary to distribute the reform benefits more equitably across the society, and especially to disadvantaged socioeconomic groups. project cycle stage: Implementation, Operation The effective use of IT-based e-governance systems not only strengthens the government's capability and efficiency in tax administration, expenditure, and debt management, but also enhances the quality and accessibility of public service delivery at affordable costs to many different segments of society, including the poor. IT-based public sector reforms are also very effective at standardizing processes and preventing leakage, fraud, and corruption, and thereby improving accountability and governance at all levels of public administration. For sustainable fiscal reforms with maximum institutional impact, policy-based programs should prioritize investment in IT-based systems. project cycle stage: Operation A program design of this nature should avoid numerous and complex policy actions, and focus on the core elements of the government's reform agenda. Policy actions must be prioritized thoroughly based on a clearly defined, time-bound roadmap. Policy-based programs should be supported by an accompanying TA to meet all targeted policy actions in a timely manner, and strengthen the government's capacity to ensure the effectiveness and sustainability of the reforms. An accurate assessment of training and capacity building needs should be carried out at the fact-finding stage to determine the precise scope of the TA support. project cycle stage: Design, Appraisal, Implementation Ensuring continuity of staff at the program directorate builds institutional memory and supports the successful implementation and sustainability of the reforms. project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/west-bengal-development-finance-program-pcr
North Karnataka Urban Sector Investment Program, Tranche 1: Completion Report | India | Water and Other Urban Infrastructure and Services | 2015-08-13 | There is a need to develop a database of reliable consultants for executing agencies. KUIDFC can prepare a performance evaluation report of the consultants, which can be input into this database. Furthermore, to ensure better performance, consultancy contracts can be developed with bonus and penalty clauses based on deliverables achieved. project cycle stage: Appraisal, Implementation Construction schedules for sewerage contracts should be realistic to avoid the repeated need for contract extensions. project cycle stage: Design, Implementation Project designs should include greater focus on ensuring the provision and delivery of service and maintenance of assets. This can be done by incorporating a stronger institutional development component specifically targeted at creating/ strengthening maintenance units within the ULBs and institutionalizing O&M procedures, through adequate training and capacity-building measures. project cycle stage: Design, Implementation, Operation Community development activities have proved to be a major asset to this project and have led to enhanced acceptance of the project and associated behavioral changes. Commencing these activities retroactively prior to loan approval will enable community involvement in the project during the design and implementation phases as well. project cycle stage: Design, Implementation, Operation There should be a dedicated budget for gender action plan (GAP) implementation project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/ind-north-karnataka-urban-sector-investment-program-t1-pcr
Capacity Building for Commercial Bank Lending for Solar Energy Projects: Technical Assistance Completion Report | India |  | 2015-07-01 | The second component of the TA or technical assistance (technical due diligence support) was linked to the Solar Power Generation Guarantee Facility. Only banks selected as partner commercial banks under the Solar Power Generation Guarantee Facility were eligible to avail of the technical due diligence support (i.e., NordBank LB of Singapore and L&T Infra Finance of India). Local commercial banks had certain concerns regarding the facility including disagreement on pricing of the guarantee facility. As a result many local banks were reluctant to sign up as partner commercial banks under the guarantee facility and were unable to avail of the technical due diligence support under the TA. Delinking the TA from the solar guarantee facility would have increased the utilization of the technical due diligence support component of the TA and provided for broader knowledge sharing across the banking community, irrespective of their need for credit support from ADB. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/capacity-building-commercial-bank-lending-solar-energy-projects-tcr
Deepening Capacity Building for Mainstreaming Public-Private Partnerships: Technical Assistance Completion Report | India | Education, Energy, Health, Transport, Water and other urban infrastructure and services | 2015-06-01 | The achievements under the TA (technical assistance) contribute towards initial sustainability of ADB support towards PPP (public-private partnership) mainstreaming. However, experiences under the TA have shown that the level of PPP institutionalization continues to be uneven across states and central line ministries given that systemic changes in government institutional structures requires considerable time and effort. For ensuring likely sustainability of ADB interventions in the medium to long term, enhanced focus is required on creating a sustainable institutional setup within state governments to carry forward PPP activities. The results from the capacity building exercise may be maximized if the exercise is tied in with a sustainable institutional setup within the state governments and central line ministries. Also, further work on capacity building may be based on the current emerging challenges such as the need for more robust project structuring. To facilitate monitoring and evaluation, any future TA support should clearly delineate the deliverables under the support to be provided and develop a framework for monitoring the deliverables at the initial stages of TA design and implementation. This should include well considered indicators and targets for the outputs and outcome in the design and monitoring framework with clearly defined data source and collection approach, and a mechanism for monitoring the indicators. Since TA administration can become complex and cumbersome with a multitude of consultants, as was the case under this TA, suitable options for implementation arrangements, including consulting inputs, should be explored to reduce administrative complexity and to have better oversight and monitoring of consultant outputs. Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/deepening-capacity-building-mainstreaming-public-private-partnerships-tcr
Second India Infrastructure Project Financing Facility: Facility Completion Report | India | Multisector | 2014-09-30 | 1. Project-related matters. The success of India Infrastructure Project Financing Facility II draws important lessons of building and maintaining strong partnerships during project implementation, not only with the government and India Infrastructure Finance Company Limited (IIFCL) but also with development partners, banks and financial institutions, project sponsors, and other stakeholders. Building awareness, continuous dialogue, and strengthening safeguard practices of IIFCL and banks/ and financial institutions are crucial to ensure effective project implementation and disbursements. With continuous support from development partners, IIFCL will build on integrating safeguard measures to minimize subproject risks through (i) continued training to enhance capacity of its environmental and social safeguard management unit and consortium partners; (ii) regular updates of its environmental and social safeguard framework (ESSF) to align with the requirements of development partners; and (iii) leading the advocacy with banks and financial institutions through workshops and dissemination. IIFCL conducted consultation workshops for banks and financial institutions on the ESSF approach for addressing safeguard issues when financing infrastructure public-private partnership projects. The extensive coordination and collaboration with other development partners such as the World Bank, Japan Bank for International Cooperation, and German development cooperation through KfW to develop a common ESSF is an important lesson in achieving successful project implementation. [Main text, para. 52] project cycle stage: Design, Implementation Lesson Topics: 2. ADB financial sector operations in India. The limited fiscal space for government guarantees, including to India Infrastructure Finance Company Limited, emphasizes the need for innovation and well-structured ADB interventions in the financial sector and infrastructure financing, including public nonsovereign operations, for ADB to remain relevant to changes and financial market developments in India. It is becoming apparent that domestic capital market reforms are important to address the issue of long-term capital and provide opportunities for insurance, pension, provident, and mutual funds to finance infrastructure development in India. [Main text, para. 53] project cycle stage: Implementation, Operation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/india-second-india-infrastructure-project-financing-facility-fcr
Madhya Pradesh Power Sector Investment Program (Tranche 3): Project Completion Report | India | Energy | 2014-09-01 | To improve the environmental performance of loans, the following measures are suggested: (i) a systematic and continuous approach in developing awareness and periodic capacity enhancement of the project staff regarding ADB's environmental policy, procedures, and requirements; (ii) as appropriate, ensuring timely mobilization and continuation of environmental experts by the executing agency, consultants, and contractors until loan closure; (iii) systematic supervision, monitoring, data mapping, and reporting mechanisms on implementation of environmental safeguards; and (iv) periodic reviews by environmental experts associated with the loan in order to undertake timely corrective actions, where needed. The following social measures are suggested: (i) advance capacity development for project staff on ADB's social safeguards policy, procedures, and requirements; (ii) deployment of resettlement experts by the executing agency and consultants until loan closure, as appropriate; (iii) engagement of experienced nongovernment organizations to assist in implementing resettlement; (iv) timely supervision, monitoring, evaluation, and reporting on implementation of resettlement plans; (v) periodic social safeguards reviews by ADB experts and then initiating corrective actions, as required; (vi) addressing issues related to temporary impacts due to use of private land for stringing transmission lines and erecting towers, which are perceived by affected persons to cause permanent impacts by restricting access to the affected land for purposes of cultivation and devaluing land and assets under the corridor of impact; and (vii) ensuring disbursement to affected persons of compensation for damage to crops and trees prior to commencing civil works related to stringing transmission lines. Such measures can be expected to improve the social safeguards performance in ADB-assisted projects. Madhya Pradesh Power Transmission Company Limited (TRANSCO) followed integrated project management practices to ensure (i) proper planning, (ii) effective project monitoring mechanisms, and (iii) application of skills of motivated and well-trained personnel. In addition, ADB needs to strengthen its assessment of the safeguards capacity of the executing agency at the project appraisal stage, identify capacity gaps, and suggest measures for efficient safeguards management. These would help in successfully implementing infrastructure projects even on vastly spread terrains like that of Madhya Pradesh. The knowledge and insights TRANSCO has gained in these aspects may be assembled and disseminated to other executing agencies in appropriate fora. Timely management of rights-of-way in spite of constraints and optimally utilizing ADB and counterpart fund, offer lessons to be adopted for other projects. The advance procurement actions greatly helped in timely project execution and should be adopted for future projects. Moreover, this project's partnership process involving stakeholders, and particularly contractors, in addressing complex technical and economic matters can set an example for future ADB projects in India. In general, good project management practices were followed and involved sequencing activities and a well-structured breakdown of the work content. This resulted in enhancing construction management practices to a higher level of efficiency by adopting a more formal project management methodology that is based on global standards. TRANSCO is of the view that the multitranche financing facility was appropriate for managing a large infrastructure project. This helped it to be in an appropriate state of project readiness and contributed to savings on commitment fees and interest cost. TRANSCO advocates using similar structures elsewhere, and particularly for fledgling new organizations. Depending upon the complexity of a given project, it views a facility with duration of 7-10 years to be about ideal. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/madhya-pradesh-power-sector-investment-program-tranche-3-pcr
Rural Cooperative Credit Restructuring and Development Program: Program Completion Report | India | Finance | 2014-09-01 | Conduct adequate due diligence. ADB's policy framework was based largely on the recommendations of the high-level task force. Given the task force's expertise, there is merit to using such a report as the basis for ADB's program. Yet, ADB still needs to conduct adequate due diligence - specifically, how to implement and monitor the task force's recommendations and how to mitigate the facility's risks. Include systems for data collection. The program design could have benefited from a greater focus on data collection. Because data, particularly for district central cooperative banks and primary agriculture credit societies, was minimal at inception and still deficient at close, it is difficult to measure the program's impact. Better data could have supported program modifications, cancellation, or expansion. Practical steps that would have improved data collection would have been to (i) complete the special audit before the program's start, (ii) sequence computerization of the district central cooperative banks and eventually the primary agriculture credit societies (which was slotted toward the end of the program) at the beginning, (iii) fund the monitoring and data collection (that had been part of the cancelled accompanying TA) with internal staff consultancy or other resources rather than eliminate it from such a large loan program. Prove the concept before expanding. Although India wanted to introduce the reforms across the country simultaneously, another option would have been to pilot it in one or two states. If the pilot was successful, it would motivate subsequent participants, who would also be able to learn from the lessons of the pilot state(s). Moreover, ADB can add more value by concentrating its monitoring and support in one state than by spreading itself across a larger footprint. Plan realistic time frames. Despite 36 months of extensions, there remained unmet tranche release conditions. Even as of this project completion report 12 months after program cancellation, it is unclear when policy actions such as implementation of the action plan for ineligible PACSs and the computerization of the PACSs will be completed. Given the scope of reforms, the different governing layers, and the number of institutions involved, 42 months was not realistic. When targeting ambitious reform programs, longer time frames are necessary. Scheduling larger disbursements toward the end of the program can replace some of the momentum that the longer time frame will struggle to maintain. Design effective risk mitigation measures. ADB's risk assessment anticipated much of the program's eventual problems. However, the mitigating measures were inadequate to address the risks. More generally, given the size of the loan (which represented 58% of ADB's loan approvals for India in 2006), additional risk mitigation measures would have been appropriate and could have included piloting the program in one or two states prior to large-scale expansion, ADB participation in the National Implementation and Monitoring Committee, and a midterm program evaluation. Avoid tranche release conditions that require statutory changes. The program anticipated potential amendments to India's Banking Regulation Act, National Bank for Agriculture and Rural Development Act, and Deposit Insurance and Credit Guarantee Corporation Act as well as to states' cooperative societies acts. Remarkably, the participating states did all amend their cooperative societies acts. Still, ADB's programs should carefully assess relying on legislative actions, particularly at the national level, because its influence over the legislative process is likely limited. Moreover, in this particular program, the government was able to accomplish many of the intended changes through regulatory and executive actions, which suggests that additional due diligence could have a priori yielded alternatives to legislation. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/india-rural-cooperative-credit-restructuring-development-pcr
Chhattisgarh State Road Development Project | India | Transport | 2014-08-01 | Project implementation delays. Project implementation experienced significant delays. The initial delay was caused by insufficient project readiness, inadequate dedicated staff assigned by Public Works Department, delays in finalizing the design reports and bid documents, and time needed to obtain environment and/or forest clearance for tree cutting. During construction, the delays were caused by poor performance of some contractors and Naxalite attacks. To avoid implementation delays, project preparation should be undertaken before approval. A project implementation unit with adequate staff should be in place before approval. Other projects also identify these lessons and corrective actions have been incorporated. Coordination with other government agencies for forest and environmental clearance should be enhanced. ADB has been providing training to the project implementation unit on procurement, safeguards, and contract management. Performance of contractors. During implementation, the significant delay in completion of the works was caused by poor performance of some contractors. For future projects, the qualification criteria for contractors should be strengthened. The contractual provisions related to contractor performance, such as mobilization, staffing, and deployment of equipment and funds, need to be strengthened to minimize the possibility of poor performance by the contractors. To improve the environmental performance of projects, the following measures are suggested: (i) a systematic and continuous approach in developing awareness, and periodic capacity enhancement of project staff regarding ADB's environment policy, procedures, and requirements; (ii) ensuring timely mobilization and continuation of environment experts by the executing agency, consultants, and contractors until closure of a project as appropriate; (iii) systematic supervision, monitoring, data mapping, and reporting mechanisms on implementation of environmental safeguards; and (iv) periodic reviews by environment experts associated with the project to undertake timely corrective actions, if any. These measures will be particularly relevant, given the magnitude of air and noise emissions from road operation and community safety impacts, which may increase due to the likely increase in traffic growth rates. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/chhattisgarh-state-road-development-project-pcr
Western Transport Corridor Project | India | Transport | 2014-08-01 | The National Highways Authority of India undertook several measures towards achieving project readiness such as (i) project preparation using its own funds; (ii) deployment of a project team at its headquarters and field office during the initial stage to supervise project preparation and undertake procurement activities and pre-construction activities; and (iii) advance action on civil works procurement, recruitment of construction supervision consultants, and pre-construction activities such as shifting of utilities, cutting of trees, and land acquisition. All the contracts were awarded within 5 months from the Board approval for the project. However, due to inappropriate selection of the contractors, a significant delay in the completion of the contracts was caused by (i) weak planning; (ii) weak project management capacity; (iii) poor performance of the contractors; and (iv) inadequate participation of the lead partner, particularly the joint venture contractor, who was awarded three contract packages. Three out of five civil works contracts were ultimately terminated after a considerable delay. The criteria for the qualification of the contractor under a joint venture and for the award of multiple contracts should be strengthened. The contractual provisions to ensure the participation of the lead partner need to be strengthened. The performance of contractors on projects in India has always been a matter of concern. The contractual provisions related to contractors' performance, such as mobilization, staffing, deployment of equipment and funds, release of payments, bonus for early completion, and penalties, need to be strengthened so that poor performance by the contractor is discouraged. The performance of the contractor should be assessed in the initial stages of the contract and the decision on termination, if warranted, should not be delayed. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/western-transport-corridor-project-pcr
Western Transport Corridor Project: Validation of Completion Report | India | Transport | 2014-08-01 | The PCR (project completion report) identified a few important lessons from the experience with contractors. The criteria for the qualification of contractors under a joint venture and for the award of multiple contracts should be strengthened. The PCR did not elaborate how this can be accomplished. This needs to be further assessed to formulate concrete steps to ensure that prequalified contractors are indeed capable as claimed and have the technical and financial resources to complete the proposed project. While performance bond requirements seek to guarantee contractor performance, this seemed ineffective under this project. There is also a need to strengthen provisions related to contractors' performance, such as mobilization, staffing, deployment of equipment and funds, release of payments, bonus for early completion, and penalties so that poor contractor performance could be discouraged. Likewise, the performance of the contractor should be assessed at the initial stages of the contract and the decision on termination, if warranted, should not be delayed. This validation finds these lessons appropriate and has no further lesson to offer. project cycle stage: Design, Appraisal, Implementation | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/projects/documents/western-transport-corridor-project-pcr
Rural Roads Sector II Investment Program - Project 4 | India | Transport | 2014-06-01 | Subproject packaging and procurement. During procurement for civil works packages, the response to bid was low. Some packages received no response, even after the 7th call. Repackaging and rebidding for such contract packages slowed down the procurement process. In the meantime, the ADB procurement review revealed that a number of contractors had been awarded more than one contract and that most of them submitted bids for multiple contracts within a district. This indicates that the size of the packages should be determined in close consultation with the implementing agencies to suit the technical and financial capability of local contractors. Time requirements for completing a subproject. Following the Pradhan Mantri Gram Sadhak Yojana (Prime Minister's Rural Roads Program) guidelines, each civil works contract has a stipulated completion period of 12 months. However, 12 months were found to be inadequate, especially considering the pre-construction activities, contractor's capability, and weather conditions in the project area. At least 18-24 months were found to be needed for all project activities. Proper timing of signing the civil works contracts, in relation to the monsoon period, may avoid the loss of construction time to the monsoon. This should be incorporated and considered in other similar projects. Fostering local contractor industry. All civil works contractors for the project were local, and some of them were small and lacked working facilities, fund resources and/or skilled and qualified staff. During civil works procurement, the responses from bidders were low, which led to repackaging (split into small packages) and rebidding of some civil works packages. Some of the civil works packages were geographically spread out, which made it difficult for contractors to manage their resources, labor, and materials. In future projects, local road development authorities may develop adequate measures to assist small contractors in terms of equipment, funds, and project management. In the meantime, the state governments should strengthen contract management to ensure the proper and timely completion of subprojects. Monitoring of environmental impacts. It is important to ensure continuous engagement of project implementation consultants to avoid gaps in environmental impact monitoring activities during project implementation. In future projects, if a new project implementation consultant is to be recruited, the start of the new contract should be immediately after, or overlap with, the existing project implementation consultant contract. The handover process should be seamless to avoid the gap in the monitoring activities. Capacity building for project implementation consultants in environmental impact monitoring should be considered to ensure consistency in the quality of monitoring activities. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-roads-sector-2-investment-program-project-4-pcr
Assam Governance and Public Resource Management Sector Development Program | India | Public Sector Management | 2013-01-10 | 1. The sequencing of multifaceted fiscal reforms is of paramount importance in achieving sustainable outcomes. Regulatory changes in the tax system are a necessary, but not sufficient condition for successful fiscal consolidation. Revenue administration also needs to be strengthened. Increases in revenues should be complemented with more politically challenging measures to enhance expenditure management; budget prioritization and resource allocation; public sector enterprise reform; debt management, and public accountability. Subsequently, encouraging private sector investment through policy actions supports economic growth, and thus fiscal consolidation, by creating opportunities for public-private partnerships and reinforcing government's regulatory function in the economy. Accompanying social programs are likewise necessary to offset the negative impact of the reforms on stakeholders. project cycle stage: Lesson Topics: 2. Program design of this nature should focus on the core elements of the government's fiscal reform agenda, and avoid numerous policy actions, with overarching themes, until fiscal consolidation measures generate positive results. Overly ambitious and complex conditions could lead to delays in tranche releases and program completion, undermining the achievement of fiscal outcomes. The careful configuration and sequencing of the policy actions through multiple tranches, using an appropriate time frame, provide the executing agencies with enough flexibility to meet specific targets and a gestation period. project cycle stage: Lesson Topics: 3. A key consideration in achieving successful program implementation and sustainability in the long run is the development of competencies in government through capacity-building and training programs. Given the large capacity-building needs of Government of Assam in areas like the modernization of public finance management and information technology systems, the sector development program modality with a project loan component, rather than a regular piggybacked technical assistance, was an appropriate choice. Without such support, the executing agency could not have implemented the policy actions on time. project cycle stage: Lesson Topics: 4. The active involvement of state government officials is a must for institutionalization of fiscal reforms. The commitment depends not only on the macroeconomic situation but also on the external and internal push for reform, preferably expressed in fiscal responsibility legislation, government's tenure in terms of the electoral cycle, and on the need to maintain social cohesion. Sufficient time and resources need to be devoted to cultivating dialogue and building consensus among all stakeholders in designing, formulating, and implementing long-term fiscal reforms. project cycle stage: Lesson Topics: 5. Building institutional memory strengthens the success of the implementation. Programs of this nature could not deliver the desired outcomes unless the program directorate achieves continuity of staff over the implementation period. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/assam-governance-and-public-resource-management-sector-development-program-pcr
MFF - Madhya Pradesh Power Sector Investment Program (Tranche 1) | India | Energy | 2013-01-08 | 1. Compliance with environmental requirements associated with ADB assistance can be improved through (i) systematic, ongoing efforts to develop awareness, and periodic capacity enhancement of project staff regarding ADB's environmental policy, procedures, and requirements; (ii) ensuring timely mobilization and the ongoing participation of environmental experts with the executing agency, consultants, and contractors, beginning during preparation and continuing until loan closure (as appropriate); (iii) systematic supervision, monitoring, data mapping and reporting mechanisms on implementation of environmental safeguards; and (iv) periodic reviews by environment experts associated with the loan to enable timely corrective actions to be taken as needed. project cycle stage: Lesson Topics: 2. Compliance with social safeguards requirements associated with ADB assistance can be improved through (i) advance capacity development of project staff regarding ADB social safeguards policies, procedures, and requirements; (ii) deployment of resettlement experts by the executing agency and consultants throughout the loan period, as appropriate; (iii) engagement of an experienced non-government office to assist with implementation of resettlement activities; (iv) timely supervision, monitoring, evaluation and reporting on implementation of resettlement plans; (v) periodic social safeguards reviews by ADB experts, with corrective actions undertaken, as required; (vi) addressing issues related to temporary impacts from the use of private land for stringing transmission lines and erecting towers, which are perceived by affected persons to be causing permanent impacts in terms of restriction in access to the affected land portion for cultivation, and devaluation of the land and assets under the corridor of impact; and (vii) ensuring disbursement to affected persons of compensation for damage to crops and trees prior to commencing civil works related to stringing of transmission lines. project cycle stage: Lesson Topics: 3. Implementation of infrastructure projects, even in large regions such as Madhya Pradesh, can be successful given (i) proper planning; (ii) effective project monitoring mechanisms; and (iii) the application of skilled, motivated and well-trained personnel. The knowledge and insights gained by Madhya Pradesh Power Transmission Company Limited in this regard can be disseminated to other executing agencies through appropriate forums. The advance procurement actions greatly helped in timely project execution, and should be adopted for future projects. The partnership that was developed with stakeholders (particularly contractors) enabled complex technological and economic issues to be addressed in an exemplary manner, and the approach could be employed in other ADB projects in India. Good project management practices have been followed through sequencing of activities and structuring of work, and efficiency gains have resulted from adoption of enhanced construction management practices that use a formal project management methodology based on global standards. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/mff-madhya-pradesh-power-sector-investment-program-tranche-1-pcr
India Infrastructure Project Financing Facility | India | Finance | 2012-11-01 | Project-related. Since the India Infrastructure Project Financing Facility (IIPFF) was rated as highly successful, the lessons learned focus on ADB operations in the financial sector in India rather than being limited to the appraisal and implementation of the facility. While the executing agency did not raise any concerns about ADB's 4-month approval process for subprojects under IIPFF, they built it into their own appraisal procedures to allow for effective coordination with the other consortium lenders. This demonstrates that (i) clear communication and adequate expectations about the length of ADB's implementation procedures are essential to ensure the executing agency's satisfaction with ADB; and (ii) there is room to improve and streamline internal implementation procedures to reduce endorsements to less than 4 months, thereby demonstrating client-orientation and relevance. The Ministry of Finance (MOF) emphasized the limited fiscal space for public guarantees, including to the India Infrastructure Finance Company Limited (IIFCL). MOF agrees with IIFCL on the importance of credit enhancement products without guarantees by the sovereign. ADB was asked to play a catalytic role in the development and implementation of such products. The MOF and the executing agency both expressed concern about the delays in the approval process. ADB clearly needs to strengthen innovative product development to ensure that interventions are relevant to changes and developments in the financial markets in India and to increase internal coordination to avoid delays in credit risk appraisal and approval. Another lesson learned is the importance of dialogue and raising awareness for environmental and social safeguards. Initially, the emphasis on safeguards was considered a hindrance rather than an important aspect of IIFCL's project appraisal. Continuous dialogue and awareness raising with senior management and staff training on safeguards were crucial in making safeguards an important consideration in the credit decision-making process. IIPFF benefitted from extensive coordination and collaboration with other development partners such as the World Bank, Japan Bank for International Cooperation, and Kreditanstalt fu?r Wiederaufbau (KfW) to develop a common environmental and social safeguard framework (ESSF). General. In assessing the overall effectiveness of ADB's intervention through the facility, the performance indicators should be more accurate and aligned with the stated impact and outcomes following ADB's Guidelines for Preparing a Design and Monitoring Framework (2007). | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/india-infrastructure-project-financing-facility-pcr
Karnataka Urban Development and Coastal Environmental Management Project | India | Water and other urban infrastructure and services | 2012-11-01 | Fully staffed project management unit (PMU) and project implementation units (PIUs) and the complete involvement of the project authorities from project preparation is necessary to create ownership and commitment. Adequate consultations with all stakeholders during project formulation and appraisal of the project, based on the primary data or validated secondary data, will ensure more locally rooted and systematic planning, help build local ownership, and lead to better project implementation and sustainability of project outputs. Advance actions for consultant selection, procurement, land acquisition, and statutory clearances can help in timely completion of projects. The project and contract schedule should be realistic, taking into account the technical complexities of the project components, the capacity of executing agencies, consultants and contractors, and the available working season in project towns. Adherence to sound engineering design principles based on required primary surveys and validated secondary data can lead to more efficient outcomes and avoid delays. Adequate time needs to be allocated for surveys and engineering design. House service connections for urban water and sewerage should be part of the project scope to ensure optimum utilization of outputs and timely delivery of benefits. Small investments in areas like micro-finance, SHG formation, low cost sanitation facilities, and skills upgrading training can have large social and economic impacts and help build local support for a project. For institutional reform, use of a standardized set of systems and processes and a centralized control system at the state level helps to reduce implementation effort, time, and cost, and attain acceptable quality, irrespective of urban local body (ULB) capacity and location. Targeted awareness campaignsaimed at changing the behavior of urban residents are necessary to achieve design results. Involvement of committed local nongovernment offices (NGOs) and their continued involvement at least for a year after project completion can enhance project effectiveness and sustainability. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/karnataka-urban-development-and-coastal-environmental-management-project-pcr
Rural Roads Sector II Investment Program (Project 2) - State of Orissa | India | Transport | 2012-11-01 | The project was the third ADB loan to India for rural road development and the second under the Rural Roads Sector II Investment Program. The project has helped the government at both central and state levels to identify gaps in various project implementation activities, and the lessons include those listed below. Project benefit monitoring. For investments in physical infrastructure to be effective and sustainable, the investment program needs to focus more on sex-disaggregated data analysis. Road improvements have a high potential to bring improvements in reproductive health, education, possession of movable assets, employment opportunities, and nutrition. Monitoring of selected sex-disaggregated key indicators should be incorporated in future subprojects under the program. Time requirements for completing a subproject. Following the Prime Ministerï¿½s Rural Roads Program (PMGSY) guidelines, each civil works contract had a stipulated completion period of 12 months. However, it was found that 12 months were insufficient, especially given pre-construction activities, the capability of contractors, and adverse weather conditions in the project area. It was found that at least 15-20 months were needed for all project activities. The proper timing of the signing of civil works contracts in relation to the monsoon period may avoid the loss of construction time due to the monsoon. This should be considered and incorporated into future subprojects under the investment program. Project readiness and utility relocation. Project preparation had some weaknesses during the design phase, especially in site reconnaissance and consideration of design alternatives. Strengthening this aspect would avoid problems and associated delays in project implementation. Relocation of electricity poles and telecommunication lines was a common problem faced in almost all contract packages. Therefore, early and precise identification and preparationï¿½such as sufficient survey provision, accurate cost estimation, adequate and timely budgeting, and adequate coordination with concerned departments and state organizationsï¿½ should be incorporated into future subprojects. Availability and capacity of the contractors. The number of contractors was limited and the number of responses from bidders was low. All civil work contractors were local and some lacked working facilities, funding resources, and/or skilled and qualified staff. The weak capacity of some local contractors was a major cause of project delays. Also, some civil works packages were geographically spread out, making it difficult for contractors to manage their resources, labor, and materials. Although some contracts were terminated and new contractors selected for the balance of the work, the overall capacity remained inadequate. In future projects, contract management should be enhanced, and the contract packages could be larger in scale to attract experienced, reputable nationwide or global contractors. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/rural-roads-sector-ii-investment-program-project-2-state-orissa-pcr
Tsunami Emergency Assistance (Sector) Project | India | Agriculture, natural resources and rural development, Energy, Public sector management, Transport | 2012-11-01 | Use of existing institutions for execution of emergency projects is beneficial as the time lag related to the induction of counterpart staff (experienced in most project management units or PMUs and project implementation units or PIUs) can be avoided and sector and location-specific institutional knowledge and resources are immediately available. Extended missions of ADB can play a critical role in building capacity and providing hand-holding support to executing agencies and implementing agencies without prior experience in complex, multi-sector projects. Coordination between donors, nongovernment organizations (NGOs), and government departments in any disaster management project can be more easily achieved if there is one executing agency and PMU for all emergency projects at the state level. Adequate tenure of key staff members in executing and implementing agencies is important for smooth and speedy implementation. Without a proper personnel policy or transfer planning, states are unable to place into required positions staff trained in the implementation of complex projects. In planning for similar projects with inexperienced executing and implementing agencies, training needs to be assessed upfront. Targeted, specific, and minimal consultant inputs can not only save loan funds for more critical development work, but can also ensure speedy and effective capacity building of government staff through ï¿½learning by doing.ï¿½ Third party quality audit (TPQA) consultants can help improve project outputs and outcomes. The timing, methodology, and outputs of benefit monitoring and evaluation (BME) consultants at pre- and post- project implementation stages need to be carefully and stringently defined to obtain meaningful outputs with adequately quantified data. Use of legal experts in areas like microenterprise insurance and exploring alternate insurance mechanisms may lead to more effective outcomes. Adherence to sound design principles based on required surveys and studies can lead to more efficient outcomes and avoidance of delays. Identification of the need for statutory (including environmental) clearances and obtaining such clearances early can help avoid delays in project implementation. Small investments in livelihood restoration and water supply and sanitation schemes can have large social and economic impacts, especially on women and vulnerable populations. Complex emergency projects require simple reporting and monitoring processes. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/tsunami-emergency-assistance-sector-project-pcr
East-West Corridor Project | India | Transport | 2012-10-01 | The project was the third loan under ADB's multi-year lending program to the National Highways Development Project (NHDP) and the first loan for the east-west corridor. Some lessons were learned during project implementation that can be applied to ongoing and future ADB projects in India. Land acquisition and resettlement. The initial delay in project implementation was primarily caused by slow procurement, land acquisition, and resettlement activities. This is a common issue for all projects in India. Project implementation also experienced prolonged delays in clearance for cutting of trees. For ADB-funded projects, such constraints are now being addressed through a project readiness checklist and training and capacity building programs for the executing agencies. This will ensure that preconstruction activities are carried out in advance and only well-prepared projects are taken up for approval. Project preparation and readiness. The construction of Surajbari Bridge encountered engineering problems, which significantly delayed project completion. Wherever required, a separate contract for such major bridges should be made, so that only qualified contractors are awarded the contracts for such specialized works. A thorough survey, investigation, and design should be carried out in initial stages in order to enhance project readiness. Such critical works should be started immediately upon the award of contract. An action plan for mitigating risks and resolving emergencies should be prepared and implemented, as required, for timely completion of the project. Performance of the Contractors. During implementation, significant delay in the completion of the contract was caused by poor performance of a joint venture contractor, who was awarded three contract packages. For future projects, the criteria for qualification of the contractors under a joint venture, and for the award of multiple contracts, should be strengthened. The contractual provisions related to contractor performance, such as mobilization, staffing, and deployment of equipment and funds, need to be strengthened so that poor performance by the contractor is discouraged. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/east-west-corridor-project-pcr
West Bengal Corridor Development Project: Completion Report | India | Transport | 2012-10-01 | Project readiness. Project readiness should be enhanced before implementation. Project preparation was mainly conducted through ADB technical assistance projects. The engineering requirements of the state highway component were based on the government's project feasibility study. At appraisal, a long list of rural access road (RARs) was prepared. During implementation, a large amount of work was required to review the engineering design for the state highways and select the RARs. Such tasks took a long time and delayed overall project implementation. For efficient project implementation, adequate project readiness should be ensured during appraisal. In addition, it should be considered during contract packaging whether large contracts would attract more experienced and better-performing contractors. Capacity of the implementation agency. The initial project delay was mainly caused by holdups in establishing a fully functional PIU, and weak capacity in project implementation caused by staff shortages. Subsequently, during implementation, the PIU was enhanced by transferring some technical staff from the West Bengal Public Works (Roads) Department (WBPWRD). However, most of these individuals had little experience of internationally funded projects. A fully functional PIU, headed by a project director with adequate administrative, financial and technical authority needs to be in place from the appraisal stage. Capacity building programs, including trainings on ADB policy and procedure should be arranged at project appraisal. Tight monitoring and control. Target-based periodic monitoring and close involvement by high-level government officials significantly contributes to tightening of monitoring and control of field activities, which helps to expedite project implementation. Land acquisition and resettlement. At appraisal, preparation of the resettlement plans was mainly based on preliminary socioeconomic assessment, which resulted in large variation in the estimated number of affected people and utility relocations during implementation. In accordance with government and ADB policies, compensation and assistance was provided to non-titled affected people, and their income level was restored. Compensation and special assistance to vulnerable people was also monitored. In future projects, a detailed resettlement plan should be prepared with an almost final estimation of inventory of loss, land requirements, and availability of the right of way. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/west-bengal-corridor-development-project-completion-report
MFF - Rural Roads Sector II Investment Program (Subproject 1) | India | Transport | 2012-01-03 | 1. Following the Pradhan Mantri Gram Sadak Yojana (Prime Ministerï¿½s Rural Roads Program) guidelines, each civil works contract had a stipulated completion period of 12 months. However, it was found during the implementation that 12 months was inadequate and that 15-18 months were needed. The proper timing of the signing of civil works contracts in relation to the monsoon period will avoid the loss of construction time due to the monsoon. This should be incorporated and considered in following subprojects under the multitranche financing facility. project cycle stage: Lesson Topics: 2. The Pradhan Mantri Gram Sadak Yojana (Prime Ministerï¿½s Rural Roads Program) roads usually generate new traffic and are sometimes being used as a shortcut if they provide a through route. Some field visits identified that some of the roads being used as shortcuts have already deteriorated. Consultation with communities also revealed that local residents were concerned about the quality of design and that it might not cater for future traffic. Also, the recent traffic survey (during the project completion review mission for the Rural Roads Sector I Project) found much higher traffic on the project roads than anticipated at appraisal. Systematic catering for future traffic growth must be strengthened, both in planning methodology and also in broader road network management. project cycle stage: Lesson Topics: 3. Some of the construction delays were caused by nonavailability of the contractors, including lack of working facilities, mobilization of resources, and/or skilled and qualified staff. Also, some of the civil work packages were geographically spread out which made it difficult for the contractors to manage their resources, labor, and materials. In future project formulation, the size of contracts should be adjusted to the availability of contractors. Also, as a sector-wide issue, the capacity of the construction industry should be increased substantially. A concerted effort is necessary, not only from the government offices dealing with infrastructure but also the offices dealing with the construction industry, technical education, and human resource development. Fostering construction and maintenance capacity, especially in rural roads, could be considered in future Pradhan Mantri Gram Sadak Yojana (Prime Ministerï¿½s Rural Roads Program) programs. Currently, there are some issues in routine maintenance contracts, such as fewer contractors participating in the bidding, or some contractors disappearing before the maintenance period is completed. project cycle stage: Lesson Topics: 4. Relocation of electricity poles and telecommunication lines was a common problem faced in almost all contract packages. Early identification and preparation - such as sufficient survey provision, accurate cost estimation, adequate and timely budgeting, and adequate coordination with concerned departments and state organizations - should be incorporated into future subprojects. project cycle stage: Lesson Topics: 5. The price for some materials, especially cement, steel, and asphalt, was substantially adjusted during implementation. Large-scale price eslalation led the contractors to slow down the work. Since the standard contract period for the Pradhan Mantri Gram Sadak Yojana (Prime Ministerï¿½s Rural Roads Program) works is only 12 months, provision for price escalation is not included in the civil works contract. This means that if the works take longer than 12 months for any reason, price escalation potentially becomes an issue. Future project preparation and implementation should consider price escalation and/or adopt special clauses applicable when the work is extended to more than 12 months. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/mff-rural-roads-sector-ii-investment-program-subproject-1
Rajasthan Urban Infrastructure Development Project | India |  | 2011-12-01 | Along with consultations related to project formulation and design, consultation with participating towns on cost recovery, tariffs, and user charges is crucial forsustainability. Advance action on the recruitment of project consultants can help avoid delays. Acting in advance to begin designs, package bids, and obtain all statutory clearances can help avoid delays. The cell for obtaining statutory approvals and clearances set up in the project management unit (PMU) at a later stage expedited clearances. Information, education, and communication aimed at changing the behavior of urban residents are necessary to achieve design results. Involving specialist agencies for specific componentsï¿½the Indian National Trust for Art and Cultural Heritage for this project's heritage component, for exampleï¿½ leads to positive outcomes. A good project performance monitoring system is essential to avoid ad hoc or delayed decisions. Weekly contractor review meetings, a practice introduced by the Urban Development Department (UDD), can help get past implementation hurdles in a timely manner. Small investments can have large impacts and make a big difference to people's lives. Examples from this project include the hospitals in the project cities and the diversion channel for rainwater in Kota. Including house service connections and door-to-door solid waste collection in the project scope ensures that the assets created will be used effectively. Providing for price variation in the contracts of private operators reduces project risks and is a fair practice. Achieving critical mass in the staffing of the PMU and project implementation units (PIUs) and retaining key staff members for the duration of the project are important factors in smooth implementation. A number of engineers involved in the project's design and familiar with packaging and contract conditions remained with PMU through implementation and greatly facilitated its execution. Providing awards and incentives to contractors for quality and timely delivery, as done by the UDD, helps foster a spirit of competition and better performance. Timely induction of counterpart staff and building up their capacity is critical to a successful handover of assets to urban local bodies (ULBs) and line agencies. Initiating community awareness and participation program (CAPP) activities early on and continuing them beyond the end of the project enhances a project's effectiveness and sustainability. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rajasthan-urban-infrastructure-development-project
Mumbai and Chennai Ports Project | India |  | 2011-11-01 | (No section on lessons provided in the report.) | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/mumbai-and-chennai-ports-project
Rural Roads Sector I Project | India | Transport | 2011-11-01 | The project was the first of its kind to use an ADB loan to implement a rural roads program in India. The project helped the states identify gaps in various program implementation activities. Some of these lessons learned are listed as in the following paragraphs. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-roads-sector-i-project
India: Madhya Pradesh Power Sector Development Program [Loans 1868/1869] | India | Energy | 2011-02-28 | 1. The power sector reform program needs to go beyond regulatory and institutional areas, and encompass accountability and incentive mechanisms to improve operational performance of power sector entities. The sector development program in Madhya Pradesh (MP) was based on the premise that regulatory and institutional reforms would result in improved performance of power sector entities. Although the regulatory and institutional reforms were implemented as intended, there was no significant improvement in the performance of most sector entities in MP. While there are several reasons for this, such as the underlying political economy issues constraining the measures that can be taken to reduce the aggregate technical ad commercial losses, the lack of financial autonomy, financial incentives and managerial accountability could have contributed to under-achievement of this important development outcome. The management of a utility is not responsible for financial performance and state government of MP has regularly stepped in to finance the cash deficit. The regulatory interventions were also limited to annual tariff settings based on progressively improving performance norms. [Executive summary, Main text, paras. 65, 149] project cycle stage: Implementation Lesson Topics: Sector Related Issues: Energy planning/management Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform 2. Restoring the financial viability of the power sector in the prevailing context of Madhya Pradesh requires a holistic approach encompassing technical, institutional, and governance measures. The improved operational efficiency of utilities and tariff adjustments aimed at reducing the cross-subsidies to residential and agricultural consumers can address part of the problem; however, the underlying issue in the power sector remains the high aggregate technical and commercial (ATC) losses. Reducing ATC losses requires technical measures (reducing the overloading of distribution feeders and having high-voltage distribution system [HVDS] and bundled conductors to prevent electricity pilferage), institutional measures (improved metering, billing and bill collection) as well as governance-related action (discouraging electricity theft by taking legal action against pilferers). Underlying political economy issues such as affordability to Madhya Pradesh agriculture sector in the event of full cost recovery for the supply of electricity to that sector also needs to be taken into account. As some of these issues are beyond the mandate of power sector entities, they have to be tackled as part of a broader fiscal reform initiative, given the high fiscal burden resulting from the power sector cash deficit. [Main text, paras. 88, 150] project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Country Context: political economy factors Sector Related Issues: Energy planning/management Policy & Reform: Public sector reform Methodologies/Approaches: Holistic approach 3. Overreliance on the private sector for power generation investments when there are structural issues in the distribution sector that may not result in desired outcomes. Financial viability and cost recovery in the sector are important considerations for private sector investments in power generation in the absence of opportunities to sell electricity outside the state. Before India s Electricity Act of 2003 was enacted, it was difficult to attract private sector investments to power generation in Madhya Pradesh, for investors were concerned about Madhya Pradesh State Electricity Board's ability to set aside adequate cash flows to meet power purchase obligations (escrow cover). After the provisions of the Electricity Act related to the setting up of a competitive power market and open access to a transmission network were implemented, private investors have shown increased willingness to invest in power generation in Madhya Pradesh as demonstrated by the recent success in initiating several private sector investments with likely capacity additions of more than 1,500 MW from private sector projects in next 2 3 years. [Main text, para. 124-125, 151] project cycle stage: Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financial management Sector Related Issues: Energy planning/management Sector Related Issues: Private sector | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/india-madhya-pradesh-power-sector-development-program-loans-1868-1869
Assam Power Sector Development Program | India | Energy | 2010-11-01 | Before ADB's support, the Assam State Electricity Board (ASEB) had not taken on transmission and distribution (T&D) projects of such magnitude due to financial constraints. However, the successful project implementation amply demonstrates that, if appropriate institutional support is provided, it can carry out such a project adequately. ASEB, with the support of the Government of Assam (GOA), took advance action to acquire land and clear other statutory hurdles, which eased implementation. In earlier ADB-assisted power sector projects, land acquisition and resettlement issues generally caused delays. Although ASEB was initially not fully conversant with ADB procedures, timely support from ADB and willingness of ASEB staff to adopt these practices helped implement the project. ASEB and GOA fully supported the project and retained key project management unit (PMU) staff. Like other state electricity boards, ASEB experienced difficulties in obtaining state government budgetary support, which badly constrained its operations. Since Assam's financial condition is particularly serious, addressing financial issues upfront is key to successful reform. Investments under the multitranche finance facility (MFF) will include institutional development, ensuring a sustainable reform program. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/assam-power-sector-development-program
Power Transmission Improvement (Sector) Project | India | Energy | 2008-11-12 | 1. With proper planning, effective project monitoring mechanisms, and motivated and well-trained personnel, infrastructure projects can be implemented successfully. Contributing to the successful performance of this energy project is the capacity of the Power Grid Corporation of India Limited (POWERGRID) to formulate and appraise, arrange finance for, and carry out engineering, procurement, and construction of a variety of projects across the country [Main text, paras. 30, 36, 44, 60] project cycle stage: Implementation Lesson Topics: 2. Advance actions on the end of the government can facilitate project implementation. The Power Grid Corporation of India Limited (POWERGRID) took advance action to acquire land and to obtain statutory clearances, which helped in timely project implementation. In some of the earlier ADB-assisted power sector projects, delays in land acquisition delayed the start of construction. [Main text, paras. 30, 61; Appendix 10] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Project management 3. Regular discussions with the Government on implementing assurances under the project prompted the Government to (i) address the issue of dues from state electricity boards, (ii) take necessary actions to enable the Power Grid Corporation of India Limited (POWERGRID) to enter into commercial contracts with beneficiaries, and (iii) bring in the regulatory regime at central and state level. The implementation of availability-based tariff in all the regions also helped POWERGRID to operate the regional grids with improved system stability and reliability. [Main text, paras. 10, 44, 59, 62] project cycle stage: Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-transmission-improvement-sector-project
Gujarat Power Sector Development Program | India | Energy | 2008-10-15 | 1. For successful implementation of reforms, it is essential to conduct thorough consultations with, and seek and obtain support from, all stakeholders. Regular consultations on reforms by the state government and the Gujarat Electricity Board (GEB) management with GEB staff, consumer representatives, and industry chambers have significantly helped in successful program implementation. Unlike other states where the state governments enacted various legislation to reform the power sector, it was the implementation of the provisions of such legislation with the full support of the political and administrative system of Gujarat that made a difference in the success of the reform program in that state. [Main text, paras. 50-52, 56, 71, 74] project cycle stage: Implementation Lesson Topics: Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation 2. To avoid delays in implementation, project processing teams need to give adequate attention to the executing agency's (EA) preparedness in starting the procurement activities. Despite being a well-conceived project and the approval for advanced procurement actions, these activities were not given enough importance during loan processing - causing implementation delays. Areas that also need to be considered include: (i) procurement capacity assessment of the EA before designing major infrastructure projects; (ii) proper implementation arrangements from the very beginning of the project (e.g., Resident Mission to monitor and support the EA); and (iii) appropriate measures to support the EA during project implementation (e.g., use ADB procurement specialists inputs through planned missions and customized trainings, and consultants to fill gaps in capacity). [Main text, paras. 32-33, 43, 75] project cycle stage: Design, Implementation Lesson Topics: Project Management: Procurement Project Management: Project management Capacity Development: Capacity development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/gujarat-power-sector-development-program
Madhya Pradesh Power Sector Development Program | India | Energy | 2008-04-06 | 1. With proper planning and timely guidance to the executing agency, the project could be implemented as per schedule. project cycle stage: Implementation Lesson Topics: 2. The Madhya Pradesh State Electricity Board (MPSEB) with the support of the state government took advance action to acquire land and other statutory clearances, which helped in project implementation. In earlier ADB-assisted power sector projects, delays in land acquisition delayed the project. Although MPSEB staff were not fully conversant with the multilateral bank's procurement procedures and guidelines, timely support from the resident mission and the willingness of MPSEB staff to adopt these practices had helped expedite the procurement process. Collaboration between MPSEB and ADB had also helped MPSEB to adopt the procurement practices of multilateral development agencies. MPSEB management and the state government also supported project implementation, retaining the key staff of the project management unit during the project implementation period. project cycle stage: Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/madhya-pradesh-power-sector-development-program
Urban and Environmental Infrastructure Facility Project | India | Water and other urban infrastructure and services | 2008-02-20 | 1. More in-depth and careful assessment of the PPTA outputs could have led the project appraisal team to wait to submit the Urban and Environmental Infrastructure Facility to the Board for approval until one of the envisaged Project components (i.e., to create a project support facility) was formulated. The evidence suggested that ADB did not adequately consider the PPTA's outputs, and perhaps was more focused on project approval than on achieving results. project cycle stage: Design Appraisal Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Modality: Technical Assistance Project Design: Appraisal Project Design: Subprojects Project Management: Risks/Risk management 2. The absence of an enabling urban sector policy and institutional framework adversely affected the subproject pipeline. In reality, despite the amendment to the State Municipal Acts28 and the implementation of some of the provisions of Constitution (Seventy Fourth Amendment) Act, 1992 (allowing for greater community participation, private sector participation and decentralization), municipalities were not sufficiently empowered and face several constraints. In several states, municipalities are still insufficiently involved in the decision making process. Other problems related to delays in funds transfer to municipalities and poor recovery from various tax and non-tax resources. Reforms in the urban infrastructure sector were slower than envisaged by the processing team. project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Funding Project Design: Subprojects Capacity Development: Institutional analysis Country Context: Decentralization Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Methodologies/Approaches: Community approach 3. Some urban infrastructure subsectors, such as urban transport in large metropolitan areas, could provide commercialization opportunities in the future. Commercialization of more basic urban infrastructure, such as water supply and sanitation, could potentially occur through public-private partnerships. But for this to happen, closer attention should be paid to ensuring that a suitable institutional framework is in place, strengthening urban local bodies' capacity, and structuring projects effectively. project cycle stage: Lesson Topics: Capacity Development: Human resources management Sector Related Issues: Private sector Sector Related Issues: Public-private partnership Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform 4. Under the Urban Environmental Infrastructure Facility (UEIF), the ADB loan to ICICI Bank was denominated in dollars. However, targeted urban local bodies' revenues were in rupees; therefore, six of the seven subloans were denominated in rupees. While this was not the case for the UEIF, such a currency mismatch may affect the usefulness of a credit line - depending on the availability of hedging instruments and the asset-liability management capacity of financial intermediaries. The local-currency loan product, newly introduced by ADB under the Innovation and Efficiency Initiative reforms would offer a solution to avoid such currency mismatches. project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Foreign exchange Finance & Financial Aspects: Local currency Project Design: Appraisal Project Design: Project design Project Management: Risks/Risk management 5. Development of a well-functioning debt market remains a challenge in India. The term money markets have insufficient depth and limited instruments to establish reliable short-term pricing benchmarks. Likewise, the government securities market lacks the liquidity to establish reliable pricing benchmarks for other long-term instruments. Moreover, development of the corporate-debt market is hampered by cumbersome procedures for public issuance of securities; a narrow investor base (this is partly due to remaining obstacles to institutional investing); and a lack of innovative debt, derivatives, and securitization instruments, among other reasons. ADB funds translated into higher costs than the comparable loans from domestic financial institutions available at lower interest rates, albeit for shorter durations. This was due to a lack of domestic currency hedging instruments. Thus, potential benefits of ADB's longer-tenure loans were not fully realized by ICICI Bank and its subborrowers. project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Foreign exchange Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/urban-and-environmental-infrastructure-facility-project
National Highways Project | India | Multisector | 2008-01-17 | 1. The Project showed that a contractor's ability to commit resources to a contract is crucial to performance. Prequalification documents require bidders to demonstrate their technical and financial capacity, and bid documents require them to commit technical and financial resources for the implementation of the works if awarded the contract. However, there are no effective mechanisms to ensure that bidders who prequalify and are awarded the contract indeed provide the required equipment, working capital, and management staff in the project sites as stipulated in the bid documents. The provisions in the bid documents must be made more rigorous and stringent to ensure that the contractors provide the committed technical and financial resources for project implementation and that the projects are completed on time. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Procurement 2. The absence of detailed field investigations during the design stage caused delays and necessary changes in the original design. To avoid such delays, the quality of the design can be improved through detailed review and thorough field investigations. project cycle stage: Design Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design In the case of the Project, implementation was delayed at the start primarily by inadequate project readiness. The lessons were incorporated by ADB in its subsequent loans to National Highways Authority of India. project cycle stage: Concept, Design, Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/national-highways-project
Karnataka Urban Infrastructure Development Project (Loan 1415/1416-IND) | India |  | 2007-11-30 | 1. Institutional development and training should be given equal priority with development of physical components. This has been done to a great extent in this project, enabling the Karnataka Urban Infrastructure Development and Finance Corporation (KUIDFC) itself to undertake the design of the North Karnataka Urban Sector Investment Program, with KUIDFC supplying the project concept and details while ADB prepares only the Report and Recommendation of the President (RRP). project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development Country Context: Prioritization Sector Related Issues: Urban sector/development 2. Since project preparatory technical assistance (PPTAs) in situations such as those occurring in India need to do much identification work, and are not generally given the time and resources to include detailed design and procurement, ADB should consider granting bridging technical assistance (TAs), or alternatively approving TA loans, so that when an investment loan becomes effective, subcomponents can be tendered and civil works can start within the first year. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Project Management: Procurement 3. The capabilities of urban local bodies (ULBs) acting as implementing agencies need to be investigated in more detail, especially in small ULBs such as Ramanagaram and Channapatna, so that the Karnataka Urban Infrastructure Development and Finance Corporation (KUIDFC or any other Project Management Unit) will not have to implement the work on their behalf or turn the civil works over to a specialized agency such as the Karnataka Urban Water Supply and Drainage Board (KUWSDB) for operation and maintenance (O&M) and tariff collections. An extensive program of capacity development needs to precede and accompany physical investments in small towns, especially when these are expected to be operated on a cost recovery basis. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Capacity development Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development Components should be designed so that they can be replicated in other integrated urban development projects (IUDPs). The project has been successful in this with regard to water supply, internal roads anddrainage, slum upgrading and low-cost sanitation. It has been less successful in sewage treatment plants (STPs), truckterminals, municipal buildings, and residential sites and services schemes. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Country Context: Decentralization Sector Related Issues: Health and sanitation management Sector Related Issues: Roading Sector Related Issues: Urban sector/development Given the numerous problems with consultants andcontractors, partly due to procurement and safeguard arrangements promoted by ADB that arevery different to government requirements, there is a need for much hands-on support in aproject that involves many agencies and small towns that have not previously been involvedwith ADB. Since the Karnataka Urban Infrastructure Development Project (KUIFDC) was being set up at the same time, constant ADB projectadministration support is required. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement Project Management: Project administration Sector Related Issues: Urban sector/development Project preparation and design for complicated, multisector, multi-town projects such as the Karnataka Urban Infrastructure Development Project (KUIDP) should be allotted adequate time to do the necessary technical, financial, socioeconomic and institutional analysis so that ultimate project implementation and evaluation closely resemble original project objectives, outputs and financial projections. Time needs also to be taken to build consensus within urban local bodies (ULBs) on the importance of operation and maintenance (O&M) of assets. This is especially the case when a central government decides on the allocation of foreign loans to states, and where the intra-state demand for a particular loan-based project orfor some preconceived components may not be strong at the start of the Project Preparatory Technical Assistance (PPTA). project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Modality: Technical Assistance Monitoring & Evaluation: Project evaluation Project Design: Project design Project Management: Operation and maintenance Project Management: Project management Capacity Development: Institutional analysis Capacity Development: Ownership Country Context: Decentralization Sector Related Issues: Urban sector/development The ultimate focus should be on theprovision of affordable services and the cost recovery thereof, not just the provision of civilworks and equipment. Least-cost analysis should identify the type of technical solution thatwould provide the service at the lowest cost for the project as well as the beneficiary.Performance-based private sector participation schemes should be pursued, and serviceprovision emphasized. It can be questioned whether expensive water-borne sewerage (versusthe proven double vault compost low-cost sanitation units) was necessary in small towns suchas Ramanagaram and Channapatna. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Sector Related Issues: Urban sector/development The urban local bodies (ULBs) and their clienteles should be involved in thedesign of all project components, especially water, sewer and drainage components. Designand implementation according to beneficiaries felt needs generally leads to better post-project cost recovery. Involvement of nongovernment organizations (NGOs) leads to good results, particularly in identifying needsregarding slum upgrading and low-cost sanitation components. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Project Design: Project design Country Context: Decentralization Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/karnataka-urban-infrastructure-development-project-loan-1415-1416-ind
Country Assistance Program Evaluation for India (2007) | India |  | 2007-09-30 | ADB's adoption of more complex loan processing, implementation, and safeguard requirements, while important, has increased the nonfinancial costs of borrowing. This has increased the pressure on ADB to offer value-addition, such as (i) objective analysis and advice on policy and operational issues; (ii) capacity development; and (iii) support for increased supply of public and semipublic goods including infrastructure networks, energy efficiency, clean environment, inclusive development, and regional cooperation. To be effective in this competitive environment, ADB will need to clearly understand and respond to the needs of India, which is one of its largest and most important clients. The Government of India and ADB needs to review mutual expectations and objectives, and proactive efforts for their realization to further elevate their partnertship and make it more equally rewarding. [Main text, para. 195(ii)] project cycle stage: Concept Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Project Design: Appraisal Project Management: Project management Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Assistance programs can succeed if the client demonstrates strong ownership of and commitment to the establishment of a conducive policy and institutional environment for sector development which is shared by other stakeholders to ensure sustained effectiveness. project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Capacity Development: Ownership Policy & Reform: Policy reforms/framework Methodologies/Approaches: Sectoral approach Even with small overall assistance compared to large overall investment requirements (as in the case of India), ADB support can make significant contributions to the development process, not only through financial resource transfers, but more importantly through support for project design and implementation, introducing best practices for Project Management, procurement, and financial management; and through policy dialogue and associated capacity development assistance for the identification and implementation of appropriate policy options. A large number of ADB-financed projects contributed to best practice development at the sector level.[Main text, para. 195(i)] project cycle stage: Concept, Design, Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Procurement Project Management: Project management Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Project implementation performance can be dramatically improved, if proactive portfolio management approaches are adopted by regional departments particularly the allocation of adequate staff and TA resources for project preparation and implementation, timely capacity development support for new executing agencies (EAs), and the initiation of regular sector-based tripartite project implementation review meetings. project cycle stage: Design, Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity development Capacity Development: Human resources management Prospects of enhanced effectiveness are increased when assistance is focused onrelatively few areas than when scattered over a large range of sectors and states. project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Country Context: Prioritization Policy & Reform: Policy reforms/framework | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-india-2007
Gujarat Public Sector Resource Management Program (Loan 1506-IND) | India |  | 2007-07-31 | 1. Public sector reforms are an iterative process over 5 10 years. While the OEM rated the GPSRMP as successful, the 2-year design provided insufficient time to achieve the reform agenda, and did not adequately anticipate the complexityof implementation or the impact of exogenous factors. This is equally applicable to SOE reforms, where neither the technical complexity nor the time required to implement different SOE reform options, was adequately recognized in the design. At the time of the OEM, about 10 years after the program was designed, SOE reforms continued. Reforms require a long-term commitment combining loan and adequate grant resources in different configurations in response to the progress of reforms. Ideally, an indicative allocation of additional resources should be programmed at the design stage. [Main text, para. 83] project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Lending modality Modality: Program Project Design: Project design Policy & Reform: Public sector reform 2. Central government policy change or natural calamities are exogenous factors that are not highly improbable risks, but rather events that are reasonably likely to occur in the medium term. Perhaps they should be treated more like assumptions than risks. Irrespective, policy actions, tranche conditions, and covenants should be individually assessed in terms of the effect exogenous factors could have on them and mitigation measures designed accordingly. However, as the impact of natural disasters is particularly difficult to estimate and mitigate, mechanisms to review conditions and covenants either negatively or positively impacted by such factors need to be clearly specified in the design. [Main text, para. 85] project cycle stage: Feasibility, Appraisal Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Impact evaluation Project Design: Project design Project Management: Risks/Risk management Country Context: Emergency Policy & Reform: Policy reforms/framework A state lending program by multilateral institutions, constitutionally must involve the national government, which is the Borrower, onlending to the states. Mechanisms need to be in place to align reform targets between ADB, the state, andcentral government. This also requires flexibility within ADB for Management to make adjustments required to achieve outcomes. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Project administration Country Context: Decentralization Policy & Reform: Reform Methodologies/Approaches: Targeting Public resource management programs provide an opportunity to explicitly target revenue and expenditure reforms to support the state government's anticorruption agenda. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Public governance Policy & Reform: Reform Methodologies/Approaches: Targeting Quantitative targets are important to focus reform and its inherent processes. However,if quantitative targets must be used as loan conditions or targets in national-state reformagreements, the assumptions and limitations of such targets, along with transparentmechanisms to address the impact of exogenous influences, need to be clearly defined in thedesign. This applies equally to process conditions focusing on developing systems andinstitutional capacity, where the magnitude, sequencing, and pace to achieve the outcome mayalso require renegotiation during implementation. Institutional mechanisms are required toadequately respond to changes during implementation that materially affect loan conditions.This may include Management having the flexibility to make adjustments to ensure achievementof outcomes without having to revert to the ADB Board. An alternative is to focus loan conditionsat a broader level of balanced budget over the cycle and use quantitative targets as indicatorsover a longer period. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Indicators Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity development Policy & Reform: Reform Methodologies/Approaches: Process approach Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/gujarat-public-sector-resource-management-program-loan-1506-ind
Private Sector Infrastructure Facility in India (Loans 1480/1481-IND) | India | Multisector | 2006-09-30 | 1. The timeliness and complementarities of ADB operations were key factors in the success of a pioneering project with a primary objective as broad as private sector participation in infrastructure development. The Private Sector Infrastructure Facility (PSIF) was timely, as it complemented the government's policy reforms aimed to promote private sector participation. Likewise, several other ongoing and follow-on ADB operations complemented the PSIF. Institutional and policy reforms supported by public sector operations resulted in PSIF-funded subprojects; satisfactory outcomes of these subprojects enhanced further involvement of the private sector in infrastructure development. [Main text, paras. 10, 61, 63, 79] project cycle stage: Implementation Lesson Topics: Project Design: Subprojects Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework 2. Under the Private Sector Infrastructure Facility, ADB loans were denominated in dollars while all subloans were denominated in rupees. Such a currency mismatch may constrain the usefulness of ADB's credit lines. It is expected that the local currency loan product, newly introduced by ADB under the Innovation and Efficiency Initiative (IEI) reforms, will respond to issues related to the currency mismatch between credit lines extended by ADB and subloans extended by financial intermediaries. Likewise, in conjunction with the IEI reforms, ADB can now offer more flexibility in cost-sharing arrangements, and expand the list of eligible expenses that ADB can finance. [Main text, paras. 38, 82-83] project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Lending modality Policy & Reform: Reform 3. Given the relatively stringent environmental and social guidelines for infrastructure projects now in place in India, the executing agency deemed that ADB needs to shift its focus to implementation and enforcement of these guidelines from at-entry assessments. Such a shift would contribute to quality control of subprojects, while improving the usefulness of ADB credit lines. In the operations of the private sector infrastructure facility, the time spent by ADB in reviewing environmental and social impact assessment reports, prior to approval of subloans, was in some cases excessive. This resulted in delays in ADB s subloan approval and subsequent change in subborrowers' financing, leading to underutilization of ADB's credit line. [Main text, para. 64-65, 84] project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Project Design: Appraisal 4. Benchmark floating interest rates have not yet been fully established in India, and fixed interest rates were still predominantly used for long-term financing. Most subloans were prepaid during and after the period when domestic interest rates were decreasing. Had floating interest rate lending been more actively used, there might have been fewer instances of prepayment. [Main text, para. 21, 23, 85] project cycle stage: Appraisal Lesson Topics: 5. ADB needs to take an innovative approach in formulating the Private Sector Infrastructure Facility (PSIF) III listed in the Country Strategy and Program Update. Given the significant changes in India's financial sector and its approach to private sector infrastructure projects, the executing agency no longer considers the credit facilities, covered under the government guarantee (such as PSIF), abreast with the present government policy on Public-Private Partnerships. Strengthening of ADB's capacity in subsovereign and nonsovereign public sector financing, as envisaged under the Innovation and Efficiency Initiative, would be essential in responding to the changing economic environment and client needs in India. [Main text, paras. 36, 86] project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Public-private partnership 6. ADB needs to consider an alternative approach to creating a functional monitoring framework that balances increased administrative costs with the need for, and use of, the data collected. Options may include specifying the required data and timing of data collection in a loan agreement, selecting sample subprojects for detailed performance evaluation, and clarifying the benefit monitoring and evaluation (BME) of prepaid subprojects in the loan agreement. Evaluation noted the lack of design and monitoring framework as well as performance indicators and targets making the BME of the Private Sector Infrastructure Facility inherently weak. Hence, the importance of a clear and pragmatic solution for the purpose of developing an effective and efficient monitoring and evaluation framework for a credit line. [Main text, paras. 53, 87] project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Loan Agreement Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection Project Design: Subprojects | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/private-sector-infrastructure-facility-india-loans-1480-1481-ind
Karnataka Urban Infrastructure Development Project | India |  | 2006-05-15 | A good financial and physical project performance monitoring system is essential to avoid ad hoc or delayed decisions. project cycle stage: Feasibility Lesson Topics: Changes in EAs, IAs, and consulting staff must be minimized by planning long-term assignments from the beginning. When prolonged engagement of consulting services is envisaged, as in the urban sector, procedures for extending services and changing personnel need to be incorporated into the consulting service contracts. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Urban sector/development Contract monitoring procedures and training must be provided to EAs, IAs, project consultants, and contractors. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building Focus must be shifted from creation of assets to provision of improved service, taking into account the O&M of the constructed facility, its pricing, and revenue collection. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Operation and maintenance New water and sewerage schemes should include house service connections, installed at the same time as street lines are constructed. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development Policy and reform aspects need to be realistic and politically doable. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Policy & Reform: Policy reforms/framework Policy & Reform: Reform Project components must undergo detailed planning and appraisal to confirm demand and sustainability. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Design: Project design Project implementation arrangements need to be clearly defined, and detailed procedures established at the project's start. project cycle stage: Design Lesson Topics: Smaller towns must receive O&M support for the first few years after implementation is completed. The field work conducted for this report found that many of the new facilities were not used for up to 18 months after the works contracts were completed. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Sector Related Issues: Urban sector/development The capacity of smaller cities and towns is not adequate to plan, design, or implement major projects or to operate new facilities. Though mandated by the 74th Constitutional Amendment, small towns have not yet developed sufficienthuman capital or the financial wherewithal, and require extensive capacity building. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Urban sector/development The participating towns need to be fully engaged and consulted during loan formulation, including discussions on the details of capital and O&M costs and the impact on their budgets, revenues, taxes, and tariffs. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial analysis Project Design: Appraisal Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/karnataka-urban-infrastructure-development-project
Power Transmission (Sector) Project | India | Energy | 2005-09-09 | Regular discussions with the government on implementing assurances under the project prompted the government to (i) increase the rate of return on the executing agency's (POWERGRID's) equity from 12% to 16% ; (ii) address the issue of dues from state electricity boards (SEBs); and (iii) take necessary actions to enable the executing agency to enter into commercial contracts with beneficiaries. Further, the implementation of availability-based tariff (ABT) in all the regions helped the executing agency to operate the regional grids with improved system stability and reliability. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Public governance Loan Agreement: Covenants Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation The executing agency took action to acquire land and other statutory clearances well in advance, which helped in project implementation. In earlier ADB-assisted power sector projects, delays in land acquisition had delayed the project before construction could start. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Resettlement Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management With proper planning, effective project monitoring mechanisms, and motivated and well-trained personnel, infrastructure projects can be implemented successfully even in difficult terrains, despite adverse weather conditions and areas affected by insurgencies. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project management Country Context: Emergency | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-transmission-sector-project
Industrial Energy Efficiency Project in India (Loan 1343-IND) | India | Energy | 2005-02-28 | If domestic currency lending were available for commercially oriented public sector entities, the demand for ADB funds might have increased significantly. Although the project formulation had some weaknesses, the difficulty in disbursing the loan is a strong indicator that the loan proceeds were not competitive. The transaction costs and financial terms were not attractive to subborrowers. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Finance & Financial Aspects: Local currency Project monitoring and supervision arrangements should be in place before project implementation. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration Project Management: Project supervision Since the subprojects are scattered, domestic consultants could have been engaged to visit each subproject at least once during implementation. Visiting all subproject sites during project implementation is an essential part of the project administration. project cycle stage: Implementation Lesson Topics: Project Design: Subprojects Project Management: Consultants Project Management: Project administration Project Management: Project supervision The executing agencies of financial intermediation loans should be required to provide ADB with the subloan agreement before the first disbursement for the respective subproject. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Loan Agreement: Relending Agreements Project Design: Subprojects Project Management: Executing/Implementing agencies The relaxation of subproject selection criteria and simplification of disbursement procedures can undermine the attainment of project objectives. These measures might have been appropriate to accelerate loan disbursements. However, they gave insufficient consideration to their impacts on project outcomes. As a consequence, project selection and assessment became a repackaging exercise; and the project scope, as implemented, deviated considerably from that envisaged at appraisal. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Subprojects The simplification of disbursement procedures can make the verification of project costs and expenditures difficult. Under simplified procedures subborrowers should be required to maintain records of all expenses financed under the project for more than just one year after the loan closing date. As with project loans, the executing agencies should be required to maintain original receipts for all expenses financed under the ADB loan for at least 5 years after loan closing. Such measures are needed to ensure the presence of a strong trail for auditing, and that the funds are used for the purpose intended. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project supervision | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/industrial-energy-efficiency-project-india-loan-1343-ind
Gujarat Public Sector Resource Management Program | India |  | 2004-12-15 | ADB's monitoring of program implementation should have been more rigorous, especially for a program that was envisaged to be completed in two years. In addition, the program should have taken into account government constraints in terms of human resources, both in quantity and quality, in implementing the reforms. Since the program aimed at undertaking several areas of fiscal reforms all at once, the technical assistance (TA) to the state government during implementation should have been prepared in a comprehensive manner. This requires either a single comprehensive TA undertaking or several TA undertakings that concertedly help build or enhance the capacity of government officials in ushering all intended structural adjustments. However, the accompanying TA only covered one aspect of the program (creating an enabling environment for the private sector to participate in investing in key infrastructure sectors through the establishment of Gujarat Infrastructure Development Board or GIDB). Capacity building in the other important reform areas, namely tax reforms, expenditure management, and state-owned enterprise (SOE) restructuring, was not incorporated in the accompanying TA. Even though two stand-alone capacity-building TA activities for strengthening the restructuring of SOEs and public finances were implemented concurrently with the program, coordination and supervision mechanisms among all capacity-building TA activities including the accompanying TA, were not provided for under the program at appraisal. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Public governance Modality: Program Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Management: Project management Project Management: Project supervision Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Although several advisory technical assistance (TA) activities were provided prior to the processing of the program loan, the program was prepared without a specific comprehensive preparatory TA. The policy conditions were based on thorough policy dialogue between ADB and Government of Gujarat (GOG) high-level government officials, who were champions of tax reforms and state-owned enterprise (SOE) restructuring. However, an in-depth analysis and projection of baseline and reform scenarios would have helped the program's design by identifying reform measures that were carefully prioritized, appropriately sequenced, and well balanced among various reform areas (revenue, expenditure, and public enterprise reform) and achievable within the planned time frame. Particularly, the program set specific numerical fiscal targets for future years during program implementation and identified these targets as tranche conditions, without allowing for adjustment in the case of deviation from the underlining assumptions. Therefore, the links between deviations from the program's economic assumptions and the targeted fiscal deficits were not integrated into the policy matrix.Such in-depth analysis could have provided a clear link between policy actions and desirable outcomes, such as a reduction in fiscal deficit and debt burden. The effectiveness of each policy action would also be assessed through such analysis. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Public governance Loan Agreement: Covenants Modality: Program Modality: Technical Assistance Monitoring & Evaluation: Baseline data Project Design: Project design Project Management: Executing/Implementing agencies Country Context: Prioritization Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Targeting Divestment of a specific, identified sate-owned enterprise (SOE) may not have been suitable as a tranche condition in the policy matrix, since it undermined the state government's leverage in price negotiation with the potential buyers of the SOE shares. The public's knowledge of the tie between divestment of SOE shares and tranche release could have motivated the potential buyers to offer much lower prices than those that were fair for the shares. Low share price offerings may not have occurred if the divesting SOEs had great profit potential. Unfortunately, most of the SOEs that were to be restructured and/or privatized did not have such potential. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Policy & Reform: Policy matrix Policy & Reform: Privatization Policy & Reform: Public sector reform Gujarat was selected as the first Indian state for which ADB would provide assistance to undertake this type of program lending because of its reform orientation. The program showed that strong commitments from high-level officials who were champions of the reform were critical to carrying the program through numerous obstacles, including external shocks and implementation difficulties. However, the programï¿½s successful implementation also required support ownership from different levels of government, including local government bodies, and different levels of government officials across various relevant departments. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Ownership Country Context: Decentralization Policy & Reform: Reform The program's design should have taken into account the ground reality in terms of legal environment, political commitments, public support, and government capacity and resources. Legal impediments, both at state and national levels, to proposed policy actions must be checked thoroughly. When setting goals, program designers should also take into account political cycles, particularly the timing of future elections and budgetary cycles. Fiscal reforms may have adverse impacts in the short term through increased tax payments and user charges, reduced opportunity to be recruited in offices in the public sector, and closed state-owned enterprises (SOEs). But in the long term, reforms should bring about sustainability in the fiscal stance of not only a focal state but also the fiscal stances of other states and the government as a whole. Program design should recognize the spillover effect of proposed reform initiatives. Specifically, program design should examine whether a state government or ADB's future focal state can be fiscally sustained if it is to follow suit in adopting similar reform initiatives. Therefore, terms of payments for settling past liabilities of a state government and its SOEs, including debt outstanding to financial institutions and salary arrears, should be carefully negotiated with creditors. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Public governance Crosscutting Issues/Themes: Sustainability Modality: Program Project Design: Project design Capacity Development: Institutional analysis Capacity Development: Ownership Country Context: Decentralization Policy & Reform: Policy matrix Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/gujarat-public-sector-resource-management-program
Madhya Pradesh Public Resource Management Program | India |  | 2004-12-15 | A number of measures, when duly observed, enhance the developmental impact and effective implementation of a project or program. Namely, actual requirements for satisfactory program implementation need to be properly costed before project implementation. Then sources of financing should be clearly identified, and irrevocable confirmation should be secured for the commitment from sources of financing to ensure smooth project implementation. Funds must also be made available in a timely manner, and, most importantly, a sound contingency plan must be prepared, in case these funds are no longer available or are grossly delayed. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Modality: Program In addition to technical assistance on Support for the Government of Madhya Pradesh Public Finance Reform and Institutional Strengthening, and Strengthening Local Government in Madhya Pradesh (implementation of which overlapped with the program), preparatory technical assistance might have contributed to developing the foundation for the program framework and provided some of the more urgent capacity-building activities before program implementation started. project cycle stage: Feasibility Lesson Topics: Modality: Program Modality: Technical Assistance Capacity Development: Capacity building Policy & Reform: Policy reforms/framework Lessons learned from previous programs were incorporated into the design of the program, including the importance of capacity building and institutional strengthening for seamless, self-sufficient, and satisfactory implementation. Learning from the Gujarat Public Sector Resource Management Program, the timeframe for implementation of reforms was extended to 3 years. Extensive dialogue between ADB and the Government of Madhya Pradesh (GoMP) preceded program design. Unrealistic time frames, revenue projections, and tax buoyancies were avoided. And the need to ensure an appropriate regulatory and pricing framework for the power sector at an early stage of comprehensive reforms was reflected in program design. project cycle stage: Concept Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Energy planning/management Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework The program demonstrated the importance of a flexible approach to modeling a reform agenda. As suggested in progress reports, a cluster framework for such a program would have allowed for a more organic approach, vis-ï¿½-vis formulating specific tranche release conditions to address unforeseen changes during program implementation without deviating from the fundamental assumptions and deliverables of the program. Similarly, even if the probability of occurrence is slim, all possible shocks should be a part of the program's contingency plan and, hence, design. Both feedback and spillover effects should be considered carefully and whenever possible, and incorporated in project design as appropriate. A horizontal approach to reform can still benefit from prioritization of certain sectors over others and should ensure a holistic approach to reform, as no sector functions independently from the rest of the economy. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Loan Agreement: Covenants Modality: Cluster operations Modality: Program Project Design: Project design Country Context: Prioritization Policy & Reform: Reform Methodologies/Approaches: Holistic approach Methodologies/Approaches: Process approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/madhya-pradesh-public-resource-management-program
Capital Market Development Program in India (Loan 1408-IND) | India | Finance | 2004-07-31 | Adequately developing the institutional, administrative, and regulatory framework required a substantial commitment of time and resources. Therefore, the importance of government ownership and dialogue cannot be underestimated. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Capacity Development: Ownership Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Policy & Reform: Reform Capital market development requires a certain depth of human resources or skills in the market. Ensuring sufficient skills and capacity to implement complex reforms were critical to the success of the program. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Capacity Development: Capacity building Capacity Development: Human resources management Policy & Reform: Reform | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/capital-market-development-program-india-loan-1408-ind
Selected Technical Assistance for Fiscal Management and Tax Administration in India | India | Public Sector Management | 2004-07-31 | ADB's capacity building technical assistance (TAs) for programs often are designed with short durations, so the advice or capacity built up can feed into these programs before their intended start dates. In addition, these TAs often have a wide scope and large numbers of consultancy assignments to be conducted within a short period of time. Since the purpose is not loan preparation but capacity building, longer TA durations that straddle the period before and after the approval of program loans are appropriate. Given that the capacity building needs are very large in this area, flexibility in the employment of TA resources is important to allow all resources to be used. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Public sector reform Advisory work in several states through technical assistance (TA), and followed up by program loan policy matrixes, has proven to be capable of piloting new practices and systems (e.g., value-added tax preparation, medium-term fiscal frameworks, fiscal responsibility acts, computerization of treasuries, etc.). Thus, they provide examples for other states to follow. At the same time, pilot activities in states that need nationwide decisions can lead to wasted effort if not well prepared at the central level. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Public sector reform Short duration, wide scope fiscal technical assistance (TAs) also run the risk of duplicating work of TA funded by other external agencies. This is particularly true in agencies other than the finance departments, such as health, education, and local government agencies. Such TA needs to be carefully coordinated during implementation. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Study tours and foreign training of senior government staff as part of technical assistance (TAs) are often not effective for building long-term capacity, because of the frequent transfers of senior officers. Such instruments might be useful for objectives that can be achieved within a very short period, or in cases where decisions need to be made based on the study of systems in foreign countries. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Public sector reform Successful fiscal management is only partly related to improvements in capacity building or the institution of legal and procedural instruments. Many factors, such as political will and the absence of calamities, are beyond the control of the technical assistance or ADB. TAs will do best when capacity building is embedded in larger fiscal programs of the government, which carry top priority. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Public sector reform Technical assistance (TA) that combines capacity building in revenue generation, budget preparation, and expenditure and debt management should only be undertaken in the context of fiscal management-oriented public resource management programs. These programs can build upon the TA's outputs. Stand-alone TAs in fiscal management that are confined to one of these components would do better. Generally, ADB needs to have clear fiscal management strategies in countries receiving fiscal assistance. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Public sector reform To make the case for necessary reforms that finance and revenue departments wish to implement, the strategic use of technical assistance (TA) outputs in fiscal management is usually important to win the endorsement by governments. TAs in fiscal management preferably should include advice from (i) international experts, as they often are perceived to be more objective; (ii) national research institutes; or (iii) domestic consultants with a national standing, who command respect across party lines. Direct advice by ADB can also play this role, and more direct assistance from ADB staff for administering TA is essential. For practical as well as strategic reasons, conducting advisory work through high level committees and frequently meeting with working groups is very important, as the experience with some TA has shown. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants Capacity Development: Capacity development Policy & Reform: Public sector reform | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/selected-technical-assistance-fiscal-management-and-tax-administration-india
Gas Rehabilitation and Expansion Project (Loan 1285-IND) | India | Energy | 2003-12-31 | ADB should be prepared, in line with its country strategy, to independently assist the government in developing and updating the country's sector strategies and policies. project cycle stage: Country Partnership Strategy Lesson Topics: ADB should make realistic efforts at the time of project appraisal to assess its potential leverage through loan covenants, with respect to both the borrower and improvements and reforms to the sector overall. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Design: Appraisal Policy & Reform: Policy reforms/framework Because of the lack of impact of ADB s loan covenants on the government s policies, consideration should be given as to whether it is appropriate for ADB to impose loan covenants relating to reforms in sector policy on investment projects. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Impact evaluation Policy & Reform: Policy reforms/framework If ADB approves a loan substantially in advance of government approval for projects, a reassessment should be made of total project costs and the size of the ADB loan, once all approvals have been obtained. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Loan Agreement Project Design: Appraisal In projects that lead to expanded industrial and manufacturing activities, ADB should be assured that all relevant environment, health and safety regulations of the respective governments will be complied with. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector The inclusion of intangible non-investment costs in the total project cost, especially items such as physical and price contingencies and interest during construction, should be fully justified on the basis of the specific conditions relating to the country and to the project. Care should be taken to avoid arbitrary percentage mark-ups and double-counting. If necessary, alternative, more realistic scenarios should be used. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design There should be a realistic assessment of financial costs, technical risks, inflation and the competitive situation for the procurement of all project investment components. In particular, ADB should rely on technical experts at all times to examine the basis for project cost estimation and the impact on cost estimates of any changes in project scope or technical specifications. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Consultants Project Management: Procurement Project Management: Project administration Project Management: Risks/Risk management There should be clear justification of the technical, environmental and financial additionality, and ADB s developmental and policy involvement in projects, at the time of appraisal. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Project Design: Appraisal Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/gas-rehabilitation-and-expansion-project-loan-1285-ind
Coal Ports Project | India | Transport | 2003-09-15 | Although ADB approved advance action on the recruitment of consultants andretroactive financing for the preparation of design and bid documents for the project'scomponents at the request of the government, the benefits of the approval did not materialize,owing to the substantial delay of about 16 months in the appointment of the consultants. Lack ofadequate delegation of powers to the executing agencies (EAs) in the appointment of consultants resulted in thedelay. Although there were other implementation delays caused by the EAs, the time needed fordesign, bid preparation, and awarding works was not estimated in a realistic manner duringappraisal. There is a need for appraisal missions to more carefully estimate the time required forsuch complex infrastructure works. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Country Context: Decentralization Sector Related Issues: Transport planning If a project involves major investments to be made by some agencies other than the executing agency, it is generally not adequate only to set up a high level committee and provision loan covenants ensuring the investments required by the other agencies. All the stakeholders and the beneficiaries of the project should have a substantial stake, preferably financial, in a project and share its associated design, implementation, and commercial risks. Under the project, all the design, implementation, and commercial risks were borne by the facility provider. None were borne by the facility users. It would have been a more effectiveapproach to ensure that (i) for all captive dedicated port facilities (those meant for use by asingle user), there should be an equitable sharing of the design, implementation, andcommercial risks associated with the project, in the form of equity ownership, debt provision,and sharing of costs and revenue between the facility provider and the facility user; (ii) aminimum annual throughput agreement should be in place between the various facility providersand the facility users; and (iii) the minimum throughput agreement should also include aprovision on the assured opening date of the facility and penalties for any delay in opening. project cycle stage: Design Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Project Design: Project design Project Management: Project management Project Management: Risks/Risk management Sector Related Issues: Transport planning Reflecting the disputes between the executing agencies and the consultants, systems for ensuring theaccountability of consultants, such as professional liability insurance, should be devised andbuilt into consultancy contracts. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/coal-ports-project
LPG Pipeline Project | India | Energy | 2003-09-15 | For a gas project of this magnitude, a high level of preparedness and planning on the part of the executing agency, given regular monitoring and review by ADB, enabled timely completion and realization of project objectives. ADB followed closely all activities, through headquarters and INRM review missions. These proved valuable in expediting project schedules and monitoring major milestones. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Other: Resident Mission Sector Related Issues: Energy planning/management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/lpg-pipeline-project
Housing Finance Project | India | Finance | 2003-08-15 | Formal agencies hesitate to lend to community-based finance institutions (CFIs)/non-government organizations (NGOs), which are seen as high-risk borrowers due to the discontinuous and uncertain income streams of the ultimate beneficiaries, lack of security, incapacity of the intermediary, etc. The perceived risk compelled housing finance institutions (HFIs) to be selective in lending through this window. Housing Development Finance Corporation Limited (HDFC) for instance, has reported 100% recovery in assistance to CFIs/NGOs, but not out of the project funds, suggesting that to meet the large gap in housing for the poor, specialized HFIs with a social mandate, such as Housing and Urban Development Corporation Limited (HUDCO), are still relevant. However, to sustain such institutions, a transparent mechanism is needed to meet the social costs of such intermediation, and processes and procedures of field-level institutions such as the cooperative societies need to be changed fundamentally. Linkages between CFIs/NGOs and HFIs for slum networking can be realized only after some of the macro issues relating to state policies on land title, cost recovery, transparency of subsidies, improved governance, and reform of state agencies' financial management are solved. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Civil society Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Project Management: Risks/Risk management Sector Related Issues: Urban sector/development Policy & Reform: Public sector reform Policy & Reform: Reform Project experience emphasizes that (i) a different set of guidelines must be adopted to assess and mitigate risks under community-based finance institution (CFI)/NGO assistance, (ii) high intermediation costs should be recognized, and (iii) intermediaries' capacity must be upgraded. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Civil society Finance & Financial Aspects: Financial analysis Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity building Methodologies/Approaches: Community approach The project would have achieved a higher leverage had the borrowers shouldered a higher share of the project cost. The prevalence of subsidized government-sponsored schemes discourages cost recovery even from those willing and able to repay. Field reviews of some low-income group schemes revealed many instances of higher investment than estimated by the borrowers, funded by informal sources such as savings, moneylenders, etc. While many such beneficiaries regularly serviced such informal loans, often at usurious rates of interest, repayments to government intermediaries were irregular. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Urban sector/development To facilitate monitoring and timely response, executing agencies must understandearly on ADB's procedures and feedback requirements. The usually stipulated free and statement of expenditure (SOE) limits are often irrelevant in these kinds of projects where the subloans constitute individual mortgage loans, which are too small ($1,000-10,000) to be above the limits. A format should be devised to capture data during disbursement to better monitor subprojects and facilitate subsequent reviews on a random basis. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project reporting To maximize the chances of project success, particularly in policy reformand institutional development, the borrowers' roles need to be clearly laid out and agreed uponformally. project cycle stage: Design Lesson Topics: Project Design: Project design Capacity Development: Capacity development Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/housing-finance-project
Industrial Credit and Investment Corporation of India Limited | India | Energy, Finance, Transport, Multisector | 2003-08-15 | A project-to-project approach to infrastructure development is not likely to advanceprivate-sector participation significantly, certainly not to the extent the government presentlyimagines. Capacity remains weak, and regulatory and institutional structures, standardizedsystems and processes especially at the state level remain insufficient. In order to addressthese problems, ADB has approved a TA to identify and resolve gaps in policy, the operatingenvironment, and governance structures. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity assessment Capacity Development: Capacity development Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework India's long-term debt market remains underdeveloped and suffers from a number ofimpediments. It has few players; inadequate support infrastructure; very limited participation bylong-term investors such as funds and insurance companies; and a weak secondary market,which leads to poor liquidity and the absence of a benchmark yield curve. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Private sector The Private Sector Infrastructure Facility (PSIF) encouraged the two development financial institutions to set up dedicated units for infrastructure. These groups provide a complete range of financial services, from identifyingprojects to structuring complex transactions.The PSIF financed debentures for the subprojects, with the objective of developing anactive secondary market for infrastructure securities. Most of the subprojects had not begun stable commercial operation, however, making the debt instruments unattractive investments. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Subprojects Sector Related Issues: Private sector | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/industrial-credit-and-investment-corporation-india-limited-0
Second North Madras Thermal Power Project | India |  | 2002-12-13 | A single turnkey contract would have avoided to some extent the delays experienced inthe implementation of the project resulting from inordinate delays in the award of severalcontracts and coordination between various contractors. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Procurement Methodologies/Approaches: Consultation/Participation An integrated project management system equipped with computerized managementinformation systems to regularly review the project's progress is essential in organizations like theRegular discussions with the central and state governments and with TNEB onimplementing assurances such as subventions and power tariffs has prompted the governmentof Tamil Nadu to establish the Tamil Nadu Electricity Regulatory Commission, with a mandate todetermine power tariffs for different categories of consumers, including agriculture.(TNEB). Such systems may help to take timely corrective actions to resolve problems as theyarise, fix the responsibilities, and enhance the accountability of the staff involved. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Project Management: Management information system Project Management: Project management Sector Related Issues: Energy planning/management Regular discussions with the central and state governments and with the Tamil Nadu Electricity Board (TNEB) on implementing assurances such as subventions and power tariffs has prompted the governmentof Tamil Nadu to establish the Tamil Nadu Electricity Regulatory Commission, with a mandate todetermine power tariffs for different categories of consumers, including agriculture. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Loan Agreement: Loan Agreement Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Policy & Reform: Policy matrix The preparation of a project, including the ready availability of requisite land, is the key to successful implementation and derivation of benefits. Central and state government organizations should consider the availability of and problemsassociated with acquiring land for infrastructure projects at the time of project appraisal. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Appraisal Project Design: Project design Country Context: Decentralization The Project Completion Mission feels that, to curtail procurement delays, ADB might consider deputing a procurement specialist with sector-specific experience as a part of the inception mission, or it might advise the executing agency to hire an experienced consultant toprepare and evaluate bid documents. Doing so may substantially improve the quality of biddocuments and reduce the time needed to review and finalize bid documents and evaluationreports. Further, the inception mission should put more emphasis on familiarizing the executingagency staff with ADB procurement requirements and procedures. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Human resources management The successful completion of large-scale infrastructure projects requires critical evaluation of the executing agency's preparedness and commitment to start project implementation as envisaged. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Ownership | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-north-madras-thermal-power-project
Unchahar Thermal Power Project | India | Energy | 2002-09-13 | In addition to the merits of the project, ADB must also evaluate other issues such as the executing agency's (EA's) capability and past performance to execute the project within schedule and budget. The successful completion of large-scale infrastructure projects requires evaluation of the EA's preparedness and commitment to start project implementation as envisaged. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Ownership To curtail procurement delays, ADB may consider deputing a procurement specialist with sector-specific experience as a part of the inception mission or advise the executing agency (EA) to hire an experienced consultant to prepare and evaluate bid documents. Doing so may substantially improve the quality of bid documents and reduce thetime needed to review and finalize bid documents and evaluation reports. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/unchahar-thermal-power-project
North Madras Thermal Power Project (Loan 798-IND) | India | Energy | 2002-06-30 | A single turnkey contract would have avoided the considerable delays experienced in the implementation of the project resulting from inordinate delays in the award of several contracts and coordination between them. In future projects, it is essential to discuss and agree with the Borrower and the executing agencies, prior to ADB Board approval, the systems, procedures, and timeframes for bidding and contracting processes for such turnkey contracts. Such an approach would have an additional advantage of allowing for intense scrutiny by all the concerned parties and ensuring strict compliance with ADB's Guidelines for Procurement, particularly in view of the large value of the contract. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Procurement Severe project delays caused by difficulties in land acquisition could have been overcome by contracting out land acquisition and making it a precondition for ADB approval of the loan or for loan effectiveness. Experience in Indonesia and the Philippines demonstrates that the private sector is also effective in acquiring land expeditiously. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Appraisal Sector Related Issues: Private sector | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/north-madras-thermal-power-project-loan-798-ind
Industrial Energy Efficiency Project | India | Energy | 2002-04-15 | Delegation of the Industrial Energy Efficiency Project (IEEP) to the India Resident Mission (INRM) contributed to its success, which achieved its development objectives within the envisaged time frame. Experience with the IEEP indicatesthat sufficient efforts are needed before loan effectiveness to explain ADB's procedures on procurement, environmental aspects, disbursements, etc. to the Project Monitoring Unit (PMU) officials well in advance and to obtain agreement on administrative arrangements. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Finance & Financial Aspects: Disbursement Project Design: Appraisal Project Management: Procurement Project Management: Project administration Project Management: Project management Country Context: Decentralization Other: Resident Mission Sector Related Issues: Energy planning/management Judging from project implementation, industry has considerable awareness of thebenefits of introducing energy efficiency measures. The scope for investments in this field is substantial, particularly in small and medium sectors of industry, which the Industrial Energy Efficiency Project (IEEP) did not cater to. This was partly due to the final cost of funds to the subborrowers, which were not concessional.Another factor is that the executing agency (Industrial Development Bank of India) is mainly engaged in assistance to large-scale industrial units, as itssmall-scale operations were transferred to Small Industries Development Bank of India (SIDBI). project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Sector Related Issues: Industry and Trade The Industrial Development Bank of India (IDBI), with its historical experience in development banking and years of expertise in project finance was an effective agency for channeling funds under the project. However the recent financial sector reforms and globalization of Indian industry have closed IDBI's access to low-cost funds, made its income taxable, and compelled it to reorganize its priorities. Hence a subsequent project might need an incentive structure to enable sustained long-term commitment of IDBI in partnerships focusing on energy efficiency and environmentalmanagement objectives of ADB. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Ownership Capacity Development: Partnerships Sector Related Issues: Energy planning/management Sector Related Issues: Industry and Trade Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/industrial-energy-efficiency-project
Road Improvement Project (Loan 918-IND) | India | Transport | 2002-03-31 | A major technical issue that was adjusted during implementation and adopted for other projects entailed reducing the quantity of tack coat application. This resulted in cost savings in construction and maintenance, and helped avoid excessive bleeding of bitumen, leading to longer road life. project cycle stage: Implementation Lesson Topics: Project Management: Operation and maintenance Sector Related Issues: Roading Contract award should be done only after land acquisition, removal of obstructions, and necessary clearances from various government department and ministries to ensure good start-up. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Appraisal Project Management: Procurement The project underscores the effective use of construction supervision consultants as the engineer according to internationally agreed standards and not as advisors. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Project supervision There is need for more detailed and systematic project preparation and checking by supervision consultants before commencement of works. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Consultants | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/road-improvement-project-loan-918-ind
Second Ports Project (Loan 1016-IND) | India | Transport | 2001-12-31 | No project preparatory TA was provided. The project formulation and design relied on the executing agencies own feasibility studies. While India s technical knowhow in the design and implementation of port projects is undoubtedly among the strongest of ADB s developing member countries, foreign expertise would have been beneficial for a sector that was, and still is, experiencing fast technological changes. At the very least, ADB should have better ensured the quality of project design by hiring an independent international consultant to review all project designs; this might have helped avoid the long delays for Kakinada Port. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Sector Related Issues: Transport planning The project consisted of a mix of unrelated subprojects and did not have a homogenous scope or a coherent theme. The project was put together at a time when ADB was just about to complete a detailed port sector study. The study correctly forecast that traffic generally was rising very fast and identified the need for new capacity in detail at all major and minor ports. There was also a general acceptance of the need for radical reform in the ports sector at that time. Efficiency in India's ports, measured in total throughput handled per employee, was well below international standards for reasons that were familiar elsewhere in the world: the ports were overstaffed, controlled by State monopolies, and in need of competition and private operators. This knowledge should have provided a useful guide for devising a comprehensive project based on, first, the facilities that would need to be built during the 1990s and, second, reforms to significantly increase productivity of the existing facilities.The nature of the required reforms was very clear from experience in other countries. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Project Design: Subprojects Sector Related Issues: Transport planning Policy & Reform: Reform The traffic forecasts at appraisal proved overly optimistic. Large increases in petroleum traffic were predicted, while in practice such traffic has fallen; and the Kakinada forecasts were also too high, mainly because the assumed development of natural gas-based industries never materialized. Economic forecasting is admittedly very difficult, and it is hard to pinpoint specific lessons. One central point, however, is that Indian project plans are often unreliable. Typically, several locations compete for one potential investment. Many projects are cancelled; most of those that eventually go ahead are delayed by bureaucracy; and in the end they go to only one of the competing locations. The tendency of overoptimism in traffic forecasting should be factored in when formulating future projects. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Data collection Project Design: Project design Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-ports-project-loan-1016-ind
Gas Rehabilitation and Expansion Project | India | Energy | 2001-12-14 | ADB observed that the training components were delayed and were not utilized to theextent provided for under the loan. This was due to lack of proper assessment andplanning during appraisal. In future projects, ADB needs to undertake a realistic assessmentof the training needs of the executing agency. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Despite the delay in ordering the compressors (from July 1993 to April 1995), the projectwas completed with only four months delay, and the ADB-financed components of the projectwere completed on time. This shows that there is still some scope for reducing the timeschedule by effective appraisal. It is suggested that during appraisal, detailed discussionsshould be held with the executing agency and resident mission staff to finalize a far more realistic implementation schedule. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Other: Resident Mission Sector Related Issues: Energy planning/management The executing agency (Gas Authority of India Limited or GAIL) has not used the provisions for physical and price contingencies which accounted for almost 15 percent of the total project cost. This indicates that the estimates forthe various components of the project were adequate and that the project implementation practices of GAIL are good. A more realistic assessment of project costs should be made at appraisal. As a share of the net ADB loan, the surrendered amount is almost 40 percent. There is therefore an element of overestimation at the appraisal stage and this needs to be looked into for future projects. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Management: Executing/Implementing agencies | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/gas-rehabilitation-and-expansion-project
Hydrocarbon Sector Program Loan (Loan 1148-IND) | India | Energy | 2001-01-31 | ADB sent mixed signals to the government when it allowed OECF to release the second tranche while canceling its own second tranche. In the implementation of program loans, ADB should adopt a flexible approach. Flexibility and willingness to adapt will be a crucial factor for the success of ADB s future operations. project cycle stage: Implementation Lesson Topics: Modality: Program Project Management: Project administration Methodologies/Approaches: Process approach Success of program loans depends on the formulation of realistic policy and institutional reforms. For the program, the target of 20 percent divestment of the government's equity in the leading oil company was unrealistic. No analysis was conducted regarding what regulatory and market preconditions for such a large and complex divestment should take place without jeopardizing shareholder value. The RRP s analysis on program risks did not even mention that potentially poor market response could adversely affect compliance. In addition, the target for additional domestic crude oil production was unrealistic as it ignored the fact that the investments alone were no guarantee of finding and producing oil. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Modality: Program Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity development Sector Related Issues: Energy planning/management Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/hydrocarbon-sector-program-loan-loan-1148-ind
Telecommuncations and Second Telecommunications Projects (Loan 886/954-IND) | India | Information and Communication Technology | 2000-08-31 | Project administration also needs to closely monitor tender evaluation and procurement procedures to ensure that they conform to ADB guidelines. It is not acceptable for an executing agency to fragment bids to identify components that could be contracted by other suppliers. This practice is contrary to ADB guidelines and causes delays in implementation. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Project administration needs to closely monitor the policy environment in which a project is being implemented, in addition to its usual activities regarding procurement and other implementation activities. Any major changes should be assessed in light of the project s rationale and objectives, and the economic and financial feasibility of the project should be reassessed to ensure continued relevance. If the rationale is no longer relevant or the project is no longer viable, steps should be taken to terminate the project. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Procurement Project Management: Project administration Policy & Reform: Policy reforms/framework The evaluation demonstrates the need for a sound project rationale. It should be based on a well-defined and focused country operational strategy, supported by project performance audit report (PPAR). A PPTA should be mandatory if there is little or no experience in the sector. Project preparation should include an assessment of the sector s policy environment and the scope for private sector involvement in the sector. Support for interventionist government policies is not appropriate. Project preparation should also assess the institutional capabilities of the executing agency and ensure that sufficient consulting services are provided during project implementation. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Post-evaluation Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) |  | http://www.adb.org/documents/telecommuncations-and-second-telecommunications-projects-loan-886954-ind
Financial Sector Program Loan (Loan No. 1208-IND) | India | Finance | 1999-12-31 | Identification of effective performance indicators at formulation will make ADB s monitoring activities more solid and efficient. In setting measurable targets with appropriate indicators, the growth potential of a concerned sector and the structural rigidities hindering full use of this potential need to be fully discussed with the government. This would enhance government confidence in dealing with the reform measures and thus would be a key aspect of the program loans by which ADB could maximize value added in policy formulation by the government. project cycle stage: Feasibility Lesson Topics: Modality: Program Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Policy & Reform: Reform Methodologies/Approaches: Targeting In support of bank recapitalization, the World Bank's technical inputs and ADB's somewhat flexible arrangement in the use of counterpart fund are different but complementary approaches. In general, ADB should carefully assess government capacity, especially when assisting in the recapitalization of banks, and should expect to offer technical inputs depending on the needs. In this regard, ADB could analyze the results of bank recapitalization in developing member countries, and consolidate the findings as the basis for future technical inputs. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Institutional analysis Policy & Reform: Policy reforms/framework India has steadily liberalized the financial sector without experiencing any major banking crisis. Such an outcome could be attributed to the government s solid authorship, prioritization, and timing and sequencing of financial reforms. In principle, several important steps were taken: (i) strengthening of the legal, regulatory, and supervisory framework; (ii) rehabilitation of institutions with the recapitalization and financial restructuring of major banks; and (iii) liberalization and commercialization of the sector. Swift macroeconomic stabilization and a conservative approach to capital account liberalization on the external front could be the other factors that contributed to the successful undertaking of the financial sector reform program. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Country Context: Prioritization Policy & Reform: Policy reforms/framework Policy & Reform: Reform The allocation of surplus resources obtained by the reduction in intermediation costs depends on market conditions and the policy environment. The long-term goal should be increased benefits for borrowers and depositors, which could be ultimately measured by the interest rate spreads. To achieve such a long-term goal, the remaining impediments limiting the transfer of benefits to depositors and borrowers need to be removed. ADB should have a clear perspective on these aspects when addressing the issues in intermediation costs. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Policy & Reform: Policy reforms/framework The policy matrix should avoid setting unspecified targets. Clarity in program measures is needed in such cases including: (i) gradual reduction of interest rate on cash reserve ratio; (ii) reduce substantially interest rate subsidy on priority credits; (iii) gradually phase out export refinancing; (iv) ceiling on bank deposit interestrates progressively phased out; and (v) progressively reduce, with a view to eliminating, cross holding of equity. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Indicators Project Design: Project design Policy & Reform: Policy matrix Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/financial-sector-program-loan-loan-no-1208-ind
Rayalaseema Thermal Power Project | India | Energy | 1999-05-31 | For advisory TAs with cross-cutting concerns (such as the environment), ADB should improve coordination with the executing agency and relevant recipient agencies, and undertake follow-up review to ensure effective implementation of the recommendation. project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Technical Assistance Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation The economic and financial reevaluation based on resource cost savings for nonincremental benefits demonstrated that poor consumers were actually paying more in the without project scenario than in the with project scenario. Furthermore, the sensitivity analysis revealed that the net benefits to the poor can be increased by improving the quality of coal and reducing system losses. Consequently, the tariffs can be raised without reducing the net benefits to the poor. These can be useful in the policy dialogue in future projects. project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Policy & Reform: Policy matrix The use of indigenous coal in power generation adds to the fuel cost and causes environmental degradation because it is transported over a long distance and has a high ash content; it also requires an appropriate ash handling system. While there is a strong need to continue taking effective and consistent steps to control environmental pollution, the possible financial/economic cost implications and environmental impact as reflected in the project s operation reconfirm ADB s policy of moving away from coal-fired power generation. project cycle stage: Concept Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial analysis Project Design: Project design Sector Related Issues: Energy planning/management With the power sector reform in India, the State Electricity Boards will be able to implement financial restructuring measures aimed at allowing them to perform more on a commercial basis and ensure viability of the project investments. However, this has to be a gradual process of restructuring and subsequent privatization rather than through an attempt of quick tariff reform through project covenants. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Loan Agreement: Covenants Sector Related Issues: Energy planning/management Policy & Reform: Privatization Policy & Reform: Reform | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/rayalaseema-thermal-power-project
Advisory and Operational TAs in the Power Sector in India | India | Energy | 1998-12-31 | ADB's current strategy in the power sector in India to focus on a few states has contributed substantially to accelerating the reform process. The formulation and content of TAs (especially the cluster approach and the intensive training modules) demonstrated the impact of ADB's assistance in accelerating the reform process. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Capacity Development: Capacity building Policy & Reform: Reform Appropriate ADB supervision is vital for achieving intended TA benefits. On the other hand, there is also a need for periodic monitoring of the TAs - required not only during implementation but also after completion. Follow up on the implementation of the TAs' recommendations subsequent to their completion will also ensure institutional memory when the staff associated with the conduct of the TA studies are transferred or promoted. project cycle stage: Implementation, Operation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Management: Project supervision | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/advisory-and-operational-tas-power-sector-india
Ports Development Project (Loan 842-IND) | India | Transport | 1996-06-30 | During supervision of a project, ADB should be aware of the potential impacts on viability and sustainability of a reduction in trade volumes when the actual estimates become available for comparison with forecast estimates. The executing agencies should be prepared for such problems as a reduction in traffic volumes and action plans should be developed, based on more vigorous port marketing to port users and shippers to respond to lower-than-anticipated growth in trade. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Sector Related Issues: Industry and Trade One of the major reasons for the lower reestimated EIRRs for each port covered by the project is that container traffic has grown at a lower rate than was anticipated at appraisal. The forecasts were not developed on a commodity by commodity basis to reflect industry and agricultural demand. Trade projections developed for container ports need to reflect more accurately the changing international shipping patterns and the nature of interport competition, based on planned shipping developments developed by the liner operators. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Design: Project design Sector Related Issues: Industry and Trade Sector Related Issues: Transport planning The modernization of port facilities to handle more effectively containers was introduced without the full understanding and cooperation from dockside labor. In ports where containerization is to be introduced for the first time, or where it is likely that significant numbers of unskilled laborers will no longer be required after containerization, labor disputes should be anticipated. Despite the covenants in a subsequent loan to reduce labor levels, dockside labor remains militant and the container freight station (CFS) and Inland Container Depot (ICD) facilities are not fully utilized. The prior support of union and nonunion labor, particularly where labor requirements will be reduced, should be sought before undertaking future investments in containerization in ports. project cycle stage: Feasibility, Appraisal Lesson Topics: Loan Agreement: Covenants Crosscutting Issues/Themes: Employment Sector Related Issues: Transport planning Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/ports-development-project-loan-842-ind
Environment Capacity Development Projects in Selected South Asian Countries | India, Sri Lanka | Agriculture, Natural Resources, and Rural Development | 2010-12-31 | 1. Developing environmental management capacities of national and provincial agencies requires long-term sustained support. Environment agencies need to stay abreast of the latest advances in global environmental technology, which is not easy in a developing member country given the competing demand on limited resources and the externality nature of environmental management. Where an external donor agency is the primary source of such assistance, a programmatic approach - a long-term process that assists ongoing Capacity Development, with each intervention forming part of a longer-term agenda to build environmental management capacity at national or provincial level - has a better chance of success than an isolated technical assistance (TA). Lack of such sustained assistance affected the long-term outcomes of the Sri Lanka environmental impact assessment TA. [Executive summary; Main text, para. 55-58,95] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Technical Assistance Capacity Development: Capacity development Methodologies/Approaches: Program Approach 2. Sector-specific environment capacity development stands a better chance of success if associated with a project or a program. An environment-strengthening technical assistance (TA) that is associated with infrastructure lending can be more effective in reforming environmental practices if loan tranches are linked to progress on the TA project's milestones. The Environment and Social Division TA in Sri Lanka benefited from this approach. Evaluation noted that the success of the Sri Lanka's National Highways Project was inextricably linked to the successful execution of associated TA on safeguard capacity building at Road Development Authority. [Executive summary, Main text, paras. 19,96] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Lending modality Modality: Technical Assistance Capacity Development: Capacity development Methodologies/Approaches: Sectoral approach 3. Municipal clean development mechanism (CDM) projects have long-term development benefits. Although complex in nature owing to scale and multitude of stakeholder involvement, municipal CDM projects in populous countries and regions (as in the case of the CDM technical assistance in India) may well offer an unusually attractive combination of environmental and social benefits. Because of this, continued TA will be relevant if good ownership is evident. [Main text, para. 97] project cycle stage: Concept Design Lesson Topics: Crosscutting Issues/Themes: Environmental benefits Modality: Technical Assistance Capacity Development: Ownership 4. Access to primary data is essential for robust environmental scrutiny. Lack of an agreed data-sharing protocol among scientific and consulting community and government establishments is emerging as a major source of inefficiency in administering environmental safeguards, because it leads to needless duplication and delays. It increases the cost of the process, reduces its credibility, and imposes an unnecessary burden on the regulated community. Credibility of an initial environmental examination (IEE) or environmental impact assessment (EIA) is directly related to the quality of data used in its preparation. In a number of cases, the data used to justify IEE or EIA conclusions are not attached to the reports themselves and remain unavailable to third parties. While limited access to certain types of natural resource data may be justified on the grounds of national security or strategic considerations, large-scale de facto privatization or withholding of EIA-related data is not in the public interest. The EIA process in Sri Lanka suffers from this problem. [Main text, para. 98] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Monitoring & Evaluation: Data collection and management 5. Decentralization of environmental assessment and management functions needs to be accompanied by strong local capacity. In both India and Sri Lanka, decentralization of environmental assessment was not supported with adequate institutional capacity at provincial levels and led to inefficiencies. The environmental clearance process (2006) in India enshrines decentralization of decision making at the state level. However, due to varying levels of economic development in states, it often meets limited capacity and skills in scoping and reviewing environmental impact assessments (EIAs) at the state environment departments, state pollution control boards (SPCBs), and the appraisal committees. In Sri Lanka, absence of enabling statutes and capacity constraints limits devolution of EIA decision making to the provinces. [Main text, para. 99; Appendix 3&5] project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Capacity Development: Capacity development 6. Ensuring the effectiveness of technical assistance (TA) requires support that focuses on relatively few areas than spread over multiple sectors and states. Unduly broad terms of reference (TOR) tend to weaken TA focus. A TA with a very large scope tends to hide an uncertain grasp of key issues and rarely serves anyone's interest and ends up becoming irrelevant. The result is excessive cost and duration of the project and a rising gap between the volume of consultant outputs and the readiness of the client to use them; this is even more critical when the absorptive capacity of the executing agency is weak. As an example, the environmental management cluster TA in India, which registered an unsuccessful performance, had with five components, four implementing agencies, and 157 person-months of consulting inputs took more than 7 years to complete. [Main text, para. 78,100; Appendix 3] project cycle stage: Design Lesson Topics: Modality: Technical Assistance Methodologies/Approaches: Targeting 7. Effective cluster technical assistance (TA) management requires centralized coordination from ADB. Shared responsibility for cluster TA management is ineffective. The environmental management cluster TA in India has clearly demonstrated the importance of one ADB officer managing the overall cluster instead of different officers being responsible for different components (which contributed to administrative inefficiencies and lack of synergy among components). Involvement of different mission leaders in developing a cluster TA can well be justified, but extending that approach to implementation is not. [Main text, paras. 42, 48, 62, 101] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Cluster operations Modality: Technical Assistance 8. Frequent dialogue with technical assistance (TA) counterparts can improve project performance. Institutional reform is a slow and demanding process, one that requires close partnership between ADB and the executing agency, built on trust. Periodic supervision missions from ADB headquarters stand less of a chance to generate that trust. Resident missions, on the other hand, are close to the scene of action and can better appreciate the context and dig deeper into possible sources of implementation difficulties. Limited field presence in the early days of the environmental management TA for continued and intensive discussions, not only with India's State Pollution Control Board but also its Ministry of Environment and Forestry, was among the factors that hampered project performance. This lesson supports a similar finding in India's country assistance program evaluation of 2007 - that greater delegation to the resident mission will boost client responsiveness. [Main text, para. 42,102] project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Project supervision Capacity Development: Partnerships Policy & Reform: Reform Methodologies/Approaches: Policy dialogue 9. Absence of a mandate reduces the executing agency's efficacy in knowledge transfer through the technical assistance (TA). Executing agencies are responsible for adopting and disseminating the TA product and require a clear mandate, complementary institutional preconditions, and skills to do so. In the absence of these, the transfer of know-how, expected of TA projects, will not occur or be seriously diminished, as was demonstrated in the cleaner production financing component of the environmental management TA in India. [Main text, para. 103; Appendix 3, para. 69] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Technical Assistance Capacity Development: Technology/Technology transfer | Technical Assistance Performance Evaluation (TPER) | Unsuccessful | http://www.adb.org/documents/environment-capacity-development-projects-selected-south-asian-countries
Vocational Education Strengthening Project: Completion Report | Indonesia | Education | 2015-09-30 | Given the range of physical, nonphysical, and capacity building activities throughout the project duration, the formulation of appropriate indicators measuring the project's outcomes should have been more realistic in line with the sequencing of project implementation activities. Much of the quality impacts, such as improved exam scores and employment rates, were beginning to take effect only toward the end of project implementation, following the completion of upgrading physical facilities, improvement of teachers' qualifications, and adoption of new teaching methods. project cycle stage: Concept, Design, Implementation, Completion Given the complexity of the project activities that were implemented across 90 model and 230 alliance schools throughout the nation, the project design could have considered more efficient implementation arrangements in procuring equipment for all the schools. The initial arrangement of central procurement through NCB (national competitive bidding) method turned out to be very time-consuming and less effective. More thorough due diligence for procurement arrangements would have facilitate smoother implementation of project activities at lower costs. project cycle stage: Design, Implementation Since major project activities were managed by the schools themselves, a specific approach should have been designed to provide remedial support to relatively poor performing schools such as additional capacity development programs, especially in planning and management practices, monitoring and evaluation. project cycle stage: Design, Implementation The delayed start of establishing EMIS (Education Management Information System) across model vocational schools prevented the adequate gathering of data throughout the project duration. Although an M&amp;E specialist was also recruited to independently monitor and evaluate project activities, the project performance management system and specific measures for key output and outcome indicators were not all adequately developed. This makes it difficult to fully assess the progress of some indicators or the quality of outputs achieved. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/ino-vocational-education-strengthening-pcr
Supporting Water Operators' Partnerships: Technical Assistance Completion Report | Indonesia | Water and other urban infrastructure and services | 2015-07-01 | (i) Twinning partnership enable the recipient to adopt the knowledge and experience from the mentor to improve their performance in NRW (nonrevenue water) management, energy efficiency, wastewater and septage management. (ii) Twinning partnerships provide an effective and valuable tool to develop the operational and financial performance of water operators and to enable them to better plan for their sustainable development. (iii) More support is required to develop the capacity of wastewater utilities and assist them towards financial sustainability, but such support needs to be specifically targeted and monitored closely. (iv) CIB (continuous improvement and benchmarking) initiatives need to be more carefully planned and applied based on the capacity of the water operator. (v) Training is in high demand by wastewater/water operators, particularly in planning, operations, and maintenance where inadequacies result in the greatest inefficiencies. (vi) Expert operators can provide access to knowledge and experience that is not available from consultants. (vii) Post-twinning initiatives and access to financing for scaling-up and replication of successful activities are needed. Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/ino-supporting-water-operators-partnerships-tcr
Sustainable Aquaculture Development for Food Security and Poverty Reduction Project: Completion Report | Indonesia | Agriculture, Natural Resources, and Rural Development | 2015-06-30 | The delay in project start-up could have been avoided if the government had issued Government Regulation No. 7 of 4 February 2008 immediately after project effectiveness. project cycle stage: Implementation The project adopted excellent design features of poverty targeting, community participation, capacity building for both the project implementers and the project beneficiaries, and microenterprise business development in aquaculture production and processing. project cycle stage: Design The project developed strong institutional capacity and good coordination and teamwork among national and district agencies, encouraged dedication among the NGOs (nongovernment organizations) and CEWs (community-based extension workers), and supported the active participation of project beneficiary groups. project cycle stage: Implementation Gender mainstreaming through group formation and capacity building training programs in aquaculture production and food processing is an effective strategy in empowering women. project cycle stage: Implementation Forming and strengthening cooperatives is a good strategy in sustaining project benefits after project completion. project cycle stage: Completion, Operation Use of voluntary extension workers recruited from local communities by district agencies will help ensure continuity of extension services to local project beneficiaries. project cycle stage: Operation A functional management information system should have been developed in DGA (Directorate General of Aquaculture). project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/sustainable-aquaculture-development-food-security-and-poverty-reduction-pcr
Capital Market Development Program Cluster: Completion Report | Indonesia | Finance | 2015-06-29 | Long-term perspective. The adoption of the medium-term blueprint for a capital market master plan meant that the government had a set of long-term objectives to guide and shape medium-term policy design and implementation. The close consultations involving the government, ADB, and other development partners strengthened the government's ownership and increased the potential for funding agency buy-in. project cycle stage: Design, Implementation Flexibility in design. Capital market development is complex and involves major changes to the legal and regulatory framework, institutional arrangements, financial infrastructure, and human capacity. Hence, sufficient time must be allocated to program implementation. Design flexibility is also a key consideration. The use of the program cluster approach gave CMDPC (Capital Market Development Program Cluster) implementers the opportunity to refine the policy actions proposed for succeeding subprograms to reflect the government's achievements, changes in the policy and economic environment, and lessons from previous subprograms. project cycle stage: Concept, Implementation Technical assistance resources. Under the CMDPC (Capital Market Development Program Cluster), the government adopted legal, policy, and institutional measures and established supporting infrastructure. Many of the concepts were relatively new and therefore required extensive consultation and coordination to ascertain stakeholders' understanding, acceptance, and adoption of the new measures. Substantial TA support was necessary to ensure that best practices were incorporated and then consolidated throughout implementation to achieve the intended results. The CMDPC identified a program of TA projects at the outset to help implement the medium-term program and improve the likelihood of compliance with completed activities. The selection of individual consultants was based not only on merit but also on their perceived ability to work well with local counterpart staff and their sensitivity to the local culture. These criteria are considered essential for the successful transfer of knowledge. project cycle stage: Concept, Implementation Emerging risks. The transition from a centrally controlled economy to a market-led economy creates new forms of risks. The presence of international banks, the offer of more sophisticated services to depositors (credit and debit cards for automatic teller machines and electronic funds transfer systems), and the increase in lending demonstrate increasing investor confidence in Indonesia's capital market system. With these encouraging developments, however, come new risks and challenges - such as the impact of global financial crises on Indonesia's fiscal sustainability, i.e., close to 30% of Indonesia's bond holders are foreigners. project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/capital-market-development-program-cluster-pcr
Water Supply and Sanitation Sector Development: Technical Assistance Completion Report | Indonesia | Water and other urban infrastructure and services | 2015-06-01 | The main reason for weak performance in achieving MDG (Millennium Development Goal) targets on water supply and sanitation is the low level of expenditure by sub-national governments through their own budgets. The evident under-investment at sub-national level is at least partially a result of lack of effective priority setting in sub-national plan and budget preparation as well as a lack of effective coordination between national and sub-national governments to achieve a national development priority and commitment. Resources should be used more efficiently. Examples of inefficiencies include: (i) in the water sector, high water production capacity does not directly ensure a high proportion of house connections; (ii) a high percentage of water is wasted through leakage; (iii) water companies that are not in a 'full cost recovery' position are still required by Law to contribute to the local government's income. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/water-supply-and-sanitation-sector-development-tcr
Power Transmission Improvement Sector Project: Completion Report | Indonesia | Energy | 2015-05-22 | One of the major lessons from implementing the project is the importance of obtaining land and forestry permits, acquiring land, and obtaining ROWs (right of ways) for transmission lines at the right time. ADB and PLN (Perusahaan Listrik Negara, or State Electricity Company) have different strategies on the timing of obtaining ROW: PLN's practice is to obtain ROW after transmission towers are erected, while ADB's policy is to obtain ROW before the erection of transmission towers. A clear, standardized, and agreed-on compensation structure between ADB and PLN should have been defined at the beginning of the project. project cycle stage: Design, Implementation ROW (right of way) was one of the major hurdles for the transmission line subprojects. Some ROWs were fragmentarily obtained for some sections (e.g., different segments for some sections), and conductor stringing was delayed because contractors preferred to string the sections continuously and at one go. project cycle stage: Implementation Clear and timely communication among project stakeholders would have strengthened project implementation, and differences in policy and practice could have been mitigated. Better communication between PLN (Perusahaan Listrik Negara, or State Electricity Company) and ADB would have also avoided implementation delays because both parties would have been more responsive to the needs of and required adjustments for the project. project cycle stage: Implementation Building institutional and knowledge management capacity within PLN (Perusahaan Listrik Negara, or State Electricity Company) would have ensured a smooth turnover of the project during personnel changes and reorganization. Capacity assessment and capacity-building activities throughout the project's life would have been effective in addressing institutional and project management gaps. project cycle stage: Implementation, Completion | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/power-transmission-improvement-sector-project-pcr
Nutrition Improvement through Community Empowerment Project: Completion Report | Indonesia | Health | 2015-05-08 | A project that requires behavioral change within communities needs a long-term agenda. Measuring the impact of such a project will take time. A project may be deemed successful on the basis of short-term outcomes, but it may not endure, particularly if there were deficiencies during project implementation. Thus, setting impact performance indicators to be achieved by 2012 (the year of project closing) might have been too short-term. Perhaps a period of at least 3 years after project closing would have been more appropriate. project cycle stage: Implementation, Completion, Operation Highly qualified consultants and community facilitators are critical for capacity development and community empowerment projects. Since a community-driven nutrition project should focus on capacity development and community participation and empowerment, hiring highly qualified and committed consultants and community facilitators becomes critical. Moreover, the quality of training for community facilitators, provision of adequate guidance, and a good M&E (monitoring and evaluation) system to measure the performance of community facilitators, consultants, and local government agencies alike also play a significant part in ensuring quality community facilitation and empowerment. project cycle stage: Implementation The absence of a gender action plan and limited gender-related targets in the loan agreement have hampered the effectiveness of the project in ensuring that all activities are maximized for women's benefit. For instance, the project included the development of nutrition policy, programs, and surveillance. However, the lack of gender-related targets in this regard makes it unclear whether these policies included gender-related elements, such as to ensure that different living and working conditions faced by women in various environments would not impinge on their nutritional needs. Such elements should have been accommodated in the policies and specified in gender-related targets. The project also failed to highlight men's role as equal partners in family and community nutrition. Men may influence to some degree household budgets and food-buying patterns, so they need to be made aware of the nutritional needs of mothers and children and be involved as active partners in meeting these needs. Some studies also indicated that the husbands' support for breast-feeding might increase the success of promoting exclusive breast-feeding. The project failed to include these aspects in its design and targets. This may have contributed to the underachievement of the target to increase the number of children exclusively breast-fed (the outcome indicator). project cycle stage: Design, Implementation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/nutrition-improvement-through-community-empowerment-project-pcr
Geothermal Power Development Project: Technical Assistance Completion Report | Indonesia | Energy | 2015-05-01 | During 2010-2014, lack of access to concessional financing was just one of many roadblocks to developing geothermal power in Indonesia. During this period, only 135 MW were added nationally and no PPAs (power purchase agreements) were signed under the feed-in tariff released in 2012. Given the sector's overall slow-down during this period, only institutions with a sound understanding of ADB procedures ? and, if they are first-time borrowers, those who have received significant prior capacity building ? should be considered for a PPTA (project preparatory technical assistance). Project cycle stage: Design, Implementation | Technical Assistance Completion Report |  | http://wcm.adb.org/projects/documents/ino-geothermal-power-development-project-tcr
Preparation of the Forest Investment Strategy: Technical Assistance Completion Report | Indonesia | Agriculture, natural resources and rural development | 2015-04-01 | Despite the explicit indication of the risk of not reaching consensus between all stakeholder groups, the consultant team failed to effectively mitigate this risk, leading to delay in the submission of the Plan to the FIP (Forest Investment Program). Noting the monthly reporting schedule of the team leader to the Ministry of Forestry, ADB, WB (World Bank), and IFC (International Finance Corporation), a risk mitigation plan of the consultant team could have been included for discussion and endorsement by the Ministry of Forestry, ADB, WB, and IFC. The technical assistance (TA) description mentions as one of three objectives to strengthen capacity of stakeholders at different levels for preparation and implementation of the Plan. Although this objective was not reflected in the TOR (terms of reference) of the S-CDTA (small-scale capacity development TA), the workshops and field visits served as implicit capacity building activities of which records were kept and shared with the Ministry of Forestry, ADB, WB, and IFC. The lack of output related to capacity building does imply, however, that there is no specific reporting of capacity building objectives or achievements. Drafting a national plan to attract significant investment in a sector that is both highly dynamic and highly contentious is no mean task and the delays in the execution of activities, drafting of the Plan and submission to the FIP were unavoidable. The final result is positive, with the Plan receiving $70 million in funding, and the experience of intensive stakeholder engagement in all steps of the process is an important lesson for all involved that can only be beneficial during the implementation phase of the Plan. Project cycle stage: Design, Implementation, Operation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/preparation-forest-investment-strategy-tcr
Participatory Irrigation Sector Project: Validation of Completion Report | Indonesia | Agriculture, Natural Resources, and Rural Development | 2015-02-10 | The PCR (project completion report) identified a number of lessons derived from the implementation of the project. While all of these are appropriate, this validation highlights mainly two of these as they have wide applicability across developing countries and within ADB. The first lesson deals with the reinforced conviction that WUA (water users association) and/or WUAF (water users associations' federation)-guided participatory irrigation management can be successfully implemented at the district level and in the lower levels in developing countries. The participation of farmers in these schemes improved project implementation as compared to the situation when there was exclusive reliance on administrators and contractors. The second lesson relates to the need to avoid overwrought arrangement for project disbursements. In this project, prorated financing arrangements from three different fund sources across each category of expenditure constrained the flow of funds. The size of imprest accounts should also be large enough to provide adequate cash flow for the executing agencies to operate while disbursement applications are being processed. This is particularly applicable for sector projects. project cycle stage: Design, Implementation | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/indonesia-participatory-irrigation-sector-project
Madrasah Education Development Project: Validation of Completion Report | Indonesia | Education (EDU) | 2015-01-16 |  | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/indonesia-madrasah-education-development-project
Renewable Energy Development: Project Completion Report | Indonesia | Energy | 2014-09-01 | At project implementation, Perusahaan Listrik Negara (PLN) (State Electricity Company) should have assessed whether the engineering, procurement, construction modality was effective and appropriate for renewable energy projects. Experience from the project indicates that it may be more effective and efficient to procure engineering services and civil and electromechanical works separately. ADB and the government should have evaluated the cost efficiency of renewable energy-based power generation in remote regions. Based on the total cost of each of the subprojects which included design, engineering, construction, project management, and social safeguards compliance), the average cost of 1 MW of power generation in 2013 is $2.7 million, considerably higher than diesel-based generation at $1 million per MW. However, the cost of $2.7 million per MW does not factor in the feed-in tariff for renewable energy and the longer life span of renewable energy plants compared with diesel generators. Additionally, the health and environmental benefits accrued from renewable energy use are much higher than those of diesel. On social safeguards, the project was hampered by difficulties in land acquisition, securing forestry permits, and soliciting project acceptance from affected people. The project lacked preparatory work on addressing social issues at the outset. There were gaps in communication between the following stakeholders: (i) ADB and PLN on how social safeguards were to be implemented, especially since the latter's existing corporate social responsibility guidelines may have been used in congruence with ADB's Safeguard Policy Statement (2009); (ii) the project and the affected people on the social, environmental, and health impacts of the power plants on their communities; (iii) the government, PLN, and local and provincial governments on project implementation and accountability, since the local/provincial governments were also given the authority to approve rural electrification projects; and (iv) PLN's head office and PLN's regional/local offices on complying with ADB's Safeguard Policy Statement (2009). On project management and implementation, PLN's financial and management capacity needed to be strengthened and/or supported by qualified consultants and training. The project's design should have therefore included capacity assessment and capacity-building components to improve PLN's internal and project-related financial and management systems. The feed-in tariff should apply to public and private power producers to boost renewable energy development and give it a bigger share of the energy mix in Indonesia. The project would have benefited from the feed-in tariff which provides better rate of return for the renewable energy power development. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/indonesia-renewable-energy-development-pcr
Rural Infrastructure Support to the PNPM Mandiri Project II: Project Completion Report | Indonesia | Agriculture, Natural Resources, and Rural Development, Education, Health, Public Sector Management, Transport | 2014-09-01 | The project yielded the following insights for similar, future community-driven development projects: (i) Inclusive involvement of community members in decision making and implementation of infrastructure projects is needed to ensure ownership and transparency. (ii) Community facilitators and consultants must be well selected so that only qualified and committed personnel are deployed to support communities in the empowerment process and on technical matters. (iii) Sufficient time should be allowed to ensure that all community members understand the community-driven development approach and will be involved in prioritizing their needs, taking investment decisions, and developing infrastructure proposals. (iv) Project managers (government officials) must understand the value of promoting genuine participation and public trust and be interested, motivated, and capable to do so. Project management training for officials may need to include these aspects. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/indonesia-rural-infrastructure-support-pnpm-mandiri-project-ii-pcr
Second Decentralized Health Services: Project Completion Report | Indonesia | Health | 2014-09-01 | Project scope and coverage should be feasible. To increase impact, project resources should not be spread over a large geographic area. A large number of intended outputs most likely will slow down project implementation. Investment priorities based on health needs and poverty incidence may contribute to increased effectiveness. Capacity development requires continuous investment. Human resource development is key to providing improved health services. A large number of health staff, including medical doctors and midwives, received scholarships to build capacity in obstetrics and neonatal care. However, local governments' fiscal capacity to finance capacity development was limited or nonexistent. Significant investments, both in terms of capacity building and health infrastructure, will be required to meet the maternal mortality MDG target by 2015. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/indonesia-second-decentralized-health-services-pcr
Participatory Irrigation Sector Project | Indonesia | Agriculture, natural resources and rural development | 2014-06-01 | Institutional coordination. The project developed good coordination across the three executing and implementing agencies both horizontally and vertically, which was essential to deliver project outcomes that relied on an integrated approach. Appropriateness of a participatory approach. The project has shown that the participatory approach in irrigation development and management is a feasible concept and that farmers are eager to be involved with irrigation operation and maintenance (O&M) and management. The involvement of water users association and water users association federation in the irrigation commission provided a good approach to address irrigation water distribution, cropping patterns, and O&M planning and implementation. Farmer involvement in rehabilitation. Water user association involvement in rehabilitation works yielded better quality and more efficient implementation than similar works implemented by contractors. The water users association and water users association federation were also willing to contribute their own resources to the work program. Participative irrigation development and management system. The project was transformative in developing the national system for participatory irrigation management and development. In most project provinces, this approach is now applied to the government's own provincial and district programs. Roles, tasks, and capacity of water users associations and federations. Further support is needed at district and provincial level to ensure water users association and water users association federation develop into effective and sustainable organizations. Sufficient district and provincial level resources should be allocated to ensure that project gains are sustained and enhanced. Operation and maintenance of rehabilitated infrastructure. Greater focus should be placed on O&M arrangements, which should be incorporated into the participatory irrigation management agreement with district governments. The Rencana Pengembangan dan Pengelolaan Irigasi (district irrigation management plan) is an effective planning mechanism that provides appropriate O&M for district systems using a needs-based budget approach. Agricultural development. The agricultural program was initially limited to classroom training, but adjusted to promote field level agriculture demonstrations and rehabilitation of tertiary irrigation canals. It was very successful and contributed to the high economic returns of the project. Financial management. The use of prorated financing across the three sources of funds for all expenditure categories should be avoided. Adequate initial advances to imprest accounts should be provided to minimize pre-financing of loan activities through government temporary accounts. The fund flow mechanism adopted by Directorate General of Regional Development for regional activities should not be used in future projects. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/participatory-irrigation-sector-project-pcr
Madrasah Education Development Project | Indonesia | Education | 2014-03-01 | Ensure government ownership and good management. Government ownership and good management are essential. Ministry of Religious Affairs demonstrated strong ownership of the project by making sufficient financial, human, and technical resources available in a timely manner. Good coordination and communication among all project stakeholders, i.e., ADB, government agencies, madrasahs, consultants, and communities, are key factors in the success of the project. Creating positive synergies and a harmonious working environment among key stakeholders throughout the life of the project is essential to successful project implementation. Promote a community-driven development approach. The success of the madrasah development plan (MDP)-based improvements in each participating madrasah suggests that a community-driven development approach could provide a model for the development of all madrasahs. The requirement to jointly formulate an MDP in each project madrasah created an environment for participatory planning at the level of the individual madrasah for the formulation of both long and short-term plans, and became the starting point of a development process that had the full support of the wider community. Even though project madrasahs were funded entirely through block grants provided from project funds, the MDP-based approach to madrasah strengthening ensured community ownership through the process of MDP formulation. As a result, community participation remained high. This was demonstrated by community cash and in-kind contributions totaling about $3 million to support the provision of teaching and learning facilities. Systematically involve district administrations. A systematic approach toward involving the district administration and Ministry of Education and Culture education offices is required to realize wider development impact. It would be beneficial to harmonize madrasah development with Ministry of Education and Culture district education plans and integrate MDPs into the annual district development plans. Greater capacity-building of district-level Ministry of Religious Affairs staff will be essential for sustaining quality improvements in the madrasah education system. Greater collaboration with the Ministry of Education and Culture is also essential to ensure more efficient use of government resources. Support institutional development beyond training. The project was also intended to build the institutional and professional capacity of the madrasah education management system. To that end, the project provided funds for Ministry of Religious Affairs officials to take doctoral and master's degrees overseas. However, institutional capacity building requires more that training. It also requires streamlining of the organizational structure, job functions, professional skills, resources allocation, and accountability system. Further efforts are needed to create and implement a capacity-development plan that will support the institutional capacities of Ministry of Religious Affairs at all levels, starting from the central level. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/madrasah-education-development-project-pcr
Community Water Services and Health Project | Indonesia | Agriculture, Natural Resources, and Rural Development, Health | 2013-01-10 | 1. Involving beneficiaries at all stages of planning and implementation of upgrading activities and promoting inclusive community empowerment are critical in ensuring pro-poor investments and sustainability. project cycle stage: Lesson Topics: 2. Community facilitators and consultants must be qualified and committed; sufficient time should be allocated for community empowerment - ensuring that community members are sufficiently involved in prioritizing their needs, developing investment proposals, and making decisions. project cycle stage: Lesson Topics: 3. More attention should be given to operation and maintenance (O&M) planning and management, including awareness of resource requirements for O&M measures and sound financial and reporting systems. project cycle stage: Lesson Topics: 4. Covering a large number of remote villages spread over four provinces may not be an effective way to maximize the use of resources. The effectiveness of the investment in generating development impact, as well as project efficiency, would have improved in a focused geographic approach. project cycle stage: Lesson Topics: 5. Project management has significant roles in achieving project objectives. The weak project management and insufficient capacity of project stakeholders prevented the delivery of optimum project benefits. project cycle stage: Lesson Topics: 6. Indicators to measure the achievement of project outcome need to carefully consider the scope of all activities carried out under all outputs. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/community-water-services-and-health-project-indonesia-pcr
Sixth Development Policy Support Program | Indonesia | Industry and Trade, Public Sector Management | 2013-01-03 | 1. The program framework has proven successful in enabling the use of a flexible medium term framework that promotes ownership by the government, as was evident in the Development Policy Support Program (DPSP) series. In addition, the medium-term framework allows changing government priorities to be successfully incorporated, as occurred under DPSP-6. The medium-term framework also promotes a continuous dialogue with the government on reform, thereby contributing to government ownership and allowing a program to efficiently respond to new or increased economic risks and shifts in government policy priorities. The continuing policy dialogue also allowed ADB to effectively respond and exit the DPSP series in a timely manner at the conclusion of DPSP-6. project cycle stage: Lesson Topics: 2. Numerical targets such as gross domestic product growth rate and poverty incidence should be used with caution, as a global financial crisis can adversely and unexpectedly affect achievement of these targets, as was the case under Development Policy Support Program - 6. project cycle stage: Lesson Topics: 3. There may be merit in carefully reviewing donor coordination mechanisms to determine if there are more effective ways to coordinate structural and sector programs. If alternative approaches to achieving the same high level of coordination could be formulated, such techniques may allow more resources to be dedicated to each donor's programs and thereby increase the likelihood they will succeed. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/sixth-development-policy-support-program-pcr
Indonesia: Rural Income Generation Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2012-12-10 | 1. Data availability (of income and non-income variables at the village and district levels), costs in time and resources, and simplicity of application tend to play a greater role in determining the actual targeting mechanism used; it is therefore important to allocate resources to ensure that a project's targeting mechanism has these elements. [Main text, para. 21] project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Data collection and management Methodologies/Approaches: Targeting 2. Bank Rakyat Indonesia (BRI) appreciated the presence of third-party providers of intermediation services to self-help group (given BRI's insufficient experience with non-collateralized loans). This validation notes that such intermediaries need not be government personnel because contractual field liaison officers or nongovernment organizations (with potentially better financial skills than Agency for Agricultural Human Resources Development staff) could also perform such role without posing hidden costs to government. [Main text, para. 22(i)] project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation 3. This validation stresses the importance of inherent incentives in ensuring prompt repayment of non-collateralized loans from the perspectives of the subborrowers in making the payments and the conduit financial institution (the Bank Rakyat Indonesia in this case) in collection. [Main text, para. 22(ii)] project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Sector Related Issues: Rural development 4. This validation emphasizes the significance of clarifying upfront how the reflows would be utilized through a sunset provision to give the bank an incentive to maximize repayment and minimize arrears. [Main text, para. 22(iii)] project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Sector Related Issues: Rural development 5. The administrative workload of implementing project activities at the district level across many provinces overwhelmed the executing agencies, resulting in delayed decision making, weak supervision of field personnel, and low sense of ownership among the beneficiaries; project activities ought to have focused on a few provinces at a time. [Main text, para. 22(iv)] project cycle stage: Implementation Lesson Topics: Project Management: Project supervision Capacity Development: Ownership Sector Related Issues: Rural development Methodologies/Approaches: Targeting 6. The intensive demands of such a project on ADB supervision suggest that project management should be delegated to or shared with the Indonesia Resident Mission. Given the significant requirement for consultant inputs, ADB may facilitate the government's engagement of consulting firms instead of individual consultants. [Main text, para. 22(v)] project cycle stage: Country Partnership Strategy Lesson Topics: Project Management: Consultants Project Management: Project management Project Management: Project supervision Other: Resident Mission | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/indonesia-rural-income-generation-project
Coral Reef Rehabilitation and Management Project Phase II | Indonesia | Agriculture, natural resources and rural development | 2012-11-01 | The following lessons were learned through the project: (i) close coordination and cooperation among the district governments, the Indonesian Navy, the maritime police, Ministry of Marine Affairs and Fisheries (MMAF), District Fisheries and Marine Affairs Services, and fishing communities is crucially important during the early period of project implementation to ensure their continuous support in monitoring, control, and surveillance (MCS) activities; (ii) the integration of the district coral reef management plans (CRMPs) into the district development plans and the Mid-term Regional Development Plan with budgetary allotments is a constructive way to engage district governments in maintaining coral reef management sustainability and providing continuous financial support; (iii) obtaining the full support and cooperation of the regional legislators and local officials is necessary to fast-track the legislative approval process and budget support; (iv) multi-stakeholder involvement is critical to successful implementation and sustainability of coral reef programs; (v) the links between a bottom-up and top-down approach are key in formulating policy and providing a better foundation for law enforcement; (vi) the preparation of sound project feasibility studies requires a wide range of specific skills (e.g., in market and financial analysis) that need to be developed within the cadre of extension workers, project implementing units (PIUs), and nongovernment organization (NGO) staff. Extension workers should not only have a technical background in fisheries, but must also have business management skills. A well-prepared project feasibility study increases the likelihood of success of a livelihood project; (vii) human resource capability and the institutional strength of local governments should be considered before expensive hardware is provided; (viii) empowered communities with a high level of awareness are effective in reducing destructive fishing practices; and (ix) gender mainstreaming, particularly in the implementation of livelihood projects, is an effective strategy for empowering women. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/coral-reef-rehabilitation-and-management-project-phase-ii-pcr
Local Government Finance and Governance Reform Sector Development Program | Indonesia | Public sector management | 2012-10-01 | Program Related Technical assistance (TA) inputs. The TA work plan assumed that the policy and institutional reforms would be achieved early and that the remainder of the time would simply involve monitoring and evaluation of implementation. However, policy reforms take time, and continued monitoring and effort are required from the TA, the counterparts, the government, and ADB throughout the program to effect policy and institutional changes. Long-term perspective. The adoption of a medium-term expenditure framework for the local government budget meant that the local government was equipped with a set of long-term objectives to guide and shape medium-term policy design and implementation. The close consultation involving the government, ADB, and other development partners strengthened the governmentï¿½s ownership and increased the potential for funding agency buy-in. Flexibility in design. A local government finance and governance reform program is complex and involves major changes in the legal and regulatory framework, institutional arrangements, local government financial infrastructure, and human capacity. Hence, sufficient time must be allocated to program implementation, and design flexibility must remain a key consideration. Time lag between adoption of reforms and effective enforcement. The delays in the enforcement of minimum service standards were specifically mentioned. Coordination among stakeholders. A key factor in the acceleration of local government finance and governance reform is coordination among stakeholders. Therefore, effective coordination and information sharing are essential to successfully implement a project involving government agencies and numerous stakeholders. Project Related Full commitment from the regional governments. The successful implementation of a project depends on the support and commitment of top level management, including provincial governors, Bupati, and Walikota at the Kepala Bagian/Dinas level, as well as Tim Admin and operators. Changes in personnel at the Kepala Bagian level who are in charge of implementing the Sistem Informasi Pengelolaan Keuangan Daerah (regional financial management information system or SIPKD)/regional Sistem Informasi Keuangan Daerah (regional fiscal information system or SIKD) system in the regional governments but without the commitment to the use of the SIPKD/regional SIKD system can discontinue the implementation of the SIPKD/regional SIKD system in the concerned regional government with smooth running system. Realistic outputs are the key to success. The project was conceptualized and designed to cover 171 participating regional governments in the implementation of the SIPKD/regional SIKD in the regional governments. This was too wide a scope to cover over 36 months of implementation. Project design needs to incorporate regional governments' inputs. It is the view of the participating regional governments that the concept and design of the project can be improved. The initial design, which envisioned the implementation of SIPKD in 17 regional government work units, could be expanded to accommodate all working units since these units are all interrelated. Implementation in all work units would provide a clearer picture on the benefits of SIPKD. Better design of procurement procedures. Procurement thresholds should be more carefully considered, particularly for the procurement of information technology hardware/software, which requires a precise and timely procurement process due to the fast- changing pace of technology and the risk of obsolescence. In addition, an early consultant support should be provided to the executing agency to assist it in the design of procurement procedures. Better recruitment of consultants. Projects that require the hiring of a consultant who is responsible for the recruitment of other project consultants should consider the following during the planning stage: (i) using advance contracting and a retroactive financing method that allows the borrower to proceed, with ADBï¿½s approval, with the selection (though not contracting) of consultants before the loan effectiveness or (ii) using ADB-provided funds for a TA covering the recruitment of project completion unit consultants, and later including this as part of the cost of the TA portion of the loan. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/local-government-finance-and-governance-reform-sector-development-program-pcr
Sustainable Capacity Building for Decentralization Project | Indonesia | Public sector management | 2012-10-01 | The project produced major insights into capacity building for regional government interventions, to be considered in the design of future projects: (i) securing the commitment, ownership, and understanding of the project's stakeholders at central, provincial, and district or city levels is key to ensuring smooth implementation and to meeting sustainability and institutionalization objectives; (ii) the introduction of information and communications technology (ICT) in regional government management has helped modernize business processes and made regional government more transparent and accountable; (iii) the project produced a number of best practices to be replicated in other regions; (iv) a project with complex design and implementation arrangements at an early stage of decentralization reform is risky and may lead to delays because of the lack of experience and capacity of the newly autonomous regions and central governments in setting up the implementation arrangements; and (v)high-end technology products with over-specified features would not be recommended for regional governments because the operation and maintenance (O&M) expenses would be unaffordable and sustainability would not be secured. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/sustainable-capacity-building-decentralization-project-pcr
Rural Infrastructure Support to the PNPM Mandiri Project | Indonesia | Agriculture, Natural Resources, and Rural Development, Education, Health, Transport | 2012-01-10 | 1. Involving the beneficiaries at all stages of planning and implementation of upgrading activities and promoting inclusive community empowerment are critical in ensuring pro-poor investments and sustainability. The following are included: (a) community control of decisions over resources and investment choices; (b) simple and transparent funds flow arrangements with direct transfers to community accounts; (c) comprehensive facilitation support, including social facilitators to ensure full community participation, and engineering facilitators to oversee the technical quality of civil works; (d) strong accountability procedures, such as public disclosure of budgets and contracts; (e) community management of funds and procurement matters; and (f) training for communities in establishing effective mechanisms for operating and maintaining new infrastructure. [Main text, para. 65(i)] project cycle stage: Lesson Topics: 3. Substantial evidence demonstrates that community-driven development (CDD) approaches are more effective than other approaches to basic infrastructure development. Evidence also indicates that CDD is likely to offer better cost recovery and maintenance of completed infrastructure facilities and services because of the strong sense of ownership of the community members. In addition, CDD leads to better accountability. Transparency in decision making and procurement and increased use of audits have demonstrably reduced corruption and leakage of public funds. Sufficient time is needed to support and strengthen community participation and capacity to prioritize, design, implement, manage, and monitor project investments. [Main text, para. 65(iii)] project cycle stage: Lesson Topics: Enter lesson here2. Community facilitators must be qualified and committed, and enough time must be set aside for community empowerment activities, to ensure that community members are sufficiently involved in prioritizing their needs, developing investment proposals, and making decisions. [Main text, para. 65(ii)] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-infrastructure-support-pnpm-mandiri-project-pcr
Decentralized Basic Education Project | Indonesia | Education | 2012-01-06 | 1. Flexible management by the government and ADB allowed a complex project to be implemented successfully in a rapidly changing environment. Good communication from the project management team, together with flexible support from ADB, allowed project implementation to adapt to the changing legal and administrative environment while retaining the basic project rationale and objectives. ADB project supervision would have been enhanced if there had been greater continuity of project officers. project cycle stage: Lesson Topics: 2. The experience of the project indicates the importance of systematic record keeping in addition to ongoing monitoring and evaluation. Although implementation was generally satisfactory, there was poor documentation and recording at the central and district levels of activities and updated data relating to project activities, output, and outcomes. project cycle stage: Lesson Topics: 3. The project supported the development of district-based education information systems to strengthen district-based planning. Although most districts were still producing annual education statistics, there is room to improve data quality and the use of data in planning and management. Central Ministry of National Education maintains education statistics for the provinces; in the districts, all data are accessible through the districts themselves. project cycle stage: Lesson Topics: 4. The project framework was not stressed sufficiently by ADB during loan implementation. As a result, the government and the central facilitation unit were not fully aware of all of the objectives of the project. Further, as district project management teams were under considerable political pressure to accelerate the implementation of project activities, the project came to be viewed primarily as a funding mechanism and the emphasis on district capacity development tended to be lost. project cycle stage: Lesson Topics: 5. An important lesson is the importance of integrating project funds and activities into government processes, wherever possible. The separation of Decentralized Basic Education Project funds for districts from district government budget mechanisms weakened the link between district education development plans and the annual budgeting process, and made district capacity building less effective. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/decentralized-basic-education-project-0
Poor Farmers' Income Improvement Through Innovation Project | Indonesia | Agriculture, natural resources and rural development, Finance | 2011-12-01 | The participatory approach and the adoption of gender mainstreaming in village investment planning and implementation are key factors in the project's success. Poor farmers, including women, decided on the type of investments needed in their villages. That instilled in them a sense of ownership and responsibility that was critical to sustainability. The focus on very poor, remote villages where limited government programs were operating contributed to the success of the project. The villagers really valued the investments and were willing to provide significant contributions. Village-based planning, construction using local labors, and the operation and maintenance (O&M) of small- scale village infrastructure have leveraged local resources, as compared with contracting them to a third party. This strategy minimizes potential corruption. The mobilization of farmer groups is most effective with the active participation of village facilitators (50% of whom were women) who are village residents or respected village leaders (e.g., religious leaders), and the successful involvement of a consortium between a national nongovernment organization or NGO, local NGOs, and other civil society organizations. Close coordination between the district governments, the Indonesian Agency for Agricultural Research and Development (IAARD) and assessment institute for agricultural technologies (AIATs), and the village heads from the start of the project is crucial in ensuring their continuous support after project implementation to sustain the benefits gained from the project. An effective monitoring system that uses clear criteria and indicators to track development, including a digital map monitoring system, contributed significantly to the successful implementation of the project. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/poor-farmers-income-improvement-through-innovation-project
Indonesia: Technological and Professional Skills Development Sector Project [Loan 1792-INO] | Indonesia | Education | 2011-11-30 | 1. The competitive based funding mechanism using block grants is a useful mechanism to upgrade the quality of higher education by promoting transparency and accountability, and building a strong sense of ownership among higher education institutions (HEIs). The approach ensured that the study programs proposed for assistance were those that most satisfied both social demand and labor market demand. It allowed the HEIs to customize the mix of components for funding, i.e., staff development, upgrading of facilities and equipment, development of new learning materials and teaching methods, MIS, library, language laboratory, job placement center, etc. What made it more laudable as a mechanism for HEI was the added feature that bidders within a region compete only among themselves rather than at large, thereby ensuring geographic representation of assisted HEIs. This mechanism is found to be effective and has been adopted by other development partners, and national and local governments. [Main text, paras. 40,59,63,71] project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Funding Sector Related Issues: Education 2. Quality assurance can be further strengthened with a complementary component that verifies the quality of learning outcomes. The project supported the strengthening of the Board of National Accreditation for Higher Education and the establishment of quality assurance units to ensure the quality of the study programs. However, standards and quality per study program varied per region where quality was better in major cities, as indicated by the number and accreditation levels of study programs. The executing agency can develop a complementary component such as the institutionalization of a licensure examination that may standardize the quality of graduates. [Main text, para. 73] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Harmonization Sector Related Issues: Education 3. Institutionalizing linkages between educational entities and industries nationally and at the higher education institution (HEI) level through forums where employers can give advice on national and institution specific policies, plans, and programs, can be a good practice. Linkages between educational entities and industries by way of collaboration in curriculum design and partnerships in job orientation programs were observed during the independent evaluation mission. However, the extent varies depending on the HEIs. On the positive side, this has resulted in a growing appreciation of the importance of interaction with industries, and more relevant study programs. Hence, for institutions, the forum could be an industry advisory board composed of representatives of selected business enterprises in their area. At the national level, an annual consultative forum may be useful, where government policymakers, employers, and educators discuss policies and program design to respond to trends in the labor market. In this context, the government could encourage the continuation and expansion of a valuable practice at some HEIs, including the curriculum on-the-job training opportunities in industries. [Main text, paras. 44, 78] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Harmonization Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation 4. An integrated monitoring and evaluation system and management information system for higher education institutions can be an important tool in assessing impact of related sector initiatives. For instance, the ongoing development of an integrated monitoring and evaluation system supported by Directorate General of Higher Education's (DGHE) management information system (linked to project assisted higher education institutions and other institutions) can facilitate the preparation of an annual tracer study that would be useful to obtain meaningful impact assessments. This can also determine areas for improvement to sustain not only this project but also other initiatives of the DGHE. [Main text, paras. 54,59,79] project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Management information system Sector Related Issues: Education | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/indonesia-technological-and-professional-skills-development-sector-project-loan-1792-ino
State Audit Reform Sector Development Program | Indonesia | Public sector management | 2011-10-01 | As a general lesson, project implementation would be driven more speedily by champions or agents of change. As experienced in other projects, strong ownership and leadership are the key to a successful project. Through strong support from the BPK, all outputs and outcomes were achieved satisfactorily. The Badan Pemeriksa Keuangan (Supreme Audit Board) or BPK was transformed through institutional and regulatory reform, supported by capable auditors. The BPK has indicated that it will continue with the project, using its own resources, working independently from other agencies to reiterate their position as the supreme audit institution. If the BPK requests financial support, ADB should continue to provide it, in the form of a stand-alone project loan. Each year, the project encountered a delay in budget allocation or Daftar Isian Penggunaan Anggaran (DIPA) release, which resulted in delays in implementing planned activities. This could have been avoided if the government had allowed multi-year budget earmarking, given that the project was funded by a multi-year loan. Since this has been identified as a broad systemic issue affecting other projects, this is also being addressed in the Country Portfolio Review Mission jointly held by ADB and Badan Perencanaan dan Pembangunan Nasional (National Development Planning Agency) or BAPPENAS. Although the project met performance targets and indicators, substantive support was provided by the Investment Loan Monitoring Unit (ILMU) and the technical assistance (TA) consultants to help the Ministry of National Education- Inspectorate General (MONE-IG) implement the scholarship program. The support ranged from administrative to monitoring and evaluation, and quality assurance. As such, it was essential to have good coordination between BAPPENAS, as the executing agency, and the MONE-IG, as the implementing agency. BAPPENAS should play a role in aligning the strategic outlook of the agencies. Another lesson learned was that too many project implementation units (PIUs) were operating, at both the central and regional level (which implemented block grants). The project had seven PIUs at the central level (ILMU secretariat, BPK, Badan Pengawasan Keuangan dan Pembangunan or Financial Supervisory and Development Board/BPKP, Badan Pendidikan dan Pelatihan Keuangan or Ministry of Finance Training Agency/BPPK, Ministry of Home Affairs-Inspectorate General or MOHA-IG, MONE-IG, and Ministry of Finance-Inspectorate General or MOF- IG) and 50 PIUs at the regional level (Badan Pengawasan Daerah or Regional Inspectorate/BAWASDAs or local inspectorates in 50 districts and cities implemented the lump-sum capacity-building block grants). This created complexities due to limited project staff at the executing agency and ADB. These few project staff had to deal with a number of administrative issues, rather than with quality control. Thus, establishing simple implementation arrangements with adequate staff resources is important in ensuring smooth project implementation. In addition, strong commitment to the project from heads of regional government is required, as expressed through the availability of counterpart funding, minimal staff turnover, and continuity of PIU staff. The selection of participating regions should be aligned with the schedule of regional elections; selection should only be conducted after the new head of a regional government is appointed. In addition, it was a challenge to administer the block grant mechanism for 50 BAWASDAs and Dewan Perwakilan Rakyat Daerah or Regional Parliament (DPRD) secretariats. All the BAWASDAs had to prepare institutional development plans (IDPs) for ADB approval in order to be eligible for grant funds. Subsequently, the BAWASDAs and the DPRD secretariats were required to coordinate with the MOHA-IG to ensure their budgets were included in MOHA-IG DIPA (the budget and the activities were prepared in accordance with the approved IDP). This process resulted in delays. The budget of the BAWASDAs and the DPRD secretariats was often approved in MOHA-IG DIPA at the end of the year, which gave the BAWASDAs less than three months to implement their activities. In addition, the BAWASDAs and the DPRD secretariats lacked experience in processing payments funded by loans and grants. These issues led to certain activities not being implemented, and to low disbursement by participating BAWASDAs and DPRD secretariats. Thus, it is imperative to simplify implementation arrangements. In addition, PIU staff must be properly trained before project implementation, and DIPA issues clearly understood and resolved upfront. Advance procurement action would be preferable. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/state-audit-reform-sector-development-program
Neighborhood Upgrading and Shelter Sector Project | Indonesia | Water and other urban infrastructure and services | 2011-09-01 | The project produced some important insights for neighborhood upgrading interventions to be considered for future project designs. Involving beneficiaries at all stages of planning and implementation of upgrading activities and promoting inclusive community empowerment are key to ensuring pro-poor investments and sustainability, including (i) community control of decision- making over resources and investment choices; (ii) simple and transparent funds flow arrangements with direct transfers to community accounts; (iii) efficient facilitation support, including social facilitators to ensure full community participation, and engineering facilitators to oversee technical quality of civil works; (iv) strong accountability procedures, such as public disclosure of budgets and contracts; (v) community management of funds and procurement matters; and (vi) training for communities in establishing effective mechanisms to operate and maintain new infrastructure. Qualified and experienced community facilitators and sufficient time for community empowerment activities are important to ensure that community members are sufficiently involved in prioritizing their needs, developing investment proposals, and taking decisions. Under the decentralization law, the national government no longer exercises administrative control over regional governments. Likewise, the provincial government does not have administrative control over district governments. Subsequently, local coordinating offices are under the administrative supervision of local governments, thus establishing appropriate city management and monitoring arrangements is essential to exercise administrative and technical supervision and provide support to community neighborhoods. Covering a vast number of cities spread over almost the entire country may not be an effective way of maximizing the use of resources. A focused geographic approach would have provided flexibility for designing better social and economic benefits for the beneficiaries. The effectiveness of the investment in generating development impact, as well as project efficiency, would have been improved. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/neighborhood-upgrading-and-shelter-sector-project
Road Rehabilitation - 2 Project | Indonesia | Transport | 2011-09-01 | Project readiness. Advance procurement was used for the first time in the recruitment of consultants under a project with Directorate General of Highways (DGH), and consultant recruitment was not a cause of delays. The time for completing the procurement process for the civil works, however, was underestimated; the process took 1 year longer than planned. The lesson here is that the time required for completing the various steps has to be estimated much more carefully, on the basis of experience. Adequacy of designs for works in difficult soil conditions. For the reconstruction of road sections in difficult terrain and soil conditions, the initial designs were not based on adequate geotechnical investigations. The design reviews therefore took longer, contributing to cost increases and delays in the start of the works. Recruitment of supervision consultants. Delays in contract signing were a factor behind the decision of the consulting firms to replace the initially proposed experts, including the team leader. Although the replacements had to have the same qualifications as the people they replaced, consulting firms in such a situation generally propose less-qualified replacements. Contingencies. The physical and price contingencies were inadequate, in particular given the extensive design changes required for a number of subprojects, the expected increase in the scope of rehabilitation works over time as the roads continue to deteriorate further, and the significant unit price adjustments resulting from the fuel price increases. Premature road failure caused by overloaded vehicles. The government has not yet developed and implemented a more effective policy to control vehicle overloading. Local initiatives are more easily implemented and achieve significant results. Also, DGH is reviewing its policy of designing roads on the basis of legal axle load limits and considering other options such as designing roads on the basis of actual axle loads. For the near term, such initiatives should be strongly encouraged. Specifications for the use of coal in asphalt plant. The two cases where low-quality asphalt pavement resulted from the use of inappropriate coal as fuel for the asphalt mixing plant burners indicate a need to develop specifications and exercise stringent supervision when coal is to be used as fuel. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/road-rehabilitation-2-project
Earthquake and Tsunami Emergency Support Project | Indonesia |  | 2011-01-02 | 1. Disaster management support should be based on a needs assessment that should identify and address such implementation problems as the lack of government staff, regulations, or design standards for various physical works. project cycle stage: Lesson Topics: 2. Reconstruction support should be selective and adopt a realistic time frame, with ADB focusing on areas that are unlikely to receive support from other partners. project cycle stage: Lesson Topics: 3. Phasing of reconstruction assistance may be considered, clearly distinguishing the needs of initial emergency response from those of subsequent reconstruction. project cycle stage: Lesson Topics: 4. Proper institutional arrangements and central coordination by one agency are essential. The effectiveness of post-disaster reconstruction depends on the willingness and collaboration of relevant government agencies. project cycle stage: Lesson Topics: 5. Off-budget activities may expedite implementation as on-budget implementation ensures sustainability by establishing an extensive outreach program and building capacity for future reconstruction programs. project cycle stage: Lesson Topics: 6. Flexibility in implementation is essential, as it facilitates the design of need-based reconstruction projects through simplified documentation. project cycle stage: Lesson Topics: 7. Decentralization is essential in effective disaster management. Adapting to emerging needs is desirable in disaster reconstruction. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/earthquake-and-tsunami-emergency-support-project
Asian Development Bank Support for Decentralization in Indonesia | Indonesia | Public Sector Management | 2010-07-31 | 1. There is a need to increase the number of professional staff based in the resident mission for the analysis and management of projects and programs. The dialogue with the government and the coordination with development partners, specifically called for the presence of staff in the resident mission with deep knowledge of decentralization and familiarity with the intergovernmental issues of Indonesia. Since ADB lacks adequate resources for project supervision and monitoring, results become difficult to measure. A particular issue affecting performance is the level of resources at the resident mission. To some extent, ADB can make use of the analysis and initiatives of other development partners and it can glean some information and views from consultants working on technical assistance (TA) projects. However, additional capacity is needed to design and guide the various loans and TA provided. Flying-in staff from Manila to discuss policies and instruments with resident mission staff, counterparts, and development partners is far less preferable to having a permanent capacity in the resident mission. [Main text, paras. 69-70, 91] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project supervision Capacity Development: Capacity development Country Context: Decentralization Other: Resident Mission Methodologies/Approaches: Policy dialogue 2. Over the period of decentralization, ADB needs to increasingly work through existing government systems in support of government programs, and with and through other development partners that have the capacity to work effectively at the national and local levels. While ADB has been responsive to the needs of the government, it was unable to adjust quickly enough to the changing needs and new realities of decentralization. Amid the country's capacity issues, ADB support were slow to channel adequate resources, delegate authority, and develop new modalities to suit the changed nature of the client. [Main text, paras. 57-58,91] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Country Context: Decentralization Country Context: Prioritization 3. There is a need to prioritize efforts to optimize coordination and policy dialogue with government and other development partners. ADB's strategies for each phase of decentralization appear to have been relevant to the strategic needs of the government. However, ADB may have underestimated the speed, scale, and the requirements of Indonesia's decentralization program, especially the readiness and capacity of institutions. Indonesia decentralized faster than any other country in the region. ADB could also do more to share with, and learn lessons from, other development partners' support for decentralization. [Main text, paras. 60-63, 91] project cycle stage: Implementation Lesson Topics: Country Context: Decentralization Methodologies/Approaches: Policy dialogue | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/asian-development-bank-support-decentralization-indonesia
State Audit Reform Sector Development Program | Indonesia | Public sector management | 2010-03-01 | The major lesson learned from implementing the program is that it is generally difficult to implement reform measures that involve institutional shrinking and downsizing staff as in the case of the Badan Pengawasan Keuangan dan Pembangunan or Financial Supervisory and Development Board, now the government internal auditors (BPKP). The BPKP was a well-entrenched auditing institution with about 6,500 staff, about 5,000 of whom were spread in about 30 regional offices. The downsizing of the BPKP as contemplated under the program would have necessitated moving its staff to other audit institutions such as the inspectorate generals of individual ministries, badan pengawasan daerah or regional internal audit bodies (BAWASDAs), and the Badan Pemeriksa Keuangan or Audit Board of the Republic of Indonesia (BPK). That was found to be difficult, as it involved changes in seniority, salaries, and staff positions. The strong political backing that the BPKP appeared to enjoy further exacerbated the problem. Implementing a reform program that involved cross-agency coordination and cooperation needed the country's highest political support, while this program was supported mainly by the Ministry of Finance (MOF) as part of its public financial management reform program. The MOF by itself appeared to lack support to push for downsizing the BPKP as contemplated under the program. In the end, the government appeared willing to sacrifice the second tranche in the interests of political expediency. The $100 million involved in the second tranche was relatively small in the context of Indonesia's overall budget. Thus, its sacrifice would not have caused any budgetary problems. The other lesson learned was that this sort of vital reform measure, i.e., reorganizing the BPKP, should not have been pushed back as a condition for release of the second tranche. This appears to be a flaw in the program design. ADB should have insisted on reforming the BPKP step by step, making the government's agreement to reorganize the BPKP a condition for submitting the program for Board approval. Then government agreement to come up with a firm plan to reorganize the BPKP should have been made a condition for the release of the first tranche. Finally, the government's beginning to implement the reorganization plan for the BPKP should have been a condition for the release of the second tranche. Board approval and release of the first tranche should have been used to lever positive movement towards reorganizing the BPKP. Leaving that to the final stage of releasing the second tranche appeared to be quite late in the reform implementation program, causing the cancellation of that tranche and allowing the BPKP to maintain more or less its pre-program status. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/state-audit-reform-sector-development-program-0
Six Universities Development and Rehabilitation in Indonesia | Indonesia |  | 2010-02-01 | A midterm review of a project should not be linked to the timing of another project activity. Such a linkage was found to be counterproductive to the timely and successful implementation of the Project. The sustainability issue should be given careful attention in designing a project that requires (i) innovative services to be established and continued after loan closing; and (ii) budget allocation, human services, and commitment by decision makers. The physical appearance of existing buildings, landscape, and teaching equipment at an educational institution is a good indicator of budget allocation for maintenance and commitment by teaching and administrative staff to a good work environment. It should not be assumed that where maintenance of existing facilities is poor, new buildings and teaching equipment provided under a project will fare any better. Bank supervision of project implementation is more critical at the start when implementation arrangements are made operational than when implementation is progressing on schedule. More staff time should be allocated to review missions for projects at widely scattered locations. Poor design of and quality of completed civil works are linked with inadequate and unqualified supervision at the local project level. To eliminate these potential problems, the main implementing agency for a project should have overall responsibility for the engagement and monitoring of implementation of the services. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/six-universities-development-and-rehabilitation-indonesia
Decentralized Health Services I | Indonesia | Health | 2010-01-01 | Demand-driven approach to improve the local health situation. The project highlighted the importance of evidence-based and demand-driven project planning and implementation to address local health needs better. The establishment of district team problem-solving empowered staff and encouraged intersectoral coordination. Assess and evaluate human resource development needs. Training needs assessment and post-evaluation of training courses need to be included to assess adequacy, quality and training impact. Capacity building has to be linked to incentive structures. Investment in training has to be linked to incentive schemes (financed by local governments) to ensure staff retention, especially in remote areas. The project showed that several local governments initiated incentive schemes for medical doctors and midwives. Management skills have to be improved. Training largely focused on technical matters rather than improving management skills. In strengthening decentralization of health services there is a need to focus on health management training and monitoring and evaluation of health staff. Mobilize local leaders. Local leaders and or champions need to be identified to initiate local health care reform initiatives and the financial sustainability of activities. The project demonstrated that local regulations to support health sector reform and ensure sustainability are possible through large-scale socialization and advocacy. Strengthen management capacity for decentralized health services. While central and local staff were empowered and received diverse technical training, overall more attention needs to be given to the management of health services in the decentralized environment. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/decentralized-health-services-i
Indonesia: Engineering Education Development Project [Loan 1432-INO] | Indonesia | Education | 2009-12-31 | 1. The monitoring and evaluation system needs to be integrated and implemented within the regular activities of the project institutions and linked to the Directorate General of Higher Education's management information system to better identify improvements required in the delivery of education services. Evaluation noted data gaps and the need for closer coordination in terms of data collection and monitoring and evaluation of impacts. As such, baseline data for specific outcome indicators like enrollment rate, pass rate or graduation rate of students, job search period, etc., should be established and continuously updated in an easily accessible database for each project institution. Real-time assessments or post-evaluation studies on quality of engineering education and academic standards, for instance, require time-series trends of key education indicators which would help each university or polytechnic institution identify needed improvements for curriculum development, industry-institution linkage, staff development and access to engineering education. [Main text, paras. 53,54,76 items (i),(v)] project cycle stage: Design, Implementation, Completion Operation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Post-evaluation Monitoring & Evaluation: Project evaluation 2. Given the limitations in government funding for higher education institutions, the development of entrepreneurial capacity would be useful in establishing alternative means of ensuring cost recovery and funding maintenance and repair of facilities and equipment of these institutions. Partnering with other educational institutions, organizations, and enterprises can facilitate this objective as well as optimize utilization of facilities and equipment. For instance, some project institutions have forged training partnerships with government agencies and enterprises and are providing consulting services in exchange for payments. Some of these revenues are being directed toward repair and maintenance of their training equipment. [Main text, paras. 64,66,76 items (ii),(iv)] project cycle stage: Implementation, Operation Lesson Topics: Capacity Development: Capacity development Capacity Development: Partnerships 3. Integrated management of equipment for each university and polytechnic institution, involving an informative inventory system, operation and maintenance manuals, and staff training and accountabilities, should be instituted to permit easy monitoring of its status to promote its optimal use. The suboptimal utilization of project equipment has been noted to have affected efficiency in meeting project outcomes. [Main text, paras. 63,76 item (iii)] project cycle stage: Implementation, Operation Lesson Topics: 4. An effective screening method used in enhancing college access to the underprivileged and women could be institutionalized for each project universities and polytechnic institution. Expansion of coverage of the scholarship scheme to far-flung areas may be encouraged including the achievement of 50:50 female and male ratio goal. Evaluation noted that the project has resulted in significant changes in the project s institutions capacity which allowed opportunity for more class sessions and to increase education access of women and underprivileged students through scholarships and improving capacity of civil engineering programs. [Main text, paras. 19,48,49,65,71,76 item (vi)] project cycle stage: Design, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Vulnerable groups Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/indonesia-engineering-education-development-project-loan-1432-ino
Indonesia: Metropolitan Bogor, Tangerang, and Bekasi Urban Development (Sector) Project [Loan: 1511-INO] | Indonesia |  | 2009-12-31 | 1. Under a decentralized form of government, a more streamlined approval process (which outlines specific criteria, indicators and checkpoints) could facilitate subproject selection, approval and implementation. The project encountered difficulties due to many layers of government approvals under decentralization. The government allowed financing of urban infrastructure projects with official development assistance, however, to avail of the ADB loan, almost all details in subproject selection, approval, and funding flow needed to pass through the local, provincial and central levels of government. [Main text, paras. 50,52] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Country Context: Decentralization Sector Related Issues: Urban sector/development 2. There is a need to maintain various project impact data, including health and socioeconomic data, to continuously monitor improvements in the public health and livelihood that social infrastructure projects will yield. In the case of the urban development projects in Bogor, Tangerang and Bekasi, the benefit monitoring and evaluation report failed to capture the magnitude of project impact. Even with the physical infrastructure like urban road investment, the government and ADB also need to agree on how to measure benefits and economic value. [Main text, paras. 43,52] project cycle stage: Completion, Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Benefit monitoring and evaluation Sector Related Issues: Urban sector/development 3. To achieve better results, reducing nonrevenue water (NRW) will need continuous efforts from both the management and technical divisions of the local government water supply enterprise. The independent evaluation mission observed that initiatives to reduce NRW did not result in the target figure of 20% in Tangerang, which had the largest coverage among the eight targeted local areas. Reducing NRW is not limited in technical losses from leakage, but also includes financial losses from inaccurate meters and inappropriate billings. [Main text, paras. 40,52] project cycle stage: Implementation, Operation Lesson Topics: 4. Project experience highlighted the adverse impact of lack of demand analysis on the project design and allocation of scarce concessional resource to high priority projects. This, being an important issue with potential risk to economic viability, should have been done at the very outset. In cases of loans for improving water supply, neighborhood upgrading (kampung improvement program), drainage and flood alleviation, sanitation (showers, laundries, toilets), and/or home improvement, in-depth analysis of demand and affordability is necessary to ensure economic viability. The findings should be part of an initial baseline survey in the project preparatory technical assistance. [Main text, paras. 21,39,52(iv)] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Urban sector/development Sector Related Issues: Water resource management 5. Private sector participation (PSP) should be treated carefully, not as a major component, particularly in smaller urban development projects. A prerequisite to PSP is the establishment of profit incentives and improved regulatory capacity of sector institutions. These requires, among others, assurances of rate of return in a given time period as well as adequate provision of support in legal and financial transaction advisories. As such, the process entails a well founded analysis and full knowledge of issues. In this urban development project in Indonesia, the lack of these factors has resulted to the unsuccessful implementation of PSP initiatives. [Main text, paras. 38,39,52 items (v) & (vi)] project cycle stage: Design Lesson Topics: Sector Related Issues: Public-private partnership Sector Related Issues: Urban sector/development | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/indonesia-metropolitan-bogor-tangerang-and-bekasi-urban-development-sector-project-loan-15
Technological and Professional Skills Development Sector Project | Indonesia | Education | 2008-09-30 | 1. A meaningful monitoring and evaluation system necessitates clarity of outcome and output indicators. Those involved in designing the project could have included quality indicators such as teaching-learning performance, relevance of study programs, and employment rates. The lack of which has actually placed constraints on the assessment of the quality of teaching- learning performance and relevance of study programs at the institutional level, and project impacts at the national level (contribution to the country's international competitiveness and sustainable economic growth). [Main text, paras. 9,72] project cycle stage: Design, Implementation, Completion Lesson Topics: Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Project Design: Project design 2. The management of participating higher education institutions needs to institutionalize systems that promote modern teaching methodologies (i.e., promoting student-centered learning and encouraging critical thinking, problem-solving, and team-building). This may include establishment of quality standards for teaching techniques and monitoring of performance of lecturers in classrooms. Project experience has shown that improving competence and academic qualifications through the staff development program did not ensure promotion and strengthening of teaching-learning methods. Many lecturers who participated in staff development program still apply traditional teaching methods, devoting attention to theoretical knowledge. [Main text, paras. 24,72] project cycle stage: Design, Implementation, Operation Lesson Topics: 3. Integration of the use of educational equipment into the educational curriculum can further enhance the learning process. Infrastructure upgrading including the procurement of educational equipment has improved the overall learning and teaching environment in the participating institutions. However, monitoring reports and field visits revealed that in many institutions, the new equipment has not been fully integrated into current lessons, and is underutilized and not well maintained. Greater attention is required from higher education institutions to ensure adequate utilization of equipment by actively encouraging teaching and learning practices that promote student-centered learning. Lecturers need additional support to prepare teaching modules and lesson plans that integrate new equipment and enhance practical training for students. [Main text, paras. 28,57,72] project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Capacity building Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/technological-and-professional-skills-development-sector-project
Regional Development Account Project in Indonesia (Loan 1501-INO) | Indonesia | Multisector | 2007-05-31 | An underperforming project needs to be handled better through an effective system put in place within ADB to take action to restructure or cancel the loan. project cycle stage: Implementation Lesson Topics: Establishing a robust intergovernmental onlending mechanism is difficult and requires that ADB give extra attention to economic and financial analyses of subprojects, as well as the capacity of concerned central andlocal governments to support such an onlending mechanism. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Country Context: Decentralization Policy & Reform: Public sector reform Project preparatory technical assistance (TA) findings need to be more effectively used to address policy and institutional weaknesses before a project is submitted for Board approval. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Capacity Development: Institutional analysis Policy & Reform: Public sector reform Project-related tasks need to be integrated into executing agencies coreoperations. project cycle stage: Feasibility Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/regional-development-account-project-indonesia-loan-1501-ino
Capacity Building for Financial Governance | Indonesia |  | 2006-12-15 | Although sector institutions have adequate capacity (or can outsource) for project development, there is a general lack of capacity for planning and implementing O&M, consulting with beneficiaries, conducting environmental management and monitoring plans, preparing resettlement plans, and managing spatial planning. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Capacity Development: Capacity assessment Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation Communities and developers are not adequately aware of flood risks and how to take precautions to limit flood damage. Flood warning systems may not reach flood-affected communities effectively. project cycle stage: Feasibility Lesson Topics: Project Management: Risks/Risk management Country Context: Emergency Sector Related Issues: Water resource management Engaging NGOs in facilitating beneficiary consultation and stakeholder capacity building proved successful. NGOs support should be provided throughout the project cycle. project cycle stage: Concept Design, Feasibility, Implementation, Completion Operation Lesson Topics: Capacity Development: Capacity building Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation Internal land drainage and adequate river flooding must be carefully studied and incorporated into flood prevention planning at a micro level before detailed flood works are designed. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management It takes time to design and construct a system that is physically appropriate, socially acceptable, and cost-effective. Flood projects need long implementation periods to ensure that holistic integrated solutions will be implemented. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach The sectoral approach is an appropriate implementation modality for flood management. It is recommended, however, that the approach be adjusted to allow for sequential preparation and implementation of subprojects in tranches. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Project design Project Design: Subprojects Sector Related Issues: Water resource management Methodologies/Approaches: Sectoral approach The use of flood protection funds to safeguard such existing infrastructure as bridges, roads, and weirs appears to be a cost-effective option. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management There is a need to develop (a) river asset management systems, (b) needs-based O&M budgeting, and (c) flood damage mapping and damage assessment reporting systems that quantify direct and indirect flood and drainage damages. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Reporting Project Management: Operation and maintenance Sector Related Issues: Water resource management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/capacity-building-financial-governance
North Java Flood Control Sector Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2006-12-15 | 1. Project experience underscores the importance of speed of response in a crisis. Project design that is expansive in scope and speedy in formulation was highly appreciated by the government, and contributed to the sense that concrete assistance is being provided to address key factors undermining economic stability. [Main text, para. 54, 69] project cycle stage: Feasibility Lesson Topics: Project Design: Project design Country Context: Crisis/Post-crisis 2. While the purpose of a technical assistance loan is to encourage greater client ownership, a number of the activities were funding agency driven with very little ownership by the counterpart. Weak ownership is reflected in the uneven progress in project implementation. For example, Capacity Building for Financial Governance (CBFG) support for Bank Indonesia is assessed very positively because the activity was highly relevant and Bank Indonesia had a clear stake in CBFG success. In contrast, activity on secured transactions was dropped due to the lack of government buy-in. [Main text, paras. 23, 55, 72] project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Ownership 3. If a project includes training, then a comprehensive training needs assessment should be carried out prior to committing funding for training programs or scholarships. This would ensure training programs and scholarships are tailored for the skill needs of the agency. In some circumstances the training needs should complement organizational restructuring. In Indonesia, the economic crisis exposed weaknesses in institutions that needed to be modernized through organizational reforms. Programs to improve human resources in these agencies would be more sustainable if carried out in parallel to civil service reforms. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management Country Context: Crisis/Post-crisis Policy & Reform: Reform 4. A technical assistance (TA) needs to be placed in the appropriate agency where a potential champion can push for the reform agenda. Some components under the Capacity Building for Financial Governance (CBFG) were mismatched with identified implementing agencies. The secured transaction component, for example, was placed with the State Secretariat and then with the Ministry of Law and Human Rights, neither of which possessed appropriate technical understanding or strong interest in the activity. The Government recently drafted and submitted to Parliament a similar law but this was done under the Ministry of Trade as that agency appreciates the importance of a warehouse receipts law for improving access to credit for distributors and farmers. [Main text, para. 23, 74] project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Policy & Reform: Reform An unwieldy project design - involving multiple implementing agencies across a wide range of areas - including banking, public sector financial management, capital market development, bankruptcy and secured transactions, audits of SOEs, deposit insurance, and nonbank financial institution supervision significantly complicating oversight and management for the executing agency as well as monitoring by ADB - results to delays in implementation, and some activities can be dropped and or eventually implemented by other development partners. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Flexibility in a TA project is necessary during a crisis period where anticipating all relevant assistance needs upfront is difficult, especially in a very fluid political environment. An outline design which allows for this (several significantchanges with regard to project components and implementation arrangements being made during implementation) may experience delays in implementation and completion of the project but the original time frame can perhaps be overly optimistic where substantial institutional capacity building requires a much longer time frame. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building Country Context: Crisis/Post-crisis | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-java-flood-control-sector-project
Financial Governance and Social Security Reform Program | Indonesia |  | 2006-11-15 | 1. The program cluster approach is a useful tool for broadly based reforms that require long term institutional development (such as those pursued in the Financial Governance and Social Security Reform or FGSSR). The approach (i) combines a long-term approach that permits covering a wide range of policy and institutional reforms with flexibility to adjust to changing circumstances; (ii) permits proceeding with the gradual introduction of critical components in the sector, including developing a comprehensive legal framework and action plan to facilitate smooth operationalization; and (iii) is a useful instrument for establishing benchmarks and unifying those policymakers who advocate reforms. While the program cluster approach worked well for FGSSR, a medium term framework based on single tranche programs instead of a multitranche would have provided more flexibility while focusing on achievable, upfront outcomes. [Main text, para. 51] project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Modality: Cluster operations Monitoring & Evaluation: Baseline data Project Design: Project design Capacity Development: Capacity development Capacity Development: Ownership Policy & Reform: Policy reforms/framework Methodologies/Approaches: Program Approach 2. Instead of simply carrying over outstanding or ï¿½troubledï¿½ conditionalities from one cluster program to the next, extra efforts should be put in the preparation and implementation of ways to meet these conditionalities. In this program, the amendment of legislation, including the proposed reforms, continued to meet considerable resistance from concerned interest groups, which threatened to submit competing draft legislation to Parliament. Strong government ownership is needed to overcome objections by interest groups. [Main text, paras. 36-37, 52] project cycle stage: Feasibility, Implementation Lesson Topics: Loan Agreement: Covenants Project Design: Project design Capacity Development: Ownership Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/financial-governance-and-social-security-reform-program
Community and Local Government Support Sector Development Program | Indonesia | Public Sector Management | 2006-10-13 | 1. The type B subprojects tended to be bigger and were supposed to have longer gestation periods, be more complicated and resource intensive. Communities did not necessarily participate in the decision to construct these subprojects. By and large, community groups considered type B subprojects to be local government activities, with no (or limited) sense of ownership accruing to the community. To encourage greater community participation, public hearings were encouraged to invite an open forum for discussion of type B subprojects. Unluckily, the public hearing concept was entertained only by about 50% of the participating local governments. It is believed that more widely applied public hearings would have benefited all stakeholders involved and would have assured wider community support for these subprojects. Unfortunately, public disclosure, transparency, and public accountability are rarely practiced in Indonesia; where such practices do exist, they are often jeopardized by the local bureaucracy, which considers them too expensive. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Project Design: Subprojects Capacity Development: Ownership Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation 2. Difficulties in defining the objectives of the public awareness campaign of the investment project led to it being launched only in 2003. Campaign activities included bulletins, leaflets, reports, a website, and videos. Public awareness campaign training was included in the training programs for facilitators. Some of these efforts were well intended and helped bridge the gap between the perceptions of local government and the communities. However, better public awareness campaigns could have encouraged local government officials to participate more in construction efforts, and encouraged core teams to work more closely with communities. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity building Country Context: Decentralization Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Delays and other problems with counterpart funding result to shortened actual implementation periods, and local governments are pressed to hurry through procurement and physical implementation of type B works. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design Project Management: Procurement Project Management: Project management Country Context: Decentralization From a control point of view, the PMO would have liked to execute approval authority over disbursements. However, the delegated project implementation arrangements did not give the PMO any role for approval. This remoteness of the PMO was questioned by the executing agency; on the other hand it does reflect the requirements of decentralization. Without proper fast-track reporting via the internet (or other means), the PMO could not possibly have acted as the approval authority for such a large number of subprojects, particularly the larger type B subprojects. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Project Management: Project reporting Country Context: Decentralization Many local governments hired new consultants for the second year of their subprojects. This often resulted in extraordinary delays and had adverse effects on implementation, in addition to causing the project management office (PMO) and project management consultant (PMC) to expend considerable effort keeping track of these changes and ensuring compliance with relevant project guidelines. project cycle stage: Implementation Lesson Topics: Project Design: Subprojects Project Management: Consultants Project Management: Procurement Project Management: Project administration Project Management: Project management Most villages are in need of additional, much larger investments in many subsectors. Many local communities felt that the cost ceilings for type A and B subprojects specified in the CLGSSDP were too low and not in accordance with the reality of construction costs. Government-defined ceilings on grants to villages meant that no village could receive grants for type A subprojects of more than Rp75 million ($8,823); individual type A subprojects were limited to half that amount, or Rp37.5 million ($4,411). Thus, many of the subprojects were very small-scale and had limited impact on village economies. Furthermore, it was often difficult for these communities to identify subprojects small enough to qualify for CLGSSDP funding. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Problem identification Project Design: Subprojects O&M did not receive enough attention. Most subprojects failed to provide funding for the O&M of subprojects, and did not take into account eventual replacement of major equipment or broken or worn parts. O&M training, which was planned too late under the investment project, was rarely implemented. In most districts and cities, the envisaged O&M subteams of the core teams did not function properly. These subteams were meant to establish O&M plans for all facilities. Very few subprojects are charging any user or maintenance fees to fund maintenance works and asset replacement. Despite the large potential of user associations in water and irrigation subprojects, none have been formed to date. Such associations could assume responsibility for collecting service charges and maintenance fees and regular maintenance. Nor have already existing market vendor associations taken on an active role in O&M. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Subprojects Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Civil Society Participation Technical assistance (TA 3179-INO) designed a number of training programs on participatory planning, monitoring, and evaluation (PPME) emphasizing participatory methods and role-playing. However, the training programs failed to cover project management and failed to ensure local governmentcommitment toward compliance with investment project guidelines. The training completely ignored sustainability issues and the concept of generating revenue to fund O&M. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity building Capacity Development: Ownership Methodologies/Approaches: Participatory approach There were only a few examples of misuse of funds involving a total amount of Rp689 million (approximately $81,000) - less than 1% of the ADB loan amount. The executing agency is actively pushing to correct all misuses of funds detected by BPKP (State Auditor), and the local governments concerned are expected to pay back the indicated amounts. project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Corruption Project Management: Executing/Implementing agencies | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/community-and-local-government-support-sector-development-program
Gas Transmission And Distribution Project | Indonesia | Energy | 2006-10-13 | 1. The project introduced a unique method for introducing private equity into a previously state-owned operation. The clear corporate governance structure and transparency in the State Gas Corporation's subsidiary company was cited as a model by the private sector minority shareholders. [Main text, para. 42, 58] project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Sector Related Issues: Private sector Policy & Reform: Privatization Policy & Reform: Reform 2. Land acquisition and right-of-way disputes are often a source of project delays. The State Gas Corporationmanaged social and environmental issues efficiently to minimize any such delays. The delay in project completion was caused by entirely external factors, primarily financial and economic. [Main text, paras. 49-56, 59] project cycle stage: Concept Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Project Design: Project design | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/gas-transmission-and-distribution-project-pcr
Capacity Building Project in the Water Resources Sector in Indonesia (Loan 1339-INO) | Indonesia | Agriculture, Natural Resources, and Rural Development | 2006-08-31 | 1. Capacity building projects (and technical assistance) need to be demand driven; hence, should only be considered when there is strong demand and commitment from senior management. Since institutional development is almost inevitably reported by managers as being a good thing it can be difficult to assess real attitudes and the reasons for and extent of any resistance to change. Evaluation noted there is no indication of where demand for the project originated, nor of commitment to its objectives by senior management. The traditional ADB mode of Project Design, with a project preparatory technical assistance followed by appraisal, may fail to fully identify the institutional stumbling blocks that are likely to be encountered. To reduce the risk of institutional failure, at minimum, a detailed institutional analysis should be conducted with major input from the institution itself, combined with (i) in-depth problem analysis allowing definition of the specific problems to be tackled by the project; and (ii) preparation of an improved project framework, including risk analysis, allowing links between outputs and outcomes to be clearly defined, and assumptions made explicit. [Main text, paras. 7, 55] project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Technical Assistance Project Design: Problem identification Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Institutional analysis Capacity Development: Ownership 2. For future major capacity building activities, a more measured approach such as designing a series of technical assistance (TAs), a TA cluster loan or a capacity development loan under ADB's new multi-tranche loan facility, needs to be considered to achieve better results. Institutional development projects are inherently difficult and long term in nature. The project s attempt to address a range of problems in many areas through a single 'big bang' project has not been the best way to achieve capacity building objectives. [Main text, paras. 8, 56] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Crosscutting Issues/Themes: Sustainability Modality: Lending modality Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development 3. Training programs must be timed to match trainee availability. Annual project budgets often did not become available until May or later, which caused training courses to be conducted during the second half of the year, when many public servants were busy completing their own programs before losing unspent budget allocations at year s end. While rollover of annual allocations is now permitted, it remains desirable to attempt to schedule training courses when the intended trainees are less busy. This may make it desirable for projects with substantial training needs to augment the national and local government training budget with technical assistance funds. This would assist in allowing courses to be scheduled at the optimal time. [Main text, paras. 40, 57] project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building 4. Where there is a lack of capacity or capability to operate equipment supplied on a sustainable basis, consideration should be given to (i) providing appropriate training to staff; (ii) providing adequate spare parts under the original contract; and (iii) writing service agreements with the supplying company, prepaid for the life of the equipment if necessary. Providing consumables from project budgets may not be desirable, as this prevents development of self-reliant systems and fosters dependency. The project's installation of high-tech equipment under the project was not successful given that almost all data loggers malfunctioned within 2 years of installation in most of the core provinces, computer networks and servers did not operate to specification or broke down, mobile laboratories were largely unused, and telemetry networks often failed to operate for various technical and financial reasons. [Main text, paras. 45, 59] project cycle stage: Implementation Lesson Topics: 5. New concepts, such as results-oriented management, must be carefully integrated with existing systems and built on existing strengths to ensure its effectiveness and sustainability. Results-oriented management was used to a limited degree (e.g., in planning hydrology programs) and not as an overall approach to incentive-based management. The initiative failed due to the inability of the project to integrate them into existing government systems, among others. Decentralization to the regions made it difficult to impose management systems on provinces and districts; while Indonesia s strict budgetary and control systems have the effect of supporting existing relationships and implementation systems. [Main text, para. 34, 60(i)] project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Project Design: Project design 6. There is a need to promote adequate resourcing of data collection and processing (e.g., hydrological and meteorological) among local stakeholders, such as governors, heads of districts and subdistricts, parliamentarians and public servants in related sectors. Systems should also be developed to make data available in convenient form to users, and to advertise availability. Hydrological and climatic data are of major importance for water resource management particularly for designing new water supplies, dams and irrigation schemes. However, its collection and publication are not prioritized by government agencies. Capacity has been deteriorating with the inability to maintain equipments and skilled staff. [Main text, paras. 50, 52, 60(ii)] project cycle stage: Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Data collection Policy & Reform: Information dissemination/Public awareness Classical training has limited application although on-the-job training of trainees may be more time consuming, expensive and require skilled delivery, it is generally more beneficial. project cycle stage: Feasibility Lesson Topics: Close monitoring and flexibility by the government and ADB are desirable for pilot or initial projects in a sector. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Methodologies/Approaches: Pilot project Project outputs that are seen to be relevant and in demand by management are far more likely to be sustained post-project than those seen as less directly relevant. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Ownership | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/capacity-building-project-water-resources-sector-indonesia-loan-1339-ino
Segara Anakan Conservation and Development Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2006-05-15 | 1. Closer monitoring of the likelihood of achieving the primary purpose is essential, especially for environmental time-sensitive projects. The project should have been fully reappraised after the lagoon had irreversibly shrunk almost twofold before major activities even started. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring &amp; Evaluation: Monitoring and evaluation Project Design: Appraisal ADB should have been more expeditious in investigating irregularities in procurement. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Project Management: Procurement Given the project's inherent environmental dimensions and objectives, all relevant agencies should have been actively involved in project processing and implementation. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Project management Methodologies/Approaches: Consultation/Participation Public consultation should have been more effective in addressing the objections to the Citanduy (river) diversion. project cycle stage: Implementation Lesson Topics: Sector Related Issues: Water resource management Policy &amp; Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/segara-anakan-conservation-and-development-project
Power Development and Efficiency Enhancement Project | Indonesia | Energy | 2006-04-14 | 1. The lowest tendered price is not always cost effective, given that there is a cost transfer to the executing agency associated with delays and additional monitoring or design and construction supervision of relatively inexpensive contractors. Contractors with low bids may attempt to minimize costs by relying on low-cost subcontractors. The executing agency needs to develop capacity for risk management to minimize delays related to the bidding procedure. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project supervision Project Management: Risks/Risk management Capacity Development: Capacity development Land acquisition and right-of-way disputes are a primary source of project delays. Problems encountered by the executing agency and the contractor in land acquisition affected the contractor's ability to progress with the foundation construction and conductor stringing. The combined causes of these problems were (i) the protracted period between initial executing agency negotiations with landowners and commencement of the work, (ii) the political and economic situations in Indonesia in late 1997 and 1998, and (iii) the executing agency's late clearance of the survey route. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Executing/Implementing agencies Project Management: Procurement | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-development-and-efficiency-enhancement-project
Capacity Building to Support Decentralization in Indonesia | Indonesia | Public Sector Management | 2005-12-31 | ADB's experience with decentralization interventions in Indonesia was limited at the time of approval of the four TAs. Closer cooperation with other development partners and the use of existing mechanims for interagency coordination to screen planned and ongoing support programs was desirable. project cycle stage: Design Lesson Topics: Decentralization, is a long term process involving a multitude of stakeholders requiring capacity building at the national and local levels, and a nationwide awareness campaign to generate ownership by national and local stakeholders and the public at large. Close coordination and consensus building among central government agencies, and between central and regional governments, are key prerequisites for ensuring that the decentralization process achieves its objectives. project cycle stage: Design Lesson Topics: Capacity Development: Capacity development Country Context: Decentralization Policy & Reform: Public sector reform Methodologies/Approaches: Consultation/Participation In times of institutional and administrative change, in-depth institutional analysis of the key government agencies and identification of the proper executing agency (EA) are preconditions for successful implementation. If unclear mandates exist, agreement is needed as to where the technical assistance is to be housed and how the various stakeholders will participate in implementation. If required, the EA will need to be changed if it loses its mandate. project cycle stage: Design Lesson Topics: Project Management: Executing/Implementing agencies Policy & Reform: Public sector reform Irrespective of the urgent need for assistance, interventions taking place during periods of rapid economic, political, and administrative transitions face the risk of becoming irrelevant and ineffective, with short-lived outputs and unsustainable outcomes. ADB needs to explicitly recognize such risks and to look at different assistance modalities, including phased series interventions and interacting more effectively with other development partners as a means of mitigating these risks. Stronger and longer supervision is also required. Resident missions are probably best placed to provide this role. project cycle stage: Design Lesson Topics: Modality: Lending modality Modality: Technical Assistance Other: Resident Mission Policy & Reform: Public sector reform Technical assistance supporting decentralization should be flexible, process oriented and well supervised. Adequate resources and time are essential for developing ownership by multiple stakeholders. Effective participation of regional stakeholders in developing policies and strategies is needed to achieve policy consensus and compliance. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Country Context: Decentralization | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/capacity-building-support-decentralization-indonesia
Country Assistance Program Evaluation for Indonesia (2005) | Indonesia |  | 2005-12-31 | Accurate targeting of poor households is not simple, especially in a crisis. Local officials distributing subsidized rice or allocating school fees during the Asian Financial Crisis understandably adopted rather rough and ready eligibility criteria, or just gave everyone who demanded assistance a share. This approach persisted even after the crisis. An external study on poverty targeting indicated that providing nonluxury simple goods for example, 25 30 watts of electricity or corn (not rice, which is a luxury good in parts of Java) would improve targeting. Self-targeting via employment also can be ineffective, as the wages are attractive to the nonpoor who become about 60% of the beneficiaries. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Country Context: Crisis/Post-crisis Methodologies/Approaches: Targeting ADB has a comparative advantage in providing loans for transport and communications, social infrastructure, and finance. Subject to the government indicating that these continue to be priorities for ADB assistance, ADB should continue to target support for these sectors. Performance in the agriculture sector, the sector with largest number of loans accounting for about 14% of the lending volume, has been weaker. ADB should continue to assist this sector only if the government strongly requests it to do so, and specific measures can be identified to improve performance. project cycle stage: Country Partnership Strategy Lesson Topics: ADB should develop synergies through geographic targeting. There are two fundamental advantages to reducing the geographical coverage. First, it would reduce the transaction costs and complexity of implementation and management of operations. Second, providing essential physical and social infrastructure in the same local governments where support has been provided for strategic priorities such as capacity building for governance would improve the potential for sustainability of outcomes. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Methodologies/Approaches: Targeting ADB should provide lending for project preparation. ADB should work with the government to reduce the payment of excessive commitment fees. This will involve developing a set of project-readiness filters and allowing sufficient time for project processing to ensure that loans are not submitted for Board consideration prematurely. In Indonesia's decentralized system, adequate project preparation time must be allowed for community participation, better coordination with all concerned agencies and levels of government, and detailed design to develop bidding documents. Since project preparatory technical assistance grant resources are inadequate for such detailed preparation, it would be useful to separate government borrowing into two stages after the preliminary work on feasibility and safeguard issues has been finalized. The first loan would be a small engineering-type loan to prepare detailed design and bidding documents (which would have normally been included together with the loan for project implementation) and for project supervision. The second loan would generate the project outputs. In this manner, the commitment fees for the larger loan could be deferred until the project-readiness criteria have been fully achieved. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Although Indonesia's environment and natural resources management (ENRM) policies and legislation are adequate on paper, implementation of regulations and enforcement of the laws is weak. Capacity development is needed to equip local officials to assume their new ENRM responsibility, and to identify and cultivate champions for sustainable development. Given the weaknesses in the judicial system and the lack of enforcement, voluntary compliance should be strengthened by applying low cost, community-based enforcement mechanisms that (i) publicize the presence of 'observers,' (ii) publicly identify violators, and (iii) provide incentives for local enforcement officials to act by tracking the outcome of prosecutions. To facilitate this effort, information about environmental mismanagement and its impact should be made public. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Capacity Development: Capacity development Policy & Reform: Information dissemination/Public awareness Careful deliberation is needed to bring crosscutting issues such as governance into the mainstream of project design and implementation, accompanied by required capacities to monitor performance and evaluate impacts adequately. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Capacity building Clear and cohesive administrative procedures are needed to facilitate investment. The financial allocation systems should be strengthened to provide incentives for local governments (LGs) to follow national policies and MSS. The ability of different LGs to absorb the changes will vary. Ways of passing loan and technical assistance funds to LGs will be required once the issue of LG borrowing and assignment of responsibilities has been resolved. If requested, ADB could support the government in this effort. The key to success is ensuring that the administrative processes developed are owned by the government. Successfully addressing this issue will be essential if the Country Strategy Program envisions substantial amounts of ADB lending to support LG projects. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financing Modality: Lending modality Capacity Development: Ownership Considerable data is available at the district level on human development indicators, as well as income and expenditure levels. Planners in the central Government (CG) and local Governments (LGs), working closely together, should use this information to allocate funds and determine poverty reduction programs. Most LGs have little idea where they stand relative to national indicators (i.e., educational enrollments and infant mortality). LGs should have these data to transform the implementation of poverty reduction from a top-down endeavor into a cooperative one. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Public governance Monitoring & Evaluation: Data collection Monitoring & Evaluation: Indicators Project Design: Appraisal Methodologies/Approaches: Consultation/Participation Corruption and collusion remain problems. Decentralization might have exacerbated these problems as individual government officials and the private sector might collude to deprive the government of revenues. Such perceptions damage confidence in local government institutions and policies. There are many competing ideas on how to address governance and corruption issues. Some argue that pressure from outside is needed to support change from within. Given the enormity of the challenge, ADB should discuss with the government an action plan where stakeholders, including external development partners, advocacy groups, and civil society can play a role including the Partnership for Governance Reform. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Capacity Development: Partnerships Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation During the participatory evaluation, local governments and community participants highlighted targeting problems, including the transparency and fairness of allocations. These varied by location, with the village head playing a central role. Better-off and more well-connected people usually benefit first from project initiatives. When resources are spread thinly, the better-off usually benefit disproportionately. To improve the targeting, communities suggested increasing the role of NGOs, as they were perceived to be impartial. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Civil society Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Public governance Project Design: Project design Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Targeting Economic growth and job creation are essential to reduce poverty. Good infrastructure is essential for efficient economic growth. Studies have established links among poverty, infrastructure, and growth. These studies confirm that infrastructure is a necessary, though not a sufficient, condition for poverty reduction. The indirect impact on poverty reduction should be an adequate justification for ADB infrastructure assistance, particularly for infrastructure located in areas with a high relative incidence of poverty, without making project design overly complex by including subcomponents that aim to reduce poverty directly. Such subcomponents increase the transaction costs of the main project. They might divert the attention of the executing agency to an agenda unfamiliar to them, thus resulting in poorer than expected project performance. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design For the poor, the opportunity cost of participating in project interventions might be high. Project benefits seldom penetrate deep into the substrata of the village, and usually accrue to village elites. At the district level, the poverty reduction objective of ADB projects is often not understood. Project benefits might be dispersed to all, or captured by those best placed to benefit. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Methodologies/Approaches: Targeting Governance should be mainstreamed in ADB operations. This broader approach will require, among other things, local governments and communities to get involved in project planning, participation in implementation, and monitoring outcomes. The policy agenda needed to attract private sector investment includes legal, regulatory, civil service, and anticorruption reforms. The key to success is strong government ownership ADB should identify areas where the government has indicated that it wishes to engage. To complement the technical work and to facilitate these difficult reforms, process-based approaches should be used to raise public awareness and mobilize support for fundamental reforms. Such process-based approaches require facilitation and negotiation skills, which are scarce among both ADB and government staff. project cycle stage: Design, Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Capacity Development: Ownership Sector Related Issues: Private sector Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy reforms/framework Methodologies/Approaches: Process approach Improving technical assistance (TA) products requires action in many areas including more strategic selection of topics to be supported by TA, increasing the ownership of TAs by executing agencies, improving ADB supervision, and the recruitment of better consultants. project cycle stage: Concept, Design, Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Ownership Projects were complex and geographically spread out. The executing agency's limited monitoring and supervision capacity was strained in implementing them. Inadequate project preparation and lack of resources limited the achievements of the project. Appraising one of many subprojects led to inaccurate demand projections, resulting in idle capacity and inaccurate knowledge about social, cultural, and institutional capacity of the local governments. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Capacity development Sector Related Issues: Urban sector/development Sanitation projects are difficult to promote. Health and education and demand management components need to be included as integral part of future sanitation projects. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development Some local governments mistakenly considered integrated urban development projects as providing physical infrastructure. The ADB projects should emphasize the balance between Capacity Development, physical infrastructure, and income-creating activities of the projects. project cycle stage: Feasibility Lesson Topics: The challenge in Asian Financial Crisis-affected countries was exiting from crisis management to implementing long-term development strategies. The passage of legislation has tended to be viewed as the fulfillment of an objective, giving insufficient weight to its follow-up application. ADB interventions need to better take account of this lesson when setting legislation as a policy condition. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Loan Agreement: Covenants Country Context: Crisis/Post-crisis Policy & Reform: Policy reforms/framework The limited budget and inadequate staff capacity in project management units led to lack of coordination and, in some cases, poor quality of works. Although it was agreed during project preparation that sufficient funds would be allocated for operation and maintenance, the funds allocated were well below levels needed to operate services effectively, causing a serious service delivery problems. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Operation and maintenance Sector Related Issues: Urban sector/development There is the need to develop simple and appropriate technology to distribute drinking water to low-income people in rural areas. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development Sector Related Issues: Water resource management Methodologies/Approaches: Targeting | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-indonesia-2005
Development of Madrasah Aliyahs Project | Indonesia | Education | 2005-12-15 | Although procurement irregularities were limited to a few locations, they attracted significant attention and impeded the implementation of similar components in other places. They created a negative perception of project performance among the concerned agencies, and limited the availability of government budget allocation to overcome the weaknesses. A better monitoring system could have helped prevent this. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Finance & Financial Aspects: Counterpart funds Monitoring & Evaluation: Monitoring and evaluation Project Management: Procurement As with previous education projects, the Assistance Scheme for Facilities Improvement (ASFI) demonstrated that communities can and will participate in monetary and nonmonetary terms if they feel that their contribution is adequately accepted and recognized. The ASFI worked particularly well in private Madrasah Aliyah (MAs or Senior Secondary School under the Ministry of Religious Affairs) as indicated by the higher-than-anticipated percentage of their counterpart share. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Education Sector Related Issues: Private sector Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Project preparation needs to address more thoroughly nontechnical aspects, such as the design and sustainability of human capacity investment, and how project outputs are to be integrated into existing organizational structures. The sustainability of human investment in the Ministry of Religious Affairs (MORA) depends on the success of the institutionalization process of the project within MORA at all levels, as well as the effective utilization of knowledge acquired through the project. Likewise, setting up new institutions, such as the Common Learning Resource Centers (CLRCs) and Madrasah Development Centers (MDCs), should not be discouraged. However, more thorough upfront analysis is needed regarding the readiness of the sector to embrace these institutions. Finally, project design should consider the diverse government structures at all levels in each sector, and reflect these in the project organization. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Education Qualified domestic consultants in education are scarce, which needs to be taken into account when designing consulting packages based on a combination of international and domestic specialists. Adequate attention needs to be paid to the composition of these packages and the selection process to get the right skills mix and avoid front-end delays. Early identification of domestic experts, preferably already during project preparation, and advance recruitment of these experts would also be beneficial. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Procurement Sector Related Issues: Education Setting up new organizations, especially independent or semi-autonomous ones, is relatively easy, However, making them sustainable is much more difficult. A thorough analysis of whether the existing environment is conducive to a new organization - and what type of organization that should be - followed by a formal recognition process during project implementation are necessary to ensure sustainability. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity development The implementation and disbursement schedules have to be more realistic. Major disbursements should not be expected in the first 2 years of implementation for these types of human resource development projects. Staff development is a time-consuming process, and needs to be sequenced and synchronized adequately with the procurement of educational materials and equipment to support training. The organizational change needed to absorb the additional staff capacity is equally timeconsuming. Thus, it must be thoroughly considered before implementation to ensure sustainability of the human capacity development provided. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Project design | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/development-madrasah-aliyahs-project
East Indonesia Airports Project | Indonesia | Transport | 2005-12-15 | A project can be completed successfully and within the budget, despite extremely adverse external conditions, as long as all participants do their best to overcome such problems. project cycle stage: Implementation Lesson Topics: Project Management: Project management Capacity Development: Ownership Country Context: Crisis/Post-crisis Methodologies/Approaches: Consultation/Participation By signing the Loan Agreement, the Borrower accepts ADB's Guidelines on Procurement. Nevertheless, if the Borrower does not understand these guidelines completely, ADB should provide proper training to avoid delays in procurement. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Loan Agreement Project Management: Procurement Capacity Development: Capacity building Safety and security are important elements of airport design/layout and operations. To ensure that security installations will be effective and efficient, a consultant must be employed to review and monitor the design and implementation of these installations. ADB should adopt a mechanism to prevent cancellation of these essential services, which are related directly to achieving the project objectives. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Consultants Sector Related Issues: Transport planning Security measures are less effective or even ineffective if public awareness is minimal and the operator does not enforce security strictly. Monitoring of the adherence to relevant procedures should become a standard element of ADB's follow-up. project cycle stage: Operation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Transport planning Policy & Reform: Information dissemination/Public awareness Since loan covenants sometimes relate to long-term issues, such as financial sustainability or maintenance of facilities, future interventions and dialogue should follow-up on these issues to provide incentives for the Borrower to comply with the covenants after project completion. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Loan Agreement: Covenants Project Design: Problem identification Project Management: Operation and maintenance Policy & Reform: Policy matrix To ensure sustainability, the operator will have to allocate larger budgets for maintenance personnel and equipment at each of the airports. Additional funds will have to be used to hire more maintenance personnel, and to provide proper training for new and ongoing training for existing personnel. These expenses must be allocated irrespective of the financial performance of the airports since maintenance has a direct impact on safety and security, which must not be compromised. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Transport planning When setting up a central project implementation unit (PIU) for a project with two physically separate sites, care must be taken to ensure that the PIU maintains firm control of overall management. project cycle stage: Design Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/east-indonesia-airports-project
Metropolitan Bogor | Indonesia |  | 2005-10-14 | Delays in ADB approvals are attributed to the late provision of supportive data and information by the executing agency or implementing agencies. Late approvals contributed to implementation delays. ADB and the executing agency did not establish a mechanism for mutual clarification of cases under dispute; ADB took unilateral decisions. Electronic data transfer and more direct communication with ADB and/or the resident mission could have enhanced communication and helped reduce approval time. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Data collection and management Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Management information system Other: Resident Mission Land acquisition problems frequently affected project implementation and caused delays, which could have been avoided with more foresight during project preparation. Despite ADB's repeated insistence on resettlement plans, neither the individual project implementation units (PIUs) nor the project management unit (PMU) submitted them. It seems that, despite flagging the absence of agreed resettlement plans, no further enforcement actions were taken by PIUs or the PMU. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Project Management: Project management Local and central government must adopt cost recovery and sustainability as guiding principles for infrastructure investments. Many governments still perceive infrastructureinvestments as a central government responsibility and there is a general lack of awareness about the financial and institutional sustainability of such investments. In terms of institutional strengthening, local governments need well-planned capacity building action plans related to project implementation management and O&M. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity building Country Context: Decentralization Policy & Reform: Information dissemination/Public awareness Private investors' behavior was strongly influenced by the absence of adequate and clear guidelines, regulatory frameworks, and standards. Where these were in place, the private sector was forthcoming but, in general, its role was much smaller than anticipated. The private sector is still not ready to invest in the water supply sector, except in the context of real estate developments where investment can be charged directly to customers. Private sector participation (PSP) promotional activities can only be successful if complementary activities (e.g., policy dialogue) and thedevelopment of regulatory framework are accomplished. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Sector Related Issues: Water resource management Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework The environmental impact assessment (EIA) was not used as a guide for environmental safeguards, which will impact subprojects' environmental sustainability. Environmental considerations were low on the priority list for service operators or facility owners. Inadequate procedures, inappropriate technologies, or environmental hazards were regularly discussed and documented during ADB PCR missions. However, few adjustments were made despite repeated reminders. EIAs need to be implemented in a more rigorous fashion with full involvement of local government environmental agencies (BAPEDAL). There was no defined institutional arrangement for subproject screening or executing agency review and approval - critical for this project, which is expected to appraise a huge number of subprojects covering different sectors/subsectors. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Sustainability Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Technology/Technology transfer Methodologies/Approaches: Consultation/Participation The introduction of regional autonomy had a strong influence on project implementation, especially the delayed allocation of local development funds. Staff rotation, particularly local project managers, resulted in lack of continuity, loss of experienced personnel, and delays. Subprojects that relied on inter-institutional cooperation faced many obstacles and bottlenecks. Staff rotation issues can only be solved if the executing agency has the political will to implement projects without major disruptions due to staff transfer. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Human resources management Country Context: Decentralization The late establishment of project management units (PMUs) and project implementation units (PIUs) affected project start-up. Delayed preparation of the subproject appraisal report (SPAR) document and detailed engineering design (DED) took much longer than expected and resulted in program revisions and fund reallocations. There was some inconsistency in defining realistic project targets, which could have been avoided with a more stringent project appraisal. Centralized and consultant-driven project monitoring did not sufficiently track all aspects of this multi-sector and multi-stakeholder project. While important adjustments (e.g., loan cancellations) were made, shortcomings in the field of institutional strengthening and revenue generation were never addressed. project cycle stage: Design Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Consultants Project Management: Project management Capacity Development: Capacity building Methodologies/Approaches: Targeting The shortage of adequate O&M funds will have a negative influence on the project lifeexpectancy and the sustainability of infrastructure investments. The effectiveness of O&Mcapacity building for service providers was limited, and local governments were unable toovercome internal adverse attitudes within their own ranks and were unwilling to increase theirown capacity. The covenants should have stressed more firmly the need for adequate O&Mfunding. Increased technical support for O&M needs to be considered as part of project design. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Country Context: Decentralization The supply of low quality machinery with an unreasonably short life span should have been prevented by proper quality specifications in the bidding documents. Tender documentsmust be more specific in terms of minimum quality standards. project cycle stage: Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/metropolitan-bogor
BAPEDAL Regional Network Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2005-09-15 | ADB and its consultants should be more thorough in preparing cost estimates, especially for non-standard types of projects.The project cost was substantially overestimated at appraisal, as evidenced by the 46% cost underun and the surplus loan proceeds of almost $20 million, or 44% of the original loan amount. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Management: Consultants Frequent replacement of project directors, managers, and staff negatively affected implementation. It appears that the Ministry of Environment (MOE) selected management staff based on technical expertise rather than project management experience. The technical tasks were numerous and time consuming, so they should have been performed with input from short-term specialists. Projects of this type should be headed by well-qualified experienced project managers, who dedicate most (if not all) of their time to management, with technical staff seconded as required. In addition, consultants should demonstrate a positive commitment to knowledge transfer to create a pool of skilled staff within the agency to lead future projects. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Human resources management Capacity Development: Technology/Technology transfer The environmental sector requires significant investment in regional human resources and institutional development. Organizational structure and the focus of regional offices should be clearly identified, strengthened, and evaluated prior to deciding which facilities should be installed. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Capacity Development: Capacity development Capacity Development: Human resources management When designing projects relying to a large extent on information technology, the requirement for modern and highly sophisticated technical equipment such as GIS and VSAT satellite network stations should be carefully assessed, given high O&M costs. Unless there are technical and financial means to upgrade the facilities to keep pace with technological developments, such equipment may become quickly outdated. In addition, databases that require technical as well as statistical input - physical features of maps for GIS overlays or demographics - are time consuming and costly to maintain. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Management information system Project Management: Operation and maintenance Capacity Development: Technology/Technology transfer | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/bapedal-regional-network-project
Sumatra Urban Development (Sector) Project | Indonesia |  | 2005-09-15 | ADB project administration needs to more rigorously dealwith design and implementation arrangements when they turn out to be problematic. This requires a mission team of diverse expertise, in particular for the mid-term review (MTR) to undertake significant redesign where necessary, or following any other event - in the case of Indonesia, the sudden decentralization - that significantly impacts project structures and outcomes. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project administration Project Management: Project supervision Capacity Development: Human resources management Country Context: Decentralization Geographic and subsector coverage should be limited, depending on the number of subproject appraisal reports (SPARs) that can realistically be prepared as part of project preparation, and the level of representativeness of conditions in these SPARs vis-ï¿½-vis other towns. This is particularly important for areas with large cultural diversity such as Sumatra. The subsectors covered should ideally have similar institutional setups and functioning to reduce project complexity during project preparation - which results in exponentially larger preparation time - and administration. The integration of diverse urban development subsectors requires a project team with distinct subsector expertise to allow for better understanding and differentiated treatment of these. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Design: Subprojects Capacity Development: Human resources management Sector Related Issues: Urban sector/development Institutional capabilities - both managerial and technical - of local governments and local government water supply enterprises (PDAMs) to manage, operate, and maintain their investments and provide decent public services require a realistic assessment during project and SPAR preparation, coupled with adequately tailored training and capacity building to tackle deficiencies encountered. The sustainability of investments depends on understanding the function of and demand for subsector services in the eyes of local government and the community. Sufficient time is necessary during preparation and implementation to involve these parties in the development of investments and to ensure that technical and institutional capabilities are adequate for their use and sustainability. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Capacity assessment Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Methodologies/Approaches: Community approach Subproject appraisal report (SPAR) preparation and review should be rigorous. It should rely on thorough demand analysis based on community consultations, and include a description of the condition and service coverage of existing assets. Technical solutions offered by SPARs should be specific for each situation. Requirements for financial and economic evaluation should be prepared carefully. Expertise in relevant disciplines should be made available during the preparation and review process. SPARs should be produced in the local language and English; and the English translations should extend to the main text and not be confined to executive summaries, to allow proper evaluation of the proposal. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Project evaluation Project Design: Appraisal Project Design: Project design Project Design: Subprojects Capacity Development: Human resources management Methodologies/Approaches: Community approach Substantial delays in consultant recruitment seriously undermine the effectiveness and sustainability of services provided. Adequate attention should be paid to this during project implementation to ensure that consultant recruitment is timely, and if it is not, that appropriate adjustments are made to the packages and the related terms of reference. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Consultants Project Management: Procurement Successful implementation arrangements of previous projects, including the degree of authority and enforcement control of the executing agency, should be thoroughly assessed before transferring them to new projects. What has worked reasonably well before in smaller, centralized projects may not work for large-scale sector projects under decentralization. Adequate provision for monitoring and ensuring compliance with loan covenants by local governments and local government water supply enterprises (PDAMs) should be incorporated in the project design and implementation arrangements. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Institutional analysis Country Context: Decentralization Sector Related Issues: Health and sanitation management The substantial increase in local procurement irregularities after decentralization was due to inadequate contract administration procedures in most PIUs; this included lack of proper archiving procedures, and no records of as-builtdrawings of civil works and contract variations. A combination of additional training, frequent monitoring, increased quality control by the executing agency, and rigorous enforcement of sanctions is necessary to address the PIUs' lack of capacity - and willingness - to strictly enforce procurement regulations. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Project Management: Project reporting Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Capacity building Country Context: Decentralization | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/sumatra-urban-development-sector-project
Capacity Building Project in the Water Resources Sector | Indonesia | Agriculture, Natural Resources, and Rural Development | 2005-08-15 | Early project implementation was delayed due to a number of factors including poor consultant performance. If quality assurance procedures, closely monitoring delivery of outputs from consulting services had been in place, better value for money may have been achieved. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Project Management: Project supervision New management systems (e.g., results-oriented management) should be carefully integrated to improve planning and management systems. Often, new techniquesare best used to enhance and develop existing practices. Poor translation of ï¿½newï¿½ ideas can cause suspicion and non-acceptance during project implementation. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Project Design: Project design Capacity Development: Technology/Technology transfer Project experience confirms a commonly held view that traditional classroom training has limited application; various forms of on-the-job training brought to the trainees, while more time-consuming and expensive, and requiring skilled delivery, is generally more beneficial and of better value. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity building Sector Related Issues: Education Project implementation, particularly coordination, was complex. A more focused, compartmentalized approach to project implementation with specific implementing units (within the executing agency) held responsible for delivering simple, measurable outputs/impacts might have helped avoid some delays in early project implementation. In addition, if consultations and the preparation of implementing units had been allocated more time in the project design phase, the executing agency might have been more ready. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Methodologies/Approaches: Consultation/Participation The ability of the project to adjust when challenged by external factors was important in increasing implementation efficiency. Close monitoring and flexibility by the government and ADB optimized the use of project resources. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration Project Management: Project management The project was designed before top-down decentralization took place. A closer understanding of the characteristics, strengths, and weaknesses of local government would have led to a more tailored approach to activity design and program distribution. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Country Context: Decentralization | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/capacity-building-project-water-resources-sector
Coral Reef Rehabilitation and Management Project | Indonesia |  | 2005-07-15 | A broader ecosystem-based (area-specific) approach to addressing coral reef and biodiversity conservation issues is more effective than narrowly focused interventions at an isolated coral reef site. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design A comprehensive field survey of the pilot sites must be completed during project preparation to establish clear baseline information and realistic project targets for future operation and replication. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Baseline data Project Design: Project design Methodologies/Approaches: Targeting An integrated approach that addresses both environmental and social concerns is more effective in coral reef management than activities aimed purely at conservation. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Methodologies/Approaches: Holistic approach Coral reef information and training center (CRITC) and monitoring, control, and surveillance (MCS) equipment and methods should be of the lowest practicable level of sophistication and cost, commensurate with their objectives; if expensive equipment is necessary, selection should be based primarily on ease of use and maintenance. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Natural resource management programs are more likely to succeed if regional governments and local communities are fully involved in planning, design, and implementation. Education and information campaigns are effective ways of increasing the awareness of the various stakeholders in coastal resource management and development, including coral reef management. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Program Project Design: Project design Country Context: Decentralization Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Private sector participation can augment the operations of small-scale coastal fisherfolk and give them better access to markets for their catch. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Market analysis Sector Related Issues: Private sector | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/coral-reef-rehabilitation-and-management-project
Second Junior Secondary Education Project | Indonesia | Education | 2005-07-15 | In response to demands that quantitative indicators be included in project designs, many specific output targets were specified. This was inconsistent with the major design thrust to respond to school priorities and requests. As projects move increasingly towards demand-driven, community-based approaches, the way in which targets are set currently as part of the project framework needs to be re-examined. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Indicators Project Design: Project design Sector Related Issues: Education Methodologies/Approaches: Community approach Methodologies/Approaches: Targeting The flexible, open approach adopted by the project successfully fostered a more holistic view to education development, changing the strong public-sector focus of district and provincial officials through the insistence on the inclusion of private schools and madrasah. The greatest success was with regard to private schools, as most districts now give them financial support. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Education Sector Related Issues: Private sector Methodologies/Approaches: Holistic approach Methodologies/Approaches: Process approach The project developed a new competency-based training program for teachers and principals, who appreciated the more focused training and reduced duplication. However, more training on implementation is needed, in addition to post-testing to ensure that all competencies have been mastered. The capacity development program for new district officials was a series of linked modules but a better option for this target group would be a series of seminars combined with ongoing guidance and support, closely related to concrete job tasks. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Education Methodologies/Approaches: Pilot project The use of school development plans as a basis for project interventions was generally successful, but it requires an enormous amount of resources to ensure that development plans are sufficiently analytical and truly reflect school and community needs. The project also made progress in the development of a district-based education management information system (EMIS). However, a successful EMIS strategy requires a high degree of commitment from local government officials including assigned staff, extensive training, simple software, and clear links to education planning and policy. project cycle stage: Feasibility Lesson Topics: Project Management: Management information system Capacity Development: Capacity building Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Education Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/second-junior-secondary-education-project
West Java Urban Development Sector Project | Indonesia |  | 2005-07-15 | Despite support from local and central governments, as well as ADB, most participating local government water enterprises (PDAMs) are in a poor financial condition and have excessive water losses. The low water tariff is one key reason. The PDAMs also are managed inefficiently by those without proper experience in the water industry. The dual function of PDAMs - social and commercial - also has increased the burden on their financial capacity. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial management Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Inadequate project preparation was one of the issues that prevented full achievement of project purpose. Partly because of the limited time for preparation of the subproject appraisal reports (SPARs), demand projections were inaccurate, resulting in idle capacity of some project facilities. The poor preparation of the SPARs also resulted in improper operation of the facilities. Inadequate representation of the diverse social, cultural, and institutional capacity of the participating local governments was another consequence of insufficient resources invested in project preparation. The appraisal of only one SPAR for this sector loan, as a representative sample of conditions in 20 cities, was unreasonable. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Modality: Lending modality Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Operation and maintenance Capacity Development: Capacity assessment Proper environmental controls on the operation of solid waste disposal sites and sanitation facilities are critical to the sustainability of operations, and are needed to preventunwanted environmental impacts on surrounding areas. In most cases, improper operation of the facilities and the absence of proper environmental controls are responsible for disputes with surrounding communities and their resistance to accepting their operations. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Proper tariffs and service charges to cover operation and maintenance (O&M) expenditures and new capital investments are crucial to the operation and sustainability of project components. Most local governments keep water tariffs low for political reasons. For solid waste management, the service charge is also low relative to O&M expenditure. An improper understanding of the nature of the service is partly responsible for this. In Indonesia, solid waste management is regarded as a public service. As such, the government is expected to subsidize the service as much as possible. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Project Management: Operation and maintenance Sector Related Issues: Health and sanitation management The institutional capacities of the participating local governments to manage, operate, and maintain their investments were overestimated. As a result, the project provided insufficient training. In addition, improper training in needs assessment produced a minimal impact on local government capacity. Intradepartmental transfer of staff limited further the effectiveness of the training. The local governments' lack of political will to implement the institutional development scheme provided under the project worsened the situation. The unimproved local government capacity indicated that the integrated urban development approach, which involves diverse cross-sector investment, might not be suitable for addressing governance issues at the local level. Specific initiatives focusing on the institutional development and capacity building might be more suitable. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Human resources management Country Context: Decentralization Sector Related Issues: Urban sector/development Methodologies/Approaches: Holistic approach The limited budget and inadequate staff capacity provided for the project management unit (PMU) and project implementation units (PIUs) prevented them from performing as expected. This resulted in a lack of coordination and, in some cases, poor quality of works. O&M of the completed works is a serious problem in all cities. During preparation, the participating local governments committed to providing the necessary funds. However, the funds allocated are well below the level needed to operate the services effectively, and to establish a reserve for future investments. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Operation and maintenance Project Management: Project management Capacity Development: Human resources management Country Context: Decentralization Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation The project was too complex and geographically large. It involved seven diverse components (in their institutional setup and functioning) and 20 cities (18 local authority areas). As such, monitoring and supervision strained the limited capacity of the executing agency. project cycle stage: Feasibility, Appraisal Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Capacity assessment To monitor and evaluate the benefits of built facilities under a project, a proper BME system needs to be established at the local and central levels. Timely recruitment of consultants responsible for producing and testing necessary indicators and procedures is very important. Adequate investment in the institutionalization of the system is also needed. Further, training for local and central government staff must be provided to ensure that BME is maintained after the consultants hand over the system. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Indicators Project Management: Consultants Capacity Development: Capacity building Country Context: Decentralization | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/west-java-urban-development-sector-project
Family Health and Nutrition Project | Indonesia | Health | 2005-06-15 | Ambitious project targets, especially with regard to behavior change of populations, require high levels of technical competence of the executing agency and implementing agencies, detailed planning, and continuous monitoring of interventions. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Capacity Development: Capacity development Methodologies/Approaches: Targeting Detailed implementation arrangements and coordinating mechanisms of executing and implementing agencies are critical to success and more attention should be paid to them in the project design. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation During project appraisal, a set of simple and concise indicators for data collection should be designed and agreed upon to make the Benefit Monitoring and Evaluation (BME) System operational at project inception and review missions should be rigorous in their pursuit of ensuring BME is maintained and updated. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Project Design: Appraisal Project Management: Management information system Project Management: Project supervision Ensuring access to basic health services for the poor means that projects need to identify strategies such as effective outreach programs which address high opportunity costs such as transport costs, time and income lost by attending consultations at health centers, etc. There is work to be done, beyond the interventions included in the project, in explicitly targeting measures to ensure accessibility to health services. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Sector Related Issues: Health and sanitation management Even in emergency situations, design of projects and programs impacting on the same sector should be coordinated so as to foster synergies and to clearly delineate responsibilities and consistent approaches to sector interventions. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Country Context: Emergency Methodologies/Approaches: Consultation/Participation In a changing project context, objectives, basic design, and assurances need to be maintained but activities and indicators should be adjusted to emerging needs to make the project more relevant, efficient, and effective. This requires systematic and regular assessment and effective response by review missions. project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project supervision Outsourcing services to NGOs requires commitment at all government levels and thorough assessment of their technical capacity building requirements and accountability mechanisms. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Ownership Methodologies/Approaches: Civil Society Participation Particularly in decentralization, the project management office (PMO) and project implementation units need to be integrated into an existing unit or department rather than established as stand-alone structures to maximize technical and administrative capacity for project implementation. project cycle stage: Design Lesson Topics: Project Management: Project management Country Context: Decentralization Poverty target mechanisms need to be based on clear and consistent indicators, which are accessible and useful for decision-makers. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Indicators Project Management: Management information system Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/family-health-and-nutrition-project
Health and Nutrition Sector Development Program | Indonesia |  | 2005-06-15 | ADB and the government are capable of developing an effective large-scale emergency package in a timely manner. However, strong leadership and support from the government are required. The Health and Nutrition Sector Development Program was based on the simple idea of delivering funds directly to targeted groups, but the task of identifying beneficiaries was considerably more difficult than expected. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity development Capacity Development: Ownership Country Context: Emergency Methodologies/Approaches: Targeting Circumvention of a conventional funds flow mechanism that is slow and subject to leaks is possible, allowing the disbursement of funds directly to beneficiaries and providers of basic social services for vulnerable groups. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Vulnerable groups Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing From the outset, the Health and Nutrition Sector Development Program (HNSDP) lacked effective capacity development of staff to undertake their new responsibilities. Under the centralized system, staff were not used to making decisions. The budget for training staff on HNSDP procedures arrived late in some districts, and some community health centers started their activities before receiving any guidelines or training. The impact was significant. The distribution of block grants to health centers was delayed significantly, because managers did not feel comfortable disbursing the funds. Evaluation studies also confirmed that members of village and district committees did not comprehend completely the principals of the HNSDP. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Modality: Program Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity development Sector Related Issues: Health and sanitation management The government made a commitment to a set of policy reforms that were needed in support of decentralized service delivery and which reinforced the project loan interventions and strengthened the impact of the Health and Nutrition Sector Development Program. Although introduced as short-term assistance, the reforms in the policy matrix were a necessary part of the package. The program loan supported the initiation of nationwide sustainable policy reforms to ensure the inclusion of and equity access of the poor in key health services, and enhanced decentralized management to improve the efficiency of social services delivery. This has proved relevant after the crisis as well, as the government faces challenges in maintaining and improving the quality of health and nutrition services under decentralization. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Modality: Program Project Management: Operation and maintenance Country Context: Decentralization Country Context: Emergency Sector Related Issues: Health and sanitation management Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/health-and-nutrition-sector-development-program
Smallholder Tree Crop Processing Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2005-06-15 | Credit operations should have been professionally managed, preferably by a financial institution. The incentives for early or timely repayment or collection of fees should have been paid at the time and point of collection. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project preparation should be thorough and foresee the changes unfolding in the economy or sector. While it is not possible to fully predict the changes, the project design and implementation should be flexible and management shouldproactively address these changes during implementation. The input-output and output-outcome linkages should be carefully established, and the risks identified and mitigated. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Project management Project Management: Risks/Risk management The project aimed to change marketing regimes but lacked the inputs to do so. Farmer empowerment and organization of farmers' groups into cooperatives should have been emphasized. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Capacity development The terms and conditions of cofinancing should have been agreed on between the government and the cofinancier before ADB approval. The loan products should have been examined to ensure that they were appropriate for the interventions and cost-effective. project cycle stage: Appraisal Lesson Topics: Modality: Lending modality Project Design: Appraisal While the country has excess capacity for rubber processing, some regions may need additional processing units. However, expansion of processing units should be carefully considered, as smaller units may have high processing costs and may not be competitive in an export-dominated market. The smaller units may not have outputs sizable enough to attract the foreign buyers that dominate the market. In light of the excess capacity, projects to process rubber or other tree crops should consider input supply potential and economies of scale in deciding on the regional need for additional factories. project cycle stage: Feasibility Operation Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/smallholder-tree-crop-processing-project
Regional Development Account Project | Indonesia | Multisector | 2005-04-15 | A supporting legal framework should be in place before implementation or should be established during the early stages of project implementation. Project success and sustainability becomes difficult without enabling laws and regulatory mechanisms. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Project Design: Project design Policy & Reform: Policy reforms/framework Capacity building and institutional strengthening of executing agencies and other stakeholders are keys for success, which require more attention in the project design. Ideally, capacity building activities should precede the actualimplementation of sub-projects. ADB should provide more assistance in helping executing agencies to comply with ADB procedures and procurement regulations on a continuing basis. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building For sustainability reasons, only financially viable projects with clearly defined revenue streams and cost recovery mechanisms should be selected. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Revolving funds such as the Regional Development Account (RDA) may be difficult to manage by the government, given political sensitivities and the limited capacity in required technical, monitoring, and banking skills within regulatory agencies. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Rigorous appraisal, monitoring, and recovery mechanisms must be in place before disbursement. Budgets for site visits and reviews must be made available by the executing agency as part of government counterpart contribution. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Management: Executing/Implementing agencies Strong and continuing ownership of the government is required for successful implementation. The basic design, assurances, and project objectives need to be maintained during implementation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Loan Agreement: Covenants Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/regional-development-account-project
Higher Education Project in Indonesia (Loan 1253-INO) | Indonesia | Education | 2005-01-31 | For any employment-related project, key private enterprises should be involved at the design phase to ensure that the skills being taught are relevant to the market demand, and at the implementation phase to gain their support throughout the project. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Private sector Sector Related Issues: Public-private partnership The Benefit Monitoring and Evaluation (BME) system should be integrated into normal operations of project institutions. It should also be linked to the institution's management and information system. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Management information system Capacity Development: Capacity development The project institutions should be required to prepare annual preventive operations and maintenance (O&M) plans in accordance with manufacturers recommendations and to allocate sufficient annual recurrent budget for O&M activities. project cycle stage: Implementation, Operation Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/higher-education-project-indonesia-loan-1253-ino
Farmer Managed Irrigation Systems Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2005-01-14 | As a matter of principle, farmers should be required to contribute to construction costs and that this requirement should be clearly stated at the outset and applied as a precondition for the selection of subprojects. During implementation, the requirement for farmers to agree to a 20% contribution for the cost of the irrigation improvements was relaxed, and the farmers' contributions were less. Consequently, the project paid for a greater share of the costs than originally planned. However, the farmers provided in-kind and voluntary labor support, which increased their ownership of the project. The value of the farmers' contribution cannot be estimated accurately because clear records were not kept, but, in many cases, the contribution was significant, and most farmers' groups were willing to contribute in some way. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Design: Subprojects Capacity Development: Ownership Sector Related Issues: Irrigation management Coordination between interagency working groups at the district and provincial levels, with DWRS and PIPO, on the one hand, and DAS and agricultural extension agencies, on the other, would have been more efficient if the latter had been allocated funds directly from the Borrower (MOF) and received the funds provided by the executing agency (DGWR) in 2002. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Extension service Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation Farmers are constrained by a lack of capital from investing in agriculture activities and technical improvements. Provision of credit not subsidized as part of the project might have assisted farmers in fully realizing the irrigation potential of rehabilitated and improved farmer managed irrigation systems (FMISs). project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Irrigation management Generally, the quality of construction work undertaken by the farmers is better than works that are built by contractors. This is so because the farmers have a better appreciation of the value of properly constructed works, and participation in design and construction gives farmers a sense of pride and ownership. However, in some cases, particularly in more remote locations, the supervision of the works by district staff members was lacking, and some construction problems occurred. Assigning more district staff members to supervise schemes in such remote locations would be beneficial. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project management Project Management: Project supervision Capacity Development: Ownership Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation The Benefit Monitoring and Evaluation (BME) surveys showed that the involvement of women farmers in the project was limited to agricultural activities and that their involvement in water users associations (WUAs) organization and the management of irrigation was minimal. Special attention and assistance to support the role of women in the administration and management of WUAs is required to increase their involvement. Similar types of projects, those that are small-scale and directly benefit farmers and poor rural communities, are frequently presented by district governments to development partners, including ADB, with requests for assistance. The participatory process developed by the project is very relevant and could be replicated and expanded to other areas. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Gender Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach The comprehensive Benefit Monitoring and Evaluation (BME) surveys undertaken under the project gathered data on irrigation structures, water supply, and maintenance activities, as well as physical conditions and cropping intensity; irrigated area; agricultural production; and other benefits, such as the increase in agricultural employment. Although the goal was to reduce rural poverty, the surveys did not capture relevant data such as income distribution among the beneficiaries before and after the project. This deficiency makes accessing the poverty impact in quantitative terms difficult. project cycle stage: Feasibility Operation Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Project Management: Operation and maintenance Crosscutting Issues/Themes: Employment Sector Related Issues: Irrigation management Sector Related Issues: Rural development Sector Related Issues: Water resource management The project design envisaged that the District Agricultural Services (DAS) would be closely involved in providing support to farmers through extension services and establishing demonstration plots. However, levels of involvement of the field agricultural extension workers and support from DAS were low, particularly after decentralization in 2001. DAS and agricultural extension agencies were funded and controlled by district administration, and sufficient funds were not made available for the agricultural extension services needed to provide the planned level of support. The project would have benefited from specific and adequate funding for agricultural extension services. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Country Context: Decentralization Sector Related Issues: Extension service Water users associations (WUAs) need ongoing support beyond the project to facilitate their development into viable and responsible organizations that are committed to organizing and collecting sufficient water users fees for routine O&M, to ensure sustainability. Further assistance for strengthening WUA capacity and management is necessary. Badan Perencanaan Pembangunan Daerahor BAPPEDA II (Regional Development Planning Agency) should provide assistance for such strengthening, including ongoing monitoring and support. These arrangements can likely be implemented under the decentralization policy, which allows district governments to play a key role in providing a conducive environment and support and services to newly empowered WUAs. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Capacity Development: Capacity development Country Context: Decentralization Sector Related Issues: Irrigation management Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/farmer-managed-irrigation-systems-project
Microcredit Project | Indonesia | Finance | 2005-01-14 | Bank Perkreditan Rakyat (BPRs or village banks) can benefit from continued assistance. BPRs are well suited to microfinance because the average loan size of most BPRs is below 150% of GNP per capita. BPRs are confined geographically and cannot easily expand deposit-taking activities to expand loans. They cannot move up market because of competition from larger financial institutions (such as commercial banks), legal lending limits, and funding constraints that limit lending outreach. They are, however, well positioned to move down market. BPRs' competitive advantage is in their closeness and attentiveness to their customers, who are generally individuals, microenterprises, and small businesses. BPRs, however, often lack the desire or the funds to invest in computer systems and software, and they have no easy way to link with the payments system or wider payment networks. Negative implications for asset/loan portfolio diversification is that in some cases they are not well equipped to design new products that might facilitate moving down market to serve poorer clients with smaller loans. BPRs need to develop appropriate new products, diversify and better manage asset and loan portfolio risk, and improve their information technology. External interventions targeting BPRs might consider creating more formal linkages of BPRs and commercial banks - where a marketing/product channelingsymbiosis is likely - and strengthening of supporting institutions that help BPRs enhance their competitiveness or reduce their risks by providing treasury management services. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Management information system Capacity Development: Capacity assessment Capacity Development: Capacity building Sector Related Issues: Rural development Commercial microfinance has arrived in the country, highlighting new possibilities for private-sector operations. The project demonstrates that with the proper oversight, a portfolio of loans to Bank Perkreditan Rakyat (BPRs or village banks) - established, profitable, well-capitalized businesses - can carry low risk and earn a commercial yield. At the very least, it is possible to reduce the scope of public-sector activity in future microfinance projects/loans. Future ADB funding should further catalyze private-sector participation in microfinance, meaning that ADB funds should be leveraged with private funding. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Reform Expansion of microfinance activity does not necessarily contribute to creation of new wage earning jobs. With access to loans, a microentrepreneur can spend more time developing her/his business, and perhaps support the participation of additional family members in the business. The impact of microfinance on employment is mainly indirect, therefore, and the most significant impact of microfinance can expected to be on family incomes. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Impact evaluation Crosscutting Issues/Themes: Employment Methodologies/Approaches: Consultation/Participation If challenged, and with access to effective technical assistance, many financial institutions can move down market and adopt new methods of reaching poorer clients. The key factors were the fact that (i) the small financial institutions (SFIs) set their own interest rates to charge clients; and (ii) the project did not limit lending to a certain sector, only a certain size. Maximum loan sizes were attractive mainly to poorer clients, and also helped serve large numbers of microenterprises run by poor and near-poor women because they matched the size of their businesses. Client selection is the microfinance's business and should not be interfered with by any project or agency. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Methodologies/Approaches: Targeting In most cases, small financial institutions (SFIs) were allowed to borrow no more than 5% of their overall funding. The project created no dependency on the part of SFIs; BPRs (village banks)needed to continue gathering funds in the form of savings and time deposits from traditional customers. Sustainability of microfinance depends upon microfinance institutions' (MFIs') ability to attract and retain readily available commercial sources of funding. Credit line availability should be strictly limited so as not to create dependence on the part of the MFI. The success of a credit line intervention might best be measured in lending outreach to new borrowers combined with a substantial increase in the amount of local funding gathered by the MFI. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Monitoring & Evaluation: Impact evaluation Sector Related Issues: Private sector Sector Related Issues: Rural development Since incomes are subject to various unquantifiable externalities, success or failure of microfinance is best measured by outreach and financial sustainability. Loan size can serve as a useful proxy for depth of outreach to poor clients. It is important to gather survey data related to poverty and incomes of project participants. It is necessary to understand poverty in all its dimensions - not simply in terms of income - so well-designed social impact surveys should rightfully be incorporated into microfinance projects. Still, an increase or decrease in income by participating microenterprises should not be considered the central indicator of success of a microfinance project. There is solid evidence to suggest that a well-designed microfinance intervention will benefit those who were hitherto denied access to affordable financial services. Project frameworks should elevate sustainable financial deepening to the outcome or impact level. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Project Design: Project design There is a natural limit to how far down market small financial institutions (SFIs) can go with lending without (i) increasing operating expenses to such a point that the lending business is no longer attractive, or (ii) finding insufficient demand for such small loan amounts. This level will be different for each SFI. There was friction between ADB, the executing agency (Bank of Indonesia), and the SFIs during the project over the maximum initial loan size; the project performed a constant and difficult balancing act to push downward the frontiers of microcredit while keeping the SFIs interested in exploring those frontiers. Microfinance projects should determine a range for commercial microlending, challenge SFIs to move down market, provide proven new methodologies to assist SFIs to move down market, and allow SFIs some leverage to push back from the bottom end of the range to ensure commercial sustainability. The project demonstrates that ADB can successfully expand the frontiers of microfinance. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Executing/Implementing agencies Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/microcredit-project
Rural Water Supply and Sanitation Sector Project in Indonesia (Loan 1352-INO) | Indonesia | Water and Other Urban Infrastructure and Services | 2004-12-31 | A sector modality should be avoided or the sector project should be kept small in cases where a new approach to project implementation is being adopted, as Executing Agency and the Implementing Agency competence is unlikely to be at the required level. project cycle stage: Feasibility Lesson Topics: Modality: Lending modality Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment A single agency project management unit is limited in its authority over other agencies. Separate project management units in each Executing Agency and Implementing Agency pose coordination challenges. In projects requiring coordination from many different government departments, the central project management unit should preferably include seconded staff from all departments involved. project cycle stage: Design Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Human resources management Care should be taken in the adoption of standard designs as the circumstances at each community are unique. While it is reasonable to adopt standard sizes for e.g., public hydrants and water treatment plants to save on design and construction costs, it is not appropriate to adopt a standard depth for either shallow or deep wells as these take no account of the actual hydrogeological conditions that exist. project cycle stage: Design Lesson Topics: For projects requiring inputs from different agencies in a well-defined sequence, critical path analysis is required, and fund allocation should be made to follow the critical path. project cycle stage: Design, Implementation Lesson Topics: For projects with a clear intention to address poverty in rural areas, use of funds for water supply and sanitation facilities should follow covenanted thresholds for different sizes of communities. project cycle stage: Implementation Lesson Topics: Future ADB projects in the Water Supply and Sanitation (WSS) sector should not combine target groups that require different operational modalities. project cycle stage: Feasibility Lesson Topics: Methodologies/Approaches: Community approach Methodologies/Approaches: Targeting However, the regional water enterprise needs to be fully involved in design and implementation, and fully responsible for operation and maintenance. Community-managed schemes should be limited to the more simplified technologies that preferably depend on high-quality reliable sources and gravity distribution. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Capacity Development: Technology/Technology transfer Proper assessment of the implementation capacity of the government at all its levels national, provincial, and district is required before embarking on projects. Major changes in the project context (such as those stemming from decentralization) need to lead to adjustments in implementation arrangements. project cycle stage: Design Lesson Topics: Capacity Development: Capacity assessment Country Context: Decentralization Some technical lessons for WSS projects that need to be taken into account when designing similar projects in the future are (i) lowland villages need a different approach from highland villages both in technical and social mobilization terms; (ii) PDAM schemes need a different approach from community-managed schemes; (iii) systems based on pumps/treatment plants need to be avoided in small communities and, if unavoidable, need extra attention; (iv) special attention needs to be given to ethnic and cultural differences between areas in the approach, as some communities need more focus in terms of health and hygiene education, and mobilization; (v) willingness of the community to utilize public hydrants should be fully researched; (vi) house connection-based systems need to be offered, based on the principle of recovery of investment and operational costs by the beneficiaries; (vii) pour-flush sanitation systems should not be provided without a suitable water supply; and (viii) school toilets with a connecting water supply have a higher chance of success than public toilets/wash areas. project cycle stage: Design Lesson Topics: Project Design: Project design Country Context: Cultural constraints When rural communities do not express a clear demand for such services, are not part of the design and implementation process, are not trained, and are not willing to pay for a major part of the investment and recurrent operational costs, then efforts are likely to fail. Appropriate organizations need to be built up and strengthened before, or alongside, project implementation. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Operation and maintenance Capacity Development: Ownership | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/rural-water-supply-and-sanitation-sector-project-indonesia-loan-1352-ino
Second Development Finance Project in Indonesia (Loan 1223-INO) | Indonesia | Finance | 2004-12-31 | ADB needs to come out with a pragmatic solution for the purpose of developing an efficient and effective monitoring and evaluation framework of a Development Financial Institution (DFI) loan (data collection from subborrowers) - that balances to increased administrative costs with the need for, and use of, the data collected. Possibilities are (i) to specify the required data and timing of data collection in a loan/project agreement, and (ii) the benefits of a project are to be monitored and evaluated by an oversight implementing bank based on sample subprojects. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Loan Agreement Monitoring & Evaluation: Data collection Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects ADB's reputation and credibility would be damaged if it lends money to institutions where weak governance could lend itself to systemic risk of corruption. ADB must develop more stringent assessment procedures to avoid becoming involved in such institutions and continue to address governance issues regarding banks and corruption in conjunction with ongoing operations. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing At appraisal of a development finance institution (DFI) loan, a demand assessment should be accompanied by a thorough review of market interest rates in the local currency, interest rates and exchange rate volatility, banks' liquidity conditions, and the extent of currency and maturity mismatches on banks' balance sheets. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financial management Finance & Financial Aspects: Foreign exchange Finance & Financial Aspects: Local currency Finance & Financial Aspects: Market analysis Project Design: Appraisal If a local currency is pegged to a hard currency (at appraisal of a development finance institution loan), the increased volatility of the interest rate for a local currency loan, as well as a change in the risk profile of an FX loan if the peg is abandoned, should be recognized as risk factors. In such an event, ADB and the concerned government should consider adjusting lending and relending terms to maximize project benefits while reducing risks. Cancellation and/or prepayment of a loan would be also a possible option, if desirable. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Finance & Financial Aspects: Foreign exchange Finance & Financial Aspects: Local currency Project Design: Appraisal Project Management: Risks/Risk management Relending agreements between a government and Participating Financial Institutions (PFIs) under a Development Finance Institution (DFI) loan should include a prepayment clause similar to the one in a loan agreement between a government and ADB. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Loan Agreement Loan Agreement: Relending Agreements When considering financial covenants for Participating Financial Institutions (PFIs) under a DFI loan, the central bank sprudential regulations (including those on loan concentration, intra-group lending, and asset-liability management) and their enforcement status, and PFIs corporate governance and risk management systems should be examined thoroughly. Based on this examination, financial covenants should be included that complement PFIs' risk management and prudential guidelines. Compliance with financial covenants should be monitored regularly and treated as a condition for ADB's approval or confirmation of subloans. In this way, an enforcement mechanism for financial covenants of a DFI loan can be created. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Risks/Risk management | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-development-finance-project-indonesia-loan-1223-ino
Eastern Islands Urban Development Sector Project in Indonesia (Loan 1292-INO) | Indonesia |  | 2004-09-30 | A sector approach for intervention in the urban sector may be a more appropriate modality when decentralization is associated with adequate capacity at the local level. project cycle stage: Feasibility Lesson Topics: Modality: Lending modality Project Design: Project design Country Context: Decentralization Sector Related Issues: Urban sector/development Decentralization leading to greater local government decision making and a strong focus on community involvement is the most appropriate method to ensure ownership of a project. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Ownership Country Context: Decentralization Methodologies/Approaches: Community approach Inadequate local government capacity in remote areas can act as a serious impediment to the collection of timely and accurate data. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Data collection Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity assessment Capacity Development: Capacity building The centralized, uniform approach taken under the project failed to recognize that local government capacity was variable in the selected towns and particularly limited in the Eastern Islands. A more phased approach toward local autonomy, combined with an extensive program of capacity building and training to those weaker authorities would have been more advisable. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity assessment Capacity Development: Capacity building Country Context: Decentralization The tendency toward intradepartment transfers of staff members within local government agencies limits the effectiveness of training programs. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Human resources management | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/eastern-islands-urban-development-sector-project-indonesia-loan-1292-ino
North Java Road Improvement Project | Indonesia | Transport | 2004-09-15 | Land acquisition objectives should be realistic and funds should be available in advance of construction to finalize procurement. Contracts should not be awarded until land acquisition is complete and the land available for construction. The project was designed prior to adoption of the ADB Involuntary Resettlement. This is now mandatory for all ADB projects. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Financing Project Design: Project design Project Management: Procurement Project designs should be complete and ready for execution. The benefits over the simplified design previously used are reduced construction time, and minimized extra costs and variations due to design reviews once the contract is awarded. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Procurement Roads in Indonesia and especially the route of the North Java Pantura are subject to serious overloading. Axle-load regulations should be better enforced and design standards increased. Lessons learned on overloading and pavement design should be included in any policy dialogue with government for future road projects. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Roading Policy & Reform: Policy matrix Timely maintenance helps realize the life expectancy of the road. Under the Road Rehabilitation Project (RRP), maintenance costs issues were addressed through a specific project assurance. The proposed RRP2 includes a component on strengthening of road maintenance management. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Roading To ensure achievement and sustainability of the project benefits, the executing agency should undertake benefit monitoring and evaluation, in formats and procedures agreed to by ADB, within four years after project completion. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Executing/Implementing agencies When evaluating loan surplus for possible partial loan cancellation, sufficient contingency funds should remain to cover future price adjustment and design change without having to reduce the project scope. Revision of project scope should be based on revised project costs and updated financing plans. To address weak financial management by the executing agency, a financial management specialist was engaged under the ongoing RRO. However ADB staff should also be proactive in supporting the executing agency's financial management of the project. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/north-java-road-improvement-project
Sulawesi Rainfed Agriculture Development Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2004-08-13 | The assistance for tree crops was expected to be provided over 1 year only. For tree crops that have a long gestation period, a need exists to build in some flexibility in spreading out this assistance over a longer period, without changing the quantum of assistance, since some poor participating farmers do not have adequate resources to purchase fertilizers and other inputs. The financing plan for the first year needs to focus on the provision of required inputs, such as fertilizer for subsequent years, rather than just providing cash to farmers. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Rural development The integrated approach envisaged at appraisal recognized the need to combine crops with livestock in farming systems for rain-fed upland areas. The organic manure from livestock is essential in improving the soil structure and fertility of sloping lands. However, the lack of adequate funding for the livestock component indirectly affected crop productivity and soil conservation in the earlier years of project implementation. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financing Project Design: Appraisal Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach With the introduction of participatory rural appraisal (PRA), farmers proposed additional crops that were not envisaged at appraisal, such as candlenut, cocoa, and pepper. Funding for these new crops was considerably delayed, especially funding for pepper, as a feasibility study was required to support its inclusion in the project scope and justify ADB's financial assistance. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/sulawesi-rainfed-agriculture-development-project
Bogor and Palembang Urban Development Project in Indonesia (Loan 1111-INO) | Indonesia |  | 2004-07-31 | A land acquisition plan, environmental assessment plan, or plan to involve the community should be available in the project preparation stage. ADB accounts this in its resettlement and environment policies, and by giving greater emphasis on community participation in project preparation and implementation. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Resettlement Project Design: Project design Sector Related Issues: Land-sharing system Methodologies/Approaches: Consultation/Participation A more participatory approach toward the location of final disposal sites, involving communities and other stakeholders, would have prevented problems, such as local residents forcing closure. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Methodologies/Approaches: Participatory approach Providing expensive foreign funding for small items with limited life spans, such as handcarts and container bins, is not the most effective use of funds. Such items may be part of the project financed from local sources. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Solid waste dumpsites designed without proper environmental controls will have longterm negative impacts on the surrounding areas. Appropriate environmental safeguards need to be put in place as a component of future interventions. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management The operation and maintenance of the pilot wastewater system would have been better placed under the local water enterprise, so that charges for water and sewerage could have been levied by the same agency. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial management Project Management: Operation and maintenance Sector Related Issues: Water resource management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/bogor-and-palembang-urban-development-project-indonesia-loan-1111-ino
Financial Governance Reforms: Sector Development Program | Indonesia |  | 2004-07-15 | Accurate diagnosis is also essential to keeping the scope of the program focused and manageable and ensuring there is sufficient balance between breadth and depth to achieve meaningful results. It is further important for program design and choice of focus to reflect an appreciation of institutional requirements and constraints in implementing reforms. This relates not only to the capacity of individual implementing agencies; but also interagency coordination requirements for particular policy actions supported by the program (e.g. Ministry of Finance and Ministry of Justice in preparation of anti-money laundering legislation). In the case of Indonesia, interagency coordination requirements were further complicated by ongoing institutional and political upheavals. The highly-compressed timeframe for consultation and program formulation dictated by the crisis also meant that not all implementing agencies were closely involved in the initial policy dialogue and negotiation process and as a result, in some cases, ownership of covenants and commitment to compliance was weak - adding to difficulties in interagency coordination and program implementation. project cycle stage: Design, Feasibility Lesson Topics: Loan Agreement: Covenants Modality: Program Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Capacity development Capacity Development: Ownership Country Context: Crisis/Post-crisis Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation Although legislative action is often unavoidable in policy-based lending, it presents an important source of uncertainty in program implementation as it is difficult to estimate the timing and outcome (i.e. final form of proposed legislation) of the legislative process in governments where the legislative branch is effectively independent of the executive. Notably, in the case of the Financial Governance Reforms: Sector Development Program (FGRSDP), where the legislature had transformed itself from a rubber stamp of the executive to an assertively independent branch of government over the course of program implementation, the significant delay in third tranche release was related to conditions requiring legislative action. Moreover, while sound legal and regulatory frameworks are important to underpin sound financial governance, these also depend on a range of institutions to support their effective implementation. In Indonesia a key weakness in this implementation chain continues to be the judicial system. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Disbursement Loan Agreement: Covenants Modality: Policy-based lending Project Management: Risks/Risk management Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Care should be taken in using crises as 'windows of opportunities' for change. A crisis generally creates conditions for change, and an opportunity to introduce needed reforms. However, unless the necessary support is in place or can be built up, when the crisis recedes so may the reforms. In Indonesia's case, close policy dialogue supported by the program and recognition by the government of the fundamental relevance and importance of the reforms to Indonesia's sustained recovery have helped to ensure strong ownership and ongoing government commitment beyond the program as evidenced by the White Paper and the government's timely progress on meeting its commitments under it. project cycle stage: Feasibility Lesson Topics: Modality: Program Capacity Development: Capacity building Capacity Development: Ownership Country Context: Crisis/Post-crisis Policy & Reform: Policy matrix Policy & Reform: Reform Coordination with IMF and World Bank was challenging at both the design and implementation stage. There were initial differences on policy issues that impacted the timing of program approval as well as weaknesses in inter-IFI communication and information sharing. A working partnership, however, evolved facilitated by an effective division of labor in the financial sector where IMF focused on issues facing BI, World Bank focused on IBRA banks and ADB focused on non-IBRA banks and nonbank financial institutions. project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Capacity Development: Partnerships Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy reforms/framework Given the complexity and sensitivity of fundamental policy reforms, maintaining an effective field presence is important, especially under conditions of uncertainty and change. This is important for conducting policy dialogue at senior levels with the government and other international financial institutions (IFIs), for monitoring and supporting program implementation, helping resolve implementation issues, and ensuring that ADB headquarters clearly understands the situation in case the program requires modification. The Extended Mission for Indonesia (EMI) played this role for the Financial Governance Reforms: Sector Development Program (FGRSDP). The rationale for EMI arose given the scope and complexity of the crisis-related program which required dedicated, full-time field attention to ensure effective monitoring and implementation. While there are merits in dedicating resources to support implementation of emergency assistance and provide full-time support for the conduct of policy dialogue and monitoring at the level and intensity required by a crisis, establishment of independent extended missions outside main country resident office generated teething problems and created complications in terms of reporting mechanisms, effective coordination with headquarters and the resident mission on policy dialogue and implementation issues and imposes additional budgetary costs for maintenance of new establishment. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Modality: Program Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Management: Operation and maintenance Project Management: Project management Country Context: Crisis/Post-crisis Country Context: Emergency Other: Resident Mission Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation In responding to future crisis, ADB as well as borrowers should be particularly careful in selecting the tools for intervention. Different instruments are likely to be needed for different conditions, though they may be linked (e.g. quick-disbursing financing is provided for crisis support, while in parallel or in sequence, support is provided for longer-term policy reform). It is vital that support aims to address the fundamental causes of the crisis. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Lending modality Country Context: Crisis/Post-crisis Policy & Reform: Policy reforms/framework In undertaking policy-based lending, it is essential to have in place and to be able to build upon extensive country and sector knowledge in the design of a program, especially under the intense pressures of a crisis. In the case of Financial Governance Reforms: Sector Development Program (FGRSDP), ADB had significant prior experience in the financial sector of potential relevance through two earlier program loans. Diagnosis has an essential role to play in shaping program design. Under crisis conditions, this may be more challenging, and yet more important, given that there is little margin for addressing the wrong issues, or leaving out key crisis-related problems. In this regard, while weaknesses in the financial sector were initially assumed by both the government and international financial institutions (IFIs) to be at the root of the crisis, it is now generally accepted that the Indonesian crisis was fundamentally a twin crisis of the banking and corporate sectors which were closely intertwined and required parallel attention. While not its main focus, FGRSDP did address issues relevant to corporate debt and restructuring as well as corporate governance. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Modality: Policy-based lending Country Context: Crisis/Post-crisis Policy & Reform: Reform Program design under crisis conditions is likely to be more hampered than usual by limited information and uncertainty. Implementation is likely to require adjustments in schedule and/or activities as circumstances change or new information becomes available. Cancellation of the secondary mortgage facility (SMF) component is an example, as are delays due to capacity and coordination constraints revealed during program implementation. A flexible program timetable contributed to the ultimately successful implementation of needed reforms. Policy-based lending should thus be guided less by keeping to what may have been under the circumstances unrealistic ï¿½best guessï¿½ schedules, and more on ensuring that needed reforms are implemented effectively and sustained. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Policy-based lending Modality: Program Capacity Development: Capacity assessment Country Context: Crisis/Post-crisis Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation While sound and timely advice on bank restructuring was provided to the government that involved subjecting banks to individual agreements specifying time-bound financial performance and operational restructuring targets in order to qualify for capital injections, a corresponding commitment by the government to ensuring transparency and effective governance of the restructuring process is essential if costly scandals such as those involving Bank Bali in 1999 are to be avoided. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Capacity Development: Ownership Policy & Reform: Reform Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/financial-governance-reforms-sector-development-program
Power Sector Restructuring Program | Indonesia |  | 2004-07-15 | A cautious approach is needed while moving from a monopolistic and government owned and regulated market structure to a competitive one. The government needs to study upfront the implications of different restructuring options and prepare the sector to operate in a market environment before the introduction of competition. Evolution of competition to the retail level would depend on how the sector develops further and on socioeconomic conditions. These considerations underline the need for flexibility in the design of the program. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Modality: Program Policy & Reform: Public sector reform Implementing a program of power sector reforms leading to full competition is a complex task and involves a number of actions over a long period of time. Significant changes in the political, social, and economic environment during the implementation period would influence the strategy and time schedule. Further, the executing agency does not have full control over actions relating to legislative changes. Thus it is difficult to prepare a highly realistic implementation schedule at the appraisal stage. However, to maximize chances of success, thorough policy research and design, adequate assessment of implementation arrangements, and full government ownership should be ensured at the time of program formulation. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Modality: Program Project Design: Appraisal Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Energy planning/management Policy & Reform: Reform The power sector restructuring program should include components and/or covenants to improve the operational performance of the government owned power utilities during the transition period prior to their privatization. Simultaneous monitoring of loans that are interlinked in realizing an objective (for example this program loan, the TA loan and other investment loans provided to PT Perusahaan Listrik Negara or PLN (State Electricity Enterprise) can improve the effectiveness of program implementation. project cycle stage: Feasibility, Appraisal Lesson Topics: Loan Agreement: Covenants Modality: Program Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Energy planning/management Policy & Reform: Privatization Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/power-sector-restructuring-program
Private Junior Secondary Education Project | Indonesia | Education | 2004-07-15 | A fairly strong supply-based resource allocation was evident throughout the project in the provision of predeterminedpackages to schools, despite persistent efforts by ADB to promote a more demand-drivenapproach. In some instances, the allocations proved inappropriate, e.g., classroom constructionin schools with declining enrollments. Resource allocation modalities that promote locallydefined needs-based allocation should be encouraged, since they can drive local school andcommunity-based planning. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Education Methodologies/Approaches: Community approach As considerable resources will be needed to fund the expansion in the annual output from the primary schoolsystem entirely in the public sector, there is a clear argument for continued, strong fosteringof public-private partnerships in junior secondary education (JSE) provision. The success of any such policy will depend onmore effective control of public school growth as well as selective support to the private sector.It is clear that the migration of students among sectors is driven by parental decisions involvingboth cost and quality factors. To stem such migration, efforts are needed to promoteequalization in both areas. This suggests the need to address the inequity in inputs to theprivate sector (in comparison with the public sector) in order to attain the desired equity inoutput. The project has shown how improved quality can boost enrollment and thereby privateschool sustainability. Project experience suggests that quality can be best improved through long-term commitments to recurrent costs, particularly the provision of full-time teachers, andnot through piecemeal or one-off interventions. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Operation and maintenance Capacity Development: Ownership Sector Related Issues: Education Sector Related Issues: Private sector Sector Related Issues: Public-private partnership The project experiences indicate that impact is most evident the closer an intervention is to the beneficiary. The seconded-teacher program has been particularly successful in this respect. This is a noteworthy area as it has the potential to fulfillmany of the government's avowed policy objectives (i.e., supporting private schools, promoting school-based management, and enhancing quality). Salary costs constitute the major item of expenditure for the majority of private schools. Thus, providing government-funded contract teachers reduces salary expenditures, and, in turn, frees up funds that the school management can then use for other items. Furthermore, as previously noted, the provision of full-time teachers to private schools has the potential to yield quality improvements in the classroom. The importance of teachers in parental perceptions should not be underestimated. In comparison with non-earmarked grant support, contract-teacher deployment offers a lower risk method of providing budgetary support while also facilitating greater contact with the private sector.Moreover, the great advantage of providing support through contract teachers is that they are both more 'upgradable' and 'movable' than physical facilities. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Monitoring & Evaluation: Impact evaluation Project Design: Project design Sector Related Issues: Education Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework The project has highlighted the importance of taking a systemic, holistic approach to education planning and development.Private junior secondary education (JSE) is only one subsector of the JSE system. Provision of JSE also falls under thedomain of the Ministry of Religious Affairs (MORA) through both public and private madrasah. Analysis of national trends over the last 5 years indicates important interplays among these subsectors, with significant student movement not only between public and private JSE but also between the secular and madrasah subsectors. There is a danger that, without amore holistic, sector-wide perspective in project formulation by both government and funding agencies, future interventions could in effect merely promote student migration between subsectors, without significantly increasing participation in the JSE sector as a whole. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Indicators Project Design: Project design Sector Related Issues: Education Sector Related Issues: Private sector Methodologies/Approaches: Holistic approach The project highlights a critical dilemma facing government: the economic rationale for focusing resources on the most viable schools set against the right of all children to a good education. It is clear that size is critical for the sustainability of private schools. Given the dependence of private schools on student fees, remote areas with low population densities will seldom be able to fully support self-financing schools that offer quality education. The schools in these areas are the ones most in need of government assistance. Conversely, the areas that offer the most promising conditions for private schools are areas of high population density where large enrollments can be achieved. Field visits indicate that private schools in these areas, however, are most at risk from competition due to the expansion of public schools. Logically this would point to a policy of targeted support, extending help to the most needy schools, i.e., small rural schools, while effectively regulating the growth of public schools in urban areas so as to have complementarity rather than competition. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Sector Related Issues: Education Sector Related Issues: Private sector Sector Related Issues: Rural development Sector Related Issues: Urban sector/development Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/private-junior-secondary-education-project
Upland Farmer Development Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2004-07-15 | The farmers training and on-farm verification trials should have been undertakenbefore planting. While planting tree crops ahead of schedule enabled the projectto meet or exceed the planting targets, it damaged the quality of plantations inthe long term. Similarly, livestock development, which plays an important role in the upland areas, should have been introduced from the beginning of the project. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Rural development The government should have undertaken project preparatory activities, includingestablishing the project's management structure, training project administrativestaff, launching initial farmer group mobilization and on-farm verification trials, and improving roads to facilitate access to the project sites. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Project management Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation The lack of extension advice on maintenance, processing, and marketingcontributed to the low output prices farmers in remote areas received.Addressing these issues would considerably increase farmers' incomes. Likewise, the project provided limited training and support to farmers for alley cropping. As a result, some farmers did not follow sustainable agriculture farming systems envisaged at appraisal. To ensure that farmers practice sustainable forest management, re-greeningactivities should have been undertaken with wider participation of farmers inspecies selection. The activities also should have been accompanied by farmers'training on environmental management. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Extension service Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation To ensure the efficient delivery of seedlings, a site-specific evaluation ofalternative means of supply, including the establishment of on-site nurseries,should have been carried out. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/upland-farmer-development-project
Engineering Education Development Project | Indonesia | Education | 2004-06-15 | Centralized procurement of equipment, instructional materials, textbooks, and other related items is efficient only if the coordination and cooperation with the users is effective. Otherwise, decentralized or individual procurement by each beneficiary institution of these items should be considered. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Procurement Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation Leadership can be a key factor in the effective execution of a project. In-house seminars and workshops should be conducted to improve the leadership capacity of project personnel. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity building The deployment of international and domestic consultants should be synchronized to maximize the benefit from their inputs. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Consultants The Program Relevancy Fund (PRF) has been one of the most successful activities of the project. Future education projects dealing with the economic development of the country should involve the government, industry, and educational institutions as partners from project design to implementation. Project design should have some flexibility built in to anticipate changes in input or technology. The flexibility in the design of this project made inclusion of the information and communication technology (ICT) component possible. A good sustainability plan, supported by budgetary resources, should also be included in project design. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Partnerships Capacity Development: Technology/Technology transfer Sector Related Issues: Education Sector Related Issues: Industry and Trade The project must draw up a written plan of action and activities for those returning from overseas fellowship programs, so they understand what they are expected to do when they are back in the country. project cycle stage: Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/engineering-education-development-project
Basic Education Project | Indonesia | Education | 2003-12-15 | Engaging some domestic consultants as international consultants did not prove to be successful as they lacked wider international experience and knowledge. More care should have been taken during the selection and engagement of academic consultants. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Given the required inputs, madrasahs demonstrated their potential for improved quality andcontributed significantly to the government's efforts to provide quality 9-year basic education toall. The model madrasahs were successfully established; however, the success of theinstitutions depended greatly on the leadership of the principals. Therefore, the selection andrecruitment of model madrasah principals should be competitive and based on performance. project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity development Capacity Development: Human resources management Sector Related Issues: Education Some problems emerged that were related to the centralized procurement of instructionalmaterials. In addition, in some areas the supply of the textbooks did not match increasedenrollments, especially at private madrasah tsanawiyah or MTs (junior secondary school under Ministry ofReligious Affairs). Several textbooks and teacher guides were not used byteachers who found these books irrelevant. project cycle stage: Appraisal Lesson Topics: Project Management: Procurement Sector Related Issues: Education Sector Related Issues: Private sector The Assistance Scheme for Facilities Improvement (ASFI) program proved to be one of the project's successful components. Often the communities accomplished two to three times more than the expected targets, through largercontributions and greater efficiency in the use of available resources. The ASFI program can beused as a strategy for community participation for future aid projects. However, loan or grantcomponents should comprise at least 50% of ASFI costs, for wider coverage, especially inpoorer communities and remote areas. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Methodologies/Approaches: Community approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/basic-education-project-0
Sumatra Power Transmission Project | Indonesia | Energy | 2003-12-15 | Given the termination of the construction supervision consultancy because of financialconstraints, the lack of project progress reporting up to the expiry of the consultant's contractresulted in significant delays and difficulties in subsequent supervision and administrative services. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Project administration Project Management: Project reporting Project Management: Project supervision Land acquisition and right-of-way disputes of the type experienced by the project arelikely to be encountered more frequently as members of the community become more aware oftheir rights and become involved in prolonged negotiations. This serious issue, which has arisenelsewhere, not just in Indonesia, may affect other projects in the future and should be taken intoconsideration when preparing upcoming projects. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Numerous tender packages and contracts result in additional administrative work andcoordination problems. Future contracting procedures should ensure adequate timefor processing contracts and optimize the number of tenders and contracts. project cycle stage: Appraisal Lesson Topics: Project Management: Procurement Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/sumatra-power-transmission-project
Sustainable Agriculture Development Project in Irian Jaya | Indonesia | Agriculture, Natural Resources, and Rural Development | 2003-12-15 | A project that involves crops that take long to produce but have long-term benefits,should consider the long-term interests of the participants and assess the risks involvedrigorously. Project design should provide for periodic monitoring of government interventions,and the macroeconomic environment that affects production and marketing. To improve the effectiveness of monitoring and evaluation, institutional arrangements should ensure that regular and well-coordinated benefit monitoring surveys are conducted at timely intervals, and that the results are fed back into the executing agency's monitoring system. project cycle stage: Design, Feasibility Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Even though the project provided advance procurement, implementation was notpossible because of the government's restrictive budget policy, which allows budget allocationonly after the loan agreement is signed. Therefore, it is recommended that preparation of ashortlist of consultants be a condition for loan negotiations. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Loan Agreement Project Management: Consultants Project Management: Procurement For a project with many components and executing agencies, it is essential to have only one projectmanager and one consolidated project implementation budget, under the project manager'scontrol, from the beginning. If these conditions cannot be met, the project should be designedwith fewer components and a single executing agency. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Intercropping of tree crops with food crops while trees are still young helps controlweeds, and increases farm income. Low-cost, low labor-input technology is appropriate forindigenous farmers. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Crosscutting Issues/Themes: Employment Capacity Development: Technology/Technology transfer Sector Related Issues: Rural development Participation of farmer-beneficiaries in all stages of project preparation andimplementation enhances institution building and management, and achievement of the objectives of projects. Meaningful participation of beneficiaries from the onset will require substantial time, effort, and flexibility, and intensive technical supervision. But this would result in more viable and sustainable projects through the benefits of cost savings, mobilization of farmers' resources, development of a sense of ownership among farmer-beneficiaries, and improved ability of the beneficiaries to manage the project after its completion. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Project Design: Project design Project Management: Project management Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Ownership Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation The short duration and inappropriate composition of ADB review missions contributed toinadequate project supervision. Special attention should be given to supervision of projectsinvolving expertise not available in ADB. In such cases, recruitment of short-term specialists toparticipate in the ADB missions may be essential. project cycle stage: Implementation Lesson Topics: Project Management: Project supervision Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/sustainable-agriculture-development-project-irian-jaya
Asian Development Bank Assistance to the Power Sector in Indonesia | Indonesia | Energy | 2003-07-31 | Despite the notable progress, the operational and financial performance of the executing agency (P.T. Perusanhaan Listrik Negara) and the sector still point to the need for continued effort in institutional strengthening and capacity building. The focus should clearly be on the evolution of a competent and independent regulatory body that respects the cost-recovery principle and allows tariffs to cover just and reasonable costs without getting entangled in the cumbersome and unpredictable political processes. project cycle stage: Concept Operation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Executing/Implementing agencies Capacity Development: Capacity building Policy & Reform: Reform Policy-based program lending has been only moderately efficacious and financial assistance alone clearly had only a limited impact on the speed and scope of sector reform. Program loans need to be disbursed fast, but the implementation of stipulated policies relating to structural changes need a much longer time frame. This calls for new and imaginative lending modalities, such as hybrid loans with both project and policy implementation components (sector development programs) or a cluster of program loans each tied to implementation of key specific milestones of the sector reform. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Cluster operations Modality: Lending modality Modality: Policy-based lending Modality: Program Policy & Reform: Reform The results of ADB's operations reflect in large part the appropriateness of government policies. Until 1997, the government and the executing agency (P.T. Perusanhaan Listrik Negara) regularly prepared policy papers and power sector development plans to set objectives, identify investment program, and allocate resources. ADB operations were formulated in the light of such government policies and plans, reconciling them with ADB's sector and lending policies through policy dialogue during country programming and project processing missions. This highlights the importance of policy dialogue in ADB operations. When ADB was unable to secure the government's compliance of tariff-related obligations, it wisely refrained from further lending to the EA after 1995. Lending resumed only in 1999 in the policy-based program lending modality mainly to restructure the sector. Further lending is considered in the context of corrective action by the government in relation to power tariffs. This highlights the importance of a clear focus on implementation of agreed policies. project cycle stage: Concept Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Lending modality Modality: Policy-based lending Modality: Program Project Design: Problem identification Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework While the targets prescribed in ADB's financial covenants had not often been reached, they have clearly helped the executing agency (P.T. Perusanhaan Listrik Negara) to press the government to move in the right direction. Thus during 1990-1997, the EA achieved positive and moderate returns on its revalued assets (3.5% to 6.2%), good debt service coverage ratios, and reasonable self-financing ratios (22% to 37%).This was also the period when the EA was being given larger sized loans (average size $295 million compared to $39 million in the earlier years). When the government appeared unresponsive to the timely cost-recovery needs of the sector and was willing to let the EA incur losses, ADB ceased to lend to the sector. This highlights that financial covenants could help move governments in the right direction, even if the exact targets are not often met. When this ceases to happen, there is no point in continuing to lend and repeating the same covenants. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Methodologies/Approaches: Targeting | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/asian-development-bank-assistance-power-sector-indonesia
Social Protection Sector Development Program | Indonesia |  | 2003-06-13 | A further lesson is the need for clarity of purpose. The Program's prime objective wascrisis alleviation, to prevent things from getting worse, rather than poverty reduction. While thereis considerable overlap between the two objectives, there are also some design deficiencies.Much of the discussion about the Program focused on its contribution to helping the poor, yet some of the poorest groups (e.g., children who had already dropped out of school) were notincluded. Designers of any future crisis-related assistance should be aware that interventionschosen to meet a short-term emergency may not be sufficient to tackle the long-term problemsof chronic poverty. project cycle stage: Lesson Topics: Even where there is common purpose, different stakeholder groups adopt differentapproaches. In addressing the social issues arising from the economic crisis, for example, thepolitical imperative for the Government was to spread the benefits of the Program as broadly aspossible. An inherent danger in this is that the intended focus on the most vulnerable groupscan lose some of its sharpness. project cycle stage: Lesson Topics: Insufficient attention was paid to program management at the outset of the program.More effective management structures evolved during the course of implementation, but theywere not part of the program design. The integration of the program's education component intothe larger Scholarships and Grants Program (SGP) facilitated its implementation. It benefited from the management team established in the Ministry of National Education (MONE), the training provided to district and school committees, and the publicawareness campaign supplemented by other aid agencies. Integration of the education component into a nationwide program also enhanced theimpact of the program and leveraged significant other aid agencies' inputs. The impact of thehealth component was more limited geographically. It was not until the introduction of the Health and Nutrition Sector Development Program (HNSDP) that national coverage was achieved. project cycle stage: Design, Feasibility Lesson Topics: Modality: Program Monitoring & Evaluation: Impact evaluation Project Management: Project management Capacity Development: Capacity building Sector Related Issues: Education Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness It is possible for ADB and the government to develop an effective large-scale emergency package in a timely manner. However, there has to be strong leadership and support from government. Aid coordination helps a great deal. It also helps if the program has simple and well-defined objectives. The education component was based on the simple idea of delivering funds directly to two target groups - poor students and needy schools. The health interventions were also based on the principle of delivering funds directly to identified target groups, but the task of identifying beneficiaries was considerably more difficult for health, and consequently the health component ran into more difficulties. One of the key issues for social protection policies aimed at risk mitigation is identifying the vulnerable groups. The program demonstrated that this is not an easy task since it relies oncommonly agreed criteria and accurate data, neither of which existed. There is still a need forimprovements in these two areas. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Vulnerable groups Finance & Financial Aspects: Financing Modality: Program Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Ownership Country Context: Emergency Sector Related Issues: Education Sector Related Issues: Health and sanitation management Methodologies/Approaches: Targeting It is possible to circumvent a conventional funds flow mechanismthat is slow and subject to leakage, for the disbursement of funds directly to beneficiaries and service providers of basic social services benefiting the vulnerable groups. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Vulnerable groups Finance & Financial Aspects: Disbursement Last, the Program was a set of largely successful, short-term arrangements introducedunder crisis conditions. These arrangements have been maintained and extended beyond theend of the Program, through the World Bank-assisted national SGP and the HNSDP. The crisisforced the Government to take bold and decisive action. As Indonesia moves beyond the crisis,the opportunity arises to address longer term policy issues, relating to equity of access andquality improvement in the provision of social services. The crisis increased the motivation forchange. The challenge now is to maintain the momentum. project cycle stage: Lesson Topics: The Program attempted to provide a package of interventions that were generallyappropriate. Unsurprisingly it ran into problems in remote areas, where underdevelopedcommunications and transportation caused difficulties and indeed rendered even the routineexercise of administration difficult. In some remote parts of Irian Jaya (West, Central, and EastPapua), where there is a concentration of vulnerable ethnic groups, or Maluku (Maluku andNorth Maluku), where there is intercommunal violence, the standardized solutions presented bythe Program may not have been appropriate. Future social protection program plans shouldtherefore consider the design of short-term emergency interventions in different geographical,ethnic, and political contexts. project cycle stage: Lesson Topics: The set of policy reforms to which the government committed itself reinforced the project loan interventions and strengthened the impact of the program. Although introduced as short-term assistance, the process of reform set out in the policy matrix was a necessary part of the package. Indeed, it has been one of the enduring legacies of the program. The program loan supported the initiation of nationwide sustainable policy reforms to ensure the inclusion of and equity of the poor in key social services, and enhanced decentralized management to improve the efficiency of social services delivery systems. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Modality: Program Monitoring & Evaluation: Impact evaluation Project Design: Project design Country Context: Decentralization Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/social-protection-sector-development-program
Senior Secondary Education Project | Indonesia |  | 2003-03-14 | Although the project is considered successful, the Project Implementation Unit (PIU) felt that relatively more time wasdevoted to delivering project inputs and less time was devoted to site monitoring, impact analysis, and quality assurance of project outputs. Future results-based project management should respond to this weakness. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Continuity of Project Implementation Units (PIUs) and of project managers with staff management skills , are crucial elements for successful projects. project cycle stage: Implementation Lesson Topics: Project Management: Project management Capacity Development: Human resources management The project design could have focused on fewer objectives, which would have helped enhance the quality of project implementation. Some planned activities were beyond the project's scope, such as the development of Pusat Pengembangan Penataran Guru (PPPGs or Center for Teacher Training Development) as centers of excellence. A more careful assessment of each planned intervention at the time of project design would have been beneficial. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/senior-secondary-education-project-0
Third Local Roads Project (Loan 1232-INO) | Indonesia | Transport | 2002-12-31 | As kabupaten road upgrading and rehabilitation works can produce very high economic investment return rates (EIRRs) and generate significant socioeconomic impact, such works should remain a focus for ADB lending operations. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financial analysis Sector Related Issues: Roading In many kabupatens, the costs for periodic maintenance overlays of hot rolled sheet pavement are now about equivalent to the previously-more-common penmac type of pavement. As it provides a smoother riding surface, a flexible pavement matrix that more readily accommodates expansive soil types, and a longer pavement life if properly maintained, hot rolled sheet pavement should be used instead of penmac wherever possible. project cycle stage: Design, Operation Lesson Topics: Project Management: Operation and maintenance Sector Related Issues: Roading The capacity of the executing agency and its relationship with the implementing agency is a crucial factor in ensuring that the project is implemented as planned. There should be some chain of authority between the two that makes the latter accountable to the former. Ensuring accountability to a central body is essential in a decentralized administrative structure, especially if the implementing agency is a local government unit. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Project Design: Project design Project Management: Executing/Implementing agencies Country Context: Decentralization The economic impact of road works is short lived if routine maintenance is delayed or poor. High-quality civil works at initial implementation are essential, but follow-on routine maintenance is necessary to sustain the benefits gained through the improved road surface. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Sector Related Issues: Roading The provision of equipment is a necessary but not the sole condition sufficient for strengthening the capabilities of implementing agencies to plan and undertake road works. More importantly, in Project Design, ADB should ensure that there is an enabling environment for the implementing agencies to plan and undertake such works. While they may be technically capable and proper equipment would provide them with the necessary tools, the political climate and the administrative structure need to be conducive as well. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Public governance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building Sector Related Issues: Roading Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/third-local-roads-project-loan-1232-ino
Junior Secondary Education Project (Loan 1194-INO) | Indonesia |  | 2002-11-30 | Better quality monitoring and evaluation processes need to be incorporated into projects during their preparation or, at the latest, during appraisal. In this regard, three factors are important for the quality of such processes. First, sufficient staff resources must be allocated to allow more attention to be given to the use of data for educational and developmental purposes. Second, having monitoring and evaluation begin at project start-up is too late for establishing systems and methods to collect essential baseline data and to monitor early project activity properly. Third, the focus of monitoring and evaluation for management is usually well executed. The learning focus that demands the collection and use of data for feedback and maintenance of what is working well needs more attention. To inform future development, the impact of positive contributions should be analyzed and understood. Thus future monitoring and evaluation processes should record not only what was achieved, but also how it was done, and should capture not only inputs and outputs, but also impacts and their sustainability. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Capacity Development: Human resources management The education system is achieving a high level of competence and maturity in an increasing number of schools and administrative and support agencies. There is much to learn from local experience in reaching this level rather than seeking solutions and ideas from abroad or from international consultants who will rarely have the necessary insights into local social contexts. The OEM observed some examples of good management and innovative approaches in schools, but notes that no systematic process is in place to document and disseminate learning from these experiences and to replicate them. The dissemination of successful practices can contribute to sustainability by recognizing and consolidating successful schools and providing a positive learning opportunity and source of support for others. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Crosscutting Issues/Themes: Sustainability Project Management: Consultants Sector Related Issues: Education Policy & Reform: Information dissemination/Public awareness | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/junior-secondary-education-project-loan-1194-ino
Rural Water Supply and Sanitation Sector Project | Indonesia | Water and Other Urban Infrastructure and Services | 2002-10-15 | Associated with the need to adopt adequate project management systems, is the need to recognize risks involved in project implementation and to design and implement robust risk monitoring and response systems. In the case of rural water supply and sanitation systems, a key characteristic of project design is that many subprojects will be undertaken as part of a 'design and construct' process. While criteria were stated for subprojects and the project's covenants required a process that considered demand, there was no overall risk management approach to ensure that these critical activities were implemented. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Finance &amp; Financial Aspects: Market analysis Loan Agreement: Covenants Monitoring &amp; Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Project management Project Management: Risks/Risk management Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Consultants were used extensively throughout the project, but the coordination of consultant inputs was poor. As a result consultant inputs were probably both ineffective and inefficient. An example is the use of consultants for essentially administrative tasks and the failure to provide sufficient resources for consultants to adequately inspect works. In a similar way, audits did not pick up the major underperformance of the project. Audits should focus on risk areas such as outcomes and inappropriate use or misuse of project resources, and should be provided with sufficient incentive to report problems. project cycle stage: Implementation Lesson Topics: Finance &amp; Financial Aspects: Financing Project Management: Consultants Project Management: Project management Project Management: Risks/Risk management Methodologies/Approaches: Consultation/Participation Institutional strengthening in the project was limited to training. As a result, the institutional impact flowed from the agencies to the project rather than the other way. While institutional strengthening is about building capacity, it is also about building capability and the will to use it. Capability includes the attitude and behavioral traits that enable achievement of purpose. At the community level this is characterized by demand for water. At the institutional level, demand for the project should be assessed in terms of a real desire to see the project purpose achieved. This level of institutional demand should be as real a prerequisite for institutional strengthening as demand for water is for water facilities. In the same way, projects cannot create institutional capability if there are no adequate prospects to supply basic skill levels. Alternative institutional approaches are needed when the basic institutional prerequisites cannot be satisfied. project cycle stage: Feasibility Lesson Topics: Finance &amp; Financial Aspects: Market analysis Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Lessons highlighted include the importance of local knowledge in the design process, the importance of the price of water on demand, and the importance of tariffs to achieve sustainable operations. Most international agencies have changed their approach to rural water supply and sanitation based on a need to better respond to community demand. Project implementation failed to reflect these changes. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Crosscutting Issues/Themes: Sustainability Finance &amp; Financial Aspects: Financial analysis Finance &amp; Financial Aspects: Market analysis Project Design: Project design Project Management: Project management Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Policy &amp; Reform: Public sector reform The agencies involved in the project acted in a way that indicated they firmly believed their views were more important than those of the recipient community. This impacted on the project in a number of ways. In some cases officials who seemed not to want to spend time or resources on community involvement usurped the community's role. In other cases community participation was reduced to labor. All of this makes a bottom-up approach difficult to implement. Unless project designs include ways to overcome such attitudes, community-based approaches will be difficult to implement, and will continue to impact negatively on community, gender, and poverty objectives. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Community approach The fundamental reason for the project's lack of success is the need to move away from the supply oriented approach of traditional government engineering agencies toward a more consumer-oriented approach to providing community services. While a significant degree of technical skill and management rigor is still required, the new approach needs to be totally premised on a service-oriented organization culture, and this has not been apparent in the government agencies involved in the project. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity development Sector Related Issues: Health and sanitation management Policy &amp; Reform: Public sector reform The issue of demand management is not restricted to communities. Perusahaan Daerah Air Minum (PDAMs or regional water supply enterprises) are more attuned to the demands of their consumers than are the government's implementing agencies. The relationship between public works authorities and PDAMs is one of service provider and client. This relationship was generally poorly handled within the project as PDAMs were forced to take on systems that were mostly unprofitable and for which they had little or no involvement in planning and design. Future projects should see PDAMs and other utilities as a key client group. project cycle stage: Feasibility Lesson Topics: Finance &amp; Financial Aspects: Market analysis Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation The project, a complex one, was implemented with such loose project management structures and processes. Coordination was identified as a problem many times, specifically, between implementing agencies, between levels of government, and between consultants and contractors. Many of the fundamental requirements for a project management system were lacking and certainly there was no overall quality management system. Aspects of project implementation were impacted by the lack of project management systems. The lack of a logical framework meant that the processes linking inputs, activities, outputs, and outcomes were not explicitly recognized and certainly not monitored. Monitoring was generally restricted to input counting as evidenced by failure of reporting systems to indicate problems early in the project. Project experience indicates that there is a clear need to implement a project management system that is based on valid implementation processes and that provides relevant information about achievement of purpose. This is particularly true when the project is intended to produce many small outputs in widely dispersed remote locations. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring &amp; Evaluation: Monitoring and evaluation Monitoring &amp; Evaluation: Reporting Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Methodologies/Approaches: Consultation/Participation The use of standard designs was intended to improve quality and reduce cost. But many of the standard designs were inappropriate for local conditions. There was a failure to recognize when standard designs were inappropriate, and to act to change specifications. project cycle stage: Design Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/rural-water-supply-and-sanitation-sector-project-0
Second Integrated Irrigation Sector Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2002-09-13 | Benefit monitoring and evaluation (BME) was not successful in generating usefulinformation, either during project implementation or for post project reviews.There is a need to review the BME approach because the system was not beingused by government agencies in view of the lack of incentive to use it, and its not being understood by water users associations (WUAs). project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Post-evaluation Project Management: Executing/Implementing agencies Sector Related Issues: Irrigation management Parts B (agriculture), C (coordination), and D (irrigation services fee or ISF) were very much subsidiary toPart A (irrigation) and did not get the attention that was needed from theimplementing agencies. As a result they were generally less successful. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Irrigation management Sector Related Issues: Rural development The agricultural support through integrated agriculture demonstration units (IADUs) was mistimed, with agriculturaldemonstrations being hindered by lack of water in irrigation systems where improvements were not yet completed. Yet there was ample time within the project period to carry out agricultural development activities after the completionof many systems. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development The concept of efficient operation and maintenance (EOM) largely failed. It did not result in increased government operation and maintenance (O&M) spending as decentralization has largely transferred responsibility for O&M from provincial irrigation agencies to district governments. The approach to system operation was flawed, being too complicated for many of the staff involved, as well as for farmers who are increasingly playing a role in system operation. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Management: Operation and maintenance Country Context: Decentralization Sector Related Issues: Irrigation management The implementation period was too short to allow for full development of tertiaries and land in new schemes. Insufficient time also meant that water users associations (WUAs) did not get enough support to build their capacity for system operation and maintenance (O&M). project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Irrigation management The quality of construction work remains a problem, but there is no easy solution. Giving consultants a larger role as engineers to approve all payments to contractors may not be cost-effective on projects such as the Second Integrated Irrigation Sector Project (IISP-2) where there are many scattered small-scale work sites. Farmers could take a greater role, but they lack training and expertise. And they have become used to accepting substandard work in the knowledge that it will be rebuilt by another rehabilitation project within a few years. The use of precast concrete sections for lining smallcanals and for structures could reduce quality control problems at small work sites. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement Sector Related Issues: Irrigation management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/second-integrated-irrigation-sector-project
Second Land Resource Evaluation and Planning Project (Loan 1099-INO) | Indonesia | Agriculture, Natural Resources, and Rural Development | 2002-08-31 | A more realistic implementation schedule should be considered when designing a project. Given the multiple EAs, the scattered priority areas, the delayed release of funds due to rigid centralized and bureaucratic system, project implementation took longer than expected. Also, a thorough assessment of the capability of the staff of concerned government agencies should be undertaken at project design. For the project, the slow digitizing process was attributed to limited staff capability while the delay in procurement was also a result of the inadequate understanding of ADB s procurement guidelines by the EAs staff (on top of the delay in the release of funds). project cycle stage: Feasibility Lesson Topics: Flexibility in design and implementation, and responsiveness to user demand in defining project activities through a more participatory manner are important to meet stakeholders needs. The top-down approach employed in the project resulted in outputs being considered irrelevant in most provinces. A bottom-up approach with areas and scales defined and contracts undertaken at the provincial (or district) level would probably have ensured that the outputs would be useful and used as well as providing more capacity in the provinces to expand from the pilot areas using their own resources. project cycle stage: Feasibility Lesson Topics: Introducing change to bureaucratic procedures is difficult in many developing countries. Where a project seeks to introduce major changes (such as a user pays principle for a service that has previously been provided free), the mechanisms need to be assessed in detail and accompanied by adequate institutional analysis and policy dialogue at the time of project design. A loan covenant may not be sufficient to ensure that the objective is achieved. project cycle stage: Feasibility Lesson Topics: It is worth the effort of ADB and concerned agencies to develop support for new technical systems among senior management in government agencies concerned (and the private sector). One of the successes of the project was its generation of interest in and support for digital mapping, GIS, and improved physical planning among management at all levels and in a range of agencies. project cycle stage: Design Lesson Topics: Multiple executing agencies (EAs) complicate project design. In practice, project management did well to coordinate project activities and achieve the majority of planned outputs. However, a smaller number of EAs would allow more focus on improving outcomes, and less on procurement, logistics and coordination. project cycle stage: Design Lesson Topics: Projects in sectors with rapidly evolving technology require the inclusion of systems which promote allocation of budget (or cost recovery) for equipment upgrading and replacement and the training of existing and new staff following project completion. project cycle stage: Feasibility Lesson Topics: The mechanisms for extension from pilot to other areas need to be clearly defined. Under the project, it was anticipated that mapping the priority areas would promote expansion to other areas. In practice, only limited expansion has occurred. project cycle stage: Feasibility Lesson Topics: When designing follow-on projects, more effort needs to be made to understand the lessons from the earlier project(s), both completed and ongoing, to ensure that they are fully incorporated. project cycle stage: Design Lesson Topics: Where the outputs from one component represent inputs to another, a phased project should be considered. The project would have benefited greatly from such an approach, with Bakosurtanal base mapping produced under the first phase and supplied to other agencies at or shortly after the commencement of the second phase. project cycle stage: Feasibility Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-land-resource-evaluation-and-planning-project-loan-1099-ino
Tree Crop Smallholder Sector Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2002-07-15 | An assurance should have been included in the Loan Agreement to ensure that thegovernment would provide adequate funding for agro-inputs and other necessaryactivities after loan closing. This would have helped the executing agency secure such funding from the government even after the loan closed. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Loan Agreement Project Management: Executing/Implementing agencies Sector Related Issues: Rural development Closer coordination between the major external agencies would have been helpfulin avoiding two similar studies in the same sector being taken by ADB and the World Bank. project cycle stage: Appraisal Lesson Topics: Credit should not have been delivered through a government department. Althoughthe farmers received the agro-inputs in a timely manner, there is very little incentive for the executing agency to continue with it after the project has been completed. However, it must continue for the next 10-15 years to ensure sustainability. Since the governmenthas not provided the necessary agricultural inputs to the farmers as envisaged afterthe financial crisis, farmer debt may need to be written down in somecircumstances. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Country Context: Crisis/Post-crisis Sector Related Issues: Rural development In order to effectively implement the issuance of land certificates, the National Land Agency (BPN) should have been one of the executing agencies. Land titles and land tenure security areextremely important and should be given high priority in future projects. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Project Management: Executing/Implementing agencies It is more appropriate to utilize and upgrade existing provincial agricultural offices during implementation rather than construct new facilities as they would bemaintained and operated after the closing of the project. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Rural development The project preparatory technical assistance (PPTA) for the Phase II project should have been carried out after the mid-term review so as to prepare a more realistic project; this would have enhanced the chances of its being taken up for implementation. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design When the government provides planting materials and inputs, it gives farmersreasons to complain if yields are low, and reasons not to pay back the credit to the government. Farmers should have been given a choice of suppliers of planting material from which they could make their own selection, thus shifting some of the responsibility onto the shoulders of the farmers. Farmers could have also been given the opportunity to buy agro-inputs from their local KUD (Village Cooperative Unit) or other outlet. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/tree-crop-smallholder-sector-project
Rural Health and Population Project | Indonesia | Health | 2002-06-14 | A project developed around a clear concept (referral system), with the right mixof infrastructure strengthening, capacity building, and health system reforms, canquickly generate benefits in terms of improved coverage and quality of services.Benefits will be significant if the project focuses on essential services (primaryhealth care services, including the district referral hospital) and targets thepopulation groups at highest risk. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Policy & Reform: Reform Appropriate advance actions would help project implementation and preventinitial implementation delay. Advance action should include the recruitment of keyproject staff and consultants. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project management Effective project monitoring and evaluation requires that a simple system (e.g., asimple set of indicators and guidelines for data collection) be designed at thetime of appraisal, and made operational at the beginning of a project. In thisproject, the project-related monitoring system must be integrated in the existinghealth management information system. Benchmark data must be collected atthe beginning of a project. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Management information system Sector Related Issues: Health and sanitation management Frequent supervision and monitoring should be conducted at all levels of projectimplementation (central, provincial, and district level) to improve the quality ofproject implementation. Field visits are essential. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Project Management: Project supervision Country Context: Decentralization Future international fellowships programs should include provision for financingEnglish language training, which will expand a pool of health professionals whocould apply for, and benefit from, the fellowships. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Good performance of the project implementing units such as the Central Project Secretariat or CPS (at thecentral level) and the project teams in the five provinces was largely due to therecruitment of experienced full-time staff as well as long-term consultants. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project management Capacity Development: Human resources management In general, provincial health authorities are capable of playing a key role inimplementation of health sector development projects, if necessary with initialassistance of long-term consultants. The institutional capacity at the district level is still limited and is likely to be amajor constraint in the future - particularly in the context of decentralization.Adequate technical assistance must be provided to overcome this constraint. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Risks/Risk management Capacity Development: Capacity assessment Country Context: Decentralization Sector Related Issues: Health and sanitation management Intensive training of project staff on ADB and government procedures (contracts,disbursements, reimbursements, and withdrawal applications) has to be carriedsoon after project inception. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Management: Procurement Project Management: Project management Capacity Development: Capacity building Investment in training of trainers guarantees the transmission of knowledge in thelong run and reinforces sustainability. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Operational studies and pilot initiatives, although modest in terms of investment,can be effective tools to initiate complex reforms in the sector. project cycle stage: Feasibility, Appraisal Lesson Topics: Policy & Reform: Reform Methodologies/Approaches: Pilot project | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-health-and-population-project
Vocational and Technical Education Project | Indonesia | Education | 2002-06-14 | Future project design may take into consideration that without the provision of adequate micro credit facilities in the project, the case for self-employment of the poor is unlikely to have any impact. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Crosscutting Issues/Themes: Employment Given the present level of vocational and technical education (VTE) development and the weakened condition of the Indonesian economy, public training systems need to be upgraded in a financially sustainable manner. Periodic upgrading of skills and knowledge arising from new technologies as well as changing job markets require continuing instructor training. The government's current funding constraint for such training may be met by setting up a training or endowment fund from the loan. It is recognized that, in the long run, sharing the cost of training with employers and trainees is an important means of sustaining an effective system. The involvement of the private sector at all stages of VTE development will enhance local ownership and relevance. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Capacity building Capacity Development: Ownership Capacity Development: Technology/Technology transfer Sector Related Issues: Education Sector Related Issues: Private sector Lack of funds for repair and maintenance of school equipment and buildings iscommonly observed, mainly due to (i) the government's inability to provide sufficient operation and maintenance (O&M)budget, and (ii) ADB's general policy of not financing O&M. Future project design may considersetting aside an endowment fund from the loan for the O&M. With an appropriate mechanismfor its operation, the dedicated fund could be used by the school for O&M of physical facilities.In addition, schools should be encouraged to generate additional funds to support theirrecurrent activities. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/vocational-and-technical-education-project-0
Tenth and Eleventh Road (Sector) Projects (Loans 966/1115-INO) | Indonesia | Transport | 2002-04-30 | Road betterment works have been effective in that they have compensated for delayed or poor routine maintenance. However, they cannot solve problems relating to the long-term sustainability of roads. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Sector Related Issues: Roading The sector-lending approach has resulted in successful road sector projects. The capacity of the executing agency is the most crucial factor for achieving this success in other developing member countries. However, ADB and the Borrower need to pay adequate attention to better selection of subprojects and better quality of civil works during implementation, followed by adequate attention to routine maintenance. project cycle stage: Feasibility, Appraisal, Implementation, Operation Lesson Topics: Modality: Lending modality Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity assessment Sector Related Issues: Roading | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/tenth-and-eleventh-road-sector-projects-loans-966-1115-ino
Eastern Islands Roads (Sector) Project | Indonesia | Transport | 2002-04-15 | ADB cost estimates are too conservative, resulting in substantial amounts of loan savings. project cycle stage: Appraisal Lesson Topics: In terms of environmental damage, other than upgrading components, most roadworks involved improvements to the existing alignment within the right of way. No environmental assessment was deemed necessary for these projects duringpreparation. However, during implementation two road betterment works werefound to be passing through sensitive preservation areas. ADB requested the executing agencyto undertake environmental studies to mitigate the potential damage caused bythe increased traffic, land slides, encroachment, etc. These studies were doneonly at the end of the project implementation period. One road section in EastKalimantan was therefore completed before the environmental studies werecarried out. The reports recommended some actions to be taken to mitigatepredicted environmental damage. It was found, however, that the necessaryfunding arrangements to monitor and manage the environmental plans for theseroads were not in place. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Roading In the investment program, more emphasis should be given to routine andperiodic maintenance instead of rehabilitation-asset preservation vs. capacityexpansion. The practice of omitting roadway drainage in order to save funds for additional rehabilitation works should be avoided. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Roading Sector Related Issues: Water resource management Project readiness for immediate implementation after loan approval is critical. In 2001 at a joint ADB/World Bank Country Portfolio Performance Review, ProjectImplementation Readiness Criteria were agreed, which list various actions thatshould be completed prior to loan negotiation and effectiveness. A retroactive application of these criteria would show that this project was far from ready for implementation at the time of loan approval. Given this status of project preparation at appraisal, ADB should have devoted more resources toward an implementation review in the first year, to get theproject ï¿½off the ground.ï¿½ project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal The project coverage in 13 provinces for betterment, periodic maintenance,upgrading, and bridge replacement was overextended geographically. Thisresulted in small subprojects scattered over remote areas, which could not beeasily monitored. While a case can be made for broader coverage on equitygrounds for less developed areas, this approach has diluted the possible impactof the project on network or corridor improvements and capacity building. Also,the three main funding agencies (ADB, World Bank, and Japan Bank forInternational Cooperation) are all currently working on similar activities in the project provinces, stretching the limited counterpart staff capacity. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Roading The project was designed as a sector loan, but was implemented more as a project operation in which the main focus was on implementation of the project subcomponents. Due attention was not paid to the broader sector issues, suchas review of annual investment programs and status of the Policy Statement and Action Plan for the Road Sector. Policy Statement and Action Plan for the Transport Sector (PSAP2) should have been updated within the period of project implementation and has taken longer to be developed than expected. These data are important for future project formulation. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Lending modality Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework The simplified final engineering design model used by the executing agency did not provesatisfactory. This should only be used in conjunction with adequate fieldinvestigations. More thorough economic analysis should be done, particularlytraffic counts and projections. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Roading The Study for Road Network Development in the Eastern Islands should not beclassified as institutional strengthening. Such a study that (i) reviews themedium-term future requirements of road network development, (ii) preparesproposals for provincial road master plans, (iii) identifies priority investments, and (iv) conducts prefeasibility studies for future investments - is preparatory innature. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Capacity building Country Context: Prioritization Sector Related Issues: Roading There is too much reliance on international consultants. This input should begradually cut back through local capacity building. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Capacity Development: Capacity building Too many loan covenants to be complied with will dilute their importance. Also,the loan covenants should be underpinned with adequate arrangements andresources for their implementation. A covenant on its own is like an ï¿½unfoundedmandate.ï¿½ project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Design: Project design | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/eastern-islands-roads-sector-project
Second Development Finance Project | Indonesia | Finance | 2002-04-15 | ADB should respond quickly with necessary changes in terms and conditions as requested by the government and participating financial intermediaries (PFIs) during project implementation. As discussed above, ADB left the interest rate issue unresolved, although the government and the PFIs requested a change from ADB's pool-based interest rate to a market-based interest rate, at a very early stage in project implementation. Had that been done at an early stage, loanutilization and attainment of project objectives would have been much greater. The extensions made in the dates for loan commitment and closing, and the relaxations made in some loan conditions, were largely ineffective in achieving these aims. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Management: Project administration Project Management: Project supervision As far as possible, ADB should not mix private sector-related lending practices with those of the traditional development finance institution (DFI)-type lending such as the subloan conditions prescribed for the subborrowers/subprojects and the loan conditions prescribed for participating financial intermediaries (PFIs). First, the pricing of ADB's private sector-related loans should be competitive with those of commercial sources, and second, ADB loan conditions and controls should be kept to the bare minimum. Otherwise, private sector banks and subborrowers will seek alternative sources of finance, as happened under this project. The numerous loan conditions and controls should be replaced by specific guidelines, which should be properly laid down and well explained, up front, to all participating parties. Thereafter, the project should be allowed to proceed in accordance with existing practices and market conditions. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Loan Agreement: Covenants Project Design: Project design Project Design: Subprojects Sector Related Issues: Private sector The long and time-consuming subloan reimbursement procedure increased the cost of funds to the private sector subborrower. Such increased costs, in turn, reduced the competitiveness of the export-oriented subprojects.Therefore, ADB should take steps to shorten that procedure as much as possible. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Project Design: Subprojects Project Management: Project administration Sector Related Issues: Industry and Trade Sector Related Issues: Private sector | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/second-development-finance-project
Agricultural Technology Schools Project (Loan 1050-INO) | Indonesia | Education | 2001-12-31 | Government assurance on providing sufficient resources for school maintenance is necessary but insufficient. More effective measures are needed to ensure the establishment of a reliable funding source for school maintenance after project completion, including, for example, setting aside a fixed amount from the government budgetary allocation or student fees to establish a maintenance fund, and developing regulations to ensure exclusive use of the fund for school maintenance. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Education Innovative project design such as the production unit (PU) concept needs to be accompanied by close supervision of project implementation. The supervision should not focus on an exact conduct of a blueprint project design. A process approach needs to be adopted to permit flexible adjustment of project design during implementation, and the supervision should focus on timely identification of issues emerging during implementation. project cycle stage: Design, Implementation Lesson Topics: Project Design: Problem identification Project Design: Project design Project Management: Project supervision Methodologies/Approaches: Process approach Provision of hardware and software inputs to schools can improve the quality of educational inputs, such as better school facilities and better trained teachers. Without effective management systems and incentive schemes in schools, however, the improved inputs may not lead to improved quality of educational outputs and efficiency. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Education The analysis of government budgetary implications from the viewpoint of a single project is insufficient as the concerned government may have many competing uses for its budgetary resources. project cycle stage: Appraisal Lesson Topics: The cost of school maintenance is not particularly high if conducted regularly and promptly. The lack of a regular funding source for school maintenance, however, may lead to ad hoc arrangements, delays in the required repairs, and further deterioration of facilities. project cycle stage: Design Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Operation and maintenance Sector Related Issues: Education The design of an education project should give particular attention to the long-term operation of the project schools after completion when there are no more funds from the project, and the financial support from the government may not be fully available and may be subject to delays in its release. Intensive consultation needs to be conducted during the design stage with concerned government authorities, school principals and teachers, and local communities to develop effective measures to ensure a reliable funding source, including, when appropriate, the use of loan proceeds to establish income-generating activities for the schools. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Education Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation The establishment of a public school needs to avoid any potential adverse impact on private schools in the project area that serve the same set of clients. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Education Sector Related Issues: Private sector The provision of a large amount of one-off training under a project without a budget for continued upgrading of teachers skills after project completion may not be cost effective. The lack of proper incentive schemes in schools may also restrict the full impact of the training as teachers may not be motivated to fully utilize their skills. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building The provision of a standard investment package for all project schools may simplify project implementation and obtain better terms in procurement. The short-term gain, however, is at a long-term cost of inefficiency and weak sustainability, as the investment package may not match well the needs of individual schools leading to idle facilities and the additional burden of maintaining these facilities. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Market analysis Modality: Lending modality Project Management: Procurement Sector Related Issues: Education The sole use of government forecasts for human resources and static data to estimate demand for schools is insufficient. Efforts are needed also to consider factors that influence private decisions on school choices as well as the future trend of demand for schools of the given type after the project investment. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Data collection Sector Related Issues: Education Sector Related Issues: Private sector Using only a nationwide forecast for demand for schools is also insufficient. Efforts are needed to estimate local demand for individual schools, which take into account regional variations especially in terms of population density and competition from other schools. Instead of using a standard model for all schools, flexibility should be exercised in the design of subprojects based on local conditions. Local communities and school representatives should be invited to participate in the subproject design. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Data collection Project Design: Project design Project Design: Subprojects Sector Related Issues: Education Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/agricultural-technology-schools-project-loan-1050-ino
Integrated Irrigation Sector Project (Loans 1017/1018-INO[SF]) | Indonesia | Agriculture, Natural Resources, and Rural Development | 2001-12-31 | A human resources development program should be the basis of the training program. Training units need to be incorporated into the structural organization. All staff holding positions (surat keputusan) should be compelled to undertake a fixed number of training days as instructors each year. All irrigation staff attending should have fixed work positions with the respective government organization. A training monitoring system and information system should be established to provide feedback for future courses. Operation and maintenance (O&M) implementation and budgetary and organizational policy need to be clear before further training at district and subdistrict levels can be effective. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Management: Management information system Project Management: Operation and maintenance Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management Sector Related Issues: Irrigation management Although the performance of consultants was generally satisfactory, specific aspects should be addressed in future irrigation projects to ensure optimal use of consulting resources. First, weak agency staff will not benefit from day-to-day counterpart strengthening unless staff are assigned full time, given specific tasks, and provided with project funds for subsistence and travel. Second, the role of consultants in construction supervision should be as Engineer, not assistant. This will result in a fairer, transparent execution of contracts. Third, the main task and assisting roles of consultants need to be adequately defined and resources allocated accordingly. Fourth, projects must avoid a high number of consulting contracts that require an inordinate amount of executing agency administration. Lastly, the effectiveness of consultants and severe staffing problems (with personal disputes leading to staff changes) illustrate the need to closely monitor and ensure value for money from both domestic and international consultants. Mechanisms should be incorporated into future projects to ensure that a reasonable level of performance is attained during implementation and recorded on certifiable curriculum vitae of consultants. project cycle stage: Design Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Project Management: Project supervision Capacity Development: Human resources management Sector Related Issues: Irrigation management Commissioning requirements have only been studied at the demonstration subdistrict offices. A two-year commissioning period is generally required for adequate development programs for medium-scale schemes with a four-year period for large and major schemes. Programs should include(i) continued training of staff and water users associations (WUAs) in operating schemes until an optimum acceptable management level is reached;(ii) minor modifications and infrastructural improvements that may be necessary for structures and gates to ensure accurate measurement and control and/or system extensions;(iii) development of adequate information techniques for reporting crop planting activities from the field to the operators;(iv) adjustment and change from a theoretical (as designed) water allocation system to one based on actual needs (social and technical), calibration of measuring structures, and the development of appropriate water management techniques;(v) adjustment and optimization of needs-based budgets;(vi) familiarization period between operators and farmer groups necessary to develop relationships and trust;(vii) minor repairs to structures that may have been overlooked by the contractors and supervision staff;(viii) review of tertiary system infrastructure; and(ix) purchase and commissioning of necessary equipment and training in its use. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Reporting Project Design: Project design Project Management: Procurement Capacity Development: Capacity building Capacity Development: Ownership Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Community organizers are required to ensure beneficiaries participate in government-led activities. However, a sustainable mechanism should be introduced whereby project beneficiaries are not dependent on community organizers. Farmers need to participate and be organized into WUAs (or other suitable institutions) at the earliest possible stage of system planning. Ensuring farmer involvement in tertiary system construction and main system design, and prior to agreement on the modality of subproject development and O&M, is essential. For farmers to be available to participate in planning and design activities, field motivators must be active and in place in a timely manner, coinciding with the fielding of the survey, investigation, and design consultant. All costs and time-consuming coordination activities should be borne by a community organizer consultancy or integrated into the survey, investigation, and design consultancy. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Design: Project design Project Design: Subprojects Project Management: Consultants Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation More involvement of provincial and district authorities and beneficiaries in key policy directives is essential. Implementation of government operation and maintenance (O&M) policy should be formulated, explained, and discussed jointly with the provincial water resources service (PWRS) district and provincial managers, BAPPEDA (provincial and district), and other senior provincial government officials in a participatory manner. Understanding of, and/or preparation for, the implications of the policy on short-term and long-term planning is minimal. A long-term provincial/district irrigation development plan should be ratified by provincial planners and beneficiaries, and used for annual program definition. project cycle stage: Design, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation Nationally managed provincial irrigation project activities need to be transferred to the local provincial water resources services (PWRS) and district water resources services. The pressure to retain control at the center (national and provincial) rather than to delegate and decentralize continues to decrease institutional and project implementation efficiency. During Project Design, institutionalization of project activities needs to be given priority. The optimal arrangements for decentralization need to be determined, with proper definition and assessment of roles, responsibilities, and absorptive capacities of PWRS and district water resource services. All future irrigation development projects should be formulated with mechanisms encouraging and ensuring the full participation and ownership of beneficiaries with the support of PWRS and district water resources service for future system management. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Ownership Country Context: Decentralization Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation Regular coordination meetings within provincial and district planning agencies are important and should concentrate on the needs for interagency planning; identification of planning priorities; and assessment of proposals for scheme, subproject, and sector M&E, as well as institutional development coordination. Interagency action programs for irrigation development can be successful through regular consultations at regional planning agency (BAPPEDA)-chaired routine meetings. Provincial water resources service (PWRS) needs to strengthen its technical department for irrigation planning and design, theRegional Development Planning Agency (BAPPEDA) needs to allocate regular budgets to fund such meetings, and beneficiaries need incentives and assistance to participate in bottom-up planning and implementation activities. An appropriate cost recovery mechanism could be arranged to ensure that provinces and districts are able to raise adequate funds to finance their policymaking, coordination, and monitoring functions. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Funding Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation Project Design: Project design Project Design: Subprojects Capacity Development: Capacity building Country Context: Decentralization Country Context: Prioritization Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Specific recommendations for improved farmer participation in irrigation developments and management include (a) small scheme design activities (handover [PIK] and village [PID] schemes) should be carried out in a participatory manner at subdistrict level with support from district offices and consultants; (b) water users association (WUA) establishment and strengthening activities under the multiagency on-farm water management (PTGA) training program should be accelerated and routine PTGA training (pembinaan pengairan) financed through the regional development budget; the legal status of WUAs should allow the WUA to undertake contracts with second parties and choose where they obtain their services; and (c) WUAs should be formed before rehabilitation and upgrading (R&U) design activities commence and be encouraged, by the use of community organizers, to participate in system design. A program of tertiary and field-level system construction with farmer participation should be scheduled to be complete within one year of the main system works. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Project Design: Project design Project Management: Consultants Capacity Development: Capacity development Country Context: Decentralization Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Strengthening of administrative sections of provincial water resources service (PWRS) and district water resources service through the focused training of administrative staff and streamlining of procedures is required. The gradual increase in depth of experience in technical departments should free senior staff from involvement in routine administrative issues if appropriate delegation of tasks can be achieved. The proposed introduction of efficient management information systems could also be very effective in promoting the more efficient use of staff time. Special care needs to be taken in preparing budgets, cost estimates, and realistic implementation schedules. Designs, bills of quantities, and contracts must be carefully checked by the project staff. This involves senior staff spending more time and effort on supervision. All checking should be carried out independently within a quality assurance framework. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Project Management: Management information system Project Management: Procurement Project Management: Project administration Project Management: Project supervision Capacity Development: Capacity building Sector Related Issues: Irrigation management To achieve farmer contributions through provision of labor and materials to field-level system construction, significant efforts, outside the capabilities and time constraints of provincial water resources service (PWRS) staff, are required. These efforts should not be underestimated; district and subdistrict officials understand these requirements better than national planners. Every project should include comprehensive, long-term, institutionalized water users association (WUA) development programs. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Extension service Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Water Users Association (WUA) formation and operational efficiency are prerequisites to the implementation of government policy in many aspects of irrigation development. Beneficiaries must participate if they are to feel a sense of ownership and responsibility, which will also effect attitudes to irrigation service fees (ISF) and operation and management (O&M). Lack of appreciation of the need to develop linkages with target groups during WUA formation has hindered programs for WUA development. In forming WUAs, care has to be taken to minimize disruption to existing social structures. Farmers are reluctant to form and join government-induced WUAs that substitute for traditional associations that have survived for a long time. WUA establishment and strengthening should be accelerated with a focus on (i) quality organizations, (ii) involvement in tertiary and main system O&M, and (iii) a clear linkage between irrigation service and ISF. As the government has not been able to adequately fund postproject O&M, private O&M managers, financed by WUAs, should be considered as an alternative to publicly provided O&M. All future development projects should include components specifically orientated toward WUA development. However, WUA institutional building is a complex process: appropriate performance indicators must be identified and progress of capacity building efforts strictly monitored. An institutionalized PTGA (on-farm water management) subproject should be used to coordinate the activities. However, training activities require administrative, logistical, and organizational assistance. Full-time PTGA subproject working teams will be necessary for the larger irrigation schemes and in districts with significant irrigation developments. Training at the field level (PTGA level C) with a two-year routine follow-up program and regular backstopping activities are required for all technical irrigation and village schemes in accordance with the respective development programs. The training and PTGA unit should be institutionalized and training budgets provided through routine regional development budget sources at district and provincial levels. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Operation and maintenance Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Ownership Country Context: Cultural constraints Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/integrated-irrigation-sector-project-loans-1017-1018-ino-sf
Higher Education Project | Indonesia | Education | 2001-12-14 | ADB supervision of project implementation is more critical at the start whenimplementation arrangements are made operational, than when implementationis progressing on schedule. More staff time should be allocated to reviewmissions for projects at widely scattered locations. project cycle stage: Implementation Lesson Topics: Project Management: Project supervision Capacity Development: Human resources management Human resource development was uniformly recognized as among the mostsignificant contributions made by the project. Returning fellows at each institutionwere eager to point out accomplishments and recognition received by theircolleagues. However, project institutions were not always perceived as havingprovided sufficient opportunities for advancement and research started duringdegree programs. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Human resources management Sector Related Issues: Education Overseas training has contributed to academic networking through theestablishment of collaborative research projects and joint publication activities.This has contributed to capacity building at the project universities, and providedinternational recognition for Indonesian scholars. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Education Participation of beneficiary institutions of higher education in the project design and implementation is crucial to enhance ownership and sustainability. Sustainability should be given careful attention in designing a project that requires (i) innovative services such as student advisory, computer, and language centers to be established and continued after loan closing; and (ii) budget allocation, human services, and commitment by the executing agency and institutional decision makers. Before project closing, attention should be given to ensure sustainability of theproject facilities and any weaknesses or defects in construction and relatedfacilities should be adequately addressed. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation Poor design and quality of completed civil works are linked to inadequate andunqualified supervision at the local project level and to inadequate seniormanagement. To eliminate these problems, the main implementing agency for aproject should have overall responsibility for the monitoring of implementationactivities. Projects with complex designs should be delegated early on to the residentmission. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Project supervision Country Context: Decentralization Other: Resident Mission The timing of the international and domestic consultants' services must besynchronized to gain maximum benefit from their inputs. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Consultants | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/higher-education-project-0
Second IKK Water Supply Sector Project (Loan 1069-INO) | Indonesia | Water and Other Urban Infrastructure and Services | 2001-11-30 | Community participation is a key factor to ensure that anticipated socioeconomic benefits are realized from the delivery of water supply services through the proper operation of physical facilities. project cycle stage: Design Lesson Topics: The success of a sector-type project depends on the efficient control and coordination of project implementation; the ability of local governments (or implementing agencies) to take remedial measures (using shared knowledge) in the subprojects to solve common problems; and regular assessment of subproject performance. project cycle stage: Design Lesson Topics: Without preparing annual benefit monitoring reports for a few years after project completion, it is not possible to effectively monitor the achievement of the project purpose and goal. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Benefit monitoring and evaluation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-ikk-water-supply-sector-project-loan-1069-ino
Central Java Groundwater Irrigation Development Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 2001-11-15 | Flood protection projects should be based on a holistic approach considering thecomplete river system from the upper catchment area to its mouth. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach Pump procurement should be timed to match the hydrological characteristics of the wells to avoid a mismatch of pumps and wells. Replacement of pumps and power units and major repairs should be the responsibility of Water Users Associations (WUAs) to ensure sustainability of the groundwater systems' operations. Water user and pumping charges applied by Water Users Associations (WUAs) only meet the operational costs of fuel, electricity, and pump operator's wages. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Procurement Sector Related Issues: Irrigation management Support for the introduction of High-Value Crops (HVCs) requires more ongoing assistance from competent government agencies such as the Ministry of Agriculture, and provincial and district agricultural services. A bottom-up participatory approach is required to match farmers' expectations with potential benefits. Many farmers are reluctant to adopt HVCs for various reasons such as, the required additional investment exceeds theirresources, volatile markets mean higher risks, and market information is inadequate.Moreover, the higher investment in HVCs can mean higher loss due to pests and theft. Many farmers, too, have a preference for growing rice at every opportunity for reasons of food security and cultural preference. Some areas selected for groundwater irrigation have limited capability for growing HVCs other than rice because of their soil type, drainage, and other physical characteristics. Similarly, areas with corrosive groundwater present continuing problems of well failure and the need to use more expensive material and provide special protection measures. More consideration should be given to the feasibility of developing such areas. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Country Context: Cultural constraints Sector Related Issues: Irrigation management Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach The Benefit, Monitoring, and Evaluation (BME) program should be assigned a higher priority from the outset and be closely supervised by project management to ensure that information on the operational, agricultural, social, and economic impacts can be monitored and evaluated during the project and after its completion. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Impact evaluation Project Management: Project management Project Management: Project supervision Country Context: Prioritization The main consultants should be closely involved in the preparation of the terms of reference for topographic surveys, geotechnical work, and socioeconomic surveys;contacting local contractors for undertaking such surveys; and for supervision and management. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring & Evaluation: Data collection and management Project Management: Consultants Project Management: Procurement Project Management: Project management Project Management: Project supervision | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-java-groundwater-irrigation-development-project
Eastern Islands Urban Development Sector Project | Indonesia |  | 2001-11-15 | Although generally more expensive than asphalt penetration, hot mixed roads are clearly more sustainable in the long run, and compared to main drainage maintained by Dinas Pekerjaan Umum Kabupaten (DPUK or District Public Works Service), the maintenance of kampung area drains is much better due to community ownership. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Health and sanitation management Sector Related Issues: Roading Sector Related Issues: Urban sector/development Methodologies/Approaches: Community approach As their operating tariffs are only about 30 percent of breakeven tariffs, Perusahaan Daerah Air Minum (PDAMs or Regional Water Supply Enterprises) are not financially viable. However, local parliaments are unwilling to raise tariffs. With impendingprivatization of PDAMs, key decision makers should know that the user-pays principle must beapplied if the utilities are to continue providing and improving services. Reducing unaccountedforwater from 40-60 percent to 25 percent is unrealistic. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financial analysis Loan Agreement: Covenants Sector Related Issues: Health and sanitation management Policy & Reform: Privatization Policy & Reform: Public sector reform Proper assessment of water resources must be the basis for supplying water fromboreholes. In Kupang, for example, improper assessment led to underutilization of several waterreservoirs. Due to poor engineering, sewage and sludge treatment facilities on Lombok Islandare massively overdesigned and constructed, estimated at several times the actual requirement. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Project supervision Sector Related Issues: Health and sanitation management The Kampung Improvement Program and Market Infrastructure ImprovementProgram component has brought about the most direct social, community, andenvironmental benefits as the target beneficiaries take ownership and maintain the walkways, minor roads, drains, public water hydrants, and toilets provided by the project. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental benefits Project Design: Project design Capacity Development: Ownership Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development Methodologies/Approaches: Community approach The mere provision of final disposal facilities and sewage treatment facilities by itself is inadequate for the safe disposal of human waste. The facilities, which are unused, are a massive waste of capital. Enforceable laws and regulations requiring all owners of septic tanks to pay for and use these facilities are preconditions for any investment in such facilities. While waste may be collected and removed from urban areas, the final disposal sites may not be managed properly. The education of the public, and training and retention of staff, of operatives and managers of these facilities are also essential. The revenue from tariff collection is almost negligible, and a more realistic and enforceable tariff structure is required to make this service sustainable. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development Policy & Reform: Information dissemination/Public awareness Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/eastern-islands-urban-development-sector-project
Three Integrated Urban Infrastructure Development Projects: Secondary Cities Urban Development (Sector) Project, Botabek Urban Development Project, and Bandar Lampung Urban Development Project (Loans 983/984[SF]/1077/1078-INO) | Indonesia |  | 2000-11-30 | Demand-side management should constitute a more important part of future integrated urban infrastructure development projects (IUIDPs), especially for solid waste and sanitation components. First, waste generation may be reduced through encouragement for recycling and provision of proper incentives for in-site waste removal. Next, offering these services free of charge could generate demand for desludging services of human waste. The treated sludge as compost may be sold to farmers to allow operation and maintenance of solid waste management in a sustainable manner. Large-scale kampung improvement program may be implemented under future IUIDPs where sufficient institutional capacity exists. This can include bus terminals, markets, and possibly urban housing improvements, contributing to effectively achieving urban renewal. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Institutional analysis Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development Methodologies/Approaches: Holistic approach Integrated urban infrastructure development projects (IUIDPs) should envisage vertical integration of water-related project components (such as water supply, drainage, and sanitation) and incorporate social and environmental concerns explicitly. Future IUIDPs and water supply and sanitation projects should take a river basin-oriented approach to balance water quantity and quality. Potable water for drinking purposes should be distributed as bottled water, using public-private partnerships. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Sector Related Issues: Health and sanitation management Sector Related Issues: Public-private partnership Sector Related Issues: Urban sector/development Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach Integrated urban infrastructure development projects (IUIDPs) should pursue further integration of project components involving the introduction of social sector components, such as community-based health care and environmental education. Involving the private sector and encouraging community participation should be actively pursued in future IUIDPs as both contribute to improving accountability in the delivery of services. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Governance Project Design: Project design Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Sector Related Issues: Urban sector/development Methodologies/Approaches: Community approach Methodologies/Approaches: Holistic approach Success in integrated urban infrastructure development projects (IUIDPs) largely depends on how well the implementation arrangements facilitate community participation for a sense of ownership and proper operation and maintenance. Strong local participation and ownership can alleviate the adverse impact of an economic crisis on IUIDPs. Kampung improvement program and market infrastructure improvement program are successful models for improving urban living conditions through community participation, which is also the most effective way to ensure effective monitoring and evaluation and good service delivery. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Operation and maintenance Capacity Development: Ownership Sector Related Issues: Urban sector/development Methodologies/Approaches: Community approach Methodologies/Approaches: Holistic approach The integrated approach for urban infrastructure development allows objective-oriented modifications of project design and components, which is very effective for improving the urban living environment. Integrated urban infrastructure development projects are most appropriate for project cities in the population range of 100,000-500,000. For smaller cities, without strong urban dynamics, the sector lending approach could be applied, focusing on individual sectors. For larger cities and urban areas influenced by a megacity, standalone projects would be appropriate to affect urbanization patterns and have a measurable impact on urban living conditions. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Lending modality Modality: Program Project Design: Project design Sector Related Issues: Urban sector/development Methodologies/Approaches: Holistic approach Water of potable quality need not be distributed through a piped water supply. Potable water from water treatment plants, as well as smaller quantities from shallow groundwater is better delivered when distributed in bottles, through public-private sector participation. Most tropical areas of developing member countries are endowed with sufficient annual rainfall for shallow groundwater to be the most accessible and sustainable source. The fundamental problem is the pollution of this groundwater, due to inadequate sanitation practices. This problem cannot be overcome by extending piped water supply alone, which requires greater investment. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Project Design: Project design Sector Related Issues: Health and sanitation management Sector Related Issues: Public-private partnership Sector Related Issues: Urban sector/development Sector Related Issues: Water resource management | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/three-integrated-urban-infrastructure-development-projects-secondary-cities-urban-developm
Marine Sciences Education Project (Loans 894-INO/895-INO[SF]) | Indonesia | Education | 2000-07-31 | Feedback from the survey of the project fellows points to a critical factor in achieving satisfactory project outcomes: the process of fellow selection, supervisor support of fellows, and preparation of fellows prior to their formal training. The interviews with fellows and on-site inspections suggest that this component of the project was successfully implemented, although it could have been improved by more language training before the fellows went overseas. project cycle stage: Design Lesson Topics: Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Education Project success begins with sound design. A fundamental deficiency in the design of this project was the confusion between concepts such as objectives and strategies. Rigorous design guides implementation, facilitates monitoring and evaluation, and ultimately determines success or otherwise. Design should not be limited to one-shot projects but should look at long-term involvement in a subsector to increase sustainability, at the same time considering the involvement of other external sources. Even for relatively narrow projects such as this one, increased aid coordination is desirable. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Cluster operations Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Strategies need to be adopted that have a reasonable prospect of assisting in the attainment of all objectives. The analysis of this project demonstrates a failure to implement logical, best-practice ideas to achieve such objectives. This is particularly the case in matters as critical as improved teaching and management outcomes. Research training and academic coursework in technical subjects alone are ineffective for improving teaching or management. Furthermore, the policy environment must be conducive to stimulate growth in a sector in order for academic programs in that sector to flourish. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/marine-sciences-education-project-loans-894-ino895-inosf
Nusa Tenggara Agricultural Development Project | Indonesia | Agriculture, Natural Resources, and Rural Development | 1999-12-31 | For farmers to accept the concept of paying irrigation service fees, they need to be introduced at the outset of the project and set at a level that is realistic in terms of the actual costs of providing effective operation and maintenance. If the amounts levied and collection levels are minimal, there is little prospect for the introduction of efficient operation and maintenance and for farmers to play a more prominent role than is generally the case. project cycle stage: Concept Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Operation and maintenance Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Providing improved physical facilities for agricultural support services is not an appropriate response when the agricultural staff do not have the logistical support to maintain an effective extension service. There are lower cost options to improve this situation, including the semiprivatization of agricultural extension. project cycle stage: Feasibility Lesson Topics: Project Management: Operation and maintenance Sector Related Issues: Extension service Sector Related Issues: Rural development Policy & Reform: Privatization Sustainability of irrigation projects would be better ensured if timely and adequate maintenance could be provided. This would avoid early physical deterioration and production shortfalls requiring costly rehabilitation works resulting in less than optimal economic returns. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Sector Related Issues: Irrigation management There should be adequate arrangements for coordination for complex projects where many executing agencies are involved with activities that are closely interrelated. Greater success could be achieved if activities are synchronized during project implementation. For projects primarily on irrigation development, major agencies should be the lead EAs and have the responsibility for providing coordination with other agencies. Planning institutions should concern themselves mostly with simply providing overall monitoring of the project. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Water users associations need adequate support from skilled community organizers to help the officers develop their skills and the confidence to play more effective roles in managing water distribution and in maintaining the systems. project cycle stage: Feasibility, Implementation, Operation Lesson Topics: Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity building Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Community approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/nusa-tenggara-agricultural-development-project
Seventh, Eighth and Ninth Port Projects (Loans 688/797/951-INO) | Indonesia | Transport | 1999-12-31 | An overcautious approach by appraisal teams has in some cases resulted in underinvestment during Indonesia s phase of rapid growth. Container traffic grows extremely fast in developing economies at early stages of containerization. The growth was underestimated for all projects. Shipping specialists are needed to participate in feasibility studies to ensure that realistic forecasts are made of the type of vessels that will call. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Design: Project design Capacity Development: Human resources management Sector Related Issues: Transport planning The entry of the private sector requires extremely careful and detailed planning. Promoting competition or including surrogates for competition is a precondition for success in international container terminal privatization. The key to increasing productivity is the replacement of government operations with competing private sector operations. Tariff reform is a key enabling factor for port reform and the attraction of private participation. However, ADB s TA (under the evaluated projects) concentrated on improving efficiency of existing government bodies. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Private sector Sector Related Issues: Transport planning Policy & Reform: Privatization Policy & Reform: Public sector reform | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/seventh-eighth-and-ninth-port-projects-loans-688797951-ino
Bank Assistance in the Water Supply and Sanitation Sector in Indonesia | Indonesia | Water and Other Urban Infrastructure and Services | 1999-09-30 | Important project benefits, such as targeting of the poor and addressing the needs of women, will only be achieved if the participation of such groups in the project is actively encouraged. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Project Design: Project design Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Targeting Standards of O&M are still inadequate, as evidenced by the high levels of Unaccounted For Water (UFW), intermittent operation, erratic or declining levels of production, and inadequate spending on O&M. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Health and sanitation management The lack of performance indicators for institutional strengthening makes it difficult to evaluate its effectiveness and impact, and is a notable weakness. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Capacity Development: Capacity building The priority for ADB should be to encourage the privatization of the larger successful local water and sewerage enterprises to serve as role models and lead the recovery of the sector. project cycle stage: Concept Lesson Topics: Sector Related Issues: Urban sector/development Policy & Reform: Privatization Policy & Reform: Reform There is an urgent need for a revised tariff structure, based on the principles of economic efficiency, financial viability, social equity, and administrative simplicity. However, setting loan covenants to make adjustments in the tariff structure should be accompanied by the government's will to implement the decision, which is a difficult process. project cycle stage: Feasibility Lesson Topics: Loan Agreement: Covenants Project Design: Project design Sector Related Issues: Health and sanitation management | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/bank-assistance-water-supply-and-sanitation-sector-indonesia
Fisheries Infrastructure (Sector) Project (Loan 693-INO) | Indonesia | Agriculture, Natural Resources, and Rural Development | 1997-12-31 | ADB should ensure that it provides an appropriate mix of expertise for project supervision. This is particularly important where ADB establishes a procedure, such as the review of subproject feasibility studies, to ensure implementation prudence. project cycle stage: Feasibility Lesson Topics: Project Design: Subprojects Project Management: Project supervision Detailed, accurate information is required for making investment decisions. Many of the fish landing centers were developed using information that was too broad to be of any use in gauging the impact of increased fishing effort in specific localities. In the absence of reliable information, a more conservative approach is warranted. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Sector Related Issues: Rural development For sector projects, the capability of the executing agency for implementation is crucial. Particular care is needed in assessing the strengths and weaknesses of the executing agency at the time of project formulation. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Future fisheries infrastructure development should consider that (i) the remaining underexploited fishing grounds are likely to be fished by large commercial ventures as opposed to small, artisanal fishers. To encourage further development of commercial ventures, the elements that contribute to private sector decisions need to be understood before expensive infrastructure is built. It is difficult to predict private sector changes, and greater involvement of the private sector in the planning and development stages for such infrastructure is warranted; and (ii) for the artisanal fishers who typically catch small pelagic fish, comprehensive programs that act to limit fishing pressure on the small pelagic stocks and, where appropriate, provision of alternative livelihood opportunities to fishing may be needed along with any port infrastructure development. The focus of future infrastructure development for this group would probably not be on increasing catch, but on such aspects as reducing costs of landing and marketing fish, sector monitoring and regulation, fish quality, waste disposal, and health aspects. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach Port infrastructure by itself is not sufficient to encourage sustainable development of fishing. In particular, complementary policies to support desired private sector changes, and full recognition of the open or public nature of the fisheries resource are required. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/fisheries-infrastructure-sector-project-loan-693-ino
Food Crop Sector Program (Loans 1014/1015-INO[SF]) | Indonesia | Agriculture, Natural Resources, and Rural Development | 1997-12-31 | Obtaining detailed and sound analyses of the sector as a basis for formulating policy reforms is crucial, and this process must not be overly hurried. ADB's involvement in such policy formulation and dialogue extended over a period of nearly three years prior to loan approval. At the same time, however, due attention needs to be paid to the appropriateness and timing of targets established in meeting the policy objectives. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Targeting Sufficient attention must be given to the institutional requirements for implementing irrigation O&M targets. Familiarity with the new procedures in provincial and field offices themselves could have made the targets realistic. Formulators of targets should have sufficient knowledge of the legal and administrative steps that have to be taken at each level of government before implementing new measures. In addition, greater beneficiary participation and commitment to O&M and cost recovery could have obtained with (i) greater attention being given to strengthening local water resources staff capacity, and (ii) better integration of agriculture and irrigation services. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Operation and maintenance Project Management: Project administration Capacity Development: Capacity building Capacity Development: Institutional analysis Capacity Development: Ownership Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Targeting The revised program lending policy, although introducing the concept of relating the size of the loan to the cost of implementing the reforms, remains unclear as to what proportion of the cost is appropriate for ADB to finance, leaving it largely to the initiative of the mission leader. This loan followed two large program loans already provided and the size of the country program to Indonesia seems to have influenced the size of the loan, rather than the possible costs of the reforms. While suggesting that the cost of reforms should be a key element in determining the size of a program loan, in the country context a degree of influence or leverage can only be achieved if the size of the loan is also commensurate with the scale of the country program. It is appropriate for ADB to give greater consideration to this issue. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Policy & Reform: Reform | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/food-crop-sector-program-loans-10141015-inosf
Ninth Road (Maintenance) Sector Project (Loan 863-INO) | Indonesia | Transport | 1997-12-31 | International consultants proved useful for overseeing the design and construction supervision activities as their involvement overcame the weakness in the certification system for domestic consultants. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Project supervision Maintaining roads in good condition will generate substantial benefits through lower vehicle operating costs, lower routine maintenance, and avoidance of subsequent expensive rehabilitation works. Periodic maintenance by itself is not always capable of providing a durable surface, especially where the road foundation is weak. The focus on just periodic maintenance may not always be appropriate. Future projects should consider a wide range of possible works including road betterment or upgrading. This is particularly appropriate if the road network has been brought up to a reasonable overall condition, allowing the problems of capacity, localized structural weakness and geometric conditions to be addressed. project cycle stage: Feasibility Operation Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Roading The Simplified Final Engineering Design Model (SFED) does not produce an accurate basis for project planning or the tendering of works. A more detailed and accurate database and data collection system that will eliminate errors and averages is required. Until the deficiencies in this planning tool can be resolved, future road projects should provide for the preliminary design and evaluation of candidate roads under more conventional procedures prior to their inclusion as part of the project. Where the SFED continues to be used, the introduction of a process of rapid field confirmation of the SFED -generated designs will be beneficial, and the terms of reference for detailed design consultants ought to provide flexibility for the employment of short-term specialists to address any problem which may not have been brought out in the preliminary designs. project cycle stage: Design, Feasibility Lesson Topics: Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Consultants Sector Related Issues: Roading | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/ninth-road-maintenance-sector-project-loan-863-ino
University of Sriwijaya Project (Loan 737-INO) | Indonesia | Education | 1997-12-31 | The decision to establish an energy study program was justified by the availability of natural resouces in the region. It would have been necessary to review existing study programs offered by other universities (competitors), and the demand for and supply of graduates to determine the challenges and scope of establishing such a program. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Education Sector Related Issues: Energy planning/management The suggestion of the PPTA consultants to increase interdisciplinary teaching overlooked strong disincentives for doing so. Interdisciplinary teaching would require that students register in courses at several faculties. Since tuition fees are paid to the faculty where students are registered, interdisciplinary teaching would split tuition fees among several faculties. Apart from the little interest of faculties to share tuition fees, an administrative system for doing so is not place. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Sector Related Issues: Education | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/university-sriwijaya-project-loan-737-ino
Impact Evaluation of Bank Operations in the Industrial Crops and Agro-Industry Sector in Indonesia | Indonesia | Agriculture, Natural Resources, and Rural Development | 1997-08-31 | In addition to the use of conservative yield assumptions during appraisal, appropriate risk analysis is needed. In the case of cotton, pests are always a potential problem while for the cocoa/coconut project, concerns were raised about the suitability of the area during project preparation. Evaluation of the effects of different assumptions for these factors on project viability may have led to alternative development proposals. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Management: Risks/Risk management Sector Related Issues: Rural development Project implementation targets need to be defined in terms of the development purpose, rather than simply in terms of physical achievements. Achievement of the latter may not necessarily lead to the project objectives. For example, the focus on crop cultivation targets for the cotton project was not consistent with the objective of raising farm income. The preparation of project frameworks during project identification and their subsequent refinement during project preparation and appraisal will help in this regard. By clarifying the relationships between goals and project inputs, and identifying the risks and means to monitor the program, this tool should facilitate flexibility during project implementation to enable inputs and outputs to be modified in line with changed circumstances. project cycle stage: Concept Feasibility, Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Problem identification Project Design: Project design Project Management: Risks/Risk management Methodologies/Approaches: Targeting Smallholders do not generally adopt high input, high output production systems. Even in the Nucleus Estate and Smallholders oil palm projects which provide a relatively assured and high income, the smallholder producers use lower than recommended amounts of fertilizer and adopt relatively low management standards. This is not to say that low input, low output systems cannot produce good returns, but that an appropriate balance must be achieved between the expected output and the investment. Project preparation and appraisal studies should give particular attention to this issue in the design of smallholder components, and should use conservative assumptions about farmer responses and the yields that are to be expected. This will help avoid arrangements where smallholders will have difficulty in repaying credit packages. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Rural development The matching of processing capacity with actual crop outputs has not been adequately achieved to date in ADB-assisted projects. This appears related to the use of overoptimistic assumptions regarding yields and the need to establish all of the processing capacity under the ADB loan. Underachievement of area targets also has contributed to the underutilization of processing capacity. All of these cases point to the need for more detailed analysis at the time of appraisal, and exploration of ways of funding a more progressive buildup of processing capacity. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Design: Project design Sector Related Issues: Rural development The Nucleus Estate and Smallholders (NES) projects can reduce poverty and generate national economic benefits. The experience so far suggests that a successful outcome requires (i) strong profitability of the core productive unit or crop; (ii) adequate capacity and capability of the nucleus estate and/or mill operator to implement and operate the scheme; and (iii) a strong interdependence, for example, through product processing, between the nucleus estate (and/or mill operator) and the smallholders to facilitate credit recovery. For the completed ADB projects, these conditions were achieved only for the oil palm projects. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financial management Capacity Development: Capacity assessment Sector Related Issues: Rural development There do not appear to be any significant and widespread price incentives for smallholders to produce higher quality industrial crops such as cocoa and rubber. Smallholders can obtain similar incomes whether they smoke dry their rubber or sell it in low quality lump form, and sun-dried cocoa beans earn just about as much as fermented beans and require much less effort on the part of the producer. Given this situation, efforts to improve smallholder incomes through improvements in the quality of crop outputs will be difficult and project proposals built upon improving product quality will require detailed assessment of the commercial operations of produce traders. project cycle stage: Concept Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Problem identification Project Design: Project design Sector Related Issues: Rural development | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-bank-operations-industrial-crops-and-agro-industry-sector-indonesia
Health and Population Project (Loan 743-INO) | Indonesia |  | 1997-06-30 | Experience with this project reconfirmed the importance of (i) a clear and well-focused Project Design, where inputs are necessary and sufficient to attain objectives; (ii) well-analyzed and articulated reasons for ADB's intervention; (iii) an accurate analysis of the financial implications of the project to ensure that counterpart funds and operating budgets are available; (iv) baseline data needed to set and attain specific targets; (v) a project office to ensure timely implementation of subprojects, which seem otherwise to lack ownership among regular staff not specifically paid to follow-up on ADB-financed subprojects; (vi) training of counterpart staff in project administration and reporting requirements; (vii) careful monitoring and supervision by ADB of complex projects such as this; and (viii) close coordination and cooperation among various aid agencies. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project administration Project Management: Project reporting Project Management: Project supervision Capacity Development: Capacity building Methodologies/Approaches: Targeting The project demonstrates the importance of a well-structured project design according to the principles of the logical framework. It is essential that inputs and activities are of such nature that they can attain objectives and goals. It was correctly assumed that the health status of the population could be improved by better quality health services. However, the project focused on improving the physical environment of hospitals, which contributes only indirectly to the quality of medical services. It would have been useful if (i) targets had been set for each hospital's contribution toward attaining sector goals (contributions to improved health services that can be verified by measurable indicators, and operational targets for efficiency and quality); (ii) reasons for shortfalls in reaching these goals had been identified (including external factors such as an increasing number of private hospitals); or preference for traditional medicine, which may improve the health status of the population while adversely affecting the utilization rates of hospitals; and (iii) necessary improvements (including a cost-benefit or cost-effectiveness analysis) had been determined on this basis. An additional advantage of planning a project in this way would be that hospital management and local governments could have been involved in defining targets and project inputs, and could have been made aware of operating expenses and other inputs in terms of staff time and abilities needed. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Indicators Project Design: Project design Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Targeting When deleting project components, like the consultant services on O&M, it is necessary to assess how far this will affect the possibility of attaining project objectives. If the latter would be jeopardized, it is necessary for ADB to analyze whether it agrees to a change of objectives. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Operation and maintenance | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/health-and-population-project-loan-743-ino
Land Resource Evaluation and Planning Project (Loan 730-INO) | Indonesia | Agriculture, Natural Resources, and Rural Development | 1996-12-31 | Accurate needs assessment at the time of project formulation would have given increased attention to capacity building for sustainable development. Association of the ultimate data users in defining the data to be collected would have ensured that the data produced meet with the users' requirements. The project would have benefited from a more careful assessment of the utilization of data available at appraisal. The project largely discounted valuable Regional Physical Planning Programme for Transmigration material about the land systems of Sumatra, preferring to proceed and identify new land units. This required further work, which was not cost-effective. project cycle stage: Feasibility, Appraisal Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Project Design: Appraisal Project Design: Project design Capacity Development: Capacity assessment Capacity Development: Capacity building Expectations about the sustainability of project benefits should be realistic. It was too optimistic to expect that the provincial/regional development planning agencies would be self-sustaining in their land use planning roles utilizing GIS technology at the end of the project implementation period. Continuation of required inputs for two years after project completion would have helped ensure that the computer systems put in place were functioning with adequate funding for their maintenance and upgrading, and that the methods and techniques of resource evaluation and planning were understood and applied on a daily basis by the provincial/regional development planning agencies. project cycle stage: Completion Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Operation and maintenance Capacity Development: Technology/Technology transfer In addition to sustaining technical capabilities in user agencies, project outputs need to be presented in a manner such that users can readily assimilate them into their intended activities. Some of the data supplied by the National Coordinating Agency for Surveys and Mapping and Center for Soil and Agroclimate Research to the provincial/regional development planning agencies are not in readily usable formats. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Reporting Capacity Development: Capacity building Project components should be appropriately sequenced. The timing of the arrival of consultants and the equipment which they need should be correctly planned and synchronized. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Consultants There is a risk inherent in entrusting a technical agency with coordination work outside its jurisdiction. Making the National Coordinating Agency for Surveys and Mapping (BAKOSURTANAL) responsible for the coordination of project activities skewed the project during implementation towards supplying data to the provincial/regional development planning agencies, the area the former knew best and was most comfortable with, rather than strengthening them in the application of data, which was the project's original objective. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation There is little value in supplying expensive equipment that cannot continue to be used and upgraded when necessary. The cost of supply of equipment comprised nearly one quarter of the total loan disbursements with the majority being computer hardware and software. The experience of the project highlights the importance of ensuring adequate funding for equipment maintenance and for upgrading hardware and software. Special arrangements need to be made for maintenance of equipment in remote areas. project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Operation and maintenance Project Management: Procurement Capacity Development: Technology/Technology transfer There was a need to balance specific technical training with more general training, such as hands-on courses designed to teach operational and computer maintenance skills. Decision makers at senior level would also have benefitted from short courses, placing of the project in the wider context of their strategic and policy responsibilities. project cycle stage: Feasibility Lesson Topics: Project Management: Management information system Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity building | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/land-resource-evaluation-and-planning-project-loan-730-ino
Irrigation Package Project (Loan 581-INO) | Indonesia | Agriculture, Natural Resources, and Rural Development | 1996-09-30 | In the design of rehabilitation projects, the optimum level of investment should be studied carefully because the impact of rehabilitation on agricultural production may not be as large as is often thought. Rehabilitation per se does not bring about appreciable increases in crop yield unless such rehabilitation makes a real difference in the availability of water. Therefore, potential benefits of rehabilitation schemes need to be researched carefully. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development Institutional capacity in the sector requires improvement. Improvements are needed particularly in the executing agency's quality control over feasibility studies and engineering design. Cost recovery including the collection of irrigation service fee should be further strengthened although progress has been made in the institutionalization of irrigation service fee. Decentralization of responsibility for irrigation O&M to provincial agencies continues to be delayed because such transfer involves reduced central government support for O&M costs. The financial support for O&M should not hinge on the transfer of responsibility. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Institutional analysis Country Context: Decentralization Sector Related Issues: Irrigation management The appropriateness of the traditional objectives associated with irrigation projects requires review. The study country has already achieved rice self-sufficiency and is poised to become a rice-exporting country. Under the circumstances, economic viability, commitment of beneficiaries, and cost recovery should become an increasingly important criteria in screening irrigation projects. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Capacity Development: Ownership Sector Related Issues: Irrigation management Well-designed and well-maintained schemes are essential for the success of irrigation schemes. This is particularly true given the present and projected levels of the price of rice. Many feasibility studies and engineering designs have not been thorough. Project experience points out, in particular, that it is necessary to take a river-basin approach to the management of water resources in areas with potential scarcity of water. Such an assessment of water resources should take into account drinking water and industrial water requirements as well as irrigation. project cycle stage: Design, Feasibility Operation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Irrigation management Sector Related Issues: Water resource management | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/irrigation-package-project-loan-581-ino
Seventh Road (Sector) Project (Loan 692-INO) | Indonesia | Transport | 1996-05-31 | The executing agency's simplified engineering design procedure has been an effective way of determining road upgrading and has supported the rapid implementation of road upgrading in rural areas. The practice, however, could be further improved by ensuring that (i) adequate field data are assembled prior to commencement of Simplified Final Engineering Design (SFID) activities; (ii) sufficient time is scheduled for field surveys; (iii) experienced personnel are recruited, and (iv) contractors are required to complete all survey and testing activities within a specified period. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Roading Sector Related Issues: Rural development The project clearly demonstrates the importance of enforcing vehicle weight regulations particularly for the trucks. The design standards set by the executing agency have been appropriate for rural conditions, only if overloading is curtailed. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Roading Sector Related Issues: Rural development The project highlights the importance of adequate road maintenance, appropriate training of field personnel, and providing sufficient maintenance equipment, backed up by satisfactory workshop facilities. The government has achieved significant progress in upgrading its road maintenance capabilities over the past decade based on the policy dialogue and assistance provided by ADB in the road sector. Further field training of staff (in the executing agencies and contractors) is required to ensure that the latest techniques in applying asphalt materials are utilized. project cycle stage: Operation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Roading Policy & Reform: Policy reforms/framework There is an urgent need to maintain and circulate up-to-date road accident statistics, particularly to identify where serious accidents have occurred. For the project, it was not possible to identify the nature of the problem, on a road-by-road basis, because of the inadequate data base. The policy dialogue in relation to rural roads should include the need to upgrade road accident data collection and analysis, on a network basis. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Sector Related Issues: Roading Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/seventh-road-sector-project-loan-692-ino
Agro-Industries Credit Project (Loan 881-INO) | Indonesia | Agriculture, Natural Resources, and Rural Development | 1996-01-31 | Project experience highlights the importance of designing the capacity building component. While an institution building component was built into the project through an advisory TA, there was no direct link between the TA and the project, and as a result, neither of the executing agencies benefited from the TA. The active involvement of government and executing agencies, their commitment to the project, efficient implementation, and sustainability are all functions of institutional capacity. In the case of one of the executing agencies, capacity building should have focused on project administration and supervision. The executing agency did not have the capacity to handle environmental aspects of loans. An advisory TA addressing these aspects should have been granted prior to the loan. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Ownership The project highlighted the importance of adhering to an identified pipeline at appraisal. For loans involving credit lines to DFIs for a particular subsector such as agro-industries, the pipeline of subprojects to be financed at appraisal has supposedly been studied for consistency with the government's macroeconomic development and sectoral plans, so that any deviation from the established pipeline might undermine this consistency. The subprojects that are performing well such as rattan, animal feed, and crumb rubber belong to sectors that were included in the original pipeline of subprojects eligible for financing whereas problem accounts belong to sectors outside this pipeline. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Subprojects There is a need for ADB to assess the institutional capacity of the executing agency at appraisal, particularly with respect to subproject evaluation and project supervision. Agro-industries projects involve high risks, indicating the importance of sensitivity analysis in the appraisal of subprojects. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project supervision Project Management: Risks/Risk management Capacity Development: Institutional analysis | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/agro-industries-credit-project-loan-881-ino
Fifth Port Project (Loan 375-INO) | Indonesia | Transport | 1995-11-30 | Greater attention at appraisal should be paid to emerging trends of cargo shipment and future traffic growth and their implications for long-term investments in civil infrastructure. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Appraisal Project Design: Project design The construction of new berths can reduce port congestion. However, operational improvements of existing facilities can delay the need for investment in new facilities. Such operational improvements should be sought as a first step prior to undertaking new construction. The change in work hours by the stevedores between 1980 and 1985 demonstrated that even seemingly difficult labor arrangements need not be a constraint to the adoption of operational improvements. project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Project management Sector Related Issues: Transport planning The project highlights the benefits of maintaining a flexible attitude toward project design during implementation. This was demonstrated by the change in the design of the project so as to provide a container handling capability, despite knowing that delays in project implementation would occur. This change enabled a dramatic increase in the containerization of cargo and better port efficiency and financial performance of the executing agency than would otherwise have resulted. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/fifth-port-project-loan-375-ino
Institutional Support to Water Supply Enterprises in Indonesia | Indonesia | Public Sector Management | 1995-08-31 | An accurate assessment of the effective demand for the services to be provided and the absorptive capacity of the proposed beneficiary agencies are fundamental in advisory TAs. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development In serious attempts at training instructors and institutionalizing training, there must be at least one long-term consultant to oversee a number of training courses conducted by instructors. It is not enough to give instructors one-week additional training in instructional techniques; they must have on-the-job training i.e., in conducting training courses. project cycle stage: Feasibility Lesson Topics: Project Management: Consultants Capacity Development: Capacity building | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/institutional-support-water-supply-enterprises-indonesia
Second Irrigation Package Project (Loan 627-INO) | Indonesia | Agriculture, Natural Resources, and Rural Development | 1995-02-28 | A BME system needs to be standardized and integrated with the management information system. Socioeconomic surveys should become a routine part of a feasibility study not only to more accurately ascertain the present agro-economic conditions and household incomes but also to involve potential beneficiaries in the planning of projects and choice of crops. In order to make better use of BME systems, the involvement of national agencies (such as the national development planning agencies) should be considered. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Management information system Due to the dominant effect of the price of rice on the viability of irrigation projects and the volatility of rice prices in the world market, it is necessary to take a cautious view in the design of irrigation projects that may lead to producing exportable surplus of rice. The factors critical in the selection of such projects are, inter alia, large realizable incremental benefits, suitability of the physical conditions, good O&M potential in terms of the willingness to pay irrigation service fees, and community leadership and participation. Where conventional technologies are not economically viable, the use of cost-effectice, small-scale and viable technologies needs to be explored. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Capacity Development: Technology/Technology transfer Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Institutional capacity is a continuing concern in the sector. Improvements are needed in procedures for the prequalification of contractors, quality control of feasibility studies and engineering design, the standard of construction supervision, cost recovery including the collection of irrigation service fees, and O&M including the organization of water users associations. For areas with soil, geological and topographical problems, more thorough technical studies including engineering design should be prepared prior to appraisal. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Operation and maintenance Project Management: Procurement Project Management: Project supervision Capacity Development: Capacity building Sector Related Issues: Irrigation management The appropriateness of the traditional objectives associated with irrigation projects requires review. In a country which has achieved rice self-sufficiency, the impact of irrigation projects in employment increase is modest and may need to be viewed as an attendant benefit. Of the objectives mentioned in the Appraisal Report, that of increasing the living standards of farmers by raising incomes appears more relevant in the context of poverty reduction. Even in the pursuit of an income objective, it needs to be recognized that irrigation may be just one of the several options available to increase farmers' incomes. For this reason, the planning for rural area development should become increasingly multisectoral. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Sector Related Issues: Irrigation management Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-irrigation-package-project-loan-627-ino
Bank Assistance to the Urban Development and Housing Sector | Indonesia, Malaysia, Pakistan, Thailand | Water and Other Urban Infrastructure and Services | 1997-12-31 | A new town strategy has the clear advantage of an organized town structure with a full complement of urban services that can be created, including social, commercial, and industrial areas. Setbacks, however, can arise from the cost and availability of land - a problem increasingly encountered as megacities expand forcing new towns into less attractive locations, limiting their size, and reducing their effectiveness in diverting pressure from primary cities. project cycle stage: Feasibility Lesson Topics: Project components are implemented separately, often in areas that are not linked, so that no systematic infrastructure network is developed. Synergetic effects - one of the main rationales for the approach - cannot be attained in this way due to the following problem: the larger the number of subsectors included in an integrated project, the greater the risk that firstly, resources are spread too thinly, thus reducing the significance and likely impact of each intervention project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Urban sector/development Methodologies/Approaches: Holistic approach Providing urban infrastructure and services to underdeveloped regions of a country, thus integrating them into the national economy and the country's infrastructure network is an important contribution. project cycle stage: Feasibility Lesson Topics: The roles of agencies at the beginning of a project are not specified and neither are expectations in the institution at the end of a project. Apart from this design flaw, consultant services and training are not integrated into institutional reform programs that include reviewing and deciding on the role of the institution as regards the private sector, and analyzing internal work procedures to attain efficiency gains. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Institutional analysis Sector Related Issues: Private sector The service orientation of public agencies that provide municipal services is inadequate because their policies and services are not focused on clients and customer satisfaction. Under such circumstances, capacities to analyze demand, ability, and willingness to pay; design services which meet demand; and collect, process, and adjust to feedback on client satisfaction are limited. project cycle stage: Feasibility Lesson Topics: These factors have become even more crucial in times when local authorities are responsible for loan repayment, thus want to influence the choice of subprojects, their location and technical standards, and ensure that projects do not have a negative impact on their financial position. project cycle stage: Concept Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Institutional analysis | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/bank-assistance-urban-development-and-housing-sector
Support for Trade Facilitation in the Brunei Darussalam-Indonesia-Malaysia-Philippines East ASEAN Growth Area: Technical Assistance Completion Report | Indonesia, Malaysia, Philippines | Industry and trade | 2015-04-01 | Some lessons from the TA (technical assistance) implementation include: (i) rigorous diagnosis and further refinements in TA design based on regular consultations with both government agencies and the private sector are important to maintain TA relevance and client ownership; (ii) challenges from the clients' staff turnover on implementation could be mitigated through regular consultation with their management and broader participation in TA activities, while changes in priorities and delays resulting from management's turnover were harder to mitigate and hence affected the delivery of outputs and the attainment of outcomes; (iii) data collection and analytics to demonstrate results should be made more vigorous with active participation from clients to supplement the administration of the TA and garner stronger support from relevant government authorities; and (iv) trade facilitation needs to be linked more closely to trade policy and investment promotion by countries in order to generate more traffic demand so that more efficient controls would result in greater flows of goods and people, thereby contributing to achieving outcome and impact. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-for-trade-facilitation-in-bimp-eaga-tcr
Public-Private Partnership Development in Brunei Darussalam-Indonesia-Malaysia-Philippines East ASEAN Growth Area and Indonesia-Malaysia-Thailand Growth Triangle: Technical Assistance Completion Report | Indonesia, Malaysia, Philippines, Thailand | Agriculture, natural resources and rural development, Education, Energy, Finance, Industry and trade, Public sector management, Transport | 2015-07-01 | The scope of the TA (technical assistance) was overly ambitious and the difficulty in identifying viable PPP (public-private partnership) projects with a subregional dimension was underestimated. Due to inadequate reconnaissance and analysis of the scope and demand for PPPs at the regional level prior to preparation of the TA, there was a lack of viable regional PPP projects for pre-feasibility studies. Similarly, the establishment of a subregional PDF was not grounded in any assessment of the nature or function of such a facility, or its underlying need. The major lesson is that viable PPP projects are in short supply, and a TA to prepare feasibility studies for undefined projects was premature. The lack of viable regional projects meant that the demand for the PDF (project development facility) was also overestimated. Thus, another lesson is to ensure that there is adequate demand and need for a subregional PDF facility before preparing a TA to establish a PDF. Despite these shortcomings, the changes in scope enabled the TA to support the preparation of GCAPs (Green City Action Plans) and to identify potential urban PPP projects under the IMT-GT (Indonesia-Malaysia-Thailand Growth Triangle) GCI (Green Cities Initiative). Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report |  | http://wcm.adb.org/projects/documents/public-private-partnership-development-in-bimp-eaga-and-imt-gt-tcr
Strengthening Sound Environmental Management in the Brunei Darussalam, Indonesia, Malaysia, and Philippines East ASEAN Growth Area: Technical Assistance Completion Report | Indonesia, Philippines | Agriculture, natural resources and rural development | 2015-07-01 | Foremost is the need for continued dialogue and engagement with the BIMP-EAGA (Brunei Darussalam, Indonesia, Malaysia and Philippines-East Asia Growth Area) countries and key groups within the BIMP-EAGA institutional structure (e.g., Environment Cluster Working Group) to rally support for endorsement by Malaysia and then by senior officials of the REP (Regional Environmental Program). Within ADB, this can be done in coordination with SERD's (Southeast Asia regional Department) Regional Cooperation and Operations Coordination Division, which has a country specialist for Malaysia. It may be possible to get Malaysia on board because of its active engagement in the CTI (Coral Triangle Initiative) and HOB (Heart of Borneo) programs and its support to ADB's TA (technical assistance) projects on these initiatives. The only challenge in moving the REP forward is the sustained commitment of human and financial resources, particularly from countries. This will require the establishment of a BDU (business development unit) or a project facilitation unit for BIMP-EAGA. The BDU will liaise with countries, review, prepare and incubate projects, assist countries to develop project formulation and management capacity, and assist donors and countries to undertake monitoring and evaluation exercises. The BDU would need to be initially funded by ADB but would eventually be supported and based within the BIMP-EAGA secretariat or nodal agency. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-sound-environmental-management-asean-growth-area-tcr
Environment Capacity Development Projects in Indonesia and the Philippines | Indonesia, Philippines | Agriculture, Natural Resources, and Rural Development | 2010-11-30 | 1. Capacity development for environmental management introduced alongside broader administrative reform program (such as decentralization) could promote environmental protection efforts had there been clear transfer of functions to and assignment of roles at the local level as well as prior capacity development. Capacity development for environmental management is inherently difficult due to its cross-sectoral nature. Success depends greatly on the buy-in from the sector it aims to influence. When capacity development is introduced alongside a broader administrative reform program, such as political decentralization, environmental technical assistance (TA) is likely to be closely tied to progress in the wider effort. Environmental reform, in effect, becomes vulnerable to broader administrative reform. Indonesia?s environmental impact assessment capacity-building TA, in particular, suffered because the functions of local government remained unclear during reforms and bureaucratic capacity and efficiency, local technical capacity and transparency, and accountability were insufficient, as was support for learning and innovation. The TA tried to make up for these deficiencies but could not bridge the capacity gap. [Main text, paras. 31,46,60,90] project cycle stage: Implementation, Completion Lesson Topics: Capacity Development: Capacity development Capacity Development: Ownership Policy & Reform: Reform 2. Continued funding and policy support are needed to sustain outcomes of environmental capacity development efforts. Environment management initiatives are typically underfunded due to their externality nature, often considered an unintended consequence of a development activity; making sustainability a crucial factor. For instance, the SME cleaner production TA in Indonesia lacked suitable government policies and institutional mechanisms to ensure continued financial and technical support which hampered mainstreaming of cleaner production in the sector. When formulated, the TA did not fully address the question of how to sustain the activities that the project championed. Environmental capacity development generally attracts less sustained funding than capacity development in sectors such as transport and energy, with their potential to generate revenue. Particular attention in environmental capacity development must, therefore, be given to the sustainability of financial support. Successful examples of securing resources for environmental purposes must be drawn upon including the use of market-based instruments, environment user fees as pollution charges, and payments for ecosystem services. [paras. 54,72,78,91] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Capacity Development: Capacity development 3. ADB's technical assistance (TA) sequencing is critical for introducing new environmental and technological concepts especially in many developing member countries (DMCs) where environmental capacity has yet to be established. The example provided by the small and medium enterprise (SME) cleaner production TA is typical. It was approved only 2 months after the approval of another TA on strengthening business development services (BDS) for SMEs. The BDS TA was to support implementation of key recommendations of a medium-term action plan including promoting SME BDS, simplifying regulations, and ease SME access to credit?an ambitious scope of work in itself. These TA projects implemented in parallel by two executing agencies lacked justification and did not ensure synergy. This evaluation supports the findings of the 2006 special evaluation study on TA performance that recommended that CPS ?should include a clear strategy and program for TA with a long-term framework and measurable indicators of expected outcomes.? Evaluation also acknowledges that ADB has made progress in this regard by using sector assessment strategies and road maps alongside CPS formulation so that TA projects can be more firmly anchored in a DMC?s national development planning agenda and long-term sustainability can be made more likely. [Main text, para. 92, Appendix 4, paras. 15-16,35] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Capacity development Methodologies/Approaches: Targeting 4. Strong provincial capacity is required in the establishment of an efficient country safeguard system. The impact of efforts to strengthen institutional and technical capacity through the technical assistance projects remained weak. Hence, the need to continue developing the capacity of environmental offices in Indonesia and the Philippines for more efficiency in administering the environmental impact assessment process, environmental mitigation planning, and implementation. Possible areas of intervention in Indonesia should include (i) streamlining functioning and institutional mandate of provincial and regional environmental agencies, (ii) improving inter-government and inter-ministerial coordination in resolving regulatory and institutional gaps, (iii) greater political and institutional support for Industrial Performance Rating Program, and (iv) developing a master plan for national capacity building for environment management with donor coordination. In the Philippines, improvement can be made in simplifying the EIA process, more efficient project categorization, alternative analysis, and public disclosure. Both countries can benefit from further strengthening of the technical skills of implementing institutions, improving their use of strategic environment assessment as a tool in regional development planning and strict enforcement of post construction environmental monitoring. [Main text, paras. 60-63,93] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Capacity Development: Capacity development 5. Anticipating institutional and other changes during a technical assistance (TA) project?s lifetime should be an inherent goal of TA formulation. Waning interest in TA objectives by an executing or partner agency is not uncommon, as the Metropolitan Manila Development Authority demonstrated to some extent in the Pasig environmental management project. Continuous support of individuals and institutions cannot be taken for granted. Building solid relationships with the executing or implementing agency to shield the TA from the effects of personnel changes should be considered as important as the delivery of the project?s technical content. TA team leaders must be more than technicians. They must be able to engage the entire hosting organization. A TA with resiliency built-in will ultimately benefit the client organization itself by also making it less dependent on individuals. Adequate consideration of the dynamics of underlying conditions must remain an essential part of TA design. [Main text, paras. 79,94] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Capacity Development: Partnerships 6. A more focused technical assustance design can achieve better results in capacity development. Too many activities tend to weaken TA focus. TA projects usually have shorter implementation duration than loan projects and need to avoid too wide a scope. Both the environmental impact assessment (EIA) capacity-building TA in Indonesia and the Pasig environmental management TA in the Philippines produced more outputs than the target audiences were able to fully use. These TAs also involved more than one executing agency. Reducing the number of participating organizations can often improve focus and lead to better targeting of TA capacity-building resources. [Main text, para. 95, Appendix 3 para 4] project cycle stage: Design Lesson Topics: Project Design: Project design Methodologies/Approaches: Targeting 7. Project duration needs to suit the current country context especially when it comes to introducing new technologies and addressing capacity issues in a dynamic institutional landscape. The TA projects in Indonesia were both implemented at a time when institutions were assuming new mandates and struggling to address new roles. Decentralization was moving rapidly and taking little account of weak implementation capacity in district and municipal environmental offices. The 1997 Asian financial crisis, moreover, had depleted the financial capacity and workforce of the SME sector, which made its ability to ramp up and engage with the SME cleaner production TA questionable. In both cases, designers could have considered longer project duration that would more likely ensure improved TA impact and sustainability of the outcomes. [Main text, paras. 81,96; Appendix 4, paras. 3,35] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Risks/Risk management Methodologies/Approaches: Targeting | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/environment-capacity-development-projects-indonesia-and-philippines
When Do Rural Roads Benefit the Poor and How? | Indonesia, Philippines, Sri Lanka | Transport | 2006-02-28 | Project design in the future should be much more explicit about theobjective of poverty reduction and that appropriate measures be included as the means ofachieving this. More pro-poor investments in the future require genuinely integrated projectcomponents that offer the poor, too, some opportunity to diversify and broaden livelihoods, andthus strengthen livelihood capital with which to make use of improved rural roads. For this,linkages with complementary activities and services, which support the broadening of livelihood opportunities for the poor, are needed. Simply improving a road is not enough; the poor alsorequire support in being able to make use of it. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach The ability of the poor and very poor to make significant economicuse of the road depends on their asset base and the entitlements to resources and opportunitiesthat they can command, as well as the passage of time. In a few instances, the poor who haveinvested savings in a small business or used their skills have graduated from poverty, using thebenefits from the road. However, the poor and very poor primarily benefit through the indirectimpacts of road improvements, of better access to state services and improved provision ofservices to the village, and of opportunities in alternative livelihood income streams where thepreconditions for their development are right. The poor can also benefit broadly fromimprovements to the rural economy through increased opportunities for agricultural wage labor,but again these impacts are contingent on favorable preconditions being in place. Thepreconditions shaping the potential for development of an area can be classified broadly intotwo groups: external conditions (macro factors) and structural poverty problems. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Impact evaluation Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Roading Sector Related Issues: Rural development The case studies selected in each country were either sector road investments orintegrated projects. The impact of improved transport services that enhanced competition andreduced transport costs for the entire community (especially those using regular transport)appeared to be greater in the transport sector projects. Under the integrated projects, it wasanticipated that the poverty reduction impact would be greater as roads were linked to otherinvestments, which could broaden livelihood opportunities for the poor. In practice, however, thiswas not always the case. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Modality: Program Crosscutting Issues/Themes: Employment Sector Related Issues: Roading Policy & Reform: Reform Methodologies/Approaches: Holistic approach The poor and very poor assign a high priority to basic access. It reduces theirvulnerability, and they consider it a matter of dignity to be able to communicate with the outsideworld and engage in social activities outside the village. The increased availability of intermediate modes oftransport with larger carrying capacity to collect water, firewood, etc., is likely to have a greaterinitial impact on their well-being. They need to first accumulate surpluses even periodically to beable to seize new opportunities that motorized transportation may bring. project cycle stage: Concept Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Sector Related Issues: Roading | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/when-do-rural-roads-benefit-poor-and-how
Small and Medium Enterprise Investment Program - Tranche 1: Completion Report | Kazakhstan | Finance | 2015-09-15 | The project experienced disbursement delays to SME (small and medium-sized enterprise) sub-borrowers, partly due to safeguard requirements. Significant support from the project team was required and signaled the need for PFIs to adopt a minimal ESMS (environment and social management system) to be able to meet categorization requirements. It also showed the importance of continuous dialogue, awareness raising, and capacity building, crucial to making safeguards an important consideration in the credit decision-making process and to the sustainability of the results. ADB's support increased the capacity of the PFIs (participating financial institutions) and improved their standing with other donors and funders. project cycle stage: Implementation Damu charged a uniform margin to all PFIs (participating financial institutions). In line with the government's intention that Damu function effectively on a self-sufficient basis, Damu should have priced its loans to PFIs according to risk. This intention was limited both by the project's design and by Damu's capacity. A minor change in the MFF (multitranche financing facility) has given Damu the flexibility to charge market-based margins to improve its sustainability and reward better-performing PFIs. project cycle stage: Feasibility, Implementation Up-front disbursement to the PFIs (participating financial institutions) of the entire loan amount was required by the funding mechanism used for the tranche. While this helped avoid problems in the financing of subprojects, it also limited the option to reward better-performing PFIs. In this case, the only available incentive mechanism was participation in future tranches under the MFF (multitranche financing facility). project cycle stage: Design, Implementation The overall objective of supporting SME (small and medium-sized enterprise) medium-term lending was only partially achieved. A key success factor lies in the selection of PFIs (participating financial institutions), which should be sustainable finance providers. The development of SME portfolios requires not only exceptional liquidity support at a time of liquidity squeezes, but also a strategic commitment and adequate capacity and technical expertise of PFI staff and their SME clients. While the parallel TA (technical assistance) contributed to this, more targeted assistance could have improved the performance of the project. Additional covenants could have been added to improve its impact. Limited access to finance for SMEs is also linked to other factors, such as financial infrastructure deficiencies, supervisory weaknesses, and the overall health of the financial sector, which could not be addressed through a credit line intervention. project cycle stage: Feasibility, Implementation Finally, the DMF (design and monitoring framework) indicators were not appropriate to assess the overall effectiveness of ADB's intervention. The performance indicators should have been more accurate, better defined, and aligned with the stated impact and outcome. The indicators also did not measure improvements in the loan maturity for SME (small and medium-sized enterprise) loans in the PFIs' (participating financial institutions) portfolio, which was considered relevant for development impact. project cycle stage: Completion, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/small-and-medium-enterprise-investment-program-t1-pcr
CAREC Transport Corridor 1 (Zhambyl Oblast Section) Investment Program - Tranche 1: Validation of Completion Report | Kazakhstan | Transport | 2015-02-10 | The PCR (project completion report) identified three lessons. The first lesson was the need for realistic cost estimates. To avoid loan cancellations, effective due diligence should be undertaken through detailed engineering studies, examination of market rates of construction materials and consultant remuneration, and inclusion of careful calculations of physical and price contingencies in the project cost estimate. The second was the need for clearly identifying the role of the project management consultant. The original terms of reference did not properly define the tasks and deliverables of each expert and considerable time for refinements was needed. The third was the need to improve the executing agency's project management capacity. Inadequate knowledge and expertise of MOTC (Ministry of Transport and Communications) and the Committee for Roads on safeguards and procurement affected smooth project implementation. This validation supports these lessons. In addition, the validation notes traffic forecasts should be much more realistic, and reflect impacts of follow on projects on expected usage. Similarly, more effort should be taken to establish sustainable asset management systems, supported by credible sources of funding. project cycle stage: Design, Feasibility, Appraisal, Implementation | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/kazakhstan-carec-transport-corridor-1-zhambyl-oblast-section-western-europe-western-people
CAREC Transport Corridor 1 (Zhambyl Oblast Section) Investment Program - Tranche 1 | Kazakhstan | Transport | 2014-06-01 | Need for realistic cost estimates. During implementation it was realized that costs for civil works and consulting services had been overestimated, and that contingencies were excessive, which resulted in cancellation of 33.8% of the loan proceeds. Furthermore, various changes in scopes and designs were required to accommodate the geological conditions and needs of local populations, which had not been identified at design stage. Robust due diligence should be performed at appraisal (e.g., through detailed engineering studies, examination of market rates of construction materials and consultant remuneration, and inclusion of careful calculations of physical and price contingencies in the project cost estimate). Need for clear identification of the role of the project management consultant. The expected role of the project management consultant for the investment program was unclear in the beginning, and the original terms of reference did not properly define the tasks and deliverables of each expert, which resulted in considerable refinements to the terms of reference during implementation. The roles and responsibilities should have been properly defined during project preparation. Need for further improvement of the executing agency's project management capacity. Inadequate knowledge on the part of Ministry of Transport and Communications and Committee for Roads relating to safeguards and procurement, and a lack of staff with appropriate expertise were major factors affecting smooth project implementation, and ultimately resulted in stakeholder complaints. Some improvement has been observed in the executing agency's project management capacity as a result of internal restructuring; establishment of a new unit for financial management; involvement of local authorities in efficient, close monitoring of projects; and adoption of a new national transport sector program. Nonetheless, providing continuous support for building capacity and enhancing knowledge to the executing agency and the newly established KazAvtoZhol Open Joint Stock Company is important, particularly for procurement, safeguards, and administration of contracts for civil works and consulting services. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/carec-transport-corridor1-zhambyl-oblast-western-europe-western-prc-t1-pcr
Kazakhstan: Countercylical Support Loan | Kazakhstan | Public Sector Management | 2012-12-10 | There is a need to ensure a better coordination between the sovereign and nonsovereign operations in ADB so that the two sets of operations can operate in the country in a seamless manner. This is especially important in view of the enhanced role of nonsovereign operations under Strategy 2020 in a high middle income country such as Kazakhstan. [Main text, para. 29] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Harmonization Project Management: Project management | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/kazakhstan-countercylical-support-loan
Countercyclical Support Loan | Kazakhstan | Public sector management | 2010-12-01 | ADB's business procedures for processing crisis response programs should be streamlined and abbreviated, as in the case of the Countercyclical Support Facility (CSF). This allows for crisis responses to be timely and prevent further deterioration of the economy. By not having any policy conditions other than the government's countercyclical expenditure programs, the Kazakhstan Countercyclical Support Loan (KCSL) was an effective and efficient instrument to respond to the financial crisis. While reforms to correct policy inconsistencies during crisis situations might be desirable, countries that are in the middle of financial crises would find it difficult to simultaneously undertake both crisis mitigation and reforms. What these countries need most urgently in times of financial crisis is quick and timely fiscal support to address the economic and social impact of the crisis. However, as crises open opportunities for reforms, policy dialogue should be initiated for follow-up operations. But such dialogue should not at any time delay the timely provision of financial crisis support. The success of a financial crisis response is highly contingent on the government's ability to quickly put together its own anti-crisis plan. ADB intervention can be in the form of financing for the anti-crisis plan. In the case of the KCSL, the government already had its employment-generation program (EGP) in place, and was able to use the KCSL funds immediately to finance the EGP. However, since the KCSL is a budget support instrument, it is difficult to track and link the financing with specific development results (e.g., which public works project it funded). Crisis response operations can be more successful if the government has well- defined implementation arrangements and monitoring mechanisms to be successful, as was the case with the KCSL. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/countercyclical-support-loan
Rural Area Water Supply and Sanitation Sector Project | Kazakhstan | Agriculture, natural resources and rural development | 2010-12-01 | Project targets should be achievable. Cost estimates should be based on thorough and professional assessments as part of a feasibility study, instead of aspirational or subjective considerations alone. Measures ensuring government commitment to implement institutional development and provide counterpart funds should be carefully reviewed and tied to the release of funds. Detailed design engineers and supervision and implementation consultants should be recruited in advance of project approval, to increase project readiness. The project implementation schedule should be realistic. Delayed payments to contractors adversely affect implementation. ADB and the government should work together to ensure timely disbursements. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/rural-area-water-supply-and-sanitation-sector-project
Road Rehabilitation Project in Kazakhstan (Loan 1455-KAZ) | Kazakhstan | Transport | 2005-12-31 | A comprehensive institutional and policy reform agenda requires intense policy dialogue and a high degree of engagement to ensure that the agenda has national ownership and is well supported by ADB during implementation. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation It is difficult to bring about overall change in policies, processes, and standards. An extended timeframe is often required. The design of the project assumed that international systems for road design, construction, and maintenance as well as road sector policies and institutions could be quickly transferred to Kazakhstan to replace those of the former Soviet Union (FSU). In practice, the road sector institutions and their professional and technical capacities were deeply aligned with FSU systems and could not be changed as quickly as ADB anticipated. In Soviet times they had been considered very successful, so it was difficult for them to accept the need to change. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Sector Related Issues: Roading Policy & Reform: Policy reforms/framework Policy & Reform: Reform Policy & Reform: Transition economies Rehabilitation of roads using existing embankments, roadbeds, and drainage inherited from the former Soviet Union (FSU) may involve uncertainties that could adversely affect the stability of the road base. In some cases these uncertainties may affect the life and economic returns of rehabilitation investments. This should be assessed when preparing new investment projects in FSU countries. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Roading Policy & Reform: Transition economies Road safety audit should be mandatory for all road projects and their road safety impacts need to be measured. project cycle stage: Design, Feasibility Lesson Topics: The following are specific lessons regarding the use of International Federation of Consulting Engineers (F d ration Internationale des Ing nieurs Conseils; FIDIC) contract methods in transition countries: (i) detailed designs and specifications should be of a high standard, since these will become the basis of the construction contract and cannot be changed subsequently without contract variation; and (ii) the government may require regular advice and support to ensure that it understands its role as employer, understands the roles of the consultant and contractor, and understands how to use FIDIC provisions to address problems encountered during construction including problems not foreseen in the contract, design, and specification. project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Roading Policy & Reform: Transition economies | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/road-rehabilitation-project-kazakhstan-loan-1455-kaz
Road Rehabilitation Project | Kazakhstan | Transport | 2004-04-15 | ADB has learned that the executing agency's opinion needs to be considered in procurement, even if the executing agency does not fully understand the procedures of ADB's Guidelines for Procurement. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Better and more project-specific terms of reference for the consultants (including the PPTA consultant), closer supervision, and more training in ADB procedures for the project implementation unit and executing agency, as well as advice in selection of consultants and contractors, would have reduced the technical problems during project implementation. project cycle stage: Design Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Project Management: Project supervision Capacity Development: Capacity building Many delays in the project were due to the executing agency's and the Borrower's reluctance to accept the international contract conditions, and the failure to honor the Engineer as the Borrower's representative in the project. The Borrower (represented by the Ministry of Finance) would have benefited from more and continual training in international competitive bidding (ICB) procedures and in application of ADB's various guidelines. project cycle stage: Design Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Capacity Development: Capacity building The executing agency has learned that it should be prepared to actively participate in project preparation (including PPTA and advisory TA) and to oversee the work of consultants and contractors to gain strong ownership in all project components and in all decisions made. In this project, the executing agency largely ignored the advisory technical assistance and the maintenance assistance during the civil works. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Procurement Project Management: Project supervision Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/road-rehabilitation-project-1
Basic Education Project | Kazakhstan | Education | 2003-12-15 | Systematic follow-up by the executing agency (Ministry of Education and Science or MOES) and Department of Education (DOE) on equipment procurement, delivery, and installation was inadequate. Given the on-going large-scale procurement of equipment, MOES and DOE need to strengthen their systems for monitoring equipment delivery, installation and related follow-ups. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Procurement Teachers considered the 10+1 computer classroom configuration most efficient from a pedagogical perspective. The 5+1 configuration was considered appropriate for providing access to computer education in small rural schools, but was pedagogically less efficient. Large schools needed more than one computer classroom. project cycle stage: Feasibility, Appraisal Lesson Topics: Sector Related Issues: Education Sector Related Issues: Rural development The roles of each agency should be clarified to avoid implementation delays. While the Ministry of Education and Science (MOES) was the executing agency and the Project Implementation Unit (PIU) was responsible for planning, budgeting and implementing project activities, several delays occurred when the Ministry of Finance (MOF) reviewed and rejected financing of activities that were included in the annual budget approved by MOF. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Education Similar projects in the future should take into account the complexity of developing an Educational Management Information System (EMIS) framework, establishing and modifying the system, and building the necessary capacities, which for this project were underestimated at appraisal. The rapid computerization of all general secondary schools was an enormous achievement that was made possible by the high level of commitment in the executing agency (Ministry of Education and Science or MOES), oblasts, raions and schools. Computers are being used for informatics as well as other subjects, and are increasingly integrated with the new curriculum and new generation textbooks. Discussions with staff and teachers at Republican Institutes for the Improvement of Qualifications of Leaders and Research/Pedagogical Staff of the Education System or RIIQs (formerly Republican Teacher Improvement Institute) and teacher improvement institutes (TIIs) highlighted the need to provide continuous, targeted training to teachers to achieve more effective teaching and learning. It is also important to reduce skill gaps among teachers and between teachers and students. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building Capacity Development: Ownership Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/basic-education-project
Pension Reform Program (Loan 1589-KAZ) | Kazakhstan | Finance | 2003-09-30 | Equally important, the success of the government s pension reform depended on the creation of its components laws and regulations; administrative and regulatory bodies; and market actors, such as private pension funds and asset managers, administrative and regulatory procedures, and infrastructure (computer networks, databases, and so forth) and the ability of the government to explain and justify the reform to a public that had lived most of its life under a system of central economic planning. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Private sector Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy reforms/framework Policy & Reform: Reform Shifting from a pay-as-you-go (PAYGO) pension system to a partially or fully funded system also deprives the government of resources for addressing social issues and should only be pursued if additional resources can be obtained to ease the cost of the transition. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Policy & Reform: Reform Policy & Reform: Transition economies Shifting from a pay-as-you-go (PAYGO) pension system to a partially or fully funded system contributes to capital market development in early-stage transition economies and creates institutional pressure to strengthen financial market regulation and oversight. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Policy & Reform: Policy reforms/framework Policy & Reform: Transition economies Taking into account the context in which the pension reform was enacted, the reform was not only tremendously ambitious, it was designed and implemented more rapidly than virtually any other reform in the former Soviet Union and the scope of the reform was particularly impressive when juxtaposed against Kazakhstan s nascent capital markets and the inadequacy of the infrastructure that had supported the administration of the old pay-as-you-go (PAYGO) system. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Policy & Reform: Reform Policy & Reform: Transition economies The implementation of a funded pension system requires a substantial commitment of time and resources to adequately develop the institutional, administrative, and regulatory framework on which the system depends. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Capacity Development: Ownership Policy & Reform: Policy reforms/framework The introduction of a funded pension system in the absence of other mechanisms to assure a minimum level of benefit adequacy and to effect a reasonable degree of income redistribution from the comparatively well-off to the less fortunate may not provide effective long-term social insurance to the working population. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Policy & Reform: Reform Policy & Reform: Transition economies The success of a funded pension system in providing adequate income replacement depends upon the capacity of the capital markets to absorb substantial inflows of investment capital and generate adequate returns to fund participants. In countries with nascent capital markets, the inflow of capital may exceed the absorption capacity of the markets and could expose invested assets to inappropriate risks. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Management: Risks/Risk management Capacity Development: Capacity assessment Policy & Reform: Transition economies | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/pension-reform-program-loan-1589-kaz
Educational Rehabilitation and Management Improvement Project | Kazakhstan | Education | 2002-09-13 | For initial contracts with international suppliers, due to the wide dispersion of projectsites throughout the country, site delivery and installation were not included but were carried outunder a separate contract with a forwarding agent. However, owing to problems related todetermining liability when delivered equipment was defective, in subsequent contracts under theBasic Education Project (BEP), site delivery and installation were, whenever possible, the responsibility of the supplier. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Project Management: Procurement Sector Related Issues: Education Implementation benefited greatly from the project's simple, straightforward design, which laid the foundations for further cooperation between the government and ADB in the education sector. This initial approach was followed by a more comprehensive project, Basic Education Project (BEP), to build on the project's initial implementation experience and to support broader reforms. project cycle stage: Concept Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education Policy & Reform: Reform Project implementation experience highlighted the importance of a capable, efficient, and stable Project Implementation Unit(PIU). Project management was significantly weakened by the frequent changes in project manager and other PIU staff, which undermined continuity and resulted in ADB and the executing agency having to spend significant resources throughout project implementation on training and orienting new staff. It also greatly increased the project's reliance on internationalconsultants, who played a key role in keeping project activities on track. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building Capacity Development: Human resources management The Educational Management Information System (EMIS) component was significantly delayed due to initial delays in assigning a responsible counterpart agency and insufficient consultant inputs. The complexity of developing an EMIS framework, establishing and modifying the system, and building up necessary capacities were underestimated at appraisal. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building Sector Related Issues: Education The majority of staff trained externally under the project remained in project-relatedpositions for less than a year before moving to jobs outside the education system. Thissignificantly reduced the effectiveness of the training in supporting project activities. In futureprojects, ADB should carefully review with the government the question of retaining externallytrained staff in relevant positions. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Education The project included provision for 20 person-months of domestic consultants to support the Project Implementation Unit (PIU) in different aspects of project management. Given the high turnover of PIU staff and the wide range of unanticipated issues that arose during implementation, this component proved very useful in providing the project with flexible operational support. Key areas requiring support included translation of documents, customs clearance of equipment, and inspection and follow-up of equipment delivery and installation in schools. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project management Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/educational-rehabilitation-and-management-improvement-project
Special Assistance Project (Loans 1337-KAZ[SF]/1338-KAZ) | Kazakhstan | Multisector | 2001-12-31 | A timely response to an economic crisis may not be consistent with the achievement of immediate development objectives. First and foremost, the project attempted to address an identified critical shortage of foreign exchange through quick disbursement. Second, it sought to achieve a number of development objectives namely, arresting the decline in living standards through meeting basic needs for medicines, medical equipment, and medical spare parts; and supporting imports by enterprises to halt the decline in output and employment. To an extent, the two thrusts proved to be incompatible. The achievement of development objectives was predicated on adherence to a number of conditions imports of medical items against a positive list and approval of individual applications by enterprises. However, these conditions caused delays that worked against quick disbursement. On the other hand, the project demonstrated that rapid disbursement reduces control, which may result in less-than-expected or unevenly distributed development impacts. project cycle stage: Design Lesson Topics: Care should be taken in the selection of conditions, particularly in a rapidly changing situation such as during the early stages of transition, because unintended and negative consequences may result. The requirement to allocate at least 60 percent of loan proceeds to enterprises in the private sector, while a sound policy in other circumstances, was made with an inadequate understanding of the structure of the private sector at the time. Even where conditions are sound, sufficient capacity must exist for them to be met and monitored. In situations of economic crisis and reform, substantial TA is likely to be required to mitigate the risk posed by weak institutional capacity, and to ensure effective monitoring and evaluation of implementation and impact. project cycle stage: Appraisal Lesson Topics: Emergency lending is likely to require a higher level of ADB support and supervision than normal lending activities. Moreover, special assistance projects should be used to build relationships and set directions for future lending and not simply be an end in themselves. This in turn indicates a need for more input by ADB, including supporting TA, than perhaps required by the project itself. It also highlights the desirability of establishing a representative office in a country early in a transition or reform process, when local capacity is at its weakest. ADB s decision to have a representative in East Timor is a good response based on the experience with Kazakhstan. project cycle stage: Appraisal Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/special-assistance-project-loans-1337-kazsf-1338-kaz
Agriculture Sector Program in Kazakhstan | Kazakhstan | Agriculture, Natural Resources, and Rural Development | 2001-11-30 | Adequate resources to undertake program monitoring must be provided. The difficulty of measuring the impacts of the social protection measures would not have arisen if the monitoring system and its required resources had been established from the outset. Reliance on the implementing agency to monitor the social protection assistance without clear guidance was a weak feature of the program. The scale of the retrenchment in agriculture was not fully understood during the program preparation and the social protection measures for mitigating the effects on the unemployed were inadequate. With hindsight, the program should have been complemented by initiatives to increase nonagricultural rural employment to mitigate the effects of the retrenchment in agriculture. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Social protection Monitoring & Evaluation: Data collection Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Crosscutting Issues/Themes: Employment Sector Related Issues: Rural development Methodologies/Approaches: Program Approach The program focused on the enactment of legislation and changes in institutional arrangements, to effect outputs that included new laws and regulations, and the divestment of the state s involvement in commercial agriculture. The program s immediate output was the creation of a legal framework and an enabling policy environment. While these achievements are impressive, the sector performance has been mixed and affected by exogenous factors. Sustained recovery of the sector requires continuing efforts to strengthen institutional capacity in the new economic environment; developing systems, including law enforcement, to implement policy changes effectively; and completing structural adjustments. project cycle stage: Concept, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Legal system Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Reform Methodologies/Approaches: Program Approach The program reforms have far reaching impacts on the society. The earlier top-down approach to accelerate policy decisions had bypassed consultative processes that would be pursued under normal circumstances. The PCR confirmed that the dynamics of policy reforms in the transitional context makes it difficult to design reforms with a long time horizon and a blueprint approach. Further refinements will be required as the society and its constituencies adjust to the new realities, as was the case when Presidential Decree on Land was revised into a new Land Law. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Policy & Reform: Policy reforms/framework Policy & Reform: Reform Policy & Reform: Transition economies Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Program Approach The success of the program stems from the strong commitment of the government to the reforms and the country s consistent political resolve to accelerate the economic transition. The policy dialogue during the program fostered the government s ownership of the reforms. Considering the rapidly changing policy environment and the urgency with which the country faced a crisis situation due to the former Soviet Union (FSU) breakup, ADB appropriately relied on in-house expertise in preparing the program. The policy dialogue between ADB and the government, and consultations with other development agencies including the World Bank, IMF, United Nations Development Programme, United States Agency for International Development, and European Union Technical Assistance for the Confederation of Independent States, led to the development of consistent policy measures. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Capacity Development: Ownership Country Context: Crisis/Post-crisis Policy & Reform: Policy matrix Policy & Reform: Reform Policy & Reform: Transition economies Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Program Approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/agriculture-sector-program-kazakhstan
Kazakhstan and the Kyrgyz Republic: Joint Evaluation of the Almaty-Bishkek Regional Road Rehabilitation Project [Loans 1774 and 1775] | Kazakhstan, Kyrgyz Republic | Transport | 2009-03-31 | 1. Project design of physical infrastructure projects need to adopt a more holistic approach that understands the logistics chain rather than just a road section. Donor agencies and executing/implementing agencies need to ensure that complementary projects are implemented in parallel or sequentially to make certain that overall trade costs are reduced and thus full benefits of the road infrastructure can be realized. Effectiveness of the Project was reduced due to the lack of an adequate bridge on the Chu River at the international border crossing on the Almaty Bishkek road. Furthermore, inadequate border-crossing facilities has resulted to inefficiencies for road users (i.e., long queuing times to cross the border). [Main text, paras. 89-90] project cycle stage: Design, Operation Lesson Topics: Sector Related Issues: Transport planning Methodologies/Approaches: Holistic approach 2. Quality-at-entry standards need to ensure that the institutional analysis is of sufficient quality to identify risks and establish appropriate mitigation measures. To address the gaps in institutional capacity, the provision of technical assistance should be appropriately structured during project preparation. In this raod rehabilitaton project, public sector institutions responsible for roads continue to lack adequately trained human resources in the areas of Project Management, procurement, technical supervision, and road maintenance. The Project would have benefited from an assessment of implementation capability and a simpler project design structure. Taking into account the delays in decision making as well as poor contractor performance in Kazakhstan, the use of project implementation units should have been reconsidered. [Main text, paras. 91-92] project cycle stage: Design Lesson Topics: Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management Sector Related Issues: Transport planning 3. Loans to developing member countries require realistic conditions for loan effectiveness and the Government's full ownership of covenants to ensure their timely implementation. The ratification of the cross border agreements (CBA) between Kazakstan and Kyrgyz Republic was a condition for loan effectiveness. The condition was helpful, otherwise, the CBA ratification could have been prolonged. However, the ratification was delayed affecting loan effectiveness and implementation. Furthermore, towards the end, the two Governments did not follow through the implementation of the CBA. As a result, the costs in terms of delays in loan effectiveness did not yield the expected benefits from the agreement. [Executive summary, Main text, paras. 93-94] project cycle stage: Country Partnership Strategy Lesson Topics: 4. Sustainability of road projects hinges on the provision of sufficient and continued funding and human resources. Funding allocations for road maintenance need to be based on a rigorous planning regime and be transparent. These require strong commitment of the benefiting government through productive and sustained dialogue to enable policy and institutional change. Lack of adequate allocation of funds is a major issue facing both Kazakhstan and Kyrgyz Republic as current allocations from both Governments central budgets are not sufficient to fulfill the maintenance requirements. [Executive summary; Main text, paras. 69, 95-96] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Loan Agreement: Covenants Project Management: Operation and maintenance 5. Harmonization of project financing could be considered under the Paris Declaration to improve implementation efficiency and reduce transaction costs. The use of parallel financing created implementation issues in Kazakhstan, since the Government was required to comply with two different sets of implementation procedures which contributed to delays and higher transaction costs. [Main text, paras. 46, 97-98] project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Crosscutting Issues/Themes: Donor coordination/harmonization Crosscutting Issues/Themes: Harmonization | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/kazakhstan-and-kyrgyz-republic-joint-evaluation-almaty-bishkek-regional-road-rehabilitatio
Institutional Strengthening and Policy Support to the Road Sector in Kazakhstan, Kyrgyz Republic, and Mongolia | Kazakhstan, Kyrgyz Republic, Mongolia | Transport | 2002-10-31 | The RETA design was appropriate for Mongolia, but not for Kazakhstan and the Kyrgyz Republic. Regional groupings should take note of government priorities and ongoing relevant activities. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Country Context: Prioritization The success of the first-generation TAs highlights that the scope should be simple and achievable within the given timeframe. project cycle stage: Design Lesson Topics: The TAs were appropriate for transition economies, yet it may be appropriate in the future not to focus only on workshops and training on procurement processes but to also provide job classification and description as part of the human resource development program. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Procurement Capacity Development: Human resources management Policy & Reform: Transition economies The very low salary structure in the civil service relative to the private sector in Kazakhstan and the Kyrgyz Republic makes it difficult for the governments to retain or recruit competent staff. Capacity building within the existing pay scales may not be possible. In Mongolia, salaries are low but there are limited opportunities outside the public sector. However, there is a limited range of available courses, which restricts the supply of qualified people. There is a need to strengthen the technical training facilities for the road sector in Mongolia. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Private sector Sector Related Issues: Roading While government allocations to the road sector have increased significantly since the road fund in Kazakhstan was abolished, the executing agency (Department of Roads) retains little flexibility to reallocate funds in cases of savings. In the Kyrgyz Republic and Mongolia, the lesson learned is that a road fund by itself is not a guarantee that sufficient funds will be provided to maintain the road network. There is a need for better coordination among external aid agencies in ascertaining the usefulness or otherwise of road funds. If there is no agreement, then the ADB covenant that violates another agency's basic philosophy should be abandoned. project cycle stage: Design Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Sector Related Issues: Roading | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/institutional-strengthening-and-policy-support-road-sector-kazakhstan-kyrgyz-republic-and
Prevention and Control of HIV/AIDS and Other Communicable Diseases in Central Asia Regional Economic Cooperation Countries: Technical Assistance Completion Report | Kazakhstan, Kyrgyz Republic, Tajikistan, Uzbekistan | Health, Industry and trade | 2015-07-01 | Engaging development partners like WHO (World Health Organization) or other UN (United Nations) agencies should be guided not only by project-based service agreements but preceded by an umbrella memorandum of understanding (MOU), which would address the sensitivities of each party, and may include provisions for seeking Board waiver for ADB's procurement guidelines. As international organizations are guided by their own rules and regulations, negotiating the legal, financial and administrative details will be less tedious and time consuming if there is a pre-existing basic document that defines the status of each party and harmonizes their respective rules and regulations (e.g., consulting services recruitment and management, prior approval for procurement of equipment, and agreed requirements before contract signing) in a way that satisfies the mutual needs for transparency and accountability. With a funding source that has a narrow timeline, it is important for ADB and the financier to agree on specific milestones in TA (technical assistance) implementation period (e.g., consulting services recruitment), with failure to meet these specific milestones triggering joint re-examination of the merits of continuing with the TA. Strict utilization deadline from the Cooperation Fund for Fighting HIV/AIDS in Asia and the Pacific (contributing to more than 80% of the TA resources) led to cancellation of the TA, as start- up delays (due to failed negotiation with WHO and subsequent new consulting firm recruitment) left less than 6 months for fund utilization. Project cycle stage: Feasibility, Implementation | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/prevention-control-hiv-aids-and-other-communicable-diseases-carec-countries-tcr
Environment Management Technical Assistance Projects to Selected Central Asian Republics | Kazakhstan, Kyrgyz Republic, Tajikistan, Uzbekistan | Multisector | 2007-08-31 | 1. Funding agency coordination should go beyond individual project implementation and consider the areas each development partner could best focus on to promote the efficient and effective use of resources. In the Central Asian republics, the large number of development partners active in the environment sector did not lead to the most effective and efficient achievement of results. As efforts are ongoing to coordinate this assistance, ADB should actively participate in this undertaking. [Executive summary; Main text, paras. 1, 23, 78] project cycle stage: Appraisal, Implementation, Operation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Funding Country Context: Prioritization 2. A regional solution is required to address transboundary issues and manage transboundary protected areas. To facilitate and broker agreements, some regional cooperation bodies have been formed (e.g., Interstate Commission on Sustainable Development and International Coordinating Water Commission). ADB has not made a major contribution in these efforts. ADB's regional cooperation efforts should take a proactive role in brokering agreements for resource management, environmental information harmonization and sharing, and security. Maximum participation by the countries in the region is a key ingredient to achieving successful results. [Executive Summary; Main text, paras. 31, 79] project cycle stage: Concept Design Appraisal Operation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental benefits Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Regional cooperation 3. The benefits of successful training-of-trainers programs can only be sustained if the programs are institutionalized in the agencies' human resource development program and an annual budget is committed. Evaluation noted that the training programs have improved awareness of the participants and upgraded their skills to higher standards. However, failure to institutionalize the training programs limited the benefits to the participants (including its sustainability). [Executive summary; Main text, paras. 39-41, 80; Appendix 3] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity development Capacity Development: Human resources management Capacity Development: Ownership 4. The technical assistance (TA) projects had no direct linkage with the country operational strategy, the country strategy and program and country environment assessments (which came much later). If the interventions had been sequenced such that country environmental assessments were prepared and a roadmap that included a TA program drawn up on the basis of findings, then a strategy for intervention could have been implemented. Such sequencing would help ensure synergy and complementarities with other development partners, nongovernment organizations, and the government's own programs. [Executive summary; Main text, para. 81; Appendix 2] project cycle stage: Concept, Design, Operation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Modality: Technical Assistance Project Design: Project design 5. A more intensive consultation among stakeholders could have contributed to better needs assessment and enable strong country ownership and commitment to technical assistance (TA) projects. In addition, more focused and realistic designs would have allowed for efficient and effective TA results. Evaluation noted the mixed quality of TA designs where some were well-balanced with realistic objectives and scope (such as those implemented in Kyrgyz and Tajikistan) while others were overambitious in scope and budget (regional management information system), had inadequate needs assessments and lacked government support (i.e., Kazakhstan). [Main text, paras. 21, 61-62, 66, 71, 82] project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Civil society Modality: Technical Assistance Project Design: Project design Capacity Development: Ownership Capacity Development: Partnerships Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach 6. The effectiveness of technical assistance (TA) depends heavily on the knowledge, skills and familiarity with local conditions of the consultants. The recruitment of consultants should place reasonable weight on their understanding of local realities, the methodologies required, the terms of references, and the difficulties and constraints of TA implementation. This will leave very little room for misunderstanding with regard to expectations (e.g., too much reliance of international consultants on national experts in Kyrgyz affected the quality of TA outputs). ADB should also encourage the use of national consultants who have the skills, know the language, and whose services can be tapped by the executing agency for continuity even after TA completion. [Executive summary; Main text, paras. 35, 84] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Modality: Technical Assistance Project Management: Consultants Capacity Development: Capacity assessment Capacity Development: Institutional analysis | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/environment-management-technical-assistance-projects-selected-central-asian-republics
Selected Technical Assistance in the Education Sector in Three Central Asian Republics | Kazakhstan, Kyrgyz Republic, Uzbekistan | Education | 2002-09-30 | In countries with limited capacity in the English language, problems can occur because of poorly comprehended, or interpreted statements, or translated documents that may cause misunderstandings and delays. These problems can be overcome by (i) identifying translators, interpreters, and/or research assistants with good command of the English language to be recruited on an ad hoc basis; and (ii) allowing sufficient time for the translation of reports and in-depth review by national counterparts. project cycle stage: Implementation Lesson Topics: Project Management: Project reporting Country Context: Cultural constraints Inception missions should familiarize consultants with the goals and objectives of the TAs, establish the critical achievement factors, and emphasize the importance of being sensitive to the needs of the country. Consultants must establish cordial relationships with respective EA officials. Both ADB and the government should provide clear guidance to EAs during TA implementation to prevent unfavorable situations. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies The design of TAs should allow some flexibility to adapt priorities and focus of TOR of consultants and TA outputs to better respond to the needs of recipient agencies. The EAs knew what they wanted, but had little experience in the technical and administrative aspects of TAs and relied much on ADB for the design of TA. The experience gained from the six TAs indicated that successful TAs were those in which suggestions for refinement in scope submitted by EAs were considered and approved by ADB during implementation. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Country Context: Prioritization The EAs implemented education management information system (EMIS) and collected information and data on selected indicators. However, with one exception, they were unable to present their findings to decision makers in a meaningful and concise manner. Future ADB support to strengthen the evaluation capacity of developing member countries should provide training in data management such as analysis of data, statistical tests, cost effectiveness analysis, and presentation of findings. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Data collection Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building Sector Related Issues: Education While the business of education pertains to the ministry responsible for education, it is also the concern of other ministries and institutions. Thus, stronger or explicit links should be developed between the education ministry and other line ministries, notably the finance ministry for budgeting and financing of education and the Cabinet of Ministers for monitoring the implementation of education reform. Experts from other ministries should be involved in TA working groups. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/selected-technical-assistance-education-sector-three-central-asian-republics
Strengthening Safeguards Capacity in the Urban Sector: Technical Assistance Completion Report | Kiribati | Health, Public sector management, Water and other urban infrastructure and services | 2015-08-01 | A number of ECD (Environment and Conservation Division) staff were on leave at various times over the course of the TA (technical assistance), this meant the TA consultant had to produce and leave some training materials for ECD staff to deliver to their colleagues. Further, the TA consultant became like a technical advisor to ECD staff and was consulted on many matters beyond the TA, while this did not detract from the key TA targets or deliverables it did underscore the need for flexibility from the consultant to provide support and advice beyond the strict confines of the TA's TOR (terms of reference). Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/kir-strengthening-safeguards-capacity-urban-sector-tcr
Sanitation | Kiribati | Water and other urban infrastructure and services | 2008-06-18 | 1. The restructuring of the Public Utilities Board has lost momentum, and may even have shifted into reverse. Technical Assistance can quickly provide an organization with appropriate policies and procedures (and fulfill their terms of reference), but support and reiteration must continue to maintain progress and fully embed organizational changes. Time is needed to digest, discuss, test, and tailor new approaches over several business cycles. project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development Policy & Reform: Public sector reform 2. At present, the Public Utilities Board is not strongly held to account for its water resource extraction, service levels, efficiency, or financial viability. Technical Assistance can provide the initial motivation to address these issues, but permanent regulation and accountability mechanisms are required to maintain appropriate organizational focus. project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development Policy & Reform: Public sector reform 3. Maintenance and improvement of infrastructure based services, even those based on new infrastructure, require constant monitoring, evaluation, and planning. Public Utilities Board (PUB) restructuring was limited by staff shortages at management levels, and is now even more severely constrained by even higher vacancy levels. The Technical Assistance outcomes could have been enhanced by helping PUB develop strategies to recruit and retain staff, including, for example, the training and promotion of lower level staff, increased remuneration, succession planning, international recruitment, and bonded overseas scholarships. project cycle stage: Design Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Capacity Development: Human resources management Capacity Development: Institutional analysis Opportunities to consolidate early restructuring and community development gains were overlooked at the later stages of the Project. Early project directions had been influenced by TAs and the PIUs but expanding infrastructure, civil works, and contracting priorities dominated the later stages. The inexperienced steering committee failed to coordinate the Project adequately or to sufficiently develop shared goals and action between all players. This limited the success in achieving some project objectives - a 24-hour water supply, for example, or a meter-based tariff, operating-cost recovery, or community empowerment, with bottom-up accountability. Some proposed activities were not implemented. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project administration Methodologies/Approaches: Participatory approach Simple infrastructure, robust materials, and low O&M requirements promote sustainable service delivery. The constant-flow water supply system, on the other hand, has added complexity, cost, O&M needs, and more opportunities for user abuse, and it remains only partially effective to date. Landfill leachate controls added complexity, cost, O&M needs, and are no longer operated due to sewer flooding. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Operation and maintenance The impasse between the Government and landowners over development of the Abatao and Tabiteuea water resources, and the reluctance of landowners to vacate the Bonriki and Buota water reserves, are examples of the strong link between land and water issues. Government efforts to manage water resources are at odds with the landowners' traditional views and concerns over the agricultural sustainability of their land. A lack of alternative land for settlement constrains effective protection of water reserves project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Country Context: Cultural constraints Sector Related Issues: Water resource management The inaction in removing settlements from water reserves, poor mplementation of the constant-flow water supply system, and continued reliance on a flat rate tariff ï¿½until all households are connected,ï¿½ are examples of where local custom and traditional practice have dictated a less-than-effective or a higher-cost approach. project cycle stage: Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Project administration Country Context: Cultural constraints Sector Related Issues: Water resource management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/sanitation
Strengthening Audit Capability in the Pacific | Kiribati | Public Sector Management | 2002-10-31 | Requirements for regional training programs need to be thoroughly investigated to ensure that (a) programs do not offer techniques or processes that cannot be applied in some Pacific developing member countries (PDMCs), and (b) cost estimates cover the entire programs and not just the time slice supported by ADB. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/strengthening-audit-capability-pacific
Financial Sector Program and Institutional Strengthening of the Financial Sector Project to the Republic of Korea (Loans 1601/1602-KOR) | Korea | Finance | 2005-12-31 | At the time of the Asian financial crisis, ADB did not have an appropriate lending instrument for crisis support and had to resort to traditional program lending with accompanying conditionalities to help its clients in a time of financial crisis. Given the flexibility and the responsiveness of ADB and the Government's high ownership of the reforms, the absence of such an instrument was not problematic. project cycle stage: Appraisal Implementation Lesson Topics: Modality: Lending modality Modality: Policy-based lending Country Context: Crisis/Post-crisis Policy & Reform: Reform Crisis situation lending to address financial sector instability must not neglect the human cost that such crises extract from displaced workers, particularly from low-income workers and other vulnerable groups. The adequacy of social safety nets should be reviewed in the face of large-scale external economic shocks. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Vulnerable groups Country Context: Crisis/Post-crisis During crisis situations, effective coordination among multilateral financial institutions (MFIs) and sharing of information in a transparent manner are needed to insure that external aid programs are consistent and comprehensive and do not overlap or work at cross purposes. Responsibilities should be allocated on the basis of core competencies. ADB s involvement as one of the three MFIs responding to the crisis was essential to address a number of key weaknesses in the financial sector (particularly the nonbank financial sector). project cycle stage: Feasibility, Appraisal Lesson Topics: During periods of severe financial market instability, temporary credit support may be necessary to prevent viable enterprises from failing for lack of capital. Such programs must be eliminated once the financial markets have stabilized to prevent moral hazard and to enable the efficient allocation of investment capital on the basis of market forces. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Policy-based lending Country Context: Crisis/Post-crisis Once a crisis has passed, attention should be given to further institutional strengthening to prevent future market failures. This suggests that periodic surveillance is needed to track developments, provide early interdiction when problems emerge, and facilitate learning across developing member countries. project cycle stage: Operation Lesson Topics: Capacity Development: Capacity development Country Context: Crisis/Post-crisis Policy & Reform: Reform Speed, client ownership, and the ability to leverage windows of opportunity to introduce otherwise politically contentious reforms are essential when responding to crisis situations. project cycle stage: Feasibility Lesson Topics: Modality: Policy-based lending Capacity Development: Ownership Country Context: Crisis/Post-crisis Policy & Reform: Policy reforms/framework The success of financial sector reforms is often dependent on reforms elsewhere in the economy, such as in the corporate sector during the crisis in Korea. The Government's willingness to allow ailing chaebols to fail, and its commitment to tackling weaknesses in the corporate sector were essential for the success of the financial sector reforms supported under the financial sector program loan (FSPL). project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Policy-based lending Policy & Reform: Policy reforms/framework Policy & Reform: Reform | Project/Program Performance Evaluation Report (PPER) | Highly successful | http://www.adb.org/documents/financial-sector-program-and-institutional-strengthening-financial-sector-project-republic
Comparative Infrastructure Development Assessment of the Kingdom of Thailand and the Republic of Korea: Technical Assistance Completion Report | Korea, Thailand | Energy, Transport, Water and other urban infrastructure and services | 2015-04-01 | In Thailand and the Republic of Korea, as in other countries of the region, development is primarily assisted by infrastructure investment that follows an integrated plan at the national level supported by long-term sector master plans. The quality of such plans depends on if they are based on thorough comparisons of the likely benefits of possible projects for efficiency, productivity, and social and environmental objectives, compared with their likely costs. Moreover, the practicality of the plans depends on if they are consistent with medium-term fiscal strategies and annual budgets. Following the Republic of Korea's example, Thailand should form a comprehensive territory or land-use plan synchronized with the national infrastructure investment plan. Another key lesson learnt based on the assessments undertaken is that both countries would benefit from clearer separation of sector regulation from policy formulation and implementation, with more protection for the independence of regulatory authorities. The need for a separate, independent regulator is especially important where the implementing agency has responsibility for contracting. Similarly, in several infrastructure subsectors, both countries would benefit from more competition to drive improvements in service quality and efficiency and obtain more private financing for new investments, if their policies and regulations provided a more reliable basis for private participation. This involves operators' long-term ability to set user charges that fully recover the costs of investment, operation, and maintenance. At times this also can depend on well-specified, sustainable subsidies. Experience in both Thailand and the Republic of Korea has shown the importance of this for the financial viability of PPPs (public-private partnerships). Their experience with PPPs also suggests that for the sake of obtaining the most effective investments and protecting the public from unduly high user charges, social cost?benefit analysis should be applied to all proposals with assistance from national planning bodies. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/comparative-infrastructure-development-assessment-tha-and-kor-tcr
Investment Climate Improvement Program: Validation of Completion Report | Kyrgyz Republic | Finance | 2015-10-20 | The lessons presented in the PCR (program completion report) and summarized in this validation are suitable. First, implementation of institutional reforms is more effective and efficient when there is a detailed blueprint with measurable indicators, and implementation arrangements are in place. Second, to attract investments, Kyrgyz Republic firms should also strengthen their productive capabilities and improve their competitiveness. Third, the significant changes in the methodology of the 2015 Doing Business report have negatively affected the Kyrgyz Republic's overall position in the ranking, making it difficult to measure achievements against the program's initial target. However, this validation notes that the Global Competitiveness Report can provide a good alternative source of information on the country's overall competitiveness. And last, the PCR indicated that the report's usefulness lies more in monitoring the country's performance over time rather than measuring progress against other economies. This validation adds the lesson that extensive dialogue is needed, particularly for reforms that meet resistance, to facilitate better cooperation and implementation. project cycle stage: Concept, Design, Implementation, Operation | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/kyrgyz-republic-investment-climate-improvement-program
CAREC Transport Corridor I (Bishkek-Torugart Road) Project 2: Completion Report | Kyrgyz Republic | Transport | 2015-09-11 | Addition of At-Bashy road. The final approval for constructing the At-Bashy access road was not provided until May 2013. The late addition of this component was part of the reason that the grant and loan closing date needed to be extended. Additional works of this magnitude should be identified, appraised, and approved at an earlier project stage to ensure completion of all works within the allotted period. project cycle stage: Design, Appraisal, Completion Communication. During construction of At-Bashy road, some disputes arose between the contractor and the local population, causing late completion of minor but essential works e.g. sidewalks and drainage. Information on these incidents was not promptly reported to all parties concerned. Not being fully aware of the situation, IPIG (Investment Projects Implementation Group) initially advised ADB that there was no need to extend the loan and grant closing period. However, when the extent of remaining works to be completed became apparent, an extension was provided. This issue was swiftly resolved. It is important to ensure proper communication between contractors, consultants project implementation unit and, ADB by fielding an ADB mission to help dispute resolution. It is also vital to field ADB missions to coincide with the completion of physical works, to enable the mission to verify completeness of such works and assist in determining whether loan and/or grant extensions are needed. project cycle stage: Design, Implementation, Completion Inspection facility. Construction on the proposed facility has not yet started. The inspection facility is planned to be delivered using alternative financing sources. Cross- border facilities such as this require both expert inputs from, and coordination between, various government agencies. This can be difficult to achieve in a timely manner. In addition, specialist skills are needed for designing and implementing such projects. project cycle stage: Design, Implementation Frost heave cracking. The combination of high altitude, low temperatures during winter and frozen ground beneath the project road resulted in the appearance of frost heave cracks. Cracks have been filled in with bitumen but will reappear after each winter. The cracking issue needs to be monitored on an ongoing basis with cracks filled in as they appear. To minimize risk of further cracking, snow needs to be removed entirely from the roadbed and not merely left on shoulders, and weight limits for goods vehicles need to be strictly enforced to ensure undue stress is not placed on the project road. project cycle stage: Design, Implementation Maintenance. In order to sustain project benefits it is critical that the project road is appropriately maintained. The frost heave cracking issue needs to be monitored by MOTC (Ministry of Transport and Communications) on an annual basis and, in order to prevent further widening, cracks must be filled as they appear. Whilst maintenance budgets have increased, MOTC needs to allocate further resources to protect the substantial investment in road infrastructure that has occurred on this road corridor over the last decade. project cycle stage: Operation Capacity development component. Originally a total of $0.5 million was allocated to the capacity development component, but only $0.01 million was actually spent. Additional attention could have been given at appraisal to properly identify and cost each part of the capacity development component. project cycle stage: Design Consultation. There is a need to ensure an appropriate level of public consultation during project development to enable the local population to have an input into project design and ensure greater'buy-in', which would likely result in fewer disputes between the contractor and local population. project cycle stage: Concept, Design, Implementation Road Safety. Despite the safety features (e.g., barriers) built into the project, the increased speeds resulting from the new road will likely have an impact on both the frequency and severity of road traffic collisions. Collisions on the project road will need to be monitored carefully by MOTC (Ministry of Transport and Communications) during 2015 - 2020 in coordination with the police force and, if and when collisions start to occur, timely and appropriate remedial engineering measures may need to be put in place to counteract any increased risk. project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/carec-transport-corridor-1-bishkek-torugart-road-project-2-pcr
Support for Strategic Assessment of the Kyrgyz Economy to Promote Inclusive Growth: Technical Assistance Completion Report | Kyrgyz Republic | Public sector management | 2015-08-01 | During preparation of the M&E (monitoring and evaluation) methodology and guidelines, the M&E consultant faced difficulty in coordinating the implementation of the M&E activities between government agencies which were responsible for M&E of the development strategy and program. Several meetings were held for reconciling the differences, but the situation remained the same. Hence, (i) improved coordination at multiple levels (coordination in M&E system design, coordination across sector and governmental agencies and administrative bodies, coordination in data collection); and (ii) clear division of responsibilities between the governmental agencies are required. The extra effort made at the end to publish and disseminate the report was worth the time and resources. Dissemination efforts are important in expanding the use of the TA (technical assistance) outputs. Sharing the findings of the Strategic Assessment through presentations and publications to government officials and decision makers in Russian helped expand the audience, and actual use of the report's findings. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-strategic-assessment-kyrgyz-economy-promote-inclusive-growth-tcr
Second Community-Based Early Childhood Development: Technical Assistance Completion Report | Kyrgyz Republic | Transport | 2015-04-01 | This shifting of priorities towards infrastructure projects was consistent with the increased selectivity of ADB- supported sectors in the Kyrgyz Republic at the time. However, this re-prioritization had a tradeoff: as of 2015, the Kyrgyz Republic continues to face challenges in reducing infant mortality rates and increasing access to preschool programs. Further support to the Kyrgyz Republic on improving quality of and access to early childhood education remains relevant. The introduction of the streamlined business processes in 2010 has reduced the risk of non-utilization of project preparatory TA (technical assistance). The new business process allows for approval of the project preparatory TA as part of concept approval. Project cycle stage: Concept, Design, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/second-community-based-early-childhood-development-tcr
Investment Climate Improvement Program: Completion Report | Kyrgyz Republic | Finance, Industry and Trade, Public Sector Management | 2015-03-25 | Implementation of institutional reforms under the program was more effective and efficient when there was an adequate and detailed blueprint with clear and measurable results indicators, as well as where project-type implementation arrangements were in place to facilitate the change process (e.g., the business registration system or the new inspection process for tax administration were supported by detailed blueprints and financed through investment projects). The $2.9 million grant approved under the program cluster was thus very useful. The government accelerated implementation of the SWFT (single window for pre-customs clearance of foreign trade) when the policy action was reworded to become more results-oriented rather than process-focused. project cycle stage: Concept, Design, Implementation Despite an improvement in the business environment, firms in the Kyrgyz Republic have had limited progress in developing new productive capabilities: the number and sophistication of products exported with comparative advantage by Kyrgyz Republic firms has declined. It is possible that the increase in investment has been directed to sectors that produce non-tradable goods and services or that produce a limited number of tradable products (e.g., mining). This questions whether improvement of the overall investment climate is sufficient to attract investments that can bring additional productive capabilities to a country. project cycle stage: Operation It is problematic to use a country's overall position in the Doing Business report to monitor progress in improving the business environment and overall competitiveness. The report has been subject to criticism and methodological problems have been identified. Its usefulness for monitoring progress in similar programs lies more in monitoring the country's performance over time - particularly in indicators that are not sensitive to the representative case used by the World Bank team - rather than measuring progress against other economies. project cycle stage: Concept, Design, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/investment-climate-improvement-program-pcr
Tax Administration Reform and Modernization Project: Completion Report | Kyrgyz Republic | Public Sector Management | 2015-03-24 | Some of the functions of an electronic tax administration system cannot be effectively used without certain external preconditions. In particular, automated payment and collection functions require an effective electronic payments system operated by the financial sector and an effective treasury system. These conditions are still not fully present in the Kyrgyz Republic, which limited the project's outcome. project cycle stage: Operation Tax administrations (or any other organization) should not overly rely on external experts to develop and maintain software. In particular, they should keep and be able to use the source code of externally developed software. The difficulty in upgrading the legacy system (KITIS, or Kyrgyzstan Integrated Tax Information System) was also due to lack of knowledge by the STS (State Tax Service) of the source code, and lack of an agreement with the software developers. These difficulties and the subsequent decision to develop a new customized software solution significantly delayed the project. It is also critical to have in place information technology expertise to monitor the software development process and ensure that critical features are made effective. project cycle stage: Design, Implementation, Operation Automation and improved information technology systems can be first steps for change of business processes and improvements in governance. It is, however, extremely difficult for a tax administration to move into full automation from a very low level. project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/kgz-tax-administration-reform-and-modernization-project-pcr
Community-Based Infrastructure Services Sector Project (Supplementary Grant) | Kyrgyz Republic | Water and other urban infrastructure and services | 2014-06-01 | Do not reengage in a sector with poor past performance until the government demonstrates its commitment and ownership by creating an enabling environment for delivery of sustainable outputs. At appraisal, all parts of previous project arrangements should be thoroughly reviewed to identify the real causes of past project implementation issues. For key past problems, new solutions should be sought, rather than trying to modify past arrangements. Despite the urgency of government requests for additional financing, conduct a thorough due diligence on all government entities involved and ensure that the available resources fit the scope of the project. Understand that project implementation will require significant ADB staff resources, and allocate resources for additional support to bolster areas where project implementation was previously weak. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/community-based-infrastructure-services-sector-project-supplementary-grant-pcr
Regional Customs Modernization and Infrastructure Development Project | Kyrgyz Republic | Industry and Trade | 2014-06-01 | Project implementation capacity of the executing and implementing agencies. The provision of training for the executing and implementing agencies at the outset, not only in ADB procurement procedures but also in project management techniques, would probably have reduced the project start-up delays. Future projects should include appropriate training to new executing and implementing agencies at start-up. Training in basic information and communication technology skills. While the project recognized the importance of training in basic ICT skills for users of the unified automated information system, it left the provision of this training to the executing and implementing agencies. Because this is a prerequisite for any large-scale ICT system development, future projects should set this as an appropriate loan covenant. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/kgz-regional-customs-modernization-and-infrastructure-development-project-pcr
Vocational Education and Skills Development Project | Kyrgyz Republic | Education | 2014-06-01 | Choose sustainable implementation arrangements. Although the same person headed the Agency for Vocational Education and the project implementation unit, there was a lack of integration between the two organizations. The project activities were separately implemented and managed by the project implementation unit without involving the staff of the Agency for Vocational Education. As a result, activities initiated under the project may slow down after the departure of the project implementation unit consultants. An alternative is to embed the project implementation unit within the existing administrative structure of the agency, involving key staff supported by project implementation unit consultants. Such an arrangement will automatically mainstream project activities into the regular activities of the agency, thereby enhancing sustainability. Use a competitive funding mechanism to select schools for assistance. If the criteria are not carefully determined, the government may select schools whose management and staff are not ready and/or committed to the objectives of the project or the changes it brings. Some of them behave with a sense of entitlement, which leads to complacency in achieving output targets or in adopting new systems and procedures. An alternative selection process is through a competitive funding mechanism. ADB and other donors have used this approach in different countries quite successfully. It forces eligible institutions to compete with each other by preparing funding proposals based on project guidelines. The guidelines specify priority programs that will be supported, eligible expenditure items, the maximum allowable amount per program, and the geographic coverage to ensure equitable representation. Training on how to prepare project proposals can be provided to all eligible institutions. A committee evaluates and selects the proposals worthy of support. Experience has shown that such an approach engenders a strong sense of ownership and commitment to deliver the promised results. Include a change management process. In a project where a new mindset is crucial as new concepts, systems, and processes are introduced, a change management strategy has to be put in place anticipating the possible areas of resistance, and understanding the underlying reasons and means for overcoming such resistance. This aspect is often overlooked, as in the case of this project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/vocational-education-and-skills-development-project-pcr
Investment Climate Improvement Program System Support Project | Kyrgyz Republic | Finance | 2013-08-11 | 1. Implementation of a single window for foreign trade is an extremely complex process that requires a long-term commitment and high-level support. It also requires continuous dialogue with all concerned government agencies to lower resistance to change, including by middle managers and operational staff. The project should have had a longer implementation period and should have included a stronger communication and change management component. A project administration manual and a design and monitoring framework (DMF) at an earlier stage could have helped expedite implementation. Stronger risk assessment at appraisal might have avoided some of the challenges faced during the project. project cycle stage: Lesson Topics: 2. It is unlikely that civil servants in the Kyrgyz Republic have the necessary incentives to manage complex projects as unremunerated, part-time project managers, even if they are highly competent. It is also unlikely that public procurement processes can be managed without specialized procurement skills. A fully dedicated project manager and a procurement specialist should have been appointed to the project. project cycle stage: Lesson Topics: 3. Projects with significant information technology (IT) components require specific expertise in designing the software's technical specifications and bidding documents, and monitoring a software developer's work. The terms of reference for IT experts should have required candidates to have minimum experience in writing technical specifications for software development that were successfully tendered. The project technical cell should also have retained an international IT expert throughout project implementation to support implementing agencies in supervising software development. project cycle stage: Lesson Topics: 4. Information technologgy training for government agencies' staff was expensive. It may be more efficient in future procurement plans to have a separate package for training in basic information and communication technology, as there are many institutions in the country that provide these services. project cycle stage: Lesson Topics: 5. Raising awareness of end-users is an important component of projects that streamline government administration. It helps increase demand for the systems, reduce misinformation, and support the overall change. The funding allocation to public awareness campaigns under the project could have been higher. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/investment-climate-improvement-program-system-support-project-pcr
CAREC Transport Corridor 1 (Bishkek-Torugart Road) Project 1 | Kyrgyz Republic | Transport | 2013-03-06 | 1. Although ADB approved advance contracting and retroactive financing, project implementation experienced initial delays mainly in procurement. Commencement of civil works was delayed for about 3 months because of delayed recruitment of the construction supervision consultants. In the future, implementation should be scheduled to ensure timely recruitment of consultants prior to civil works start. Contract duration must take into account unexpected weather conditions which may hinder the planned execution of works. project cycle stage: Lesson Topics: 2. In view of complexity and needs, customs projects require coordination with multiple ministries and agreements with neighboring countries. Diversified expertise and resources are required both from the government and funding agencies. In the future, customs component should be separated from road rehabilitation projects. Customs modernization should preferably be covered by regional cross-border projects. project cycle stage: Lesson Topics: 3. In ongoing and future projects, training and advice on ADB's safeguard policy and procedure need to be strengthened, and this should be extended to consultants and related personnel. Strong safeguards compliance monitoring by the executing agency, consultants, and ADB can help in timely resolution of any issues that emerge during project implementation. Furthermore, the survey of all the houses adjacent to the project road was good practice, and one which should be applied to all other ADB projects in the country. project cycle stage: Lesson Topics: 4. Because of budget constraints in the last year of project implementation, counterpart funds were not available for 2012 (as of writing of the PCR). During project implementation, availability of counterpart funds should be consistently monitored to avoid payment gaps to contractors, which may cause construction delay. Early action from the government may be taken, such as seeking supplementary financing, scope reduction, or seeking cofinancing opportunities. project cycle stage: Lesson Topics: 5. Road safety and road asset management components should be included in all future projects since they are keys to project sustainability and effectiveness. Since road safety involves various agencies, design and implementation arrangements for this component should be based on discussions with all related agencies and policy dialogue held with high-level government. Similarly, a comprehensive road asset management plan should be developed during project design in consultation with the agencies responsible for road assets development, operation and maintenance, overall financial allocation and releases, and auditing and accounts. Prior to approval of loans, it should be ensured that sufficient funds and proper management are available for the project roads after project completion. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/carec-transport-corridor-1-bishkek-torugart-road-project-1-pcr
Second Education Project | Kyrgyz Republic | Education | 2013-03-06 | 1. Curriculum reform requires strong government ownership and commitment in terms of counterpart financing and policy changes required to support the reform. Improving national school education outcomes requires adequate time and funding. Sufficient teacher capacity building activities, learning and teaching materials, and appropriate learning environments should accompany the curriculum reform. Teachers need at least 3-5 days of face-to-face training on the new assessment and classroom teaching requirements, instead of the 1-day orientation and selflearning modules provided to most teachers under this project. Comprehensive due diligence and accurate cost estimates at project design and appraisal are critical for project success. project cycle stage: Lesson Topics: 2. Provision of learning and teaching materials (LTMs) for more than one grade should be funded to effectively launch a new curriculum. For textbook bids, good practice involves achieving continuity of content and approach by bidding subject textbooks for a series of grades, i.e., mathematics LTMs for grades 1-4 have to be developed by the same team of authors. A shortage of LTMs and poor teacher capacity can undermine the whole curriculum reform process. project cycle stage: Lesson Topics: 3. Better infrastructure directly increases attendance rates, and brings significant savings from improved heating and energy efficiency of buildings. The inclusion of maintenance of supplied equipment and training for relevant staff as part of the supply contract is an effective tool to ensure equipment sustainability and ongoing effectiveness. Thorough assessment of compliance with qualification requirements during consultant recruitment can prevent unnecessary problems and delays during project implementation. project cycle stage: Lesson Topics: 4. The dilemma of this project is the lack of achievement and partial achievement of some outcome indicators, while planned outputs were mostly delivered. Ensuring the direct link between supported activities, outputs and outcome, and relevance of their indicators is critical. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-education-project-pcr
Country Assistance Program Evaluation for Kyrgyz Republic | Kyrgyz Republic |  | 2012-08-15 | 1. ADB's responsiveness to the country's evolving circumstances. ADB has been one of the country's largest sources of financing, making significant contributions to improving the country's road networks, PSD, education, and ANR. The majority of ADB's sector programs, which helped reform policies and institutional arrangements, provided a strong foundation for future support. ADB also responded quickly in times of crises and emergency needs, which was highly appreciated by the government. [Main text, para. 139(i)] project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Capacity Development: Capacity development Country Context: Emergency Sector Related Issues: Education Sector Related Issues: Private sector Sector Related Issues: Rural development Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework 2. Solid cooperation among major development partners. Aid has been well coordinated among main development partners at the strategic level, within key sectors, in major projects, and in portfolio reviews and major economic and sector work. Joint planning and priority setting has been undertaken, given serious absorptive capacity in the public sector. The resident mission has been playing an important role in aid coordination. [Main text, para. 139(ii)] project cycle stage: Design, Implementation Lesson Topics: 3. Government's willingness to mount challenging reforms. ADB has assisted the government in undertaking many challenging reforms, including privatizing SOEs and rural lands, defining new institutional arrangements for managing rural irrigation, building good corporate governance, right-sizing and upgrading the quality of basic education, and involving the private sector in the delivery of essential drugs. [Main text, para. 139(iii)] project cycle stage: Design, Implementation Lesson Topics: Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Privatization 4. Lack of government ownership and executing agencies' accountability and capacity in the rural WSS sector. Lack of government commitment and a mandate for a specific agency to look after rural WSS activities can result in frequent changes in the executing agencies (not only in ADB projects, but also in those of the World Bank), with irregularities in implementation performance and serious governance issues. [Main text, para. 140(i)] project cycle stage: Design, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Ownership Sector Related Issues: Water resource management 5. Overambitious assistance programs. Resources were spread thinly in many sectors without sufficient sector linkages to reinforce cross-sectoral outcomes/impacts and sufficient assessment of government readiness. [Main text, para. 140(ii)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Design: Project design Methodologies/Approaches: Targeting 6. Inadequate long-term planning for major policy and institutional reforms. The long-term nature of policy and institutional reforms requires proper sector roadmaps to set out the critical milestones for both the reforms and their concomitant enforcements in a phased manner. [Main text, para. 140(iii)] project cycle stage: Design Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform 7. Ad-hoc provision of ADTA. TA provision that was not well integrated into the overall CPS can result in 'one-off capacity creation,' which was not sufficient for the executing agencies' 'long-term capacity development.' [Main text, para. 140(iv)] project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development 8. Standalone PIUs/PMUs. The use of standalone PIUs/PMUs not integrated into the executing agencies' normal operation systems, while creating 'short-term capacity substitution,' can contribute to projects whose ownership and sustainability are in doubt. [Main text, para. 140(v)] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Ownership 9. Inadequate attention to road maintenance and the software side of regional cooperation. Low emphasis on road maintenance and the software side of regional cooperation can result in weak sustainability of the road network and weak implementation of cross-border agreements. [Main text, para. 140(vi)] project cycle stage: Design, Operation Lesson Topics: Project Management: Operation and maintenance Sector Related Issues: Roading Sector Related Issues: Transport planning | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-kyrgyz-republic
Kyrgyz Republic: Community-Based Early Childhood Development Project | Kyrgyz Republic | Health | 2011-12-01 | 1. To be useful during project performance reporting and outcome and impact determination at project completion, country-specific definitions of data and monitoring variables established during project preparation needs to be consistent with international conventions. This is important for new and innovative projects or when variables are linked with global goals and programs like the millenium development goals, just like in the Community-Based Early Childhood Development Project in Kyrgyz Republic. [Main text, paras. 25, 26] project cycle stage: Design, Implementation, Completion Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Post-evaluation Monitoring & Evaluation: Reporting Project Design: Project design | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/kyrgyz-republic-community-based-early-childhood-development-project
Kyrgyz Republic: Community-Based Infrastructure Services Sector Project | Kyrgyz Republic | Agriculture, Natural Resources, and Rural Development, Health, Transport, Water and Other Urban Infrastructure and Services | 2011-11-01 | 1. There are clear benefits to involving ADB resident missions in project supervision.These include closer (hands-on) involvement and better understanding of the local environment. In the case of the Community-Based Infrastructure Services Sector Project in Kyrgyz Republic, significant disbursement delays were reported prior to 2005. The situation improved after the Kyrgyz resident mission began screening withdrawal applications. In 2007, ADB transferred responsibility for project administration from ADB headquarters to the resident mission. This resulted in stronger coordination with the executing agency and improved project administration. [PVR Main text, paras. 19, 24; see also PCR Main text, para. 64] project cycle stage: Implementation Lesson Topics: Project Management: Project supervision Other: Resident Mission 2. To adequately apprise ADB of the severity of project problems, projects may require (i) in-depth analysis by missions, and (ii) a established mechanism for consultants to prepare realistic reports to project management units (PMUs) and ADB. In the case of the Community-Based Infrastructure Services Sector Project in the Kyrgyz Republic, project documents revealed that in the early years of the project, the PMU or consultants did not adequately apprise review missions on the seriousness of the project's problems (e.g., 45 subprojects had unsatisfactory performance due to problems relating mainly to poor design, construction, and operation and maintenance). [PVR Main text, para. 24; see also PCR Main text, para. 24] project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Management: Project management | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/kyrgyz-republic-community-based-infrastructure-services-sector-project
Southern Transport Corridor Road Rehabilitation Project | Kyrgyz Republic | Transport | 2011-10-01 | The completion of the project was delayed by about 1 year, primarily due to the failure to finalize cofinancing arrangements with Organization of the Petroleum Exporting Countries (OPEC). This issue might have been avoided if the final solution (financing by the government) had been adopted faster. In the future, the government and ADB need to select cofinancing partners carefully. As the Kyrgyz Republic is a mountainous country and the project area is known for its slope instability, these challenges should have been taken into account during project preparation. Careful and rigorous technical design and appropriate advance actions would have contributed to a higher degree of project readiness for implementation. Sufficient contingency is needed to cover cost increases. For future projects, a design-build contracting can ensure more sophisticated engineering and mitigate the risk of price escalation. During implementation, the civil work contractor demonstrated resilience and a strong ability to engage in complex civil works under the challenging geological and climate conditions. Civil works contracts under future projects need to offer greater incentives to contractors for better performance and penalize those contractors with poor performance. The project road is part of a Central Asian Regional Economic Cooperation (CAREC) corridor undergoing rehabilitation under various project supported by several financing institutions during the same period. As these projects are not expected to be completed at the same time, the benefits of the complete corridor will not be fully achieved until the entire Osh- Sary-Tash-Irkeshtam-Karamyk road is improved. This is expected to happen in 2012. The project framework should have taken these rehabilitation activities into account, and Ministry of Transport and Communications (MOTC) should have coordinated the project schedule with those of the other externally funded projects. Reliable data are essential to identifying problems and monitoring progress. However, the project progress reports often lacked substance, contained stale information, and did not effectively address implementation issues. The requirement of thorough reporting could have been better formulated in the supervision consultant's terms of reference. MOTC needs to review the project progress reports. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/southern-transport-corridor-road-rehabilitation-project
Agriculture Area Development | Kyrgyz Republic |  | 2011-06-01 | Comprehensive and integrated projects can be successful. The success of this project can be attributed to the initial emphasis on the project management unit (PMU) obtaining a clear understanding of the project, an initial focus on process and procedures, minimum turnover of key PMU staff, good oversight by Ministry of Agriculture and Water Resources (MAWR), good partnerships with other donors, and successful contracting and supervision of local civil works and agriculture extension firms. Although this was the first agriculture investment project with MAWR the 3-year extension could have been avoided had the bidding documents been prepared, the management consultants and PMU staff contracted, and target farms identified earlier. The project required close attention to many details, and it could have immediately and effectively performed many administrative tasks if the resident mission had had more capacity to assist the project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/agriculture-area-development
Southern Agriculture Area Development Project | Kyrgyz Republic | Agriculture, Natural Resources, and Rural Development, Finance | 2011-02-05 | 1. The government did not have a strong commitment to the objectives of the project. After just over a year after project effectiveness the government requested a major change in scope so as to focus the project on irrigation and drainage, and land improvement issues. This implies the project design did not completely match the long-term objectives of the government. It is important that there is a clearer understanding between ADB and government of the key development objectives at the time of project design so as to avoid costly changes in scope during project implementation. project cycle stage: Lesson Topics: 2. The project design included 2,559 person-months of national consultants, approximately 35 people for each year of the 6 year implementation period. Despite the national consultant inputs appearing to be recruited through a firm/s on a quality- and cost-based selection basis, such a large requirement of consulting input could have potentially been difficult to effectively manage. project cycle stage: Lesson Topics: 3. The project performance report (PPR) ratings were inconsistently applied over the period of project implementation. The ratings are 'satisfactory' and 'highly satisfactory' until November 2008, and are then rated 'at risk' and 'potential problem' for the month December 2008. The ratings then revert to 'satisfactory', before the project is again rated 'at risk' and 'potential problem' in December 2009. There is no justification to explain this inconsistency and is likely due to staff error from inadequate attention in correctly updating the PPR and applying correct performance ratings. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/southern-agriculture-area-development-project
Kyrgyz Republic: Emergency Rehabilitation Project [Loan 2045-KGZ] | Kyrgyz Republic | Agriculture, Natural Resources, and Rural Development, Education, Energy, Transport | 2010-12-31 | 1. Emergency projects such as this one tend to be difficult to administer and implement and difficult for ADB to properly guide and oversee. This is because speed is of the essence to restore normal activity, and subprojects tend to be spread over large geographical areas. As such, ADB has to depend not only on review mission diligence but also on consultants and the government agencies involved. ADB's procedures, while fully adequate for non-emergency projects, tend to slow the implementation of emergency projects such as this one, so due diligence is sometimes truncated. As a result, subprojects were undertaken that do not meet requirements or necessary approvals. The social infrastructure projects under this project are cases in point. Prior to due diligence approval, works were undertaken and retro-financed after due diligence approval. Also, three of the new schools, while probably needed, did not meet subproject selection criteria. ADB may wish to review its procedures for such projects so that such compromising activities can be avoided. [Main text, page 9, section E(ii)] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: 2. Taking into account issues related to sustainability, it is apparent that the project outcomes can be sustained if the government allocates adequate funds and resources for operation and maintenance based on a rigorous and transparent planning regime. [Main text, page 9, section E(ii)] project cycle stage: Implementation, Completion Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/kyrgyz-republic-emergency-rehabilitation-project-loan-2045-kgz
Banking Sector and Capital Market Development Program | Kyrgyz Republic | Finance | 2010-12-01 | Implementation of the program demonstrated that consistent government support is critical to success. The effective implementation of the banking sector component is attributable to the National Bank of the Kyrgyz Republic's (NBKR) strong commitment and ownership of the proposed reforms. In contrast, the capital market component lacked a clear champion as a result of political developments. Therefore, despite intensive policy dialogue, and awareness and capacity-building efforts, the pace of reforms did not proceed as well as anticipated. The ownership and rationale of policy reforms should be carefully assessed at appraisal. In assessing ownership, it is important to remember that policy actions affect many stakeholders, even within the government. In this case, the legislative branch was not enthusiastic about adopting complex new laws pertaining to the regulation of capital markets that would then be interpreted by agencies outside their direct control. The process of translating drafts of the Law on the Securities Market from English into Russian and back into English affected its readability in English. Achieving a reasonable and consistent standard of translation into both Russian and English remained a problem. Once the final version of the draft law has been adopted, it would be desirable if an official English translation could be produced for the benefit of ADB, foreign investors, and other interested parties. In the meantime, an accurate consolidated translation of the final draft of the law should also be produced for the records of the technical assistance (TA). | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/banking-sector-and-capital-market-development-program
Community-Based Early Childhood Development Project | Kyrgyz Republic | Health | 2010-01-12 | 1. A multisector project requires a strong executing agency that can coordinate multiple implementing agencies. Major reforms also require strong leadership from the executing agency. The Administration of the President of the Kyrgyz Republic as the executing agency contributed enormously to the project's success despite the major regime change in the middle of project implementation. project cycle stage: Lesson Topics: 2. As the project proved, communities are powerful agents for designing and implementing projects that they themselves benefit from. Those community developed projects are likely to be sustainable. project cycle stage: Lesson Topics: 3. Implementing a project in a new field, especially in a dynamically changing transition economy, requires flexibility on the part of both the government and ADB. Willingness to adjust the project's design to a new environment or new findings and acceptance of extra time required for the adjustments is essential. To be successful, the project must also be transparent to receive support from local governments and communities. project cycle stage: Lesson Topics: 4. Given that the idea of community-based preschools was innovative for the country, sufficient time should be given for a legal and regulatory framework to be established to adequately serve preschool educational services at the community level. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/community-based-early-childhood-development-project
Community-Based Infrastructure Services Sector Project | Kyrgyz Republic | Agriculture, Natural Resources, and Rural Development, Health, Transport, Water and other urban infrastructure and services | 2010-01-12 | 1. If there are many small subprojects, the sector project modality should be adopted only with an executing agency having strong implementation capacity. project cycle stage: Lesson Topics: 2. Improving the quality of the feasibility study will minimize uncertainty in identifying subprojects and lead to more precise cost estimates. When subproject cost estimates are uncertain, adequate physical contingencies should be provided in sector projects to mitigate against potential cost overruns. project cycle stage: Lesson Topics: 3. Procurement problems can be reduced by introducing prior review of procurement documents. In a sector project with many small subprojects, contracts should be grouped into larger packages to reduce the number of civil works contacts. This will help the PMUs as well as ADB to concentrate more effectively on fewer contracts. Use of clear and stringent evaluation and qualification criteria in selection of contractors should be mandatory, and establishing consortia of contractors should be encouraged. project cycle stage: Lesson Topics: 4. Community participation in all stages of implementation, from identification to design to construction processes, is critical for the success of investments. project cycle stage: Lesson Topics: 5. The introduction of in-kind beneficiaries' contributions should be carefully evaluated in projects where the works are done by contractors and not by the communities themselves. project cycle stage: Lesson Topics: 6. Community-based projects should be implemented with more involvement of local administrations than of just the central government. project cycle stage: Lesson Topics: 7. Community-based organizations should be provided basic operation and maintenance kits to ensure sustainability of project activities. project cycle stage: Lesson Topics: 8. Establishing a joint project management unit at sector level can be a more efficient and cost-effective solution and help ensure a harmonized approach among the financing institutions. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/community-based-infrastructure-services-sector-project
Social Services Delivery and Finance Project | Kyrgyz Republic |  | 2005-09-15 | Experience highlighted the need for significant project contact with the national government even when the targets are local governments and communities.The location of the project implementation unit (PIU) made monitoring of the development of national policies and initiatives difficult. The cost of implementation arrangements was minimized by establishing a project presence only at the project sites and by recruiting only civil engineers, administrators, training specialist, and discretionary grant fund (DGF) coordinators. The PIU did not have either education or health specialists who could have been effective interlocutors with line ministries. The project manager discussed sector issues with line ministries only when problems arose. The implementation arrangements ensured the quality and timely implementation of civil works, and provision of equipment and strong support to communities. However, disbursements, consultation with the executing agency and coordination with line ministries suffered. The liaison office established to resolve these issues proved insufficient. project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Human resources management Country Context: Decentralization Sector Related Issues: Education Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation It is important to ensure that appropriate national policies and strategies are at an advanced stage of preparation when planning local capacity building. During preparation, the project had two options regarding scope. One was to reform policies and set standards nationally, and the other to strengthen decentralized management and service provision by local government and communities. The project took the second option and achieved its objectives and produced the intended outputs. However, technical effectiveness, impacts on the poor, and the sustainability of investments were undermined by the limited scope of reform nationally, particularly regarding budget planning and allocation, and by the failure of reforms to proceed at the same pace as project investments locally. Although national policy reforms were not in the project scope, the project could have worked more closely with other donors to help the government accelerate the planning and implementation of reforms. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity building Country Context: Decentralization Policy & Reform: Policy reforms/framework The discretionary grant fund (DGF) successfully responded to community social infrastructure needs and mobilized community support. However, poor communities without strong leadership had difficulty preparing proposals and needed significant support in accessing the DGF. To ensurethe full participation of the most disadvantaged communities, similar schemes should ensure that adequate support is provided. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building Methodologies/Approaches: Community approach The project provided computers and training for the social protection management information system (SPMIS) in the project oblasts but did not provide technical support nationally toward designing the system. At appraisal, it was envisaged that other agencies would help the Ministry of Labor and Social Protection (MOLSP) design the system, but this support did not materialize. Eventually, MOLSP technicians developed the system, but they pointed out that designing it was difficult and time consuming and were uncertain of the quality of the network. This component could have been implemented more promptly and efficiently if the project had provided a comprehensive package including hardware, software, and technical support. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/social-services-delivery-and-finance-project
Second Phase of the Corporate Governance and Enterprise Reform Program | Kyrgyz Republic |  | 2005-08-15 | Corporate sector reforms, including enterprise restructuring, require a strong long-term commitment, especially in a transition economy. A multitude of policy, legal, regulatory, institutional, and cultural issues have to be addressed. Thisneeds time and, in all probability, several rounds of reform. Every new round should address the unfinished agenda while making necessary adjustments to changing economic and political framework conditions. Corporate Governance and Enterprise Reform Program (CGERP-II) successfully built on CGERP, which continued even earlier reforms. Further, the timing of enterprise sector reforms should be well coordinated with financial sector and judicial reforms, because these are interlinked and can support or disrupt each other. The smooth coordination of CGERP, FIRM (Financial Intermediation and Resource Mobilization Program), and CGERP-II was essential for achieving satisfactory results under CGERP-II. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Project Design: Project design Country Context: Cultural constraints Policy & Reform: Policy reforms/framework Policy & Reform: Transition economies In the area of enterprise restructuring, it is especially important to ensure sufficiency of conditions to achieve intended results. Frequently, (understandable) opposition on the part of managers, staff, and government representatives has to be overcome. Analytical, conceptual, and organizational work has to be combined with legal and financial support. Compensatory measures have to be carefully designed to be effective. Much attention has to be given to the political economy dimension of reforms. It is highly unlikely to achieve all this within a broad program that includes many other components in related but, nevertheless, different areas. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Human resources management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Public sector reform Legislation needs to be enforced to become effective. Substantial legal work in the areas of corporate governance and disclosure, and bankruptcy has taken place (since 1992). Legal work has been complemented by capacity building in regulatory bodies and, more recently, by judicial reforms to facilitate enforcement. While regulatory capacity has to be further strengthened, and judicial reforms continued, the importance of market pressure for enforcement should not be underestimated. Even the most efficient and creative regulator cannot substitute for the lack of capital markets in providing incentives for sound corporate governance and disclosure of public enterprises. Likewise, functioning capital markets can significantly facilitate enterprise resolution. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Capacity Development: Capacity building Policy & Reform: Public sector reform Delays could have been avoided if the detailed design had been undertaken properly. For future road projects, it is essential that a proper feasibility study be carried out. Proper review of detailed designs and feasibility study reports are essential to avoid last-minute and unplanned land acquisition. In this project, road designs and construction plans were approved well in advance, such that resettlement could have been foreseen. Bidding documents should clearly identify any difficult conditions that may have a negative impact on project implementation. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Appraisal Project Design: Project design Project Management: Procurement Sector Related Issues: Roading Site safety issues are of prime importance during project implementation and the subsequent operation of the project road. In future projects, loan review missions need to double-check site safety compliance by the executing agency and contractors to avoid accidents. project cycle stage: Implementation, Operation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-phase-corporate-governance-and-enterprise-reform-program
Education Sector Development Program | Kyrgyz Republic |  | 2005-05-13 | ADB was the major donor in the education sector, and supported the sector through a comprehensive approach that encouraged other donors' involvement to build on the Education Sector Development Program (ESDP) results. Stronger donor coordination and information sharing in future projects should be ensured through various mechanisms, including the International Advisory Council on Education, established in 2003 as an executing agency (Ministry of Education) initiative, which includes all donors working in the country's education sector. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Program Project Management: Executing/Implementing agencies Sector Related Issues: Education Methodologies/Approaches: Holistic approach The Education Sector Development Program (ESDP) was the first external loan project for the Ministry of Education (MOE), and at the beginning of implementation, MOE counterparts and project implementation unit (PIU) staff were unfamiliar with ADB's operational procedures and guidelines. In addition to formal training, routine operational contacts with consultants played an important role in developing staff capabilities in MOE and PIU. But this capacity building was hampered by high turnover of counterpart and PIU staff, including frequent changes of project manager. This highlighted the importance of staff continuity to ensure sustainable capacity building. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Program Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Education The mutually reinforcing nature of the policy reform program, the investment project, and the associated TA was a key factor in the successful performance of the Education Sector Development Program (ESDP). The program and the project were complementary in many key areas, and the associated TA provided related capacity building. This was the principal rationale for the adoption of the sector development program Modality, and the ESDP provided validation for the sector development approach. project cycle stage: Appraisal Lesson Topics: Modality: Program Modality: Technical Assistance Capacity Development: Capacity building Sector Related Issues: Education Policy & Reform: Policy reforms/framework Methodologies/Approaches: Sectoral approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/education-sector-development-program-3
Power and District Heating Rehabilitation Project | Kyrgyz Republic | Energy | 2004-08-13 | Due to the rapid shift from industrial to residential power demand, the existingtransmission line is congested, and the new transformers provided under the project cannot befully used. Such a trend is common in transition economy countries and needs to beconsidered in demand forecasts and transmission planning. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Energy planning/management Policy & Reform: Transition economies For future projects, a special mission should review the financial viability of successor companies and assess their capability to implement projects prior to the unbundling of executing agencies. When problems are foreseen, agreements should be reached with borrowers to take corrective measures. In this project, unbundling Kyrgyz National Energy Holding Company or KNEHC (the executing agency) was considered necessary by development partners to reform the energy sector. However, the unbundling resulted in a lack of initiative to complete the remaining components. After the split of KNEHC, the Project Implementation Unit (PIU) became a part of National Electrical Grid, but the PIU was unable to enforce effective control over the implementation and monitoring of three parts of the project. Bishkek Heating System (BHS) had the most implementation problems. The loan proceeds were used to procure pipes before KNEHC was unbundled, but BHS inherited incomplete works and debt service obligations. The remaining pipelines account for $6.2 million of the new pipes, or 8% ofthe total project cost. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Energy planning/management Policy & Reform: Reform The project was financed by several organizations, each having different set of rules andprocedures for procurement. This resulted in a longer learning period, and projectimplementation was delayed at the beginning. For future projects with new executing agenciesand several financing organizations, special procurement training should be arranged during theproject preparation stage. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-and-district-heating-rehabilitation-project
Flood Emergency Rehabilitation Project | Kyrgyz Republic | Agriculture, Natural Resources, and Rural Development, Energy, Education, Health, Water and Other Urban Infrastructure and Services, Multisector | 2003-12-15 | The executing agency's (Ministry of Ecology and Emergency Situations's) ability to implement the project was overestimated at appraisal, which required changes to be made in the implementation arrangements during the course of implementation,and the provision of significant additional consultancy inputs. For example, no provision for hiring a detailed design firm was included in the project at appraisal.The executing agency did not have the capacity to undertake adequate design works, and during projectimplementation, a decision was made to engage such a firm. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment The retention money for the civil works contractors was to be paid entirely fromcounterpart funds at the end of the project. Although this mechanism mitigated the financialburden on the government during implementation, it resulted in some contractors not being paidafter project completion. project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Management: Procurement The supervision of the 39 subprojects was inadequate. As a result, performance of thecontractors was not always satisfactory and included such problems as the use of substandardmaterials. project cycle stage: Implementation Lesson Topics: Project Design: Subprojects Project Management: Procurement Project Management: Project supervision | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/flood-emergency-rehabilitation-project
Road Rehabilitation Project | Kyrgyz Republic | Transport | 2002-12-13 | For new executing agencies (EAs) dealing with the ADB for the first time, particularly in transition economies,more attention needs to be given to familiarize them with ADB guidelines and procedures forsmoother project implementation. project cycle stage: Design, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Policy & Reform: Transition economies The feasibility study and preliminary design should have been followed by more carefuldetailed design, and the project scope should have been reconsidered to allow proper treatmentof the mountainous sections of the road. In this particular case the consultant that had beenengaged to prepare the feasibility study and detailed design for the project was also engaged toprepare the detailed design for the Second Road Rehabilitation Project as well. While this hasnumerous benefits, a possible disadvantage is that possible deficiencies in the consultant'swork experienced in the first project may affect the second project as well. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Consultants Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/road-rehabilitation-project-2
Agriculture Sector Program (Loan 1407-KGZ[SF]) | Kyrgyz Republic | Agriculture, Natural Resources, and Rural Development | 2002-10-31 | ADB staff resources for the supervision of the program and the associated TAs were limited, and review missions were heavily burdened with other tasks. This resource constraint shortened the time available for staff to review and supervise the program implementation, leaving little time for reviewing the assessments of the TA consultants and government statements claiming notable achievements. Resources for supervision should be allocated to match the demand imposed by the complexity of the program. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Project administration Project Management: Project supervision Capacity Development: Human resources management Capacity building, in the midst of downsizing across all sectors, coupled with frequent changes in the government, was difficult to achieve. Difficulties were compounded by lack of experience given the scale of the transition, and an unforeseen political context and processes to effect and manage changes. Institutional development could not be effectively achieved when reorganization, downsizing, and staff changes occurred frequently, and when the government was forced to stipulate fiscal austerity instead of budgetary support for redefined roles and functions. Institutional reforms require an in-depth institutional assessment that specifies the requisites of capacity-building initiatives and the conditions for the initiatives to succeed. project cycle stage: Feasibility Lesson Topics: Project Management: Risks/Risk management Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Institutional analysis Policy & Reform: Reform Corporatization and privatization of state organizations were not followed up, as there was no requirement for the government to monitor the status of the emerging enterprises once it no longer held any shares in the entities. In some cases, privatization proceeds could not be recovered easily, and were reported still outstanding and not fully paid to the government. Further, the commercial and financial viability of privatization efforts should have been emphasized, without which privatization could effectively mean dismantling and liquidation of state assets, and subsequent insolvency and bankruptcy of emerging entities. The second tranche release conditions included corporatization and privatization measures, and this could compromise the quality of the privatization process as the specific steps for corporatization and privatization were not indicated. Privatization initiatives should have clear objectives to distinguish them from other acts of dismantling state interests such as liquidation of state assets and divestments. Steps for pursuing privatization should be spelled out, emphasizing transparency, and indicating the milestones for monitoring progressive achievements based on the desired objectives of privatization. Further, ex-ante analysis of privatization s fiscal impact should be conducted during the design of future programs. project cycle stage: Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial analysis Project Design: Project design Policy & Reform: Privatization Policy & Reform: Public sector reform Policy & Reform: Reform The dynamics of policy reforms makes it difficult to design and implement reforms with a one-time blueprint approach as a yardstick. Refinement and deepening of reform measures were evident, and adjustments were needed to respond to unforeseen dimensions of the reforms, and incorporate ways to overcome resistance to change. Sticking to fixed conditionalities is not the best option when such measures are overtaken by events and affected by changed circumstances. Delays in implementation of certain measures do not necessarily reflect waning support for reforms, for delays may mean unrealistic timeframe, or the change processes may require repeated attempts to overcome resistance to change. The impacts and likely consequences of reforms may extend over a considerable length of time, even beyond the postevaluation period. Long-term engagement is required, with options to devise other measures along the path of the desired reform direction. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity development Policy & Reform: Policy reforms/framework The program timeframe of 24 months was unrealistic and did not specify the phases of institutional changes that would have allowed capacity building over the designated period. The timeframe was dictated by the urgency to provide budgetary support to the country. The policy content of a program loan should be realistically appraised against the time required for implementing the specific policy measures and their requisite components, taking into account ex-ante risk assessments and the absorptive capacity of the government to implement such initiatives. Although predicting the outcomes of reforms was difficult, a logical framework and a monitoring and evaluation system for the program should have been developed. project cycle stage: Appraisal Lesson Topics: Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/agriculture-sector-program-loan-1407-kgz-sf
Financial Intermediation and Resource Mobilization Program | Kyrgyz Republic |  | 2002-08-15 | As long as corporate governance of potential borrowers has not markedly improved, thevulnerability of banks can be diminished only at the cost of reducing their role in financialintermediation. One cannot expect credit growth to resume without a successful restructuring ofthe corporate sector to ensure effective debt resolution and viability of potential borrowers.Therefore, the timing of financial and corporate sector reforms should be well coordinated.Recognizing this, ADB has been engaged in policy dialogue on the governance andrestructuring of the corporate sector and reached agreement on a reform agenda. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Financing Policy & Reform: Policy matrix Policy & Reform: Public sector reform Policy & Reform: Reform Improved regulation and transparency of financial markets are necessary conditions forsignificantly increasing their role in resource mobilization, but not sufficient ones. As far as atransition economy is concerned, meaningful equity markets cannot be developed rapidlywithout the massive sale of state shares in companies through the stock exchanges.This link between privatization and the development of local equity markets should beconsidered in the design of future privatization policies and programs. In turn, thenonconformance of state-owned enterprise's (SOE's) with listing requirements and corporate governance standards actsas a deterrent to their entry into the capital market. The expectation of privatizing poorly performing enterprises without prior restructuring through the stock exchange is unrealistic. Technical compliance with a condition to offer sharesin companies that cannot be sold is a meaningless exercise that contributes nothing todeveloping equity markets. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Program Project Design: Project design Policy & Reform: Privatization Policy & Reform: Public sector reform Policy & Reform: Transition economies It is necessary to clearly define the role that foreign banks are to play in banking reforms of a transition economy from the onset of a reform program. The question is how to efficiently use foreign investment as a vehicle for stabilizing and modernizing the banking sector, and increasing confidence and financial intermediation. So far, few, if any, transition economies have managed to successfully reform the banking system without systematically integrating foreign banks in restructuring and consolidation (Siegelbaum et al, pp. 140 and 141). project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Policy & Reform: Public sector reform Policy & Reform: Reform Policy & Reform: Transition economies Kairat Bank (KB), established in 1999 to manage performing assets of and deposits from problembanks, proved underfunded by September 2000. This development is typicalfor a transition economy confronted with severe fiscal constraints and a lack of properaccounting figures that reflect the real quality of assets. A banking sector crisis and a furtherdecline in public confidence in the banking system could be prevented only by a flexible andtimely reaction of the authorities under the Financial Intermediation and Resource Mobilization (FIRM) Program. KB was recapitalized with government bonds in March 2001 and its nonperforming loans (NPLs) were transferred to the Debt Restructuring Agency (DEBRA). The expectation, however, that KB could be privatized soon after recapitalization was unrealistic. This observation is in line with theexperience of other transition economies (Enoch et al, p. 58). project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Country Context: Crisis/Post-crisis Policy & Reform: Privatization Policy & Reform: Transition economies Methodologies/Approaches: Process approach Not much progress has been made in the consolidation of the Kyrgyz banking sector. It has proved more difficult than anticipated to privatize or merge banks and to enforce the orderly exit of weak banks. In dealing with the weaknesses in the banking sector, the Kyrgyz authorities were hindered by the absence of a recognized legal framework, weaknesses in thejudiciary, the lack of precedent, the fear of losses among the banks' customers, and the political strength of owners or managers. This underlines the fact that the Kyrgyz Republic is a typical transition economy in this respect, too (Enoch et al, p 54). Strong political commitment to proceed with banking consolidation is especially important when interventions aretaking place, as legislation is being passed and enacted. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Capacity Development: Ownership Policy & Reform: Privatization Policy & Reform: Transition economies The strengthening of banking sector intermediation is a lengthy process in a transitioneconomy, especially if it has a small and vulnerable banking sector prone to recurrent crises. Inthe Kyrgyz Republic, the crises in 1998 and 1999 have resulted in a significant decline in thebanking sector as a share of GDP, a trend that has not been rapidly reversed. Thiscan be partly explained by a serious and sustained loss of public confidence in the bankingsystem, even in those cases where depositors did not in principle lose anything. In addition,examples of other transition economies point to the importance of consolidation, which is noteasily accomplished in a typical transition economy, to pool a critical mass of resources formeaningful levels of intermediation. What is more, there is a clear link between financial andcorporate sector restructuring. All these factors point to the need of sustained interventions inthe financial sector of a transition economy to significantly improve financial intermediation. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Financing Country Context: Crisis/Post-crisis Policy & Reform: Public sector reform Policy & Reform: Transition economies | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/financial-intermediation-and-resource-mobilization-program
CAREC Regional Road Corridor Improvement Project: Completion Report | Kyrgyz Republic, Tajikistan | Transport | 2014-01-09 | 1. Project engineering design. To avoid potential cost overruns during the project implementation period, the engineering design of roads at the project preparation stage should be based on the most reliable traffic forecasts and sufficient geological and climate surveys to enable the preparation of realistic designs without the need to amend them later. Road safety issues should be identified during the project design period in consultation with local communities, and features that enhance road safety, including on sidewalks and at bus shelters, should be adequately reflected in the project design. [Main text, para. 52] project cycle stage: Design, Implementation Lesson Topics: 2. Border infrastructure improvement. The benefits of good infrastructure at border crossings can be fully realized only when countries on both sides of a border fund complementary investments and when their border control agencies cooperate. Projects should support the construction and renovation of border-crossing points in a country where investments to upgrade complementary facilities on the other side of the border have been completed or are nearing completion. [Main text, para. 53] project cycle stage: Country Partnership Strategy Lesson Topics: 3. Performance-based maintenance (PBM). Implementing PBM contracts requires sufficient preparation and time for transition. More attention should be given to PBM readiness and to such important factors as allocating proper budgets, developing institutional frameworks, establishing legislation and procedures, recruiting qualified consultants, mitigating negative effects on road maintenance units, and fostering local private contractors. In both countries, the PBM pilot testing was delayed mainly because of the lack of experience and knowledge of the executing agencies. When introducing new concepts and practices to a country, ADB should provide adequate technical support and consider well the local administrative system and situation and share global best practices, as well as including such activities as organizing a study tour and assisting in systematic implementation of related reforms for the whole sector. [Main text, para. 54] project cycle stage: Implementation Lesson Topics: Project Management: Project administration Project Management: Project management Capacity Development: Capacity development 4. Road safety and road asset management. Road safety and road asset management components should be included in all future transport projects because they are essential to the sustainability of projects and to their effectiveness. As road safety involves various agencies, the design and implementation arrangements for this component should be based on extensive discussions with all related agencies and policy dialogue with high-level government bodies. Similarly, comprehensive road asset management plans should be developed during project design in consultation with the agencies responsible for road assets development and for operation and maintenance. [Main text, para. 55] project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Transport planning 5. Regional project. This project was designed as a regional project including two countries. A joint effect was observed by executing the two countries' projects simultaneously, yet different institutional frameworks and different effective procedures were required in the two countries. Thus, full agreement among stakeholders is necessary in designing future regional projects. [Main text, para. 56] project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Project Design: Project design | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/carec-regional-road-corridor-improvement-project-pcr
Regional Trade Facilitation and Customs Cooperation Program | Kyrgyz Republic, Tajikistan | Industry and Trade | 2006-12-15 | Customs reforms deal with a variety of issues pertaining to a country's policies, laws, and institutions, particularly in transition economies. Considering the two countries' stage of development as well as the availability of resources, it was acknowledged during program implementation that all concerns cannot be suitably addressed by a single round of reforms. The process takes time and requires a long-term view. Every new set of measures should build on past reforms. Results of the program made it clear that approval of the Regional Customs Modernization and Infrastructure Development Project (RCMIDP) was essential to advance the reform process. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Legal system Modality: Program Project Design: Project design Sector Related Issues: Industry and Trade Policy & Reform: Policy reforms/framework Policy & Reform: Reform Policy & Reform: Transition economies Packaging the program loan with TA grants represented a holistic approach and regional perspective to customs reform and it also provided a built-in assistance program to facilitate government officials' efforts to implement required policy changes. Related PPTA, in particular, offered technical support in preparing various investment plans for future financing of customs infrastructure. With this technical support, together with TA 6058-REG, customs authorities recognized the benefits of customs modernization across and outside of CAREC member countries. This not only convinced customs authorities of the benefits of reforms but also made it possible for them to undertake the necessary reforms. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Finance & Financial Aspects: Financing Modality: Program Modality: Technical Assistance Project Design: Project design Sector Related Issues: Industry and Trade Policy & Reform: Policy reforms/framework Methodologies/Approaches: Holistic approach The fulfillment of a key policy condition in the Kyrgyz Republic was slightly delayed due to the need to first amend a pertinent law. To facilitate compliance with program conditions requiring passage of laws, it is important to undertake upfront and sustained policy dialogue with policymakers, members of Parliament and other stakeholders, including to disseminate the benefits of reform through seminars and workshops. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Loan Agreement: Covenants Modality: Program Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Trade facilitation and customs reforms require intensive and ongoing cooperation and coordination with trade partners. Regional forums (e.g., those organized by the Customs Cooperation Committee) provide a good venue for multi-country discussions and a convenient launching pad for bilateral talks. Such meetings also build camaraderie among countries and their top officials, and they help foster regional economic cooperation. The governments of the Kyrgyz Republic and Tajikistan did not have difficulty fulfilling program conditions that called for bilateral agreements and negotiations, as neighboring countries also saw the benefit of such reforms and were therefore strongly supportive. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Modality: Program Sector Related Issues: Industry and Trade Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/regional-trade-facilitation-and-customs-cooperation-program-0
Basic Education Sector Development Program: Validation of Completion Report | Lao PDR | Education | 2015-12-24 | Three important lessons were identified in the PCR (program completion report) and this validation acknowledges them as important. In particular, taking a sector-wide approach to sector development with implementation support that is closely linked to and complements policy reform is important. It is clearly essential to ensure that there is close alignment of the content of the RRP (report and recommendation of the President) and the explicit outcomes and outputs in the DMF (design and monitoring framework). This validation notes that there were a number of inconsistencies in the RRP. project cycle stage: Concept, Implementation There was clearly strong coordination and strategic dialogue among all stakeholders in this program. This appears to have been a strong feature of the BESDP (Basic Education Sector Development Program) implementation effort with the executing agency, consultants, and ADB freely interacting and discussing issues that allowed some recovery from initial delays. project cycle stage: Implementation There was value gained by engaging MOES (Ministry of Education and Sports) units as implementing partners to help build institutional capacity and ensure sustainability at post-project. This is often discussed in the design of development aid programs but is rarely evident in the final implementation. In this program, the careful identification of responsibilities and division of labor, clear unit and individual accountability, and sustained monitoring were critical to its success. project cycle stage: Design, Implementation, Operation It is essential that the DMF (design and monitoring framework) in the RRP (report and recommendation of the President) accurately presents the outcomes, outputs, and indicators that will be used to evaluate the performance of the program. Monitoring systems should be specified in the RRP and established at implementation and that responsible staff are identified at central and local levels for monitoring key activities. project cycle stage: Concept, Implementation, Operation | Validation of Project/Program Completion Report | Successful/Generally successful | http://wcm.adb.org/documents/lao-people-s-democratic-republic-basic-education-sector-development-program
Northern Greater Mekong Subregion Transport Network Improvement Project: Completion Report | Lao PDR | Transport | 2015-10-31 | The project demonstrated that the upgrading of national roads that connect the poorer districts of the Lao PDR is a viable means of addressing accessibility to markets and services for poor rural districts. The project provides an important link in the GMS (Greater Mekong Subregion) transport corridors connecting northern Thailand, northern Viet Nam, and the southern provinces of the PRC (People's Republic of China). The project will enhance subregional connections between the northern Lao PDR and surrounding countries, as well as economic growth and poverty reduction within the country. project cycle stage: Operation Project implementation delays in the civil works for contract R4-1 (Xieng-Ngeun - Pak Khone) were caused by a non-performing contractor, requiring the reallocation of part of the civil works to the performing contractor for contract R4-3 (Nam Pui Bridge - Paklay Bridge) to expedite and complete works in a timely manner. The lesson learned from this is that the executing agencies of future projects need to identify and replace non-performing contractors at an early stage and replace them with performing contractors. An additional lesson learned is that executing agencies need to carefully scrutinize the financial, management, and equipment capacities of bidders during bid evaluation. project cycle stage: Implementation Another important lesson learned from the project was that the use of a 6-year implementation period and design - construct contracts for the civil works packages was successful in addressing implementation delays that have occurred in previous road projects in the Lao PDR. The reasons for this success are (i) consultants can review contractors' designs easily and maintain the quality of design, and (ii) design - construct contracts can shorten the implementation period. The four project road contracts under the direct control of ADB and the supervising consultants, together with the rural access road and periodic road maintenance contracts were completed within their contract periods. Only project road section R4-1, financed by the Government of the Republic of Korea, experienced delayed implementation and a civil works contract extension of 14 months, with provision of additional government contributions for road works. project cycle stage: Design, Implementation Regarding use of the RMF (road maintenance fund), while the funding base for the RMF is broadening and annual expenditure allocations increasing, the fund is now spending only part of its income on maintenance and the amount for routine maintenance is relatively small. The RMF is not independent from the government budget system, and in 2014 - 2015 only 89% of fuel levy revenue is budgeted to be spent. This raises potential concern as to the future sustainability of the overall road maintenance. It is recommended that future projects consider how the road maintenance funds accounting system could be independent from the government budget system and made more flexible, to cover all maintenance work for roads. As for the road maintenance for the project roads, the PCR (project completion report) mission noted some maintenance work in progress during the field visit. However, more significant road maintenance activity occurs after the annual rainy season and needs to be reviewed. project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/lao-northern-gms-transport-network-improvement-project-pcr
Northern Region Sustainable Livelihoods Through Livestock Development Project: Completion Report | Lao PDR | Agriculture, Natural Resources, and Rural Development | 2015-06-24 | The speed with which VLF (village livelihood fund) loans were absorbed shows that there is a strong unmet demand for credit among livestock producers. Access to finance is a constraint to further expansion of livestock production. Increases in loan ceilings and tenure terms are needed to meet the needs of commercial producers. The issue is whether such finance is best provided through commercial channels at market rates or through ad hoc, heavily subsidized arrangements like the VLF. project cycle stage: Feasibility, Implementation While the project design was inclusive of women and ethnic groups (and while it met related targets), the poorest households were harder to reach, despite the attention given to poverty targeting. The poor had less free time to participate in project activities, and were less able to bear the risk of intensified livestock. project cycle stage: Design, Implementation Experience from this project and from other countries at a similar development stage shows that the transition from low-input livestock to commercially oriented production is a lengthy process that is seldom achieved in less than 10 years or by any single project. Sustained donor engagement is important. project cycle stage: Implementation, Operation Attitudinal change is a slow process. The limited education of women and their traditional household roles constrained their participation in LPG (livestock production group) meetings, which included men and women. These factors also caused women, especially those from ethnic groups, to revert to traditional livestock practices. project cycle stage: Implementation Language was a barrier to full participation by the relatively isolated ethnic groups, particularly ethnic women. The project's provision for numeracy and Lao language training was too small to be effective. More effort is needed to conduct training and prepare extension materials in different ethnic languages. project cycle stage: Implementation Achieving GAP (gender action plan) targets relied on suitable training of DAFO (district agriculture and forestry office) and DLWU (District Lao Women's Union) staff in participatory methods, and clear and realistic targets for women's participation that were easy for project staff to understand and monitor. In contrast, the objectives of the EGDP (ethnic groups development plan) were less clear, and little specific training was given to project staff, which limited some outputs of the EGDP. project cycle stage: Implementation A highly centralized management structure is unsuited to projects covering dispersed, remote areas because it limits the flexibility to respond to community demands and needs, and it stifles the initiative and ownership of implementing partners like the DAFOs (district agriculture and forestry offices) and PAFOs (provincial agriculture and forestry offices). project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/northern-region-sustainable-livelihoods-through-livestock-development-project-pcr
Capacity Strengthening of the National Statistical System: Technical Assistance Completion Report | Lao PDR | Public sector management | 2015-06-01 | TA (technical assistance) implementation faced challenges at the initial stages due to the EAs (executing agencies) limited experience in working with ADB. A suitable coordination mechanism was not in place at TA inception, which led to a delay in creating the TA work plan and launching activities. These issues were resolved after DDS (Department of Data Service) staff were assigned as TA coordinators to liaise with line ministries that were involved in TA activities. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/capacity-strengthening-national-statistical-system-tcr
Strengthening Capacity for Enhanced Operational Effectiveness: Technical Assistance Completion Report | Lao PDR | Public sector management | 2015-06-01 | Major lessons include the need to involve senior officials and counterpart technical staff at the early stage of TA (technical assistance) design to ensure relevance and national ownership during implementation. ADB's Country Partnership Strategy sector indicators should align with the current national sector indicators to ensure government and ADB staff regularly monitor progress toward achieving sector targets. There is a need for better designed project monitoring and evaluation systems, more consistent vertical logic, and more detailed consideration of assumptions and risks. Project cycle stage: Design, Implementation, Country Partnership Strategy | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-capacity-enhanced-operational-effectiveness-tcr
Support for Post-Private Sector and Small and Medium-Sized Enterprises Development Program Partnership Framework: Technical Assistance Completion Report | Lao PDR | Industry and trade | 2015-05-01 | (i) Continuous policy dialogue and policy development are important for sustaining reforms; (ii) institutional development and engagement of stakeholders in the program are necessary for quality policy development; and (iii) Trade policy should include measures that increase the benefits to SMEs (small and medium-sized enterprises) from trade. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-post-private-sector-and-sme-development-program-tcr
Renewable Energy Development in Remote Communities Project: Technical Assistance Completion Report | Lao PDR | Energy | 2015-03-01 | The unsuccessful result of the PPTA (project preparatory technical assistance) mainly ascribes to the transition of Lao PDR's status from being eligible for 50% grant and 50% loan to loan only. However, there are lessons to be learned from the PPTA such as the need for the project concept to have a clearer vision and methodology to implement rural electrification in the most challenging remote areas of Lao PDR. Also, the original PPTA implementation duration which was effectively only for six months from the signing of the technical assistance letter, including the recruitment of the consulting firm, is judged to be too short, especially when the terms of reference included an assessment of renewable energy resources. Splitting the project preparatory activities into a PPTA and a CDTA (capacity development technical assistance), and also dividing responsibilities between a consulting firm and an individual consultant do not seem to have been an effective approach either. Project cycle stage: Concept, Design, Implementation | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/lao-renewable-energy-development-remote-communities-project-tcr
Basic Education Sector Development Program: Project Completion Report | Lao PDR | Education | 2014-09-01 | Sector development program modality. The Basic Education Sector Development Program demonstrated the efficacy of the sector development program (SDP) modality in providing complementary policy and implementation support, if well designed and supported. However, in future SDPs, it will be important to link program and project components more explicitly (e.g., identifying how the project will support achievement of policy actions) to maximize efficacy, while ensuring close alignment in the content of the Reports and Recommendations of the President and the design and monitoring framework. It will also be important to correctly balance comprehensiveness with feasibility, ensuring a critical mass of interventions while avoiding excess complexity or spreading resources too thinly. Maintained strategic dialogue. The original project design's alignment with the government's objectives benefited from strong dialogue during the design phase, as well as from ADB's prior engagement in the country's education sector. Implementation also benefited from continuous close dialogue between the executing agency, consultants, and ADB (including on policy and technical dimensions), which allowed for recovery from initial delays and timely and flexible responses to emerging issues. It also enabled ADB to share relevant regional experiences, tapping its role as a leading development partner organization supporting secondary education sector reforms in the region. Strong support and cooperation from the resident mission played an important role, as did the relative continuity in ADB, the project management unit, and consultant teams throughout implementation. Engaging Ministry of Education and Sports (MOES) units. The approach of engaging multiple MOES units as focal points for implementing particular interventions posed some challenges but proved advantageous on balance, enhancing ownership and building capacities to sustain benefits post-project. In addition to close coordination, careful specification of responsibilities and division of labor, clear unit and individual accountability, and sustained monitoring are critical in such a model. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/lao-pdr-basic-education-sector-development-program-pcr
Northern and Central Regions Water Supply and Sanitation Sector: Project Completion Report | Lao PDR | Transport, Water and other urban infrastructure and services | 2014-09-01 | The free connection policy has clearly shown its enormous impact on water supply coverage. A condition of connecting a premise to the water supply is that it must have a sanitation facility complying with local sanitation regulations. Residents are willing to install an approved sanitation facility so they can access the free connection to the piped system. Moreover, this policy has tremendously impacted sanitation coverage in the target communities. The tariff adjustments enabling the participating provincial nam papas substantially to comply with the agreed financial objectives for the sector have demonstrated that key reforms do need to be leveraged from closely linked investments. The executing agency has acknowledged the success of the tariff reform leveraged off the water supply investments under the project. Design of the project was developed based on an understanding that a significant degree of sector reform had been achieved and capacity developed under previous initiatives. In reality, this understanding was overly optimistic. With the benefit of hindsight, the design was too complex and ambitious, such that the scope exceeded the resources available and the absorptive capacity of some stakeholder institutions. Procurement packaging needs to be rationalized for effective and efficient contract management. No matter how small, contracts still require significant resources for bid document preparation, bid evaluation, contract negotiation and award, and contract management. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/lao-pdr-northern-central-regions-water-supply-sanitation-sector-pcr
Roads for Rural Development Project | Lao PDR | Transport | 2014-03-01 | The project demonstrated that the improvement and upgrading of rural roads in the poorer districts of the Lao PDR is a viable delivery mechanism for the planning, development, and management of rural access roads to yield developmental benefits to poorer and remote communities. While project cost escalations compared with appraisal estimates are difficult to anticipate, a primary lesson learned was the benefit of advanced design and tender document readiness for civil works being prepared at appraisal. This allows early civil works contracting and mobilization, ensuring appraisal loan completion dates can be achieved. The difficulty of accurately assessing the full economic impact and poverty reduction benefits of this project because of the delay in conducting baseline benefit monitoring highlights the need to ensure the immediate commencement of baseline data measurement prior to civil works commencement. This lack of focus on the benefit monitoring evaluation system within both the Ministry of Public Works and Transport and implementing consultants is a lesson learned in that future projects need to include benefit monitoring evaluation capacity building and training with executing agencies at both national and provincial level. Project implementation delays in the civil works for contracts C03 (Pakton-Ban Vang road) and C05 (Sayabury-Hongsa-Thaxoan road), requiring the reallocation of a part of civil works to the performing contractor for contract C01 (Pakxane-Thasi road) to expedite and complete works in a timely manner, indicates a lesson learned that executing agencies of future projects need to identify and replace nonperforming contractors at an early stage. An additional lesson learned is that executing agencies need to more carefully scrutinize the financial, management, and equipment capacities of bidders during bid evaluation. Another important lesson learned from the project was the successful integration with complementary agricultural development programs such as the Sanxai coffee estate developments under the International Fund for Agricultural Development project. To more directly facilitate agricultural development activities along rural roads being developed in future, consideration could be given to developing selected rural development schemes to directly support communities located along the rural roads. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/roads-rural-development-project-pcr
Rural Finance Sector Development Program | Lao PDR | Finance | 2013-01-10 | 1. To increase ownership and longterm commitment to goals, it is important that program support be embedded in a government strategy. Extensive preparation was made for the Rural Finance Sector Development Program in terms of market assessment and dialogue with government. The program was successful due to the close alignment of government and program objectives. project cycle stage: Lesson Topics: 2. Considering the extensive nature of program preparation related to client demand, the monitoring and evaluation of the program should have included a periodic assessment of client satisfaction or interim impact of the program objectives on clients. The customer satisfaction survey conducted as part of the project completion report review indicated that clients have appreciated an improvement in access to finance and in services provided, but that there are some serious consumer protection issues that need to be addressed. project cycle stage: Lesson Topics: 3. The reason why the program was not rated highly successful is because, despite the fact that the overall objectives were achieved (as defined in the design and monitoring framework), the linkage of the program to ultimately reducing poverty is weak. There was no substantial increase in access to formal financial services to rural, low-income clients. project cycle stage: Lesson Topics: 4. If success is likely at the midpoint of a technical assistance (TA), planning for follow-on support should then be undertaken. The outcome of the program could have been stronger with follow-on TA, particularly in the case of the Catalyzing Microfinance for the Poor TA. Feedback from a range of microfinance providers and stakeholders confirmed the need for follow-on support. project cycle stage: Lesson Topics: 5. Appropriate design of procurement proposal is important. The criteria for selection of an information and communications technology and management information system consulting firm was overly ambitious. Delays in implementation could have been avoided with more reasonable criteria. project cycle stage: Lesson Topics: 6. Translating training into institutionalized practice. Despite intensive onsite technical assistance, the Agriculture Promotion Bank management placed inadequate focus on the development of its human resources and capacity building, which were needed to ensure long-term sustainability. A number of staff training programs designed by the consultants experienced delays. Implementation of recommended action steps (such as the monthly monitoring meetings suggested for the branches) were not given sufficient importance. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-finance-sector-development-program-lao-pdr-pcr
Health System Development Project | Lao PDR | Health | 2013-01-07 | 1. Project design should include detailed implementation plans for the first year. If project implementation is not carefully planned, delays are inevitable. Simply listing outputs and fixing a timetable does not constitute effective planning, as illustrated by substantial delays of the training activities in this project. project cycle stage: Lesson Topics: 2. Consider carefully the implications of any major reallocation of project resources. When there are substantial unit-cost increases in a particular cost category (e.g., equipment or civil works), consider the project's overall objectives and priorities carefully before deciding to reallocate funds from other inputs. The alternative of reducing the quantities of those inputs having inflated costs will usually be an option. project cycle stage: Lesson Topics: 3. A health equity fund (HEF) is mainly funded through donor support and should have a larger government contribution to ensure ownership and commitment. Launch of comprehensive social health protection mechanisms such as HEF should be accompanied by an independent evaluation to assess cost-effectiveness, financial sustainability, and appropriate mechanisms to expand nationwide. Comprehensive communication interventions would have been beneficial to ensure a common understanding about beneficiaries' entitlements and providers' obligations. project cycle stage: Lesson Topics: 4. Despite the financial implications, health equity fund administration should have been continued by a third party to not unnecessarily burden the limited administrative and financial management capacities of the provincial health offices. Identifying mechanisms to enhance transparency would have increased the funds' efficiency. project cycle stage: Lesson Topics: 5. There was no verification undertaken as to whether the target mechanism used was appropriate to reach all eligible beneficiaries, nor was there an explicit targeting system to support ethnic groups. The targeting mechanism of health equity fund (HEF) should have been evaluated prior to scaling up the scheme. Careful consideration should be given also to adding a post-identification procedure to avoid denying HEF benefits to the poor who for some reason are not on the Ministry of PIanning and Investment lists. project cycle stage: Lesson Topics: 6. Data were regularly collected through the monitoring system. Nevertheless, data quality at entry remains poor and incomplete because it is not complemented by data from national routine reporting systems. Provinces and districts would benefit from capacity building on monitoring and evaluation to be able to use project data for results-based management. It is particularly important to monitor implementation of recommendations made during a midterm review and to evaluate and report on training outcomes. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/health-system-development-project-pcr
Lao People's Democratic Republic: Greater Mekong Subregion: Northern Economic Corridor Project | Lao PDR | Transport | 2012-12-17 | For regional projects, all parties should agree on uniform standards covering, in this case, vehicular movements across international boundaries. Both Thailand and the PRC have higher legal axle load limits than the Lao PDR. This creates enforcement issues on permissible axle load limits and should have been resolved early on in project preparation. [Main text, para. 28] project cycle stage: Implementation, Operation Lesson Topics: Sector Related Issues: Roading Sector Related Issues: Transport planning | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/lao-people-s-democratic-republic-greater-mekong-subregion-northern-economic-corridor-proje
Northern Community-Managed Irrigation Sector Project | Lao PDR | Agriculture, natural resources and rural development | 2011-11-01 | Because farm activities are highly seasonal, timely start-up of implementation is crucial in agriculture projects. This experience shows that the 6-month delay in mobilizing consultants contributed to the loss of a year of crop demonstration trials in the Year 3 subprojects. Agricultural extension activities usually consume a relatively small share of the total budget in irrigation projects, and therefore may get less attention from irrigation departments, which tend to focus on irrigation construction. The project experience shows that agricultural extension has a high pay-off where it is relevant to farmer needs, well supported by extension staff, and done over enough time to allow farmers to observe and digest the results. A comparison of the project and the Community-Managed Irrigation Sector Project (CMISP) experiences shows that effective control of construction costs through careful subproject selection, design, and construction supervision is essential to ensure that economic benefits are achievable. The project managers effectively absorbed the lesson of the CMISP, where high construction costs for many subprojects contributed to an ex-post EIRR that was well below the appraisal estimate. Almost all communities are experienced in managing their irrigation schemes and cultivating irrigated rice, but there remains a need for ongoing technical support and extension outreach after the schemes have been upgraded and turned over. There should be routine monitoring and support to the water user associations (WUAs). Without such support, the community-managed irrigation (CMI) systems will be slow to achieve their full economic potential, even though the investments may be economically viable as they stand. Project targets aimed at including vulnerable groups (women and ethnic groups) should be based on a thorough understanding of realities and local institutional capacity. In the project's gender action plan, the goal of reducing rice deficits was to be achieved by having women constitute 50% of farmers. Since rural women by tradition are fully active in farming, the 50% target was irrelevant. Moreover, there is no logical link between rice deficits and the number of female farmers. Similarly, the goal of achieving equality of extension staff by gender and/or ethnic group should have recognized local budgetary and human resource constraints. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/northern-community-managed-irrigation-sector-project
Lao People's Democratic Republic: Banking Sector Reform Program | Lao PDR | Finance | 2011-10-31 | 1. To improve the success of policy reform interventions, there is a need to ensure that executing and implementing institutions have adequate capacities in terms of staff and skills to supervise the implementation and operationalization of the reforms. For example, the Bank of the Lao People's Democratic Republic (PDR) under the Banking Sector Reform Program in Lao PDR could have rigorously supervised and controlled the banking system had it acquired adequate capacity to do so. Its lack of capacity still partly explain the continuing weak financial positions and nonperforming loans of state-owned commercial banks in Lao PDR. [Main text, paras. 14, 19] project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity building Capacity Development: Capacity development | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/lao-peoples-democratic-republic-banking-sector-reform-program
Second Education Quality Improvement Project | Lao PDR | Education | 2011-10-01 | Community ownership. To increase enrollment and sustain school operation and maintenance, community ownership is key. Strong community ownership and increased awareness of children education will improve enrollment in secondary and post secondary education. Quality of teachers. Teacher motivation and competency are a key factor in improving the quality of the education systems. Therefore, the provision of in- service training, as well as improved incentives for teachers should be continuously reviewed and adjusted to ensure motivation and retain teachers. Strengthening institutional capacity. To improve the effectiveness and efficiency of education management, it is essential to focus on building the capacity of provincial and district education offices during project implementation. Monitoring and evaluation. The establishment of a monitoring and evaluation system during project inception is important and it should be maintained until the project completion. Lessons learned and recommendations from the evaluation should be considered in the design of future projects. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/second-education-quality-improvement-project
Private Sector and Small and Medium-sized Enterprises Development Program Cluster (Subprograms I and II) | Lao PDR | Industry and trade | 2011-08-01 | This performance evaluation suggests several lessons. First, continuous policy dialogue and policy development are important for sustaining reforms. Under the Private Sector and Small and Medium-sized Enterprises Development Program Cluster (PSME) this was achieved through regular reviews, production of policy discussion notes, and joint work with counterparts. The post-program partnership framework (P3F) has been instrumental in maintaining the dialogue between ADB and government counterparts. Second, institutional development and engagement of stakeholders in the program are necessary for quality policy development. Third, policy-based programs should be designed to reflect the capacity of the executing and implementing agencies, and policy reforms should be commensurate with the program loan or grant amount. Fourth, trade policy should include measures that increase the benefits to small and medium-sized enterprises (SMEs) from trade, including measures to make it administratively easy to obtain certificates of rules of origin, an outreach strategy to help SMEs on trade policy developments and utilization of preferential trade agreements, and implementation of intellectual property rights that could benefit SMEs, such as geographical indications (regional trademarks). | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/private-sector-and-small-and-medium-sized-enterprises-development-program-cluster
Northern Area Rural Power Distribution Project | Lao PDR | Energy | 2011-06-01 | Transmission lines that traverse populated rural areas in the Lao PDR should continue to use the shield wire system and/or single-wire-earth-return system to minimize objections by affected persons and enhance the socioeconomic impact of the transmission component; The design of distribution networks should be improved by giving due attention to ensuring reliability and operational maintenance objectives rather than focusing solely on meeting connection targets; Consultants should be required to fulfill their obligations under the terms of reference and to ensure adequate reporting on implementation that will anticipate cost savings or overrun situations in time to take appropriate action; In the climate of international commodity volatility, contracts for supply materials and equipment for distribution systems should have provision for changes in aluminum, copper, and steel prices that might occur during the bid evaluation process; and The financial loan covenants for Electricite du Laos (EDL) should be accompanied by an agreed plan to achieve compliance over a prescribed period. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/northern-area-rural-power-distribution-project
Lao People's Democratic Republic: Vientiane Urban Infrastructure and Services Project [Loan 1834-LAO] | Lao PDR | Transport, Water and Other Urban Infrastructure and Services | 2010-12-31 | 1. A deeper analysis would have enabled a better assessment of the timing, resource requirements, and political will for institutional and policy reform. Implementing urban institutional reform is complex. It has failed to achieve the desired outcomes in part due to deficiencies in upstream project preparation. Designers of the project must pay careful attention to the following aspects of urban institutional reform: (i) its acceptance by all key stakeholders through a participatory process; (ii) a thorough understanding of local politics; (iii) realistic phasing, sequencing, and timing of its institutional and policy reform; and (iv) an appropriate balance between allocated resources and expectations of the stakeholders involved. A more open-ended policy dialogue may also prove more helpful than the application of loan covenants. If substantial policy change is involved, it would also be prudent to consider this as either (i) separate and parallel policy work in support of the investment components; or (ii) a two-phase process, with policy development preceding the investments. [Main text, paras. 8,54,92] project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Sector Related Issues: Urban sector/development Policy &amp; Reform: Policy reforms/framework Methodologies/Approaches: Policy dialogue 2. Difficult decentralization reforms will benefit from a systematic sector-wide approach to change. While building toward common reform agenda goals, several ADB initiatives toward decentralized urban governance were not adequately linked. This long process would have benefited from a comprehensive reform framework based on institutional, political, and economic imperatives and a clear sector road map. Actions have to be based on solid analysis and engineered to fit into a road map prepared in consultation with stakeholders, for example, a realistic time frame within the context of a medium-term fiscal framework. [Main text, paras. 84,93] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Country Context: Decentralization Sector Related Issues: Urban sector/development Policy &amp; Reform: Policy reforms/framework 3. A balanced approach to urban land use could potentially address some of the challenges of urbanization. A bottom-up approach to urban land use could help avoid a potential overload of infrastructure and service networks due to overcrowding, pollution, increased poverty, and environmental degradation. Building on the success of the village area improvement initiative, in particular (but also community participation initiatives in earlier ADB-supported urban projects), ADB's support for community planning could complement and support higher level urban and regional plans. This would facilitate the involvement of underserved communities in determining their priorities. Such community planning may be acknowledged within the development planning and management system. [Main text, para. 94] project cycle stage: Implementation Lesson Topics: Sector Related Issues: Urban sector/development Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation 4. A demand-driven community approach facilitates better implementation. The village area improvement experience highlights the importance of proactive communities during the design, implementation, and maintenance of projects. The use of similar principles may be replicated or expanded for a larger set of beneficiaries. An important lesson from the village area improvement program is its use of a demand-driven approach to development instead of the top-down, supply-driven activities of the past. The main advantages of the village area improvement approach are community inputs and an applied gender-balance concept. These include (i) the participation of many parties, (ii) consultations, (iii) action at the grassroots level, and (iv) the solidarity of the village committee members. [Main text, paras. 70,79,95] project cycle stage: Implementation Lesson Topics: Sector Related Issues: Urban sector/development Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation 5. Clear horizontal and vertical roles for urban sector agencies are important under a multisector approach. A multisector approach in the urban sector is readily implementable in the Lao People s Democratic Republic, because, for the most part, subsectors are within the mandate of the ministry responsible for urban development and its provincial branches. The approach can be enhanced further with the inclusion of urban transport in urban projects. This would not be difficult, given the mandate of the Ministry/Department of Public Works and Transport (MPWT/DPWT). But a multisector approach may be truly tested only when more stakeholders are added to urban projects or programs, bringing in expertise from outside MPWT/DPWT. Moving forward, stronger links may have to be established between (i) infrastructure and services provision and job creation and economic development; and (ii) investments in wastewater treatment and other initiatives responsive to urban issues (e.g., vehicle emissions) that involve outside agencies. Limited experience in dealing with outside agencies suggests that an expanded multisector approach will be difficult to implement without clarifying roles and responsibilities across agencies, horizontally and vertically. [Main text, paras. 56,96; Appendix 6] project cycle stage: Implementation Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/lao-peoples-democratic-republic-vientiane-urban-infrastructure-and-services-project-loan-1
Banking Sector Reform Program | Lao PDR | Finance | 2010-12-01 | Political support and macroeconomic stability are vital to the success of a development assistance program. At the time the Banking Sector Reform Program (BSRP) was approved, the government had just come out of a severe macroeconomic and fiscal crisis. The fiscal situation had stabilized by 2003 with a deficit equivalent to 5.6% of gross domestic product (GDP). The severe constraints on budget resources and suppressed spending on the economic and social sectors meant that the MInistry of Finance's (MOF) priorities were not closely aligned with the goals of the Bank of the Lao PDR (BOL) and the BSRP (which required a substantial placement of interest-bearing government recapitalization bonds in the two state-owned commercial banks or SOCBs). Focus in scope is important. The extended time period, the considerable amounts of counterpart and staff time, and the breadth of technical assistance (TA) support involved in program implementation (6 years and about $6 million in loan and grant-based TA resources) clearly indicate the scope and complexity of the program. Significant additional support was also provided under rural finance-related projects to address Agriculture Promotion Bank (APB) and microfinance-related measures. The BSRP's core and immediate objective was to address the crisis facing the banking sector by restructuring and restoring the SOCBs to financial health. Reforms directed at this objective required close attention and significant support given their urgency and fundamental nature. As noted above, however, the program's scope also included a wide range of other measures (e.g., reform of the judicial system) that diluted focus and complicated implementation (involving a significant number of implementing agencies, for one, made coordination more difficult) without directly supporting the achievement of the program's main objective, partly because of the much longer time and greater resources needed for effective implementation. Closer assessment of the judicial system at the time of program formulation could have highlighted the very basic level of capacity present, the long-term nature of the support needed, and inherent difficulties in meaningfully achieving the proposed goals within the program time frame and available resources. The program's approach to dealing with nonperforming loans (NPLs) might have concentrated more fruitfully on strengthening credit assessment with a focus on future cash flows rather than security, through greater support for the development of needed procedures and capacity in this regard. Attempting concurrent reforms of a fundamental nature in the legal and judicial system requires a significant commitment of resources over the medium to long term, well beyond those available under the program and its associated TA. The program's significantly longer than anticipated implementation also meant that there was considerable turnover of key staff within executing and implementing agencies as well as on the ADB team (six mission leaders over the course of implementation). These changes contributed further to delays as new staff learned their responsibilities and adjusted to the many exigencies of a complex and wide-ranging program. A program of more focused scope would have helped reduce the effective transition period for new staff, thereby allowing more effective and timely implementation. The tranche conditions were overloaded with complicated policy reforms and involved too many implementing agencies with different interests, overstretching the weak administrative capacity of the government. Policy conditions included adherence to complicated and lengthy governance agreement agreements; legislative reforms, among them, amendments to the Secured Transactions Law, the Law on (Civil) Judgment Enforcement, the Law on Civil Procedure, and the Anti-Money Laundering Law; the establishment of a financial intelligence unit at the BOL; and the placement of recapitalization bonds at the two SOCBs. A governance agreement to insulate a state bank from political interference was a relatively new instrument; its use in the Lao PDR was therefore tantamount to an experiment. Flexibility can help strengthen stakeholder ownership and support effective implementation. The first set of governance agreements had to be revised to unlock progress in implementation. Funding should be commensurate to the size and scope of the program to align incentives. The total amount of funding under the program was $15 million (spread over three tranches), yet the release of funds was contingent on compliance with some 42 conditions, some of which carried costs significantly greater than the program amount (e.g., recapitalization of the SOCBs). Interest payments alone on the recapitalization bonds were estimated at $18-$20 million over the originally anticipated program period of 3 years. Many conditions also involved fundamental and far reaching institutional changes that contributed to prolonging the implementation period by 3 years. This suggests a mismatch between the magnitude and scope of the reforms undertaken and the program amount, further diluting the incentives for timely and effective implementation. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/banking-sector-reform-program
Small Towns Development Sector Project | Lao PDR | Finance, Transport, Water and other urban infrastructure and services | 2010-12-01 | The community's involvement in various project activities and its interactions with the government and project staff greatly enhanced the sense of ownership. Community participation and contribution was the key to successfully completing the village upgrading subcomponent. This was evidenced by the fact that the actual community contribution of $206,000, mainly in cash, exceeded the estimated amount of $200,000 expected at appraisal to be mainly as labor. The success of the village upgrading subcomponent indicates the importance of stakeholder consultation throughout the planning, design, and implementation stages. Given the limited time and resources under the project, capacity building for urban development administration authorities (UDAAs) focused on construction management and supervision, operation and maintenance (O&M) of infrastructure and of sanitary landfills, and exchange of lessons among UDAAs. Various workshops were organized on these topics for managerial staff, accountants, and engineers of UDAAs. By strengthening core capacities, the project created momentum for continued support of long-term capacity building to enable UDAAs to provide quality public services. The project's geographical coverage posed a major challenge to monitor subproject implementation in 12 project towns located all over the country from the northern tip (Phongsali) to the south (Samakkhixai). Particularly during rainy season, it was time-consuming for project coordination unit (PCU) staff and consultants to travel to the project towns, as well as for personnel from UDAAs and project implementation units (PIUs) to attend meetings and workshops. Due to its underestimation at appraisal, insufficient travel budget hindered effective monitoring of subproject implementation in the project towns. The decentralized approach introduced during implementation contributed to strengthening the capacity of PIUs and speeded up project progress. PIUs demonstrated their abilities in implementing, supervising, and monitoring physical activities, as well as in managing civil works contracts. As a result, the project implementation was expedited at around midterm and caught up to schedule despite the delays in early stages of project implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/small-towns-development-sector-project
Country Assistance Program Evaluation for the Lao People's Democratic Republic: Sustainable Growth and Integration | Lao PDR | Agriculture, Natural Resources, and Rural Development, Finance | 2010-10-31 | 1. Securing the outcomes of development assistance in a small transitional economy requires the capacity and operating mode of the state be substantially transformed to develop new ways of regulating the economy and delivering public goods and services. Assistance needs to recognize the complex political economy of reform and work with other development partners especially in difficult areas of public administration and justice sector reforms. There is a need to take into account critical structural changes in governance (such as the changing roles and powers of central and subnational institutions in the system of government) and much greater emphasis needs to be placed on long-term institutional development, especially at the subnational level. In Lao People's Democratic Republic, ADB sector operations tried to address governance issues at the individual sector level, improving project-related procurement and financial management. But, without addressing and tackling other fundamental governance issues (e.g., poor public administration and weak capacity at the subnational level) with more suitable programs, a gap remained between recognizing a challenge and actually delivering effective strategies to deal with it. [Main text, paras. 34,82,87] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Capacity Development: Capacity assessment Capacity Development: Capacity development Country Context: political economy factors Country Context: Transition Policy &amp; Reform: Public sector reform Policy &amp; Reform: Reform Policy &amp; Reform: Transition economies 2. An aspect of assistance to an economy in transition is that there are many binding constraints and achieving successful outcomes requires progress in addressing them as a whole. While ADB cannot engage in all areas, it needs to identify which parallel constraints may affect its interventions and find ways such as development partner coordination to ensure that these constraints are addressed. To be selective while adding new priority areas of intervention, ADB needs to limit lending to a few sectors and prepare to phase out some sectors or subsectors based on a clear action plan, considering both ADB corporate priorities and the country's sector situations and partner coordination. As a large partner, ADB needs forward-looking analytic instruments and approaches to assess which constraints may become more important in the future. This entails increasing interactions with non-state actors, including academia and the private sector. In the future, greater attention will need to be paid to improving the synergies between the GMS program and the national program, particularly in terms of policy and institutional change associated with the 'software' aspects of the GMS program, such as the agenda to facilitate trade and transport. [Main text, paras. 35,36,80,88, Appendix 3] project cycle stage: Country Partnership Strategy Lesson Topics: Country Context: Prioritization Country Context: Transition Policy &amp; Reform: Transition economies 3. Continuity and long-term commitment in core sectors is required to deliver sustainable development outcomes. A stand-alone approach to projects has severe drawbacks in a country highly constrained by resource and capacity deficits. Sectoral assessments point to the prevalence of multiple project implementation units, parallel management systems, dependency on projects, and the lack of institutionalization arising from reliance on the project modality. These factors raise costs and erode long-term impacts. There is a clear need to adopt more program-based approaches in sectors for long-term engagement. [Main text, paras. 70,86,89] project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Project Methodologies/Approaches: Holistic approach Methodologies/Approaches: Sectoral approach Methodologies/Approaches: Targeting 4. The resident mission has, as a trusted partner, made important and growing contributions to the success of the ADB program. Delegation of project implementation support has had a significant impact on efficiency in delegated sectors, and the presence of local technical experts able to engage in dialogue and respond to ad hoc requests for advice has enhanced ADB's role as a source of advice to the government. Development challenges in the Lao PDR are no less complex than in much larger countries that can support scaled-up lending programs and greater staff resourcing. If ADB is to place greater emphasis on presenting knowledge solutions to this small economy in transition, one way to proceed is to further expand the capacity and responsibility of the resident mission, as well as the sector divisions, to enhance ADB's service delivery and program implementation. [Main text, paras. 34,85,91] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Country Context: Transition Other: Resident Mission Policy &amp; Reform: Transition economies 5. ADB and other development partners need to help the government address emerging vulnerability that threatens growth in the Lao PDR and its development path. These include environmental and social (E&amp;S) risks associated with natural resource exploitation, including foreign investment in mining, hydropower, and agriculture, as well as climate change risks, which may potentially compound other risks in natural resource management through effects on water resources. As a large player, ADB cannot treat these issues only in so far as they affect ADB projects. If it has instruments to address them, it should regard mainstreaming their use as a high priority. The chronic underfunding of recurrent expenditure identified in a number of sectors cannot be treated as a risk external to ADB assistance; rather, solutions need to be mainstreamed and coordination with other partners and the government needs to be pursued for addressing the underlying issues. [Main text, paras. 80,82,92] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Sector Related Issues: Water resource management | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-lao-peoples-democratic-republic-sustainable-growth
Lao People's Democratic Republic: Rural Access Roads Project | Lao PDR | Transport | 2009-12-31 | 1. A balance between forest conservation and conversion of forests into farmlands necessitates land use planning and appropriate land use controls. While acknowledging the need to increase food production, the continued conversion of secondary forests to farmlands has become a major issue linked with the improvement of roads. The need to conserve natural resources remains high but is now competing with the need for broad-based food security. This requires robust land use control laws that need to be enforced appropriately. Project appraisals should include land use planning to reduce the depletion of forests. [Main text, paras. 81,92] project cycle stage: Design Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Sector Related Issues: Roading Sector Related Issues: Transport planning Policy &amp; Reform: Policy reforms/framework 2. In the future, ADB should focus on a particular province or area to achieve implementation synergies, as well as to maximize project impact. The Rural Access Roads Project was characterized by a geographical spread of its subprojects in four different parts of the country. This created several implementation issues and diluted the impact of the project. [Main text, paras. 45,93] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Design: Project design Sector Related Issues: Roading Methodologies/Approaches: Targeting 3. Addressing opium cultivation in Lao PDR requires interventions that would complement road improvement. Although the Rural Access Roads Project was effective in reducing opium cultivation in the project impact area, there has been a rise in opium cultivation in other parts of Houaphan. While this is admittedly outside the control of the project, it implies that there is a need to put in place economic structures that create alternative livelihoods for the people in this province. In other words, improving roads alone is insufficient to create new economic activities. The government and other development partners need to address this issue in a more comprehensive manner. [Main text, paras.48,72,94] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Sector Related Issues: Roading Methodologies/Approaches: Holistic approach 4. The improvements in road designs needs to address safety issues linked to steep terrain in Lao PDR. Construction of roads remains a challenging task owing to steep slopes and landslides. The use of slope stabilization techniques for reducing landslides need to be mainstreamed. Moreover, at the appraisal stage, the preliminary road designs need to incorporate slope reduction measures to ensure road safety. It is noted that there needs to be an appropriate balance of economic viability of such measures. ADB and the Ministry of Public Works and Transport need to work together to identify low cost structures. [Main text, paras. 21,95; Executive Summary] project cycle stage: Design Appraisal, Country Partnership Strategy Lesson Topics: Project Design: Appraisal Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Roading 5. In ensuring that differential interventions are able to address inequality among ethnic communities, the appraisal team need to ensure proper assessment of social groupings and collection of baseline data at appraisal as well as use external monitors for social safeguards implementation. Roads may increase inequality between ethnic groups since benefits do not accrue equally to all groups. In the case of the project, all the ethnic communities were grouped into one category which negated addressing inequality among the communities. The project also lacked good baseline data which could have contributed to a sound project design. [Main text, paras. 44,76,97] project cycle stage: Design Appraisal Lesson Topics: Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Vulnerable groups Project Design: Appraisal Project Design: Project design Sector Related Issues: Roading 6. External agencies can be useful in environmental monitoring especially if concerned government agency lacks the capacity to ensure proper implementation of environmental safeguards. Given the lack of capacity within the Ministry of Public Works and Transport to monitor the implementation of safeguard measures in road rehabilitation affecting conservation areas, the International Union for Conservation of Nature has been an effective third party monitor. [Main text, paras. 79,98] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring &amp; Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Roading | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/lao-peoples-democratic-republic-rural-access-roads-project
Greater Mekong Subregion: East-West Corridor Project (1727-LAO[SF] and 1728-VIE[SF]) | Lao PDR | Transport | 2008-12-31 | 1. Complementary investments and institutional changes can help promote economic activities and facilitate trade in the transport corridor in the Greater Mekong subregion. Corridor-level impacts show an upside in promoting economic activities and facilitating trade, but benefits are still constrained by institutional constraints on the ground. The improvement of the road is not sufficient to trigger investments from the private sector. Policy and institutional changes are necessary to encourage private sector activities in production and services. [Main text, paras. 89, 108] project cycle stage: Operation Lesson Topics: 2. Multimodal planning is important for enhancing the effectiveness of the transport corridors. The improvement of the facilities at Da Nang port has removed logistics bottleneck and created synergies on the East West Corridor in Lao PDR. Government and development partners could extend such planning approach to other sectors such as railways and inland waterways. [Main text, paras. 53, 109] project cycle stage: Operation Lesson Topics: 3. Although the use of loan savings for additional works was justified, ADB could have carried out appropriate economic due diligence at approval and at completion to ensure that the selected subprojects were economically viable. In Lao PDR, there was no clear rationale for the selection of road projects and the use of loan savings on one of these additional works deprived the construction of a border facility that could have helped facilitate regional integration. [Main text, paras. 30, 32, 72-73, 102, 110] project cycle stage: Design, Completion Lesson Topics: Finance &amp; Financial Aspects: Disbursement Sector Related Issues: Roading Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/greater-mekong-subregion-east-west-corridor-project-1727-laosf-and-1728-viesf
Basic Education (Girls) Project | Lao PDR | Education | 2008-11-09 | 1. A successful approach in addressing teacher shortage in projects areas is the recruitment and training of local ethnic teachers. Student recruits from ethnic groups were given incentives such as scholarships, accommodation and tutorials. After completion of their studies, they were promoted to become permanent teachers. A pre-service and in-service training programs to accommodate students with less than 8 years of schooling. A community-based semester was also included to encourage students to maintain contact with their ethnic roots. At project completion, more than 95% of project ethnic teachers remain teaching in their villages. The Ministry of Education has adopted this approach nationwide with some adjustments to ensure there are sufficient funds to support it. [Main text, paras 17, 43, 45(i)] project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Education 2. An effective benefit and monitoring evaluation system could have better managed intended project results. Benefit monitoring and evaluation did not appear as formal issues in the project's preparation. Although the project working group and project coordination unit did maintain sound overall management control of the Project, the absence of clear time lines and milestones made detailed project monitoring and evaluation impossible. The initial project objective was clearly concerned with raising the quality of primary education, particularly for ethnic girls, but this concern was never articulated in terms of qualitative indicators during the project design. All available indicators were set to measure quantitative achievements, such as the number of schools to be constructed and number of teaching staff to be trained. [Main text, paras. 9, 38, 40, 45(ii-iii)] project cycle stage: Design, Implementation, Completion Lesson Topics: 3. A more realistic time scale and limited scope and geographical coverage should have been reflected at the time of project design. The Project exceeded its original targets by building more schools and training more staff than anticipated, but this was only achieved through an extension of project duration and by supportive and proactive officials at all management/implementation levels. Issues such as difficult logistics, adverse climate, poor communications, and an inadequate understanding of ADB procedures should have been better addressed in the initial project design. A sharper focused project on fewer provinces would have permitted a more thorough piloting of the project's innovative approaches before they were replicated on a wider scale. [Main text, paras. 22, 45(iv)] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Capacity Development: Partnerships Sector Related Issues: Education Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/basic-education-girls-project
Water Supply and Sanitation Sector Project | Lao PDR | Water and other urban infrastructure and services | 2008-01-08 | 1. Increasing water tariff before investments were made in water supply facilities would have made the project financially viable and sustainable. Noncompliance with financial loan covenants that included water tariff increases that would have been sufficient to cover O&M, depreciation, and debt service contributed substantially to the poor financial position of the provincial water supply companies and the project's low ratings for efficiency and sustainability. [Main text, paras. 33-34, 58, 64] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Loan Agreement: Covenants Sector Related Issues: Water resource management 2. High connection charges have resulted in low connection rates - limiting accessibility to water services. A more appropriate approach for water companies is to keep ownership of the assets and charge the depreciation cost by building this into the water tariffs or by imposing a flat rental fee. [Main text, paras. 52, 61, 65, 70] project cycle stage: Operation Lesson Topics: 3. The project management units should have made sure the water companies and the provincial departments of public works and transport understood their obligations to achieve the defined outputs and comply with the covenants in the loan agreement. Evaluation noted that the apparent lack of awareness of these stakeholders have led to the low achievement of the outputs and noncompliance with financial covenants. [Main text, paras. 45, 50-35, 58, 66] project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Sector Related Issues: Water resource management 4. There is a need for continuing support to ensure effective community participation. The community awareness and participation program (CAPP) appeared to be less effective, considering the low level of disbursements from the revolving fund and the slow implementation of the sanitation works. This was because the consultants were not based in the project area and could not provide continuous support to the newly formed water supply and sanitation user groups. [Main text, paras. 18, 38, 40, 67] project cycle stage: Implementation Lesson Topics: Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/water-supply-and-sanitation-sector-project
Community-Managed Irrigation Sector Project | Lao PDR |  | 2006-11-15 | 1. Formation and registration of the water users association (WUA) needs to be undertaken at the earliest appropriate time. Appropriate participation by women and men from all ethnic groups in the project area needs to be ensured in the process. Greater efforts are needed to ensure adequate participation by women in project activities, including recruitment and training of community level organizer and election of females to WUAs. In this project, the timing of WUA registration has contributed to implementation delays and women involvement failed to meet its target level of participation. [Main text, paras. 28, 31, 62(i,iii); Appendix 14] project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Vulnerable groups Project Design: Subprojects Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation 2. Greater efforts are needed to consult more fully with the communities in developing community action plans to guide subproject selection and design of interventions. Each subproject should include additional extension and demonstration of improved agricultural technologies for upland areas that do not benefit from the irrigation improvements. Stricter application of subproject selection criteria is needed at all stages of subproject identification in order to avoid developing subprojects that are less economically viable. In this project, some irrigation schemes did not fall within the selection criteria and increased investment cost per hectare. [Main text, paras. 14, 20-22, 51, 62(ii, iv,v)] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Design: Subprojects Sector Related Issues: Extension service Sector Related Issues: Irrigation management Sector Related Issues: Rural development Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation 3. More rigorous evaluation of design alternatives and supervision of infrastructure construction by the Office of National Project Director could have prevented cost escalations. These would have facilitated the design of viable least-cost solutions (as against the costly schemes in 3 subprojects) for improving irrigation infrastructure and higher quality construction, respectively. [Main text, paras.20-22, 62(vi, vii)] project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management Project Management: Project supervision Sector Related Issues: Extension service Sector Related Issues: Irrigation management 4. Continuing engagement of staff from executing agency's project team would allow smoother start-up and administration of follow-on projects. The project completion report has noted that the project extension period enabled preparation of the follow on project (Northern Community-Managed Irrigation Sector Project or NCMISP) and the smooth transition of the executing agency's project team to implementing NCMISP. [Main text, paras. 59, 62(viii)] project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Project administration Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/community-managed-irrigation-sector-project
Xieng Khouang Road Improvement Project | Lao PDR | Transport | 2006-09-14 | 1. The prequalification process needs to be more rigorous to avoid delays in implementation of civil works contracts by the incorrect choice of contractors.The prequalification of firms that do not have the capacity to undertake civil works implementation in a timely manner results not only in delays to civil works but has also necessitated the extension of the input of the construction supervision consultants. [Main text, para. 28, 62] project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement 2. Environmental problems encountered due to the lack of an environmental management plan and contractors not taking an active role in protecting the environment could be avoided by ensuring that a plan is developed and that civil works implemented by contractors are more actively monitored. Inadequacy of slope protection measures and disposal of spoil in the project as discovered by the Special Review Mission was similar to the findings of a safeguard reviewmission for Loan 1989-LAO: Northern Economic Corridor. ADB should ensure that adequate measures are undertaken to avoid their recurrence. [Main text, paras. 36, 59, 64] project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring & Evaluation: Monitoring and evaluation Project Management: Procurement Project Management: Project supervision Sector Related Issues: Roading Implementation schedules envisaged at appraisal need to be more realistically projected in light of other projects implemented in the Lao PDR. The Sixth Road Project was delayed 4 years due to similar problems with contractors. The Fourth Road Project was delayed about 3 years and the Fifth Road Project by about 18 months. project cycle stage: Feasibility Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Procurement Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/xieng-khouang-road-improvement-project
Primary Health Care Project in the Lao People's Democratic Republic (Loan 1348-LAO[SF]) | Lao PDR | Health | 2006-05-31 | 1. Systematic collection and recording of provincial health data is necessary in project monitoring and evaluation. Lack of baseline data in the pilot areas at the start of the project make it difficult to assess the outcome of the project. Thus, it is important to have a systematic health data recording in place. [Main text, para. 60, 61(ii)] project cycle stage: Feasibility Lesson Topics: Monitoring &amp; Evaluation: Baseline data Sector Related Issues: Health and sanitation management Methodologies/Approaches: Pilot project 2. Information dissemination and public awareness activities are necessary in changing behavior that would help improve health status. When people are informed, they can act accordingly. Regular training workshops conducted among health workers to update their knowledge, and the dissemination of health information among poor people living in remote areas significantly contributed to the positive impact on health as measured by its indicators. [Main text, paras. 61(iii)] project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring &amp; Evaluation: Indicators Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Policy &amp; Reform: Information dissemination/Public awareness 3. Effective outreach program and use of local human resources, such as employing local health workers and mobilizing village health volunteers, increase the probability of project sustainability in projects providing primary health care projects to rural poor living in remote areas. The Primary Health Care Project's outreach programs have helped empower women by providing practical skills and knowledge to address basic health issues. Trained health workers continue to share their new skills and knowledge with village health volunteers, to sustain health services provided to their communities. [Main text, paras. 43, 54, 61(iv)] project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Human resources management Sector Related Issues: Extension service Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development 4. Constant flow of financial, human, and technical resources are very important in sustaining the provision of and benefits from primary health care services. Follow-on projects help to ensure the flow of financial and technical health-care services to the pilot areas. This indicates the benefits of ADB focusing its operations and having a long-term involvement in a sector. However, the availability of funds will eventually end. Institutional reforms and appropriate budgetary allocation are needed to ensure that the project benefits are sustainable. Supervision, skills training, and skills upgrading need to be sustained to enhance the quality of services provided by health workers. The education of women is particularly important because of their role in the home (e.g., hygiene, nutrition, child care, and family planning). [Main text, para. 61(v)] project cycle stage: Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Sustainability Finance &amp; Financial Aspects: Financing Modality: Program Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Education Sector Related Issues: Health and sanitation management Policy &amp; Reform: Policy reforms/framework Methodologies/Approaches: Pilot project 5. The Project demonstrated the advantages of partnership, with other development agencies collaborating from project preparation throughout project implementation. Good working relationships were developed with the World Bank, United Nations agencies, and nongovernment organizations. Funding agencies using the same project coordination unit provided a model for aid harmonization, resulting in complementary financial and technical support that helped to sustain the Project. [Main text, para. 56, 61(vi)] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Capacity Development: Partnerships Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/primary-health-care-project-lao-peoples-democratic-republic-loan-1348-laosf
Country Assistance Program Evaluation for the Lao People's Democratic Republic (2006) | Lao PDR |  | 2006-04-30 | Complicated project/program design deterred achievement of development effectiveness. Inadequate project preparation in the agriculture and natural resources and water supply sectors led to implementation delays, cost overruns, and cancellation of components. In all program loans, proposed policy conditionalities were too complex and ambitious to implement. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Policy-based lending Modality: Program Project Design: Project design Project Management: Project administration Sector Related Issues: Rural development Continuity is key to achieving critical masses and development effectiveness. The success of the Country Programs in generating critical masses and achieving development effectiveness reflected a systematic and continued series of interventions, allowing succeeding projects to build on past achievements (e.g., in the energy and transport sectors). project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Crosscutting Issues/Themes: Sustainability Limited government absorptive capacity and ownership resulted in a shortage of counterpart funding and recurrent cost financing. ADB lent too much for the Government to effectively absorb. This was reflected in inadequate counterpart funding and recurrent cost financing. The former caused delays in project implementation, higher bid prices, and substandard work across sectors. The latter threatened project sustainability in some sectors (e.g., education and health). project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance &amp; Financial Aspects: Counterpart funds Finance &amp; Financial Aspects: Financing Capacity Development: Ownership Limited strategic partnerships among development partners resulted in piecemeal outcomes. Weak aid coordination during the country assistance program evaluation period resulted in a lack of strategic partnerships (e.g., cofinancing strategies, and program-based or sector-coordinated approaches) and in piecemeal outcomes. However, progress on aid coordination and harmonization has recently improved. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Weak government gommitment deterrs achievement of development effectiveness. Weak government commitment was also reflected in delayed compliance with policy reforms and limited follow-through on the issuance of implementation decrees. Both had negative effects on delivering the expected development results. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Managing for Development Results Capacity Development: Ownership Policy &amp; Reform: Policy reforms/framework Without overall sector focus and coherent strategy by sector, investments become diffused and fail to achieve development effectiveness. Without overall sector prioritization and a clear strategy for each sector, any investment could be justified as a priority. This led to scattered investments, particularly in the agriculture and natural resources sector. project cycle stage: Country Partnership Strategy Lesson Topics: | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-lao-peoples-democratic-republic-2006
Champasack Road Improvement Project in the Lao People's Democratic Republic (Loan 1369-LAO[SF]) | Lao PDR | Transport | 2005-11-30 | Geographic targeting is one way to develop synergies in ADB's operations and needs to be considered during the formulation of the country strategy and program and country strategy and program updates. project cycle stage: Concept, Country Partnership Strategy Lesson Topics: Impact evaluations at the sector and country level would yield an adequate understanding of the socioeconomic benefits of road projects. project cycle stage: Operation Lesson Topics: Monitoring &amp; Evaluation: Impact evaluation Monitoring &amp; Evaluation: Post-evaluation Sector Related Issues: Roading In this case, geographic targeting could have developed synergies and generated savings if a related project (viz., irrigation) had been initiated in parallel with the transportation project, at the formulation stage. This approach could have avoided the need for the irrigation project to dig up the roads after project completion. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Transport planning Methodologies/Approaches: Targeting Information related to the amount allocated for periodic maintenance (operation and maintenance) should be monitored during project administration and collated at the project completion stage to ensure that the funds have been used for the intended purpose. project cycle stage: Implementation, Completion Lesson Topics: Monitoring &amp; Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Project Management: Project administration Material testing should be conducted jointly in the presence of both the contractor and the consultant. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project supervision Requiring that Benefit Monitoring and Evluation be undertaken 2 years after project completion was a standard clause in loan agreements when the project was processed. There is a high risk that such covenants will not be complied with. Greater recognition needs to be given to the fact that Executing Agencies (EAs) do not wish to allocate their scarce funding for such studies, as their day-to-day operations do not require such data. While ADB placed priority on monitoring project impacts on poverty for every project, the EAs did not feel that this was the most appropriate way to spend their limited budget.At the institutional level, ADB now recognizes that, due to considerable costs and problems in establishing clear linkages between project inputs and impacts, monitoring of poverty effects at the project level will be done only on a sample basis. project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance &amp; Financial Aspects: Financing Loan Agreement: Covenants Monitoring &amp; Evaluation: Benefit monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Risks/Risk management The contractor did not perform to the required level. The materials used by the contractor were substandard, resulting in pavement failure that had to be rectified, causing delays in project completion and additional costs. While the contractor can be held accountable for such problems, the supervision consultant should be involved in a proactive manner to help detect such problems and plan remedial measures. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project management Project Management: Project supervision To achieve better subregional cooperation, an integrated approach is needed. In the case of the project, the full benefits of the improved road within Lao People's Democratic Republic (Lao PDR) will not materialize unless there is a proper linking road within Cambodia. A road project could have been initiated in Cambodia within the Greater Meckong Subregion (GMS) framework to link the project road with an improved road in Cambodia. The GMS Program is an ideal platform for such integrated planning of infrastructure in the region. However, such an integrated approach should consider each country's transport plan. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Transport planning Methodologies/Approaches: Holistic approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/champasack-road-improvement-project-lao-peoples-democratic-republic-loan-1369-laosf
Industrial Tree Plantation Project | Lao PDR | Agriculture, Natural Resources, and Rural Development | 2005-11-15 | ADB should have committed more resources to supervise a project designed to introduce a totally new concept in a country that lacked implementing agencies with sufficient capacity. It was critically important to improve the capacity of project staff about the socio-technical profile (STP), and environmental and gender issues at the early stage of project implementation. The poorly planned midproject expansion undermined the development of focused, core areas identified in the project preparation. The expansion also overextended implementing agencies' (APB, PPCU, and DAFO) staff. The distant locations of some of the new project sites also added to the challenge of marketing. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Gender Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Project supervision Capacity Development: Capacity building Policy & Reform: Information dissemination/Public awareness Capacity building is a gradual process that should be carefully sequenced and planned. Creating capable institutions mid-project is unrealistic. Project preparation was inadequate in assessing the institutional capacities of the executing and implementing agencies (DOF/PCU, PPCUs, DAFOs and APB). ADTAs provided significant training to APB, PCU, and PPCU staff, but these training initiatives fell short of building sufficient capacity. The Agriculture Promotion Bank (APB) was a relatively new institution with extremely limited capacity in commercial and agricultural banking. Industrial tree plantation was a new area for the Department of Forestry (EA). A crash course in plantation establishment provided by project and ADTA consultants did not result in an effective plantation extension system. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Sector Related Issues: Extension service Sector Related Issues: Rural development Provision of ADB Asian Development Fund (ADF) resources and public-sector subsidized loans to favored large private-sector enterprises raises questions about governance and validity. If the plantation sector is economically viable in Lao PDR, then private enterprises should be willing and able to borrow at market interest rates. As it stands, many of the large enterprises are not current with their debt payments on subloans - despite (or perhaps because of) the favorable loan conditions granted to them. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Targeted and subsidized credit led to abuse and inefficiency, setting back the country's rural credit sector and credit culture. The gross loss and delinquencies significantly damaged the Agriculture Promotion Bank's (APB's) portfolio. Farmers were led to believe that impossible gains were attainable. This left most planters heavily in debt, with little chance of paying off their loans. Less costly approaches that would have been less damaging to APB and to the rural financial sector could have been considered. One possible option: providing guidance and grants for inputs (seedlings and fertilizer) directly to participating small farmers in exchange for land preparation and a commitment to maintain the land. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Management: Operation and maintenance Sector Related Issues: Extension service Sector Related Issues: Rural development The project demonstrated the viability of establishing well-managed plantations and cultivating tree crops (mainly eucalyptus) across wide areas of the country. However, the government and ADB should have done more to foster and support existing private sector initiatives. Plantation crop production is a business that requires efficient management, scientific know-how (seedling selection, soil- and water-sufficiency assessment, pest control, etc.), significant capital, marketing savvy, and long-term investment prospects. Therefore, it does not easily lend itself to small- and medium-scale farmers looking to learn the business. But there appears to be some room in the industry for advanced small- and medium-scale farmers who link their activities to the activities of those market leaders. Such farmers should seek close integration (in areas such as management, capital, technical guidance, physical inputs, and marketing) with the larger private enterprises. A logical sequence is: (i) larger, corporate-run plantations are established; (ii) at the same time, the market for plantation trees is developed; and (iii) small- and medium-scale plantations are established and linked to the larger enterprises. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Industry and Trade Sector Related Issues: Private sector Sector Related Issues: Rural development The project gambled that a viable market could be created midproject and sustained. While such gambles are a natural part of private-sector entrepreneurship, they are simply too risky for major public sector investments. More work should have been done in the project-preparation stage to clarify the policy issues and simplify regulations on cutting, transporting, and marketing the final wood product. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Industry and Trade Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/industrial-tree-plantation-project
Secondary Towns Urban Development Project | Lao PDR | Multisector | 2005-10-14 | A more holistic approach should be taken in the design and implementation of the Community Awareness and Education Program (CAEP component), which was less successful. Implementation should be carried out by competent and dedicated field staff members and consultants who understand the local customs and culture. The holistic approach should establish a common goal shared by all parties involved. The CAEP should define the quality of life that the people strive for, list problems and issues, develop plans, list projects to achieve the outputs desired, take action to implement changes, monitor results, look for early warnings that predict errors, adjust actions at an early stage, and replan where necessary. The success of this type of a program begins with one common goal shared by all concerned. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Problem identification Project Design: Project design Project Management: Consultants Project Management: Project management Country Context: Cultural constraints Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Holistic approach Consultants should closely monitor the performance of contractors and advise the executing agency early on if corrective measures are needed to prevent construction delays. Consultants' work and performance should be monitored more closely by the executing agency and ADB to ensure the quality of output. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement It is essential to improve coordination between all parties concerned with the project in order to avoid delays in implementation. During the detailed design for the project, documents were sent to all departments and organizations affected by the proposed works for review and comment prior to bidding. Some reviews were not completed, resulting in the need to change the scope of work for drainage and road components during the execution of the work. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation Project design and implementation procedures should be carefully examined and determined during appraisal, taking into account government regulations for preparation of detailed designs, and involvement of stakeholders. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Methodologies/Approaches: Consultation/Participation The capacity of government personnel, local authorities, and project staff should be strengthened through adequate training prior to the implementation of the project to familiarize them with ADB's implementation procedures. project cycle stage: Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-towns-urban-development-project
Postsecondary Education Rationalization Project | Lao PDR | Education | 2004-03-15 | The project included advance actions for initial procurement with retroactive financing.This helped the Project Implementation Unit's (PIU's) initial activities. Advance action for consultant selection, however, wasavailable only up to the preparation of the long list of candidates. A provision for more concreteadvance action could have mitigated initial delays, considering the time required for selectingconsultants. Such a provision could include consultant selection up to receipt ofconsultant proposals prior to loan effectiveness. A project preparatory technical assistancecould help the government take advance action. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Procurement Project Management: Project management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/postsecondary-education-rationalization-project
Sixth Road Improvement Project | Lao PDR | Transport | 2003-03-14 | The prequalification exercise resulted in the unconditional prequalification of three companies. In hindsight it is clear that none of these companies had the capacity to undertake more than one contract. Ultimately this contributed significantly to the delay of the civil works implementation since one company was awarded all three road packages but could not complete the works on its own and had to hire plant and labor from other companies. The delays resulted in higher implementation costs, in particular the extended duration of the supervision consultants. More care should have been taken in the prequalification process. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Management: Consultants Project Management: Procurement Sector Related Issues: Roading While the delayed implementation of the project is partly attributable to the awarding of all road packages to the same contractor, it should have been expected that the privatization process would create difficulties because of the inexperience of the companies involved and their less than optimum resources. However, the works were ultimately completed to a relatively high standard. Since completion of the project, the newly privatized and commercialized companies have successfully tendered for works projects under international competitive bidding. It is considered that the timetable for the privatization of the state-owned enterprises was somewhat optimistic. While there were delays and additional costs, the privatization process has been successful and is ongoing with the mechanism in place. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Procurement Sector Related Issues: Roading Policy & Reform: Privatization Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/sixth-road-improvement-project
Theun-Hinboun Hydropower Project (Loan 1329-LAO[SF]) | Lao PDR | Energy | 2002-11-30 | A qualified and adequately staffed environmental and social monitoring unit should be in place prior to and during project implementation to monitor the impacts and take proactive mitigation actions in a timely manner. The responsible authority in the country should build capacity to fulfill its oversight function and ensure appropriate supervision of similar projects in the future. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring &amp; Evaluation: Monitoring and evaluation Project Management: Project supervision Capacity Development: Capacity building Given the importance of PPAs and their intrinsically complex nature from technical, commercial, and legal points of view, ADB should, if requested, provide assistance to its developing member countries in drafting and negotiating such PPAs. project cycle stage: Feasibility Lesson Topics: The successful financing, implementation, and operation of the project can serve as a model for such public-private partnerships in the power sector. The ingredients for success are (i) through technical and economic evaluation of a suitable hydropower site, (ii) choice of a group of developers that has the necessary financial and technical experience, (iii) negotiation of a purchasing power agreement (PPA) that is advantageous to all parties involved, and (iv) the willingness to learn from mistakes made and take responsibility to mitigate them. project cycle stage: Feasibility, Appraisal, Implementation, Operation Lesson Topics: Finance &amp; Financial Aspects: Financing Sector Related Issues: Energy planning/management Sector Related Issues: Public-private partnership Transbasin hydropower projects, even if quasi-run-of-river in design and operation, can have significant environmental and social impacts. Their implementation should not proceed without gathering adequate baseline data and designing a comprehensive mitigation program. Sufficient time and resources should be allocated for this prior to implementation. Any postapproval mitigation measures need to be supervised closely for timely implementation by parties responsible. project cycle stage: Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Finance &amp; Financial Aspects: Financing Monitoring &amp; Evaluation: Baseline data Monitoring &amp; Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project supervision Sector Related Issues: Energy planning/management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/theun-hinboun-hydropower-project-loan-1329-lao-sf
Vientiane Integrated Urban Development Project | Lao PDR |  | 2002-07-15 | Foreign and local civil works contractors should be carefully selected through a prequalification process to disqualify those who are incompetent. Local competitive bidding should be considered to choose local contractors, which are considered more economical and efficient for minor civil works. project cycle stage: Appraisal Implementation Lesson Topics: Lack of detailed discussions about technology, design standards and communityparticipation partly resulted in the need to change the scope of work for the roadand sanitation components. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Health and sanitation management Sector Related Issues: Roading Methodologies/Approaches: Community approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/vientiane-integrated-urban-development-project
Nam Ngum-Luang Prabang Power Transmission Project (Loans 928/1308-LAO[SF]) | Lao PDR | Agriculture, Natural Resources, and Rural Development, Energy | 2002-06-30 | A basic premise at formulation - that project design called for conventional engineering systems and methods of construction - proved faulty, and impaired the efficacy of implementation with regard to scheduling and the availability of funding. Non-uniform design considerations, including provision for variable tower heights, tower spans, and tower support structures, are lessons of experience now being applied to transmission projects for adjoining provinces with similar mountainous topography. project cycle stage: Design, Feasibility Lesson Topics: Finance &amp; Financial Aspects: Financing Project Design: Project design Sector Related Issues: Energy planning/management Feasibility estimates that are dependent on detailed engineering after loan approval should include a wider contingency margin to avoid the possible need for supplementary financing and delays. project cycle stage: Feasibility Lesson Topics: Finance &amp; Financial Aspects: Financial analysis Finance &amp; Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Sector Related Issues: Energy planning/management More rigorous checks are needed at commissioning to avoid the possibility of faulty equipment leading to the impairment of technical operating performance. project cycle stage: Implementation, Operation Lesson Topics: Monitoring &amp; Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Project Management: Project supervision Sector Related Issues: Energy planning/management The introduction of monthly adjustments is a suitable mechanism for increasing tariffs to acceptable and viable levels without causing undue consumer resistance which can arise with one-off major adjustments. project cycle stage: Feasibility Lesson Topics: Finance &amp; Financial Aspects: Financial management Project Design: Project design Sector Related Issues: Energy planning/management Transmission projects that involve the carriage of electricity across populated rural areas should also plan to provide for the distribution of electricity to such areas so as to minimize objections and enhance the socioeconomic impact. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Energy planning/management Sector Related Issues: Rural development | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/nam-ngum-luang-prabang-power-transmission-project-loans-928-1308-lao-sf
Primary Health Care Project | Lao PDR | Health | 2002-06-14 | Primary health care (PHC) services should be made affordable and community-based,particularly outreach services. The cost-sharing system established under the project has generated income for purchases of essential drugs. Payment for drugs has not been reported as an impediment to care in any of the project facilities. The funds received are essential for maintaining the centers and for assuring adequate supplies of drugs. However, health facilities cannot operate on the revolving drug fund alone, and the management committee should explore options for more cost sharing and community financing. project cycle stage: Feasibility Lesson Topics: Finance &amp; Financial Aspects: Financing Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Extension service Sector Related Issues: Health and sanitation management Methodologies/Approaches: Community approach Since the Lao PDR health care delivery system is in its early stage of development, a national policy on development of health facilities is essential to achieve optimal coverage of health services. Its implementation will require mapping and a facility survey based on population norms approved by the Ministry of Public Health (MOPH). Operational policies should be developed for the use of district hospital buildings and health centers. The buildings should be simple in terms of materials and construction and they should include adequate water supply, power supply, cleanliness, and landscaping. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management Policy &amp; Reform: Policy reforms/framework The methods for training ofhealth workers in the Lao PDR are simple and participatory, using modules and verbalpresentation of technical materials followed by exercises, role-plays, and actual practice in asupervised setting. The regular retraining received by health workers has helped them tomaintain an acceptable quality of care and performance under the integrated supervision anddecentralized management at the provincial and district levels. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Health and sanitation management Methodologies/Approaches: Participatory approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/primary-health-care-project
Nam Leuk Hydropower Project | Lao PDR | Energy | 2002-02-15 | As a result of underbidding, there might be ï¿½unfair competitionï¿½ between civil workscontractors from different countries as one contractor might budget the treatment of laborers inaccordance with his or her ï¿½own country styleï¿½ and the other in accordance with the terms ofreference. project cycle stage: Appraisal Lesson Topics: In spite of the fact that ADB's existing procurement guidelines provide clear and adequate provisions for (i) relevant experience and past performance in prequalification of bidders, (ii) performance in past projects for civil work contractors, and (iii) particularly low bidding prices of successful bidders, the very same contractor, in spite of the initial poor performance on the project, was still prequalified for other ADB-financed projects and contracts awarded, indicating that more diligence in prequalifying and award of contracts is required. ADB should ensure that its prequalification criteria are fully adhered to and actively work with the executing agency in its prequalification process by assessing the contractors' resource estimates against specificationrequirements. Also, performance bonds for civil works should be expanded to includeperformance criteria for environmental mitigation works. It must be noted that even with very poor contractors, projects can also be implemented at a financial benefit to the owner, provided that project management knows how to handle such a contractor in a proactive manner through innovative actions. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial benefits Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/nam-leuk-hydropower-project
Second Financial Sector Program | Lao PDR | Finance | 2001-12-14 | The appraisal and design of technical assistance (TA) 2642, which was done during loan appraisal, were deficient. The TA assumed a banking system and state-owned commercial bank (SCB) sector more developed than was in fact the case. The operations of the SCBs have been directed from the Bank of Lao PDR (BOL), including setting of lending and deposit targets and interest rates. The SCBs had little understanding of risk management, as the conditions under which they operated did not require them to systematically deal with risks. Technical assistance (TA) 2642 was tasked to explore and arrange joint-venture partnerships and management contracts. Considering the political economy and economic climate at that time, such arrangements were premature. Even now there is political reluctance to increase the autonomy of the SCBs. This will have to be addressed in the bank restructuring plans of the SCBs and future financial sector development program of the government. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Policy & Reform: Public sector reform The government did not give much thought to the steps to be taken and the coordination efforts required by the program before it sought ADB financial support. Neither the government nor ADB devoted enough time or effort to building government ownership of the reforms. ADB did not adequately assess the preparedness of the government and the executing agency to own the reforms. ADB's evaluation of the implementation capacity of the executing agencywas too optimistic. ADB underestimated the bureaucratic and cumbersome legislative process. Continuity and perseverance by ADB in monitoring and supporting program implementation are essential. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Ownership Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation The Second Financial Sector Program loan (FSPLII) underestimated the scope of work involved in changing the fundamental behavior of an established system. In hindsight, the design of the program agenda was optimistic and theimplementation period originally envisaged for the program was unrealistic. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Modality: Program The state-owned commercial banks (SCBs) should not be recapitalized unless they have a high degree of independence to operate commercially. Recapitalization should be based on improvement in performance as measured by performance indicators. This should be documented in a restructuring plan. The Second Financial Sector Program loan (FSPLII) recognized at appraisal, but did not support by tranche release conditionalities, the need for measures to increase the autonomy of the state-owned commercial banks (SCBs), i.e., joint ventures, management contracts, and privatization. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Program Monitoring & Evaluation: Indicators Project Design: Appraisal Policy & Reform: Privatization Policy & Reform: Public sector reform Waivers of tranche conditions should be given only sparingly, and only for strong valid reasons. Waivers were given in First Financial Sector Program loan (FSPLI) to policy actions with little or no progress because of delay in implementation of TAs supporting the tranche conditions and technicalities difficult for the government to understand and resolve. Owing to this precedent, the government did not press on with some Second Financial Sector Program loan (FSPLII) reform measures in the face of delays and complexities. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Program Modality: Technical Assistance Policy & Reform: Policy reforms/framework Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/second-financial-sector-program-0
Private Sector Education in the Lao People's Democratic Republic | Lao PDR |  | 1999-12-31 | Relatively simple equipment in the right hands can do a great deal. The interest in computerization was a significant factor in the success of the TAs and remains important to the sustainability of the executing agency's work. But key skills and areas of knowledge should always be backed up within an agency. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Technology/Technology transfer The effectiveness of a TA can be enhanced by detailed planning and careful recruitment of consultants. Both TAs used a phased approach in which the consultants provided several months of input, left certain things to be done by counterpart staff, and then returned for follow through. This approach can maximize the value of limited consultant time. Furthermore, having consultants with high cultural awareness and the correct expertise is a significant factor in their ability to meet TA objectives. project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Country Context: Cultural constraints Methodologies/Approaches: Process approach | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/private-sector-education-lao-peoples-democratic-republic
Selected Financial Sector TAs to the Lao People's Democratic Republic | Lao PDR | Finance | 1999-12-31 | ADB experience points to the critical importance of (i) correctly assessing government capability and absorptive capacity, and the extent of political and administrative support for change, which are only really measured through monitorable indicators or preconditions; (ii) comprehensive diagnostic analysis of both the EA and the recipient institutions, including in-depth analysis of decision-making processes and the interrelationship of the EA and the beneficiary institutions with other areas of the government; and (iii) understanding the historical role of the financial system in transitional economies and the significance of ideology. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Indicators Project Management: Executing/Implementing agencies Capacity Development: Institutional analysis Policy & Reform: Reform Policy & Reform: Transition economies Country experience demonstrates the importance of TA logistics, particularly timely and accurate translation and interpretation, and availability of full-time counterpart assistance. TA effectiveness is compromised by (i) assuming counterpart without analysis of the EAs ability to perform, and (ii) running multiple TAs or multi-componented TA where the EA or recipient agencies lack qualified counterpart staff. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Human resources management TA experience warns against attributing functional shortcomings in a sector or organization to lack of trained staff and systems. The TAs demonstrate the weakness of applying technical fixes before (i) addressing key institutional and policy reforms necessary to make improvement in technical competencies sustainable; and (ii) implementing adequate accounting standards, independent audits, and autonomy for the state commercial banks (SCBs). Training TAs would be more effective if TA design (i) included needs assessment and follow-up for skills use; (ii) focused the training programs as means to effect change in institutions, rather than just as an output; and (iii) included a plan for monitoring the impact that training has on the institution. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management Capacity Development: Institutional analysis Policy & Reform: Policy reforms/framework The TAs highlight the importance of (i) appropriate sequencing; (ii) staff continuity at ADB and EAs; (iii) preceding credit inputs with proper frameworks for credit analysis and administration, debt recovery, and bank supervision; (iv) closer coordination among credit providers in the banking sector so as not to undermine common objectives; and (v) providing the time and resources to gain acceptance for and implementation of those outputs, then monitoring for their impact. project cycle stage: Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/selected-financial-sector-tas-lao-peoples-democratic-republic
Institutional Development and Strengthening of the Ministry of Agriculture and Forestry (Phases I and II) in the Lao People's Democratic Republic | Lao PDR | Multisector | 1997-12-31 | A participatory approach with committed counterpart staff during technical assistance (TA) implementation was expected by ADB. But the number of staff with adequate basic qualifications and experience in a transition economy is limited and is subject to other demands on their time. Defining desired TA outputs, clarifying staffing requirements and indicators of performance (as encapsulated in a logical framework), and facilitating technology transfer with appropriate working relationships between consultants and local staff would have helped in ensuring greater cooperation from the executing agency and ownership of the TA outputs. Allowing counterpart staff to perform training activities in a transition economy with language difficulties and limited resources can serve to augment and facilitate the quick transfer of skills to government institutions. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Transition economies For optimal training benefits, training needs assessments are important to anticipate skill levels and direct development of training courses. Spaced repetition of workshops, phasing of workshops to ensure cross-fertilization of ideas, and routine interaction with trainees after workshops are important to sustaining the training benefits. The training of trainers contributed to the success of the TAs, but greater benefits would have been reaped with a wider circle of trainers and interaction with local staff. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/institutional-development-and-strengthening-ministry-agriculture-and-forestry-phases-i-and
Third Road Improvement Project (Loan 866-LAO[SF]) | Lao PDR | Transport | 1997-09-30 | Funding commitments towards road maintenance need to be strengthened and practices that result in funds being reallocated for construction improvements removed. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Operation and maintenance Sector Related Issues: Roading Project design needs to specify the level of road improvement to be achieved in terms of international benchmark standards. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Roading There is a need to ensure that civil works are monitored against the project's design specifications, and where deviations apply that these are documented and approved under the authority of ADB and the executing agency. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project reporting Sector Related Issues: Roading | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/third-road-improvement-project-loan-866-laosf
Strengthening the Industrial Waste Management Capability of the Ministry of Industry and Handicrafts in the Lao People's Democratic Republic | Lao PDR | Industry and Trade | 1996-12-31 | From the outset, a strong sense of ownership on the part of the recipient agency should be secured for both the TA and subsequent activities and action plans, along with establishment of a close and sustained partnership with ADB. This was successfully achieved, resulting in good performance. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Ownership Capacity Development: Partnerships In a nascent sector of a lesser developed country, ADB should first assist in developing an overall conceptual framework for the sector and the proposed TA through vigorous diagnostic assessment. In such a sector and country, a TA prerequisite is to secure a minimum staff core at master level knowledge in integrated waste management. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Modality: Technical Assistance Capacity Development: Capacity assessment Capacity Development: Human resources management Results expected to be achieved should be proportionate to available resources, whether financial, time, or human. There should preferably be at least one long-term consultant to oversee a sustained pace of progress and identify further assistance needs after an institution building TA is completed. project cycle stage: Appraisal, Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Consultants Capacity Development: Capacity building | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/strengthening-industrial-waste-management-capability-ministry-industry-and-handicrafts-lao
Road Sector Management in Lao People's Democratic Republic, Papua New Guinea, and Philippines | Lao PDR, Papua New Guinea, Philippines | Transport | 2002-12-31 | Assessing risks that are known to be associated with any pavement management system like the road assessment management system should be stressed in the terms of reference of the consultants; otherwise, such risks may be ignored, affecting the long-term sustainability of the system. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Consultants Project Management: Risks/Risk management Sector Related Issues: Roading For politically sensitive recommendations, a technical assistance attached to a loan, possibly with a covenanted time-bound action plan, may be a more effective mechanism than a stand-alone technical assistance as ADB and the other stakeholders will remain engaged through the duration of the loan. It has been an advantage that progress in implementing the politically sensitive recommendations related to privatization in the Lao PDR and disbanding Bureau of Equipment in the Philippines could be monitored by frequent loan review missions over a long period. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Policy & Reform: Privatization In the initial stages of transition, when economies have pervasive state control over road sector institutions, and a banking sector that is not motivated to deal with the private sector, privatization may take the form of management buy-outs and may precede attempts to reform the banking sector. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Private sector Sector Related Issues: Roading Policy & Reform: Privatization Policy & Reform: Reform Policy & Reform: Transition economies Long-term involvement with the stakeholders should be required, with support and follow-up over a period of 5 or more years, to maintain momentum and stakeholder interest. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Where significant retrenchments are anticipated, technical assistance projects (TAs) need to consider recommendations for transitional arrangements, including change management and counseling. These are necessary to minimize the social costs of downsizing. Furthermore, in TAs that substantially affect components of the executing agencies, the reporting channel of the consultants needs careful consideration. project cycle stage: Completion Lesson Topics: Crosscutting Issues/Themes: Social protection Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Policy & Reform: Reform | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/road-sector-management-lao-peoples-democratic-republic-papua-new-guinea-and-philippines
Ban Sok-Pleiku Power Transmission Project in the Greater Mekong Subregion: Technical Assistance Completion Report | Lao PDR, Viet Nam | Energy | 2015-03-01 | In the development of transmission lines, safeguard requirements for associated facilities should be carefully evaluated and assessed from the TA (technical assistance) formulation to realize the financing of such projects. In particular, for the case where ADB is not financing an associated facility, ensuring compliance with ADB safeguard requirements of such an associated facility by the private power developer would not be easy as ADB has no leverage to ensure compliance. Project cycle stage: Feasibility, Appraisal | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/ban-sok-pleiku-power-transmission-project-gms-tcr
Supporting the Tenth Malaysia Plan, 2011-2015 - Advisory to the Export-Import Bank of Malaysia Berhad: Technical Assistance Completion Report | Malaysia |  | 2015-06-01 | The major lesson is the need to facilitate regular dialogue with development financial institutions in Malaysia, on ADB's due diligence and risk pricing procedures re. NSO transactions. The TA (technical assistance) was the first reimbursable TA negotiated by ADB/SERC (Southeast Asia Department-Regional Cooperation and Operations Coordination Division)/SEPF (Southeast Asia Department-Public Management, Financial Sector, and Trade Division), with a government-owned financial institution in Malaysia. The implementation of the TA was initiated by SEPF in third quarter 2012. By mid-2013, the Government was preparing for general elections; the focus of major government-owned financial institutions was increasingly being drawn into the political process. In this context, ADB provided a capacity building framework for the technical upgrading of risk management procedures in a financial institution, and indicated the willingness to re-engage with either EXIM (Export-Import) Bank Malaysia, or another state-owned financial institution, at the appropriate time. Project cycle stage: Implementation | Technical Assistance Completion Report |  | http://wcm.adb.org/projects/documents/supporting-10th-malaysia-plan-2011-2015-advisory-export-import-bank-malaysia-berhad-tcr
Technical Education Project | Malaysia |  | 2007-06-27 | 1. Estimates of labor supply and demand should be treated as indicators of trends rather than as concrete targets. The Report and Recommendation of the President (RRP) made some detailed assumptions about the number of professionals, assistant engineers and technicians that would be required by the end of the project. Given the potential volatility of labor markets - as seen in the late 1990s that had a major influence on project implementation - it would have been better if the project had used available labor market data to produce indicators and from that propose trends, rather than making detailed predictions that were no longer valid by project's end. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Indicators Methodologies/Approaches: Targeting 2. Original estimates for project enrollments should be reviewed and adjusted at the time of the midterm review, so as to reflect actual rather than forecasted socioeconomic conditions. At the time of the project's midterm review, when the full effects of the delays in construction and implementation became clear, enrollment predictions should have been adjusted to reflect the existing situation. project cycle stage: Design Lesson Topics: Project Design: Appraisal Project Design: Project design 3. Risks and assumptions with regards to project implementation should be clearly outlined. Although the need for institutionalizing a benefit monitoring and evaluation (BME) system, tracer studies and analysis of efficiencies has been raised continuously by ADB since the 1980s, Technical Education Project's design did not raise the successful implementation of BME as a major assumption, given previous experience. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project Management: Management information system | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/technical-education-project
Technical and Vocation Education Project | Malaysia | Education | 2004-08-13 | A project's mid-term review should focus not only on assessing progress ofimplementation, but should also recognize shifts in policy and trends, and reviewappraisal targets and project components accordingly. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Methodologies/Approaches: Targeting Lessons and experiences from career guidance, industrial liaison, andplacement units and tracer studies should be incorporated into the actionplans of the Technical Education Department (TED). A system that regularly incorporates these data into TEDpolicies and plans would facilitate better planning and resource allocation. project cycle stage: Implementation, Operation Lesson Topics: Project Management: Management information system Capacity Development: Capacity development Sector Related Issues: Education The benefits of logical frameworks and indicators should be recognized. Theproject was designed before the mandatory introduction of logical framework inADB. The absence of performance indicators that are provided in a logicalframework seriously hampered the effective monitoring of the project and itsmanagement because targets for some subcomponents were not fully quantifiedor qualified. That made it difficult to measure progress, or identify areas wheredifficulties might arise. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/technical-and-vocation-education-project
National Coastal Erosion Control Sector Project | Malaysia | Agriculture, Natural Resources, and Rural Development | 2002-10-15 | ADB-funded projects that dovetail well with existing government policy initiatives (in this case, the project's relationship with the National Coastal Erosion Control Plan [NCECP]) have a greater chance of successful implementation and sustainability. Project sustainability is enhanced where the agency, which will ultimately be responsible for project operation and maintenance, is closely involved during the project preparation and implementation phases. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project administration Project Management: Project management Policy & Reform: Policy reforms/framework Coastal protection interventions involving regular, high levels of re-investment, which indicate a negative economic internal rate of return (EIRR), should be carefully scrutinized to assess the intangible benefits and their overall economic efficiency in terms of least cost options. The selection criteria for the inclusion or substitution of subprojects should have been more comprehensive, and included not only technical and social considerations, but also more formal analyses of the financial and economic aspects (such as EIRR), and environmental impacts. ADB should also have had a greater role in the approval of selection or substitution of subprojects. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Project evaluation Project Design: Project design Project Design: Subprojects Coastal protection works that give immediate relief to large areas of flood proneagricultural land are frequently more efficient than erosion control works toprotect land (even valuable land) where the loss of land and property is moregradual. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Sector Related Issues: Water resource management Sector loans, which provide considerable flexibility for final subproject selection, are appropriate where the implementing agency's capability is high. project cycle stage: Appraisal Lesson Topics: Modality: Lending modality Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment To ensure ongoing benefits from TAs for institutional strengthening, it isimportant to aim to retain trained and experienced staff in the target institutions,especially in specialist technical fields (such as coastal engineers under thisproject). project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/national-coastal-erosion-control-sector-project
Third Health (Sector) Project (Loan 980-MAL) | Malaysia | Health | 2002-06-30 | ADB s flexibility regarding ICB requiring it for civil works contracts of $7 million or more proved beneficial in the context of the capacities in the subject country. project cycle stage: Appraisal Lesson Topics: Project Management: Procurement Capacity Development: Capacity assessment Human resource planning in the context of staff shortages and competition with the private sector is an important component of any program to expand public health care. project cycle stage: Feasibility Lesson Topics: Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Policy & Reform: Public sector reform Master planning for upgrading a range of old hospitals can be a model of some interest to other countries. Given the scarcity of the needed multidisciplinary expertise in consulting firms, much attention needs to be paid to the selection and supervision of consultants. project cycle stage: Feasibility Lesson Topics: Project Management: Consultants Project Management: Procurement Sector Related Issues: Health and sanitation management Methodologies/Approaches: Holistic approach TAs dealing with complex policy issues such as those in the health sector should be judged not only in the short term, but also in the long term, as outputs may also contribute to high-level discussions on the future of health care. project cycle stage: Operation Lesson Topics: Modality: Technical Assistance Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework The presence of an especially assigned project implementation unit (PIU) is crucial for the success of a large and complex project. The PIU s retention by the executing agency after project completion enabled follow-up as well as use of the built-up expertise for the management of other projects. project cycle stage: Design, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/third-health-sector-project-loan-980-mal
Rehabilitation and Upgrading of Water Supply Systems Sector Project | Malaysia | Water and Other Urban Infrastructure and Services | 2001-12-14 | Decisions concerning corporatization and privatization ofpublic utilities are complex, encompassing a range of technical, financial, socioeconomic, andpolitical issues. The infrastructure investments under this project do not require corporatizationor privatization to be successful. Moreover, privatization was not initially identified as a projectoutput. While the need to finance large investments may underlie a decision to privatize,corporatization and/or privatization are undertaken for a variety of other reasons, as appears tobe the case in Malaysia. Under these circumstances, efforts to promote corporatization and/orprivatization within the scope of an infrastructure loan project might be expected to meet withlimited success. In line with this, covenants relating to commercial accounting andorganizational restructuring could have been relaxed or dropped. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Lending modality Project Design: Project design Sector Related Issues: Energy planning/management Sector Related Issues: Health and sanitation management Policy & Reform: Privatization Policy & Reform: Public sector reform The anticipated nonrevenue water (NRW) reduction to 27 percent by project completionwas too ambitious given the small scale of the project. Effective and sustained reduction ofNRW needs a comprehensive and detailed action plan with monitoring milestones. An NRWaction plan should include a substantial commitment of financial and human resources, carefulplanning and delineation of achievable targets, and periodic program monitoring and evaluation.In addition, information exchange among State Water Authorities (SWAs) would help solve common problems associatedwith NRW and would reinforce NRW control efforts. Most SWAs have developed or aredeveloping NRW control programs but implementation has been hampered by financialconstraints. In light of this experience, a key focus of loan projects for NRW control should bethe establishment of ongoing and sustainable NRW programs. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Targeting The financial risks associated with regulated public utilities are closely tied to the regulatory policies and practices of thegovernment. In the current case, tariff policies are the most significant source of jeopardy forfinancial sustainability. It is important to anticipate this source of risk and to address it forcefullyduring the implementation of loan projects for public utilities. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Energy planning/management Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform When a large number of subprojects are involved in aproject and each subproject requires a number of activities in sequence, i.e., design,procurement, and construction, the effect of compound delays should be properly andconservatively assessed and reflected in the appraisal implementation schedule. For a projectconsisting of a large number of geographically dispersed subprojects, strong central projectcoordination at the state rather than the central level is essential for smooth implementation anddissemination of useful information to participating water districts. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project management Country Context: Decentralization Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness When the project was appraised, itwas not standard practice to prepare a project performance monitoring and evaluation systemincluding risk analysis. Project experience highlights the importance ofanalyzing risks, including the detailed action plan for nonrevenue water (NRW) reduction. For purposes of evaluation, project targets should be logically linked to project activities and methods to monitorthe achievement of these targets should be based on indicators that can be reliably measuredat an appropriate scale. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Management: Risks/Risk management Sector Related Issues: Health and sanitation management Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rehabilitation-and-upgrading-water-supply-systems-sector-project
Health Services Development (Sector) Project (Loan 815-MAL) | Malaysia | Health | 1997-04-30 | Institutional development needs to be based on an institutional analysis and be designed in such a way that desirable institutional changes are implemented immediately. For projects in the health sector, a detailed analysis must be undertaken to identify all the major institutional constraints that inhibit the quality of health services. The decision-making processes, work and information flows, procedures, and regulations of the hospitals and health centers concerned must also be reviewed to identify the internal inefficiency problems that affect the delivery of health services. The effective remedial measures can then be incorporated in the project design to redress the institutional constraints and problems identified. The provision of consultant services and limited training of a few individuals are not sufficient to overcome institutional weaknesses. Often, efficiency gains can be achieved by changing processes rather than upgrading physical health facilities. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Consultants Capacity Development: Capacity building Capacity Development: Institutional analysis Sector Related Issues: Health and sanitation management Investment in constructing or rehabilitating physical health infrastructure need to take into account the affordability of incremental recurrent costs and staffing requirements. It is important to realistically project the anticipated operational and maintenance and staffing requirements, and determine how these requirements will be met. In this respect, there is a need to review the planning and budgeting processes of the government in allocating public resources to the health sector. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial analysis Project Management: Operation and maintenance Capacity Development: Human resources management Sector Related Issues: Health and sanitation management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/health-services-development-sector-malaysia
Urban Transport Planning Project in Malaysia | Malaysia | Transport | 1996-12-31 | Future TAs should put more emphasis, as well as allocate more resources, to the training of trainers to ensure that some continuity in skills development is established. The risk of departures of trained staff, particularly in developing member countries with labor shortages, is significant and a system to replace departing staff needs to be put in place. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Risks/Risk management Capacity Development: Capacity building Capacity Development: Human resources management The design of the TA should require that the terms of reference include provisions for the consultant to assess the budgetary implications of the proposed urban transport plans. If such plans are unrealistic in terms of financing requirements, then 'second best' plans may need to be formulated. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Consultants Sector Related Issues: Transport planning Sector Related Issues: Urban sector/development | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/urban-transport-planning-project-malaysia
Kedah Water Supply Project (Loan 652-MAL) | Malaysia | Water and Other Urban Infrastructure and Services | 1996-06-30 | The main concerns about implementation of the project were the difficulties faced by the executing agency in complying with the loan covenants regarding the introduction of a commercial accounting system, full cost recovery through tariff adjustments, significant reduction of NRW, and establishment of a BME system. Apparently, not much consideration was given as to whether they were achievable or appropriate within the context of the project. In addition, no assistance was provided to the executing agency in complying with these covenants. Thus, covenants in the Loan Agreement should be based on a detailed consideration of whether such covenants are appropriate and feasible, or whether their compliance could be achieved better through other means such as policy dialogue or technical assistance. ADB should be careful about imposing loan conditions in an environment in which they are not feasible, or in which they are impractical, especially for a project in which resources, assistance, or guidance are not included in the design. project cycle stage: Appraisal Lesson Topics: The project demonstrated that the least-cost approach to water supply project planning is an effective method to achieve an efficient technical design to produce and deliver goods (i.e., water) to the consumers. It is now commonly accepted that in a fast developing country, water is increasingly viewed as an economic good and hence it is necessary to assess the economic efficiency of the water supply system. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Management information system Capacity Development: Capacity building Sector Related Issues: Water resource management To achieve a significant reduction in the NRW, a detailed program to achieve realistic targets must be outlined. Also, in the future, projects that double production capacity, and install new service reservoirs to improve water pressures, should include measures to prevent breakages and losses in the older parts of the system that may be caused by increased water pressures. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Water resource management Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/kedah-water-supply-project-loan-652-mal
Second Trengganu Tenggah Development Project (Loan 583-MAL) | Malaysia | Agriculture, Natural Resources, and Rural Development | 1996-01-31 | Planning is a continuous process. While a master plan can provide overall guidelines, the assumptions and details need to be continually reassessed. This requires a capability within the executing agency for assessment and long-term planning. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building The development of towns does enable a higher level and range of services to be provided in settlement areas compared with an estate type settlement pattern, and can encourage youth to remain in rural areas. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Rural development Sector Related Issues: Urban sector/development The environmental problems such as soil erosion and impact on wildlife could have been managed better and minimized if an environmental impact assessment had been carried out during the design stage and the mitigation of impact properly designed and implemented. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Project Design: Project design | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-trengganu-tenggah-development-project-loan-583-mal
Technical and Vocational Education Projects in Malaysia, Pakistan, Papua New Guinea and Sri Lanka | Malaysia, Pakistan, Papua New Guinea, Sri Lanka | Education | 1999-12-31 | One-Shot' projects do not work: a long-term focus is a must. Given the long program cycle needed for sustained development of the subsector, a series of overlapping projects with consistent core objectives, aiming over a longer period (a decade or more), is needed to make an impact on key subsector indicators while strengthening government capacity to manage the subsector. With a series of projects, the perennial problem of inadequate funding after project completion could then be partly eased through the projects' provision of incremental recurrent cost allocations. Based on experience, loan covenants requiring the DMC to provide adequate funding after project completion were not enough to ensure sustainability. This implies that once an aid donor decides to assist the technical education and vocational training (TEVT) subsector, it must be prepared to provide that assistance on a long-term basis. ADB could engage in more substantive policy dialogue with governments and develop a framework for sector development to be implemented over a decade or more supported by continuing financial inputs. Taking a holistic approach at the beginning of the first intervention and making a long-term commitment to support a complete program cycle would be in keeping with ADB's character as a development institution. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Cluster operations Monitoring & Evaluation: Impact evaluation Project Design: Project design Capacity Development: Capacity building Capacity Development: Ownership Sector Related Issues: Education Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Holistic approach Methodologies/Approaches: Program Approach A technical education and vocational training (TEVT) system without industry linkage is untenable. Strong linkages with industry provide access to valuable inputs. These include not only opportunities for industry exposure of students and teachers alike, but also the built-in feedback mechanism on the type, level, and quality of personnel needed. These are critical inputs in deciding the menu of course offerings and corresponding curriculum content which could minimize the mismatch between supply and demand. Even more important, linkages with industry gains the inputs of industry executives/managers which could have a significant influence on the corporate culture of technical and vocational schools and the way things are done, as clearly demonstrated in the case of few project schools with active industry participation. Project concepts should incorporate mechanisms to obtain commitment from industries and to engage them as major stakeholders in the development of TEVT. project cycle stage: Concept Lesson Topics: Project Design: Problem identification Project Design: Project design Capacity Development: Ownership Sector Related Issues: Education Sector Related Issues: Industry and Trade Leadership can spell the difference in project performance. In spite of the numerous constraints faced by the project institutions, there are always one or two in each country that stand out above the rest because of leadership. Interviews with some of these exemplary leaders reveal that the following characteristics, among others, are critically important: a vision of what the leader wants the institution to be; the willingness to take risks to do what ought to be done even if it does not strictly follow the bureaucratic process; an attitude of not depending only on the government budget; personal courage to stand up to extreme political pressure; ability to mobilize the support of the community (especially the parents and community leaders) to rally behind a cause; ease in dealing with industry people and firm belief in industry participation; creativity and initiative; and, above all, personal integrity. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Risks/Risk management Capacity Development: Capacity development Sector Related Issues: Industry and Trade Methodologies/Approaches: Community approach | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/technical-and-vocational-education-projects-malaysia-pakistan-papua-new-guinea-and-sri
Developing the Revenue Administration Management Information System: Technical Assistance Completion Report | Maldives | Public sector management | 2015-07-01 | The success hinged on (i) the political independence and reform-minded leadership of MIRA (Maldives Inland Revenue Authority); (ii) conduct of public awareness campaigns, which helped build the public trust for MIRA; and (iii) enhancement of human resources and institutional capacity of MIRA, which produced successful results in taxpayer registration, compliance, enforcement and tax collection. Major lessons include the following: Political considerations have to be factored in while determining the pace of tax reforms. The DMF (design and monitoring framework) should avoid indicators that are dependent on legislation by the Parliament. The TA (technical assistance) activities must be carefully assessed to minimize delays and spending beyond initial budget. Effective coordination with other TAs needs to be ensured to avoid duplication of consultants' inputs. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/mld-developing-the-revenue-administration-mgt-information-system-tcr
Institutional Strengthening for Economic Management: Technical Assistance Completion Report | Maldives | Public sector management | 2015-06-01 | A consensus on all the implementation arrangements (such as formulation of components) should be reached between the EA (executing agency) and ADB before the TA (technical assistance) is approved. This would minimize delays in the TA completion, smoothen project implementation, and maximize effective disbursement of TA funds. Furthermore, when a TA is part of a wider reform program anchored on a policy framework, there are greater synergies between the TA and program loan as well as greater ownership and commitment to TA work and generally greater impact. Project cycle stage: Feasibility, Implementation, Operation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/institutional-strengthening-economic-management-tcr
Private Sector Development Project | Maldives | Industry and trade | 2014-08-01 | Project design. The project was originally designed primarily to reduce obstacles to the development of micro, small, and medium-sized enterprises (MSMEs) through complementary initiatives. However, at the request of the government, a public-private partnership (PPP) output that was somewhat unrelated to MSMEs was also included. Although PPPs are an important aspect of private sector development, and MSMEs may participate in PPP projects, the activities in support of PPPs did not add much value to the overall project. The PPP development initiative could likely have been better executed through a separate PPP-focused project. Furthermore, a simpler and perhaps less ambitious project that had fewer outputs, involved fewer participants, and required less expert knowledge (particularly related to PPPs) might possibly have been completed on schedule. Project appraisal. Better cooperation between ADB and the executing agency in the preparation of the design and monitoring framework, as well as a more detailed assessment of appropriate project impact, outcome, and output performance indicators, could have improved performance monitoring, project evaluation, and possibly the project's ratings. In addition, a more detailed analysis of imprest account ceilings could have limited delays in project implementation. The imprest account ceiling for the line of credit facility had to be raised, with some difficulty, during implementation. This problem was fully addressed in the follow-up Inclusive Micro, Small, and Medium-Sized Enterprise Development Project (IMSMEDP). Project coordination. While Enterprise Development Unit successfully served as a central project administrator in place of a dedicated project management unit (PMU), the roles, responsibilities, and reporting lines were not sufficiently clear from the outset. This caused some communication issues and processing delays throughout implementation. This issue has been addressed in the follow-up IMSMEDP, which makes use of a dedicated PMU. 4. Project groundwork. Structuring and implementing a PPP project is complex, time-consuming, and requires significant resources and commitment by all parties involved. Knowing that the PPP concept was at an early development stage in the Maldives at the time of project inception and that few ministries had the capacity or resources for PPP project development, ADB and the executing agency should have identified appropriate focal points and obtained stronger management commitment from relevant line ministries to ensure efficient implementation. 5. Improved monitoring. Considering the broad scope of the project and the capacity constraints of the Ministry of Finance and Treasury and the implementing agencies, implementation might have benefitted from more extensive monitoring and more frequent reviews, as well as the establishment of a project performance and monitoring system. By the time of the midterm review - 17 months behind schedule, in March 2012 - only 75% of contract awards were complete and disbursements stood at only 54%. 6. Consulting packages. Although the initiatives under the project were largely complementary, each project output required a distinctly different knowledge base and skill set in consulting services. However, output 2, suboutput 2 made use of three consulting packages, involving a consulting firm and two individual consultants. While the use of two individual consultants was deemed the most economical approach at the time of inception, their deliverables overlapped somewhat and could possibly have been consolidated in one contract package to improve overall project management. 7. Interest rates for financial intermediation loans. ADB policies for financial intermediation loans require that onlending rates for subborrowers should be market-based. For the PSDP, the Bank of Maldives line of credit facility onlending rates were in line with similar loan schemes in the Maldives targeting MSMEs from financial intermediation loans from other international financial institutions, and were in excess of Bank of Maldives' cost of funds. The line of credit facility lending priorities included extending credit to new MSMEs in outlying atolls, where the broader strategy was to support inclusive economic growth, job creation, inclusion of outer islands in national development, and private sector investments. In future, projects involving financial intermediation loans will require careful monitoring of compliance with ADB policies. This is particularly important for onlending to repeat MSME borrowers to ensure a move towards more commercial lending practices. 8. Output specific. Stakeholders have provided the following observations to improve sustainability: (a) Line of credit facility. The line of credit facility could have been structured as a revolving facility to extend the benefits to MSMEs and improve sustainability. To leverage ADB funds, ADB could also have provided the line of credit facility under a fund management arrangement through which the BML could have administered the less expensive ADB funds and cofinanced at market rates. This would have resulted in competitive, all-in, blended costs to the borrowers. (b) Cost-sharing facility. Instead of a cost-sharing scheme where development partner funds are depleted - or perhaps in addition to one - a scheme that used cost-sharing facility funds as equity-type capital could have been designed under which the cost-sharing facility would be repaid if and when the business benefiting from the funds became successful. Such an arrangement could also help align incentives between the business development service center and the MSMEs. (c) Business development service centers. While it may be difficult to charge small enterprises that may be cash constrained up-front fees for training and advisory on business plans or marketing, business development service center could instead arrange with these businesses to earn commissions or to benefit from profit sharing on future sales. This would make the business development service center operations more sustainable. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/private-sector-development-project-pcr
Regional Development Project, Phase II - Environmental Infrastructure and Management | Maldives | Water and other urban infrastructure and services | 2014-08-01 | The government and the Ministry of Energy and Environment (MEE) had implemented the Regional Development Project prior to this follow-up project. The government asked that project implementation support be provided to help implement Regional Development Project, Phase II - Environmental Infrastructure and Management. Although MEE was not fully conversant with ADB procedures at first, timely support from ADB and willingness of the MEE staff to adopt these practices helped implement the project. The Ministry of Finance and Treasury and the government fully supported the project. Like the agencies that acted as the implementing agency before it, the Ministry of Energy and Environment experienced problems in obtaining approval for (i) establishment of the regional project advisory committee; (ii) government budgetary support; (iii) an operations and maintenance strategy; and (iv) project design changes. Investment under the project should have also includes increased institutional governance strengthening, ensuring a well-balanced, sustainable project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/regional-development-project-phase-2-pcr
Economic Recovery Program | Maldives | Public Sector Management | 2013-02-09 | 1. A key consideration in sequencing is that legislative and regulatory reforms require changes in the capacity of institutions, meaning policy and rules; in the organizations charged with implementation; and in the abilities and management practices of responsible government officers. This cascade of legislative and regulatory requirements - from institutions to organizations to people - would seem to provide a strategic sequence for reforms, but, in practice, this is not a linear sequence. Rather, people - officials and stakeholders - are involved from the outset of the reform process. Because policy reforms are an iterative, negotiated process, attention needs to be given to developing and maintaining a broad consensus for reform. This is one of the most difficult and important challenges in sustaining change in management processes. It is important to note that developing and maintaining a broad consensus for reform was one of the hallmarks of the Economic Recovery Program. This ensured unwavering government commitment to the program's strong legislative and regulatory reform content. project cycle stage: Lesson Topics: 2. In addition to appropriate reform sequencing, ambitious and complex programs and projects are more likely to succeed if significant attention is given to building the capability and ownership of the relevant stakeholders. The Economic Recovery Program successfully tackled a wide range of issues in a short time, while also contributing significantly to developing capacity at the Ministry of Finance and Treasury. project cycle stage: Lesson Topics: 3. Institutionalizing change-management practices among those charged with implementing reforms - such as the efforts undertaken in the Economic recovery Program to provide staff with technical skills to implement new revenue measures at Ministry of Finance and Treasury - requires upgrading of technical and change-management competency. It is necessary to enable government to sustain capacity development programs beyond the life of a program (for example, by providing training experts, particularly to develop soft capacities). project cycle stage: Lesson Topics: 4. The Economic Recovery Program (ERP) was developed in close consultation with the government and development partners such as the International Monetary Authority (IMF) and the World Bank through many joint missions, and was designed through a holistic approach. The ADB shared the policy matrix with the IMF and the World Bank and coordinated closely with them in the final design. The ADB also attended the Development Partnership Forum in the Maldives in March 2009 and held discussions with other key development partners. The ERP demonstrated that a comprehensive and holistic consultation process can ensure effective diagnosis of the issues, leading to a strong, relevant policy matrix that prioritizes reform measures and sets realistic timelines in collaboration with the development partners. project cycle stage: Lesson Topics: 5. The Economic Recovery Program (ERP) comprised 59 policy actions - 39 for the first tranche and 20 for the second tranche. The total number of policy actions under the ERP was significantly large and represented a challenge in terms of monitoring and implementation. The number of policy measures should be limited so that ADB can monitor compliance with them effectively throughout the program. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/economic-recovery-program-pcr
Domestic Maritime Transport Project | Maldives | Transport | 2013-01-10 | 1. Although the project cost estimate was made in 2002, procurement for the civil works was during 2008-2009. Due to price escalation, the bid prices received were much higher than originally estimated. Eventually, the implementing agency reduced the project scope so as to fit the project costs within the original cost allocation. In the future, it would be beneficial to shorten the time between detailed design and procurement and to use advance procurement to minimize start-up delays. Price escalation should also be factored into the project cost estimate. project cycle stage: Lesson Topics: 2. There were initial start-up delays due to re-advertising of the institutional development and capacity building component and rebidding of the infrastructure investment component (IIC). The latter impacted the implementation schedule most and resulted in a one-year delay in completing the IIC. This also necessitated extending the loan by one year to December 2010. In the future, it would be beneficial to undertake more robust feasibility studies. project cycle stage: Lesson Topics: 3. Due to frequent restructuring within the government agencies, the PIU team was unstable throughout implementation. For future projects, permanent technical staff within the project implementation unit (PIU) team should be retained as much as possible to ensure continuity of key knowledge and information throughout the project. To further mitigate this situation, future projects could include strong procurement and project management support to the PIU to ensure smooth project implementation. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/domestic-maritime-transport-project-pcr
Maldives: Tsunami Emergency Assistance Project | Maldives | Agriculture, Natural Resources, and Rural Development, Energy, Public Sector Management | 2012-12-27 | A lesson identified from this project is the need for ADB to focus more on sectors in which it has substantial experience, from which it can draw from during the relatively fast pace of processing and implementing an emergency project. Also, given limited resources, sector selectivity is important to ensure a significant impact. Moreover, emergency project designs should likewise incorporate provisions for operation and maintenance of project facilities to ensure their sustainability. [Main text, para. 30] project cycle stage: Country Partnership Strategy Lesson Topics: Methodologies/Approaches: Sectoral approach Methodologies/Approaches: Targeting | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/maldives-tsunami-emergency-assistance-project
Employment Skills Training Project | Maldives | Education | 2012-01-06 | 1. Timely selection and training of project staff is essential for effective implementation. The delayed establishment and operationalization of the project implementation unit prevented activities from being properly sequenced during the first 2 years of project implementation. project cycle stage: Lesson Topics: 2. Stakeholder support is essential for increasing awareness and acceptance of technical and vocational education and training (TVET). To ensure the sustainability of the project's achievements, the government must provide continuing financial and human resources support to increase awareness and acceptance of TVET, particularly in the form of career guidance and social marketing. Continued cooperation by the National Career Guidance Center, nongovernment organizations, job centers, and private sector training providers in facilitating career guidance, social marketing, and job creation should be further encouraged and sustained. project cycle stage: Lesson Topics: 3. It is important to establish and maintain a network for cooperation in competency standards development within the region where similar issues and problems regarding the promotion of technical and vocational education and training and development of competency standards prevail. Benefits from this approach include facilitated adoption and adaptation of established standards, which may be applicable to Maldivian requirements, as well as the mutual sharing of ideas, processes, competency standards, and materials on skills training. project cycle stage: Lesson Topics: 4. The relevant stakeholders (i.e., various ministries, agencies, employers, training providers, youth, parents, schools, and communities) are often unaware of technical and vocational education and training (TVET) and its various features and components, and continued efforts to bring them onboard must be made through interagency cooperation and coordination, workplace visits, and promotional campaigns in schools and communities. For these to be effective, interagency cooperation and coordination in TVET policies, legislation, programs, and budgets needs to be strengthened at the central and local levels. This will ensure that problems and issues related to TVET are addressed through a participatory approach and government agencies, private sector agencies, and local communities have a clear understanding of their tasks and responsibilities. This will also prevent conflicts in management decision making and avoid duplication of work, plans, and strategies for TVET. project cycle stage: Lesson Topics: 5. The establishment of a dynamic labor management information system would have been useful in gathering relevant information for guiding the employment sector councils in identifying high demand occupations and developing competency-based skills trainings that are demand driven. Also, such as a system would have provided important information to support policy-related decision making, planning, and interagency cooperation and coordination and helped determine and quantify project achievements. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/employment-skills-training-project-0
Information Technology Development Project | Maldives | Information and communication technology | 2011-12-01 | Project design. The project was the first of its kind for ADB in the information and communications technology (ICT) sector and in the Maldives. ICT projects are very different from transport projects, in design, implementation, and operation. ICT projects need to have a physical infrastructure for connectivity, software applications for the connectivity to be functional, and a regulatory regime to support the connectivity and applications. The project suffered delays, especially in the initial phase, due to the complexity of the project components and the Ministry of Finance and Treasury's (MOFT) lack of experience in ADB procurement procedures in the ICT sector. Local information and communication technology environment. Project design should adequately consider the local situation, including sector development status, regulatory framework, and local capacity for implementing the project and absorbing the new technology. The implementation should be conducted jointly by external consultants and local experts to avoid transitional issues. Unlike transport projects, the completion of an ICT project, especially of turnkey projects, only means half the project is finished and many follow-up issues in operation, maintenance, and sustainability need to be attended to. Therefore, the design and formulation of an ICT project should consider not only implementation, but also the operation phase. Sustainability. Projects with adequate counterpart funds (capital and operational) can encourage government ownership and improve sustainability. The project plan should incorporate a strong operational and sustainable model. Some of the factors leading to unsatisfactory sustainability in ICT projects include an inadequate financial and business plan, and a lack of trained personnel, ownership, and support from public leaders. Project management. Adapting to a formal project management framework approach and a central repository for tasks, processes, guidelines, and templates can help a great deal with the efficient implementation, monitoring, and evaluation of a project. This can have positive impacts on the overall efficiency of the organization, as well as reporting. Technical expertise. To expedite project implementation and avoid project delays, the gap between technical and management expertise should be bridged by frequent consultations and diverse team compositions. For example, ADB missions should include information technology (IT) and procurement experts, who may provide adequate and timely guidance on technical matters and ADB procurement. The government's supervision and oversee consultants should facilitate mutual understanding and trust between the contractors and government, and provide adequate problem solving. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/information-technology-development-project
Outer Islands Electrification (Sector) Project | Maldives | Energy | 2011-12-01 | Island selection and subproject appraisal were inefficient, delaying the commencement of contract processing by over 2 years and suggesting a recommendation for altering the approach that is shown in the next section. Forming separate, miniature utility cooperatives on individual islands with an average population of only 1,511 people, each with a separate loan agreement and inspector, proved very difficult to implement. This suggests that one island is too small a unit to justify this approach. The availability of technical expertise on each island varies significantly, and the requisite financial-management and tariff-setting expertise is scarce. The government?s decision in 2009 to form regional utility companies (RUCs) was good for the project, as their taking over ownership and operation enables economies of scale and operational efficiencies, including more effective utilization of technical and managerial skills across islands. Had RUCs existed at the beginning of the project and acted as IAs for clusters of projects within their territory, numerous implementation and coordination problems could have been avoided. In formulating similar loan projects, ADB should ensure to the extent possible that achieving outputs is within the grasp of the implementing agency (IA). Depending on the Ministry of Planning and National Development (MPND), an agency without a stake in the subprojects, to spearhead the benefit and poverty monitoring and evaluation (BPME) proved problematic, as its withdrawal from that commitment left the IA unable to complete that part of the project. Passing the Cooperative Societies Act, the necessary enabling legislation before subproject loan agreements were possible, was known at project approval to be the responsibility of Parliament and therefore something the government could guarantee. Yet project formulation as set out in the report and recommendation of the President (RRP) implicitly assumed that this legislation would be passed in a timely manner and offered no robust contingency plan should the legal entities to operate subprojects fail to materialize. For future projects located on numerous outer islands, formalized feedback channels from local island development committees (IDCs) to the IA should be established as part of project design. A notable feature of this project was the difference in the performance of the batch 1 and batch 2 contractors, though both contracts were undertaken by the same consortium. The main difference was in project management requirements. Particularly for projects involving outer islands, which by their nature introduce communication and logistical challenges, ADB should ensure that bid documents specify minimum requirements relating to project and contract management, requiring bidders to fully describe planned contract and project management plans in their bids and stating that ADB will not approve contracts unless satisfied that these plans are adequate to ensure successful and timely completion. ADB must supervise an IA more effectively if it has not established a prior record of successfully managing ADB-funded projects. ADB review missions throughout the project noted early warning signs that the project faced difficulties. More proactive and decisive action by ADB might have effected more efficient implementation. For example, when it became apparent that legislation would be delayed, ADB could have engaged the government to discuss an acceptable alternative, rather than simply leave it to a review mission to urge the government to take unspecified corrective action. There are underlying systemic challenges associated with project implementation on the outer islands of the Maldives that must be considered in project design, as these conditions are different from those of other South Asian developing member countries. First, direct project oversight is more difficult because of transport issues unique to the archipelago. (Many outer islands are remote, with transport by lengthy, infrequent, and irregularly scheduled boat trips. The only alternative of hiring fast private boats is very expensive.) Second, a subproject on a particular outer island is naturally much smaller than infrastructure projects in larger countries. Third, the cost of hiring international consultants for long periods makes consultant costs disproportionately high when compared with direct project costs such as civil works, and the availability of local consultants may be limited in a small population. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/outer-islands-electrification-sector-project
Country Assistance Program Evaluation for the Maldives | Maldives |  | 2011-09-30 | 1. Continued engagement, long-term focus, and appropriate phasing within a sector will enable better policy dialogue, improved sector outcomes, and increased development impact. Given the limited resource envelope available to the Maldives, ADB needs to prioritize which sectors it needs to focus on. In the past, it has been involved in as many as nine sectors, often based on decisions to support specific projects. This has contributed to lack of continuity, intermittent engagement, and constrained resources available to any one sector over time. A long-term focus in sectors of demonstrated comparative advantage, combined with adequate resources, analysis of constraints, regular policy dialogue, and project lending and capacity development programs is required for improved results. Accordingly, parallel efforts also need to be coordinated with development partners to optimize complementarities. [Main text, paras. 99-100,104,190,210] project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Lending modality Capacity Development: Capacity development Country Context: Prioritization Methodologies/Approaches: Policy dialogue Methodologies/Approaches: Targeting 2. An incremental approach and long term focus for capacity development through ADB's advisory technical assistance is likely to be more effective, although demonstrable results take time. Various country experiences have noted that interventions for developing sector capacity incrementally over a longer period of time have succeeded in strengthening capacity, whereas ambitious single interventions have not. In the case of Maldives, capacity development TA activities were provided alongside individual projects rather than as part of a long-term strategy to meet institutional development needs. As a result, little continuity and sequencing of assistance is apparent in various sectors and contribution to institutional development has been limited. [Main text, paras. 122,213] project cycle stage: Design Lesson Topics: | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-maldives
Postsecondary Education Development Project | Maldives | Education | 2009-08-14 | 1. Early establishment of an adequately staffed project implementation unit (PIU) is important, especially in a subsector without prior experience of externally funded projects. The project experienced substantial time overrun given its failure to appropriately staff the PIU. Hence, an adequately staffed PIU could be a condition of loan effectiveness or disbursement, as appropriate. Where full-time staff for a PIU cannot be committed, recruitment of project implementation consultants should be considered. [Main text, paras. 32, 62] project cycle stage: Design Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Project management 2. If cofinancing arrangement is not finalized before approval of a project, ADB needs to take a more conservative approach in project design and should not include cofinancing for project scoping and costing. In the event of cofinancier's withdrawal from the Project, as a safeguard, related components should have been covered by ADB or Government funding to preserve the integrity of project design. The AusAID financing did not materialize during and even after appraisal which subsequently reduced project scope. [Main text, paras. 8,63] project cycle stage: Design Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement 3. Government and stakeholder ownership positively contribute to sustaining project benefits. The ownership of the Government is visible as it continued to provide increased funding to Maldives College of Higher Education (MCHE) after completion. The highly relevant and acceptable MCHE course offerings enjoy wide support in the country. All key stakeholders are proud of the MCHE achievements as it successfully delivered the majority of the outputs and met their expectations. [Main text, paras. 54, 64] project cycle stage: Design, Appraisal, Implementation, Completion Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Capacity development Capacity Development: Ownership 4. The status of benefit monitoring and evaluation (BME) needs to be regularly followed up and more rigorously, if it is part of loan covenants. Hands-on support for BME activities could have added value to the project. To be meaningful, BME should be integrated into an existing national monitoring system such as the Statistical Office under the Ministry of Planning and National Development. [Main text, paras. 44, 65] project cycle stage: Design, Implementation, Completion Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design 5. Technical assistance should be provided for capacity development before introducing new initiatives and reforms. The standard time frame of 5 years to implement projects is not realistic especially in social sector projects in a country where capacity must be built before implementing reforms and innovative actions. [Main text, para. 66] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/postsecondary-education-development-project
Republic of the Maldives: Validation of the Country Strategy and Program Completion Report | Maldives |  | 2007-06-30 | 1. A strong central project management unit in the executing agency equipped with adequate technical staff would help to improve project implementation. project cycle stage: Design, Implementation Lesson Topics: Project Management: Project administration Project Management: Project management Project Management: Project supervision 2. ADB needs to better assess institutional capacity weaknesses, strengthen human resource management systems, and build capacity in selected government agencies. Considering the limited annual technical assistance (TA) budget, a more flexible modality (such as a TA loan) needs to be contemplated. ADB assistance to capacity development needs to be conditional on Government appointing qualified staff in the institutions supported by ADB TA. project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Technical Assistance Capacity Development: Capacity assessment Capacity Development: Capacity development Capacity Development: Institutional analysis 3. A more integrated approach, with common themes across projects and sectors, should be explored to develop synergies within ADB's operations in the Maldives. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Harmonization Methodologies/Approaches: Holistic approach 4. ADB should carefully assess the operational benefits and costs related to maintaining a local office in the Maldives. project cycle stage: Country Partnership Strategy Lesson Topics: | Country Partnership Strategy Final Review |  | http://www.adb.org/documents/republic-maldives-validation-country-strategy-and-program-completion-report
Third Power System Development Project | Maldives |  | 2005-05-13 | If a firm were to be retained, the contract should be based on payments tied to the satisfactory completion of milestones and deliverables (performance-based contracting). Although this would require more work upfront by the executing agency in preparing very detailed Terms of Reference and expected outputs for the consultants, it would guard against significant cost overruns. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement It may be more efficient to have one contractor for a project unless there is a strong justification to break up a contract. Breaking up the project into three lots with the potential for three different contractors (although the project ended up with only two contractors) ultimately proved to be unwieldy. Coordination of the two contractors for three separate packages took up much of the time and effort of the implementation consultants and contributed significant cost overruns for them. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Management: Consultants Project Management: Procurement Methodologies/Approaches: Consultation/Participation More appropriate financial requirement of the contractors could have safeguarded against hiring a contractor who could not or would not provide adequate service because of financial constraints and was ultimately detrimental to the project. project cycle stage: Implementation Lesson Topics: Retaining one or two individual consultants instead of a firm (i.e., one electrical engineer and one civil engineer) with significant experience in procurement and project management to work full time in the executing agency could be an option. It would cost less, and they would only have the interests of the executing agency to look after. In addition, these consultants could be supplemented with specialist engineers for engineering issues outside their areas of expertise. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-power-system-development-project
Public Sector Program - Subprograms 1 and 2: Program Completion Report | Marshall Islands | Public Sector Management | 2014-01-10 | 1. Program context and government ownership. The intended program outcome of achieving fiscal sustainability was overambitious, given the historically slow pace of reforms in the Republic of Marshall Islands and in other countries facing fragile situations. Moving forward with the reforms needed to fully deliver the program outputs required approval of three key pieces of enabling legislation, but the program design did not take into account the likelihood of a lengthy parliamentary approval process and underestimated the political opposition such reforms might encounter. The program's design did anticipate the political sensitivity associated with some of the proposed reforms and supported a public consultation process to garner support and build ownership, but resistance has continued and is still delaying approval, which was initially expected to come by program completion. [Main text, para. 37] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform 2. Design and monitoring framework (DMF). The program's DMF was overambitious (para. 8) and, based on ADB guidelines for DMF preparation could have been correctly recast to make the outcome the intended impact and output 1 the intended outcome. The outcome and impact statements and indicators and targets in a DMF need to be realistic and take into account the country context. [Main text, para. 38] project cycle stage: Design Lesson Topics: 3. Policy actions: All Pacific developing member countries, including the Republic of Marshall Islands (RMI), have great difficulty implementing policies to support long-term adjustments. The program included several line expenditure conditions under output 2 that the government struggled to implement and monitor (para. 16). In the end, the government decided to make across-the-board expenditure cuts rather than the targeted cuts proposed under the program. The condition targets were related to budget estimates rather than budget outturns. Achieving these estimates requires a strong budgetary system, but the system in the RMI is weak. It may have been more appropriate to set conditions relating to budget processes and controls rather than estimates that proved difficult to execute. [Main text, para. 39] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Policy & Reform: Reform 4. On-the-ground support. Policy dialogue required on-the-ground support from ADB. Establishment of the ADB development coordination office in November 2011 played a key role in forging policy dialogue, although this was undertaken issue-by-issue (expenditure management, taxation, and state-owned enterprise reform) rather than through a holistic approach. Other development partners also provided substantial support for public sector reform in the Republic of Marshall Islands, but the coordinated dialogue with government that has been used successfully in programs elsewhere in the Pacific was missing. In the absence of a central foreign assistance unit or other aid coordination mechanism within government and if the proper channels for timely communication are not in place, risks of duplicated, excessive, or insufficient support in certain reform areas exist. [Main text, para. 40] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Policy & Reform: Reform Methodologies/Approaches: Policy dialogue | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/rmi-public-sector-program-subprograms-1-2-pcr
Skills Training and Vocational Education Project | Marshall Islands |  | 2006-11-15 | 1. In the case of a weakly performing, fragile, state (such as the Republic of Marshall Islands) - where governance is weak and institutional performance can also be expected to be poor - project design must pay far greater attention to examining the effective demand for any public sector improvement and the need to strengthen institutions and capacity development. [Main text, paras. 3, 53-54, 64(i)] project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Project Design: Project design Capacity Development: Capacity development Capacity Development: Institutional analysis Policy & Reform: Reform 2. National consultants should be preferred over international consultants where qualified, skilled, and otherwise competent national consultants exist. Greater attention should be given to consultants' terms of reference, so that this may complement local capacities. There is a growing cadre of Marshallese consultants in the field of economics and social development and ADB is increasingly employing them. [Main text, paras. 43, 46, 64(ii)-(iii)] project cycle stage: Appraisal Implementation Lesson Topics: 3. The engagement of a full-time, qualified accountant who is experienced in ADB loans can greatly assist project implementation. In this project, the accountant did an excellent job of tracking all orders. and ensuring timely payments to vendors and proper distribution of landed goods. [Main text, paras. 45, 64(iv)] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Project Management: Procurement Project Management: Project administration | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/skills-training-and-vocational-education-project
Ebeye Health and Infrastructure Project | Marshall Islands |  | 2004-12-15 | External management and privatization are critical for successful and viable operation of utilities in small island communities. The ongoing management contract with American Samoa Power Authority or ASPA (an external entity) was a key to the improvement of the operations of the power and water utility. ASPA's technical expertise, controls, and discipline in managing the operations - and its strict adherence to rules for revenue collection - helped to turn around the loss-incurring, government-owned public utility. Therefore, the appointment of a private sector operator to manage and control the utility for a minimum of 18-24 months as a condition of loan effectiveness was a key to project success. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Sector Related Issues: Energy planning/management Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Policy & Reform: Privatization Extra precaution should be taken in materials and equipment specifications to take into account the harsh external environmental conditions in the Pacific islands, such as high humidity, excessive salt content in the air and water, high temperatures, exposure to elements, etc. These conditions contribute to rapid and excessive corrosion of materials and equipment. project cycle stage: Implementation Lesson Topics: For projects of this size and in such a remote location, international competitive bidding often is not possible. Several bid attempts failed due to a lack of responsive bids, as few international bidders expressed interest in civil works that required even minimal mobilization. This caused much of the project's delay. A preferable approach would involve the use of domestic contractors (through local competitive bidding) where feasible, and negotiated bids with international contractors based on the island or with prior work experience in the Marshall Islands. project cycle stage: Implementation Lesson Topics: For proper collection and professional management of public utilities, strong controls, operating guidelines, and appropriate legislation should be in place from the start. This was done before the project began, which led to an immediate turnaround. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Sector Related Issues: Energy planning/management Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework Minimal implementation problems were encountered because (a) adequate consultations were undertaken with all stakeholders during project preparation; (b) a domestic project manager headed the project management unit (PMU); (c) the government, particularly the Office of the President, provided full support; and (d) ADB provided some flexibility in implementation to address the special circumstances of the project. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach Rehabilitation of equipment and completing unfinished buildings was significantly more complex than anticipated, and the main reasons for the 1-year delay in implementation. Given the isolation and remoteness of the location, an implementation period longer than 30 months should have been provided. project cycle stage: Feasibility, Appraisal Lesson Topics: Single-source procurement should be allowed in cases where, in rehabilitating old equipment, the only option for procuring spare parts is the original manufacturer of the equipment. project cycle stage: Implementation Lesson Topics: The inadequacy of the original hospital design, and non-compliance with health and safety standards, was not fully anticipated during project design. This was a unique situation, and such work in the future should be undertaken after more thorough investigation. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/ebeye-health-and-infrastructure-project
Fiscal and Financial Management Program | Marshall Islands |  | 2004-06-15 | Negotiations on the Compact [Compact of Free Association between the Governments of the Marshall Islands and the United States of America (US)], especially the extension of the economic assistance package, complemented and reinforced this reform program. The Compact Negotiation Office (CNO) became a partner and stakeholder in the reform process. The CNO helped champion many of the program reforms, and moved forward on many reforms when the executing agency (Ministry of Finance) was still lagging. In contrast, the government showed little support for the reform program during the Public Sector Reform Program (PSRP). The PCR for the PSRP recognized that lack of champions of reform within the government, which made reforms much more difficult to implement. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Policy & Reform: Public sector reform The implementation of the program provides a useful comparison with the difficulties faced during the implementation of the Public Sector Reform Program (PSRP). Many of these difficulties can be attributed to the fact that the PSRP involved severe, painful, and enforced reductions in the number of employees in the public service. Even so, it is interesting to note the differences that appear to have allowed for a smoother implementation of the program. Among the most notable differences was the improved dialogue between ADB and the government, which was willing to address reforms. The administration implementing the program was elected in 1999, and initially addressed the outstanding conditions of the PSRP. The new government then proceeded to implement the program with the assistance of ADB, moving forward on a number of reform fronts. The openness of the new administration made implementing reforms more realistic. Although some progress in fiscal policy has been demonstrated, some weaknesses endure. project cycle stage: Concept Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Loan Agreement: Covenants Modality: Program Policy & Reform: Policy matrix Policy & Reform: Public sector reform The improved design of the program can be attributed to a more consultative and participatory process than in the Public Sector Reform Program (PSRP). Meto 2000, created under a Pacific Islands Economic Report (PIER) TA, involvedwidespread consultation with the community about the impacts of the PSRP and the priorities for further reform. The recommendations of the Meto 2000 led to many of the reforms included in the program. When it came to implementing the program, Meto 2000 ensured a greater understanding of the reform process and the need for the reforms. However, the reforms under the program were less painful and less dramatic than those required under the PSRP. project cycle stage: Feasibility Lesson Topics: Modality: Program Modality: Technical Assistance Project Design: Project design Country Context: Prioritization Policy & Reform: Reform Methodologies/Approaches: Participatory approach The program was implemented without the coordination of a program steering committee, a noteworthy accomplishment. Good coordination between the executing agency (Ministry of Finance) and the Compact Negotiation Office (CNO) was a key to successful implementation. When problems arose, they were resolved through close consultation among key agencies - without resorting to a formal program steering committee. The CNO also needed to move forward quickly on some fronts due to the momentum of the Compact negotiating process. The result was that the program and the Compact negotiation process reinforced each other, leading to a greater impetus for reform. This situation, which is closely related to the need for champions of reform, shows how useful it can be to link reforms to parallel processes with similar objectives. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/fiscal-and-financial-management-program
Majuro Water Supply and Sanitation Project | Marshall Islands | Water and Other Urban Infrastructure and Services | 2004-03-15 | A single turnkey contract, while easier to implement, is not always the most effective and efficient way to implement a multiple component project. project cycle stage: Appraisal Implementation Lesson Topics: Applying the principles of full cost recovery and determining onlending rates must be properly evaluated, especially for small utilities with limited financial capacity. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Monitoring & Evaluation: Project evaluation Project Design: Appraisal Capacity Development: Capacity assessment Sector Related Issues: Health and sanitation management Better understanding of local conditions, the operational setup of the utilities concerned, and the cultural environment in which the project will operate, are vital to proper design and implementation. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Country Context: Cultural constraints For smaller communities, much greater analysis is required before designing tariffs, particularly when alternative sources of water are accessible. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial analysis Sector Related Issues: Health and sanitation management In the absence of an in-depth review and analysis, accepting the continuation of detailed design consultants to continue with supervision of construction must be made with much circumspection. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Project supervision In transferring water resources to other locations from areas where there are resource limitations, better understanding of political climate and in-depth consultations leading to proper agreements should be in place prior to project formulation. project cycle stage: Concept Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation Lack of adequate consultation at project preparatory stage and at design stage with the end user and other stakeholders can reduce the impact of a project. Consultations that cover type and level of proposed facilities, size, costs involved, probable tariffs, affordability, and willingness to pay are vital for the sustainability of the project. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Methodologies/Approaches: Consultation/Participation The assumptions on revenue growth and tariff increases must be based on social indicators that are not unrealistically high. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Indicators The project design and the consequent loan size must take into consideration the size of the utility and population of the project location. Over ambitious projects can become a burden of the government and the community. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Sector Related Issues: Health and sanitation management When designing future assistance, the selection of the reservoirs and other materials to be used should take into account local knowledge on atmospheric conditions (which is highly corrosive in locations like Majuro). project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/majuro-water-supply-and-sanitation-project
Health and Population Project | Marshall Islands | Health | 2002-12-13 | As for all the projects in the social sector in the Pacific islands, a 5-year implementationperiod is too short, particularly for the achievement of performance targets. Anupfront implementation period of 6 to 8 years appears more realistic. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Sector Related Issues: Education Sector Related Issues: Health and sanitation management Methodologies/Approaches: Targeting Due to the necessity of importing trainers for many of the skills required in the Pacific island developing member countries, outcomes depend to a large extent on the performance of the consultants. The selection of the consultants must be done carefully to ensure a project's success. The experience with consulting firms was particularly unsatisfactory in the case of this project. Strong monitoring to allow for early detection of poor performance and termination of the contracts, if required, must be built into both the contracting procedures and the project's management. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Project Management: Procurement Project Management: Project management Capacity Development: Capacity building Experience from this project, as well as from other health projects in other countries,shows that external sources of aid are often in too much of a hurry to press governments toagree on policy positions consistent with their own views and priorities, allowing too little time forthe necessary political process. Also, pressures to expand the agenda to include all of thefunders' favorite subjects can result in overly ambitious plans that do not necessarily reflect what islocally considered important to improve health outcomes. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Country Context: Prioritization Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework In common with other small island states, the Marshall Islands suffers from a lack ofsuitably trained staff who can substitute for colleagues attending training courses or programs.The amount of training planned to take place during the life of the project was probablyunrealistically high. In addition, other trainings continued taking place during implementation,placing an unsustainable burden on staff. A simple way of reducing the disruptive effect oftraining would be to establish manageable blocks of time, for example two periods of 6 to 8weeks each year, during which training can take place. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Human resources management The assistance provided to the Project Implementation Unit (PIU) for project implementation capacity proved of greatbenefit. However, it did not compensate for weaknesses in accounting. Where very limited accounting skills are available within the country, future projects must provide for additional capacities in this area. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial reporting Project Design: Project design Project Management: Project management Capacity Development: Capacity building The health education campaign has been less successful than anticipated because of the absence of a family health coordinator. The position has remained vacant in view of the inability to recruit a suitable candidate either locally or internationally. In general, as regards covenants requesting additional recruitments, they were in obvious conflict with the requirements of another ADB loan supporting the Public Sector Reform Program to decrease public service employment. Coherence has to be sought within ADB's programs and projects. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Design: Project design Project Management: Procurement Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Public sector reform The time budgeted for the consultants for the health financing and accountabilitysegment was obviously too short. Instead of one consultant for 8 person-months, twoconsultants for a total of 5 person-months were recruited. This did not allow enough time foreither of them to work along with local counterparts and implement any substantial change. Experience from other Pacific Developing Member Countries (PDMCs) has shown that a minimum of 1-2 years is required to obtainresults in this sector. However, most borrowers are reluctant to include long consultancies inprojects for economic reasons. Nevertheless, this concern must be balanced with the necessityof building long-term working relationships to obtain change and build capacity in smallcountries that lack skilled staff. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Corruption Finance & Financial Aspects: Financing Project Design: Project design Project Management: Consultants Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/health-and-population-project-0
Basic Education Development Project | Marshall Islands | Education | 2001-12-14 | All local training, especially that involving in-service teachers, needs to be continued and funded by the government after the conclusion of the project. Continued refresher courses are necessary to keep the teachers updated on the latest developments and changes in the curriculum. Similarly, continued government funding is necessary to provide adequate textbooks and materials to support curriculum implementation. Inadequate funding and lack of support will make it difficult to achieve any Basic Education Project (BEP) objectives. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Education As this was the first loan to the education sector, the executing agency had no prior experience with ADB procedures. The inception mission should have provided sufficient time and all necessary training and familiarization to the executing agency and the Project Implementation Unit (PIU). The Basic Education Project (BEP) design correctly called for the engagement of a consultant to establish the PIU, train the executing agency staff in ADB procedures, and prepare the implementation plan andschedules. The nonrecruitment of the advance action consultant contributed to the difficulties and delays in implementation. project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Project Management: Project supervision Capacity Development: Capacity building Sector Related Issues: Education In the design of educational projects in the Pacific, due consideration must be given to the lack of institutional capacity, weak management, and inadequate recurrent funding. Therefore, longer implementation periods should be considered. Implementation capacity needs to be assessed during appraisal. In this context, ADB should monitor education projects more closely, and missions should include an education sector specialist from time to time. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Human resources management Sector Related Issues: Education It is important that the executing agency and ADB be aware of ongoing and upcoming aid agencyactivities in the same sector to avoid duplication of efforts. All aid agency activities in a particular sector need to be coordinated to avoid difficult projects' working at cross purposes. project cycle stage: Appraisal Lesson Topics: Lack of provision for a qualified project accountant as part of the counterpart staffwas a major shortcoming of the project. Future project design should include aqualified project accountant in the Project Implementation Unit (PIU) funded under the loan. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Human resources management Providing curriculum development, training, and physical infrastructure can help,but are unlikely to produce significant improvements in student performance andachievement unless an appropriate overall educational environment isestablished. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Education Policy & Reform: Policy reforms/framework Since the education delivery system in the Republic of the Marshall Islands (RMI) is based on the US model, the consultants recruited should have been conversant with the US education system and should have had experience in the Pacific. Likewise, sequencing and overlap of consultants' engagement could have been better planned and coordinated. project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Project administration Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation The long lead times and lack of qualified local contractors in the Pacific must beconsidered in the design of civil works components and in the determination ofimplementation schedules. If local contractors and suppliers are to be used, moreextensive evaluation of capability must be carried out. Bid documents have to becarefully prepared and materials specifications clearly stated to avoidcomplications during civil works implementation. The flexibility to conductnegotiated bids should be given. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Procurement | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/basic-education-development-project
Strengthening the Energy Sector Regulatory Framework: Technical Assistance Completion Report | Micronesia | Energy | 2015-08-01 | ADB project officers should identify and resolve divergent or conflicting expectations of TA (technical assistance) outcomes between national and state-level actors at the outset of TA design. TAs assisting FSM (Federated States of Micronesi) can be required to serve multiple clients at different levels whose demands and expectations may conflict, or compete for resources and attention. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-energy-sector-regulatory-framework-tcr
Public Administration Review of the National Government: Technical Assistance Completion Report | Micronesia | Public sector management | 2015-02-01 | TA (technical assistance) processing requires a careful assessment of the government's ownership. Clear understanding of TA goals, objectives, and activities need to be established at the processing stage. Even at the early stage of TA implementation, regular communications with the government and consultants are required for effective TA implementation. Public administration reforms require a strong political commitment by top policymakers since they can affect the entire government. In the TA, the Personnel Division could not perform well as the IA (implementing agency) with its limited administrative capacity. Further, organizational structure of public administration, one core element of the TA, was far beyond the responsibilities of the Personnel Division. It is thus important to choose appropriate government units as the executing and implementing agencies. It is also critical to consider an appropriate resource allocation to TA that covers a wide range of topics in a public administration reform initiative. While the project officer requested an additional financing after the revision of the TA goals and objectives in consultation with the government, it was not materialized due to the lack of TA resource in the department. The success of reforms depends on technical merits of proposed reform options, but more on political feasibility. ADB needs to consider a long-term commitment with appropriate resources once it decides to intervene in public administration reforms. ADB also needs to avoid any disruption of TA implementation due to a transfer of a project officer during the TA implementation. Project cycle stage: Design, Feasibility, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/fsm-public-administration-review-of-the-national-government-tcr
Private Sector Development Program | Micronesia |  | 2010-12-01 | Broad consultation, awareness raising, and development of skills of key state stakeholders during loan preparation would have enhanced program implementation and possibly reduced the delays in achieving loan effectiveness. Transforming state-owned enterprises and establishing an enabling environment for private sector foreign investment takes considerable time and ongoing support. Individual capacities, particularly in the executive and legislative branches of government, need to be assessed before an accurate judgement can be made of the time needed to prepare for loan effectiveness and then to implement reforms. Continued formal opportunities for dialogue on private sector development with policy makers and legislators after the second tranche had been released may have helped maintain the impetus for change in the enabling environment for private sector development. Such formal discussions with legislators may have improved their understanding of the constraints facing the sector and thereby facilitated earlier passage of key legislation. The implementation of civil works was delayed due to the time taken to reach government agreement on design, approval procedures, and project implementation unit (PIU) staffing. Early stakeholder and beneficiary involvement during project preparation is needed to ensure project quality and ownership that can minimize such delays. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/private-sector-development-program
Basic Social Services Project | Micronesia | Education, Health | 2010-11-01 | Adequate consultation and participation at the state and community level during project design and scope change are essential for understanding the institutional capacity, and for identifying appropriate implementation arrangements and required technical assistance. Although most of the project activities were at state level, the project was designed to be managed at the national level. Consultations with all stakeholders at state or lower level during the design and preparation of scope changes would have been helpful to identify most appropriate activities and arrangements. It is essential to include maintenance components for new systems and facility renovations to ensure the sustainability of project outputs. The project initiated several new monitoring systems and supported renovation of health and education facilities. Since it often takes time for staff to understand the usage of new systems and facilities, 6 to 12 months of maintenance services are required to support the gradual shift of maintenance responsibility to the national and state governments. Providing long-term technical assistance at the state level would be more appropriate to support long-term development, including human resource development and monitoring and quality control systems. Institutional capacity developments require gradual changes and long-term support at the local level would be more efficient. To improve ownership, state governments should be closely involved in project monitoring and evaluation. Although the Federated States of Micronesia (FSM) government and ADB flexibly responded to the changes required as a result of second Compact, few activities were implemented during the first 5 years after the project was approved. To respond to such changes, long-term technical assistance on the ground and closer communication between local stakeholders and ADB is critical, through consultations and review missions. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/basic-social-services-project
Water Supply and Sanitation Project | Micronesia |  | 2005-01-03 | 1. In FSM, the readiness of essential legislative support and project cofinancing by the state and national governments should be confirmed at project appraisal or the loan negotiation stage to avoid implementation delays. project cycle stage: Appraisal Lesson Topics: 2. Land acquisition remains a difficult challenge in all states. Future projects must attempt to resolve such issues at appraisal to minimize land issues. Where land acquisition is necessary, the acquisition process should be established early at appraisal stage. project cycle stage: Design Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Appraisal Project Design: Project design Project Management: Procurement 3. For works such as wells, reservoirs, water tanks, and other capital assets constructed on land belonging to third parties, such transactions should be properly documented with lease registers and approved minutes. These should be reflected in the annual financial statements of the utility corporations. The financial statements should clearly explain the procedure in dealing with leases to ensure fair valuation of the assets. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Sector Related Issues: Water resource management 4. Necessary design changes and construction variations with major cost implications should be discussed and agreed with ADB early to avoid implementation delays. project cycle stage: Design Lesson Topics: 5. Where a single utility corporation (UC) is responsible for both water and power, the UC must maintain separate records for the water supply operations and power operations to assist in cost recovery. project cycle stage: Operation Lesson Topics: Monitoring & Evaluation: Data collection and management Sector Related Issues: Water resource management 6. A review of variations for the expansion of distribution systems should, in future, include the legal requirements for connection, particularly where the extension involves use of leased land. project cycle stage: Design Lesson Topics: 7. Comprehensive connection programs should be developed to include targeted areas, businesses, compliance and enforcement, connection maintenance, and connection targets. Such programs are especially relevant in places such as Chuuk. An associated public education and awareness program should be developed to improve community understanding of the benefits of connection, availability of lifeline block supplies, and payment methods. Customer data and performance indicators must be reported properly to the management in a timely manner to allow necessary adjustments in operation and maintenance, budgets, and connection programs; and to improve administration and customer relations. project cycle stage: Design Lesson Topics: Project Design: Project design Policy & Reform: Information dissemination/Public awareness 8. Establishment of suitable and appropriate indicators is important to properly monitor and evaluate the effectiveness of the Project during implementation. These should include water quality baseline data to evaluate improvements in quality under the Project. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/water-supply-and-sanitation-project
Fisheries Development Project | Micronesia | Agriculture, Natural Resources, and Rural Development | 2002-12-13 | A project designed to be commercial and ï¿½private sectorï¿½ in nature must be allowed to be truly commercial and not be constrained by excessive bureaucracy, government monopolies, and requirements to use particular government services (such as transshipping and airfreight management). In this instance, the lack of vertical integration in fishing, handling,transport, and marketing is a constraint on possible commercial success for Micronesia Longline Fishing Corporation (MLFC). Duplication of activity that reduces efficiency, such as the operation of fishing fleets by both MLFC (privatesector) and National Fisheries Corporation (public enterprise), must also be avoided. In this context, it is difficult tocomprehend how the project, in the design phase, could have been conceived as a pilot project. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Methodologies/Approaches: Pilot project ADB standard tendering requirements were more complex than desirable for many aspects of procurement for the project. It is imperative for a private sector fishing company, whose primary objective is to keep the vessels out at sea fishing, to be able to act fast when mechanical failures occur and be able to buy the necessary spare parts immediately. For the Commercial Fisheries Development component (Part A), this sometimes caused considerable downtime of the vessels while Micronesia Longline Fishing Corporation (MLFC) was going through ADB's procurement guidelines. project cycle stage: Appraisal Lesson Topics: Project Management: Procurement Sector Related Issues: Private sector Sector Related Issues: Rural development In Project Design, the realities - financial, physical, and geopolitical issues - must be clearly understood. In the case of this project, the presence of fish stocks does not necessarily mean that a viable commercial fishery can be developed. Conversely, however, fisheries projects will not always fail if they are appropriately designed in the context of a clear understanding of the situation confronted (such as reliability of airfreight). Where the project involves a commercial component, a careful analysis of the public policy setting and enabling environment will provide important guidance on the likelihood of success. Agreement to support a project such as this could then be predicated on governments, particularly state governments, making certain policy, regulatory, and legislative changes. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework The project was subject to a major design change: the replacement of new vessels with the purchase of secondhand vessels. For this, the Commercial Fisheries Development component (Part A) of the project should have beentemporarily suspended and a full review undertaken so that the likely outcomes of such a change could be fully understood. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Rural development The selection of consultants without Pacific experience, along with consultants who did not have appropriate technical skills, led to unsatisfactory and/or incomplete outcomes. project cycle stage: Appraisal Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/fisheries-development-project-0
Regional Road Development Project: Completion Report | Mongolia | Health | 2015-08-25 | Cost estimation. The initial cost estimates based on the feasibility-level design were inaccurate. Cost estimates based on a detailed design, together with an analysis of unit rates and price escalation factors, would have produced more reliable estimates which would have helped to reduce the implementation delays early in the project. project cycle stage: Design, Feasibility, Implementation Provisions for price escalation in civil works contracts. The absence of such provisions contributed to repeated contract terminations and delays. In inflationary conditions, contracts need to include provisions for price escalation. project cycle stage: Design ADB missions and Resident Mission support. During the early stages, the project would have benefited from more frequent missions by suitably qualified staff, as well as the involvement of an international transport staff person at the Mongolia Resident Mission to support project implementation. project cycle stage: Implementation Incorporating lessons and risk mitigation. Previous ADB-funded road projects in Mongolia had shown that the MRT and contractors have limited experience and that there have been problems with contractors' mobilization efforts. These lessons were not sufficiently incorporated in the implementation arrangements. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/regional-road-development-project-pcr
Third Health Sector Development Project: Completion Report | Mongolia | Health | 2015-06-26 | Very high turnover of MOH (Ministry of Health) staff slowed policy reforms that required legislative approval and government commitment. Although government changes cannot be predicted, a longer-term assessment of overall political stability would be valuable, so as to prioritize project policy goals that are necessary for project implementation and sustainability. A key lesson is that reform ambitions need to match the actual capacity of government agencies and factor in turnovers. Also, high staff turnover has an eroding effect on the institutional capacity of MOH, particularly in areas of policy analysis, continuity of policy reforms, and institutional memory. Therefore, future health projects should instigate skills development, training on policy analysis, and regular briefings and information sharing for MOH staff to improve counterpart competence, both individual and organizational. The government should enforce the implementation of current legal acts, such as the Civil Service Law, to make professional staff appointments independent from political changes in government. Strengthening legal enforcement is a more sustainable approach, but would require consolidated efforts by all political parties. project cycle stage: Feasibility, Implementation, Operation The working relationship between MOH (Ministry of Health) and the project team was to be assisted by working groups whereby MOH staff would work in tandem with project staff and consultants. This arrangement was meant to co-opt MOH in project implementation. Often however, the ministry officials' understanding of their role was limited to reviewing and commenting on project outputs, and that project staff and consultants would be responsible for project outputs. This view is shared widely across all government institutions, not just MOH. The working relationship between MOH and a project team could be improved with clearer cooperation arrangements and agreed schedules. An expanded management board version, where project-related stakeholders are invited to the formal management board meeting as observers with the right to vote, could be an option to be explored in the future. In the longer term, ADB should consider not to establish a parallel PIU (project implementation unit) and instead engage ministry staff in project administration. Although this approach could possibly result in slower project implementation because of staff overload and unfamiliarity with ADB regulations and procedures, overall government ownership and commitment could increase significantly. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/third-health-sector-development-project-prc
Preparation of Regulations and Capacity Development Plan for Involuntary Resettlement: Technical Assistance Completion Report | Mongolia | Public sector management | 2015-06-01 | Firstly, although the drafting of legislation is always urgent, a phase-wise approach proved to be more efficient to accommodate the changing political situation. It was important to maintain ADB's financial commitment to continue the momentum and ensure the complete draft legislation was provided to the government. Secondly, it was very important to prepare the regulations before the law was reviewed by Parliament, because civil society believes that the intent of new laws can be modified by government if regulations are drafted later. Thirdly, there were two retreats held for the project working group members to finalize the draft law and regulations; however more efforts could have been spent on building public awareness during this final stage, including parliamentarians. This was included in the scope of work but specific activities were to be determined by MCUD (Ministry of Construction and Urban Development). Given the political uncertainty and sensitivities of legislation relating to land, MCUD was reluctant to hold public awareness meetings to seek consensus. Some members of civil society voiced objections to increased powers of the State to apply eminent domain. MCUD believes these groups did not fully understand the details of the draft legislation which proposes very limited scope to use eminent domain while strengthening the due process to safeguard citizens' rights. Subsequently, the Vice Minister requested ADB to provide further support for public awareness campaigns. EARD (East Asia Department) decided not to extend TA support any further because MCUD has the capacity to do this when the timing is appropriate. In late 2014, the Prime Minister resigned and a new coalition government was formed. So the timing of submission to Parliament is still uncertain, especially with elections in 2016. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/preparation-regulations-and-capacity-development-plan-involuntary-resettlement-tcr
Road Sector Capacity Development: Technical Assistance Completion Report | Mongolia | Transport | 2015-06-01 | Cultivation of a culture of maintaining the roads and managing the road assets is essential to protect the road sector investments and sustain the road assets in Mongolia. Sector reforms, particularly legislation, are susceptible to political climate change and require persistent investment of time and human, technical and financial resources. ADB needs to pursue them at both the highest Ministry level as well as the technical specialist and middle-management levels. When designing the national consulting service input, it is important to take into account the human resource constraint in Mongolia, which is reflected in the shortage of qualified road engineers, transport planners, traffic modelling specialists and other technical expertise. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/road-sector-capacity-development-tcr
Education Sector Reform Project: Completion Report | Mongolia | Education | 2015-03-31 | Project design and implementation schedule. Design and implementation of policy reform activities are inherently complex, requiring coordination between various stakeholders. Considering the complexities, sufficient time should be allowed. Some of the target years specified in the DMF (design and monitoring framework) were unrealistic. Given the time required for design and implementation, especially under uncertain political situations, an adequate degree of flexibility needs to be built into the project design to respond to changes in the government's policies and priorities. For the design of and capacity building for policy reforms, a technical assistance attached to the project could have been considered. Contract awards and disbursements concerning policy reform activities tend to be slower than investment activities, which should be taken into account in the preparation of procurement plans and the projection of contract awards and disbursements. project cycle stage: Design, Implementation Procurement of technical equipment and materials. Lack of capacity to prepare bidding documents, evaluate bids, and monitor contract execution can significantly delay project implementation. Procuring technical equipment and materials - notably natural science laboratory equipment, didactic books for TTIs (teacher training institutes), and ICT (information and communication technology) learning objects - proved particularly challenging under the ESRP (Education Sector Reform Project). Careful capacity assessment and planning can prevent procurement delays arising from capacity constraints. project cycle stage: Appraisal, Implementation | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/education-sector-reform-project-pcr
Customs Modernization Project: Validation of Completion Report | Mongolia | Industry and Trade | 2015-02-10 | The PCR (project completion report) identified a few important lessons from the project. Reengineering of business processes should be aligned with international standards to maximize harmonization of customs procedures across borders and to facilitate international trade. The setting up of task forces comprising experienced staff from the executing and implementing agencies and from other pertinent agencies proved effective in reengineering the business processes. Proactive engagement with the private sector, particularly with the trading community, helps ensure buy-in of the reengineered business processes and user-friendliness of the system. This validation holds similar views with these lessons and has no other lesson to offer. project cycle stage: Implementation, Operation | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/mongolia-customs-modernization-project
Updating the Energy Sector Development Plan: Technical Assistance Completion Report | Mongolia | Energy | 2015-02-01 | Two main lessons were learned from the TA (technical assistance). First, the executing and implementing agencies' understanding on ADB's guidelines and consultant selection process are essential for smooth TA implementation. Lack of understanding on these critical implementation issues resulted in prolonged contract negotiation and delayed mobilization. Second, possible risk in the government change and likely restructuring should be factored in the implementation schedule to avoid likely set- back during the TA implementation. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/updating-energy-sector-development-plan-technical-assistance-completion-report
Education for the Poor - Financial Crisis Response Project | Mongolia | Education | 2014-08-01 | Strong government commitment to the education sector and the strategic leadership of the Ministry of Education and Science (MEDS), backed by a highly capable project implementation unit, were important for keeping the project on track. Their commitment and policy oversight ensured that the findings and recommendations from implementation and from the studies supported under the project were considered in the formulation of evidence-based policy. Having a project implementation unit that was well equipped with qualified, experienced staff also contributed to efficient project management and implementation. Training on disbursement and procurement procedures early on could help prevent deviation from appropriate institutional procedures. The emphasis on capacity building helped to strengthen capacity for planning, implementation, and monitoring at the central, provincial, soum, village, and school levels. Stronger capacity ensured timely implementation and also contributed to greater awareness of the long-term impact of education sector programs. The studies under the project provided extremely useful insights into international best practices, raised issues about implementation, and made policy recommendations for consideration by the MEDS. The project implementation unit ensured that for each study, the draft findings were shared at a policy workshop that included MEDS officials and other stakeholders. Having these workshops built into the project design was very useful. This approach has helped to create a better education policy for Mongolia, one based on evidence and practical experience. Selection of a consulting consortium that consisted of professional education institutions, both national and international, proved to be very effective in providing guidance on international best practices while aptly assessing local conditions so as to make assessments and recommendations. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/education-poor-financial-crisis-response-project-mongolia-pcr
Customs Modernization Project | Mongolia | Industry and trade | 2014-03-01 | Implementing a customs modernization program entails efforts by not only the customs authority, but also various other government agencies involved in regulating international trade. Strengthening interagency coordination for policy consistency and harmonization is a key to success. Business process reengineering, which is at the core of customs reform, must be conducted in line with international standards, particularly the World Customs Organization's Revised Kyoto Convention. This will maximize harmonization of customs procedures across borders in the interest of facilitating international trade. Ownership by the borrower, particularly the implementing agency, is critical to successful implementation. An efficient project management office with dedicated staff and supported by experienced international and national consultants plays an indispensable role in project implementation. Setting up task forces with experienced and motivated staff from the executing and implementing agencies, as well as staff from other government agencies depending on the nature of tasks, proved effective in executing tasks related to business process reengineering, which is both policy oriented and technical in nature, or to testing and accepting customs automated information system, which relied heavily on ICT. For customs modernization projects with high ICT content, a pilot operation period of at least 1 year needs to be included at appraisal. This will give system developers and project designers a chance to factor in user feedback before final acceptance. Proactive engagement with the private sector helps ensure effectiveness of business process reengineering, improve system user-friendliness, and facilitate acceptance by the trade community. Close donor coordination will ensure that project activities are implemented in a synchronized manner. For ICT-related projects, attracting and retaining high-caliber engineers is a challenge and requires special solutions, e.g., designing special incentive packages. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/customs-modernization-project-pcr
Social Sectors Support Program | Mongolia | Education, Health, Finance, Public Sector Management, Water and other urban infrastructure and services | 2013-01-03 | 1. There is a need for sustained engagement in social protection. The enduring relevance of the Social Sectors Support Program, which has continued after the financial crisis, underlines the importance of the key objective of ADB's Social Protection Strategy to build social protection systems in non-crisis years and its emphasis that such a system should not be based on a oneoff response to a crisis. Sustained engagement in policy dialogue in non-crisis years is critical to building demand for social protection beyond the crisis response. This engagement sustains political support in non-crisis years, especially when it is part of ADB's inclusive growth agenda. project cycle stage: Lesson Topics: 2. By underpinning some of the most important policy issues in the social sector, the Social Sectors Support Program (SSSP) maintained ADB's position at the center of social sector policy reform in Mongolia. Further modernization of the social protection system, including wider and better use of targeting, will require continuous external technical and capacity development support to strengthen institutions and human resources. The SSSP also created the scope to (i) jump-start ADB's partnership with the new government elected in July 2012 by expanding on the SSSP policy reform measures, (ii) build on ADB's long track record in the social sector, and (iii) sustain the strong collaborative links with development partners that the SSSP reinforced. project cycle stage: Lesson Topics: 3. Even in the context of a crisis situation, the 20 months allowed at appraisal for the Social Sectors Support Program's (SSSP) implementation was inadequate, particularly for achieving the technically and politically challenging goals of social welfare targeting and consolidation. A reform process in this area tends to be protracted and highly contentious - a fact that was established by the Social Security Sector Development Program (2002-2009) and reconfirmed by the SSSP. An enormous amount of time and resources were needed to establish the proxy means test and the intersector database, especially in an environment where resistance to reforms and reluctance to shift from categorical targeting were strong. When designing future programs to reform social protection in Mongolia, ADB will need to conduct a deeper analysis of the potential obstacles and consider making implementation periods longer to adjust to them. project cycle stage: Lesson Topics: 4. The technical assistance (TA) attached to the program proved to be crucial to achieving the policy reforms. The TA inputs ensured the technical quality and overall sustainability of the policy measures and contributed significantly to the success of the program. The experience points to the need to back up program loans with strong technical assistance. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/social-sectors-support-program-pcr
Third Education Development Project | Mongolia | Education | 2012-09-01 | The Third Education Development Project (TEDP) was the first ADB-financed investment project to include a technical and vocational education and training (TVET) component. The original project design envisaged the development of a TVET policy framework, as well as the development of training standards and a national vocational qualifications framework. After the reformulation of component 3, ADB concentrated mainly on upgrading the six model TVET schools on a pilot basis, while Millennium Challenge Corporation (MCC)/Millennium Challenge Account (MCA) and Deutsche Gesellschaft fu?r Internationale Zusammenarbeit (GIZ) took the lead under their respective projects in developing a TVET policy framework. The project underscores the importance of continued and strengthened harmonization and coordination among the development partners through the Education Donors' Consultative Mechanism platform, established in 2005. As a long-term development partner in Mongolia's education sector, ADB is well positioned to contribute to policy development in TVET. Another lesson learned from the project is that management training and staff development must be provided and that TVET schools must be helped to strengthen their links with industry, in addition to upgrading the learning environments in TVET schools. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/third-education-development-project-pcr
Third Education Development Project | Mongolia | Education | 2012-03-09 | 1. The Third Education Development Project was the first ADB-financed investment project to include a technical and vocational education and training (TVET) component. The original project design envisaged the development of a TVET policy framework, as well as the development of training standards and a national vocational qualifications framework. After the reformulation of component 3, ADB concentrated mainly on upgrading the six model TVET schools on a pilot basis, while the Millennium Challenge Corporation/ Millennium Challenge Account and the Deutsche Gesellschaft fï¿½r Internationale Zusammenarbeit took the lead under their respective projects in developing a TVET policy framework. The project underscores the importance of continued and strengthened harmonization and coordination among the development partners through the Education Donors' Consultative Mechanism platform, established in 2005. As a long-term development partner in Mongolia's education sector, ADB is well positioned to contribute to policy development in TVET. [Main text, para. 47] project cycle stage: Lesson Topics: 2. Based on project experience, management training and staff development must be provided and that technical and vocational education and training (TVET) schools must be helped to strengthen their links with industry, in addition to upgrading the learning environments in TVET schools. [Main text, para. 47] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-education-development-project-pcr
Mongolia: Integrated Development of Basic Urban Services in Provincial Towns Project | Mongolia | Energy, Water and Other Urban Infrastructure and Services | 2011-12-31 | 1. A thorough analysis of beneficiary preference, demand, and willingness to pay needs to be conducted to ensure that preconceived notions on demand are verified, validated, and confirmed on the ground by the beneficiaries. Very often proponents from the central government have a different concept of needs and priorities from agencies at the field or local level. Local involvement in project conceptualization ensures greater success, as there would be better ownership of its components and a more accurate identification of the needs of intended beneficiaries. Additional gains will be made through greater commitment for sustained operation and maintenance and more accurate assessment of willingness to borrow. [Main text, para. 22] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Methodologies/Approaches: Consultation/Participation | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/mongolia-integrated-development-basic-urban-services-provincial-towns-project
Financial Regulation and Governance Program | Mongolia | Finance | 2011-12-01 | The evaluation offers some lessons regarding the need to (i) properly adapt the scope and time frame of comprehensive and sensitive policy reforms to institutional capacity, (ii) carefully sequence reforms, and (iii) take a long-term approach to development. Developing capital markets is a long-term process, for which 10-20 years may be considered a realistic time frame. Capital market reform should focus on a limited set of highly selective and sequenced reforms that are within reach of government implementation capacity. Rather than focusing capital market reforms on very ambitious final outcomes. In general, it is proposed that program loans should either not include highly complex and far-reaching policy reforms or build on enhanced policy dialogue, comprehensive technical assistance, and intensive monitoring and review by ADB. Lack of technical understanding on the part of political decision makers requires support for comprehensive and consistent advisory technical assistance throughout the drafting and approval process of new legislation. Corrective action regarding the scope and implementation arrangements of a program should be considered at an early stage if implementation falls behind schedule and/or government capacity, ownership, and commitment shows signs of receding. The provision of technical assistance (TA) should match the scope of targeted policy reforms and the capacity of implementing agencies. In addition, it appears from the evaluation of the program that ADB's great reliance on TA consultants to develop much of its policy and advisory input affects its ability to develop sustainable internal capacity on policy issues. It has thereby reduced ADB's ability to quickly respond to government requests for policy advice and to engage in long-term dialogue. To improve ADB's processing and supervision of complex program loansï¿½particularly those that entail policy reforms, development of new laws and/or amendment of existing laws, and human resource and institutional development elementsï¿½sufficient supervision budgets, staff skills, and staff incentives should be ensured. Ideally, staff should be given incentives and enabled to maintain their program supervision roles for longer periods, thereby improving program implementation. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/financial-regulation-and-governance-program
Second Phase of the Governance Reform Program | Mongolia | Public sector management | 2011-12-01 | The evaluation offers lessons regarding the need to properly adapt the scope and time frame of reforms to institutional capacity and to sequence reforms. Budget reform should be regarded as an evolving process and should focus on a more limited set of reforms that are within the reach of government institutions. Organisation for Economic Co-operation and Development (OECD)-type budget systems in developing countries and emerging markets must be based on a solid platform of financial management (the micro basis of broader budget system reform) within Ministry of Finance (MOF), line ministries, and other government agencies. In Mongolia as well as many other developing countries, this aspect of public financial management (PFM) reform has proved to be particularly problematic. Reforming PFM systems is a long-term process, for which a time frame of 15-25 years is often considered realistic. In general, program loans should either exclude highly complex and far-reaching policy reforms or build on intensive policy dialogue and enhanced monitoring and review by ADB. Corrective action regarding the scope and implementation arrangements of the program should be considered at an early stage if implementation is observed to fall behind schedule or government capacity, ownership, and commitment show signs of receding. To improve ADB's processing and supervision of complex program loansï¿½particularly those that entail policy reforms, development of legislation, and human resource and institutional developmentï¿½strong in-house specialist expertise, instead of predominant reliance of consultants, should be ensured, in particular sufficient provision of budget for supervision and staff skills. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/second-phase-governance-reform-program
Mongolia: Rural Finance Project [Loan 1848-MON] | Mongolia | Finance | 2010-12-31 | 1. There is a need to lay down a firm legal, regulatory, and supervisory foundation prior to embarking on promotion of financing institutions, such as savings and credit cooperatives (SCCs). In this case, ADB attempted to establish the regulatory structure in parallel to project implementation, which did not work well. The two activities should have been better prepared, and sequenced as separate projects. The regulatory structure should have been supported by a comprehensive technical assistance with adequate resources to prepare and promote the legal, regulatory, and supervisory framework, to have it passed by the legislature, and to ensure adequate institutional capacity to execute that framework. With the regulatory structure in place, the implementation should have proceeded with components for training, promotion, and institution development of SCCs. That approach would have had better prospects for success in establishing a sustainable rural finance system. [Main text, page 6, section E(ii.a)] project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Policy & Reform: Policy reforms/framework Policy & Reform: Reform 2. There is a need to enhance the capacity of ADB staff to quickly assess changing project circumstances and adjust project parameters to ensure greater use of ADB loan funds and better attainment of project objectives. [Main text, page 6, section E(ii.b)] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Project Management: Project management Capacity Development: Capacity building | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/mongolia-rural-finance-project-loan-1848-mon
Second Health Sector Development Project | Mongolia | Health | 2010-12-01 | Policy reforms should not be too numerous and should be well integrated into an overall project. Highest priority should be given to policy reforms (and covenants) that are necessary for project implementation or sustainability. A stakeholder analysis should be conducted for all proposed policy reforms, and a strategy developed for moving systematically to the desired policy reform reflected in the project's design and monitoring framework. Means of compensating the losers should be identified (e.g., by including project investments in institutions adversely affected by policy reforms). Progress toward achievement of policy reforms needs to be monitored carefully. The need to strictly adhere to the guidelines for the design and monitoring framework to ensure the participatory formulation of achievable objectives backed by relevant activities is a major lesson from this project. Lessons from the irregularities with civil works in Zavhan aimag are the need to (i) provide external monitoring of civil works in addition to regular monitoring by MOH and various statutory inspection bodies (ADB has organized external monitoring for subsequent projects in the health sector), and (ii) strengthen the bid evaluation capacity of MOH (the weak capacity of some of the firms involved in irregularities could have been detected at an early stage). The relationship between MOH and the PIU needed to be discussed from the beginning of the project. This would have avoided the PIU isolating itself from the Ministry of Health's (MOH) decision-making process, as happened too often during the first 2 years of implementation. Decision-making procedures need to be clarified to involve MOH departments and higher authorities in decisions affecting bidding processes, consultant selection and outputs, policy matters, and resource allocation in the health sector. This requires setting up working groups within MOH and ensuring decisions are made by higher bodies and authorities of MOH. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/second-health-sector-development-project
Social Security Sector Development Program | Mongolia | Finance, Public sector management | 2010-12-01 | Targeting. Social welfare reform is a sensitive and protracted process. The Social Security Sector Development Program (SSSDP) pioneered new concepts and approaches at a critical time in the country s history, but the reforms it initiated are not complete. The progress made by the program in developing a new vision for social welfare was undermined by the introduction of universal benefits. New efforts at introducing proxy means test (PMT) under the Food and Nutrition Social Welfare Program and Project (FNSWPP), are attempting to help ensure that the reform agenda is sustained. The Draft Social Welfare Law of 2010 will be another measure of how far the reforms are accepted. Livelihood support councils. As part of the reforms pioneered by the project, the government introduced livelihood support councils. The councils clearly have an important contribution to make and have the legal mandate to do so. However, there is uncertainty as to how effective they are nationally and what is the full range of their responsibilities. A national assessment of the strengths and weaknesses of the councils is urgently needed. Updating the social security sector strategy paper. The Social Security Sector Strategy Paper (SSSSP) was a major milestone and the document is still a valuable guide for the sector. There is a need to update it, and this should be a priority once key decisions have been made regarding the proposed consolidation and targeting of benefits. Use of information, education, and communication. The SSSDP conducted an intensive information, education, and communication campaign to garner support among the public and politicians for the reforms. As Mongolia enters a new period of reform that may result in the introduction of a national PMT, it is vital that a new information, education, and communication campaign is put in place and sustained. Increasing roles for nongovernment organizations. The SSSDP brought civil society into social welfare provision for the first time in Mongolia. The role of nongovernment organizations (NGOs) can be expanded in the areas of monitoring of policy implementation, service, and advocacy for reforms. Civil registration. The SSSDP failed to explicitly address a fundamental weakness in the social welfare system: the systematic exclusion of unregistered households. Efforts to overcome this flaw need to be accelerated. Creating incentives at vocational training centers. The investment in training and workshop equipment has helped the vocational training centers to generate income. This income could provide a sustainable fund for equipment replacement and student scholarships. Improving the impact of business incubation centers. The impact of the centers could be furthered by (i) providing start-up loans and performance-based support, (ii) providing better outreach to remote areas, and (iii) developing business incubation center packages that better target the livestock development needs of herders. Social insurance. The State Social Insurance General Office (SSIGO) made considerable progress in improving its technical capacity under the project. It is likely that even greater progress would have been made had the office been given greater autonomy and more involvement in policy making. Monitoring and evaluation. The project did not have an adequate monitoring and evaluation (M&E) system. Analysis on gender and socioeconomic impacts are not available because of a lack of collection and disaggregation of data. The limited capacity of the M&E unit needs to be addressed if the impacts of future reform initiatives are to be properly assessed. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/social-security-sector-development-program
Integrated Development of Basic Urban Services in Provincial Towns Project | Mongolia | Energy, Water and other urban infrastructure and services | 2010-10-01 | Institutional weakness has been a key constraint to timely and efficient project execution and to long-term sustainability of newly created assets. Local capacity constraints were exacerbated by a centralized system of governance, management and decision making. Local infrastructure investments remain largely at the discretion of the central government and local officials lack the budgetary and human resources or skills to maintain assets and to effectively respond to the constituents' needs. The incentives and resources for local governments to strengthen services are limited. The project's implementation arrangements, which vested almost all responsibility for implementation at the central level, may have contributed to these weaknesses. The project would have benefited from greater local involvement in project planning, design and implementation, and by addressing local capacity constraints and incentives for quality service provision. The project had only limited, uneven success in raising tariffs, resulting in underfunding of operation and maintenance (O&M). This raises the need for wider institutional and policy reform. The support of ADB and other development partners has focused on helping the government to rebuild assets but has placed less emphasis on building the institutions and systems required to ensure these assets are maintained and used efficiently. Given the acute needs for infrastructure rehabilitation and expansion in urban areas in the 1990s, this emphasis on infrastructure provision was understandable. Today Mongolia lags behind other former socialist countries in institutional reform and strengthening and risks wasting resources on infrastructure that it cannot maintain and manage properly. While the project addressed this issue, it placed insufficient emphasis on delineating the functions of the aimag governments and the public urban service organizations (PUSOs) and on strengthening lines of accountability for delegated service provision. The issue of tariffs is complicated by (i) the high cost of servicing in some areas, particularly the ger area settlements; and (ii) the government's willingness to subsidize service tariffs. The project supported a dialogue between ADB and the government around urban service reform, tariff issues, the application and targeting of government subsidies, and the development of more transparent, efficient and equitable mechanisms for directing such subsidies in public services. Lessons learned indicate the need for (i) detailed project formulation during the project preparatory stage, (ii) adoption of simple and affordable technologies in construction and facility improvements, and (iii) parallel provision of institutional development and training during project implementation. It is vital that relevant institutions and beneficiaries at the local level are fully involved in all stages of project preparation, design and construction. Measurement of sector performance and progress in achieving urban economic development and improved service provision, including in those areas specifically related to the Millennium Development Goals and the National Development Strategy, is compromised by an absence of disaggregated data and a lack of clear and measurable indicators. The project did not include monitoring of a set of clear indicators for which data is available or can be readily obtained. Better analysis of existing information and trends is required at preparation and greater attention needs to be paid to the development of a robust baseline and measurement and evaluation of outputs, outcomes and benefits. Certain lessons have already been incorporated in The Southeast Gobi project, which was approved in April 2010. In contrast with L1907, aimags have primary responsibility for the design and construction of infrastructure, including procurement and oversight of construction supervision. Design and build contracts aim to avoid technical problems at the design stage and shorten the period required for completion of works. The Southeast Gobi project also supports a reform process in which tariffs are set through a tender process in which firms compete for the right to manage service provision. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/integrated-development-basic-urban-services-provincial-towns-project
Cadastral Survey and Land Registration Project | Mongolia | Agriculture, Natural Resources, and Rural Development | 2010-01-12 | 1. Mongolia is a large country with a small population and limited technical capacity. The project represented a major change to existing practices in institutions with few technical resources and limited technical capacity. In future interventions of this type, greater emphasis should be placed on measures to build technical and management capacity in the executing, implementing, and end-user institutions. Due to ADB's flexibility in adjusting implementation arrangements, implementation was not negatively impacted, despite institutional changes during the initial years of the project. project cycle stage: Lesson Topics: 2. Elements of the project were technically complex. While the technical assistance consultants did a good job of specifying the system requirements, there were insufficient resources to fully familiarize the client with the technical approach, and to moderate requests for system enhancements. As a result, there was a communication gap between the client and the National Land Information System (NLIS) contractor, which ultimately resulted in the system design moving away from the structure originally specified. Additional technical resources would have mitigated, and might have avoided, this situation. ADB's midterm review suggested that a third-party review of the NLIS design be carried out. This was not taken up although it might have resulted in a better outcome. project cycle stage: Lesson Topics: 3. The level of complexity of the National Land Information System (NLIS) was also a challenge for ADB. While the technical assistance consultant provided useful reporting and briefing notes, the consultant and ADB were unable to prevent delays that resulted from the negotiations between the executing agency and contractor. More technical support during NLIS design could have helped. project cycle stage: Lesson Topics: 4. In designing the National Land Information System, more attention could have been paid to the external constraints likely to impact negatively on the system (such as power and connectivity constraints). A more incremental approach to system development might have been more appropriate, with complexity added as external infrastructure improved. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/cadastral-survey-and-land-registration-project
Second Health Sector Development Project | Mongolia | Health | 2010-01-12 | 1. Policy reforms should not be too numerous and should be well integrated into an overall project. Highest priority should be given to policy reforms (and covenants) that are necessary for project implementation or sustainability. A stakeholder analysis should be conducted for all proposed policy reforms, and a strategy developed for moving systematically to the desired policy reform reflected in the project's design and monitoring framework. Means of compensating the losers should be identified (e.g., by including project investments in institutions adversely affected by policy reforms). Progress toward achievement of policy reforms needs to be monitored carefully. The need to strictly adhere to the guidelines for the design and monitoring framework to ensure the participatory formulation of achievable objectives backed by relevant activities is a major lesson from this project. project cycle stage: Lesson Topics: 2. Lessons from the irregularities with civil works in Zavhan aimag are the need to (i) provide external monitoring of civil works in addition to regular monitoring by Ministry of Health (MOH) and various statutory inspection bodies (ADB has organized external monitoring for subsequent projects in the health sector),40 and (ii) strengthen the bid evaluation capacity of MOH (the weak capacity of some of the firms involved in irregularities could have been detected at an early stage). project cycle stage: Lesson Topics: 3. The relationship between Ministry of Health (MOH) and the project implementation unit needed to be discussed from the beginning of the project. This would have avoided the PIU isolating itself from MOH's decision-making process, as happened too often during the first 2 years of implementation. Decision-making procedures need to be clarified to involve MOH departments and higher authorities in decisions affecting bidding processes, consultant selection and outputs, policy matters, and resource allocation in the health sector. This requires setting up working groups within MOH and ensuring decisions are made by higher bodies and authorities of MOH. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-health-sector-development-project
Second Education Development Project | Mongolia | Education | 2009-11-12 | 1. A systematic approach to education development can further facilitate successful project implementation. The Project's design and its objectives were closely tied with Education Sector Master Plan 2006-2015, which enabled the Second Education Development Project to support major government initiatives in the education sector. The Government's strong commitment to Second Education Development Project objectives was an important enabling factor for all project activities. Advocacy on the importance of project interventions to the overall education system reform is necessary for the project management unit staff. Project management unit staff members need to enhance their understanding as to how their work contributes to the broader scope of education policy and planning by the Ministry of Education, Culture and Science. [Main text, paras. 16,31,32,42,43,50] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Education Policy & Reform: Information dissemination/Public awareness 2. Enhancing the design of project interventions requires a thorough feasibility analysis, consultation process, and when necessary, pilot testing. This could have avoided implementation of an ineffective design for the textbook rental scheme and could have identified early on, the effects of liberalizing textbook production on project targets. [Main text, paras. 14,15,52] project cycle stage: Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity development 3. In ensuring the project's financial sustainability, it is necessary to strengthen financial management and bolster budgeting capacity at the school level. Operational budgets at school level are inadequate for information communication and technology (ICT) investments and for rehabilitated schools' operation and maintenance. The current economic situation in Mongolia compounds the issue of operation and maintenance budgets for ICT and capital investments. [Main text, paras. 45,54] project cycle stage: Design, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Project Management: Project management ADB's closer monitoring and supervision of project M&E activities would have strengthened compliance with the covenant on project implementation monitoring. Further, if the expected outputs of policy reform take longer than the project implementation period, immediate objectives expected during completion should be set out separately from long-term goals. Broad education indicators (e.g., net enrollment ratio, dropout rates) can be attributed to several factors, and the development of projectspecific indicators should be strengthened. In addition, Ministry of Education, Culture and Science staff reported that training received in M&E was insufficient given the complexity of this function and continuous changes in the education system. Continuous training in M&E needs to be adapted to the context of project information needs and existing M&E procedures and processes. Finally, collection of data for education indicators must be improved and a national achievement test must be reintroduced to allow the Government and donors to evaluate the impact of project activities on learning outcomes. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-education-development-project
Country Assistance Program Evaluation for Mongolia: From Transition to Takeoff (2008) | Mongolia |  | 2008-09-30 | 1. There are numerous areas in which ADB did add value over and above the financing provided. The use of program lending to support reform in the areas of governance and social protection, the introduction of a sector development program in education, and the approach adopted for reforming the health sector were new to ADB during the evaluation period. ADB policy dialogue and a corporate policy of staying the course when reforms ran into opposition helped maintain forward momentum. ADB's role as a neutral broker in the Central Asia Regional Economic Cooperation (CAREC) has allowed Mongolia to negotiate on equal terms with its much larger neighboring economies and to build the trust and confidence required to tackle problems regionally. While fostering aid coordination has been difficult, ADB has stayed the course, and there are encouraging signs that support to the social sector can evolve into a platform for more harmonized sector-wide assistance approaches. [Main text, paras. 87-88, 107-108; Appendix 6] project cycle stage: Design, Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Regional cooperation Crosscutting Issues/Themes: Social protection Finance & Financial Aspects: Financing Modality: Policy-based lending Policy & Reform: Reform Methodologies/Approaches: Policy dialogue 2. Across the program, performance was best when (i) a thorough sector diagnostic informed the preparation of assistance initiatives, (ii) there was sustained high-level support from the Government and Parliament for agreed reforms, and (iii) the Government had both the capacity and the willingness to fully implement agreed policy and institutional reforms. At the project level, designs that were simple had superior outcomes. Capacity-development efforts have been the most successful in those institutions, such as the National Statistical Office and Bank of Mongolia, that have managed to retain skilled staff. [Main text, paras. 38, 80, 105, 109] project cycle stage: Concept, Design, Feasibility, Appraisal, Implementation, Completion Lesson Topics: Project Design: Project design Capacity Development: Capacity development Capacity Development: Human resources management Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Policy dialogue Methodologies/Approaches: Program Approach 3. A mix of indirect and targeted interventions to augment human resources, enhance living conditions, and provide better access to services was an appropriate strategy for addressing poverty in Mongolia. ADB's main contribution to poverty reduction was indirect, through support for establishing a market economy, restoring fiscal stability, enhancing Mongolia's connections to regional and global markets, and fostering a process of private sector-led growth and employment creation. Starting in the late 1990s, poverty reduction was woven into the design of ADB assistance, as the assistance focus shifted to fostering inclusive growth and social development. This led to its focus on non-income poverty determinants, through support for improving the quality of health and education services to the poor, providing basic urban services in provincial cities, and assisting poor farmers in western Mongolia. In addition, Japan Fund for Poverty Reduction (JFPR) grants have played an important role in pilot-testing innovative approaches to service delivery in the urban ger and remote rural communities. [Main text, paras. 82-90, 119] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Regional cooperation Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Urban sector/development Methodologies/Approaches: Pilot project 4. A more focused results framework with specific indicators in the country strategy and program (CSP) would have been more useful in tracking the progress of ADB operations. In Mongolia, a results framework was included in its CSP for 2006 2008, but tracking results has proved to be difficult because of the large number of qualitative targets and indicators, weak connection between the expected results of ADB support and national goals and objectives, and lack of full awareness and institutional capacity within the government. [Executive summary; Main text, paras. 68(vii), 122, 123] project cycle stage: Concept, Design, Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Capacity Development: Institutional analysis Capacity Development: Ownership 5. More careful diagnostics at the onset might have resulted in a more measured approach to reforming public sector management. ADB support to restore fiscal stability and enhance budgetary control has been successful in Mongolia; however, succeeding public administration reforms (which adopted the New Zealand approach) had mixed results given the advanced nature of the law as well as the lack of capacity to implement these reforms. [Executive summary; Main text, paras. 103, 124] project cycle stage: Concept, Design, Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity assessment Capacity Development: Institutional analysis Policy & Reform: Public sector reform Policy & Reform: Reform Methodologies/Approaches: Participatory approach 6. ADB provided assistance to help the Government introduce many new laws. These were often drafted under considerable time pressure and often drew on international best practices. Once new laws were adopted, ADB then provided support to help build the institutions that would put them in place. In some instances, this was successful, but in many cases it left institutions with large capacity gaps. A highly fragmented TA effort temporarily plugged a number of these gaps and relied excessively on building capacity by training officials, many of whom have moved on. In retrospect, a more systematic approach to Capacity Development, pilot-testing institutional innovations, and developing new laws within the Mongolian legal tradition could have been more effective. [Main text, paras. 50, 56, 93, 125] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Legal system Modality: Technical Assistance Project Design: Appraisal Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Institutional analysis Methodologies/Approaches: Program Approach 7. Strategic focus and sector selectivity could have further improved portfolio performance in Mongolia. During the country assessment period, ADB's resources became stretched over a large number of regions, subsectors, institutions, and themes, losing strategic focus and steadily raising aid transaction costs. Within its sectors of operation, ADB obtained some strategic focus with the CSP for 2006 2008, but new initiatives in energy and the environment added to the complexity of the program in 2007 and 2008. The shift from a heavy emphasis on program lending in the 1980s and early 1990s to investment operations in the past decade was associated with a marked deterioration in portfolio performance, manifested primarily in substantial project start-up and initial implementation delays. [Executive summary; Main text, paras. 112, 126] project cycle stage: Operation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Modality: Project Modality: Technical Assistance Project Management: Project supervision 8. More attention to long-term public investment efficiency would have boosted long-term program returns and served to help discipline the process of public sector investment planning. The imperative of supporting a rapid transition from central planning to a market economy to cope with the fallout from the Asian financial crisis and reverse the long decline in economic performance meant that many operations were launched on the basis of a sector needs assessment and strategy, rather than on a thorough assessment of the long-term economic viability of the services created. For instance, district heating, urban water, sewerage, and sanitation services were rehabilitated before a tariff structure was put in place to sustain them. Major sections of the north south highway were constructed before there was sufficient financial and institutional capacity for maintaining it and ensuring that goods and people could flow quickly over borders. New schools and health posts were developed in remote rural areas while communities were rapidly migrating to urban centers. In an effort to be as responsive as possible, ADB assistance was designed and delivered sector by sector, and projects were spread nationwide, limiting scope for cross-sector synergies or regional economies of scale. [Executive summary, Main text, paras. 127-128] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Project Design: Appraisal Capacity Development: Capacity assessment Capacity Development: Institutional analysis Country Context: Transition Methodologies/Approaches: Sectoral approach Methodologies/Approaches: Targeting 9. ADB has had some success in leveraging its limited resources to mobilize funding from other development partners, particularly in education. It has had substantially less success in fostering harmonized assistance approaches; building country systems to lead sector development; collaborating in portfolio management, sector analysis, or country strategy development; or partnering effectively to build institutional capacity in critical areas. In the long run, building the country systems so that the Government can utilize external resources more effectively will require deeper cooperation among the country's development assistance partners. [Executive summary; Main text, paras. 42, 130] project cycle stage: Concept, Design, Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Funding Capacity Development: Capacity development Capacity Development: Ownership | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-mongolia-transition-takeoff-2008
Roads Development Project (Loan 1364-MON[SF]) | Mongolia | Transport | 2007-12-31 | 1. From a strategic perspective, ADB had appropriately chosen the Ulaanbaatar Altanbulag road for improvement taking into account the benefits of regional cooperation and trade with the Russian Federation. This has continued in two subsequent projects, which aimed at improving the link with the PRC. ADB needs to continue along these lines and expand its project selection criteria to include regional benefits in addition to the national benefits. [Main text, para. 93] project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Project Design: Appraisal Sector Related Issues: Industry and Trade ADB needs to ensure that adequate project preparation, inparticular good quality feasibility studies, are conducted before loans are processed.Compromising on the detail and length of the feasibility study could result in implementationissues and time and cost overruns. project cycle stage: Feasibility Lesson Topics: Funding of road projects has been ADB s comparative assistance advantage in the past. However, there isa need for ADB to add better value for Mongolia by bringing in innovative practices and ideas forimproving the road network and institutional capacity. Innovative approaches could be adoptedin several areas (para. 86), and lessons from other countries could be used with appropriatecognizance to the local context. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Roading | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/roads-development-project-loan-1364-monsf
Second Financial Sector Program | Mongolia |  | 2005-07-15 | A good policy measure might not generate a positive impact without support from other policy measures, and might evengenerate a negative impact in some parts of the country unless it provides for adequate countermeasures or exceptions. Therefore, in any country, introducing a new policy measure requires careful consideration of merits and demerits, close consultation with stakeholders, and the adoption of necessary support and countermeasures and exceptions. This holds true as well in the case of the policy conditions of a program loan. However, it is not realistic to expect the policy matrix to include all the necessary support and countermeasures, since negative backlash and the need for exceptions often arise only when the details of a policy measure become clear. Therefore, the government agencies responsible for implementing a policy condition should be encouraged to proactively consult with various stakeholders to arrive at the necessary support and counter-measures. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation Policy distortions need to be eliminated. Despite the efforts to develop the capital markets and the actual progress made, the volume of capital markets transactions declined instead of growing during the program period. An important reason is the existence of policy distortions that have discouraged companies from seeking a listing on the stock exchange, and the public from investing in corporate shares. For example, unequal tax treatment - capital gains on stock market investments are subject to normal income tax (up to 30%), while bank deposits are subject to withholding tax of 15% and interest earned on government bonds is nontaxable - not only discourages the public from investing in stocks but also discourages the listing of companies. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Policy & Reform: Policy reforms/framework The proper implementation of new insurance laws and regulations requires strengthened supervisory capacity. A consolidated supervisory authority for the non-bank financial (NBF) sector would make more efficient use of the scarce human and budgetary resources and maximize supervisory effectiveness. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Capacity Development: Capacity building Capacity Development: Human resources management Policy & Reform: Policy reforms/framework There is a need for a well-considered privatization policy and strategy to develop the capital markets. Another reason for the underdevelopment of the stock markets is the failure to use the stock exchange to privatize state-owned enterprises (SOEs). Although the Second Financial Sector Program prompted the State Property Committee (SPC) to sell shares from the privatization of SOEs through the Mongolian Stock Exchange (MSE) by setting a numerical target (MNT200 million annually), most of the shares were sold through private tenders and auctions during the program period since SPC stood to earn more through these than through MSE, at least in the short run. Therefore, it is crucial to bring the perspectives of capital market development into the process of establishing a privatization strategy that identifies the enterprises that are suitable for privatization through MSE and those that should be privatized through other means. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financing Modality: Program Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Methodologies/Approaches: Targeting There should be more focus on achieving objectives rather than technical compliance. Although most of the policy conditions were technically met, compliance did not always lead to the expected results. In some cases draft laws and regulations were not passed or their passage was significantly delayed; while in other cases, the legislation was later reversed by other legislation. The reasons for these unsatisfactory outcomes varied, but one common characteristic was their focus on technical compliance coupled with a fundamental inability to achieve their larger objective on a sustainable basis. During implementation, more focus needs to be put on consultations with various stakeholders including parliament members to convince them of the need for the legislation and get their agreement, to minimize the likelihood that the law is not passed or that passage of law is reversed by other legislation. In case a numerical threshold has to be set, the level should be carefully chosen to maximize the positive impact and minimize the negative, rather than being considered as a mere target in the policy matrix. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-financial-sector-program
Health Sector Development Program | Mongolia | Health | 2004-09-15 | The Health Sector Development Program (HSDP) was the first loan program for the Ministry of Health (MOH). At the outset MOH counterparts and project implementing unit (PIU) staff were unfamiliar with ADB's operational procedures and guidelines. Initially, the HSDP required intensive ADB supervisory contacts and review missions. However, PIU staff quickly learned the necessary procedures, oriented and administered project implementation effectively, facilitated policy dialogue with the government, and became a reliable partner. The PIU also facilitated close working relationships between MOH, PIU, and consultants, which was essential to successful implementation of the HSDP. project cycle stage: Appraisal Implementation Lesson Topics: Modality: Program Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Project Management: Project supervision Sector Related Issues: Health and sanitation management Policy & Reform: Policy matrix Methodologies/Approaches: Consultation/Participation The Health Sector Development Program's (HSDP's) impact was difficult to evaluate in some areas because there were no baseline data on service use. Getting baseline data was ignored due to concentration on program or project implementation, and the monitoring system received little attention. While family group practice (FGP) services are broadly meeting expectations, a change in service use was not clearly shown by groups of people categorized by age, sex, and income. To measure equitable access, it is important to establish a basis for comparison and carefully monitor the utilization of services by the poor and vulnerable groups. In future projects, a system should be established in implementation to monitor and analyze outputs and achievements, in particular, those related to service use by different groups of people. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Vulnerable groups Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/health-sector-development-program-6
Education Sector Development Program | Mongolia | Education | 2003-12-15 | Donor coordination was relatively weak at appraisal. For instance, under the Education Sector Development Program (ESDP) the government enforced a moratorium on school construction while the school mapping study was on-going, while at the same time some other donors continued their own school construction projects. The introduction of clear sector policies and development strategies supported by the ESDP and related TAs provided a framework for more effective coordination during implementation. However, this shortcoming highlights the need for stronger donor coordinationand information sharing in future projects. project cycle stage: Appraisal Lesson Topics: Modality: Lending modality Modality: Program Modality: Technical Assistance Project Design: Appraisal Sector Related Issues: Education Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Sectoral approach Strong commitment by the government to the objectives of the Edcuation Sector Development Program (ESDP) was animportant enabling factor for the comprehensive policy reforms carried out under the program,including the rationalization of staff and schools. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Lending modality Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Education Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform The complementary nature of the policy reform program, the investment project, and the associated technical assistance (TA) were a key factor in the highly successful performance of the Education Sector Development Program (ESDP). The program and the project were mutually reinforcing in many key areas and the associated TA in related capacity building. This was the principal rationale for the adoption of the sector development program modality by ADB, and the ESDP provided the first practical application and validation of the sector development program approach. project cycle stage: Appraisal Lesson Topics: Modality: Lending modality Modality: Program Modality: Technical Assistance Capacity Development: Capacity building Sector Related Issues: Education Policy & Reform: Policy reforms/framework Methodologies/Approaches: Sectoral approach The Education Sector Development Program (ESDP) was the first loan program for the Ministry of Education, Culture and Science (MOECS), and at the outset MOECS counterparts and Project Implementation Unit (PIU) staff were unfamiliar with ADB's operational procedures and guidelines. The close working relationships between MOECS and PIU staff and consultants was essential to the successful implementation of the ESDP. In addition to formal training, routine operational contacts with consultants played an important role in developing the technical capabilities of MOECS counterparts and PIU staff. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Lending modality Modality: Program Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Capacity Development: Capacity building Sector Related Issues: Education The Education Sector Development Program's (ESDP's) impact was difficult to evaluate in some areas, because pertinent statistics and information were unavailable, partly because of geographical and technical reasons. For future projects, a system to gather and maintain data and statistics and to monitor and analyze outputs and achievements should be established at an early stage of implementation. project cycle stage: Implementation Lesson Topics: Modality: Lending modality Modality: Program Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/education-sector-development-program-4
Provincial Towns Basic Urban Services Project | Mongolia | Water and Other Urban Infrastructure and Services | 2003-03-14 | Any changes in loan consultants' terms of reference or contracts should beagreed in advance between the government, the consultants and ADB. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation Appraisal projections and assumptions for incremental water sold and revaluationof assets were relatively high. Future projects should ensure that projections arebased on realistic assumption of the financial capacity for sub-borrowers. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Sector Related Issues: Health and sanitation management As a result of capacity building training, public urban services organization (PUSO) staff were able to set water tariffsfor apartment residents and institutions according to business plans and the cost recoveryprinciple. The training increased the awareness among PUSO staff ofthe importance of regular adjustment of tariff schedules for the cost recovery,which should be taken as a good lesson for enhancing sustainability of similarfuture projects. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development At appraisal, the civil works in each project town were divided into four packages. This proved to be unrealistic, as the multiple contracts would have been difficult for the public urban services organizations (PUSOs) to manage. Closer involvement of PUSO staff in the planning and packaging of civil works would have helped to avoid the need for repackagingduring implementation. project cycle stage: Feasibility Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Procurement Project Management: Project management Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation The consultants contracted under the associated technical assistance (TA) worked with the executing agency (Ministry of Infrastructure or MOI), while the loan was implemented by Government Implementing Agency for Construction, UrbanDevelopment, and Public Utilities (GIACUDPU). This arrangement hampered coordination of inputs provided under the TA and the loan. A key lesson for future projects is to place both loan and associated TA project consulting services under onecounterpart agency, to ensure coordination and synchronization of implementation. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/provincial-towns-basic-urban-services-project
Energy Conservation Project | Mongolia | Energy | 2002-12-13 | The design of any project in Mongolia involving major construction activities should take into account Mongolia's harsh winter and relatively short summer which present a unique set of challenges, made worse by the limited number of consultants and contractors experienced in working under such climatic conditions. Logistics issues are equallychallenging, as Mongolia is land-locked and most items have to be transported overland through the People's Republic of China. Special arrangements for reducing the time for tax and customs-related processing must be addressed at the project design stage to avoid delays that might result in not being able to take full advantage of the short summer. Project related staffs are usually on fixed term contract that terminates immediately after project completion. The project implementation consultants are also difficult to trace. These can create a vacuum in project related knowledge even within the executing agency. Executing agencies lack financial skills and often their accounting systems may be different from international practices; careful consideration is required in developing effective action plans that are deliverable and measurable within the specified timeframe. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/energy-conservation-project
Governance Reform Program | Mongolia |  | 2002-12-13 | An appropriate balance needs to be found between local government autonomy and public sector efficiency and accountability. In a number of aimags (provinces), there appears to be a significant overlap of activities betweenprovincial and subprovincial administrations. The implementation of the pilot program and the subsequent training initiatives at the aimag levels have demonstrated the need for consolidation of administrative and service-delivery functions at the subprovincial levels. While it is a complex issue, it needs to be addressed given the state of inter-governmental fiscal dependence. In particular, the number of sums (municipalities) and the activities that they perform need to be rationalized. This would have a favorable impact on reducing the overheads and operational costs involved in public sector administration. Further, the recent move on establishing regional development centers could facilitate the consolidation of administrative functions on the basis of regional or subregional cluster-type arrangements. ADB will provide technical assistance (TA) support to undertake a functional review of the need for and scope of such consolidation. It is essential that the government work with local governments to ensure that the reforms to the center-provincial relations that are under way now penetrate down to the subprovincial levels as well. Efforts in this area should be undertaken along with a careful monitoring of how contractual and subcontractual relations emerge at the provincial and subprovincial levels under the Public Sector Management and Finance Law (PSMFL). project cycle stage: Feasibility, Appraisal Operation Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Public governance Modality: Program Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity building Country Context: Decentralization Policy & Reform: Reform Methodologies/Approaches: Pilot project Civil service reforms are critical to ensure sustainability of public sector reforms. It is essential that the government implement a wide-ranging civil service employment and wage reform program, aimed at arriving at an optimal sizeof the public sector labor force. Average civil service salaries at different levels are about 35-50% lower than average private sector compensation at comparable levels. The government embarked on a 4-year plan in 2000 to increase civil service wages by 25% every year. Given the serious budgetary implications, the government is carefully reviewing the increase proposed for 2003. In addition, Mongolia does not have a permanent, merit-based, or well-managed civil service. While a proper implementation of the provisions of the Public Sector Management and Finance Law (PSMFL) will bring about changes, the current practice of senior-level appointments and promotions being made on political or other affiliations is not conducive to the formation of a strong cadre of civil servants. There have been frequent changes of personnel in key positions, which partly has been a reason for the lack of real commitment across various levels of the government for public sector reforms. The measures introduced under the Governance Reform Program (GRP) will be sustained through ADB technical assistance (TA) support. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Public governance Crosscutting Issues/Themes: Sustainability Modality: Program Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Private sector Policy & Reform: Public sector reform Process-oriented reforms can substitute for capacity constraints. The Governance Reform Program (GRP) has demonstrated that process and procedure-oriented reforms bring about clarity of purpose, help define objectives properly, set appropriate levels of expectations, and launch institutional changes to facilitate transition. While capacity is lacking in the Mongolian public sector, the measures introduced under the GRP have changed the way key institutions function. ADB's sector interventions have demonstrated that there is no dearth of technical knowledge and skills in the Mongolian public sector. However, the challenge is to improve public sector governance through the introduction of reforms at all levels and provide appropriate incentives to leverage the existing capacity. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Modality: Program Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Human resources management Policy & Reform: Reform Methodologies/Approaches: Process approach Public sector reforms need to be sequenced properly. The Governance Reform Program (GRP) design did not allow for a proper sequencing of all the steps needed. First, capacity constraints were identified, but the medium-term cost implications of program implementation were not fully analyzed, vis-ï¿½-vis the likely benefits or savings stemming from the adoption of all the reform measures. Given the significant capacity building needs, it is essential that the government coordinate all external funding agency activities effectively to channel grant funds to support training and information dissemination. ADB plans to steer its follow-up support in an integrated manner, by coordinating its interventions in public sector reforms with ongoing and proposed support in health, education and other sectors. Second, reservations on moving towards output-based budgeting were noted, but its applicability in certain sector ministries and agencies was not fully evaluated. It has to be recognized that a broad-based application of output-based budgeting across the entire spectrum could not be a realistic goal for future interventions. Third, a functional review of the public sector is a critical first step in introducing reforms. While this has been accomplished in part, it needs to be extended to cover all ministries and major public sector institutions prior tomoving further. This issue is currently being addressed through ADB TA. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Modality: Program Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Sector Related Issues: Education Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Public sector reform Methodologies/Approaches: Holistic approach Risks associated with the implementation of the Public Sector Management and Finance Law (PSMFL) should be managed well. There are underlying tensions that the PSMFL will recentralize authority and reduce provincial autonomy, given that Mongolia has had powerful sector ministries in the past. In particular, there are concerns that the reforms will demand an increase in accountability without any concomitant increase in authority or independence to achieve the desired objectives. There is little doubt that the budget constraints need to be hardened, which will need a streamlined top-down approachin policy formulation, planning, budgeting and execution. However, such discipline in public administration and financial management should strike a proper balance between accountability and responsibility. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Public governance Project Management: Risks/Risk management Country Context: Decentralization Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Social impact should be monitored and managed well. Given the pilot nature of the reform measures adopted, there has been no discernible social impact as a result of Governance Reform Program (GRP) thus far, as anticipated during program design. While attempts to reduce fiscal deficits in a low growth environment are likely to have an adverse social impact,both health and education expenditures have grown by 20% in nominal terms and about 12% in real terms over 2000-2002. However, fuller implementation of the Public Sector Management and Finance Law (PSMFL) and the mainstreaming of reforms in various sectors may initially have a negative impact on the labor market and reduce access of the poor to social services. It is essential that adequate compensation measures are designed and implemented. ADB technical assistance (TA) support includes a component on monitoring the impact and designing such measures. ADB will also maintaincontinuous consultation with the government to ensure that sufficient budgetary allocations are made to cushion any adverse impact of the reforms. These efforts will also be coordinated with the World Bank's proposed structural adjustment loan to support general reform measures under the government's Poverty Reduction Strategy, currently being finalized. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Public governance Crosscutting Issues/Themes: Social protection Finance & Financial Aspects: Financing Modality: Program Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Education Sector Related Issues: Health and sanitation management Policy & Reform: Public sector reform Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Pilot project | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/governance-reform-program-1
Agriculture Sector Program (Loan 1409-MON[SF]) | Mongolia | Agriculture, Natural Resources, and Rural Development | 2002-11-30 | A program design that focuses on introducing policy reforms without developing effective measures to address issues underlying government interventions may face the risk of policy reversal after the program completion. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Policy & Reform: Policy reforms/framework Farm privatization and price liberalization are not final goals but a means to achieve sector efficiency. In a capital-intensive subsector, such as wheat farming in Mongolia, privatization and price liberalization alone cannot achieve efficiency if other constraints continue to restrict farmers ability to respond to the liberalized prices. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Methodologies/Approaches: Holistic approach It is more efficient if the design of a program focuses on removing a few of the most critical sector constraints so as to enable a full realization of the positive impact of the policy reforms. In the case of the Agriculture Sector Program, the broad coverage of 10 policy objectives diluted its focus on key sector issues. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Impact evaluation Project Design: Project design Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework The initial conditions in a sector determine the positive or negative impact of policy reforms in a transition economy. If a sector was heavily subsidized prior to the reforms, such as the wheat subsector in Mongolia, application of a standard reform package of privatization, price liberalization, and withdrawal of state intervention may lead to sharp decline of sector outputs. Supplementary measures are therefore needed to offset the negative impact of the reforms. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Impact evaluation Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Transition economies The requirement for conducting poverty impact assessment (PIA) has the merit of ensuring full awareness of the potential negative impact of the proposed reform measures. The requirement that each program takes care of its social impact, however, may lead to superficial design of social reform measures. Given the focus of program design on policy reforms, it is better if serious poverty-reduction measures are designed as supplementary projects alongside a program instead of within it. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Impact evaluation Project Design: Project design Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/agriculture-sector-program-loan-1409-mon-sf
Power Rehabilitation Project | Mongolia | Energy | 2002-11-15 | Both ADB and the executing agency must exercise realistic planning during projectdesign, and concentrate on activities that traditionally take disproportionately long periods in aland-locked country like Mongolia. Project implementation arrangements and schedules mustalso consider the inherent delays associated with the executing agencies that are first-timerecipients of ADB funding. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies The collection of reliable data and their analysis is a prerequisite for the assessment ofsocioeconomic benefits in power sector projects. Both ADB and the executing agency shouldmake efforts during project formulation, implementation, and even after project completion toestablish adequate baseline and benchmark information on socioeconomic conditions in projectareas and on how to conduct a through analysis of potential impacts. project cycle stage: Appraisal, Implementation, Operation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-rehabilitation-project-0
Country Assistance Program Evaluation for Mongolia (2002) | Mongolia |  | 2002-10-31 | A sector focus, typical for ADB operations not only in Mongolia, sometimes resulted in ADB staff overlooking countrywide issues. One such example is the legal framework. A number of program loans included policy conditions to adopt laws. While legislation may have been needed from the sector point of view, these changes were not placed in the context of Mongolia's legal framework as a whole, or did not necessarily allow sufficient time for consultations according to established processes. Some laws, such as the Public Sector Management and Finance Law, are based on an Anglo-Saxon model while the entire legal system of Mongolia is based on the German model. In other areas, inconsistencies exist between laws, e.g., on taxation that enables the Government to collect outstanding taxes from bank accounts and the banking law that ensures confidentiality of account information. These disparities in legal development could have been avoided, had a country perspective been adopted, supported with relevant analytical work to identify and understand countrywide issues, in addition to the traditional sector focus. The recently introduced thematic assessments, such as those of governance or of the private sector, have the potential to play an important role in improving ADB's understanding of development or transition issues and how these need to be reflected in lending and TA. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Modality: Policy-based lending Modality: Program Modality: Technical Assistance Project Design: Problem identification Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Transition economies Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach Counterfactuals are hard to develop to prove that a strategic or more comprehensive approach is more effective than a fragmented one. However, the examples of sectors that, in Mongolia, covered interrelated aspects relevant to sector performance, indicate the value of structured and systematic assistance that has a medium- to long-term horizon with intermediate, specific milestones. project cycle stage: Country Partnership Strategy Lesson Topics: Project Management: Risks/Risk management Methodologies/Approaches: Holistic approach Methodologies/Approaches: Targeting Cross-sector variations occurred, particularly in the area of capacity building. These variations are not harmful, but it takes an exercise such as the CAPE to identify good practices and share them across sectors. The social sector projects (education and health) developed capacity-building solutions based on fairly detailed analysis of existing institutions and identification of missing ones. In the health sector, for instance, weaknesses were addressed across various levels, central and local: within the line ministry and local governments, licensing board, and sum hospitals, and family group practices. Nonetheless, both sectors will be facing difficulties in attaining their final aim due to underlying attitudinal issues that are difficult to address with external assistance, and are often not raised for reasons of sensitivity. For instance, attitudes toward health services are heavily biased toward hospital-based treatment with heavy medication, which would have to change if the country is to reap full benefits from ADB's assistance to the health sector. project cycle stage: Country Partnership Strategy Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Institutional analysis Country Context: Cultural constraints Country Context: Decentralization Sector Related Issues: Education Sector Related Issues: Health and sanitation management Looking for models and applying ready-made solutions is always a temptation, especially when radical changes are needed. However, the drawback of trying to introduce systems that work in other places can result in a series of changes (copying approaches that might not always fit) rather than a solution to problems. For instance, when introducing a complex system such as output-based budgeting under the Governance Reform Program (GRP), much attention is drawn to its technique and away from the problem of controlling public expenditure and introducing professional management into the public service. In this instance, it might have been more useful to have broad-based consultations with stakeholders at national and subnational levels to build consensus on problems and their root causes, and discuss possible solutions. ADB could support such a process the consensus building alone helping build capacities in understanding problems and appropriate solutions and bring a variety of potential tools to a dialogue of this nature. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Public governance Project Design: Project design Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Methodologies/Approaches: Consultation/Participation Policy matrixes tended to mix policy reform measures and milestones or means of monitoring the introduction of policy reforms. This practice resulted in complex policy matrixes and contributed to a confusion of what policy reforms (as opposed to monitoring mechanisms) entailed. project cycle stage: Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Targeting The amount of grant TA resources provided helped ease, to some extent, the burden of increasing foreign debt. Whether these resources were most effectively used and attained a commensurate impact was difficult to assess in view of the fragmented nature of the TA program and the absence of clearly defined links (in terms of outcomes) between TA and lending. Such links could be determined, if strategies and programs were developed around key transition (or development) issues and processes. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Program Modality: Technical Assistance Project Design: Problem identification Policy & Reform: Policy reforms/framework Policy & Reform: Transition economies The CAPE illustrates weaknesses in translating COS into operations. While key transition themes or processes were correctly identified, they were not systematically built into CAPs. This shortcoming does not apply only to Mongolia and reflects the gradual, still incomplete, transformation of ADB from a project-lending institution to a development agency with a country focus. The recent change in business processes, namely combining COSs with CAPs into CSPs, has been a first step toward addressing this shortcoming, the second one being the reorganization of ADB including the establishment of country teams. However, whether these changes in process and structure will actually effect a change in content and program will depend on each country team's ability to identify and analyze key transition or development issues that are specific and important to the country, and then translate these issues into an operational framework that specifies goals, targets, and modalities. This will require time and resources to be made available to the country teams for this purpose. project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Lending modality Project Design: Problem identification Policy & Reform: Policy reforms/framework Policy & Reform: Transition economies Methodologies/Approaches: Program Approach Methodologies/Approaches: Targeting The narrow focus on solving institutional problems reflected a lack of comprehensive insights into institutions and processes, which combined poorly with the absence of institutional performance indicators. Together these factors resulted in assistance that addressed issues within a narrow frame, without considering whether overall institutional performance could improve as a result. This was the case in assisting public resource management, where TA and lending were not conceived to complement each other, even though they had the potential to do so. Had assistance to public resource management been perceived in a programmatic way, goals could have been determined for overall process improvements that would reflect, for instance, whether the government is in a better position to exercise fiscal discipline and increase efficiency (producing the same outputs/results with fewer resources). Capacities for making relevant choices and decisions, including policy formulation and strategic planning, should become part of such a systematic capacity-building process. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Public governance Modality: Lending modality Modality: Program Modality: Technical Assistance Monitoring & Evaluation: Indicators Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Institutional analysis | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-mongolia-2002
Employment Generation Project (Loan 1290-MON[SF]) | Mongolia | Finance | 2002-09-30 | The project highlighted the need for (i) differentiating lending to microenterprises from that to small and medium enterprises, and tailoring project objectives and design accordingly; and (ii) more prudent institutional assessment of the performance and technical capabilities of the financial intermediaries such as participating commercial banks (PCBs). project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity assessment Sector Related Issues: Private sector The project s subborrowers were more skewed toward small and medium enterprises than toward microenterprises and the participating commercial banks' (PCBs ) loan administration was tailored more for the former. The PCBs were not provided with skills for microenterprise credit criteria, underwriting, loan administration, and monitoring. The feasibility study conducted under the project preparatory TA noted that the PCBs were lending to microenterprises; however, further analysis of the loan administration and credit criteria might have helped predict the weakness in the PCBs capacity to generate an adequate volume of microenterprises loans to the targeted subborrowers. The feasibility study was not thorough in analyzing microcredit delivery capabilities of the existing institutions. The study focused on utilizing the existing commercial banks, which were financially weak and ultimately failed. The fragile conditions of those banks were widely known. Alternative lending institutions should have been discussed at an earlier stage. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity assessment Capacity Development: Capacity building Sector Related Issues: Private sector | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/employment-generation-project-loan-1290-mon-sf
Ulaanbaatar Airport and National Air Navigation Development Projects (Loans 1256/1370-MON[SF]) | Mongolia | Transport | 2002-08-31 | Aviation infrastructure, in economies such as Mongolia, with vast distances and low demand, is likely to be of limited financial viability but essential for economic development and social cohesion. There is synergy in adopting an integrated approach, whereby the benefits of removing an infrastructure bottleneck through a project with relatively low rates of return, the Airport Project, are enhanced by the increase in institutional capacity generated by revenue streams from the National Air Navigation Development Project, with a high rate of return. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Transport planning Policy & Reform: Transition economies Methodologies/Approaches: Holistic approach Projects that have significant safety programs should be clearly defined and developed to fully implement safety programs, regulations, and enforcement. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Transport planning The air transport sector is inherently commercial in nature, and has the capacity to generate substantial revenue streams where there is sufficient market demand, as evidenced by the overflight revenue obtained through the air navigation development project. ADB has played a key role in identifying and helping develop the civil aviation sector, and in creating an enabling environment. The current ADB COS for Mongolia largely excludes further investment in infrastructure. The OEM believes that ADB should continue to play a role in civil aviation sector policy and investment. project cycle stage: Concept, Country Partnership Strategy Lesson Topics: Project Design: Problem identification Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework The capacity of the EA has been enhanced by the projects, while the limited commercial viability of the airline operator has been exposed. As macroeconomic circumstances are constrained, there is little that the government can do to rectify this situation by allowing basic air transport costs to rise or by making subsidy payments. A more comprehensive approach may be required through formulating market-based policies for the sector, particularly through the encouragement of private sector airlines and development of airport sites as multi-user facilities, to find effective ways to fund justifiable community service obligations. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Sector Related Issues: Private sector Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework Methodologies/Approaches: Holistic approach The successful implementation of the airport and air navigation projects demonstrates that, for economies in transition, ADB must play a proactive, up-front role in project preparation and implementation, combining strong policy and capacity-building components with physical works. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Lending modality Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework Policy & Reform: Transition economies Methodologies/Approaches: Holistic approach While noncompliance with the community services subsidy loan covenant is seen as a constraint, with an impact on the airline operator's financial performance, the expectation of direct assistance was perhaps inappropriate given the government slimited capacity to meet development needs, in any sector, and the demands on recurrent expenditure particularly exacerbated by recent harsh winters and livestock losses in the important agriculture sector. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Loan Agreement: Covenants Capacity Development: Capacity assessment | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/ulaanbaatar-airport-and-national-air-navigation-development-projects-loans-1256-1370-mon-sf
Selected Technical Assistance in the Environment Sector in Mongolia | Mongolia | Agriculture, Natural Resources, and Rural Development | 2001-01-31 | Attaching a TA to a loan should not be done for the sake of convenience of TA processing, or to provide a cover toaddress environmental or other partly applicable concerns but to directly complement the activities of the loan project and provide institutional support in order to facilitate project implementation. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Appraisal Project Management: Project management Capacity Development: Capacity building Beneficiary and stakeholder participation needs to be integrated into project preparation and implementation planning as early as possible in order to engender a sense of ownership by the targeted beneficiaries. project cycle stage: Design, Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Satisfactory performance of projects is due mainly to adequate project preparation, strong institutional capability, commitment of the executing agency, and firm government support resulting from ownership. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Institutional analysis Capacity Development: Ownership Taking into account the long program cycle needed forsustained development, a series of overlapping TAs/projects with consistent core objectives areneeded over a much longer period to make an impact on key subsectors while strengthening government management capacity. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Cluster operations Modality: Technical Assistance Monitoring & Evaluation: Impact evaluation Capacity Development: Capacity development The implementation of TAs attached to projects can succeed if the following conditions are ensured: (i) suitable TA design which should not cover a broad range of areas; (ii) adequate financial allocation; (iii) stability in staffing; (iv) teamwork among the consultants and staff of the Executing Agency which results to more appropriate recommendations and more effective outputs; and (v) closer guidance and supervision by both ADB and the government. project cycle stage: Design Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Human resources management | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/selected-technical-assistance-environment-sector-mongolia
Advisory and Operational Technical Assistance Grants to the Energy Sector in Mongolia | Mongolia | Energy | 1999-12-31 | During TA design when planning the sequence of TAs, sufficient time needs to be provided for related studies for (i) changes introduced to take root; (ii) beneficiaries to realize preconditions to maximize benefits, and take responsibility to sustain them; and (iii) recommendations of completed TAs be incorporated in proposed activities. Important recommendations of previous TAs (especially the TAs that focus on needs assessments) need to be carefully reviewed by the executing agency and ADB to instruct the next batch of consultants on the work that has already been accomplished so they do not duplicate these efforts. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Prior to and during implementation, client ownership and support from the recipient agency's top management is crucial for the success of the TA, especially in transition economies converting from centrally-planned systems and conditions to new approaches and techniques. To do this, top management needs to fully appreciate the TA benefits and become champions of change to enhance the likelihood of sustainability of benefits. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Ownership Policy & Reform: Reform Policy & Reform: Transition economies Sustainability of TA benefits needs to be addressed at design, implementation, and completion. Careful consideration has to be given to ensuring (i) sufficient technology is transferred, (ii) adequate technical equipment and computer software are available to carry on the work initiated by the TA, and (iii) resources and management support are available to make training programs sustainable. The movement of trained personnel (upwards, within the same organization, or outside for better opportunities) is inevitable. Training of trainers and a budget and a modality for training to sustain the benefits within the organization should be established in every training program. project cycle stage: Design, Implementation, Completion Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building Capacity Development: Human resources management Capacity Development: Technology/Technology transfer The importance of recognizing language barriers and providing resources for translation services or encouraging qualified local participation as part of the consulting team was somewhat recognized by the design of later TAs. However, this lesson needs to be applied in future TAs to other countries and clients when ADB initiates work in a new sector and a new client. In the initial TAs of a cluster, substantial time needs to be spent at fact-finding to understand the implementation barriers particular to the country and the sector. Whenever possible, to enhance the efficiency of training programs and better communication in the classroom, the availability of resource persons in local institutions should be explored before tapping international consultants. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financing Modality: Cluster operations Modality: Technical Assistance Project Management: Consultants Capacity Development: Capacity building To ensure adequate technology transfer and capacity building, the software and hardware needed under the TA should be purchased or rented under the TA. To provide hands-on experience, the consultants should be required to perform all the analysis for the TA in the field office. If the consultants need to return to the home office for facilities not set up in the developing member country, an adequate number of pertinent staff should accompany the consultants during the home office work period. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Management information system Capacity Development: Capacity building Capacity Development: Technology/Technology transfer | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/advisory-and-operational-technical-assistance-grants-energy-sector-mongolia
Technical Assistance to the Banking Sector in Mongolia | Mongolia | Finance | 1997-12-31 | An environment conducive to the use of skills to be imparted through training must be created before such training is embarked upon. The skills to be provided and the training programs designed for the purpose must be marketed to management, managers, and supervisors before training programs are started. project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Project Management: Project management Capacity Development: Capacity building Capacity Development: Ownership In a transitional economy, reform of the banking sector should, whenever possible, start with a grand design for the sector's evolution. Technical assistance to the banking sector in such economies needs to be supported by a long-term, well-considered, flexible strategy. Ideally, a series or cluster of TAs could be prepared with sequencing determined according to the priority of issues to be addressed and the nature of assistance to be provided. Reform would normally begin in the core areas, and expand from the central bank to commercial bank operations. Handling of individual institutions would follow thereafter. There would be some overlap among these stages. More specifically: (i) The sequencing of TA activities could start with a comprehensive and thorough assessment of the sector and identification of its structural problems. This would pave the way for an analysis of the banking sector and an assessment of its needs. Reform of the legal and regulatory environment of the banking sector could follow. Institutional strengthening and restructuring of banks should be based on a comprehensive understanding of the current commercial banking environment, including comprehensive portfolio reviews; and (ii) The omission of sufficient institutional strengthening activities directed at the supervision department of the central bank in the early TAs can reduce the overall impact of other TA components, such as the commercial bank strengthening activities in credit analysis and administration. Finally, attempts to restructure the banking sector in transitional economies are difficult indeed, notwithstanding careful and thorough preparation. project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Modality: Cluster operations Modality: Technical Assistance Capacity Development: Capacity building Policy & Reform: Policy reforms/framework Policy & Reform: Transition economies Issues regarding programming and the President's approval limit for TAs also arise. The decision to keep the second and third TAs below the President's approval limit of less than $600,000 constrained their scope and limited the work that could be done in the legal and regulatory areas of the banking sector. Additional funding could have helped deepen the assessment phase and given early momentum to structural reform. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Appraisal Policy & Reform: Policy reforms/framework Lack of effective counterpart participation diminishes the potential impact and output of the TAs. Greater openness on the part of the consultants towards counterpart participation would encourage a larger sense of ownership of the TAs and their outcomes among recipient agencies. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Capacity Development: Ownership Capacity Development: Technology/Technology transfer Methodologies/Approaches: Consultation/Participation The speed of response by ADB TAs to developments in the banking sector is critical. Delays in the processing or implementation of TAs can cause distortions and result in TAs being overtaken by events. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Appraisal Project Management: Project administration | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/technical-assistance-banking-sector-mongolia
Design of e-Governance Master Plan and Review of Information and Communication Technology Capacity in Academic Institutions: Technical Assistance Completion Report | Myanmar | Education, Information and communication technology, Public sector management | 2016-01-01 | ICT (information and communications technology) is cross-cutting in nature. It is a sector in itself, and an enabler/catalyst in other sectors. Undertaking planned and coordinated implementation of ICT and e-Governance program across all ministries in Myanmar will lead to enablement of efficient access and wider reach of public service delivery. The master plan proposes the design of common requirements and enforcement of standards and policies of e-Governance by a central agency, while leaving the flexibility to design and develop e-Governance programs in a decentralized manner with individual ministries. The ICT universities play a key role in providing skilled human resource to the labor force. Therefore, in e-Governance planning, it is important to look into the capabilities of institutions of higher learning and plan skill building in an integrated fashion. Demonstration projects contextualized to country conditions serve as an important vehicle for introducing concepts, knowledge creation, and innovations in development interventions. It is necessary to ensure the involvement of the entire ecosystem (public sector, private sector, and academe) to gain traction and up-scale/replicate the demonstrated capabilities. It is vital for any master plan to address total cost of ownership and maintenance. It is also important to consider the fast technological obsolescence nature of ICT instruments and plan adequately for methodical exit or rejuvenation approaches. The e-Governance domain requires public sector attention?particularly in the areas such as addressing last mile connectivity and reach of electronic delivery of public services, telecom regulatory matters, connectivity and automation of government functions. Finally, a national e-Governance plan requires adequate financial resources. In this context, the financial support by ADB, as well as the co-financing support from Republic of Korea e-Asia and Knowledge Partnership Fund and People's Republic of China Regional Cooperation and Poverty Reduction Fund, provided adequate and timely support. This TA's (technical assistance) funders generated goodwill and appreciation among the executing and implementing agencies of Myanmar. Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/mya-design-e-governance-master-plan-and-review-ict-capacity-academic-institutions-tcr
Support for Myanmar's Reforms for Inclusive Growth Program: Completion Report | Myanmar | Public Sector Management | 2015-07-23 | Myanmar presented a unique opportunity for ADB to launch a deeply impactful, highly relevant series of supports to help the government rejoin the global economy, accelerate economic growth, alleviate poverty, and develop the foundations for the long-term sustainable growth of the economy. ADB's approach to reengagement was proactive and positive; through consultations with government, the appraisal team ascertained key drivers of reform and focused on those with high impact. project cycle stage: Appraisal, Country Partnership Strategy With the reopening of Myanmar after so many years in relative isolation, the scope of development need was massive. Clearing of arrears was only the start of development support requirements. The government was highly motivated, spurred on by the visible benefits countrywide of the change and reform agenda on which it had embarked. However, the government's lack of familiarity with development finance institution protocol, project design and processing requirements, and implementation management and monitoring requirements has meant that subsequent deployment of development support resources could be more efficient. project cycle stage: Design, Appraisal, Implementation, Country Partnership Strategy The program shows that it is important to have well considered and immediately actionable support TA projects available to assist government in areas of high need, great challenge, or unfamiliarity. The three TAs implemented in support of the program reforms were effective in supporting government. The most important of these - the Support for Public Financial Management TA - is on going and should be sustained. In retrospect, given the nascent nature of Myanmar's reengagement, it may have been appropriate to have additional TA support on stand-by while observing government's progress on reforms. Yet it was prudent to take a cautious approach at first before adding additional supports and personnel. project cycle stage: Implementation, Country Partnership Strategy The government's goals were clear, leading to clear program goals. Going forward, implementation can be improved though provision of deeper, focused TA and additional engagement directly between ADB specialists and the government over extended periods of time. project cycle stage: Concept, Implementation, Country Partnership Strategy | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-myanmar-reforms-inclusive-growth-program-pcr
Support for Improving the Business Climate: Technical Assistance Completion Report | Myanmar | Public sector management | 2015-07-01 | Strong ownership of reforms by government counterparts can unlock high-level political support important to facilitate implementation of reforms that are beyond the formal authority of the counterpart. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-improving-business-climate-tcr
Support for Trade Policy Development: Technical Assistance Completion Report | Myanmar | Public sector management | 2015-07-01 | Timely and well-targeted TA (technical assistance) can achieve a catalytic and far reaching impact. Project cycle stage: Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/support-trade-policy-development-tcr
Improving Fiscal Revenue Mobilization: Technical Assistance Completion Report | Myanmar | Public sector management | 2015-06-01 | Close coordination/collaboration with other development partners and institutions can allow for leveraging of TA (technical assistance) outputs and strengthen achievement in terms of outcome and impact. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/improving-fiscal-revenue-mobilization-tcr
Trade Facilitation Support for ASEAN Economic Community Blueprint Implementation (Myanmar): Technical Assistance Completion Report | Myanmar | Industry and trade | 2015-05-01 | The implementation of the TA (technical assistance) highlighted a few lessons. Conducting the first-ever TRS (time release studies) was a challenge for MCD (Myanmar Customs Department). Hands-on support by the TRS expert helped MCD conduct and complete the TRS efficiently and effectively. Being the first initiative that highlighted the importance of TRS in facilitating trade, the conduct of the TRS was strongly supported both by the government and the private sectors. Communication and coordination were significant challenges in TA implementation. The number of government officials with English proficiency was limited, and therefore, translator services were critical. Direct face-to-face meetings were often the most effective and efficient means to get information. Closer coordination with MYRM (Myanmar Resident Missions) will be continued to help alleviate some of these communication difficulties. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/trade-facilitation-support-aec-blueprint-implementation-mya-tcr
Yangon-Pyi Road Improvement Project (Loan 644-MYA[SF]) | Myanmar | Transport | 1996-12-31 | The project clearly demonstrates the importance of enforcing vehicle axle weight regulations, particularly for heavy trucks. Future sustainability of bitumen pavements is dependent on the control of truck overloading. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Roading The project exemplifies the importance of understanding the technical skill base of the executing agency staff prior to implementing projects, where previous experience with international engineering standards and practices has been minimal. The careful selection of international engineering consultants to provide on-site training and support facilitates project implementation, particularly when projects involve the introduction of new engineering concepts and practices. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Sector Related Issues: Roading | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/document/yangon-pyi-road-improvement-644-MYA
Upgrading of Hospitals Project (Loan 553-MYA[SF]) | Myanmar | Health | 1995-02-28 | Cost recovery has greater chances of success when introduced gradually through pilot sites and combined with an intensive information campaign. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Pilot project Project experience confirmed the need for participation of key hospital personnel in project preparation to ensure that their priority needs are fully taken into account. Equipment packages should be prepared on the basis of specification of needs on a case-by-case basis. The standard supply strategy has resulted in underutilization and failure to meet important requirements. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Procurement Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation Project experience demonstrated the need for advance action for recruitment of consultants to complete planning and pre-implementation preparation activities to ensure that project implementation is not delayed. project cycle stage: Appraisal Lesson Topics: Project experience illustrate the value of undertaking needs assessment before drawing up equipment lists in order that the right inputs may go to the right sites. Further, machines and trained technicians go 'hand in hand'. Therefore, the installation of machines and the provision of equipment must be accompanied by technicians trained to operate them. project cycle stage: Feasibility Lesson Topics: Project Management: Procurement Capacity Development: Capacity assessment Capacity Development: Capacity building Project experience illustrated the need for identification of indigenous strategies and innovative practices. There is a strong evidence of a high degree of community participation in hospital management and sourcing of financing for development projects. Positive attitudes toward cost sharing, voluntary service, contributions of cash and kind, cost recovery, and assistance to the needy are among the observed expressions of support which help to sustain health projects. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Sector Related Issues: Health and sanitation management Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/upgrading-hospitals-project-loan-553-myasf
Public Financial Management Reform Program: Project Completion Report | Nauru | Public Sector Management | 2016-05-01 | Country ownership. The potential for large shifts in the political and economic context can create significant challenges for implementation. The program was able to succeed despite encountering such challenges as it was strongly aligned with Nauru's own strategic policy agenda, in particular the National Sustainable Development Strategy. Technical foundations. The program benefitted from, and integrated, a range of TA from ADB and other development partners. This provided a strong foundation for the program's reform agenda, which meant policy actions were both well founded and viewed as appropriate by the government, despite the political and economic changes. Donor coordination. Strong coordination amongst development partners, notably with the Government of Australia, was essential to the program's success. Australia provided in-line advisors to support the government to implement many of the program-related reforms (e.g., within the MOF and NUC) as well as TA that complemented the program. ADB's donor coordination role also meant ADB was requested by Nauru and its development partners to assist with the crucial task of establishing a new Nauru trust fund. Simplification. Institutional capacity within the government remains constrained. It is essential that ADB programs are as simple as possible in clarity of the policy agenda and ease of administration. Fewer policy actions with a tighter focus on the most important measures would assist and can help to avoid dilution of focus. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/nau-public-financial-management-reform-program-pcr
Fiscal and Financial Reform Program | Nauru |  | 2003-11-14 | Program experience highlights the (i) need for prior, transparent, and participatory assessment of the social and political feasibility and sustainability of reforms; (ii) participatory consideration of alternative means to reduce costs of personnel; and (iii) prior consideration of the means to improve the environment for alternate revenue generation, including far greater commitment to improving the environment for private sector development. A more participatory assessment could, of course, determine that no reform program is feasible. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Modality: Program Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Participatory approach | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/fiscal-and-financial-reform-program
Gender Equality and Empowerment of Women Project: Completion Report | Nepal | Agriculture, Natural Resources, and Rural Development | 2015-09-11 | Multiple and interrelated women's issues are best addressed through integrated approaches for creating better synergy. The project's approach of strengthening the capacities of the DWD (Department of Women Development) and WDOs (Women Development Offices), formation and capacity building of women's organizations, building women's knowledge about their rights, and targeted interventions to address women's practical needs, such as income generation, time-saving technologies, and women-friendly infrastructure, has given women better access to opportunities and services that responded to their needs not only for survival but also for better social mobility and empowerment. Access to microfinance and support through start-up grants were instrumental for women's economic empowerment. project cycle stage: Operation In order to reduce the gap in overall human development and gender equity indexes, the targeted interventions on women's empowerment are still highly relevant in Nepal. VDC (village development committee) clustering in the project area based on geographic contiguity and similarity should be considered when selecting project sites in remote areas. Doing so can improve staff mobility, service delivery, monitoring, and supervision. project cycle stage: Design, Implementation, Operation Intersectionality is an important element to be addressed in projects promoting women's empowerment and gender equality. Women are a heterogeneous group and their diversity based on caste, ethnicity, religion, region, and language are critical factors contributing to their abilities to benefit from and contribute to the overall project implementation. project cycle stage: Implementation, Operation Coordination with like-minded donors and other stakeholders on a regular basis helps in improving project implementation, harmonizing approaches, eliminating duplication, creating synergies, and resolving implementation issues. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/gender-equality-and-empowerment-women-project-pcr
Commercial Agriculture Development Project: Completion Report | Nepal | Agriculture, Natural Resources, and Rural Development | 2015-09-10 | Designing the project with mechanisms for communication and coordination between existing government institutions in project districts and project management structures can facilitate smooth project implementation and monitoring. This also ensures that sector offices will provide beneficiaries with follow-up services after project completion. project cycle stage: Design, Implementation, Completion The timely design and execution of a results-based monitoring system is an important means of collecting and reporting project outputs and outcomes in a disaggregated way during project implementation, and carrying out an objective impact evaluation upon completion. project cycle stage: Implementation, Completion Enterprises operated by farmer groups, especially those composed of women, the poor, and disadvantaged people, should be provided with refresher skills training, access to finance, follow-up services, and ways to maintain market links to sustain operations and benefits. The provision of land lease financing serves as a good way to reach poor and landless families by helping them access productive resources and benefit from commercial agriculture. project cycle stage: Operation Women and disadvantaged groups often do not have enough time to participate fully in project implementation and capacity development activities and thus benefit from the project. Designing the project to include targeted interventions such as intense mobilization, training, and the facilitation of access to finance, extension services, and inputs optimizes the possibility of visible improvements to their livelihoods. project cycle stage: Design, Implementation The project may be able to secure the involvement of larger processors and traders by making large financial contributions to their business plans, as smaller contributions are not helpful. project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/commercial-agriculture-development-project-pcr
Increasing Access to Energy in Rural Nepal: Technical Assistance Completion Report | Nepal | Energy | 2015-09-01 | The TA (technical assistance) faced lack of ownership. Every key stakeholder including MOF (Ministry of Finance) should have been actively involved during TA design process to understand the TA's rationale and implementation arrangements. Increasing TA ownership by MOF was crucial to the achievement of the envisaged outcome. Moreover, AEPC (Alternative Energy Promotion Centre) had no previous experience in TA implementation. It was the first time AEPC was acting as the executing agency of an ADB TA. It was therefore unfamiliar with ADB rules and procedures, which partially caused delay in implementation. A key lesson for the future is that the executing agency's capacity is assessed upfront during TA design and capacity development included as part of the TA. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/increasing-access-energy-rural-nepal-tcr
Urban Transport Planning and Management: Technical Assistance Completion Report | Nepal | Transport | 2015-07-01 | The consultant used a 4-stage transport forecasting approach (trip generation, trip distribution, mode choice, and route assignment) to prepare the urban transport plan of Biratnagar. While high quality assessment was done in Biratnagar, it was observed that this approach required extensive data collection and specialized expertise currently lacking in Nepal. For urban transport systems serving other secondary cities of Nepal, a simplified approach, such as traffic assignment model, can be built on the findings of this Biratnagar study to allow efficient use of future resources. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/nep-urban-transport-planning-and-management-tcr
Strengthening Municipalities for Urban Service Delivery: Technical Assistance Completion Report | Nepal | Water and other urban infrastructure and services | 2015-03-01 | The TA (technical assistance) played a complementary role to strengthen the capacity of the municipalities being supported under the ADB- financed investment project. Capacity development of municipalities needs long-term engagement, particularly when municipal staff do not have requisite skills (e.g., GIS or geographic information system). Project cycle stage: Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/nep-strengthening-municipalities-urban-service-delivery-tcr
Governance Support Program (Subprogram I) | Nepal | Public Sector Management | 2014-08-01 | Sequencing of reforms is crucial to achieve intended outcomes that call for a long-term partnership. For example, institutionalizing citizen engagement in local governance and instituting accountability measures before providing increased funding to local bodies reduce fiduciary risks and improve the likelihood that funds will be used properly. Regular review of existing policies and guidelines is important to assess their effectiveness and relevance in a given context, and a one-size-fits-all approach in policies and guidelines fails to achieve intended outcomes. An example of an inappropriate one-size-fits-all approach is the mobilizing of only one social mobilizer in every village development committee irrespective of its size and population, even though village development committee populations range from 1,000 to 80,000. The policy to use only users' committees for infrastructure projects is another. Public engagement in local governance processes not only empowers people, but also promotes transparency and accountability in decision making by public authorities. Policy reforms will be effective and sustainable if they are based on the findings of reviews, the assessment of gaps and of the positive and negative impacts of such gaps on development outcomes, and adequate public consultation. Capacity development is an important element of institutional strengthening. It should be linked to the findings of assessments such as the minimum conditions and performance measures so that efforts can be properly targeted to address the weaknesses identified. An integrated approach to the key elements of policy reform, institutional strengthening, a monitoring mechanism, and capacity development is needed for effective gender equality and social inclusion mainstreaming. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/governance-support-program-subprogram-1-pcr
Rural Reconstruction and Rehabilitation Sector Development Program | Nepal | Transport | 2014-08-01 | Reforms with broad-based consultations reflecting country needs and context have better chances to succeed. Much of the program's success can be attributed to participation and ownership of stakeholders during formulation and implementation of the policy reforms, as well as to alignment of the policies with the prevailing political and economic situation. Funding is necessary but not in itself sufficient for improved decentralization and local governance. Strengthening of regulatory arrangements and institutional capacity of central and local agencies for technical, procurement, financial, and safeguards management can play important roles in improving the quality of project implementation and achieving intended objectives. Lack of project readiness leads to project implementation delays. Completing requisite preparatory works prior to project approval maximizes the possibility of timely project implementation by giving adequate attention to construction quality and sustainability of facilities. Proper provisioning and implementation of advance procurement and retroactive financing can also minimize implementation delays. Packaging of numerous small civil work contracts and consultants to be procured in a decentralized manner poses procurement risks and creates challenges for timely procurement and proper management of contractors and consultants. Proper legislation and project design can ensure social inclusion and easy access of women, socially disadvantaged groups, and minorities to national politics, civil service, and leadership in local infrastructure development and management. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-reconstruction-and-rehabilitation-sector-development-program-nepal-pcr
Nepal: Country Partnership Strategy 2010-2012 Final Review Validation | Nepal |  | 2013-05-13 | 1. Simplicity needs to be balanced with a strategic focus on development results. One of the principles the country partnership strategy espoused was to keep things simple, yet it included a strategic architecture with four pillars, six sectors, 24 subsectors, six themes, and three screening tools. This apparent inconsistency was not a weakness, as simplicity is not an end in itself. What is more important is that future efforts need to address binding constraints to achieve desired development outcomes. [Executive Summary, page iii; Main text, para. 92(i)] project cycle stage: Country Partnership Strategy Lesson Topics: 2. Insufficient power sector response. The power crisis has disrupted the workings of the government, when the population needed to see that the government could perform to rebuild confidence. The country partnership strategy declared that ADB would be flexible in its response to the country's needs, but there was no emergency response to the crippling power situation. [Executive Summary, page iii; Main text, para. 92(ii)] project cycle stage: Country Partnership Strategy Lesson Topics: Country Context: Emergency Sector Related Issues: Energy planning/management 3. Policy reform overload. While reforms were needed, political volatility and a focus on more fundamental political issues crowded out attention to the more developmental reforms. In retrospect, this could have been anticipated and a more focused policy agenda supported. [Executive Summary, pages iii-iv; Main text, para. 92(iii)] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Policy & Reform: Reform 4. Program implementation. The solution to improving portfolio performance has generally been to intensify supervision. There does not seem to have been any restructuring (or cancellation) of projects that were not working or were excessively complex to begin with. [Executive Summary, page iv; Main text, para. 92(iv)] project cycle stage: Implementation Lesson Topics: Project Management: Project administration Project Management: Project management Project Management: Project supervision | Country Partnership Strategy Final Review |  | http://www.adb.org/documents/nepal-country-partnership-strategy-2010-2012-final-review-validation
Skills for Employment Project | Nepal | Education | 2013-01-07 | 1. Delivery of skills training through the private sector is a viable approach to skills development in Nepal. The success of public-private partnerships will depend on appropriate implementation design, including a competitive bidding process to select the most experienced and qualified training institutions; mandatory skills testing and job placement requirements to ensure minimum quality of training; performance-based contracts to motivate the training providers to place trainees in jobs; capacity building of the technical training providers to carry out pre-training, training, and post-training activities; and close follow-up monitoring of the training providers. project cycle stage: Lesson Topics: 2. Affirmative action policies could expand opportunities for skills development to members of marginalized groups. Without explicit targets for the disadvantaged groups, not as many trainees from the groups would have benefitted from skills training. However, the targets should not be uniform across all training areas but should vary according to type of trade, location of training, and density of marginalized groups in the area. project cycle stage: Lesson Topics: 3. Project implementation arrangements should be carefully assessed and necessary provisions made for effective project management. There should be strong ownership of and commitment to the project by all parties responsible for project implementation. project cycle stage: Lesson Topics: 4. In order to avoid major initial delays in project implementation, procurement planning must be effective, and packaging of contracts needs to be carefully thought out. Project implementation should also have a provision for supporting government officials with management consultants. Advanced actions including retroactive financing provisions should be investigated during the project design and used in establishing the project office, training packages and management support consultant. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/skills-employment-project-pcr
Nepal: Kali Gandaki - Hydroelectric Project | Nepal | Energy | 2012-12-27 | 1. The report and recommendation of the President noted that once contracts were awarded, implementation proceeded smoothly. Unfortunately, implementation of Kali Gandaki A did not proceed smoothly. Relations between Nepal Electricity Authority, its engineer, and the civil works contractor deteriorated to such a degree that on at least one occasion, ADB considered stopping the loan. The lesson that may be apparent is to involve the Nepal Resident Mission to a greater degree so that problems may be diffused sooner, rather than relying on ADB review missions to react to them later. [Main text, para. 99] project cycle stage: Implementation Lesson Topics: Project Management: Project management Other: Resident Mission 2. Another lesson highlighted in the report and recommendation of the President (RRP) was that a previous technical assistance for institutional assistance to Nepal Electricity Authority (NEA) was not as successful as expected. The reason cited was lack of NEA staff motivation. To address this problem, the RRP included as a remedy that NEA would be required under the project to introduce results-oriented incentive schemes. While this may be a laudable idea, the Independent Evaluation Department Mission saw no evidence that it was implemented. For this to be implemented, a specific loan covenant must be included and strictly enforced. This lesson pertains to the whole subject of loan covenants: they should be more strictly enforced. During ADB Board of Directors meeting on 18 March 1996, the Board expressed a similar opinion. [Main text, para. 100] project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Capacity Development: Ownership 3. The Independent Evaluation Department (IED) Mission recommends that future projects in Nepal consider projects with sufficient storage capacity to better address load shedding, which continues to affect economic growth and living standards. To consider such projects, greater knowledge of technical aspects, including geology, hydrology (including extreme events), and sedimentation, should be developed by financing agencies and/or developers. Future projects will also need greatly improved environmental and social impact assessment and implementation, bearing in mind that much of the development of future hydro projects may be undertaken by the private sector or as public private partnerships, which will require far more streamlined approaches to addressing environmental and social impacts. The IED Mission found that the elaboration of mitigation measures needs to be more stringent than was done in the 1990s for the project elaborated (Safeguard Policy Statement [2009]) and that these measures are best implemented with an area development focus as opposed to relying on a mitigation focus, as is done in industrialized countries. In an area development approach, the mitigation measures should be formulated comprehensively, to ensure that the do good principle in addition to the do no harm principle is applied. To provide the impacted population with the greatest benefit, the suite of mitigation measures typically derived from the environmental impact assessment process should be designed to promote rural development as well as biodiversity and environmental sustainability. The Safeguard Policy Statement (2009) provides information to operations on how to do this. [Main text, para. 101] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Knowledge Management Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Sustainability Sector Related Issues: Rural development 4. ADB should consider promoting complementary rural development initiatives in project-impacted areas with indicators of outcome derived from the impact assessment process. Agencies to be involved in implementing these initiatives should be preferably located at the district or village level. ADB should not rely on the polluter pays principle or on compliance mechanisms to implement its safeguards. Where feasible and government support exists, safeguards should be integrated in development initiatives in the same way that rural development projects are approached except that the design basis of these initiatives should be from an impact assessment perspective. [Main text, para. 102] project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Impact evaluation Sector Related Issues: Rural development 5. There is no doubt that selecting hydro versus thermal power in Nepal provided a least-cost intervention given the country s topography and relatively high costs of alternative energy such as diesel and oil. At feasibility study time, alternatives to the adopted design were investigated but ultimately rejected and it now appears when factoring in energy production (actual versus planned), down time due to mechanical problems in the turbines, that including considerations of operational costs into decision making process may have changed the design of the plant. Reference is made to $20 million to be invested into the plant to rectify problems (Main text, para. 61) including intake and desander configurations, cavitation on turbine parts, and vibrations in the powerhouse. In addition, procurement requirements, including international bidding will ensure that the executing agency receives competitive bids. For the lowest evaluated tender to represent approximately the least cost, value engineering (Main text, footnote 43) should be used to formally determine the least cost if it is such a concern. [Main text, para. 103] project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Procurement Sector Related Issues: Energy planning/management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/performance-evaluation-report-nepal-kali-gandaki-hydroelectric-project
Nepal: Corporate and Financial Governance Project | Nepal | Finance | 2012-12-10 | Pertaining to the appropriate balance between the hardware and software aspects of a development project, poor countries are rightly skeptical of borrowing only for consulting services because in the absence of the requisite infrastructure they fail to internalize outputs and derive gains from the institutional reforms in full. This affects the extent to which government ownership materializes through the course of implementation. The report and recommendation of the President summarized the lessons identified from prior financial sector reform projects on government ownership in terms of the reform agenda. [Main text, para. 33] project cycle stage: Implementation Lesson Topics: Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/nepal-corporate-and-financial-governance-project
Nepal: Small Towns Water Supply and Sanitation Sector Project | Nepal | Agriculture, Natural Resources, and Rural Development | 2012-12-10 | 1. The design of similar projects needs to be less complex, geographically contiguous, and realistic in scope given the time frame and available resources. [Main text, para. 21] project cycle stage: Design Lesson Topics: 2. Projects that involve active community participation and strong stakeholder ownership require adequate social preparation time. [Main text, para. 21] project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Ownership Capacity Development: Partnerships Methodologies/Approaches: Community approach Methodologies/Approaches: Participatory approach 3. A thorough institutional capacity assessment in all areas of project implementation is needed before capacity development support can be effective. [Main text, para. 21] project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity assessment Capacity Development: Capacity development | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/nepal-small-towns-water-supply-and-sanitation-sector-project
Community-Based Water Supply and Sanitation Sector Project | Nepal | Agriculture, natural resources and rural development | 2012-11-01 | Project implementation, monitoring, and supervision were logistically difficult and costly due to scattered subproject sites (both districts and village). Clustering the project area based on geographic contiguity and similarity should be considered when selecting project sites in order to improve the efficiency of implementation, monitoring, and supervision. Community mobilization should be conducted prior to water user and sanitation committee (WUSC) formation so beneficiaries will be fully aware and their participation effective. While nongovernment organizations (NGOs) were effective in community mobilization and raising awareness, their technical capacity was comparatively weak. Therefore, project formulation should include capacity assessment of all stakeholders. Simple technology and small systems are more sustainable, as operation and maintenance (O&M) responsibility for rural water supply is assigned to the community and VMWs are able to maintain these systems with limited technical skills. The project confirms that mandatory 50% participation of women and representation of caste and ethnic minorities in user-committee and executive positions that are proportionate to their populations will ensure their equal access to project benefits. Women's social empowerment can be achieved through social mobilization and capacity building in the process Covenants should be realistic and achievable to ensure sufficient control and quality of project implementation. A procurement plan needs to be prepared and agreed with the government during project design in order to define procurement requirements, create a sound financial justification for procuring these, and schedule those tasks by allocating time frames and resources. Retroactive financing and advance procurement action are needed to avoid start-up delays. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/community-based-water-supply-and-sanitation-sector-project-pcr
Urban and Environmental Improvement Project | Nepal | Finance, Health, Transport, Water and other urban infrastructure and services | 2012-11-01 | Along with consultations related to subproject design and scope, consultation with project towns on cost recovery, tariffs, and user charges is crucial for sustainability. The project should focus on a small number of physically integrated components to simplify project administration and optimize intersector linkages. Construction of sewerage and wastewater treatment plants (WWTP) was substantially delayed due to delays in land acquisition, preparation of a detailed design, and a change of site location. In order to avoid any unnecessary delay in the implementation of the project, sufficient attention should be paid to land acquisition in project preparation, and the land should be made available for the project prior to mobilization of the design consultant. The project could support the institutional reforms efficiently if there is a clear political will and stable government. Entities intended to manage operation and maintenance (O&M) for infrastructure should be established early in the project cycle, and staff trained throughout the implementation period, rather than at the very end. For operational sustainability, a long-term O&M contract could be incorporated into the construction contract for institutions having weak capacity and staff strength. Assessment of community attitudes to infrastructure, such as WWTP, should be better assessed at appraisal. For example, a participatory process to identify a feasible WWTP site would have prevented significant delays in the finalization of design and construction. A complex financing plan causes difficulties in consolidation of expenditures and slow submission of withdrawal applications. For effective gender mainstreaming and achievements, gender action plans should be prepared and agreed on by all agencies involved in project implementation. Sufficient financial and technical resources should be allocated for implementation of the gender action plan. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/urban-and-environmental-improvement-project-pcr
Economic Support Program | Nepal |  | 2012-10-01 | The program was successful in helping the government to stabilize the economy and protect vulnerable members of society and valuable lessons were learnt, particularly for other development partners, none of which had provided general budget support to Tonga before. Subsequent budget support operations by other development partners have drawn on the following lessons from ADB's experience. (i) Policy Actions need to match capacity. Technical and managerial capacity is a scarce commodity in small Pacific island nations. These were fully stretched in Tonga during the implementation of the program. In addition, the government was keen to receive ADB financing before the general elections were held, which led to ambitious, even unachievable, timeframes for completion. Therefore, the scope of the program needs to be kept as simple as possible to reflect the country's capacities, and policy actions for the release of tranches should be appropriate and achievable by the government and the executing agency. (ii) A single government-led policy matrix will enhance coordination and collaboration. The program provided a building block for future budget support operations to Tonga, for example, the World Bank's current operation. Coordination between development partners and the government has drawn from ADB's experience with the program to improve coordination and implementation. (iii) Verification requirements need to be clear from the outset. Information critical to the program was not disclosed during the design stage. More transparency through clear guidance on ADB's verification requirements would have avoided the delay in the achievement of policy actions. (iv) Technical assistance will aid program implementation. There is a need for technical assistance (TA) consultants to spend more time in the country (depending on the technicality of the policy actions) to deal with issues as they arise, and to support the timely delivery of outputs and outcomes. Related to this, umbrella regional TAs such as the Private Sector Development Initiative (PSDI) and Pacific Economic Management (PEM) have proven effective in terms of being able to rapidly and flexibly respond to Tonga's request for specific pieces of ad hoc analytical work as needed. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/economic-support-program-pcr
Rural Finance Sector Development Cluster Program | Nepal | Finance | 2012-10-01 | Program complexity and timing. The program was an ambitious attempt to reform the Nepal rural finance sector in a sustainable manner. In this, the program achieved several reforms that are likely irreversible. However, program implementation coincided with a challenging political situation: the transition from a monarchial to a parliamentary system. Thus, certain outcomes that required legislative actions could not be achieved due to non-functioning of Parliament. The complexity of program design and the implications of certain components for others added to implementation challenges, especially with respect to procurement. Program tranche. The loan tranches were front loaded with $40 million, disbursed at approval. Had the release been more back loaded, it is possible that the authorities would have had more incentive to obtain legislative approval when Parliament functioned intermittently. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-finance-sector-development-cluster-program-pcr
Secondary Education Support Project | Nepal | Education | 2011-12-01 | Design flexibility, accommodating changes for better alignment with emerging development objectives, improved implementation and contributed to reaching the desired results. Clear and precise documentation regarding when and what changed, and how the project goal, outcomes, and output were revised and embedded in new modalities, should be a critical element of this mind set. Benchmarking education quality reforms with international and regional best practices, is important and could have contributed to strengthened reforms. The dependence of reforms on proposed legal provisions should be analyzed. Both the development of the national curriculum framework and the decentralization of education could not be implemented fully because the legal provisions were not in place. Deliberately designing stakeholder participation and public debates on education policy reforms could have benefited implementation. The lack of broader stakeholder participation, particularly in the districts, risks losing ownership by implementing agencies. In the case of pool funding, efforts should be made to continue collaboration until the end, including a joint evaluation, to identify joint lessons and to maximize use of resources. Developing an indicator to measure quality improvements during the life of the project could have assisted in focusing the quality improvement interventions. A national assessment of student achievement using international standards is part of the school sector reform program. Grades 3, 5, and 8 will be assessed. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/secondary-education-support-project
Subregional Transport Facilitation Project | Nepal | Transport | 2011-12-01 | The absence of international joint venture partners in the implementation of international competitive bidding (ICB) contracts awarded to them was observed during project implementation. To ensure involvement of all joint venture partners in contract administration, it would be necessary for each individual joint venture partner to issue a guarantee against the collateral for their individual and joint liability. Issuance of individual and joint liability along with a performance bond would ensure liability for the work among all joint venture partners. The government needs to review and include interim milestone dates in the contract documents to ensure timely work completion and avoid extensions. There were some difficulties in contract administration between Department of Customs (DOC) and United Nations Conference on Trade and Development (UNCTAD). Although the contract for automatic system of customs data (ASYCUDA) was signed between Department of Roads (DOR) and UNCTAD, DOC was the main agency to supervise UNCTAD's work. DOC felt that it was less effective in the UNCTAD contract implementation because it was not a party to the contract. Contract provisions should have clearly stated the role, responsibilities, and implementation arrangements of DOC. The government needs to institutionalize a safeguard system within the organizational framework of the project, particularly during implementation, for effective monitoring and supervision of and timely compliance with safeguard covenants. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/subregional-transport-facilitation-project
Community Livestock Development Project | Nepal | Agriculture, natural resources and rural development | 2011-11-01 | Poverty mapping was a useful tool to determine the beneficiaries and suitable ways to involve them in project activities. However, to include women and the disadvantaged in commercial processing and marketing enterprises that require more resources and better skills, alternative approaches are needed, such as organizing skills training in their areas of interest, easing access to institutional loans on a group guarantee basis, and establishing links with marketing institutions. Privatization of public sector enterprises is not sufficient to achieve growth in the dairy industry. Strong links with milk-producing farmers and cooperatives are needed to ensure uninterrupted milk supplies to milk processors, achieve full capacity, and maximize investment benefits. Public-private partnership is an effective approach to promote private sector participation in the livestock subsector. This has been demonstrated by the successful operation of project-assisted meat and dairy shops, abattoirs, paravets, and veterinarians. Effective implementation of laws and regulations on operation of slaughterhouses coupled with a consumer awareness program are essential to improve hygienic meat processing and marketing, and optimize benefits from project support. The Rural Microfinance Development Center (RMDC)-supported microfinance institutions (MFIs) were successful in delivering loans and ensuring timely repayment in areas with enough opportunities to earn daily wages. However, for areas without such opportunities, farmer cooperatives should be developed to deliver loans. These cooperatives have low overheads and function even in adverse geographic and political conditions because of their community ownership. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/community-livestock-development-project
Teacher Education Project | Nepal | Education | 2011-09-01 | The absence of motivation and incentives for teachers and an effective mechanism for monitoring teachers' classroom performance emerged as major reasons for the overall improvement in the classroom teaching-learning process. Establishment and institution of a strong monitoring and evaluation and teacher support mechanism at the classroom level was necessary at the beginning of the project to continuously oversee the teaching-learning processes and provide professional support to the teachers to use the knowledge, skills, and attitudinal changes gained during training. Available evidence on using resource centers for extending professional support and services to the teachers shows it has not been very effective. The current structure of the resource centers needs to be reconceptualized with increased capacity under the School Sector Reform Program. The design and monitoring framework of the project had weak linkages among impact, outcome, and output indicators. Improvement in the overall quality and efficiency of primary education depends on many factors apart from teacher training. The outcome and output indicators were repeated. Since the National Center for Education Development (NCED) as a regular department rather than a separate project implementing unit within the NCED was involved in project implementation, there was strong ownership and coordination among stakeholders, which facilitated implementation of the project. It is difficult to implement reform measures in a country during periods of political transition, as vested interest groups actively protect their interests. Although the public-private participation approach is an efficient way to implement project activities, the effectiveness will largely depend on close follow-up monitoring and strict adherence to the selection criteria. The in-service training provided by alternative training providers was ranked low as compared to the training provided by primary teacher training centers (PTTCs) and secondary education development units. Even though the Higher Secondary Education Board (HSEB) and Faculty of Education are now taking responsibility for pre- service teacher training, there is still a need to financially support them in developing their capacity to deliver pre-service teacher training. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/teacher-education-project-0
Road Network Development Project | Nepal | Transport | 2011-08-01 | Effective orientation programs on project approaches, implementation modalities, and the roles of stakeholders contributed to successful project implementation. Implementation partners should be well informed of the approaches and strategies of the project prior to implementation. The absence of international joint venture partners in implementation of international competitive bidding (ICB) contracts awarded to joint ventures was observed during project implementation. In all cases, it was clear that the local contractors had applied for prequalification and submitted bids in joint venture with a foreign partner simply to meet the pre-qualification and post-qualification requirements. This defeated one of the main purposes of a joint venture, which is for the local contractor and, ultimately the client, to benefit from the experience, expertise, capability, and resources of an international foreign partner. To ensure involvement of all joint venture partners in contract implementation, it would be necessary to review the threshold for ICB and national competitive bidding (NCB) contracts for road construction works to have fair competition among the bidders. A few civil works contracts could not be completed even after extending the loan closing date by 18 months. The timeframe, working season, and site analysis should be considered prior to award of contract to ensure timely completion of the contracts. The project was implemented during the conflict period (2001-2006) and it faced challenges from local communities, which made additional demands and at times disrupted the work progress. Part A could not be completed as it was highly affected by unrest in Terai. A proper analysis of road design and selection of road sections should be carried out during the design phase to ensure timely completion of the selected road sections is possible. During the implementation of Part C, the change in construction method from labor to equipment based (otta seal standard) had an effect on the original road length. Detailed study on the construction method needs to be carefully undertaken during the design phase to avoid changes during the implementation phase. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/road-network-development-project
Corporate and Financial Governance Project | Nepal | Finance | 2010-12-01 | Proper sequencing and project readiness. Proper sequencing of project activities is essential for project success. The project had strong policy, legal, and regulatory content, some of which were addressed through conditions for loan effectiveness and disbursement. However, several more policy, legal, and regulatory reforms were to be supported through the cluster technical assistance (TA) that was approved with the project. Fact-finding for cluster TA was conducted only after project approval. In the absence of an enabling policy and regulatory environment, several project activities were either delayed or had to be cancelled altogether. There were also gaps in terms of project readiness. For instance, the project preparatory TA for assessing the feasibility of component 3 was only approved after project approval. When the project preparatory TA concluded that this component was not financially viable, it had to be cancelled. Capacity constraints and project complexity. Overly ambitious and complex projects are less likely to be successful. The project, which attempted to tackle a wide range of issues in several subsectors within a short time frame, was too complex given the capacity constraints of the Ministry of Finance (MOF) and the implementing agencies. Although the MOF had effectively executed ADB projects before, those projects were considerably less complex. Several implementing agencies had little or no previous experience in development-partner-funded projects. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/corporate-and-financial-governance-project
Small Towns Water Supply and Sanitation Sector Project | Nepal | Water and other urban infrastructure and services | 2010-09-01 | Project design should accommodate the complexity of community participation and the time it requires. Adequate attention should be paid to capacity development in communities to ensure the sustainability of water supply and sanitation (WSS) facilities. Effective orientation programs on project approaches, implementation modalities, and the roles of stakeholders contribute to successful project implementation. Implementation partners should be well informed on the approaches and strategies of the project prior to implementation. Community organizations require continued support during and after the transition to the post-construction period to ensure the sustainability of water supply facilities. Capacity development needs to cover not only the technical aspects of operation and maintenance (O&M) but also financial management, water demand management through public awareness campaigns, and the protection of water sources including water conservation. The first year of operation can be assigned to the contractor to provide incentives to improve the quality of construction and achieve the early completion of works. Preparing the project management and operation manual before the inception of the project will address initial operation and sustainable issues. In community-based projects, water user and sanitation committees (WUSCs) can act as reliable facilitators between the project and beneficiaries. The participation of local communities during both design and implementation is crucial for project sustainability and effective project implementation. Better linkage between health outcomes and WSS outputs should be promoted in WSS projects by including sanitation, hygiene, and health promotion activities in project design. Extensive and thorough investigations of potential project sites need to be carried out to the extent possible during feasibility studies and detailed design to ensure that designs are appropriate. Experience shows that design shortcomings have caused significant implementation delays and numerous contract variations. All components of projects should be treated as important and monitored from the early stages of project implementation. The difficulty of establishing technical support centers in five development regions of Nepal under the technical support components was mainly because the executing agency (EA) accorded them low priority and ADB did not follow up sufficiently. A unit to provide technical support to WUSCs should be established in an early stage of the project, and the staff of WUSCs should be trained throughout the project implementation period, rather than just at the end. ADB should be more involved in ensuring that appropriate mechanisms for providing technical support are in place and that the unit's capacity is strengthened. Five regional technical support centers were established very late in the project, and only one center was staffed by two people, who do not know how to operate some of the equipment. Team leader inputs should be adequately provisioned in engineering and design consultant contracts to ensure timely technical support and advice for town projects to facilitate timely decisions. A capacity-development program for beneficiaries needs to be well planned and implemented in accordance with the project implementation schedule and progress. A monitoring mechanism to measure the effectiveness of the capacity development programs needs to be established. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/small-towns-water-supply-and-sanitation-sector-project-0
Nepal: Governance Reform Program | Nepal | Public Sector Management | 2010-04-30 | 1. An ambitious, complex program or project should not be launched without being fully equipped with adequate technical assistance and other requisite resources, particularly when the design does not provide the option of accessing funds under the loan. [Main text, page 6, section E(ii.a)] <!-- project cycle stage: Design Lesson Topics: Modality: Program Modality: Project Modality: Technical Assistance --> 2. ADB must recognize that on-the-ground conditions in the borrower country may change substantially while a program or project is under preparation, especially if the preparatory process is long and the nature of unrest borders on social conflict and violence. [Main text, page 6, section E(ii.b)] <!-- project cycle stage: Design Lesson Topics: Modality: Program Modality: Project Project Design: Project design Country Context: Conflict/Post-conflict --> 3. If a program or project appears to be ambitious and complex and runs against changing on-the-ground conditions, there should be flexibility in implementation plan to reduce the scope and focus on the essential core of the program or project. The policy matrix should clearly identify such core issues beforehand. [Main text, page 6, section E(ii.c)] <!-- project cycle stage: Design, Implementation Lesson Topics: Modality: Program Modality: Project Project Design: Project design Country Context: Conflict/Post-conflict --> | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/nepal-governance-reform-program
Country Assistance Program Evaluation for Nepal: Delivering Assistance in a Challenging Environment (2009) | Nepal |  | 2009-06-30 | 1. Adoption of conflict-sensitive approach helped ADB deliver its assistance to Nepal's difficult operating environment. Strong local community support and highly relevant program and projects facilitated the implementation of ADB support during periods of conflict and political instability. Conflict assessment and participatory approaches incorporated in all sector projects and programs enabled ADB assistance to progress in many cases despite the challenging environment. [Executive summary; Main text, paras. 33, 39, 129-130] project cycle stage: Implementation Lesson Topics: Country Context: Conflict/Post-conflict Methodologies/Approaches: Civil Society Participation 10. Community projects need to be consistent with the capacity of local governments. ADB experienced capacity constraints in local governance, as it is still weak and procedures for transferring funds to local authorities are not yet in place. Reform for local government finance and a more effective system of supervising and monitoring CSOs are necessary steps toward gradual decentralization and a more effective public service delivery. They need to take place simultaneously with clear national and local roles. The number of districts, regions, and CSOs with which ADB operates should be consistent with its capacity for project design and implementation support. [Executive summary; Main text, para. 142] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Capacity Development: Capacity development Policy & Reform: Reform 11. Improved capacity and human resource development at all levels in the government are crucial for sustaining sound fiscal management and maintaining macroeconomic stability and peace. There is a pressing need for post-conflict support to assist the Government in strategizing and policy making in all areas related to binding constraints on development, as Nepal is going through a critical time of postconflict recovery. Economic and sector work would be useful in the area of cooperatives (rules, regulations, supervision), remittances, quality assurance and sustainability in local communitydriven development works. This can be achieved by providing cluster technical assistance under the ADB Nepal Resident Mission that could respond to the country's urgent requests. [Executive summary; Main text, para. 143] project cycle stage: Country Partnership Strategy Lesson Topics: Capacity Development: Capacity development Capacity Development: Human resources management 12. While the strategic focus of the CSP was relevant in 2004, there is a need for continued assistance to the Government in addressing infrastructure deficits and so contribute to achieving economic development through increased connectivity, access and social inclusion. Equally important and, to a certain extent, re-enforcing is to provide further support to improving governance by strengthening institutional capacity for public service delivery and results-based management, and by reducing opportunities for corruption through support and policy dialogue for law enforcement and better transparency in public spending. While long-term engagement is important for achieving development results, a narrowly focused approach to sector and subsector coverage would be expedient. Combined with these, private sector development and regional cooperation are other areas for continued ADB assistance. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Sector Related Issues: Private sector Methodologies/Approaches: Sectoral approach Methodologies/Approaches: Targeting 2. Continued ADB support during the conflict situation was possible through active involvement of civil society organizations (CSOs). ADB continued its operations even during the insurgency, limited implementation and outreach capacity, and absence of elected members in the local governments. During this challenging phase, as prevailing lawlessness and insecurity made it more difficult for ADB to establish direct contact with local communities, the CSOs have filled the niche. The role of CSOs for building consensus among political parties and warring factions at the local level, as well as for social mobilization and raising awareness within the community was essential. [Main text, paras. 38, 141] project cycle stage: Implementation Lesson Topics: Country Context: Conflict/Post-conflict Methodologies/Approaches: Civil Society Participation 3. The adoption of a socially inclusive approach in Nepal has led to improvements in irrigation and other services to agricultural communities, higher quality and availability of education for the poor and excluded, improved rural roads to bring excluded regions and communities into the economic mainstream, and the provision of basic water supply and sanitation in smaller towns and cities. If inclusive growth is to continue, the Government will need to focus on the continued delivery of social services to rural and urban areas. Sustaining efforts towards inclusive growth requires participation of local and regional user groups in the budgetary process. This could build on the piloted system of performance-based funding of local bodies, and the medium-term budgeting introduced in districts, municipalities, and villages over the past few years. [Main text, para. 131, 140] project cycle stage: Country Partnership Strategy Lesson Topics: Country Context: Conflict/Post-conflict Policy & Reform: Policy reforms/framework Methodologies/Approaches: Targeting 4. Experience with supporting universal education through the sector-wide approach (SWAp) has been positive as it brought more coherence to capacity development in the sector. The line ministry, educational institutions, district education offices, school management, and resource centers' teacher-training institutions were strengthened using ADB support. In continuing to develop and expand primary and secondary education of higher quality and with easier access, the lessons and experiences gained from the implementation of ADB support to the Government's school sector reform program in pilot districts will be invaluable for planning further actions towards the fully fledged adoption of school sector reform. [Executive summary; Main text, paras. 58,133; Appendix 9] project cycle stage: Design, Country Partnership Strategy Lesson Topics: 5. Support for legal reform particularly in promoting good governance needs to go beyond assisting in drafting laws to achieve the intended development outcome. Capacity constraints have undermined results to ADB's support in combating corruption and improving public service delivery. There are still many institutions in Nepal with large capacity gaps, including the judiciary; and enforcement needs to be strengthened if the legal and judicial systems in Nepal are to lead to the intended development results. [Executive summary; Main text, para. 134] project cycle stage: Operation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system 6. While the conflict, security concerns, and transport strikes have been important reasons for implementation delays, other factors persistently affecting project implementation are project design deficiencies; start-up delays; frequent changes of project officials; and constraints on budgets, institutional capacity, and project monitoring and evaluation. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Funding Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Human resources management 7. The results-based approach introduced by the CSP has been useful to the Government and ADB as it tried to identify links to the results sought by the Government to which ADB will contribute. There is still a lot of scope for further improvement, particularly in terms of reporting on outcomes, ADB contribution, and adding the results of ADB's TA operations as well. Moreover, on the Government's side, mainstreaming the tested approach and internalizing it will be fundamental for continued success and sustainability. [Executive summary; Main text, para. 136] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Benefit monitoring and evaluation 8. The efficiency and sustainability of ADB-funded infrastructure projects were affected not only by the conflict but also by infrastructure policy, institutional, and capacity constraints, particularly the lack of reform, and by low public investment. project cycle stage: Operation Lesson Topics: 9. Rural and urban roads and power supply are necessary to address infrastructure deficits. There is a growing influx of people from rural to urban areas, putting pressure on roads, housing, and public utilities and requiring the development of urban infrastructure. Opportunities have emerged to develop large power projects to generate export revenues and gain economies of scale in supplying power to domestic market. This scenario illustrates the need to make clear strategic choices so that small and large, rural and urban infrastructure projects can be appropriately timed and sequenced. Pursuing these options would require a lot of capital investment that should come from mobilizing the resources of the private sector, as well as from other development partners. ADB should play a catalytic role in this regard, something similar to the approach taken for West Seti Hydropower Project. [Executive summary; Main text, para. 138] project cycle stage: Country Partnership Strategy Lesson Topics: Sector Related Issues: Private sector Sector Related Issues: Urban sector/development | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-nepal-delivering-assistance-challenging-environment
Irrigation Management Transfer Project | Nepal | Agriculture, Natural Resources, and Rural Development | 2006-12-15 | 1. Establishing and strengthening water users association (WUAs), and planning and rehabilitating systems with the active participation of users instills beneficiary ownership of subprojects. However, before users take over responsibility for operation and maintenance (O&M), systems should be functional and able to deliver irrigation water to farmers fields with key structures rehabilitated and the canal network intact. This would also ensure the collection of the irrigation service fee (ISF) and the undertaking of routine O&M through local resource mobilization. In this project, weak performance of some irrigation systems were noted due to lack of O&M and beneficiary ownership. [Main text, paras. 12, 24, 31-32, 38] project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Subprojects Project Management: Operation and maintenance Capacity Development: Ownership Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation 2. The formation and basic capacity building of user groups and associations require sufficient lead-time before planning and rehabilitation are started. User capacity needs to be further developed by involving users in project implementation with clearly defined roles and skills-development training to ensure that they possess the necessary capacity to manage the system after completion. In this project, lead time was insufficient for orientating and training users before the commencement of construction works. Project performance was consequently affected by the lack of proper operation and maintenance and beneficiary ownership. [Main text, paras. 5, 18, 40] project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Project management Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Irrigation management 3. Small and medium systems with independent intakes or headworks have considerable potential for rehabilitating structures and reestablishing canal networks in collaboration with users and for transferring management responsibility to water users associations (WUAs). Lack of executing agency capacity to mobilize huge numbers of users constrains users' intensive involvement in planning and implementation, which limits their interest in contributing to effective system on operation and maintenance. [Main text, para. 41] project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project management Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation 4. At times, the quality of project design and implementation suffered as (i) some designs were inappropriate, (ii) proper mechanisms for quality control were lacking, and (iii) construction supervision by senior, experienced technicians was lacking. These shortcomings can be avoided by obtaining independent consultant services to supervise and maintain quality control of design and construction works and by effectively involving users in monitoring subproject implementation at different stages. [Main text, paras. 5, 25, 42] project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Consultants Project Management: Project supervision Methodologies/Approaches: Consultation/Participation Experience has shown that water users associations (WUAs) should be established first at the lowest control unit,the tertiary canal, and then established moving upward to branch and main canals. This makes each user familiar with the potential and constraints of the system and the WUAs representative and effective. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management In larger irrigation systems, WUAs at different tiers (main, secondary, tertiary canal) with clearly defined roles and functions could secure more effective beneficiary participation and system ownership. Efforts could be made to turn over secondary and tertiary canals in the larger systems. project cycle stage: Design Lesson Topics: Project Design: Project design Capacity Development: Capacity development Capacity Development: Ownership Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/irrigation-management-transfer-project
Rural Infrastructure Development Project | Nepal | Transport | 2006-12-15 | A package approach needs to be used for poverty reduction. Income generation and local development activities need to be integrated with road construction, taking road construction as an entry point for poverty alleviation. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach A simplified procedure for approval and payment should be established and put into operation before any construction starts. Laborers must be paid daily or at least once every 15days. This could be done as advance payment to laborers based on the attendance and daily rates to be cleared after completion of pieces of work. project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Procurement Sector Related Issues: Roading Sector Related Issues: Rural development Construction of roads following the labor-based, environment-friendly and participatory (LEP) approach should not be rushed. Time is needed to inform the local laborers about the approach and for all concerned to gain some on-site LEP experience. The initial construction stage should emphasize capacity building and should establish practical procedures for doing things properly and not just concentrate on achieving quantitative outputs. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Project supervision Capacity Development: Capacity building Sector Related Issues: Roading Methodologies/Approaches: Participatory approach Construction of roads using the labor-based, environment-friendly and participatory (LEP) approach requires a high level of site supervision to ensure quality standards and to support and guide labor groups. Provisions should be made for the continuous presence of trained supervisors on the site for timely measurement of completed works and timely payment. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project supervision Sector Related Issues: Roading Methodologies/Approaches: Participatory approach Despite the existence of conflict, development work is possible if community participation is high and the project is seen to be addressing urgent needs. Project experience demonstrated that, if the project is transparent and has the effective participation of local people, activities can be implemented even in armed conflicts. The engagement of local NGOs can ensure that local people are better informed and mobilized. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Project Design: Project design Country Context: Conflict/Post-conflict Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Maintenance of roads needs to be considered from the planning phase to the post-construction phase. Commitments need to be monitored against indicator(s) during the implementation stage, so that a reliable mechanism to carry out operation and maintenance after construction can be put in place. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Roading Public auditing is an excellent approach for ensuring financial transparency. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Public governance Social mobilization should be conducted before the local road users' committee (LRUC) and the labor group areformed, so workers are fully aware of how work is measured and wages paid. The social mobilization process should be given much more emphasis and sufficient time should be allowed for it to take place. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation The roles and responsibilities of institutions and other stakeholders involved in the planning, implementation, and post-implementation of the project should be clearly explained and agreed with concerned agencies while the project is being designed in order to avoid confusion and conflicts. Local institutions and offices should be given full authority for implementation of community-based rural infrastructure. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Rural development Methodologies/Approaches: Community approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-infrastructure-development-project
Third Livestock Development Project | Nepal | Agriculture, Natural Resources, and Rural Development | 2006-03-15 | 1. Continuation of project staff (particularly the project manager and other key staff) has contributed significantly to successful project implementation. It has also ensured continued feedback about field experiences to policy level, and served as a basis for better project design. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project management Capacity Development: Human resources management Policy & Reform: Policy reforms/framework 2. The private sector has been effective in delivering extension services to farmers where there is good accessibility and capacity to pay for services. Thus, increased involvement of private sector is needed to meet the demand for services. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity assessment Sector Related Issues: Extension service Sector Related Issues: Private sector Sector Related Issues: Rural development Baseline project area data should be collected before project implementation to facilitate periodic monitoring and impact evaluation. A monitoring system should be established before the project begins, and staff should be trained and assigned to implement the system with clear terms of reference. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Capacity Development: Capacity building Involvement of local stakeholders - to identify needs and deliver services to poor and disadvantaged people and women - was critical to achieving project objectives. Greater involvement of stakeholders at different levels is necessary during project design. Local knowledge should be utilized, people's needs should be analyzed, and their participation should be ensured in implementation and monitoring. Strategies and modalities for project implementation should be adjusted according to changing situations. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project management Methodologies/Approaches: Consultation/Participation The inclusion of districts for project implementation should be planned properly. More programs for relatively longer periods should be targeted at poorer districts. The impact will suffer if the project is implemented in a district for a very short period of time. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Country Context: Decentralization Methodologies/Approaches: Targeting When recruiting consultants, careful consideration should be given to the background, suitability, and timing for individual consultants' inputs. Consultant input should be properly interrelated and coordinated (with each other as well as counterparts) to maximize collaborative efforts and allow effective transfer of knowledge. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Capacity Development: Technology/Technology transfer Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-livestock-development-project
Second Tourism Infrastructure Development Project | Nepal | Industry and Trade | 2005-12-15 | ADB should insist on enforcement of bylaws and regulations, such as penalties on illegal septage disposal and solid waste disposal. The drainage system, which was designed purely for storm water, is channeling raw sewerage into the (Phewa) lake, because of illegal dumping of septage. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management Airport expansions should have considered projected traffic forecasts, and allocated land for future expansion. In Lukla, airport traffic has increased significantly and is now congested. However, new land for expansion is difficult toacquire because of new construction around the airport. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Transport planning Assessment of community attitude to infrastructure, such as waste disposal, should be better assessed at appraisal. For example, a participatory process to identify a feasible waste disposal site would have prevented significant delays in the implementation of the project. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Appraisal Project Design: Project design Capacity Development: Capacity assessment Methodologies/Approaches: Participatory approach Assurances of the government and implementing agencies should be scrutinized more carefully at appraisal stage, in view of past experience during implementation of the first tourism infrastructure development project. Only realistic assurances, based on proper assessment of institutional capacity and political context, should be incorporated as covenants in the Loan Agreement. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Project Design: Appraisal Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Sector Related Issues: Industry and Trade Capability enhancement of implementing agencies should be carried out well in advance of implementing infrastructure components based on a thorough institutional assessment. Virtually all the problems in the (Pokhara) environmental improvement component of the project were rooted in the poor capacity of the implementing agency. More emphasis should have been placed on strengthening its capacity prior to the commencement of physical works. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Institutional analysis Designs of environmentally sensitive infrastructure systems should anticipate the impacts of noncompliant behavior by the public. The drainage system (in Pokhara) discharges all water into the (Phewa) lake. Although designed for storm water, many residents have directed their sewerage lines into the drains, which will, over time, cause significant contamination of the lake. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management Entities intended to manage O&M for infrastructure should be established early in the project cycle, and staff trained throughout the implementation period, rather than at the very end. ADB should be more involved in ensuring the appropriate institutions are in place, and that their capacity is strengthened. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Project Management: Project supervision Capacity Development: Capacity building Land acquisition needs should be addressed up front, before infrastructure construction is started. Designs should be modified if land acquisition is not likely. In Pokhara, the drainage system is generally complete. However, three sedimentation traps were not constructed because the proposed land could not be acquired. Over time, this will cause increased sedimentation in Phewa Lake. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Project Design: Project design Sector Related Issues: Water resource management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/second-tourism-infrastructure-development-project
Upper Sagarmatha Agricultural Development Project | Nepal | Multisector | 2004-11-15 | Although the target-oriented approach may have worked well in delivering required outputs, overemphasizing accomplishments in terms of numbers might have affected the quality of outputs. Poor construction quality could have partly resulted from placing too much emphasis on completing lengths of environment friendly roads (EFRs) while setting aside compliance with EFR guidelines andconcerns related to the geological condition of the terrain. project cycle stage: Implementation Lesson Topics: Sector Related Issues: Roading Methodologies/Approaches: Targeting Any support for the construction of infrastructure, including buildings and bridges, must address operation, maintenance, and sustainability aspects from the very start. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Roading Delayed and often very late payments to workers and a lack of measurement transparency are the main reasons for distortion in the users group approach and the occurrence of hidden contracts. A simplified procedure for approval and payment must be put in place. This is frequently done through a system of partial advances to workers (at least fortnightly). Moreover, transparent measurement and full pay for workers must be ensured. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Finance & Financial Aspects: Disbursement Project Management: Procurement Implementation of environment friendly roads (EFRs) should not be rushed. Implementation is needed for local laborers to become aware of the concept and gain some on-site experience and for all concerned to become accustomed to all systems and procedures. The initial stage of construction should emphasize building capacity, setting practical procedures, and doing things correctly, rather than achieving quantitative outputs. Road construction by mobilizing local labor and using EFR principles requires intensive social mobilization and information dissemination sufficiently in advance of implementation, to ensure effective participation by the genuine beneficiaries. In this way, the quality and speed of works will gradually improve. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Capacity Development: Capacity building Crosscutting Issues/Themes: Employment Sector Related Issues: Roading Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Improved rural infrastructure is a key to agriculture development and income improvement in rural areas. Therefore, to achieve project benefits or ensure sustainability, the project area should be made accessible. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Sector Related Issues: Rural development Strong, reliable, relatively independent and timely monitoring systems, with appropriate procedures to provide feedback and ensure actions based on the monitoring findings, are necessary. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: When recruiting consultants, careful consideration should be given to the background and suitability of the technical personnel fielded by the consulting firm. If the consulting industry lacks specific experience in particular technical applications, such as environment friendly roads (EFRs), training must be provided. Since EFR construction is a relatively new concept, training may be needed at all technical levels, down to labor groups. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Management: Consultants Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Roading While designing the project, people's demands and needs should be analyzed thoroughly, and their participation should be strengthened at all stages of the project cycle. Frequent changes in the implementation arrangements and administration structure of the project created confusion and caused delays. Should there be genuine need for modifications, these should not be carried out without careful analysis of all relevant aspects, in consultation with all stakeholders. When management issues are particularly problematic or complex, briefly engaging an independent specialist to assist with analyses and make recommendations may be preferable. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Consultants Project Management: Project administration Project Management: Project management Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/upper-sagarmatha-agricultural-development-project
Country Assistance Program Evaluation for Nepal (2004) | Nepal |  | 2004-09-30 | A thorough assessment of the capacity of executing and implementing agencies to meet conditions of disbursement is just as essential as an assessment of overall institutional capacity. Unrealistic or unattainable conditionalities have delayed a number of projects and program loans. This is especially serious for project loans wherein physical investments might be significantly delayed while conditionalities are being met. project cycle stage: Feasibility, Appraisal Lesson Topics: Loan Agreement: Covenants Modality: Lending modality Modality: Program Project Management: Executing/Implementing agencies Project Management: Project administration Capacity Development: Capacity assessment Capacity Development: Institutional analysis An important purpose of a country strategy program (CSP) is to allow ADB and the government to make choices between one type of investment or another in an environment of limited resources. To be of value, a CSP should be specific and defined well enough so that a decision can be readily made about whether a particular project meets its priorities or not. There needs to be some basis for a sorting mechanism among proposed projects, just as there needs to be flexibility in changing or adapting the strategy as conditions change and develop over the implementation period. It would seem to be preferable to have a tight and properly defined CSP, with the facility for changes as and when justified, than a generally loose and open CSP that would allow almost any sort of investment, if a poverty-reducing rationale can be devised. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Project evaluation Country Context: Prioritization Policy & Reform: Policy reforms/framework At times, following the general guideline of keeping projects simple, using proven models and using effective agencies, is not possible. In some cases, there seems no alternative but to take on a difficult, complex project with a new or weak implementing agency. In such cases, projects must be prepared with very thorough planning and implemented with strong supervision and a high degree of attention from either consultants or ADB staff members. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project supervision Institution-building assistance often focuses on strengthening state agencies and enterprises to meet project-specific needs. Planning for institutional strengthening should reflect broader and longer-term sector development needs and include consideration of alternative institutional arrangements, such as community institutions, public utility and state enterprise privatization, central government agency role transformation, and public services provision contracting. Institutional building should focus more on strengthening the recipient organization's culture and orientation for efficient and timely delivery of services. The process should include activities to change (i) attitudes, commitment, and skills in dealing with communities; (ii) structures of institutions; and (iii) policies and procedures. project cycle stage: Design, Feasibility Lesson Topics: Modality: Program Project Design: Project design Capacity Development: Capacity building Capacity Development: Institutional analysis Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Public sector reform Policy & Reform: Reform Methodologies/Approaches: Community approach Large-scale projects represent an important aspect to strategy formulation in that they absorb a significant degree of the country's and ADB's financial and manpower resources. For that reason, the programming of future large-scale projects should be approached with caution, and the design of such projects (if taken up) should be undertaken with great care. project cycle stage: Concept, Design, Country Partnership Strategy Lesson Topics: Project Design: Problem identification Project Design: Project design Projects that, through innovation and imaginativeness, attempt to address crosscutting issues, such as beneficiary participation, gender equity, social inclusion, and environmental soundness, in their design are also most likely to be efficiently and effectively implemented and have a high degree of positive development impact. It may be argued that it will be easier to do this in some sectors than in others, but even in physical infrastructure projects or program loans, being innovative is possible, as is preceding the investment with a strong public information campaign. Delays and project implementation disputes on several projects might have been avoided or at least mitigated if potential users and beneficiaries were consulted and better informed of project or program intentions. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Social protection Modality: Program Project Design: Project design Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation Projects undertaken by sound institutions succeed, and projects undertaken by weak institutions experience implementation difficulties. At this time of limited Asian Development Fund resources, this is a particularly important point. Little call exists to design projects in sectors with weak institutions, especially when the limited resources available can be more effectively used in sectors with efficient and sound institutions. Therefore, it is required to fully assess the institutional capacity of agencies responsible for proposed projects and avoid projects that would be dependent on weak institutions. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity assessment Capacity Development: Institutional analysis Successful projects or models among projects being undertaken by bilateral sources of assistance or NGOs should be identified and scaled up. A high degree of success was achieved in water supply projects, irrigation projects, and road projects. One of the primary reasons for this is that many projects in these sectors were based on a model developed over the past two decades. ADB and executing agencies' staff members know what is expected, what procedures to follow, and how to implement projects on a step-by-step basis. Pioneering projects are bound to suffer a series of delays and setbacks, especially if the agency is new and not experienced with multilateral and, especially, ADB procedures. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Civil society Project Management: Executing/Implementing agencies Project Management: Project administration Capacity Development: Capacity building Sector Related Issues: Irrigation management Sector Related Issues: Roading Sector Related Issues: Water resource management There needs to be consistency between a Country Operational Strategy and Country Strategy Program. Since projects and technical assistance activities are the instruments used to implement a strategy, any Country Strategy Program is only as good as the projects placed in the country program. Without continuous reference to the strategy during annual country programming exercises, deviating from or missing out on important features of the strategy becomes possible. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Project Design: Problem identification Policy & Reform: Policy reforms/framework | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-nepal-2004
Fourth Rural Water Supply and Sanitation Sector Project | Nepal | Water and Other Urban Infrastructure and Services | 2004-06-15 | Arranging buffer stock for pipes and fittings should be more efficient and supported by a strong accounting and inventory control system. This should be closely linked with overall subproject monitoring systems, to ensure proper accounting of subproject costs, efficient use and distribution of supplies to subprojects, and effective inventory management. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Procurement Frequent turnover of field-based staff members disrupted subproject implementation, especially social mobilization activities that require close working relationships with communities and continued confidence-building measures. The community development process becomes even more disrupted when new staff members are not properly trained or lack relevant experience. project cycle stage: Implementation Lesson Topics: Project Design: Subprojects Capacity Development: Capacity building Capacity Development: Human resources management Methodologies/Approaches: Community approach Given the active involvement of many development partners - government agencies, external aid agencies, and NGOs - in the water supply and sanitation sector, interventions in the sector need to be well coordinated and complementary to each other, to ensure efficient resource use and effective service delivery. In line with this, the project could have collaborated more closely with other agencies active in the sector, building on effective design and implementation experiences, particularly with respect to sanitation development. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation One of the key objectives of social mobilization should be to ensure strong and broadly represented water users committees (WUCs) through a democratic process. Often, WUCs are dominated by the local elite, who tend to ignore the interests of weaker and disadvantaged groups in given communities, resulting in skewed project benefits distribution. In this respect, project designs should include clear procedures for effective mainstreaming of the interests and roles of disadvantaged groups, including women and the poor, to ensure more equitable sharing of project benefits and effective poverty reduction impacts. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Sector Related Issues: Health and sanitation management Methodologies/Approaches: Community approach Sanitation development should be an integral part of rural water supply projects, to maximize development and poverty reduction impacts. Demonstration latrines, hygiene education, and awareness campaigns are not adequate and should be complemented by more tangible support (e.g., revolving funds), to encourage households to build more durable sanitation facilities. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Policy & Reform: Information dissemination/Public awareness Some effective ways to make subprojects cost-effective include promoting effective community participation; making subproject designs, including cost estimates, public and transparent; and developing clear mechanisms for substantive but equitable community contribution. These actions will create incentives for communities to explore ways to reduce subproject costs. An effective community-based approach should include community organization capacity building and empowerment. This can be done by entrusting organizations with more responsibility and giving them decision-making roles in subproject planning and implementation, including roles related to financial and procurement matters, and distribution of project benefits that follow. This, accompanied by clear and transparent working procedures, will help promote community ownership of the implementation process and project facilities from the beginning and ensure continued community engagement and active participation. The concept of handing over subprojects to communities toward the end therefore becomes irrelevant and unnecessary. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Project Management: Procurement Capacity Development: Capacity building Capacity Development: Ownership Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Sufficient time needs to be dedicated for social mobilization activities, and construction activities should not be rushed. Adequate social mobilization is essential for full understanding of project objectives and procedures at the community level, stronger community ownership and participation, and effective implementation and sustainability. Social mobilization should not be limited to water users committee (WUC) members and should be aimed at the community at large, through effective mechanisms, such as training of local school teachers, community leaders, and political leaders. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity development Capacity Development: Ownership Sector Related Issues: Health and sanitation management Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation The implementing agency's community development efforts can be further enhanced by close partnerships with local non-government organizations (NGOs) and community-based organizations that are better positioned to effectively interact with communities on a continuous basis. Significant scope exists for replicating the partnerships with NGOs initiated under the project. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Partnerships Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach The project's important social and economic impacts could not be properly assessed, due to unavailable baseline data and poor Benefit Monitoring and Evaluation (BME). Rural water supply and sanitation project design should therefore include a prominent component for strengthening executing and implementing agencies' monitoring systems, with necessary support for establishing proper institutional mechanisms and capacity building. project cycle stage: Design, Feasibility Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Weak subproject implementation monitoring resulted in inadequate social mobilization, weak implementation of the project's sanitation component, and unsatisfactory outputs under some subprojects. An effective monitoring system to closely monitor all stages of implementation will ensure better sequencing of subproject activities (e.g., completing adequate social mobilization activities before proceeding with the construction phase and troubleshooting of key implementation issues in a timely manner). project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Sector Related Issues: Health and sanitation management Methodologies/Approaches: Community approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/fourth-rural-water-supply-and-sanitation-sector-project
Kali Gandaki 'A' Hydroelectric Project | Nepal | Energy | 2004-04-15 | For environmental, social, and resettlement issues, the Acquisition, Compensation andResettlement Plan, and the reports by the panel of international experts focused excessively onemployment and temporary benefits, studies, and reports without adequate emphasis on thepost-construction decline. This is an important lesson for the design of future infrastructureprojects. Without an appropriate plan to address the requirements for sustainable livelihoodrestoration of affected families, whose primary skill and knowledge are based on raisingagriculture and livestock, incomes are likely to decline over time. The vulnerable group ofmarginalized (Bote) people, whose livelihoods depend on traditional fishing and ferrying peopleacross the river using small boats, should be given equal access to work as transportationoperators on the reservoir to ensure their sustainable livelihood. However, the executing agency (Nepal Electricity Authority) has yet to sign a contract to engage environment and social studies department (ESSD) to monitor the environmental and social aspects during the operation of the project. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Crosscutting Issues/Themes: Sustainability Crosscutting Issues/Themes: Vulnerable groups Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Crosscutting Issues/Themes: Employment Sector Related Issues: Energy planning/management Sector Related Issues: Rural development In view of the executing agency's late submissions of audited project accounts and financial statements,ADB should consider directly appointing external auditors, with funding from the loan proceeds,to ensure timely submissions of audited project accounts and financial statements by tardy executing agencies. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies The implementation period of the project, as estimated at appraisal, was optimistic. Theproject was the largest ever implemented in Nepal. Based on the difficulties faced by otherprojects implemented by the executing agency (Nepal Electricity Authority), a longer implementation period should have been established. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies While most of the significant delays were due to unforeseen causes, substantial administrative difficulties added to the delays in project implementation, such as slow decision-making by the executing agency (Nepal Electricity Authority), five project directors during implementation and poor relationship between the executing agency (Nepal Electricity Authority), the project implementation consultant, and the civil works contractor. To avoid administrative delays in future projects, ADB should ensure that NEA does not slow down project implementation with unnecessary and cumbersome administrative procedures. ADB should ensure that the project director is capable of making decisions, and has knowledge of similar projects and what is entailed in the day-to-day running of these projects. Moreover, ADB should insist that NEA assign one project director for the duration of the implementation period. The relationship between the executing agency (Nepal Electricity Authority), the project implementation consultant, and the civil works contractor could have been improved. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Project Design: Appraisal Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Project Management: Project management Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/kali-gandaki-hydroelectric-project
Rajapur Irrigation Rehabilitation Project | Nepal |  | 2003-10-15 | Irrigation development through farmers' participation is a time-consuming process.Provisions should be made to initiate institutional development activities prior to detailed surveyand design. As proved by the project reformulation and the consequent satisfactory implementationof the project, this stipulation of lead-time for institutional activities helps build a sense ofpartnership between farmer beneficiaries and the project entity. It raises awareness of farmers andenables them to spell out their primary requirements. As a result farmers' assessed needs anddemands would have already been collected and passed over to implementation consultants upontheir deployment. project cycle stage: Concept Lesson Topics: Project Design: Project design Project Management: Consultants Capacity Development: Capacity development Capacity Development: Partnerships Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Leadership development in irrigation needs to be well addressed in the training modulesand care should be taken to essentially include the second generation of emerging leaders whocan easily undertake responsibilities in the absence of their leaders. This problem of lack ofleadership was witnessed in Rajapur when a number of main leaders of (central farmers committee) CFC deserted the areabecause of the insurgency and created a vacuum in the farmers' organization. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development Country Context: Emergency Sector Related Issues: Irrigation management The arrangement that the implementation consultants prepared the O&M manual and theTA consultants offered training based on the manual has created problems in coordinatingschedules of the two consultant teams. Assigning to the same team of professionals both activitieswould have increased the efficiency of O&M training. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Operation and maintenance Capacity Development: Capacity building Methodologies/Approaches: Consultation/Participation The project successfully demonstrated that farmers' participation could be easily solicitedand augmented if the project and its components are planned and designed as per farmers' needs.To ensure safe and smooth operation of the constructed facilities, farmers' existing structures andtheir traditional O&M practices must be closely studied while designing irrigation facilities, and thenew plan should consider such practices as far as possible. The need becomes even moresignificant if the system has been operational for a long period of time. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Training on O&M of newly built structures is equally needed for irrigation leaders and forordinary farmers. Improving the skills and awareness of ordinary farmers is even more importantbecause they are directly involved in O&M of the canal systems. This need was not realized andonly the irrigation leaders were offered training in the project. This presumably had caused themisuse and mishandling of the constructed facilities by ordinary farmers. project cycle stage: Feasibility Lesson Topics: Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Irrigation management Wherever possible, an irrigation development project should include basic agricultural development activities. In the absence of such activities the impact of the irrigation project might not be clearly visible. The lack of integration of agricultural development activities with the project had some dormant effect on the real impact of the project. It is rather unfortunate that despite huge investment in the development of irrigation infrastructure, improved farming systems are still absent in Rajapur. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Impact evaluation Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rajapur-irrigation-rehabilitation-project
Microcredit Project for Women in Nepal | Nepal | Education | 2003-09-15 | A careful assessment of women beneficiary knowledge and skills would be beneficial to identify their capacity and needs, and thus ensure scarce resources are used efficiently. Training and any other assistance should be need-and demand-driven. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Finance & Financial Aspects: Market analysis Capacity Development: Capacity assessment Capacity Development: Capacity building Instead of first linking women beneficiaries with participating banks, and later to partner financial intermediaries (FIs) or saving and credit cooperatives (SCCs) for credit services, it would have been more sustainable and viable if they hadbeen linked with FIs or SCCs in the first place. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project implementation, monitoring, and supervision were logistically difficult and costlydue to scattered project sites (both districts and village). Clustering the project area based onthe geographic contiguity and similarity should be considered when selecting project sites toimprove the efficiency of implementation, monitoring, and supervision. Community selection criteria should be pro-poor in order to reach the poorest of the poor. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project administration Project Management: Project management Project Management: Project supervision Project targets should be realistic. At the time of project design a more carefulassessment of each planned intervention against the prevailing environment would have beenbeneficial to avoid project implementation delays. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Methodologies/Approaches: Targeting The project confirms that access to microfinance services strengthens women'sinfluence over economic and household decisions and provides them with greater freedom to invest in activities that raise their own well-being and that of the household as a whole. Women's social empowerment can be achieved through social mobilization and capacitybuilding in the process of group formation. Financial and institutional development support is critical at early stages of anymicrofinance institution. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Finance & Financial Aspects: Financing Capacity Development: Capacity building Capacity Development: Capacity development Methodologies/Approaches: Community approach The project confirms that combining credit schemes with group formation andappropriate training is an effective and successful methodology. In cases where group formationis considered the most appropriate approach, qualitative and sustainable results depend onintegrating all of these aspects. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development To minimize the vulnerability of women beneficiaries who borrow for rearing livestock,livestock insurance should be made compulsory for the whole loan duration with yearly renewalpremiums automatically added to the women's outstanding loan balances. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Employment Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/microcredit-project-women-nepal
Third Road Improvement Project - Nepal | Nepal | Transport | 2003-08-15 | The actual cost incurred for four of the five improvement projects wassignificantly higher, i.e., ranging from 10% to 178% higher than estimated at appraisal.For the fifth, the actual cost was 40% lower than the appraisal estimate. The higher-than-expected costs were due mainly to underestimated geotechnical considerations,especially in slope stabilization and the decision to lay bituminous surfacing throughoutRoad 4. The roads became economically nonviable since their EIRRs dropped to lessthan 12%. If the costs were estimated more realistically, candidate roads would havebeen selected better by taking into account economic viability together with otherselection criteria - connectivity, poverty impact, and other social-economicalconsiderations - and allocation of scarce resources in the country could have beenoptimized. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Sector Related Issues: Roading The Equipment Management Unit (EMU) was an organization that used to be part of the executing agency (Department of Roads) and yet was fundedfrom foreign assistance. Its purpose was to ensure that local contractors had access to a suitable plant to carry out road projects. The EMU had been successful in serving that purpose. In fact, had not been for the EMU, the local contractors could not havecompleted their contracts. However, the fact is that although the EMU was successful in helping local contractors carry out their work, it was not economically sustainable because of (i) unexpected market weakness due to political instability, (ii) the need for the executing agency to carry out certain emergency repairs of damaged roads, and (iii) the executing agency's inability to pay the associated rent. At the same time, the financial capabilities of local contractors increased over time so that the need for EMU equipment declined. The executing agencydisbanded the EMU to reflect reality. In the future, economic viability and sustainabilityshould be considered when setting up a unit. The market forecast and sources ofmaintenance fund should especially be evaluated. What should be avoided is setting upan agency playing a commercial function but with no secure market visibility so that itsexistence would depend on continued foreign assistance. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Project evaluation Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Procurement Capacity Development: Capacity development Sector Related Issues: Roading The major problem facing road maintenance today is lack of financing. The RoadBoard Bill was expected to have been in place by 1996. Yet it was approved after 6years and is not yet fully effective. It is important to continue to dialogue with thegovernment to make adequate maintenance funds available for the road project. Therewould have been an agreement with the government on adequate funding levels forroad maintenance and the funding levels could have been a loan covenant. If properlyenforced, this covenant could have assured sufficient financing levels, at least for theproject roads. Sustainability should be given full consideration when the governmentsets up an institution so that a resulting setup does not become inactive due toinadequate operational funds shortly after project completion. project cycle stage: Appraisal Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Management: Operation and maintenance Capacity Development: Ownership Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-road-improvement-project-nepal
Selected Technical Assistance for Agricultural Planning and Statistics in Nepal | Nepal | Agriculture, Natural Resources, and Rural Development | 2002-12-31 | A strong participatory process for strategy development through a TA may lead to a focus on consensus creation too early in the formulation stage, which can detract from the innovativeness of the strategy. Participation has to be properly managed if results are to stay focused. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach ADB's sustained engagement in the agriculture sector, with a series of TAs complementing ADB's loan inputs, shows that such engagement can have positive effects on needed policy reforms. Sequencing policy and institutional changes should follow the principle of identifying the most binding constraint to a sector's development, the removal of which would generate the largest impact. Since removing a bottleneck may highlight other obstacles to reforms, this process requires a long-term perspective to nurture and gauge the success of a given policy change or reform measure. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework All TAs, even those that are primarily geared to conducting studies and drafting policies or plans, need to pay attention to capacity building and institutionalization of their outputs. Permanent government units should be involved in the studies or design of the policies or plans to get better results but also to learn by doing. project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building Careful consideration needs to be given to the division of responsibilities for collection of statistics between line ministries and statistics organizations such as Central Bureau of Statistics (CBS). Whenever a new division is mandated, a mechanism needs to be set up to ensure optimal coordination for collection and use of statistics. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Data collection Project Design: Project design Methodologies/Approaches: Consultation/Participation Perspective plans, such as promoted by ADB through TA, should be less preoccupied with output targets, allow flexibility, and focus primarily on institutional reform process. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Methodologies/Approaches: Targeting Sector review TAs, such as the agriculture sector performance review (ASPR), need to allow time to disseminate the findings properly, so that these can be digested at various levels and in various geographical areas, and the impact of such reviews improved. In general, the implementation period should be longer to allow for remedial action when problems with the utilization of delivered outputs arise. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Project design Sector Related Issues: Rural development The tying of the use of certain TA outputs to covenants of ADB program loans contributes to the effectiveness of such TAs (as well as of the loans). project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Modality: Program Modality: Technical Assistance | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/selected-technical-assistance-agricultural-planning-and-statistics-nepal
Tribhuvan International Airport Improvement Project | Nepal |  | 2002-11-15 | Most of the variation orders issued by the engineer and agreed with the various civil works contractors have been left pending for nearly 2 years awaiting the executing agency (EA) board approval. There does not seem to be any clear-cut reason for this excessive delay, except for a politicized board reluctant to make decisions where large sums of money are involved. Strong actions by ADB at an early stage may have resolved this matter. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project administration The improvement and upgrading of airport facilities generally bring broad areas of socioeconomic benefits not only to airport users but also to the general public. The relevant data are now in place to monitor the socioeconomic impacts of the project through the project benefit monitoring and evaluation carried out by the consultants. However, due to the government's failure to follow through on the loan's further capacity-building component within the executing agency (EA), the functioning of the EA is below optimum. Its financial and accounting section lack sufficient qualified staff, computer equipment, and budget. Appropriate maintenance of airport facilities is not taking place, since there is no comprehensive maintenance and repair program in place, critical maintenance equipment has not been procured, and maintenance activities are underfunded. ADB should have taken strong action in an attempt to ensure that the follow-on capacity building was implemented. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project administration Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Transport planning | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/tribhuvan-international-airport-improvement-project
East Rapti Irrigation Project (Loan 867-NEP[SF]) | Nepal | Agriculture, Natural Resources, and Rural Development | 2002-05-31 | Construction quality control should be strengthened through effective monitoring by beneficiaries. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Irrigation management Irrigation facilities should be provided only after project beneficiaries are willing to manage their operation and a strong water users association (WUA) is formed. project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Operation and maintenance Capacity Development: Capacity development Sector Related Issues: Irrigation management An integrated river basin approach should be adopted for subproject selection and design. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Subprojects Sector Related Issues: Water resource management Farmer participation should be strengthened at all stages of the project cycle. project cycle stage: Concept, Design, Feasibility, Appraisal, Implementation, Completion Operation Lesson Topics: Farmers have the potential to assume greater responsibility for O&M of constructed structures and facilities. They should be fully assisted to realize this potential, entrusted with responsibilities ranging from identifying subprojects to decision making, and made accountable for all the facilities developed. Some project farmer managed irrigation systems (FMISs) lacked resources as no funds were allocated for major repairs after the FMISs completion and handover. Before handover, a project operational plan should be developed for at least the initial years and particularly for relatively large FMISs. project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Subprojects Project Management: Operation and maintenance Project Management: Project management Sector Related Issues: Irrigation management Joint extension activities of the District Irrigation Office (DIO) and the District Agriculture Development Office (DADO) yielded positive results. Crop diversification could have been further facilitated with better coordination between the two departments at the central and district levels. While the departments joint efforts are examined, alternative measures may be assessed to further intensify training for farmers. project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Capacity building Sector Related Issues: Extension service Sector Related Issues: Irrigation management Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation Operation and maintenance monitoring and support should be extended well into the post turnover stage. project cycle stage: Operation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance Specific stages of project development have to be clearly delineated. Well-defined criteria for subproject selection (as used in the subsequent projects for Nepal) should be followed to ensure appropriate choices of subprojects. Feasibility studies with detailed surveys of the prospective subproject areas should be the norm. The studies require time, resources, and active participation of the stakeholders. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Subprojects Methodologies/Approaches: Consultation/Participation The approval process for the original project included a project preparatory TA, the usual processing missions, and various reviews. In hindsight, alternative solutions seem not to have been seriously examined and the environmental and farming contexts (the presence of Royal Chitwan National Park or RCNP downstream and the existence of a large number of farmer-managed irrigation system or FMISs in the project s command area) not adequately assessed. ADB procedures since 1987 have strengthened the environmental and social scrutiny that all proposed interventions must undergo. Alternative solutions of reaching project goals must be routinely examined throughout the selection and approval process. Even late in that process a bad idea should be rejected rather than pursued despite reluctance to do so due to costs involved and possible negative reactions to the proponent of the change. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Modality: Technical Assistance While developing and constructing a cascade of irrigation systems from the same source river, all farmer-managed irrigation system or FMISs need to be identified and ranked based on their feasibility and farmers' demand and willingness to participate. Their linkages and conflicts need to be properly investigated, using an integrated river basin approach. A procedure to resolve differences among the prospective subprojects needs to be adopted before construction starts. The results should be thoroughly assessed during the design stage by the government. Preconstruction hands-on training for water users association (WUAs) is essential to ensure the quality of civil works. Simple construction works may be awarded to WUAs capable of undertaking them. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/east-rapti-irrigation-project-loan-867-nep-sf
ADB Assistance to the Roads Sector in Nepal | Nepal | Transport | 2000-12-31 | Agricultural development may not necessarily follow road development, and specific interventions to ensure that the expected development occurs may be required. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Rural development High standards, which implies substantial expenditure, are not rewarded by commensurately large benefits. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial benefits Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Roading Modifications in scope must be carefully thought out and examined prior to approval lest they lead to arbitrary results which can reduce benefits, e.g., roads ending randomly at points between settlements. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial benefits Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Sector Related Issues: Roading Road components in agricultural or area development projects need to be planned in relation to both the agricultural needs of the area and an overall development plan for the road network. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Rural development Upgrading of hill roads are assumed to result in large maintenance savings, which do not occur in full. Future studies should adopt a more realistic view of potential savings. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Roading | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/adb-assistance-roads-sector-nepal
Fifth and Sixth Power Projects (Loans 670/708-NEP[SF]) | Nepal | Energy | 1999-12-31 | Adherence to minimum maintenance standards and practices should be a pre-condition for further investments in the expansion of the power distribution system. project cycle stage: Operation Lesson Topics: Project Management: Operation and maintenance Sector Related Issues: Energy planning/management Delays in project implementation result to revenue losses and deviations from the originally planned project scope. Capacity building should improve the project management skills and planning capability of the executing agency to prevent delays arising from difficulties in following ADB's procurement procedures and poor planning. Delays may have also been caused by a possible lack of foresight by ADB of the difficulties of project implementation given the local institutional context of the country. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Institutional analysis Sector Related Issues: Energy planning/management In the absence of adequate monitoring data on project achievements, there is the need to provide for more rigorous accountability in carrying out rural electrification programs. Equally important is the application of proper screening criteria based on either cost-effectiveness considerations and/or economic feasibility, where warranted, for the socioeconomic evaluation of rural electrification schemes. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Sector Related Issues: Energy planning/management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/fifth-and-sixth-power-projects-loans-670708-nepsf
Second Tribhuvan International Airport Project (Loans 388/783/936-NEP[SF]) | Nepal | Transport | 1999-11-30 | ADB policy toward procurement should be more attentive to the risk factors that could negatively impact the cost of contract delivery. Risks associated with hard currency exchange rate volatility could have been avoided through proper forward hedging contracts which would have protected the Borrower against large-scale devaluations among hard currencies. Greater attention should have been focused on currency movements rather than on the purely technical issues governing the procurement process. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Procurement Project Management: Risks/Risk management Government approval of prequalification listing, proposal or tender evaluation, and contract signing are subject to significant delays and uncertainty. In light of significant and repeated delays encountered leading up to and including contract award, greater efforts should be undertaken to significantly curtail needless bureaucratic delays in moving the procurement process forward to minimize costly overruns and facilitate a timely implementation period for completing a project. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Public governance Project Management: Procurement | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-tribhuvan-international-airport-project-loans-388783936-nepsf
Road Improvement Project (Loan No. 806-NEP[SF]) | Nepal | Transport | 1998-12-31 | In ensuring attendance to routine maintenance, the lineman system is effective since it overcomes weaknesses in a system that operates on a needs basis and employs bidding procedures. project cycle stage: Design Lesson Topics: Project Management: Operation and maintenance Sector Related Issues: Roading Nearby infrastructure developments helped accelerate the volume of traffic over the project roads and underscored the importance of supporting road projects where there exist mutually supportive development proposals. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Roading Roads intended as a spearhead for development are not very effective in directly alleviating rural poverty among farmers, at least in the short to medium term, and without more direct and additional assistance. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Sector Related Issues: Roading When approving changes in project scope and design to reduce costs, there is a need to ensure that the original design objectives are not compromised as they may undermine important, nonquantifiable and social benefits forming the basis of approval by external funding agencies, although the quantifiable outcomes may not be significantly affected. project cycle stage: Implementation Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/road-improvement-project-loan-no-806-nepsf
Second Livestock Development Project (Loan 745-NEP[SF]) | Nepal | Agriculture, Natural Resources, and Rural Development | 1998-12-31 | Given the capacity of the EA, project design should ensure that only components relevant to the EA s routine functions are included. It is tempting to introduce new activities for the EA, but the implications in terms of qualified staff needed to implement the activities and the expenditure to maintain facilities associated with the activities must not be ignored. This implies a thorough analysis of the role and functions of the EA during project processing. Component activities should be so designed as to contribute directly as far as possible to achievement of the stated goals. project cycle stage: Design Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Institutional analysis Software components relating to the improvement of human capacity not only for government staff but also for farmers and other private sector groups can be critical to successful implementation and achievement of the objectives of livestock projects in Nepal. Training programs directed at farmers and private entrepreneurs are as essential as training programs for government staff to achieve project objectives. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Private sector Sector Related Issues: Rural development The use of farmer groups as an approach for extension support can be effective provided the rationale for such grouping remains attractive. Sustainability of such groups will be more assured if the groups develop multiple objectives and activities as they become more confident and experienced. Extension services can be effectively undertaken by the private sector so long as proper training is given and the services complement the economic activities of private individuals. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Extension service Sector Related Issues: Private sector Sector Related Issues: Rural development Where the terrain of a country imposes a natural constraint on market accessibility, greater attention must be given to marketing and distribution of the produce to ensure maximum returns. The presumption that an existing agency will be able to handle the marketing of a project s output should be thoroughly examined, and necessary provisions made in the project design if the presumption is found unreasonable. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-livestock-development-project-loan-745-nepsf
Mini-Hydropower Project (Loan 512-NEP[SF]) | Nepal | Energy | 1998-01-31 | Project experience demonstrates the importance of addressing project weaknesses when found during implementation and addressing their underlying causes rather than simply reducing project scope to meet the budget set at appraisal. Early reports that project costs were significantly underestimated and that one subproject was no longer feasible should have alerted ADB to broader issues of appraisal quality and sound project design , and should have prompted reassessment of the entire project given the substantially higher costs and greater uncertainties. The project also highlights that when considering a project fraught with uncertainties owing to its remoteness and logistical issues, the cost of rectifying mistakes is great, and tendering should be based on detailed, not basic or preliminary investigations and designs. project cycle stage: Design Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Procurement Project experience demonstrates the importance of identifying critical assumptions and conditions necessary for success, and monitoring closely the progress in those areas. Specifically, the project's economic rationale was dependent upon load promotion and high level coordination with other government ministries to channel productive investment to the subproject areas. This prerequisite for project success should have been more thoroughly addressed and the budgetary implications discussed at appraisal. Load promotion should have been included as an integral component of the project, not simply as a loan covenant. While large-scale hydropower development remains key for Nepal's economic development, a broader lesson is that small hydropower plants may not be cost-effective, are not economically sustainable when constructed in isolation and should be considered only as a component of a larger plan for rural development. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Sector Related Issues: Rural development Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation The project demonstrates the importance of (i) sound formulation independent of pressures from the borrower to satisfy policy goals when such goals may not be particularly in line with ADB's economic development objectives, (ii) more realistic assessment of the EA's institutional capabilities, (iii) more rigorous supervision of consulting services used during appraisal, and (iv) thorough site inspections during project appraisal. With respect to project design and implementation, the appraisal should not have relied upon the continued presence of Swiss-sponsored engineers working with an autonomous body to provide support for site surveys and design of ADB's project. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Capacity assessment | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/mini-hydropower-project-loan-512-nepsf
Fifth Agricultural Credit Project (Loan 831-NEP[SF]) | Nepal | Finance | 1997-12-31 | In a highly segmented financial market where substantial transaction costs dominate, a line of credit approach alone is unlikely to ensure the financial and economic viability of subprojects. It is essential to involve efficient and transparent financial intermediaries as well as various support programs to accompany the credit, including those to increase productivity, crop intensity, cropped areas, and agricultural value added. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach In a thin, segmented market in which formal and informal agents consciously or unconsciously collude there would be a tendency for formal interest rates or investment costs to move towards informal rates rather than conversely. The absence of private commercial banks in rural areas, attributable to the persistence of high information and processing costs, and the presence of a single government agency alongside informal rural lenders, essentially ensure a duopolistic structure. Consequently, directed, subsidized rural credit programs do not result in a full increase in credit demand by target groups. Such credit programs have raised agricultural productivity but not sufficiently to cover economic and financial costs incurred. A correct identification and estimation of farmer burdens in contracting credit is crucial to understanding and improving the delivery, monitoring, and recovery of rural loans. The complexity of detailed stipulations on loan size, appraisal procedures, applicable interest rates, and interest subsidies creates an incentive to evade them. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Rural development Scattering loanable funds countrywide without exploiting the commercial potential of growth points supported, for example, under an Agricultural Perspective Plan, forfeits the chance of lowering loan risks and per unit lending costs, and reduces the effect that a given amount of rural credit can have in combination with agricultural inputs in raising agricultural output. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Rural development | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/fifth-agricultural-credit-project-loan-831-nepsf
Rural Water Supply Sector Project (Loan 719-NEP[SF]) | Nepal | Water and Other Urban Infrastructure and Services | 1997-12-31 | A central executing agency should become more of a facilitator than an implementor. The agency should focus on becoming a partner of the community in all stages of a project. Private sector involvement and educating the community to participate and assume more responsibility are indispensable. project cycle stage: Design, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation The participation of local communities from the start of rural water supply projects is a basic determinant of success. Using demand management in the design and implementation of such projects could improve both performance and sustainability. project cycle stage: Concept Lesson Topics: Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Where the availability of source water poses no problem, rural piped systems should be designed to an appropriate supply capacity with allowance for some proportion of household connections beside public standposts (PSPs) and for an adequate average water consumption level. project cycle stage: Design Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/rural-water-supply-sector-project-loan-719-nepsf
Hill Agriculture Development Project (Loan 721-NEP[SF]) | Nepal | Agriculture, Natural Resources, and Rural Development | 1997-08-31 | Analyses of performance of ADB projects in general show that the satisfactory performance of projects are due mainly to adequate project preparation (sector analysis), strong institutional capability, commitment of the EAs, and firm government support (result of ownership). It is essential to strengthen institutional capability, not only of the EAs, but also of regional/district offices and centers, as well as beneficiary groups. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Institutional analysis Capacity Development: Ownership In multisectoral projects with a number of executing and implementing agencies, the responsibility of each agency, as well as the role, authority and mandate of the coordinating body need to be clarified at the outset. They should have a lead agency or central coordination unit at the working level so that the appropriate level of system integration occurs. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation In view of the poor performance of agricultural development finance institutions (DFIs) in many of ADB's developing member countries, ADB's agricultural credit operation through agricultural DFIs should be preceded by rigorous assessment of institutional capacity and financial health of such DFIs. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Capacity Development: Institutional analysis Sector Related Issues: Rural development To enhance the prospect of project success, it is important to (a) ensure beneficiary participation as early as possible, not only in the design and implementation of the project, but in O&M after the project as well; and (b) adopt a flexible project implementation system based on the process-oriented approach with a built-in mid-term review of operations. project cycle stage: Design, Implementation, Operation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Operation and maintenance Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/hill-agriculture-development-project-loan-721-nepsf
Selected Technical Assistance for Strengthening Evaluation Capacity in Developing Member Countries | Nepal, Philippines, Sri Lanka | Public Sector Management | 2001-07-31 | Building capability with a primary focus on the central oversight agency may carry a risk that other entities may have weak incentives to provide information for performance evaluation. project cycle stage: Design Lesson Topics: Building capacity in performance evaluation requires a holistic approach that covers data collection at the field and project levels, through various levels of aggregation and analysis for the end users, all of which the technical assistance (TA) design should factor in. project cycle stage: Design Lesson Topics: Building performance evaluation capacity in DMCs is more complex, difficult, and time consuming than first envisaged such that future technical assistance (TA) should adopt a more thorough preparation process to ensure (i) high-level ownership of and commitment to performance evaluation, evidenced by budget and staff allocation, status within the institutional hierarchy, and existence of an influential 'champion for evaluation;' (ii) participation by all key stakeholders; and (iii) creation of awareness among senior decision makers. project cycle stage: Design Lesson Topics: Establishing performance evaluation systems is a means to an end?benefits are obtained when the results are used in key operational, budget, investment, andpolicy/strategy decision-making processes. Technical assistance (TA) design should include specific features to encourage, facilitate, and formalize the incorporation of evaluationresults in decision making. project cycle stage: Design Lesson Topics: For public sector capacity building to be successful, a number of conditions should exist, including (i) a commitment to accountability; (ii) a separation between the role of ministers and heads of departments to discourage political influence in management decisions; (iii) adherence to merit selection; (iv) an incentive structure for public servants which uphold the public interest; and (v) stability in staffing. If these conditions are not met, an assessment needs to determine whether the systemic or underlying problems should be addressed first. project cycle stage: Design Lesson Topics: Capacity Development: Capacity development Policy & Reform: Public sector reform Performance evaluation systems should be checked against becoming 'information supply-driven,' too complex, and too resource intensive to sustain by frequently assessing the decision makers' demand and need for information through the logical framework and ensuring that their means of verification can be measured within the limits of expected resource availability. project cycle stage: Design Lesson Topics: The introduction of computerized information systems is not a solution to poorly performing manual systems. Various institutional, management, and social factors must be taken into account during computerization. project cycle stage: Design Lesson Topics: The pace of technical assistance (TA) implementation to build performance evaluation capacity should be driven by DMC sense of ownership and commitment, and not by deadlinesimposed by the TA implementation schedule. project cycle stage: Design Lesson Topics: The responsibility for evaluation should be located as close as possible to the head of the organization to ensure the required status, budget and staff support, and an ability to operate across organizational boundaries. project cycle stage: Design Lesson Topics: To develop staff competency and confidence to carry out evaluation, as opposed to creating awareness of its importance and basic knowledge of the tools andtechniques, a case study approach to training is needed. project cycle stage: Design Lesson Topics: | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/selected-ta-strengthening-evaluation-capacity-developing-member-countries
Accelerating Economic Transformation Program: Completion Report | Pakistan | Public Sector Management | 2015-09-21 | Attaching support for this reform agenda to a crisis fighting effort and to an IMF (International Monetary Fund) adjustment program was a major handicap for the AETP (Accelerating Economic Transformation Program). A multiyear pursuit of structural transformation objectives would have benefited from not being linked to the short-term financial targets that govern macroeconomic stabilization programs, crucial as they are. In terms of both the efficacy of program design efforts and the depth of the necessary policy dialogue, a structural transformation agenda requires a continuity of engagement, experimentation, and monitoring that macroeconomic stabilization support efforts in general cannot accommodate. Macroeconomic adjustment programs often get paused or cancelled if financial targets are not met (irrespective of institutional reform achievements), and the timing of policy agreements is governed by financing pressures. In addition, macroeconomic stabilization programs have had, at best, a mixed track record in promoting medium-term growth. In view of the absence of any other modality in ADB at the time to support the macroeconomic stabilization challenge through quick disbursement of large foreign-currency resources, perhaps the programmatic approach pursued should have been focused exclusively on Output 1. project cycle stage: Concept, Design, Feasibility, Implementation Objectives under Output 3 could have been pursued further through other ADB modalities when the AETP (Accelerating Economic Transformation Program) was discontinued (as in Output 1 on energy and social protection). The lack of structural transformation had been presented as one fundamental reason why the BOP (balance of payments) crises are recurrent in Pakistan. There was a strong consensus during subprogram 1 and subprogram 2 that resource mobilization, internal or external, is not what constrains Pakistan development in normal times (i.e. outside crisis episodes). BOP inflows, credit-fueled increases in private demand and pro-cyclical fiscal policies actually seem to push aggregate demand forward at rates that eventually become inconsistent with external balance in Pakistan. Structural transformation, the industrial and export development process through which a country acquires, over time, capabilities in products whose exports grow faster per percentage point of world economic growth, seems to be the only way to break the boom-bust macroeconomic pattern of recent decades. Substantial policy work during subprogram 1 and subprogram 2 had produced a number of policy avenues for subprogram 3 and subprogram 4. project cycle stage: Design, Feasibility, Implementation | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/pak-accelerating-economic-transformation-program-pcr
Capacity Building for Enhanced Safeguards Management: Technical Assistance Completion Report | Pakistan | Energy, Transport | 2015-07-01 | Major lessons learnt are to: (i) less ownership of TA (technical assistance) outputs and outcome by EAs (executing agencies) due to change in management can negatively affect the TA implementation; (ii) LAR (land acquisition and resettlement)-related SOPs (standard operating procedures) are difficult to achieve/adopt without amending the land law and legislating a resettlement policy; (iii) success of CDTA (capacity development technical assistance) requires ensuring a systemic identification and inclusion of all relevant stakeholders in including the provincial boards of revenue; (iv) a memorandum of understanding or a clear agreement with government, including the EAs and all relevant government departments, is required to ensure TA ownership and its successful implementation; and (v) where possible, leveraging national laws for safeguards compliance should be explored. <!-- Project cycle stage: Appraisal, Implementation --> | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/pak-capacity-building-enhanced-safeguards-management-tcr
Punjab Millennium Development Goals Program - Subprograms 1 and 2: Completion Report | Pakistan | Health, Public Sector Management | 2015-02-25 | One of the PMDGP's (Punjab Millennium Development Goals Program) principal lessons is that interventions in countries with difficult socioeconomic conditions and generally weak implementation capacity require more comprehensive due diligence during design. When large complex programs are prepared in this context, ADB needs to carry out detailed, rigorous, and objective analysis of the potential implementation risks, especially those related to the executing agency. Once that is done, all necessary mitigation measures must be built into the design. project cycle stage: Design, Implementation, Country Partnership Strategy A well-thought-out conceptual design is a key to the success of any program. In the case of the PMDGP (Punjab Millennium Development Goals Program), the design set a commendable goal in the intended outcome, but it seems to have overestimated the capacity of the GOP (Government of Punjab) to help achieve it. It also relied too heavily on the establishment of the MSDSs (minimum service delivery standards) as a strategy for attaining MDGs (Millennium Development Goal) 4 and 5. In addition, the challenges commonly faced in such programs and projects due to the rotation of managers and inadequate ability to attract and retain suitably qualified staff should have been taken into account when considering the PMDGP timelines and setting the outputs and targets. project cycle stage: Concept, Design, Implementation Given the weak capacity of the executing agency, a large, well-conceived, and properly structured TA (technical assistance) project should have been piggybacked on the program to address the obstacles presented by inherent system inefficiencies and limited capacity. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/pak-punjab-millennium-development-goals-program-subprograms-1-2-pcr
Sindh Growth and Rural Revitalization Program: Validation of Completion Report | Pakistan | Agriculture, Natural Resources, and Rural Development, Finance, Health, Public Sector Management, Transport | 2015-01-30 | The lessons identified by the PCR (program completion report) are suitable. The implementation of the program highlighted the appropriateness of the cluster program modality for sustaining reform momentum. Greater effort is needed in assessing the political and economic context to determine the chances of success of reform efforts. The program design was complex with 25 policy conditions for subprogram 1 and 38 policy conditions for subprogram 2, involving a large number of implementing agencies and reform areas. There are benefits in keeping program simple by limiting the number of reform actions, agencies involved, and the number of subprograms under a cluster. This validation shares the view of the PCR that the decision to cancel the processing of subprogram 3 could have been accompanied with efforts to identify reform areas that were making progress and to support these with TA (technical assistance) or with resources on existing or new projects. project cycle stage: Concept, Design, Implementation | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/pakistan-sindh-growth-and-rural-revitalization-program
Punjab Government Efficiency Improvement Program: Completion Report | Pakistan | Public Sector Management | 2014-09-15 | 1. The design and implementation of the cluster program shows that it was too ambitious in its scope, and that depth of program engagement is more important than breadth of reforms. Improving the overall efficiency of the government is a complex undertaking. It requires major changes in existing institutional arrangements, human resource capacity, and legal and regulatory frameworks. Thus, (i) design should be based on thorough analysis of underlying issues to develop a realistic and properly sequenced set of reforms; (ii) proactive, frequent, and sustained dialogue with the political leadership as well as high- and mid-level officials is critical to create government ownership and buy-in for reforms; (iii) cluster program-type programs require a medium- to long-term implementation time frame, with very regular reporting and progress discussions, flexible implementation arrangements, frequent consideration of the need for any course corrections or changes, and a strategically planned, carefully managed, and integral role for technical assistance (TA); and (iv) given security concerns, TA design should allow sufficient time for recruitment of consultants. [Main text, para. 52] project cycle stage: Design, Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/punjab-government-efficiency-improvement-program-pcr
Sindh Coastal Community Development Project | Pakistan | Agriculture, Natural Resources, and Rural Development | 2014-03-01 | Key lessons from previous projects incorporated in and validated by this project included: (i) area-based multi-sector community development projects need to be simple to be effective; (ii) institutions with built-in capacity should be used; (iii) a flexible, demand-driven approach to community development should be followed; (iv) civil works and effective social mobilization should be balanced; and (v) the focus should be on service delivery, rather than on policy reforms involving structural changes that are beyond the scope of an area-based development project. The key lesson from this project is related to avoiding startup delays. The followings should be incorporated in similar future projects: (i) implementing NGOs should be pre-selected at appraisal; (ii) beneficiary contribution requirements should be waived, particularly for cash contributions; (iii) regular staff should be hired in favor of consultants, and (iv) project accounts and sub-accounts should be protected from administrative changes. Given the high unemployment rate in Pakistan (6.3% in 2013) and frequent bans on staff recruitment, political interference with recruitment is a systemic problem and it must be anticipated in all projects. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/sindh-coastal-community-development-project-pcr
Sindh Growth and Rural Revitalization Program | Pakistan | Public sector management | 2014-03-01 | A major lesson from implementation of this program cluster is the importance of reform momentum and of programmatic assistance for sustaining the momentum. However, the experience with some reforms in core policy areas 1 and 3 is a reminder that when sufficient political pressure is exerted, financial and technical capacity constraints can sometimes be overcome, even in the absence of programmatic support (as would have been provided through subprogram 3). This calls for greater effort during the design and implementation stages to assess the political and economic context, which can determine whether or not a reform effort will succeed. A second, related lesson is that, beyond the arguments already made on general relevance, the reform agendas chosen for program cluster support should be carefully selected during program design. Subprogram 1 had 25 policy conditions, while subprogram 2 had 38 policy conditions. The large number of implementing agencies and reform areas complicates program coordination. When reviewing the implementation of this cluster program, too often it seemed that quantity of policy actions was a substitute for the low number of consequent reforms that could be achieved within the indicative time-span. Most of the benefits associated with the reforms supported under the cluster program were conditional on the final reforms to be supported under a subprogram 3, which never eventuated. To the extent that this caused reform momentum to be lost or take a risky direction, this approach risked delaying (at a minimum) or wasting years of reform effort (TA, financial resources and government commitment). The decision to cancel subprogram 3 processing could have been accompanied by an immediate effort to (i) identify reform areas that were making progress in meeting their respective indicators, but at risk of losing momentum; and (ii) provide TA or resources on (for example) a project basis. This would probably have resulted in additional, more sustainable development results. Improving the investment climate in rural areas and increasing private sector participation is a long-term endeavor that merits ongoing reform efforts, using different assistance modalities if necessary. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/sindh-growth-and-rural-revitalization-program-pcr
Balochistan Road Development Sector Project | Pakistan | Transport | 2013-11-15 | 1. The project comprises several components comprising national highways, provincial highways and rural roads, cross-border development, institutional development, and community development. These components were implemented by different government agencies with limited coordination. Combining all of these components into one project was difficult for both ADB and the government to manage. If a project is so comprehensive, a project management unit at the national level should be established to coordinate its implementation. 2. The project experienced substantial delays due to security conditions, which led ADB to close the loan before completion of all the components. As a result, and because of weak government financing, the project experienced serious financial problems. ADB needs to pay more attention to local situation and assist in timely project completion. Only fully completing the project, the benefits anticipated can be revealed. 3. The global price for construction materials rose sharply during implementation. The delays in project implementation made this problem more serious. For some provincial roads under the project, retendering was conducted, but the low rate is unlikely to attract bidders. For future ADB-assisted projects, reasonable price contingencies should be included in the investment plan. 4. Project implementation encountered land acquisition and resettlement challenges. ADB amended the Loan Agreement, which allowed construction to start on the sections where land issues had been resolved. ADB needs to make the government well aware of ADB's safeguard policy and prepare a more feasible loan agreement under future projects. 5. All of the contractors were local, with inadequate funding, expertise, and equipment, which contributed to implementation delays. With rapid road development in Pakistan, such problems may be worsening. To promote capacity development of local and private contractors, ADB needs to strengthen the capacity-building programs, especially in the area where local construction capacity is lacking. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/balochistan-road-development-sector-project-pcr
Country Assistance Program Evaluation for Pakistan | Pakistan | Agriculture, Natural Resources, and Rural Development, Energy, Industry and Trade, Transport, Water and Other Urban Infrastructure and Services, Multisector | 2013-11-12 | 1. ADB should take care when considering program lending and budget support in politically turbulent countries and situations. In addition, the current requirement where International Monetary Fund (IMF) endorsement is needed prior to any program loan approval may need to be reviewed. The Accelerating Economic Transformation Program (AETP) was approved, independent of the IMF stand-by credit, but AETP's third tranche (and fourth) was not disbursed due to IMF determining the program being offtrack, which in turn, led ADB to discontinue its support for the reform process (Appendix 1, Linked Document K, Table K.2). Hence, ADB's tying of support to credit provided by the IMF and the World Bank diminished the chances of the AETP's success as a policy reform instrument. Generally, as an earlier evaluation has also pointed out, program loans are not an appropriate vehicle for counter cyclical support that is rapidly needed in the case of an economic crisis. In April 2013, ADB issued changes in its Operations Manual that pay specific attention to the conditions and modalities of budget support, in times of balance-of-payments crisis. Program loans should have wholehearted support from governments at various levels and a very clear policy matrix with clear milestones of achievement. Reforms should be tracked in a more systematic and transparent manner; and noncompliance with covenants should be taken seriously. Ownership of the program by government counterparts needs to be supported by continuous capacity building and policy dialogue. ADB should have more achievable and realistic goals and objectives when politically charged reforms are intended. [Main text, para. 172 (i)] project cycle stage: Country Partnership Strategy 2. Community-based small-scale projects focusing on water supply or agriculture can be successful and have a direct impact on the poor in Pakistan. Tranche 1 of the new Multitranche Financing Facility Sindh Cities Improvement Investment Program follows a new approach. It helps the North Sindh Urban Services Corporation and will be completed by December 2013. This evaluation could not determine whether an approach relying on corporatized entities will be successful and the answer may take several years. Past projects were often successfully facilitated by community-based organizations. Many subprojects showed sustainability many years after ADB's direct support ended; and some of them were picked up by other development partners. ADB's desired shift to infrastructure operations in Pakistan, relying on only large and few contracts, should take into account that certain types of projects may lead to more complete development outcomes when nongovernment organizations and community-based organizations are involved, even though they may have more contracts to administer and are therefore more tedious and intensive. [Main text, para. 172 (ii)] project cycle stage: Design, Country Partnership Strategy 3. In countries such as Pakistan, which are both flood and earthquake prone, disaster management should be a component of any country program. Disaster prevention and disaster risk mitigation measures should be given special attention in most infrastructure projects, given the increasing risk of natural disasters, particularly floods. [Main text, para. 172 (iii)] project cycle stage: Design 4. Safeguards implementation for road and urban projects needs close attention in Pakistan. There is still a deep resistance to fully embracing ADB's safeguard policies, especially by provincial and local level government officers. The resistance to ADB's wider definition of affected people, and compensation for loss of land is high. Continuous engagement on this front during project implementation remains essential. It is therefore encouraging that ADB has added a safeguards position in the resident mission, while ADB's capacity at headquarters has also expanded significantly in the last few years. [Main text, para. 172 (iv)] project cycle stage: Implementation 5. Projects in countries with well-known implementation problems need more supervision. Policy dialogue in the case of program loans and supervision during project implementation need to be intensive. The response to policy conditionality varies over time in politically unstable countries, and the program loan instrument needs to be used with care. The Pakistan program operates in a fragile environment and should be managed from that perspective. [Main text, para. 172 (v)] project cycle stage: Implementation 6. The power sector debt needs to be reduced to manageable levels. Otherwise, the management, bureaucracy, and political leadership will likely continue to address immediate and short-term issues at the expense of medium-term planning imperatives. While power sector debt remains high, fossil fuel based independent power producers (IPPs) will likely remain relatively more susceptible to financial problems. In general, unless the power sector debt is reduced significantly, the private sector's interest in setting up further IPPs is likely to remain weak. [Main text, para. 172 (vi)] project cycle stage: Implementation, Operation 7. The establishment of an apex transport planning and policy formulation agency would likely lead to improved implementation of transport projects and more effective capacity building in the sector. It would benefit the country and external partner agencies to have the fragmented sector responsibilities consolidated at the central government level and to have a comprehensive and integrated planning system in place. A transport policy and a long-term national master plan should support road network development consistent with traffic growth and other parameters. [Main text, para. 172 (vii)] project cycle stage: Implementation, Operation 8. Pakistan would benefit from national strategies for each sector. There are currently no clear operational strategies for the sectors nationally (beyond Millennium Development Goal targets), despite widespread recognition of the severity of the problems, as evidenced by the government's reference to an ?education emergency.? However, provinces are making efforts to establish clearer sector policies, aided by development partners, e.g., Punjab, Sindh, and Khyber Pakhtunkhwa. [Main text, para. 172 (viii)] project cycle stage: Country Partnership Strategy | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-pakistan
Country Assistance Program Evaluation for Pakistan | Pakistan |  | 2013-11-12 | 1. ADB should take care when considering program lending and budget support in politically turbulent countries and situations. In addition, the current requirement where International Monetary Fund (IMF) endorsement is needed prior to any program loan approval may need to be reviewed. The Accelerating Economic Transformation Program (AETP) was approved, independent of the IMF stand-by credit, but AETP's third tranche (and fourth) was not disbursed due to IMF determining the program being offtrack, which in turn, led ADB to discontinue its support for the reform process (Appendix 1, Linked Document K, Table K.2). Hence, ADB's tying of support to credit provided by the IMF and the World Bank diminished the chances of the AETP's success as a policy reform instrument. Generally, as an earlier evaluation has also pointed out, program loans are not an appropriate vehicle for counter cyclical support that is rapidly needed in the case of an economic crisis. In April 2013, ADB issued changes in its Operations Manual that pay specific attention to the conditions and modalities of budget support, in times of balance-of-payments crisis. Program loans should have wholehearted support from governments at various levels and a very clear policy matrix with clear milestones of achievement. Reforms should be tracked in a more systematic and transparent manner; and noncompliance with covenants should be taken seriously. Ownership of the program by government counterparts needs to be supported by continuous capacity building and policy dialogue. ADB should have more achievable and realistic goals and objectives when politically charged reforms are intended. [Main text, para. 172 (i)] project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Program Methodologies/Approaches: Program Approach 2. Community-based small-scale projects focusing on water supply or agriculture can be successful and have a direct impact on the poor in Pakistan. Tranche 1 of the new Multitranche Financing Facility Sindh Cities Improvement Investment Program follows a new approach. It helps the North Sindh Urban Services Corporation and will be completed by December 2013. This evaluation could not determine whether an approach relying on corporatized entities will be successful and the answer may take several years. Past projects were often successfully facilitated by community-based organizations. Many subprojects showed sustainability many years after ADB's direct support ended; and some of them were picked up by other development partners. ADB's desired shift to infrastructure operations in Pakistan, relying on only large and few contracts, should take into account that certain types of projects may lead to more complete development outcomes when nongovernment organizations and community-based organizations are involved, even though they may have more contracts to administer and are therefore more tedious and intensive. [Main text, para. 172 (ii)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Sector Related Issues: Water resource management Methodologies/Approaches: Community approach 3. In countries such as Pakistan, which are both flood and earthquake prone, disaster management should be a component of any country program. Disaster prevention and disaster risk mitigation measures should be given special attention in most infrastructure projects, given the increasing risk of natural disasters, particularly floods. [Main text, para. 172 (iii)] project cycle stage: Design Lesson Topics: Project Management: Risks/Risk management Country Context: Emergency 4. Safeguards implementation for road and urban projects needs close attention in Pakistan. There is still a deep resistance to fully embracing ADB's safeguard policies, especially by provincial and local level government officers. The resistance to ADB's wider definition of affected people, and compensation for loss of land is high. Continuous engagement on this front during project implementation remains essential. It is therefore encouraging that ADB has added a safeguards position in the resident mission, while ADB's capacity at headquarters has also expanded significantly in the last few years. [Main text, para. 172 (iv)] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Vulnerable groups Project Management: Project management Project Management: Project supervision 5. Projects in countries with well-known implementation problems need more supervision. Policy dialogue in the case of program loans and supervision during project implementation need to be intensive. The response to policy conditionality varies over time in politically unstable countries, and the program loan instrument needs to be used with care. The Pakistan program operates in a fragile environment and should be managed from that perspective. [Main text, para. 172 (v)] project cycle stage: Implementation Lesson Topics: Project Management: Project supervision Country Context: Conflict/Post-conflict Methodologies/Approaches: Policy dialogue 6. The power sector debt needs to be reduced to manageable levels. Otherwise, the management, bureaucracy, and political leadership will likely continue to address immediate and short-term issues at the expense of medium-term planning imperatives. While power sector debt remains high, fossil fuel based independent power producers (IPPs) will likely remain relatively more susceptible to financial problems. In general, unless the power sector debt is reduced significantly, the private sector's interest in setting up further IPPs is likely to remain weak. [Main text, para. 172 (vi)] project cycle stage: Implementation, Operation Lesson Topics: 7. The establishment of an apex transport planning and policy formulation agency would likely lead to improved implementation of transport projects and more effective capacity building in the sector. It would benefit the country and external partner agencies to have the fragmented sector responsibilities consolidated at the central government level and to have a comprehensive and integrated planning system in place. A transport policy and a long-term national master plan should support road network development consistent with traffic growth and other parameters. [Main text, para. 172 (vii)] project cycle stage: Implementation, Operation Lesson Topics: Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework 8. Pakistan would benefit from national strategies for each sector. There are currently no clear operational strategies for the sectors nationally (beyond Millennium Development Goal targets), despite widespread recognition of the severity of the problems, as evidenced by the government's reference to an 'education emergency.' However, provinces are making efforts to establish clearer sector policies, aided by development partners, e.g., Punjab, Sindh, and Khyber Pakhtunkhwa. [Main text, para. 172 (viii)] project cycle stage: Country Partnership Strategy Lesson Topics: | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-pakistan
Pakistan: North-West Frontier Province Urban Development Sector Project | Pakistan | Agriculture, Natural Resources, and Rural Development, Finance, Transport, Water and Other Urban Infrastructure and Services | 2013-09-27 | 1. The project design did not have an adequate analytic base that should have included an assessment of stakeholders and their capacities, and provisions for alignment due to changes introduced by the LGO 2001. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Urban sector/development Sector Related Issues: Water resource management 2. Previous project and/or sector experience in Pakistan was not internalized and reflected in the designï¿½the risk of underestimating capacity constraints could have been mitigated with a risk management strategy. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity assessment 3. Supervision missions must flag projects that are in danger of slippage before it is too late to modify the project. project cycle stage: Implementation Lesson Topics: 4. Project monitoring and evaluation systems require sets of measurable indicators and associated targets so that corrective measures can be implemented in time to achieve the project's outcome. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/pakistan-north-west-frontier-province-urban-development-sector-project
Pakistan: Chashma Right Bank Irrigation Project (Stage III) | Pakistan | Agriculture, Natural Resources, and Rural Development | 2012-12-27 | This validation notes the inefficient and ineffective compensation process for land resumed. It is essential that adequate compensation mechanisms are built into the project design and implemented. If this had been undertaken, it might have preempted the need for a protracted and expensive system for redressing grievances. Rapid compensation is highly desirable. If compensation is delayed, land values may increase and resettlers may no longer consider defined compensation rates to be adequate. [Main text, para. 24] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/pakistan-chashma-right-bank-irrigation-project-stage-iii
Earthquake Emergency Assistance Project: Project Completion Report | Pakistan | Education, Energy, Health, Public sector management, Transport | 2012-11-01 | Have a dedicated lead institution. The dedicated federal (Earthquake Reconstruction and Rehabilitation Authority or ERRA) and provincial reconstruction authorities led the overall coordination and monitoring, and facilitated procedures, policies, and strategies for reconstruction. This arrangement allowed efficient and transparent reconstruction, and established the government's commitment to and credibility in mobilizing resources. This experience demonstrated that disaster response and recovery can be improved by having dedicated lead institutions with the required additional capacities. Clarify roles and respect existing mandates. Initial delays in implementation of the project were caused by confusion about the roles of new and existing institutions. Any large- scale reconstruction operation requires clear delineation of the mandates of levels of government, to provide the structure and clarity required for all stakeholders to work with maximum efficiency. To the extent possible, the provincial and regional governments and federal agencies should be provided with capacity to perform their mandated roles. This approach may cause initial delays in response to major disasters but builds ownership and sustained capacity to manage completed infrastructure and responses to future disasters. Articulate policies, strategy, and standards early. The local populations and nongovernment organizations (NGOs) started reconstruction work well before provincial and federal governments started articulating their responses. Expectations rose, and some facilities, especially in health, were built by bilateral donors to standards that were much higher than the capacity of the line agencies to maintain them. This resulted in inconsistencies, violations of policies and standards developed for reconstruction work, and unsustainable operation of completed facilities. The government should ensure that the reconstruction policies and standards are within the capacity of the sector institutions to sustain and are delivered as soon as possible to avoid inconsistencies. Enhance transparency for effective oversight. The government-established ERRA Council, headed by the prime minister, consists of independent and reputable individuals from civil society in the affected regions. The council followed the reconstruction process and reviewed and reported regularly to the general public on its progress and outcomes, developing a sense of ownership. Independent oversight, involving representatives of civil society disseminating information to key constituents, promoted transparency and enhanced the credibility of the host government. Institutionalize ï¿½fast-trackingï¿½ and flexibility. The technical assistance (TA) attached to the project allowed flexible responses to diverse capacity gaps, and fast-tracked procurement and disbursement, and the implementation of the safeguards policy. The flexibilities allowed under the emergency policy reduced procurement time and enabled efficient mobilization of resources. However, no comparable emergency procedures existed at line agencies, and reconciliation of accounts delayed the closure of the loan account because no additional capacity was provided to ADB to handle the additional disbursement load. A reconstruction program can be fast-tracked if procedures are put in place at the line agencies to reduce timelines for approvals, disbursements, and procurements for the specified duration of the program, and if capacity is developed in the line agencies and ADB to implement those procedures. Similarly, for ADB, flexible TA and procurement procedures have proven to be excellent tools for timely delivery of emergency projects. Incentivize key staff and the private sector. The project suffered delays and cost escalations caused by high staff turnover, weak response to procurement needs, red tape and weak contract management. There were no special incentives for staff, firms, or contracts tengage in the difficult working environment and no outreach mechanism to facilitate private sector engagement. Experience shows that breaking the ?business as usual? culture during emergencies requires strong outreach and communication, and special incentives for staff and private sector to ensure good response, and to engage stakeholders in implementation. Be socially responsive in implementation. The project suffered hardly any delay from safeguard and social issues. The governance component of the project provided additional staff and built the capacity of the legal system to cope with the additional burden posed by the earthquake-affected population and reconstruction activities. Timely responses to issues facing the affected populationï¿½including entitlements, registration, grievances, and complaintsï¿½ avoided delays in reconstruction implementation and protected individual rights. Strongly embed reconstruction in the development agenda. The health, education, and transport facilities were built to higher standards than those in place before the earthquake. However, their sustainable operations were affected by endemic issuesï¿½cost recovery, quality, and sustainability of operationï¿½that existed in these sectors before the earthquake. Because of the short timeframes, the reconstruction programs tended to avoid addressing endemic development issues in their scope, but the impacts of program outputs were curtailed by these issues. To enhance impacts, reconstruction programs should be aligned with regular sector development programs to maintain the focus on reforms needed for sustainable operations during and after project closure. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/earthquake-emergency-assistance-project-project-completion-report
North-West Frontier Province Road Development Sector and Subregional Connectivity Project | Pakistan | Transport | 2012-11-01 | Project Design. The project was comprised of six components, including national highways, provincial highways (PHs), rural access roads (RARs), policy reform and institutional strengthening, border infrastructure, and road safety. Six implementing agencies were engaged to implement these components. For improved coordination and smooth implementation, it would be better to implement projects with only one or two implementing agencies. Project Implementation in an Area with Security Challenges. The security conditions in the project area deteriorated during implementation. ADB needs to consider special arrangements for such projects. For example, direct contracting or lump-sum contracts may be considered for civil works contracts, rather than competitive bidding, in particular, international competitive bidding (ICB). Project management could be outsourced, as ADB missions were not able to visit sites. Cost Estimates. Cost estimates of subprojects were prepared in 2004 on the basis of the prevailing composite schedule of rates (CSR). However, at the time of contract award there was an exceptionally high inflation. It is important to consider the inflation factor between the project design and contract award periods. Procurement and Construction. Several road construction projects were started in all the provinces within a short span of time. This resulted in a sudden increase in the demand for consultants and contractors. Hence, there was inadequate competition among contractors. Undertaking multiple large programs at one time is not good for the executing and implementing agencies and the local construction industry. Shortages will develop, bottlenecks will arise, prices will increase, the cost of production will be high, and equipment will become idle after project completion. It will be more appropriate to conduct a construction section capacity review during appraisal and stagger the works in such a way that machinery, equipment, workers, employers, and employees remain occupied. Price Escalation. The price for construction materials rose sharply during implementation due to the global economic downturn. The delays in project implementation made this problem more serious. The decisions to approve the escalation took a long time due to the extremely high amounts. All such decisions need to be made quickly in accordance with the given contract clauses. Consultant Performance. Consultant performance should be critically evaluated and monitored closely during implementation. There were many lapses and deficiencies in the design, necessitating design and cost revisions and price escalation. A proper design review may be considered to avoid these deficiencies for future projects. Future consultants selection should be strictly based on their performance records. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/north-west-frontier-province-road-development-sector-and-subregional-connectivity-pcr
Second Generation of Capital Market Reform Program | Pakistan | Finance | 2012-11-01 | Capital market reforms are particularly sensitive to economic and political shocks that affect investor confidence. This must be taken into account when designing and implementing policy-based programs in support of capital market development. With regard to financial sector oversight, the primary focus should be on regulatory objectives rather than regulatory architecture, which is a political issue. During the implementation of both the Second Generation of Capital Market Reform Program and the Accelerating Economic Transformation Program, ADB experienced difficulties because of changing views on regulatory architecture within the government. This should be avoided as much as possible. Strengthening financial sector governance often requires promulgating new legislation, which is outside the control of the executive branch. While preparation of legislation reflects government commitment to reform, unless laws are enacted, these outputs may not bring tangible changes. ADB should support the government beyond drafting legislation in sustaining stakeholder consultations until laws are enacted. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/second-generation-capital-market-reform-program-pcr
Sustainable Livelihoods in Barani Areas Project | Pakistan | Agriculture, natural resources and rural development | 2012-11-01 | In order for it to be efficiently implemented, a multisector area development project covering multiple districts must have (i) the Agency for Barani Areas Development (ABAD) as the executing agency, since it has the essential mandate; (ii) a decentralized project management model with dedicated staff and market-based salaries and benefits; (iii) flexible, demand-driven design of interventions; (iv) minimum beneficiary funding requirements; (v) fewer consultants and more regular staff; (vi) clear and realistic gender and development (GAD) targets; (vii) a duration of at least 8 years; (viii) pre-selection of nongovernment organizations (NGOs) at appraisal to avoid start-up delays; (ix) flexibility in loan extension and responsiveness to security crises and natural disasters; (xi) a dedicated sub-account for district governments; and (xii) a project performance management system designed at appraisal. The combination of a line agencies' support fund, a project allowance for concerned line agencies staff, and community participation ensured the accountability of line agencies and contractors. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/sustainable-livelihoods-barani-areas-project-pcr
Pakistan: Punjab Devolved Social Services Program | Pakistan | Education, Health, Public Sector Management | 2012-10-12 | 1. Ensure that lessons learned in previous efforts are properly understood and taken into account when developing related initiatives. [Executive Summary, page vii; Main text, para. 96] project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Education Sector Related Issues: Health and sanitation management 2. Ensure sufficient ownership and strong leadership from key members of the elected and executive bodies of the partner government. [Executive Summary, page vii; Main text, para. 97] project cycle stage: Design, Implementation Lesson Topics: 3. Undertake a rigorous institutional and policy environment assessment as part of preparatory work, with a political economy perspective that brings out formal and informal dynamics and incentives. [Executive Summary, page vii; Main text, para. 98] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Capacity Development: Institutional analysis 4. Specify the measures for reducing risks, and design the program accordingly. [Executive Summary, page vii; Main text, para. 99] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management 5. Allow a time frame for preparation and processing of loans by ADB operations staff that is commensurate with the complexity of the loans. [Executive Summary, page vii; Main text, para. 100] project cycle stage: Appraisal Lesson Topics: 6. ADB should ensure program modalities are flexible and adaptable enough to respond to changing circumstances to maximize outcomes. [Executive Summary, page vii; Main text, para. 101] project cycle stage: Implementation Lesson Topics: 7. The design of high risk institutional development programs should be less ambitious and should be linked to areas that already have political and policy support. [Executive Summary, page vii; Main text, para. 102] project cycle stage: Design Lesson Topics: 8. In closing program files, ADB should ascertain the use of funds, and if funds have yet to be channeled to their intended uses, act in accordance with the degree of fiduciary risk entailed. [Executive Summary, page vii; Main text, para. 103] project cycle stage: Completion Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/pakistan-punjab-devolved-social-services-program
Federally Administered Tribal Areas Rural Development Project | Pakistan | Agriculture, natural resources and rural development | 2012-10-01 | The project was a success primarily because of its design, which accounted for actual conditions in the project area, applied lessons from previous interventions, and incorporated and adopted efficient and sustainable delivery mechanisms. The involvement of beneficiaries in the project through effective social mobilization was critical to its success. Training, awareness raising, and capacity building of beneficiaries was also instrumental in ensuring that the subprojects were owned and operated by the communities and were sustainable. Appointing qualified staff and retaining them for the duration of the project avoided delays in implementation. The active support of the borrower and the executing agency, through timely provision of counterpart funds, steering committee meetings convened for timely decisions and approvals, and consistent monitoring and supervision, helped ensure smooth and timely implementation. ADB's proactive participation in implementation, supervision, and monitoring, and its flexibility in addressing actual conditions in the project area and providing essential support to the federally administered tribal areas (FATA) Secretariat in a timely manner was also a central factor for the success of the project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/federally-administered-tribal-areas-rural-development-project-pcr
Pakistan: Sindh Devolved Social Services Programs | Pakistan | Education, Health | 2012-08-04 | 1. Ensure that lessons learned in previous and relevant programs are properly understood and truly taken into account in developing related initiatives. The difficult Social Action Program experience with the multi-sectoral approach is raised in the project completion report and validation as a lesson missed in the program design, but this was not the underlying weakness in the design. Lessons from international experiences in devolution and capacity development were missed. [Executive Summary, page vii; Main text, para. 106] project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Education Sector Related Issues: Health and sanitation management 2. Ensure that there is sufficient ownership and strong commitment from key members of the elected and executive bodies of the partner government and other stakeholders. [Executive Summary, page viii; Main text, para. 107] project cycle stage: Design, Implementation Lesson Topics: 3. Undertake a sound institutional, political, and policy environment assessment as part of the preparatory work, bringing out formal and informal dynamics and incentives. [Executive Summary, page viii; Main text, para. 108] project cycle stage: Design, Feasibility Lesson Topics: 4. In the program design, risks should not just be mentioned or put off to a later stage. Rather, they must be properly assessed and the measures for reducing risks and mitigating measures must be clearly specified. [Executive Summary, page viii; Main text, para. 109] project cycle stage: Design, Feasibility Lesson Topics: 5. Allow a realistic time frame for preparation and processing of loans by ADB operations staff that is commensurate with the complexity of the loans. [Executive Summary, page viii; Main text, para. 110] project cycle stage: Appraisal Lesson Topics: 6. When program results are endangered by a drastically changing environment midstream in the implementation, the management of the program must be able to shift gear and find some adaptation that will maximize outcomes. ADB should ensure its modalities are flexible enough to respond to these circumstances. [Executive Summary, page viii; Main text, para. 111] project cycle stage: Implementation Lesson Topics: 7. In closing program files, ADB should make a more determined effort to ascertain the use of funds, and if funds have yet to be channeled to their intended uses, act in accordance with the degree of fiduciary risk entailed. [Executive Summary, page viii; Main text, para. 112] project cycle stage: Completion Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting 8. Subsequent discussions on ADB support that aim to partner with any provincial government need to be tailored to the specific situation in the respective province. They should take into account the new functions received by provinces in the 18th amendment, including reacquired jurisdiction over local government systems. [Executive Summary, page viii; Main text, para. 113] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Capacity Development: Partnerships Methodologies/Approaches: Policy dialogue | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/performance-evaluation-report-devolved-social-services-programs-pakistan
Agribusiness Development Project | Pakistan | Agriculture, Natural Resources, and Rural Development, Finance | 2012-03-09 | 1. A thorough analysis of institutional capacity is required during the design process. The state of inter-institutional linkages and the possible effect on project implementation of weaknesses and difficulties with these linkages also needs to be considered. [Main text, para. 44(i)] project cycle stage: Lesson Topics: 2. Policy-related work - which in this project involved preparation of a national agribusiness policy and provincial and special areas horticultural policies - will almost invariably take longer than expected and consume a disproportionate share of management resources during implementation. [Main text, para. 44(ii)] project cycle stage: Lesson Topics: 3. Consultancy output for policy work needs to be very specifically defined. For example, should the output be a policy framework or a complete, agreed and adopted policy. If the latter, it must be made clear and agreed with the borrower who is to sign off on the policy document. [Main text, para. 44(iii)] project cycle stage: Lesson Topics: 4. Attempting to work along the whole value chain from farm production to market (either domestic or export), as this project attempted to do, will almost certainly be more difficult than concentrating on a few key links. [Main text, para. 44(iv)] project cycle stage: Lesson Topics: 5. It is essential that the objectives in the report and recommendation of the President be adequately reflected in operational plans. There is little evidence, for example, that vertical integration in the value chain was facilitated by the project. [Main text, para. 44(v)] project cycle stage: Lesson Topics: 6. Developing a private sector-driven market information system in a country where government is the dominant or possibly the sole existing provider of such information is likely to be a complex, time-consuming process and one that may require some form of income guarantee for the private provider or providers. [Main text, para. 44(vi)] project cycle stage: Lesson Topics: 7. Agreement should be obtained from the borrower during loan negotiations on the use of project funds to provide equipment and services to wholly private sector firms. [Main text, para. 44(vii)] project cycle stage: Lesson Topics: 8. A clear strategy to exit from support for agencies or offices established under projects needs to be defined at the outset by firmly establishing whether the entity is expected to have a continuing role post-project and, if so, how its operations are going to be financed. [Main text, para. 44(viii)] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/agribusiness-development-project-pcr
Southern Punjab Basic Urban Services Project | Pakistan | Water and other urban infrastructure and services | 2012-01-03 | 1. Ownership and commitment of the Punjab government toward the Punjab Local Government Ordinance (PLGO), 2001 decreased over the project implementation period. The PLGO 2001 reforms were embedded in the tehsil municipal administration (TMA) selection criteria and were supported through municipal management capacity-building initiatives to ensure sustainability of investments. Due to the lack of political will and weak capacities of the implementing agencies, however, the implementation of the reforms and municipal management activities was marginal. With more focus on infrastructure, and limited attention to TMA selection criteria and related benchmarks, this gap could not be fully addressed during implementation. Urban projects need an integrated approach, and infrastructure alone cannot result in improved services, unless different services complement each other, and capacities, resources, and systems are in place to sustainably deliver these services. project cycle stage: Lesson Topics: 2. Based on the analysis at completion, one of the major flaws in the devolution process was that tehsil municipal administrations (TMAs) were given additional responsibilities without providing them the additional staff members, resources, power, and regulatory environment to deliver these responsibilities. In the absence of these four key elements, any further investments in urban services managed by TMAs are not expected to deliver sustainable results and service improvements. project cycle stage: Lesson Topics: 3. The Local Government and Rural Development Department, through the project coordination office (PCO), was the executing agency of the project. However, with limited capacity demonstrated in implementing the project for the first 2 years, PCO management was taken over by staff members deputed from Housing, Urban Development and Public Health Engineering Department, and focus shifted toward infrastructure investments. Sustainability can be better achieved if the organizations that operate services remain fully involved in its design, planning, and implementation stages. project cycle stage: Lesson Topics: 4. It was envisaged that the tehsil municipal administrations (TMAs) would be assisted in offering opportunities to the private sector in the transport, recycling, and composting of solid waste, municipal slaughterhouses, and wastewater treatment plant operations. However, except for outsourcing slaughterhouse operations, no private sector participation was achieved. Private sector participation was included in the scope of project activities without fully understanding the dynamic of such a partnership, conducive regulatory environment, economies of scale, and capacities of TMA to enter into and manage such partnerships. The overall support required for new approaches for delivering services must be better understood before these are included in project designs to ensure success. project cycle stage: Lesson Topics: 5. The community participation in design and planning subprojects was minimal. The engagement with communities was mainly through social organizers and some council members, who were not directly related to mainstream implementation of the subproject, which was one of the key reasons for weak participation. Community participation requires their intensive involvement from the design to the implementation stages, through direct interaction with key players responsible for implementation, to build ownership and sustained partnerships. project cycle stage: Lesson Topics: 6. Delay in acquisition of the required land and award of contracts without implementation of resettlement plans impeded implementation and caused premature loan closure. Efforts are needed to built safeguard capacities within countries to implement and within ADB to supervise, guide, and monitor safeguard compliance. To check against safeguard-related delays, safeguard plans and their implementation should be part of a project readiness filter. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/southern-punjab-basic-urban-services-project-4
Balochistan Devolved Social Services Program | Pakistan | Education, Health, Water and other urban infrastructure and services | 2011-12-01 | Executing agency capacity. Capacity in the executing and implementing agencies was expected to be built through the accompanying TA loan. Program outputs like developing sector strategies, implementing expenditure tracking and service delivery surveys, training communities to manage and monitor social service delivery, and other outputs critical to achieving Program outcome depended on effective technical assistance (TA) loan administration. However, executing agency capacity to administer the TA loan was inadequate. Given the capacity constraints in the province, more frequent and regular TA review missions and direct support through ADB- administered TA could have improved Program implementation. However, security concerns made it difficult to attract and retain good consultants. Sector focus of policy reform. Given provincial and district capacity limitations, a Program focusing on a single sector would have had a better chance of success. Sustained support in one sector can be less demanding for both the government and ADB. Multi-sector policy reform interventions involving governance reform are difficult to manage, and a new system of local political governance imposed by the federal government added further complications. Reform sequence. The sequence of reforms in the policy matrix was such that all substantial results could be achieved only after the completion of second tranche actions. In addition, liberal assessment of compliance allowed the release of the first tranche without achieving much toward sustainable outputs. More result-oriented sequencing of policy actions for the first tranche could have achieved some sustainable improvements in social service delivery. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/balochistan-devolved-social-services-program
National Highway Development Sector Investment Program - Project 1 | Pakistan | Transport | 2011-12-01 | Implementation issues. The highway improvement project had a realistic time frame that took the implementation issues in Pakistan into account. These include governance, security, and institutional capacity constraints. Although one of the subprojects was delayed by 12 months and project implementation was affected by floods, this did not affect the overall project schedule. All these issues are likely to continue to impact current and future projects. Advance planning and adequate contingencies are essential for efficient project implementation. Social safeguards. The N70 subproject faced several delays due to land acquisition and resettlement issues. The important lessons from this include the need (i) to raise awareness of the importance of social safeguards within the government at central and local levels, (ii) to delay contractor mobilization in future until social safeguards have been complied with, and (iii) for ADB to apply its Safeguards Policy Statement (2009) in cognizance of national laws. Improve project implementation performance. The project shows that implementation can be improved by (i) ensuring that the executing agency has sufficient capacity in safeguards monitoring, and project management; (ii) enabling continuity of staff working on project implementation within the executing agency and at ADB; (iii) raising awareness of ADBï¿½s procedures within the executing agency at the appraisal stage; (iv) making ADB expertise available within the country for project monitoring and day-to-day interactions with the executing agency, consultants, and contractors; and (v) close supervision by the executing agency, ADB, and the supervising engineer, which improved contractor performance. Quality at entry. The institutional strengthening project could have been better designed in more consultation with the executing agency. The lack of understanding within the National Highway Authority (NHA) on the benefits of project, the delays in procuring the consultants, and the change in their terms of reference indicate the lack of ownership for policy reforms and institutional strengthening within the NHA. This contributed to the poor performance of the project. Had ADB engaged in a more rigorous policy dialogue at project planning stage, the project could have been designed better and more acceptable to the NHA. This poor performance illustrates the need for the government to adopt a clear strategy on developing the transport sector in general and the sectorï¿½s institutions in particular. It has also helped identify areas for future technical assistanceï¿½project planning, safeguards monitoring, and project management. The private sector in Pakistan also faces capacity constraints that prevent efficient and effective project implementation. This could be addressed by technical assistance programs to transfer good practices from other countries as well as to improve national educational institutions. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/national-highway-development-sector-investment-program-project-1
Pakistan: Punjab Resource Management Program | Pakistan | Public Sector Management | 2011-12-01 | 1. As programs need to be driven by the borrowers, capacities of executing and implementing agencies in program implementation must be carefully assessed at appraisal so that capacity disparities can be mitigated. For example, the Punjab Resource Management Program in Pakistan could have averted problems brought about by capacity gaps had it identified the risks early on and instituted mitigating measures, such as, the recruitment of program management consultants to assist the Project Management Unit, the Planning and Development Department, and the Finance Department. The limited institutional capacity of the executing and implementing agencies ultimately reduced the relevance of the Program. [Main text, paras. 14, 25-26, 30] project cycle stage: Design, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/pakistan-punjab-resource-management-program
Rawalpindi Environmental Improvement | Pakistan | Water and other urban infrastructure and services | 2011-12-01 | Alignment with overall reforms: The project only supported implementation of reforms in the participating towns and WASA in line with PLGO 2001 and urban policy actions agreed with the government for the project (para. 53). Ownership and commitment to reforms deteriorated in general and project implementation was adversely affected. Although these risks were identified in the project design, no flexibility was built into the design to respond to these external factors. Major urban reforms cannot be undertaken in isolation from the external environment; they require political will, incentives, flexibility in design, and critical mass within the system to champion such reforms. Clarity of roles and responsibilities: The PPTA and the RRP identified overlap in administrative and geographic alignments of agencies such as WASA, town administrations, RDA, the Cantonment Board, and the CDG responsible for municipal and other urban functions (para. 55). The policy actions, PSC and PIRC established for the project were unable to address these gaps. Clarity of roles, and geographic, administrative, and sector alignment are prerequisites for effective urban governance and need to be addressed at the planning stage or should be part of project readiness checklist. Inclusive implementation arrangements: The PPTA also identified and consulted key stakeholders, including private sector developers, DHA, and the Cantonment Boardï¿½accepting their role in influencing project scope and cost. However, no formal agreement was signed with these stakeholders (para. 54). Formal arrangements with key stakeholders on the scope and cost- sharing arrangement should be part of the design and planning stage, to avoid delays and confusion at the project implementation stage. Addressing the fundamentals reforms upfront: Major governance issues of autonomy and incentives to perform, which plagued the key implementing agencies that were the urban service providers, were only captured piecemeal in the policy framework. This allowed these issues that were fundamental for the success of the project to be addressed (or not be addressed) during project implementation. The design also allowed major investment subprojects to be implemented without addressing these fundamental issues. All critical conditions that are fundamental to project success should be part of project readiness at entry. Provision of optimal environment for change: The project design included community and private sector participation in the delivery of urban services, supported by some concrete small-scale activities. However, the project did not provide clear direction and adequate resources to deliver these activities (para. 46). Flexibility is important in the design of complex loans, but for this flexibility to be used effectively, additional capacity, a guiding framework, and resources should be included in the sector loan, with supporting technical assistance to guide the use of the resources. Secondly, private sector participation requires professional management at both public and private sector ends and economies of scale rather than a piecemeal approach in a few areas. Ensuring quality in complex reform oriented projects: The consultants under the loan were hired through QCBS. The staff costs in the bids were inadequate for quality staff. This hiring process allowed weak firms to bid low and win the bids, without fully appreciating the tasks ahead. The request for proposal for complex sector loans should either be quality-based or include a bid rejection option in case of underbidding in QCBS. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/rawalpindi-environmental-improvement
Private Participation in Infrastructure Program | Pakistan | Finance | 2011-09-01 | Delays in implementation of certain aspects of the program and the overestimation of the increase in PPI projects completed suggest three lessons: (i) outputs that are prerequisites for other outputs need to have a technical assistance dedicated to them upfront; (ii) ADB program designs should include a more strategic approach to marketing the benefits of PPI frameworks to the public, the private sector, and government; and (iii) establishment of PPI frameworks needs to be accompanied by the development of ?pathfinder projects? that may be prepackaged in line with good international practice, and protected from special interest interference. In addition, experience with the implementing agencies suggests that regular and persistent communication with ADB staff in Manila, with implementing agencies, and the resident mission are critical to keeping the program on track. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/private-participation-infrastructure-program
Earthquake-Displaced People Livelihood Restoration Program | Pakistan | Finance, Public sector managements | 2011-08-01 | The owner-driven, in situ approach to post-disaster housing reconstruction is efficient, but only partially effective in achieving the desired outcomes. This is mainly because ensuring uniformity in construction quality and seismic standards is a major challenge when serving large populations, irrespective of the levels of awareness and training of the home owners. This challenge can be partly addressed if there is real-time impact and outcome monitoring, as well as an efficient feedback-and-response loop during the reconstruction. In situ housing reconstruction prevents disputes and increases efficiency, but it does not allow for improvements in historic patterns of rural, village, or town development; nor does it make possible the consolidation of housing sites and services. There is thus a trade-off between efficiency and overall effectiveness. On the other hand, outsourced reconstruction that allows household relocation by a third party may be more effective, but much less efficient and sustainable. Community involvement in owner-driven rehabilitation and reconstruction programsï¿½through training, inspection responsibilities, and village committeesï¿½ provides the human resources needed for major post-disaster housing reconstruction efforts. It also creates a greater sense of ownership, helps build capacity, reduce disputes and ensures the sustained use of seismic reconstruction techniques in the long term. Reconstruction led by communities can be expedited if house design options take into account the local skills, materials, tastes, geography, and culture. Also, innovative money-saving building techniques need local acceptance to be sustainable, but this may require more time and effort devoted to training. A major effort went into training compliance teams and developing compliance manuals used for spotted and reported noncompliance among the home owners. Employing a third party to monitor compliance directly at the household level may be the best way to get a comprehensive picture of the problems involved in the adaptation of seismic standards. Perhaps a greater focus on the ability of the compliance teams to provide on-the-spot solutions to home owners may also have yielded better results. However, this approach assumes that the home owners have the skills and financial capacity to implement the recommendations. The reconstruction grants of PRs175,000 per household offered by the government was for 400 square foot area. This was substantially lower than the prevailing rates for the desired standard of seismic-resilient construction. About 60% of the rebuilt houses were 500-999 square feet. A pre- and post-earthquake comparison (footnote 10) showed that the overall proportion of houses with less than 1,000 square feet had increased from 65% to 80%. These figures show that the government grants were not enough to satisfy the seismic-compliant construction standards and provide the required living space for families. The inadequacy of the grants may have resulted in the construction of smaller houses or the omission of essential seismic-resistant features, or both. In the future, the size of compensation grants must take into account the higher costs of applying seismic-resistant building standards and the average house size. Similarly, the release of the first three installments took less time compared with the release of the final installment. The last installment was associated with superstructure (above plinth level). Such works entail major seismic resistant components. Noncompliance during construction in this phase has resulted in delays in the release of the final installment. Future programs should build in rigorous monitoring and consultation to avoid or minimize substantial noncompliance in the final phase of reconstruction. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/earthquake-displaced-people-livelihood-restoration-program
Infrastructure Development | Pakistan | Agriculture, natural resources and rural development, Energy, Finance, Transport | 2011-07-01 | The Planning and Development Division's (PDD lack of capacity to assist the implementing agencies delayed the issuance of consultant mandates, thus slowing down work on some priority subprojects. The choice of the PDD as the executing agency was a mistake. The PDD lacked qualified staff,, access, and a track record. The setting up of new units to manage consultancy contracts does not work and should not have been proposed in the first place. ADB should have restructured its technical assistance (TA) loan much earlier, taking into account two events: (i) the approval of new multitranche financing facilities (MFFs) with project-preparation components that duplicated some of the TA's work, and (ii) dramatic changes in the economy that made some subprojects irrelevant and/or unfundable. The review missions reported on consultant services and their performance, and they did propose a major restructuring of the TA over time. If the restructuring had been done earlier and more extensively, however, all concerned would have saved time and money. The important lesson here is that one must take changing circumstances into account. While the project-preparation facilities made sense, the TA loan itself was spread too thinly. The funds were dispersed across three sectors, and were handled by numerous agencies managing subprojects in many locations. This made coordination a challenge right from the outset, especially given the absence of an experienced and capable local coordination team. It did not work. In retrospect, the multi-sector design of the TA was wrong, and approval should not be given for similar TA loans in the future. The important lesson learned here is to restrict loans to one sector at a time. When projects cross ministerial boundariesï¿½as was the case with the national and provincial stakeholders in the water resources sectorï¿½there must be a clear commitment at the design stage to avoid disputes. Otherwise, such projects should be avoided altogether. Where a large capacity-building component precedes project preparation, reviews by ADB should be more frequent. The consultants should also produce verifiable and detailed reports on progress and staff training. This will allow a more timely response to problems by both ADB and the Borrower. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/infrastructure-development
Restructuring of the Technical Education and Vocational Training System Project (Balochistan) | Pakistan | Education | 2011-06-01 | Design A well-thought-out conceptual design is a key to the success of any project. In this case, the project design had commendable objectives, but it overestimated the commitment and capacity of the executing and implementing agencies, and relied too heavily on consultants. Before a complex and innovative technical education and vocational training (TEVT) project is designed, particularly in a relatively less developed region like Balochistan, it is necessary to have extensive consultations with stakeholders directly involved with the TEVT system to develop realistic objectives and activities. In provincial projects, it is important to clarify the sector reforms that can be authorized at the provincial level. A number of the proposed reforms, such as the competency-based training (CBT) and on-the-job training, required changes in the curriculum, which fell under federal purview. Inadequate review by ADB of the Planning Commission form 1 (PC-1) and inconsistencies between the PC-1 and the report and recommendation of the President (RRP) slow down project implementation. To ensure a thorough review of the PC-1 by ADB, the project officer should be required to prepare a comparative statement identifying both the similarities and differences between the PC-1 and the RRP and loan agreement, and the Planning and Development Department (PDD) should be advised on corrective measures before the loan is declared effective. Implementation Weak capacity of project staff results in procedural lapses, possible violations of the loan agreement, and slow implementation. Moreover, stringent internal audit controls and close monitoring of expenditures bring more transparency in financial transactions. Frequent changes in project administration at ADB caused confusion and had a negative effect on project implementation. During the project, administration moved from the South Asia Department to the Central and West Asia Department, and from the Social Sector Division, via the Governance and Finance Division, to the Pakistan Resident Mission. Given the weak capacity of the executing and implementing agencies, consultants should have been recruited before loan effectiveness. Had the consulting services been available, the project would most likely have achieved at least some of its objectives. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/restructuring-technical-education-and-vocational-training-system-project-balochis
Pakistan: Reproductive Health Project [Loan 1900(SF)-PAK] | Pakistan | Health | 2010-12-31 | Implementing projects in countries with similar circumstances as in Pakistan highlights: (a) the need for start-up technical assistance to set the stage for effective project implementation as part of the loan covenant, establish the project coordination units and/or project implementation units, and ensure that a realistic implementation arrangement is put in place, even if it means revising the project implementation design, drafting a management operation manual, assisting in the opening of imprest accounts, training project staff on ADB procurement and disbursement procedures and reporting requirements, and initiating the preparation of procurement and disbursement documents; (b) the need for more frequent review missions, probably with an appropriate consultant/advisor on board, in the early years of implementation and for as long as project implementation is deemed off track; and (c) the need to take immediate action to scale down project costs, and/or cancel part of the corresponding loan, when it becomes apparent that the government is unable or unwilling to put up the necessary counterpart funds. While it is important to correctly and objectively assess implementation constraints and implementation capacity, countries with serious development needs and weak institutional capacity should be assisted with building up this capacity as part of project design. This refers to short-term project implementation capacity as well as to longer-term program administration capacity. The project starting date should be set after start-up TA has been successfully completed, and countries with weak institutional capacity should be given time to comply with the covenants and requirements for loan effectiveness through a mentoring process that the start-up TA should provide. [Main text, page 8, section E(ii)] project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Counterpart funds Modality: Technical Assistance Project Design: Project design Project Management: Procurement Project Management: Project management Capacity Development: Capacity development | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/pakistan-reproductive-health-project-loan-1900sf-pak
Mega City Development Project | Pakistan | Finance, Transport, Water and other urban infrastructure and services | 2010-12-01 | Lessons from previous projects. Lessons from two older ADB urban sector loan projects to Karachi in 1986 and 1991, respectively, which were rated unsuccessful and partly successful, include the need for (i) greater attention to sustainability, (ii) enhanced project design based on sound assessments, (iii) careful consideration for institutional shortcomings of executing and implementing agencies, and (iv) greater efforts to address the financial insolvency problems of the Karachi local government bodies. A specific lesson derived from the previous Karachi Urban Development Project is that urban upgrading is complex and must be able to deal with the broad range of problems faced by katchi abadis dwellers, including regularization and security of tenure. All these lessons suggest that urban development assistance demands a holistic approach. To be of lasting value, major capital investments need to be supported by capacity building, policy, regulatory and institutional reforms, as well as new and innovative financing vehicles that facilitate provision of high-quality infrastructure services on a sustainable basis. However, although the technical assistance (TA) loan for Megacity Development Project incorporated these lessons in its design, it failed for various structural reasons, with the lack of consensus between various levels of authorities being the most serious challenge. Avoidance of challenging issues. At both government levels (the government of Sindh and City District Government of Karachi or CDGK), there was a systematic avoidance of exposure to and tackling of various governance and institutional issues, as well as reforms required to examine and correct these challenges. Analysis of the few project subcomponents completed illustrates that the government of Sindh and CDGK only implemented easy studies that did not and could not tackle major disputes or issues that might require serious reforms in Karachi. ADB, the government of Sindh and CDGK should have been far more insistent at the outset of the project on the critical reform and governance issues than was the case on this project. Problematic shifting of priorities. Continuing problems with government approvals, and constant changes in focus, scope, and direction caused major delays. ADB noted a range of concerns over the continuing delays on the processing of the Project in its previous incarnation, the Karachi Mega City Development Program, after developing the loan proposal to the point of loan negotiations in May 2008. Following meetings in July 2008, the program was reconfigured at the request of the government of Sindh, this time an integrated, holistic urban transport program for Karachi, with new implementation arrangements. Unfortunately, the agreed deadlines were not respected while no progress was evident on steps to achieve institutional reforms. The requested revisions to the proposed Project, for a truncated investment in bus rapid transit, a shift in geographic focus to secondary cities, and a two- tranches structure did not lend itself to the envisaged sector reforms, nor was it suitable for ADB's multitranche financing facility (MFF). By November 2008, the proposed Sindh Urban Mass Transit Investment Program was also cancelled. The TA loan was originally designed to provide the prerequisite planning, systems integration, and capacity development to address the sorts of issues that arise in urban planning. However, it did not succeed. Counterpart funding and incentive issues in TA loans. Despite the challenges in project implementation, the project support unit (PSU) and local support unit (LSU) had utilized close to $4 million in counterpart funding, while ADB disbursed only 15% of the TA loan. As a result, the actual split between ADB and the government was 15:85, when the agreement was 70:30. Thus, a key lesson is that there should have been far greater oversight on the utilization of counterpart funds, as the ADB-financed expenditures and activities and overall progress of the TA loan lagged far behind. The resource utilization also shows a fundamental flaw in the design of TA loans, in which a significant share of resources is allocated for international consulting inputs. The various challenges in this TA loan, including protracted internal government approvals, delayed consultant selection. In future, ADB should very carefully examine the incentives of the executing and implementing agencies in utilizing resources. Core activities, such as recruitment of experts, are typically delayed while routine activities, such as maintenance of offices and vehicles, are approved on time, without a continuous assessment of project progress. Weak government commitment. Given the political environment and the likelihood that a significant lack of consensus might be a daily reality on this project, the design should never have been so complex, with four different subcomponents, leading to a much larger MFF expectation. Perhaps a lesson here is that to achieve early and committed buy-in to required reforms and institutional shake-up, smaller and simpler components could be tested through a small scale or project preparatory TAs, which may lead to visible and larger MFF commitments. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/mega-city-development-project
North-West Frontier Province Urban Development Sector Project | Pakistan | Agriculture, natural resources and rural development, Finance, Transport, Water and other urban infrastructure and services | 2010-12-01 | The project supported reforms only in the 24 participating tehsil municipal administrations (TMAs). The provincial government was expected to undertake reforms and address capacity gaps in all the other TMAs (52 in all). This arrangement seriously isolated the reform process. Sector loan projects should assess the political will, capacity, and incentives related to policy actions at all levels before building the support and incentives mechanism for reforms. The policy reforms agreed on at appraisal were overshadowed by the broader reform agenda introduced under local government ordinance (LGO) 2001 before project approval. Where major changes occur in the external environment of projects before ADB approval, it is more efficient to revise the project design up front rather than postpone the major adjustments. The project design was based on the assessment of seven sample TMAs and assumptions related to support for LGO 2001 from other sources to address capacity issues. The basis of the capacity assessment was seriously compromised during implementation. The project design did not have enough flexibility and depth to fill these capacity gaps, which would have required major changes in institutional arrangements and additional funding, a possibility that was avoided during implementation. Sector loans that include policy reforms should have much more flexibility and depth to absorb the changes that accompany most reform processes. There was a 3-year gap between the project preparatory technical assistance (PPTA) evaluations (in the last quarter of 1999) and the start (effectiveness) of the project (in the last quarter of 2002). Most structural and financial management plans, base maps, and priority subprojects therefore had to be reappraised at the start of the project, further delaying the project and straining limited capacity. To keep evaluations and project designs relevant, the time between project preparation and start up should not exceed 1 year. The project did not provide market-based salaries. Good staff was therefore hard to retain and turnover was high. This was a major reason for project failure. The overall cost implications of paying professional managers market-based salaries are marginal, especially when the substantial impact of weak capacities on project output and outcomes is considered, as this project demonstrated. The project design offered flexibility in developing models for community and private sector participation in the delivery of urban services, without providing a clear framework or adequate resources for these activities. Flexibility is important in the design of sector loans, but for this flexibility to be effectively used, additional capacity, a guiding framework, and resources should be included in the sector loan, with supporting technical assistance for project administration to guide the use of the resources. The project schedule was unrealistic for a complex project that relied heavily on existing capacity and several up-front conditions before the subproject investments. The scheduling of complex sector and policy loan projects has to be improved and streamlined on the basis of actual implementation experience. A major reason for the delay in project start-up was the variance between the report and recomendations of the president (RRP) and the government's PC-1 planning document. Draft RRPs and PC-1s for a project should be shared between ADB and the borrower well before loan approval. The consultants under the loan were hired through quality- and cost-based selectio (QCBS). The staff remuneration in the bids was inadequate for good-quality staff. The level of effort and the skill set specified in the request for proposal (RFP) also did not match the complexity of the assignment. Similar issues encumbered the RFP for the nongovernment organizations (NGOs), allowing generally weak firms to submit bids that could not fully appreciate the tasks ahead. The terms of reference should adequately capture the complexity of the sector loans, and the RFP fro such loans should either be quality based or include a bid rejection option in case of underbidding in QCBS. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/north-west-frontier-province-urban-development-sector-project
Punjab Devolved Social Services Program | Pakistan | Education, Health, Public sector management | 2010-12-01 | Design. The risk assessment of political resistance to devolution was not sufficiently robust, and mitigating measures were not realistic. The design should have been revised to address political resistance to implementation of the Punjab Local Government Ordinance 2001 (PLGO). Failure to do so undermined program implementation. Another significant design flaw was the multi-sector and ambitious scope of the program. This observation was also raised by the executing agency (EA) during the program completion review mission. The demands of implementing reforms across four sectors limited the extent of sustained interaction in any one sector. The water supply and sanitation sector, in particular, faces a very different set of development needs and requires specific technical expertise. The multi-sector Second Social Action Program Project faced similar implementation challenges, though this lesson was not sufficiently incorporated into the program design. Implementation. The implementation efficiency of the program was constrained by the late recruitment of the Technical Assistance Management Agency (TAMA), and the lack of recruitment of local support groups. The TAMA was meant to mobilize about 4,000 person-months of consulting services. The local support groups were expected to be mobilized in each district for 3 years to enhance capacity. For the majority of program implementation, these tasks became the responsibility of ADB and the program support unit (PSU), albeit with insufficient resources, which negatively affected implementation efficiency. A fully functional TAMA for the duration of the program would have allowed ADB to focus more on implementation of program reforms, rather than on technical assistance (TA) contract issues. Sustainability. The focus of the EA and PSU was on implementation of the policy matrix. Considerably less importance was given to the loan covenants. The PSU indicated that it would have recruited local support groups if it had been a condition in the policy matrix; however, since it was not a tranche condition, the PSU did not feel compelled to comply. This was also the case with covenants related to social sector expenditures and conditional grants, which were key covenants for ensuring improved social sector performance. Major covenants should have been included in the policy matrix for greater consistency and to increase the likelihood of compliance. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/punjab-devolved-social-services-program-0
Restructuring of the Technical Education and Vocational Training System Project (North-West Frontier Province) | Pakistan | Education | 2010-12-01 | Design A well thought out conceptual design is a key to the success of any project. In this case, the project design had commendable objectives, but it seems that the commitment and capacity of the executing and implementing agencies was overestimated, and there was too heavy a reliance on consultants. Due to lack of capacity and interest by the executing and implementing agencies, sector reforms did not get the traction that was aspired to. Before a complex and innovative project is designed, particularly in a relatively less- developed region such as the Khyber Pakhtunkhwa (KPK) province, it is necessary to have thorough consultation with stakeholders directly involved with the technical education and vocational training (TEVT) system to develop realistic activities. Some of the innovative activities under the project such as the management development program, performance-based management system, and competency-based training required many more resources and greater time allocated if they were to be developed successfully,. In provincial projects it is important to identify the sector reforms that can be authorized on the provincial level. A number of the proposed reforms under the project, such as the competency-based training and the on-the-job training, required changes in the curriculum on the federal level. Inadequate review by ADB of the government project documents (PC-Is) and inconsistencies between the PC-Is and the report and recommendation of the President are perennial problems that result in slowing down the pace of project implementation. A thorough review of PC-Is by ADB should be ensured by requiring the project officer to prepare a comparative statement identifying both the similarities and differences between PC-Is and the report and recommendation of the President and/or loan agreement, and advising the executing agency(ies) on corrective measures before declaring project effectiveness. Implementation One of the main strengths of the project was the continued presence of the same project management in the project management unit (PMU), who were selected and appointed on a competitive basis. More confusing were the frequent changes in the ADB administration of the project. During the project's 3.5-year life span, the administration moved from the South Asia Department to the Central and West Asia Department, and from the Social Sector Division via the Governance and Finance Division to the Pakistan Resident Mission. This was detrimental to the continuity of interaction with the KPK government. The frequent change in administration also affected the filing of the key project documentation, resulting in some of the files remaining in headquarters and others in the resident mission. During the inception mission, the KPK government requested a reallocation of loan proceeds in line with what was agreed to during loan negotiations. The requested reallocation required a major change in scope, which was proposed to take place during the midterm review mission, scheduled for the third year of project implementation. The midterm review mission does not necessarily need to come in the middle of the project period; it can be scheduled early on, for instance in the first year of project implementation, if it would help to get the project going after a slow start. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/restructuring-technical-education-and-vocational-training-system-project-north-we
Pakistan: Rural Finance Sector Development Program [Loans 1987-PAK and 1988-PAK] | Pakistan | Finance | 2010-11-30 | ADB experience in other countries shows that sector development programs can be used to facilitate financial sector development through the complementary and mutually reinforcing use of program, technical assistance and investment loan modalities. However, sustained political commitment is a key prerequisite for success. Lesson (iv) would appear to apply to financial intermediation loans, which were not used in the Rural Finance Sector Development Program (RFSDP). This validation finds that the RFSDP experience underpins the need for realistic assessments of governments' continued compliance with tranche conditions. The RFSDP experience also illustrates inherent incentive problems associated with the restructuring and commercialization of state banks. [Main text, pages 7-8, section E(ii)] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Modality: Lending modality Modality: Program Modality: Technical Assistance Methodologies/Approaches: Sectoral approach | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/pakistan-rural-finance-sector-development-program-loans-1987-pak-and-1988-pak
Rural Enterprise Modernization Project | Pakistan | Industry and trade | 2010-10-01 | The project attempted to indigenize the One Tambon One Product (OTOP) concept that was considered successful in Thailand and Japan. However, only limited efforts were made to understand the likelihood of the success of this initiative in Pakistan. The reasons for the program's success in the other countries and whether the same positives were present in Pakistan were not assessed. Moreover, the success of such projects is often led by a bottom-up grassroots demand for the project outputs, yet this project was a top-down initiative. Future projects that rely on the transfer of foreign programs should assess the suitability of the concept before adapting it from one country to another. The security situation in Pakistan was a major factor in the failure to recruit international consultants. In countries where security concerns prevail, project design needs to account for the difficulty in recruiting and retaining suitable international consultants. Limiting the role of international consultants to a few key positions and to supervision of national consultant inputs may contribute to greater project success. The project had a high weighting of consultant inputs in the first 6 months. It is unrealistic to expect that international consultant teams can be on the ground and achieving outputs within such a short time frame in countries such as Pakistan, given the difficulties in recruitment. An alternative may be to phase in international consultant inputs later in the project to allow for a more realistic recruitment process. However, application of the streamlined business arrangement principles should provide greater project preparedness for accelerated consultant recruitment. The project implementation schedule was amended early in the project to comply with the government's request for immediate action and results via the two- pronged approach. Unless there are clear deficiencies in project design, ADB should resist requests to change the design or implementation arrangements early in implementation, because the original project design should be given a chance to succeed. Corrective action can be taken later as problems become apparent. Ministry of Industries, Production, and Special Initiatives (MoIPSI) and the project management unit (PMU) had difficulty in understanding the requirements of the design and monitoring framework (DMF) because it lacked clarity regarding activities and output requirements. The PMU noted that, even though terms of reference had been prepared for individual consultants, the exact purpose of some of the positions and the outputs to be delivered were not clear. Review missions need to ensure that the project management fully understands the requirements of the DMF regarding achievement of activities and outputs. The officer responsible for project design should be involved in the initial stages of project management to ensure a smooth transition from processing to implementation. ADB should monitor the Planning Commission (PC-1) approval process for Pakistan projects so as to be aware of potential problems and ensure that appropriate levels of counterpart funds are guaranteed at the time of loan negotiations. The concept of a sustainable self-funding Rural Enterprise Modernization Company (REMC) providing BDS in markets with limited ability to pay was an inappropriate design. The services provided are public benefits, which are traditionally the role of government rather than private companies. The lack of private entities currently providing these services in Pakistan reinforces this point. It would have been appropriate if management of the project had been transferred to PRM. This would have facilitated communication, supervision, and resolution of issues as they emerged. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/rural-enterprise-modernization-project
Pakistan: Decentralized Elementary Education Project (Sindh) | Pakistan | Education | 2010-09-30 | 1. Overly complex and ambitious projects are difficult to implement especially when the executing agency is not familiar with the procedures and institutional practices of ADB. [Main text, page 5, section E(ii)] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies 2. Even a minor or routine problemï¿½e.g., the currency of the second-generation imprest accounts in the districtsï¿½can prove fatal and bring down the entire project if left unresolved over a long time. [Main text, page 5, section E(ii)] project cycle stage: Implementation Lesson Topics: Project Management: Project management Project Management: Risks/Risk management 3. The persistence of a minor or routine problem could mask serious underlying issues that the project design left unidentified or unresolved, e.g., ownership of the project objectives or governance issues. [Main text, page 5, section E(ii)] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project management | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/pakistan-decentralized-elementary-education-project-sindh
Pakistan: Sindh Devolved Social Services Project [Loan 2049-PAK] | Pakistan | Multisector | 2010-09-30 | This validation adds the need for steps to be taken at an early stage to keep the technical assistance (TA) on track, and ensure that it is being managed according to the objectives of the loan program that it is supporting. The Independent Evaluation Department's 2005 Sector Assistance Program Evaluation for Social Sectors in Pakistan infact had anticipated these based on the issues that it identified from the then implementation of Sindh Devolved Social Services Program. It noted that ï¿½while the program was well underway, the supporting TA loan for local government capacity building had still not become effective, thereby delinking funding and capacity building.ï¿½ It further highlighted the role of provincial line departments to dominate TA support and absence of monitoring systems to report progress. [Main text, page 6, section E(ii)] project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Project management | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/pakistan-sindh-devolved-social-services-project-loan-2049-pak
Road Sector Development Program | Pakistan | Transport | 2010-09-01 | The project timeframe did not allow adequate time for developing knowledge and understanding, processes, procedures, and the project implementation framework. More attention should have been paid to the executing agency's ability to implement the project. Inadequate capacity resulted in complex problems and incomplete outputs. The Government of Sindh (GOS) should have had greater ownership and commitment to the completion of activities. A project-based, decision making forum may have been an option to reduce processing delays. Pre-project capacity building is essential in the following areas: procurement; loan and contract administration; disbursement processes; monitoring and evaluation mechanisms; periodic reporting needs; and social and environmental safeguards. A well-qualified and experienced project team leader and consultants' familiarity with ADB processes are essential to implement an ADB-financed project. Extensive and regular coordination of ADB staff is important in developing adequate skills, capacities, and experience, and eliminating common implementation bottlenecks. A stepwise, flexible approach should have been adopted with adequate supervision support for sector specialists in the policy and reform program and capacity building activities. Overly optimistic objectives and implementation scheduling should haven been avoided. A gradual, step-by-step approach consistent with local realities should have been adopted. The local communities and government should have been considered as part of the project team as they could have played an important role in planning and implementation. ADB should have insisted on dedicated professionals with a demonstrated track record to ensure consistency, continuity and competence in the project team. Achieving the investment and reform program in a limited timeframe was difficult within a highly bureaucratic environment. The government's commitment to implement the institutional development, capacity building, and reforms program should have been carefully reviewed, discussed, and tied to funds release. A detailed implementation review and evaluation process must be conducted. An inappropriate and poorly performing consulting firm should have been replaced as soon as possible. Heavy reliance on a single group of consultants' for both components does not work. In the case of unrecoverable delays, ADB should have considered reducing the project scope, closing the loan early, or suspending the loan until all conditions were met. Late completion of pre-project activities and advance actions caused inordinate delays and ultimately incompletion. Resources should have been mobilized more quickly. Project readiness in the areas such as land acquisition, detailed design, procurement, establishment of the project management unit and project implementation units should have been in place prior to loan approval. Unrealistic work schedules, poor procurement planning, insufficient implementation details, and loose monitoring targets prolonged implementation. Over optimistic implementation plans should have been avoided. Inappropriate monitoring and reporting risks noncompliance, suspension, or early closure. ADB should enforce regular monitoring of land acquisition, resettlement, and environmental impacts. Previous performance of consultants should have been a major evaluation and selection criteria. Penalties for poor performance and failure should have been introduced in the consultancy contracts. A stricter approach should be adopted for replacing specialists. The project had difficulty in attracting international contractors; those who were contracted performed poorly. Suitable packages for local competitive bidding may yield better results. The prequalification activity should ensure participation of capable and resourceful contractors. The postqualification procedures should have been adopted for procuring civil work contracts allowing more participation and wider competition. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/road-sector-development-program
Pakistan: Agriculture Sector Program II | Pakistan | Agriculture, Natural Resources, and Rural Development | 2010-08-31 |  | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/pakistan-agriculture-sector-program-ii
Pakistan: Multisector Rehabilitation and Improvement Project for Azad Jammu and Kashmir | Pakistan | Education, Energy, Health, Transport, Water and Other Urban Infrastructure and Services | 2010-08-31 | 1. Where institutional weakness is evident, means of assuring adequate support could include capacity building technical assistance, over which ADB has more control than it does when using loan implementation consultants. [Main text, page 7, section E(ii)] project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development 2. Paying salaries for government staff in project management or implementation units can cause problems of overstaffing or inappropriate appointments. A salary supplement may often be a better option, where essential, but with strict limits on eligibility to avoid the same problems. [Main text, page 7, section E(ii)] project cycle stage: Design, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management 3. Rebuilding or rehabilitating public infrastructure in earthquake-prone areas should include earthquake resistance as a key parameter. This did not happen in the project (as far as can be ascertained) and poses a risk for the future. It is noted that many schools in the earthquake-affected area collapsed with major loss of life. [Main text, page 7, section E(ii)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Management: Risks/Risk management Country Context: Emergency 4. Most importantly, project experience would suggest that, when substantial parts of a project area are struck by a major natural disaster such as the 2005 earthquake, ADB should make a major effort to help the government redesign the project. While the project underwent two changes in scope, these related to increases in unit costs and, to a large extent, withdrawal from earthquake-affected districts. In such situations, ADB may in the future consider redesign to align the project with the needs for disaster recovery, rehabilitation, and reconstruction, meshed with assistance from other development partners. In the project, it may have been possible to effectively reorient the project to focus on reconstructing hospitals and schools in the affected districts or other aspects as decided by the government. [Main text, page 8, section E(ii)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Country Context: Emergency | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/pakistan-multisector-rehabilitation-and-improvement-project-azad-jammu-and-kashmir
Pakistan: Supporting Public Resource Management Reforms in Balochistan | Pakistan | Public Sector Management | 2010-08-31 | The design of the Balochistan Resource Management Program, supported by the technical assistance loan, was meant to promote the use of available fiscal resources for delivering services to the poor. This can happen only if the system that links the financial sector and the delivery of services to the poor exists on the ground, and is functioning properly. The situation in Balochistan clearly did not fulfill these conditions. During Board consideration of the loan, a number of members had raised this issue and cautioned the staff, saying that implementation was going to be key. [Main text, page 5, section E(ii)] project cycle stage: Design, Implementation Lesson Topics: | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/pakistan-supporting-public-resource-management-reforms-balochistan
Sindh Rural Development Project | Pakistan | Agriculture, natural resources and rural development, Finance, Public sector management, Transport | 2010-03-01 | When the project was prepared ADB was exploring the possibility of addressing the issue of labor welfare and labor standards in its operations. Various first-generation studies, policies, procedures and projects on labor, social protection and governance were under consideration. The project was a departure from mainstream project design at ADB with respect to the areas addressed and interventions planned, but it had limited potential to address structural poverty reduction measures. It suffered from unsuitable timing, cumbersome conditions and /covenants, and the selection of an inappropriate executing agency. The lessons from the project can be considered for the design of projects that address underfunded critical areas. 1. Feasible Conceptual Framework and Design Approaches The project experience raises a larger question: whether actions to improve labor rights and welfare are compatible with ADB's existing design modalities (i.e., program, sector and investment loans). The experience in Pakistan has not been encouraging with respect to any of these approaches. Program loans. Experience indicates that tenancy and labor rights cannot be effectively addressed via program loans. These loans involve (i) support by market forces that have vested interests in private sector development; and (ii) the interest of the government to have access to rapidly disbursed foreign exchange to reduce budget deficits and improve the balance of payments. Tenancy and bonded labor are land-related issues, and labor welfare requires increases in public expenditures, resulting in more budget liabilities; consequently, expansion of labor rights is not easily accomplished under program loans. The ADB experience of including labor rights in the scope of program loans in Pakistan also shows that they are not compatible, the Punjab Resource Management Programs (Subprogram 1) being the best example. Labor- related regulatory and administrative reforms were included in the design but given the program loan focus on fiscal matters and reduction of recurrent costs, these measures were not achieved because these measures required increase in public expenditure and legislation. The agenda of labor rights is also incompatible with these loans because rather than entailing restructuring of commodity, capital and fiscal markets through rapidly-disbursed loans, it involves political processes labor representation in legislative bodies, constitutional and legal provisions, an effective judicial system, and above all the abolition of a feudal structure, which is a root cause of bonded labor. Sector loans. The experience with sector loans is also not encouraging. A labor and governance review of ADB-assisted road sector loans in Pakistan reported massive violations of labor standards, despite the inclusion of contract conditions on compliance with labor standards in the standard ADB bidding documents. Sector loans lack the scope to address crosscutting themes and have mostly been successful due to established institutional linkages within given sectors. In contrast, the issue of labor rights is not confined to a sector, but is a crosscutting macro-level structural issue involving nationwide economic, sociopolitical, and legal reforms. Investment loans. Investment loans lack the scope for macro-level structural reforms as they deal with service delivery through existing local structures in a specific geographical area. At best, a capacity-building component can be included in these projects to improve efficiency of the existing structures. Multisector community development projects are generally complicated in nature and adding a labor rights protection agenda to these projects would complicate implementation. This project is a classic example of this. Conclusion. In summary, the existing ADB operational design modalities do not provide space for promoting labor rights. Links between labor rights and welfare, good governance practices, poverty reduction and the improvement of labor rights through loans by multilateral financing institutions is relatively under-researched, at least with respect to Pakistan. Yet, given the overarching focus of ADB on good governance and poverty reduction, it is critical that this be explored. Poverty reduction not only requires that income opportunities be created, but also that these opportunities constitute a means by which individuals and households can exit the absolute poverty cycle. 2. Feasible Scope and Implementation Arrangements for a Community Development Project A multisector community development project must be organic in nature (i.e., self- operating, which reduces the coordination demands on the executing agency, and the need for monitoring by ADB). This can only happen if (i) the design includes comparatively more tested and proven interventions and fewer new initiatives; and (ii) the interventions are limited in number and strategic in nature; and (iii) if an appropriate executing agency and nongovernment organizations (NGOs) are selected at the appraisal stage. Given the sector mandate of line agencies in Pakistan, provincial planning and development departments are the best institutional homes for multisector projects, as these are the only departments with a multisector mandate. In addition, they have established reporting lines and institutional relationships with line departments and district governments. The ADB- assisted North-West Frontier Porvince (NWFP) Barani Areas Development Project (phase I and II), Punjab Barani Areas Development Project, and Sustainable Livelihoods in Barani Areas Project are four examples of successful project implementation by these departments. The model of involving multiple district-based NGOs for community mobilization and selecting them through the National Competitive Bidding (NCB) process is not successful due to (i) their lack of capacity; (ii) politicization of the recruitment process; and (iii) the lengthy and cumbersome process of recruitment through the NCB process,18 which in the case of the project added limited value because of the limited number of qualified district-based NGOs in Pakistan. In the case of the Sindh Rural Development Project or SRDP (and in many other similar cases in Pakistan, such as NWFP Barani Areas Development Project - Phase II), the process of competitive bidding had been unsuccessful. Almost all of the district-based NGOs participated in bidding, mobilized their contacts against each other, and ended up in serious conflict. To avoid startup delays and politicization of the recruitment process, the most feasible mode of procurement of community mobilization services is single-source selection of one qualified NGO at the appraisal stage. Some of the successful examples of the one-NGO community mobilization model and single source selection at appraisal are: (i) Sustainable Livelihoods in Barani Areas Project; and (ii) Sindh Coastal Community Development Project. These projects have been able to start community mobilization, small-scale infrastructure and training activities soon after loan effectiveness. Projects that are innovative in nature or complicated in design inherently involve delays and require intensive ADB supervision. The potential delays should be factored into the design. Community development projects require additional time and proper arrangements for community mobilization and social preparation processes. ADB experience with such projects, including the Sindh Rural Development Project, shows they generally experience delays of 2 years. The project period should not be less than 7 years. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/sindh-rural-development-project
Chashma Right Bank Irrigation Project (Stage III) | Pakistan | Agriculture, Natural Resources, and Rural Development | 2010-01-12 | 1. All formalities, including approval of government project documents, should be completed before the loan agreement is concluded, thus avoiding potential delays between loan effectiveness and project start-up. This should specifically include project management staffing, appointment of implementation consultants, allocation of counterpart staff, and advance preparation of procurement packages. project cycle stage: Lesson Topics: 2. The incorporation of a bonus payment for early completion in civil works contracts improved the responsiveness of the contractors in correcting deficiencies in works undertaken. project cycle stage: Lesson Topics: 3. Care is needed in undertaking cost-cutting measures to ensure that these do not compromise the long-term sustainability of a project by increasing the requirement for operation and maintenance. project cycle stage: Lesson Topics: 4. Institutional frameworks and agreements related to project operation and maintence (O&M), in particular cost recovery from project beneficiaries, must be implemented effectively. In particular, where responsibility for O&M is to be shared between a number of stakeholders (e.g., provincial and local governments, beneficiaries), all parties should be actively involved in project design from the outset. project cycle stage: Lesson Topics: 5. The most effective approach to compliance is to specifically address environmental and social safeguard issues (including beneficiary consultations) at the earliest stage of the project cycle. project cycle stage: Lesson Topics: 6. Lost opportunities for gender mainstreaming at the beginning of the project were partly due to the lack of established mechanisms and clear guidelines on gender mainstreaming on the part of ADB before 2008. However, because of the inspection request that extended the Project, adjustments were made, producing gender equality results with the guidance of up-to-date manuals on gender and increased support to hire gender specialists. Similar irrigation projects in the future may want to pick up missed opportunities and explore effective ways to maximize results by building on other gender and development initiatives within the same geographical area. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/chashma-right-bank-irrigation-project-stage-iii
North-West Frontier Province Barani Area Development Project | Pakistan | Agriculture, Natural Resources, and Rural Development, Energy, Finance, Transport | 2010-01-12 | 1. A poverty reduction, multisector area development project covering very large isolated areas cannot be efficiently implemented in Khyber Pakhtunkhwa without (i) the Planning and Development Department as the executing agency, which has the essential mandate and institutional capacity for multisector interventions; (ii) a decentralized project management model; (iii) components fully designed with dedicated staff resources, operational costs for implementing agencies, and market-based reasonable salaries and benefits; (iv) flexible, demand-driven design of interventions; (v) minimum beneficiary funding requirements; (vi) well-designed consulting packages with efficient costs; (vii) a duration of 10 years; and (viii) flexibility in loan extension, and responsiveness to security crises and natural disasters. A service delivery project with gender and development objectives cannot be implemented in Khyber Pakhtunkhwa without dedicated female technical staff and proper logistical support for them including office space, residential facilities, training facilities, and dedicated vehicles. project cycle stage: Lesson Topics: 2. Selection of nongovernment agencies (NGOs) at appraisal would have ensured timely implementation of the project. Given the community mobilization as a prerequisite for all interventions, and the problem of political interference in selection of NGOs through competitive bidding, single-source selection at appraisal should be preferred. project cycle stage: Lesson Topics: 3. Feeder roads, large drinking water supply, and surface water diversion schemes cannot be classified under the umbrella of participatory small-scale infrastructure, as these schemes require specialized technical skills and high operation and maintenance costs. In the future, these should be classified as government-managed medium-scale infrastructure subprojects. project cycle stage: Lesson Topics: 4. To simplify the administration and financing of various subprojects, component-based financing is suggested for area-based rural development projects in which subcomponents will be financed by one financier only, together with government counterpart funding, instead of jointly by all financing sources. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-west-frontier-province-barani-area-development-project
Decentralized Elementary Education Project (Sindh) | Pakistan | Education | 2009-12-29 | 1. To ensure the formulation of a well grounded Project Design, a more thorough preparatory analysis could have been undertaken taking into account local realities such as implementation capacities, relationship between provincial and local governments, willingness to pay and other factors. The project's scope has been noted to be overambitious given the weak capacities of executing and implementing agencies as well as school management committees and communities. [Main text, paras. 6,33,49(i,iv)] project cycle stage: Design Lesson Topics: Project Design: Project design Capacity Development: Capacity assessment 2. ADB should have provided relevant, timely, and high-quality training to the concerned professional staff of executing and implementing agencies to facilitate effective project implementation. ADB could have been quick to assess and constructively engage in addressing procedural and implementation issues which have reduced efficiency and effectiveness of investment as most of the expected outputs and outcomes were not realized. [Main text, paras. 37,40-42,45,49(ii)] project cycle stage: Implementation Lesson Topics: Project Management: Project management Capacity Development: Capacity assessment 3. Periodic performance indicators, evaluation, and regular monitoring should have been made an integral part of the project to enable regular assessment of implementation progress. No effective monitoring and evaluation system was provided in the Project Design, which could have triggered early warning on implementation problems and bottlenecks. The lack of a midterm review was also a missed opportunity to revisit and adjust the project design. Likewise, review missions were too few to address implementation issues. [Main text, paras. 6,30,49(iii)] project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Design: Project design Project Management: Project reporting | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/decentralized-elementary-education-project-sindh
Impact Evaluation Study of Rural Water Supply and Sanitation in Punjab, Pakistan | Pakistan | Water and Other Urban Infrastructure and Services | 2009-08-31 | 1. Rural water supply and sanitation projects deliver significant gender benefits in terms of (i) reduced drudgery for women and girls engaged in fetching water, and (ii) increased girls' attendance particularly at the high school level. project cycle stage: Design, Completion, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Gender Sector Related Issues: Water resource management 2. Current rural water supply and sanitation (WSS) project designs largely focus more on improving water access to the households, and less on ensuing wastewater and solid waste management issues. Hence, the project designs need to (i) be based on lessons from past operations of ADB and other development partners and conceptual framework demonstrating clear linkages between planned development interventions and expected outcomes and impacts; (ii) include only directly relevant components and each component must be adequately resourced and implemented by the most appropriate agency; (iii) develop synergy between water supply and sanitation with strong commitment and focus supported by sizable investment in sanitation; (iv) make provision for a functional monitoring and evaluation arrangements with baseline data for the project and comparison (control) areas; (v) recognize the medium to long-term role of non-government organizations and private sector in supporting community-based organizations; (vi) make provision for additional mechanism for WSS to poorest of the poor and other disadvantaged groups because an upfront cash requirement for household connection limits their participation in conventional WSS projects and (vii) strengthen voices of females in the design and implementation arrangements. [Executive Summary; Main text, paras.83-89] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 3. ADB need to proactively partner with other development partners in water supply and sanitation (WSS) specifically in (i) creating demand for sanitation investment; (ii) improving delivery of safe water; (iii) strengthening institutional capacity of CBOs, NGOs and private sector; (iii) strengthening institutional incentive structure for effective management and WSS services; and (iv) water demand analysis, water resource mapping and water use regulations. The WSS projects in Pakistan had limited coordination or complementarities with other development partners (including local nongovernment organizations and government agencies) thereby negatively influencing project relevance and sustainability. Proactively working with other development partners ensure that expected outcomes and impacts from development interventions are realized with efficient utilization of resources and without duplication of efforts. While it is recognized that inter-agency coordination and partnerships are difficult to implement for various reasons, such partnerships tend to be successful when the collaboration starts at an early stage. [Executive Summary; Main text, paras. 90-95] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Partnerships Sector Related Issues: Water resource management 4. Collecting valid baseline data on individuals, households, and communities along with valid counterfactuals (comparison groups) is critical for assessing results and conducting rigorous impact evaluations which can assist in quantifying the impact of development interventions on household welfare. For many projects, however, data either do not exist or are inadequate to meet even basic requirements for meaningful project evaluation (e.g., in the absence of data, financial sustainability of projects could not be evaluated). [Executive Summary; Main text, paras. 80,96,97] project cycle stage: Design, Completion Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Impact evaluation 5. To maximize sustainability of project benefits, there is a need to (i) provide support to bridge finance operation and maintenance in the initial years of operations (even after project completion); and (ii) strengthen capacity of community-based organizations (CBOs) to address technical, managerial and financial management issues, among others. Evaluation noted that weak institutional and financial capacity of CBOs for operation and maintenance of WSS infrastructures places project sustainability at risk. [Executive Summary; Main text, paras. 79,80,98-100] project cycle stage: Implementation, Completion Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Post-evaluation Project Management: Operation and maintenance Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Public-private partnership | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-study-rural-water-supply-and-sanitation-punjab-pakistan
Punjab Community Water Supply and Sanitation Sector Project | Pakistan | Agriculture, Natural Resources, and Rural Development | 2008-01-06 | 1. Active involvement by beneficiaries in the project process through effective social mobilization is key to the success of rural water supply and sanitation projects. project cycle stage: Implementation Lesson Topics: 2. Training, awareness raising, and capacity-building of beneficiaries is also instrumental in ensuring the sustainability of subprojects that are owned and operated by the communities. project cycle stage: Implementation, Operation Lesson Topics: Capacity Development: Capacity building Policy & Reform: Information dissemination/Public awareness | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/punjab-community-water-supply-and-sanitation-sector-project
Second Science Education Sector Project | Pakistan |  | 2007-11-12 | A more realistic assessment of constraints could have tempered the stipulations relating to the frequency of meetings of high-level committees with a wide spectrum of participants. project cycle stage: Lesson Topics: Covenants with political and/or budgetary implications are not likely to be complied with. project cycle stage: Lesson Topics: Discrepancies between appraisal and Planning Commission Proforma I (PC-I) targets affected the scale of project achievements. Implementation tended to follow PC-I targets, revisions to which entail a lengthy process that is best preempted. project cycle stage: Lesson Topics: Greater attention needs to be paid during implementation to establishing effective BME systems capable of readily providing information on project outcomes and achievements. project cycle stage: Lesson Topics: More attention to the implementation of training activities could have led to more effective training, with courses being of sufficient duration to maximize their potential benefits. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-science-education-sector-project
Energy Sector Restructuring Program | Pakistan |  | 2007-08-13 | 1. The program could have included a mechanism of formal review after about 18 months to consider revising the content and timing of loan covenants. The objective would be to make the covenants more relevant to prevailing conditions, strengthen or bring forward some conditions, and waive or defer others. project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation 2. The program derived its strengths from the following: (i) the Ministry of Finance was well placed to see the link between Pakistan's macroeconomic crisis and the need for reforms in the energy sector; (ii) a well-thought out structure for monitoring and implementing the program was established; (iii) close coordination of the ADB loans with those of the International Monetary Fund and the World Bank. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management 3. Where possible, ADB should link its loan conditions to program aspects where it has strongly positioned itself in the policy dialogue and relationship leadership. project cycle stage: Design Lesson Topics: Project Design: Project design Methodologies/Approaches: Policy dialogue 4. Difficult lending conditions like the requirement to privatize the Karachi Electric Supply Corporation are achievable, but both ADB and the executing agency must persevere over a long period, extensive support must be provided through technical assistance and policy dialogue, and a long-term perspective must be taken. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Policy & Reform: Privatization Methodologies/Approaches: Policy dialogue | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/energy-sector-restructuring-program
Country Assistance Program Evaluation for Pakistan (2007) | Pakistan |  | 2007-05-31 | 1. The high degree of centralization of ADB's business processes (e.g., important decisions on procurement and consultant selection; loan and TA administration) undermines its operations in support of decentralization, results-based management, and its managing for development results agenda. Responsibilities, authority and resources should be devolved to resident missions to the maximum extent possible. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Finance & Financial Aspects: Financing Project Management: Procurement Project Management: Project administration Capacity Development: Human resources management Country Context: Decentralization Other: Resident Mission The number of loans and their spread across sectors or subsectors need to be aligned better with available staff and TA resources. Decisions on which sectors or subsectors to include in a more focused portfolio depend on factors such as (i) client demand and preferences; (ii) staff and TA resource availability; (iii) analytical work that identifies binding constraints; (iv) ADB's strategic priorities; (v) the programs of other development partners; and (vi) experience showing what has worked and what has not. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Lending modality Modality: Policy-based lending Modality: Program Modality: Technical Assistance Project Management: Project management Capacity Development: Human resources management Capacity Development: Ownership The project design process should result in sufficient ownership by the government for the project to be incorporated in the government's planning, approval, and budget cycle. Government capacity to lead in project design needs to be created. This would require that a portion of funds currently allocated for project preparatory TA should be made available to the government for the recruitment of consultants to assist with design and feasibility studies, and for executing agency capacity development. The balance of the project preparatory TA funds would be used to fund those parts of project design required by ADB to meet its policies. Building country capacity should also be part of ADB's strategy. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Ownership | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-pakistan-2007
Pehur High-Level Canal Project | Pakistan | Agriculture, Natural Resources, and Rural Development | 2005-11-15 | Contract packaging caused delays and legal issues. To avoid this in the future, overlapping contracts should be packaged together and the legal aspects of delays caused by interdependency should be covered under the contract clauses. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Project Management: Procurement Most water users associations (WUAs) developed under the project became dormant after project completion. To sustain operations of community organizations (WUA and women's organizations), project designs should include entry and exit strategies, which can adequately address WUA objectives. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity development Sector Related Issues: Irrigation management The executing agency did not have adequate O&M resources to operate and maintain the handed over system. Covenants did not fully cover the availability of irrigation service fee (ISF) to the executing agency for O&M, although they provided for increases in ISF to meet O&M requirements. Implementation arrangements were imbalanced as the North-West Frontier Province (NWFP) Government (as the owner) did not have the capacity or technical knowledge to influence and guide Water and Power Development Authority (WAPDA). To ensure sustainability and ownership of water sector projects, new projects should include the necessary support for reforms, which ensure financial autonomy, transparent and efficient decision-making, and availability of resources for O&M of the system. In addition, future initiatives should support capacity building of water sector institutions to implement and monitor water sector projects. project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Ownership Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Policy & Reform: Reform The monitoring system established in the executing agency was not responsible for operating the project and was discontinued after the project. In future, the priority should be to strengthen the existing monitoring systems of executing agencies responsible for operating the project, build their capacity, and ensure sustained monitoring. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity building Country Context: Prioritization To maintain the executing agency's (Irrigation and Drainage Department's) ownership of the project, consultants should be recruited by the lead executing agency who would ultimately operate the system to improve its capacity to supervise implementation by the subcontracting agency (in this case Water and Power Development Authority). Delays in contract awards and implementation could also be reduced if training on contract management and ADB procedures are organized at the outset for executing agencies. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Procurement Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Ownership Sector Related Issues: Irrigation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/pehur-high-level-canal-project
Second Girls Primary School Sector Project | Pakistan | Education | 2005-11-15 | Having a strong federal coordinating unit (FCU) would have facilitated the proper management of consultants and improved the outputs of the international and domestic consultants. The FCU should properly supervise and coordinate project activities, particularly at the provincial level. Without a strong and responsible FCU, project coordination suffers. project cycle stage: Feasibility Lesson Topics: Project Management: Consultants Project Management: Project management Project Management: Project supervision Capacity Development: Capacity assessment Methodologies/Approaches: Consultation/Participation School management committees (SMCs) should be trained to take a leading role in formulating a vision for their individual community model schools (CMSs), as each has its own dynamics. The stakeholders would thus work together for CMS improvement and maintenance with a sense of shared purpose, in the process strengtheningthe SMC-CMS relationship. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity building Sector Related Issues: Education The improvements in access to primary education should be supported by continuing efforts to enhance the quality of education, such as (i) improving teaching and learning methods, (ii) continuously developing textbooks that arouse students' interest in reading and doing research on their own, and (iii) strengthening institutional and management capacity, to increase ownership and relevance. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Ownership Sector Related Issues: Education The project was delayed by nearly 3 years mainly because of inadequate project implementation unit (PIU) staffing and frequent changes in project directors. The establishment of a core project management unit at the fact-finding stage, as agreed with the government during the Resident Mission's 2003 Country Portfolio Review Mission (CPRM) in 2003, should be enforced, and the Resident Mission should consistently follow up on the implementation of the CPRM agreements, such as the retention of project directors for at least 3-4 years, and the government referring any needed changes first to ADB before the changes are made. These actions would promote a sense of ownership on the part of the government and minimize implementation delays. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Project management Capacity Development: Ownership Other: Resident Mission The recruitment of project staff is a generic problem. Recruitment was delayed mainly because of the ban on recruitment and the requirement to secure additional clearance from the finance department, even for approved posts. ADB should have raised this issue during Country Portfolio Review Missions (CPRMs), and fact-finding mission leaders should have followed up the possibility of an exemption from the ban and from additional approval from the finance department for project staff. project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Project Design: Appraisal Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-girls-primary-school-sector-project
Capital Market Development Program in Pakistan (Loans 1576-PAK and 1577-PAK[SF]) | Pakistan | Finance | 2005-10-31 | The following performance indicators for the Capital Market Development Project were identified: (i) the number and size of equity initial public offerings, (ii) daily trading volume, (iii) market capitalization, (iv) compliance with G30 recommendations, (v) total investments in leasing assets, (vi) total assets of mutual funds, and (vii) the number of insurance policyholders and the premiums collected by insurance companies. These indicators alone are inadequate for an analysis of the extent to which the development of the capital market can be attributed to the project. A benchmark interest rate and data showing the investors demand for equity instruments, for instance, should have been included. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financial reporting Project Design: Subprojects Project Management: Project management Project Management: Project supervision The success of the capital market development program is due to ownership and leadership in reforms, supported by a favorable political economy and effective policy dialogue. The key ingredients of the effective dialogue were the following: (i) ADB processing missions gained enough knowledge about the country from the economic and sector work mission that preceded the reconnaissance mission; (ii) the reconnaissance mission had extensive policy dialogue with the agencies concerned, and broad consultations with stakeholders; (iii) the policy matrix was drafted at an early stage of processing, and the government took substantial actions before loan approval; (iv) ADB processing and review missions made an effort to come up with alternative policy measures, which led to realistic solutions while also enhancing ownership of reforms; (v) one ADB processing mission member remained responsible for program implementation almost until the end, contributing to a close and constructive partnership; and (vi) ADB continued to monitor unattained non-tranche program measures by extending the loan closing date. All these are considered good practices for ADB s policy-based lending. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Reporting Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Management information system | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/capital-market-development-program-pakistan-loans-1576-pak-and-1577-paksf
Ghazi Barotha Hydropower Project | Pakistan | Energy | 2005-08-15 | ADB should have been more actively involved with the environmental and resettlement aspects of the project even if the World Bank was responsible for these, as was noted in discussions with a World Bank mission. ADB had a total of seven different project officers throughout the project's duration, and this was detrimental to overall project coordination. Furthermore, coordination among financers could have been more efficient, if a mechanism was established for regular meetings among financers. Coordination among financers was done informally. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Project Management: Project supervision The availability of counterpart funds needs to be guaranteed more fully to avoid implementation delays, and ADB assistance to the power sector in the country should take this into account. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Sector Related Issues: Energy planning/management The environmental aspects are mainly positive, in that they obviate the need for a comparably sized (thermal) generation plant and thereby reduce the damaging atmospheric impacts of such plants. However, as demonstrated in the project, reducing the potential social impacts to manageable levels is also possible, through rigorous evaluation of alternatives and public consultation and awareness building. In this context, the selection of the final power channel alignment (and the conscious decision to avoid existing villages and settlements, even at somewhat higher costs) and locations of the barrage and powerhouse deserve to be highlighted. These decisions substantially reduced the scale of the resettlement and relocation under the project without adversely affecting its economic and financial viability. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Project evaluation Project Design: Project design Sector Related Issues: Energy planning/management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/ghazi-barotha-hydropower-project
Financial Sector Intermediation Loan in Pakistan (Loan 1371-PAK) | Pakistan | Finance | 2005-07-31 | Even after loan completion, ADB should monitor major events (irregularities) of the concerned financial institutions to the extent possible. Such monitoring will deserve extra resource allocation in some cases, depending on the type of issues that subsequently surface and the extent of ADB s direct or indirect loan exposure to the institutions project cycle stage: Completion Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial reporting Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration Project Management: Project management Project Management: Project supervision Experience underscores the necessity of a clear project purpose. The project purpose should not be used only to design the project; it should constantly be referred to in monitoring project implementation. When a project encounters unforeseen events, the project purpose should be the basis for adjusting the project scope/design or, if necessary, canceling its implementation. This judgment can only be effective if the project purpose is clearly stated. project cycle stage: Feasibility, Implementation Lesson Topics: Gross criminal irregularities and misappropriations during the project implementation are experiences that underscore the need for ADB to thoroughly reevaluate the continuing qualification criteria in case of a management or ownership change in participant institutions during project implementation. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial reporting Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration Project Management: Project management Project Management: Project supervision In case of parallel financing, regular contact with the counterpart aid agency throughout project implementation is essential. Withdrawal/cancellation of the counterpart agency should be a signal that a review and reassessment of the project are warranted. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration Methodologies/Approaches: Consultation/Participation In considering financial covenants for participant institutions under a loan, prudential regulations and other market rules, their enforcement status, and institutions' risk management and corporate governance should be thoroughly reviewed. Based on this review, financial covenants should be so determined that they complement the institutions' risk management and the country's prudential guidelines. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Corporate governance Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Risks/Risk management In the case where the counterpart aid agency had appraised the project, ADB should independently and diligently assess such appraisal. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Project management Parallel financing with another aid agency should be justified on the basis of project cost, credit demand, and complementary effects of the loans. project cycle stage: Appraisal Lesson Topics: Participating institutions have kept little information on development impacts of subprojects. Weakness in benefit monitoring and evaluation (BME) has been a common issue in ADB s development financial institution (DFI) loans. Experiences underscore the need for ADB to consider an alternative approach in creating a functional monitoring framework that balances increased administrative costs with the need for, and use of, the data collected. One possibility is to specify the required data and timing of data collection in a loan/project agreement. Another option is to select sample subprojects in case their number is large. Assigning a project administrator responsible for BME may not always be a viable option, depending on the fee that the agency charges. What is important is a pragmatic solution for the purpose of developing an effective and efficient monitoring and evaluation framework for a DFI loan. This framework could also be applied to small and medium enterprises (SME) credit, rural credit, and microcredit projects. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Management information system Project Management: Project administration Project Management: Project reporting The project actually encountered a series of negative unforeseen events, resulting in suspension of two participant institutions's repayment to the Government as well as insolvency of the guarantor of these repayments. The loan should have been restructured or cancelled when the project administrator (as well as guarantor) was brought under receivership and a replacement could not be assigned. Such a decision could be made in consideration of not only the project purpose but also the project cost and risks. A system was not effectively in place within ADB to appropriately reassess these important aspects and take responsive action to restructure/cancel underperforming loans. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Project Management: Project administration Project Management: Project supervision The risks associated with a project formulated on the basis of a weak logical framework are namely (i) inconsistency between the project rationale and objectives, (ii) excessively broad project objective (without specifying immediate objectives, or purpose), (iii) weak linkages among expected project outputs (or lack of cohesiveness in project scope), and (iv) lack of an explicit monitoring mechanism. project cycle stage: Feasibility Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/financial-sector-intermediation-loan-pakistan-loan-1371-pak
Pat Feeder Canal Rehabilitation and Improvement Project | Pakistan | Agriculture, Natural Resources, and Rural Development | 2004-12-15 | All formalities, including approval of the Planning Commission Form 1 (Project Pro forma) document, shouldbe completed before proposed projects are submitted for financing by multilateral and bilateral agencies. Specifically, attention should be focused on staffing the project management unit, appointment of project management consultants (and the possible role as project engineer), counterpart staff, and advance preparation of procurement packages. project cycle stage: Feasibility Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project management Capacity Development: Human resources management As part of project preparation, domestic conditions - resettlement, landacquisition prices, environmental concerns, and domestic cultural practices - should be carefully assessed. Mitigation measures should be incorporated in theProject Design, and brought into the physical implementation plan. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Resettlement Project Design: Project design Country Context: Cultural constraints For efficient and cost-effective implementation of projects, continuity of keypersonnel should be ensured. The transfer of staff during project implementationshould be minimal. project cycle stage: Implementation Lesson Topics: Project Management: Project management Capacity Development: Human resources management In multidisciplinary projects, adequate and strong coordination should be in placebetween the executing agency and the agency responsible for assuming theO&M responsibilities of the completed project facilities. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach Sufficient institutional development efforts are needed in association with thelarge physical investments. Farmers should be consulted intensively at theplanning and design stage, and the farmers should accept responsibilities forO&M of distributary, minor canals, and subsurface drainage facilities oncompletion. project cycle stage: Design, Feasibility Completion Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity development Sector Related Issues: Irrigation management Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/pat-feeder-canal-rehabilitation-and-improvement-project
Social Action Program (Sector) Project II | Pakistan | Multisector | 2004-12-15 | SAPPII demonstrated that complex projects need careful design, risk analysis, preparation and strong capacity of implementing agencies to adjust as necessary during implementation. The aid agencies, despite intensive coordination, failed to provide adequate technical inputs for institutional development and monitoring. ADB needs to carefully analyze management requirements that lead to good project performance. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Capacity development SAPPII provides an example of the difficulties associated with implementing complex multisector and multiprovince projects. Keeping in view the limited implementation capacity of governments , future programs and projects should be limited in terms of scope and implementing agencies, supported by adequate leadership and capacity building, and allowed adequate time for implementation and consolidation. project cycle stage: Design, Feasibility Lesson Topics: Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building The Social Action Program (Sector) Project II showed that the performance of Pakistan's public social sector strongly depends on political will, governance, and funding, which are all nontechnical issues. Uplifting the sector therefore requires financial restructuring and profound institutional reforms in governance and civil service, which are partly beyond the scope of the social sector. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Capacity Development: Ownership Sector Related Issues: Education Sector Related Issues: Health and sanitation management Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/social-action-program-sector-project-ii
Middle School Project | Pakistan | Education | 2004-11-15 | Implementation was undertaken in a disjointed manner with a focus on procurement and disbursement, and minimal focus on the project's objectives. Coordination mechanisms failed in their purpose. These were manifestations of weak ownership and commitment. Despite four extensions totaling 4 years and 3 months, project outcomes vis-ï¿½-vis the development objectives were not adequately realized. Given weak government commitment, a more stringent assessment should be made of extensions of the loan closing date. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Monitoring & Evaluation: Monitoring and evaluation Project Management: Procurement Project Management: Project administration Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Improved physical facilities are not a sufficient condition precedent to a better school andlearning environment. More critical is the presence of teaching staff and regular classes.Phasing of civil works should factor in the functional status of facilities under earlier phases. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Human resources management Sector Related Issues: Education Monitoring by the executing agencies (EAs) and Project Implementation Units (PIUs) was limited to an assessment of physical targets with negligible, if any, assessment of impact. The respective education management informationsystems were effectively non-existent in terms of generating data on project facilities. A greaterintegration of the two would have been more effective. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Project management Sector Related Issues: Education Project design suffered from three deficiencies: (i) no overall achievement goals wereset for national and provincial school participation and attainment indicators (particularlyimportant to understand the impact of non-quantifiable quality improvement components); (ii) noanalysis of value addition was considered, whereas the appropriate indicator of achievement isthe incremental growth in enrollment attributable to the project; (iii) inadequate attention waspaid to governance issues in the functioning of public schooling systems in Pakistan; (iv) andissues related to monitoring and accountability deserved more weight. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Education Supervision by the executing agency (Ministry of Education) of the international consultants' work was inadequate. Moreeffective supervision would have maximized the benefits of the consulting input. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project supervision The appointment of full-time executing agency (Ministry of Education) officials as project director and project manager wasineffectual as their responsibilities in MOE limited their ability to execute project responsibilities. The appointment of teaching staff to project schools does not assure an overall increasein access to education where staff are appointed on a deputation or transfer basis, as the gainof the project school is at the cost of a nonproject school. project cycle stage: Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Human resources management Sector Related Issues: Education The civil works' programs highlighted the need for prequalification of contractors; topsupervision; appropriate design features relevant to specific circumstances, such as for toilets inschools where water supply was inadequate or nonexistent; adequate funds for maintenance;and the presence of a caretaker to prevent vandalism. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project supervision Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/middle-school-project
Technical Education Project | Pakistan | Education | 2004-11-15 | Changing job markets and new technologies in technical education and vocational training (TEVT) require regular in-service training of teachers to upgrade their skills, as well as periodic curricula updating. The continuedinvolvement of the private sector and strengthening the Institute Management Committees (IMCs) would be important to enhance ownership and relevance at all stages. project cycle stage: Lesson Topics: Finance & Financial Aspects: Market analysis Capacity Development: Capacity building Capacity Development: Ownership Capacity Development: Technology/Technology transfer Sector Related Issues: Education Sector Related Issues: Private sector The project was delayed for 2 years mainly due to inadequate staffing of the Project Implementation Units (PIUs) andfrequent changes of project directors. Recruitment of project staff is a generic problem. Delays were mainly due to ban onrecruitment, even when the project posts were approved. Additional clearance from the FinanceDepartment was needed. For effective utilization of project facilities by timely recruitmentof staff, the government must allow exemption to project staff from the recruitment ban and waiveadditional clearances required from the Finance Department. During Pakistan Resident Mission's (PRM's) 2003 Country Portfolio Review Mission (CPRM), the government agreed to establish a core project management unit at the fact-findingstage. This agreement should be enforced to provide a sense of ownership and minimizeproject implementation delays. The frequent transfer of project directors is another generic problem. PRM should followup consistently with the government on the CPRM agreements to retain project directors at least 3-4 years. ADB should be consulted before any changes are made. project cycle stage: Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project management Capacity Development: Human resources management Capacity Development: Ownership Other: Resident Mission Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/technical-education-project-0
Urban Water Supply and Sanitation Project | Pakistan | Water and Other Urban Infrastructure and Services | 2004-11-15 | In this project, the implementing agency (Rawalpindi Water and Sanitation Agency or RWASA) was not autonomous in setting water tariffs to meet its financial needs or in engaging staff as necessary to operate and maintain the water supply and sanitation system to acceptable standards. Its dependence on budgetary support from the government will remain unless it is delegated the authority for setting water tariffs and recruiting staff. Any future assistance to RWASA should be subject to these conditions. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Human resources management Country Context: Decentralization Sector Related Issues: Health and sanitation management The management of a project management unit (PMU) should be appropriately qualified. Project design should ensure the appointment of appropriately qualified staff for key positions in a PMU. Appointing regular executing agency staff in a PMU instead of contract staff will likely enhance institutional strengthening. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/urban-water-supply-and-sanitation-project-1
Trade | Pakistan |  | 2004-10-15 | Although the overall implementation arrangement was satisfactory, some simplification at the design stage could have simplified coordination, which was demanding on the agencies concerned, particularly on the Ministry of Commerce (MOC). Program implementation was more complex than originally envisaged. TA Loan 1682 added still more challenges by involving four different ministries/departments. The problem was finally overcome after delays and protracted coordination efforts. Events not foreseen at program appraisal are inevitable, but more effort in the initial stage of a program's formulation may help clarify responsibilities of various agencies. That may help in the incorporation of measures for timely resolution of problems, leading to more efficient and timely program implementation. project cycle stage: Design, Feasibility Lesson Topics: Modality: Program Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Methodologies/Approaches: Consultation/Participation Difficulties during program implementation illustrate the deeply entrenched problem of poor capacity in almost all of Pakistan's ministries and departments. This situation was worsened by frequent change and transfer of key counterparts, a common problem in Pakistan. It is difficult to generalize, but changes of key counterparts at times seem to have resulted in both loss of institutional memory and discontinuity of agreed approaches and methodologies for program implementation. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Human resources management Program design was comprehensive, at the same time complex. The initiatives that the program supported were complemented through concerted efforts by IMF and the World Bank. The program managed to tackle key trade policies, and legal and institutional reforms in Pakistan. Its leverage on certain components, for instance on public manufacturing enterprise (PME) privatization was not adequate. This was complicated by the problems in the privatization process, and the fact that no direct assistance under the program was rendered to conduct analytical work review and monitor the process. This also applied to some of the non-tranche release conditions including, but not limited to, review of some trade laws and procedures which added considerable complexity to the program. Although compliance with these laws and procedures may have been comparatively easy, their real impacts are uncertain and difficult to assess. In hindsight, some simplification of the program components, which although making the program a bit less ambitious, could at the same time have led to more focused program results. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Disbursement Loan Agreement: Covenants Modality: Program Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Industry and Trade Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/trade
KESC Sixth Power (Sector Loan) Project | Pakistan | Energy | 2004-07-15 | Although the project's transmission component was implemented successfully, therewere considerable delays. ADB should be more circumspect in appraising the likelihood ofmeeting the project's schedule, and the risks and obstacles, ensuring that the government and the executing agencyhave committed adequate local counterpart funds, and that right-of-way (ROW) problems are minimizedduring project design and planning, particularly in a densely populated commercial area likeKarachi. project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Counterpart funds Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Sector Related Issues: Energy planning/management Costs were significant for the delay in implementation and the reduction in project scope. Worsened system losses and impaired financial position adversely affected the executing agency's (Karachi Electric Supply Corporation's) ability to comply with ADB covenants and to effectively implement the project. The implications of reducing the scope of a project should be assessed carefully in terms of operational and financial impacts on the sector where appraisal target achievements depend on the availability of local funding. To restore financial viability and operational efficiency, KESC and the government should also rigorously enforce the management schedules of ongoing investment projects. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financial analysis Loan Agreement: Covenants Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Energy planning/management Methodologies/Approaches: Targeting Many uncertainties are involved in project design and implementation in sectors that areundergoing major restructuring, such as the Karachi Electric Supply Corporation's (KESC's) case. These may include policy and institutional uncertainties that cannot be foreseen fully at appraisal. To cope with suchuncertainties and unexpected developments, close consultation among ADB, the government,and the executing agencies should be held during project implementation at the sector level, rather than theproject level. project cycle stage: Implementation Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Energy planning/management Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/kesc-sixth-power-sector-loan-project
Population Project (Loan 1277-PAK[SF]) | Pakistan | Health | 2003-12-31 | For smooth and timely project implementation, training in ADB procedures and systems is crucial and should have been provided to all project implementation units managers at an early stage. Clear information on project objectives, targets, and administrative procedures should been provided to all staff responsible for monitoring and implementing the project at the provincial and district levels. The project design should have been more program-oriented, thus making it easier to identify and monitor ADB's contribution. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Capacity Development: Capacity building Policy & Reform: Information dissemination/Public awareness No financial or economic analyses were undertaken at project appraisal or completion, and no baseline data was prepared to support comparative impact analysis. To enable high quality economic analysis, projects should incorporate baseline data, indicators, and supportive mechanisms during design. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Project Design: Appraisal The project has helped the government achieve the goals for the information, education, and communication (IEC) component through innovative initiatives such as customized promotional campaigns, participatory approaches, and local languages. This was critical in encouraging people to plan for smaller families. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Participatory approach The technical assistance (TA) did not achieve its objectives because of (i) overly ambitious design, which covered factors such as operations, management, and research within a relatively short time period; (ii) vague terms of reference (TORs); (iii) the wrong experts for implementation; and (iv) inadequate review and guidance. To support institutional development, the TA should have focused on institutional capacity-building with specific TORs and rigorous review. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Project supervision Capacity Development: Capacity building | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/population-project-loan-1277-paksf
Kotri Barrage Rehabilitation Project | Pakistan | Agriculture, Natural Resources, and Rural Development | 2003-12-15 | By building upon previous investments in irrigation, the project demonstrated that rehabilitation could produce solid economic returns with limited social and environmental problems. However, to ensure that the gains are sustainable, building O&M capacity throughout the system should be given a high priority. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Capacity Development: Capacity building Country Context: Prioritization Sector Related Issues: Irrigation management Several factors strengthened implementation: first, the designation of the supervisory consultant as project engineer provided technical and administrative advantages that expedited progress. Second, without the Department of International Development's (DFID's) grant to cofinance the project, this designation of the supervisory consultant would have been unlikely. Grant financing also made possible the extensive consulting services (14% of project costs). When consultants are financed from loan proceeds, the government is more likely to reduce their input. Third, the continuity in ADB project officers contributed to the success. Fourth, the project benefited from the government's decentralized implementation and provincial ownership. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Consultants Project Management: Project management Project Management: Project supervision Capacity Development: Human resources management Capacity Development: Ownership Country Context: Decentralization Several of the project's successes can be attributed to simplicity. The projectbenefited from a straightforward design: one implementing agency and a focused set ofobjectives and activities. In addition, the loan covenants were limited in number andreasonable. project cycle stage: Feasibility, Appraisal Lesson Topics: Loan Agreement: Covenants Project Design: Project design Project Management: Executing/Implementing agencies Significant institutional reforms were introduced in irrigation management, butgovernment commitment and funding have been lacking. Without significantimprovements to O&M, projects are likely to repeat cycles of deferred maintenance andrehabilitation. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Operation and maintenance Capacity Development: Ownership Sector Related Issues: Irrigation management Policy & Reform: Policy reforms/framework The project benefit monitoring and evaluation (BME), a frequent area of concern in projects, was partiallysatisfactory. The shortcomings were not necessarily in the execution of the BME surveys by local consultants. The deficiencies were partly due to (i) inadequate ADB communication of its information and evaluation needs, and (ii) a lack of guidance to the local consultants in conducting the surveys. To this end, more ADB involvement in thesesurveys is advisable if they are to provide useful input into ADB evaluations. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Management: Consultants Project Management: Project supervision Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/kotri-barrage-rehabilitation-project
Second Urban Development Project | Pakistan | Transport, Water and Other Urban Infrastructure and Services, Multisector | 2003-12-15 | Attached technical assistance (related to financial management and accounting)provided useful recommendations to improve executing agency financialperformance. However, after completion of the technical assistance, nomeaningful follow-up actions were undertaken by the North-West Frontier Province (NWFP) government. Underthe loan, project management consulting services were provided but did notinclude urban financial management experts. Despite ADB's strong suggestionsto recruit such experts during project reviews, the NWFP government did nottake any action. Terms of reference for technical assistance and loan consultants should have been closely coordinated in achieving the financial improvement ofexecuting agencies. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial management Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Project supervision Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation Delays in land acquisition caused many project implementation problems. Underan integrated urban development approach, the land market became highlyspeculative once project implementation started. Identification of constructionsites and land acquisition should have commenced much earlier. project cycle stage: Concept Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Sector Related Issues: Urban sector/development Methodologies/Approaches: Holistic approach Provincial Urban Development Board (PUDB) was selected as a lead executing agency for the project. However, PUDBhad no specific financial management links with Peshawar Municipal Corporation (PMC) and municipal corporations (MCs), as PUDBï¿½s main task was the physical development of urban areas in the province. This implementation arrangement resulted in only partial achievement of the institutional strengthening of local authorities. More active involvement of theDepartment of Local Government, Elections and Rural Development in project implementation should have been promoted. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation The early involvement of beneficiaries and/or communities was essential to thesuccessful implementation of the project. In particular, willingness to pay forsewerage connections and acceptance of solid waste dumping sites bycommunities should have been examined more carefully. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Ownership Sector Related Issues: Health and sanitation management Methodologies/Approaches: Community approach The project was the first ADB intervention in the urban sector in North-West Frontier Province (NWFP), and ittook almost 10 years to complete. Considering the financial and technical capabilities of executing agencies, the scale and design of the project was over ambitious. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Sector Related Issues: Urban sector/development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-urban-development-project
Punjab Rural Water Supply and Sanitation (Sector) Project | Pakistan | Water and Other Urban Infrastructure and Services | 2003-11-14 | Capacity building at community-based organizations (CBOs) through effective training programs should be undertakenearly in implementation. Responsibility for executing schemes should be entrusted to CBOs,with government line departments providing only financial and technical support. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Methodologies/Approaches: Civil Society Participation Careful evaluation is required before imposing per-capita limits on subproject costs,because they may restrict the potential for fulfilling the entire water, sanitation, and drainageneeds of communities. After setting the limits, a flexible approach is generally needed. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Project evaluation Project Design: Subprojects Sector Related Issues: Health and sanitation management Methodologies/Approaches: Process approach Design of water supply schemes should be based on the minimum pressurerequirements at terminal points. Unless this pressure is maintained, the design remainsinadequate. The executing agencies (EAs) and consultants should thoroughly review scheme designs. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Project evaluation Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management Startup delays should be avoided by taking advance action, including securinggovernment approvals; establishing a Project Management Unit (PMU); appointing the project director, PMU staff, and Community Development Unit (CDU) staff; recruiting consultants; and qualifying contractors/suppliers in advance. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project management Capacity Development: Human resources management The executing agencies (EAs) should have the capacity to review consultant outputs such as reports andworking papers, to ensure relevance and quality. The EAs should own and effectively use the Management Information System (MIS), the accounting system, and the monitoring and evaluation system. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building The sustainability of community-managed projects relies on developing community-based organizations' (CBOs') capacityto bear responsibility for their own decisions. Involving the community - the most importantproject stakeholder - from project identification to completion and O&M ensures ownership if theproject is needs-based. Social mobilization should not be restricted to a few communitymembers but should include all or most of them. Social mobilization should ensure equitabledistribution of benefits. Women's participation should be emphasized in water supply andsanitation projects to achieve lasting results since they are responsible for water collection.Nongovernment organizations (NGOs) should be involved for making social mobilization effective. Sustainability also depends on the sense of ownership. Community share in the schemecost would contribute. project cycle stage: Concept Design, Feasibility, Implementation, Completion Operation Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity development Capacity Development: Ownership Sector Related Issues: Health and sanitation management Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/punjab-rural-water-supply-and-sanitation-sector-project
Rural Access Project | Pakistan | Transport | 2003-10-15 | Compliance with the maintenance covenants relating to previous projects was difficult toverify. Provincial governments claimed that their expenditures were appropriate. Maintenanceissues with the project roads should not arise for several years. It is difficult to ensure thatadequate attention is given to ongoing maintenance through loan covenants; financial problemsfaced by some provincial governments will always be an overriding consideration. Two basicapproaches could be adopted: engineering or institutional. The engineering solution would be tobuild stronger, lower-maintenance roads. The institutional solution would be to build a self-fundingmechanism into the road sector, in the form of tolls or a dedicated road fund, or both. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity development Capacity Development: Technology/Technology transfer Sector Related Issues: Roading Delays in fund disbursement caused by unnecessary government bureaucracycontributed to construction delays because the funding delays caused cash flow problemsamong small contracting companies. Future projects should address this issue byunderstanding the real difficulties within the government offices, and initiating capacity buildingto address these problems. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Project design Project Management: Procurement Capacity Development: Capacity building Inadequate prequalification of contractors led to underbidding by some inexperiencedcontractors and to the award of tenders to contractors who lacked the technical or financialresources necessary for contracts of this size and nature. Contracts held by poor ornonperforming contractors were difficult to reassign, which caused delays and additional costs.Prequalification of civil works contractors should be based on stringent and carefully designedevaluation criteria, and should be subject to an effective due-diligence review by an independentcommittee. project cycle stage: Implementation Lesson Topics: The provincial agencies were generally happy with the support they received from thegeneral consultant (PMU), and felt that the general consultant played a major role in maintaining high qualitystandards. The opportunity for project managers to meet and discuss common problems wasappreciated. Providing opportunities for ongoing information interchange among provinceswould be beneficial. project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Consultants Project Management: Project management Capacity Development: Capacity building Policy & Reform: Information dissemination/Public awareness There was also confusion over the role of the consultant as the ï¿½engineer'srepresentative,ï¿½ and the role of the ï¿½engineerï¿½ under International Federation of Consulting Engineers (FIDIC) contract conditions. The ï¿½engineerï¿½for this project was an executive engineer of the respective province. The general view was thatthe supervising consultant should be appointed as the ï¿½engineerï¿½ under FIDIC. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Consultants This was the third in a series of ADB farm-to-market road projects (the first two were loans 758-PAK and 917-PAK. In each case, project mobilization tooklonger than anticipated. In each case, the problem was noted in the risks and remedial actions identified for subsequent projects. Actions that might reduce the delays observed include advance action on selection of the supervising consultants, but a more practical suggestion is to allow a more realistic time period for selection of consultants and contractors. Project construction periods should also be made realistic, taking into account difficult site conditions, especially in Balochistan and North West Frontier Province (NWFP). Additional time spent on planning and preparation at an early stage will reduce delays later.In particular, land acquisition and clearance must be completed before contractors are mobilized. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Project Management: Consultants Project Management: Procurement Project Management: Risks/Risk management Sector Related Issues: Roading Underestimation of the costs at the project preparation stage led to delays, because the Planning Commission Proforma 1 (PC-1)had to be revised. Pressure on contractors to reduce their rates had consequencesthroughout the project because the contractors could not absorb cash flow problems caused bydelays in payment. Civil works packages should be costed at realistic market prices, not basedon outdated rate schedules. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Management: Procurement Using Ministry of Local Government and Rural Development (MLGRD) as a central coordinating agency gave no clear benefit. Having multiple executing agencies increased the administrative burden, created confusion aboutresponsibilities, and contributed to delays. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-access-project
Swabi Salinity Control and Reclamation Project | Pakistan |  | 2003-10-15 | Based on project experience and to ensure sustained O&M ofcompleted infrastructure, O&M responsibilities during and after the completion of works(mechanisms for the handover) should be clearly laid out in project designs. The involvementand on-the-job and specialized training in O&M of the ultimate operators of a project should be built into the design and approach of a project. The training should beaccording to Project Design, and as a separate component that may continue for some time aftercivil works completion, to ensure optimal operation of a project and its' designed capacities. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Conflicts were encountered in developing parallel watercourses and outlets, due to alack of timely community involvement. The experience shows that beneficiary awarenesscampaigns and consultations with farmers concerning project designs and their impacts shouldbe launched during the design stage, to create goodwill and ownership of interventions amonglocal irrigators and avoid conflict during implementation. project cycle stage: Design Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Irrigation management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Delays in contract awards and implementation can be avoided, if training programsfocusing on ADB tendering and other procedures and bid responsiveness are organized at theoutset for executing agencies and prequalified contractors, respectively. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building The cooperative management approach practiced under the agriculture development component (ADC) was a viable model of management in a complex multistakeholder environment and could also be considered for loan projects. The model demonstrated mechanisms that were effective in collective decision making, planning, and monitoring at the operations and management levels, under a decentralized system. The analysis of this experience also showed that it is important that themonitoring and reporting mechanisms developed under such a complex model are robust [e.g., Department of Agriculture (DOA) and nongovernment organization (NGO) disputes over the use of funds were addressed at a late stage] and can ensure transparency and a workable relationship between stakeholders. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Design: Project design Country Context: Decentralization Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach Time, effort, and resources were spent on training under the agriculture development component (ADC). However, there wereno tangible indicators to monitor these outputs. The supply or demand orientation of training was also not clear. The analysis of this experience shows that for training to be effective it hasto have an optimal mix of formal and on-the-job training, with no overlap in the trainingmandates of training agencies and withwell-defined monitoring indicators related to project objectives. The supply side of trainingshould be assessed during the design stage of a project, where the demand side should bebased on a needs assessment and should be implemented on a cost-sharing basis, to ensurequality and actual need against demand. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Rural development Where sustained support of community organizations [in this case water users associations (WUAs), women'sorganizations, farmers organizations (FOs) and farmer support units (FSUs)] is needed, even after completion, for residents to optimallybenefit from a project, a separate set of clearly distinguished activities at the entry and exitlevels should be included in project designs. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Methodologies/Approaches: Civil Society Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/swabi-salinity-control-and-reclamation-project
Third Punjab On-Farm Water Management Project | Pakistan | Agriculture, Natural Resources, and Rural Development | 2003-06-13 | A project that monitors only physical and financial progress will prioritize those aspects, often excluding other equally important aspects such as social and human resource development, and institutional development. To give due emphasis to the noncivil work aspects of a project, it is essential to incorporate into its logical framework, then monitor, specific targetsthat reflect both the quantitative and qualitative achievements of its nonphysical aspects. Also, it is necessary, from a project's onset, to establish a permanent operational system to monitor and evaluate implementation performance and development impact at various stages. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity development Capacity Development: Human resources management Methodologies/Approaches: Targeting Delay in recruitment or underutilization of consultants will likely lead to weak projectmanagement and monitoring. The need for consultant inputs should be discussed thoroughlyduring project preparation. Long delays in consultant recruitment during project implementationshould not have been accepted. Proposals to reduce or modify the input of consultants duringimplementation should be carefully reviewed. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants Project Management: Project management Establishment alone of high-level Project Steering Committee (PSC) or Project Coordination Committee (PCC) to ensure intra- and interdepartmental coordination is not effective. Project designs should also clearly describeeach agency's responsibilities, and resources to implement them. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Project management Methodologies/Approaches: Consultation/Participation Routine water user association (WUA) registration and beneficiary contributions have been far insufficient to ensure ownership of this type of project, or its outputs. Genuine and voluntary participation of beneficiaries is necessary throughout the project cycle, from design, to implementation, to operation, and maintenance. This could be better achieved by establishing WUAs that build on existing groups that previously shared and managed their assets. Essential to this approach is: (i) an assessment of the beneficiaries' socioeconomics, including group dynamics of land tenure and water rights, and their effects on costs and benefits; (ii) the development and implementation, before any physical construction, of a program to promote social mobilization and full awareness of project benefits and requirements; (iii) the promotion of active beneficiary participation in decision making and monitoring; and (iv) regular monitoring and follow up of the beneficiaries after project completion. Devolvement of responsibilities, including participatory management of distributary canals, is also considered a requirement for increasing the beneficiaries' ownership of irrigation schemes. But experience in Pakistan's irrigation sector indicates low institutional acceptance of the transfer of responsibilities for irrigation management, and the need to rethink the issue. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financial analysis Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Operation and maintenance Capacity Development: Ownership Country Context: Decentralization Sector Related Issues: Irrigation management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation The availability, reliability, and efficiency of irrigation water use at the farm level can best be increased through a combination of watercourse improvement and adoption of improved farm practices. The strategy should be presented to the farmers as a comprehensive package that recognizes the necessity of each component, as well as the multiplying effect of their association, to maximize efficiency of the intervention and ensure sustainability of benefits. Thepackage must be flexible, and should include appropriate messages for different types of farmers (for example, both small and large landholders, and resource-rich as well as resource-poor farmers) who share the same watercourse command area. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity development Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Holistic approach Methodologies/Approaches: Process approach The beneficial impacts of on-farm water management (OFWM) projects can be substantial. But benefits can besustained only if resources are adequate to operate and maintain minor and distributary canals,as well as main drains, after project completion. This emphasizes the need to comprehensivelyinstitutionalize the role of each group of stakeholders during Project Design, and that agenciesthat will be responsible for post-project operation and maintenance demonstrate a high degreeof commitment before project completion. There is also a need for timely commitment ofoperational and maintenance resources. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Ownership Sector Related Issues: Irrigation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-punjab-farm-water-management-project
WAPDA Tenth Power (Sector) Project | Pakistan | Energy | 2003-06-13 | Implementation of loans and TAs can be improved through better coordination within the executing agency or Water and Power Development Authority (WAPDA) and among WAPDA, the Government of Pakistan, and ADB. In loan implementation, substantive requests for loan reallocation and extension of loan closing often originate directly from WAPDA. ADB is not always able to act quickly on the requests due to inadequate information/justification and lack of a formal request from the Economic Affairs Division (EAD). Sometimes a reallocation request from one department originates without that department being fully aware of uncommitted loan balances or the adverse impact the requested loan reallocation could have on subprojects handled by other departments. This is particularly so for sector loans where subprojects fall under different departments (viz., Thermal, Hydel, etc.). project cycle stage: Implementation Lesson Topics: Loan Agreement: Loan Agreement Modality: Technical Assistance Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project administration Methodologies/Approaches: Consultation/Participation Since the electromechanical contracts (EM-1 and EM-2) were due to commence at the same time as the civil works, the delay in the financing arrangements of EM-1 and EM-2 caused delays in the civil works. It is essential for future projects that, when contracts depend on one another, financing be secured for all parts of the project. This also applies to environmental issues. There was a delay in the KfW financing for Part A due to problems with oil handling, the wastewater plant, and gas allocations/supply. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financing Project Management: Procurement Sector Related Issues: Energy planning/management The monitoring of project progress should be strengthened further in assisting the executing agency (Water and Power Development Authority or WAPDA) meet the reporting and record-keeping requirements in particular, in the aspect of timely submitting of WAPDA's audited financial statements, project progress and completion reports in a format agreed upon by the Borrower and ADB. Although structural reform at WAPDA is expected to significantly improve corporation management, and commercial and financial performance, these areas still need improvement. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial reporting Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Project administration Project Management: Project reporting Capacity Development: Capacity building Policy & Reform: Public sector reform Policy & Reform: Reform The project was successful in many aspects except for significant delays caused by the unavailability of counterpart funds. Future ADB assistance to the power sector in the country should take into account the adequacy of counterpart funds from the Borrower or the executing agency (Water and Power Development Authority or WAPDA), possible cost overruns, and internal procedures that may affect implementation. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financial analysis Project Management: Executing/Implementing agencies Project Management: Project administration Sector Related Issues: Energy planning/management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/wapda-tenth-power-sector-project
Sindh Forestry Development Project | Pakistan | Agriculture, Natural Resources, and Rural Development | 2003-04-15 | Although the target-oriented approach may have worked well in delivering required outputs,the overemphasis of accomplishments in terms of numbers might have affected the quality ofoutputs. Plantation failures could partly result from too much emphasis on the satisfaction oftargeted numbers, while setting aside quality checks on contractor outputs and site selection. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project supervision Methodologies/Approaches: Targeting Most failures in the irrigated plantations may be caused by (i) soil salinity, (ii) improper landpreparation, or (iii) drought. Implementors may control the first two causes, but drought is obviouslybeyond human control. The soil salinity problem may be avoided by better site selection. Similarly,closer monitoring can minimize, if not completely eliminate, improper land preparation. Projectmanagement has noted that success rates are generally higher in contracts that are of moderatesize (200 ha or less) than in large contracts (more than 300 ha). This simply means that largercontracts are less manageable and thus, their quality of output is lower. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Procurement Sector Related Issues: Irrigation management Participation of local communities in the community forestry subcomponent was primarilybased on optimistic projections that a wood processing plant would be established to absorbproduction of eucalyptus plantations. This did not materialize, however, which dampenedparticipants' interest in tree plantations. Cancellation of the private sector credit component alsohighlights the need for careful policy analysis, assessment of existing and alternative tenurialarrangements, and extensive consultations with the stakeholders. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Private sector Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Social forestry appears to be an efficient strategy to promote the policy of increasing forest cover and bridging the gap between supply and demand for wood, as indicated by its EIRR of 22% compared with the overall project EIRR of 9%. But the project, in its current design, is biased toward landowners and virtually excludes the landless. Thus, there is a need to develop a strategy that promotes social forestry and helps enhance livelihood security for marginalized groups. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Vulnerable groups Finance & Financial Aspects: Financial analysis Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Rural development Methodologies/Approaches: Community approach Technical Assistance (TA) outputs can be more beneficial if (i) the TA is conducted in response to clearly identifiedgaps in knowledge, (ii) deliberate efforts are taken to respond to the outputs, and (iii) knowledge istransferred to end users. The management plans are fully appreciated because their use is readilyseen, and filled an executing agency need. In contrast, the assistance provided in developing benefitmonitoring and evaluation system was not very successful because its use was not easilyappreciated, no effort was made to utilize it, and there was no knowledge transfer. Thus for futureprojects, it will benefit the executing agency to include, when applicable, a phase fordemonstrating the use of the results, and a reasonable time for knowledge transfer. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Modality: Technical Assistance Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Problem identification Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Technology/Technology transfer The economic efficiency of developing new plantations in riverine and inland forest reserveshas not been established; this is indicated by their low EIRRs, ranging from 0 to 1%. The lowEIRRs are such that the cost of land preparation and investment in irrigation infrastructure are high,compared with the benefits derived. But it is viable to place existing plantations (where irrigationsystems are in place) under sustainable management; examples are the inland (rehabilitation) andthe existing plantations covered by the integrated management plans. However, considering anecological and environmental perspective, there would be good reasons to continue the forestcover program, including the combat of desertification, preservation of biodiversity, soilstabilization, and minimization of soil erosion. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial analysis Sector Related Issues: Irrigation management Methodologies/Approaches: Holistic approach The project management focused on the physical and financial progress of the project. But besides maintaining adequate records for irrigated plantations, qualitative information was also gathered. Data on stand density or tree cover provided some qualitative measure of achievement of targets. Project management is now using such data to decide whether or not to replant. Reporting only the extent of areas planted for any given year does not indicate the overall area planted. To more meaningfully measure project accomplishments, the area planted as a physical target for a given year should be accompanied by the accumulated areas with sufficient tree cover as a result of plantations established since the project began. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Project Management: Project management Sector Related Issues: Irrigation management Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/sindh-forestry-development-project
Selected Advisory Technical Assistance for Capital Market Development in Pakistan | Pakistan | Finance | 2003-01-31 | Attempting to deal with too many complex issues under one technical assistance (TA) is not effective. This is particularly so in situations where different sets of specialized skills are required to implement the TA. In those situations, it is difficult to engage a versatile team leader capable of leading from the front and coordinating effectively the inputs and outputs of different TA components or aspects. project cycle stage: Design Appraisal Implementation Lesson Topics: For healthy, balanced, and sustainable development of the capital market, it is necessary to develop all the major aspects of capital market development i.e., demand, supply, intermediation, and regulation. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Policy & Reform: Reform Shortcomings of technical assistance design translate into shortcomings of TA outputs. project cycle stage: Design, Implementation, Completion Lesson Topics: Strong government ownership is critical to the success of any initiative in policy and institutional reform. Even though the technical assistance had no direct bearing on the credit lines provided under the Financial Sector Intermediation Loan, to which it was attached, prior policy dialogue and ownership building had strengthened the government's resolve to address the pressing issues in the stock market, mutual funds, leasing, and regulatory areas. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Ownership Policy & Reform: Policy reforms/framework Subject to availability of adequately qualified professionals in the relevant field, as well as dedicated technical assistance administration by ADB, use of domestic consultants is highly cost effective. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Consultants Technical assistance involving complex issues should be implemented in phases, and in a proper sequence, after basic understandings have been reached with the government during the policy dialogue. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Policy & Reform: Policy matrix | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/selected-advisory-technical-assistance-capital-market-development-pakistan
Provincial Highways Project | Pakistan | Transport | 2002-12-13 | Careful consideration should be given to the selection of executing agencies. Havingmultiple executing agencies with no direct linkage with the government's hierarchy madecoordination and cooperation among the entities almost impossible. The Road MaintenanceManagement and Road Safety components would have been more successful if implemented by the Communications and Works Department (CWD). project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation Delays and extra expenses caused by pavement failures and the need to add thicker asphalt concrete on several road sections might have been avoided if supervision of the Project Preparatory Technical Assistance (PPTA)consultants, and scrutiny of the final civil works designs, had been closer. Funding constraints should not pressure design consultants to cut back on design standards; it would have been better to shorten the lengths of roads to be improved, rather than marginalizing the design. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Monitoring & Evaluation: Project evaluation Project Design: Project design Project Management: Consultants Project Management: Project supervision Sector Related Issues: Roading The drawbacks of using a central coordinating agency, the National Highways Authority (NHA), and Ministry of Environment, Local Government and Rural Development (MELGRD) in the project were: (i) assumption of a far greater role than originally envisaged, thus resisting delegation of responsibility to the provincial Communications and Works Department (CWDs); (ii) diffusion of the institutional and sectoral aspects as reflected in the loan covenants; and (iii) a general lack of ownership by the provinces. project cycle stage: Design Lesson Topics: Loan Agreement: Covenants Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Country Context: Decentralization The project had difficulty in attracting the interest of international contractors for the prequalification process. Breaking such projects into smaller packages, suitable for local competitive bidding, would probably have been better. project cycle stage: Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/provincial-highways-project
Teacher Training Project | Pakistan | Education | 2002-11-15 | Closer supervision by the federal-level executing agency, the consulting firms, and ADB review missions could have improved the outputs of the international and domestic consultants. project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project supervision Due to the failure of the federal-level executing agency to properly supervise and coordinate project activities,particularly at the provincial level, such umbrella-type project management should bediscontinued and replaced largely by a decentralized system led by Provincial Institute of Teacher Education (PITEs) or Project Implementation Units (PIUs) and coordinated by the Technical Panel on Teacher Education (TPTE). project cycle stage: Feasibility Lesson Topics: Project Management: Project management Project Management: Project supervision Country Context: Decentralization Methodologies/Approaches: Consultation/Participation Due to the high turnover of project directors and project managers, theappointment of deputy project managers from external candidates with strong project management experience would help maintain continuity of project supervision. project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Project management Project Management: Project supervision Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/teacher-training-project-0
Capital Market Development Program | Pakistan | Finance | 2002-10-15 | Although political disruptions delayed the progress of program implementation in difficult macroeconomic circumstances, strong commitment of the executing agency and solid support from the implementing agency prevented the program from derailing and enabled its successful completion. The need for strong ownership of the program by the executing and implementing agencies was confirmed, as many problems not foreseen at the time of program formulation were resolved through a concerted effort of the officials concerned. Such ownership was a result of ADB's extensive and in-depth discussions with government officials on the program design at the time of its formulation, and similar efforts should be made mandatory in processing future assistance, particularly in view of the economic and political instability in the subregion. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Despite considerable interaction and cooperation with the government, executing the program proved to be more complex than originally envisaged. For example, the intricate design of publicly owned mutual funds, involving unusual legal obligations and many politically influential stakeholders, was not fully understood at the time of program formulation.Restructuring and privatizing the funds required political consensus lacking at the time of program inception as well as substantial resources to undertake due diligence. While events unforeseen at the time of program appraisal are inevitable, more efforts may be needed in ascertaining potential areas of technical difficulties and incorporating measures to resolve them. Such efforts at the initial phase of a program's formulation will increase the likelihood of timelyprogram execution. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Modality: Program Project Design: Appraisal Project Management: Project management Policy & Reform: Privatization Policy & Reform: Public sector reform Methodologies/Approaches: Consultation/Participation The implementation of the program revealed the deeply entrenched problem of poorcorporate governance and lack of transparency in business practices and market transactions. Many of the frameworks put in place by the program will be meaningless at the operational level unless the participants adopt higher corporate governance standards. There is an immediate need to strategically address the governance issue that seriously restricts development of the capital market and the economy at large. Basic rules and regulations on market transactions, transparency on trade reporting, and timely and accurate disclosure of financial information by the issuers are some of the fundamental factors still missing in the capital market. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Modality: Program Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/capital-market-development-program-0
Third Health Project (Loan 850-PAK[SF]) | Pakistan | Health | 2001-12-10 | Availability of medicines has been a major issue for health managers. Irregular supply has adversely affected service delivery under the project. This seems more a managerial than a budgetary issue. Providing essential medicines for each facility based on demand, and decentralizing procurement to the district level as part of the devolution process would improve the supply situation. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Market analysis Project Management: Procurement Project Management: Project administration Project Management: Project management Country Context: Decentralization Sector Related Issues: Health and sanitation management Beneficiary and stakeholder participation needs to be integrated into early stages of project preparation and implementation planning to ensure ownership by the targeted beneficiaries. A needs-based community project with strong community involvement and ownership is most likely to be sustainable. Investing in social capital includes performing a thorough social assessment. To enhance the prospect of project success, it is important to adopt a flexible implementation system based on the process-oriented approach with a built-in midterm review. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Human resources management Capacity Development: Ownership Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach Efficiency and utilization of the public sector health facilities can be improved by increasing budgetary allocations. The correlation between the arrival of medicines and increased number of patients is one example. While cost sharing is still generally unacceptable to the government, it is one way of improving service and reducing the budgetary burden at the same time. More than 80 percent of rural health center (RHC) clients are willing to share at least some of the cost if high-quality services are made available to them. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial management Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Policy & Reform: Reform Experience in development initiatives points to the importance of providing assistance and policy guidance over the long term. To realize the full potential of ADB assistance, continuous investments during a long period are needed. A project provides only some initial inputs. Institution building should not be limited to the few years of project implementation, but rather should extend over a much longer period that would span a series of projects. Desired results are realized only after a series of initiatives, one building on the achievements of another, over an extended period of time. The experience with ADB-assisted projects in the health sector confirms this. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Cluster operations Capacity Development: Capacity development Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework More than 70 percent of clients of the health facilities are women and children. Maternal and child health (MCH) services, and obstetric and gynecological care, require the services of qualified and trained women medical officers (WMOs) supported by female health workers. Limited female mobility, lack of basic facilities, and security problems are the main issues that need to be addressed in posting and retaining female staff in rural facilities. Financial and other incentives have been successful in some DMCs in this regard. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Vulnerable groups Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development The implementation delay of 2.5 years is attributed to a lack of adequate project management experience of the EAs, the frequent changes of key personnel, the unfamiliarity of project implementation unit (PIU) staff with ADB procedures on recruitment of consultants and procurement, and the protracted approval process for civil works. Actions to address these issues are in fact those generally proposed to address systemic constraints in most ADB projects. Many of these actions are now made preconditions for appraisal, loan negotiations, loan approval, or loan effectiveness, or are agreed to as loan covenants. Some built-in mechanism in project design to retain key project staff up to at least one year after project completion, and to integrate them with the regular structure of the EAs, would help operationalize project facilities. project cycle stage: Design Lesson Topics: Loan Agreement: Covenants Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Project Management: Project management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/third-health-project-loan-850-paksf
Karachi Sewerage Project (Loans 1001-PAK[SF]/1002-PAK) | Pakistan |  | 2001-11-30 | As a result, the Mauripur sewage treatment plant is at risk of halting operations. The financial impact of a sewerage project on the executing agency needs to be assessed carefully. Although the financial difficulties of the EA were well known during project preparation, it was probably overly optimistic to expect that the federal government and the government of Sindh had the political will to address this issue. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Ownership Sector Related Issues: Urban sector/development Policy & Reform: Reform The BME system was to be established too late in the project cycle and the EA did not have the required skills to establish such a system. An assessment of an executing agency s capacity for establishing a BME or any other project performance monitoring system should be undertaken during the project preparation stage. project cycle stage: Feasibility Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment The main weaknesses of the project were related to its design and operation. In cases where the appraisal cost estimates for a project are based on inaccurate standard unit rates, ADB should closely monitor any redesign of the project to ensure that the design is efficient and least cost. project cycle stage: Design, Operation Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/karachi-sewerage-project-loans-1001-paksf-1002-pak
Social Action Program (Sector) Project (Loan 1301-PAK[SF]) | Pakistan |  | 2001-11-30 | Greater social sector expenditure and increased nonsalary expenditure by the government may be necessary conditions for improved social outcomes but they are not sufficient. Directing incremental expenditure and increased nonsalary funds through poorly performing and largely unchanged public institutions produces unsatisfactory results. project cycle stage: Design Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Sector Related Issues: Education Sector Related Issues: Urban sector/development Policy & Reform: Public sector reform In reform programs such as the Social Action Program (SAP), it is critical that formulation and design of projects involve all stakeholders particularly those responsible for service delivery at the provincial, district, and facility level, private providers, and the community. project cycle stage: Design, Feasibility Lesson Topics: Incremental public sector Social Action Program (SAP) expenditure will be financially sustainable only if strong efforts are made to increase revenues through means such as cost recovery, higher resource mobilization from federal and provincial taxes, and privatization of noncore government assets to repay debt (thereby reducing debt servicing and, in some cases, recurring losses). Significant resource reallocations among sectors may also be required. project cycle stage: Design, Country Partnership Strategy Lesson Topics: Opportunities for efficiency and effectiveness gains from existing expenditure need to be identified and benchmarks established for service quality and the costs of service provision if incremental public expenditure is to produce expected results. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Indicators Policy & Reform: Public sector reform Policy reform agendas need to be coherent and consistent. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Program Approach There is a need for the government to redefine the role of the public sector in social service funding and provision with a view to greater adoption of user-pays mechanisms (according to need), greater fee-for-service provision, targeting of scarce public funds to the most needy through innovative schemes such as vouchers, and genuine and widespread public-private partnerships. Public servants often see community, NGO, and private sector participation in areas of service delivery traditionally handled by the public sector as a threat. Therefore, ways of overcoming public servant resistance must be found. project cycle stage: Design, Feasibility Lesson Topics: Sector Related Issues: Private sector Sector Related Issues: Public-private partnership | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/social-action-program-sector-project-loan-1301-paksf
KESC Fifth Power (Sector Loan) Project (Loan 925-PAK) | Pakistan | Energy | 2001-10-31 | ADB needs to be more circumspect in appraising sector loan objectives and the likelihood of achieving them, particularly where target achievements depend on the availability of local funding and the capability of the power utility. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Modality: Lending modality Project Design: Appraisal Project Design: Project design Capacity Development: Capacity assessment Methodologies/Approaches: Targeting Project experience highlighted the critical importance of scale and timing for upgrading distribution systems to improve overall system efficiencies. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Energy planning/management | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/kesc-fifth-power-sector-loan-project-loan-925-pak
Karachi Urban Development Project (Loan 793-PAK[SF]) | Pakistan |  | 1999-12-31 | ADB s project administration needs to be strengthened, particularly for close monitoring and enforcement of loan covenants on financial and institutional targets. Financial covenants need to be more precise in their intentions. Weak and vague covenants tend to not be complied with, resulting in little institutional reform. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation The absence of a Project Preparatory Technical Assistance (PPTA) early in the design stage of a complex project undertaking can directly result to project design as the main weakness. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Project design Urban upgrading is complex in nature, and a piecemeal approach to a few selected problems is not an optimal solution. Urban upgrading should be designed from a plan that integrates all aspects of urban infrastructure, and involves the participation of the ultimate beneficiaries. The institutional capacity to implement the project must be present, and the financial framework in place to ensure long-term sustainability of the upgrading. The absence of any of these elements will eliminate any chance for project success. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Project Design: Problem identification Project Design: Project design Capacity Development: Institutional analysis Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/karachi-urban-development-project-loan-793-paksf
Small Dams Project (Loan 750-PAK[SF]) | Pakistan | Agriculture, Natural Resources, and Rural Development | 1999-12-31 | Beneficiaries need to be fully involved in identification, design, and implementation if ownership is to be promoted. In particular, farmers should, where possible, construct their own watercourses with necessary support from project staff. project cycle stage: Concept Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Irrigation management Establishing sustainable water users association requires time and great effort. Such an activity needs to be specified and funded under the project if it is to succeed. High-level support is likely required for about two years with some support thereafter. project cycle stage: Feasibility, Implementation, Operation Lesson Topics: Project Design: Project design Capacity Development: Capacity development Sector Related Issues: Irrigation management Involving a range of agencies in project implementation is difficult, even where quite a strong agency is responsible for coordination. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation The slow nature of change in traditional rainfed agricultural societies requires that specific measures be taken to promote technology adoption. Where projectoutcomes depend on technological change, emphasis needs to be placed on adequate agricultural extension and input supply, both during and after the project. project cycle stage: Design, Implementation, Operation Lesson Topics: Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Extension service Sector Related Issues: Rural development The timing of command area development must be coordinated with dam construction. Watercourses should be constructed to permit irrigation soon after filling of the dam to avoid excessive delay of benefit generation. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development The traditional approach to small dam and command area development is unlikely to generate high levels ofsocial or economic benefit. New approaches will be required if acceptable performance is to be achieved, with a major focus on ownership, equity, and efficiency issues. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Irrigation management Sector Related Issues: Rural development | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/small-dams-project-loan-750-paksf
WAPDA Tenth Power (Sector) Project (Loan 824-PAK) | Pakistan | Energy | 1999-11-30 | ADB should be more circumspect in its appraisal of sector project objectives and the reality of achieving them, particularly where targets depend on scale and availability of local funding. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Methodologies/Approaches: Targeting There is need for a more time-effective appraisal system for selecting and approving distribution subproject proposals to optimize investment returns consistent with minimizing technical losses. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Subprojects Sector Related Issues: Energy planning/management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/wapda-tenth-power-sector-project-loan-824-pak
Chashma Command Area Development Project (Loan 723-PAK[SF]) | Pakistan | Agriculture, Natural Resources, and Rural Development | 1998-12-31 | Drainage systems should be made an integral part of all irrigation ventures. Drainage projects should be based on detailed studies that seek realistic understanding of the physical, institutional, and socioeconomic situation in the project area. Designs must reflect O&M needs and be adjusted as field conditions become better known and evolve over time. The implications of sector policies should be reflected in designs, particularly the prices of agricultural inputs and outputs. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Rural development In complex irrigation and drainage ventures, integration of their various components is necessary, together with effective coordination among agencies involved and participation of beneficiary farmers, preferably through their associations. Explicit consideration of the resources, needs, objectives, and capabilities of farmers (who are private entrepreneurs and often rather poor) is indispensable. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity assessment Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/chashma-command-area-development-project-loan-723-paksf
Second Health and Population Project (Loan 710-PAK[SF]) | Pakistan | Health | 1998-12-31 | Identifying and measuring the benefits arising from the project is inherently difficult. Thus, the installation of a BME system would provide an effective tool in assessing project impact. It is important that (i) project objectives be stated as specific (verifiable) and as quantifiable targets to determine the level of operating efficiency; and (ii) baseline data be established for the indicators before the inception of the BME system. Additionally, BME systems should be implementable and sustainable, and designed with the institutional capability of the implementing agency in mind. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Indicators Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Methodologies/Approaches: Targeting Institutional capacity is critical to attaining success, particularly in health and population sector projects that are service oriented. Thus, capacity building and an in-depth analysis of institutional constraints are paramount concerns throughout the project life cycle. The project highlighted the need for (i) development of a viable referral network, as well as close coordination with various government agencies; (ii) decentralization of financial and management authority; and (iii) human resource development that must address not only the appropriateness and quality of training, but also issues of incentives, deployment, and career development. Current ADB operations necessarily focus on policy analyses and formulation, governance, quality assurance of health care with emphasis on preventive health care programs, education and training, and health system structure and organization. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Public governance Capacity Development: Capacity building Capacity Development: Human resources management Capacity Development: Institutional analysis Crosscutting Issues/Themes: Employment Sector Related Issues: Education Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation One area in which the project design was deficient was in using the experience of the first project regarding consulting services and fellowships. Whereas utilization of these components in the first project was minimal, the design of the project included substantial person-months of these components in spite of government-stated reluctance. This highlights the need for intensive stake holder participation in project preparation. Ownership of implementing and executing agencies from the federal and provincial governments down to district level must be ensured. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation Performance results bring out the need to consider the overall health sector financing issues in relation to any macro policy distortions and impediments. Future health and population projects need to take into account the affordability of incremental recurrent costs and staffing requirements. It is important to realistically project the anticipated O&M and staffing requirements, and identify alternatives on how these requirements would be met. A review of the planning and budgeting processes of the government in allocating public resources to the health sector will be useful in ensuring project sustainability. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Management: Operation and maintenance Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework Secondary and tertiary health care, particularly in the semiurban and urban areas, are areas where private sector participation, as well as active participation of NGOs and health volunteer groups, can be encouraged to meet the largely curative needs of wealthier individuals. This would enable the public sector to focus its limited resources on the preventive and promotive health care needs of low-income individuals. Experience from ADB projects highlights that cost-recovery measures have a greater chance of success when introduced gradually through pilot studies and combined with an intensive information campaign for community participation. At the same time, there is a need to emphasize cost-sharing and containment measures, as well as waste reduction through effective management. There is a need to provide incentives and encourage the private sector to provide health and family planning services in areas where there is heavy reliance on government subsidies. project cycle stage: Concept Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financial management Sector Related Issues: Health and sanitation management Sector Related Issues: Private sector Sector Related Issues: Urban sector/development Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Pilot project | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-health-and-population-project-loan-710-paksf
Second On-Farm Water Management Project (Loan 871-PAK[SF]) | Pakistan | Agriculture, Natural Resources, and Rural Development | 1998-09-30 | Accountability for project performance could be increased by formation of an independent monitoring cell receiving comments and complaints from project users and reporting to the top management of the executing agency. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management On-farm irrigation and drainage projects are fundamentally high-return ventures because they represent a small incremental investment cost necessary to ensure the benefits of broader irrigation development. They should be included as an integral part of any irrigation project. Moreover, improving on-farm conditions without attending to weaknesses at off-farm levels in irrigation and drainage systems has significant costs in terms of lost potential efficiency gains. This applies to both physical and institutional infrastructure. In that regard, an institution responsible for O&M that allocates most of its funds to administration rather than actual works could require major reforms. In fact, where incentives for government agencies to perform effectively are weak or absent, irrigated agriculture can improve much if farmer institutions are developed to take responsibility for infrastructure beyond the farm level as well. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity development Capacity Development: Human resources management Sector Related Issues: Extension service Sector Related Issues: Irrigation management Policy & Reform: Reform Promotion of economic efficiency and agricultural performance depends much on the proper pricing of irrigation water and agricultural inputs and outputs. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-farm-water-management-project-loan-871-paksf
Farm-to-Market Roads (Loan 758-PAK[SF]) | Pakistan | Transport | 1998-08-31 | It is important to effectively monitor (i) the selection of roads to ensure that the right type is included; (ii) the provision of embankments and drainage facilities, which can be included in the design but omitted during construction for some roads; and (iii) the collection of baseline information about individual roads prior to construction. All of these aspects bear vital implications for project performance. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Roading More autonomy is required for the apex executing agency to take quick and efficient decisions at the project level. To a great extent, this would remove the administrative bottlenecks that cause enormous delays, e.g., unnecessary reapprovals which have to be obtained from authorities outside the project. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Public governance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project formulation, including the physical targets for different components and the implementation schedule, should be based on realistic estimates of both resources and time required for various project activities, keeping in view other limiting factors such as administrative procedures and coordination between government agencies. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Project administration Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Targeting The participation and involvement of various stakeholders, including government agencies at the district and provincial levels, and beneficiaries, in project planning, implementation, and operation and maintenance are important to assure a firm commitment to implementing an effective maintenance program immediately upon project completion. project cycle stage: Feasibility, Implementation, Completion Lesson Topics: Crosscutting Issues/Themes: Public governance Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/farm-market-roads-loan-758-paksf
Gujranwala Agricultural Development Project (Loan 734-PAK[SF]) | Pakistan | Agriculture, Natural Resources, and Rural Development | 1997-12-31 | Alternative ways of ensuring that O&M activities would be undertaken rather than just covenanting the government to provide adequate budget for O&M in the face of fiscal constraints should be built into the project design. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Loan Agreement: Covenants Project Design: Project design Project Management: Operation and maintenance In-depth studies should be carried out to establish the demand for the benefits and services that important project components can offer. These studies should consider the constraints that will be imposed in providing the services. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Risks/Risk management Policy reforms that are unfocused or open-ended tend to meet with difficulties in compliance, while inconsistent policies tend to nullify any improvement in the policy environment. project cycle stage: Feasibility, Implementation Lesson Topics: The change in scope during project implementation from tubewell electrification to village electrification might have lessened the benefits arising from increased crop production as tubewells were meant not only to increase the supply of water but also as a measure to reduce the water table and prevent the occurrence of soil salinity. The change in scope could have been accompanied by a thorough study of the expected output of the original component, the consequences of not implementing the component, and alternative ways of achieving its impact. The study could also have determined whether implementing the substitute component was the most cost-effective approach. project cycle stage: Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management The expediency of using loan savings after a project has been substantially completed must be weighed against the possibility that it may be more optimal to have part of the loan canceled to help reduce the debt burden of the DMC. project cycle stage: Completion Lesson Topics: The implementation of a multicomponent project involving many executing agencies can be successful provided it is coordinated by experienced staff funded as part of the institutional strengthening plan of the project and closely supervised by ADB staff. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Project supervision Capacity Development: Capacity building With proper credit facilities, entrepreneurship can be nurtured among women and the landless; however, alternatives to using land or other assets as collateral need to be found. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Vulnerable groups Finance & Financial Aspects: Financing Sector Related Issues: Rural development | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/gujranwala-agricultural-development-project-loan-734-paksf
Hyderabad Water Supply and Sewerage Project (Loan 263-PAK[SF]) | Pakistan | Water and Other Urban Infrastructure and Services | 1997-11-30 | In a low-income setting, sophisticated sewerage systems may not be the most appropriate approach to achieving health and hygiene benefits. Amalgamating sewerage with water supply expansion may put the project beyond the capacity of the executing agency. It is best to concentrate first on providing more water along with adequate drainage. project cycle stage: Feasibility Lesson Topics: Longer delays are incurred completing large system components, and the delays are exacerbated by shortage of local funds. In project processing, the risks of nonavailability of local funds should be carefully assessed, even if prior assurance of the government has been received. project cycle stage: Appraisal Lesson Topics: The project design should select an economic least-cost option comprising innovative and smaller project components that can be individually completed with fewer delays and, once completed, can start operating independently and delivering benefits, thus improving the overall economic performance of the project. project cycle stage: Feasibility Operation Lesson Topics: Time-bound covenants requiring the utility to raise tariffs are ineffective unless ADB's review missions pursue corrective steps to prevent further erosion of financial stability. project cycle stage: Feasibility Operation Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financial management Loan Agreement: Covenants Project Management: Operation and maintenance | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/hyderabad-water-supply-and-sewerage-project-loan-263-paksf
Third Development Financing Project (Loan 878/879-PAK[SF]) | Pakistan | Finance | 1996-12-31 | Project experience point to the need for more careful project preparation to avoid design deficiencies and conflicting aims. In particular there is a need at project design (i) to ensure that investing in industrial projects will contribute to project financial viability and is consistent with attaining the overall aims of the project, (ii) to ensure that credit lines are extended with adequate planning and assurances for the way in which term funding from the PFIs can be sustained, and (iii) to give more direct assistance on improving the operational systems and efficiencies of the PFIs. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Industry and Trade | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/third-development-financing-project-loan-878879-paksf
Science Education for Secondary Schools Sector Project (Loan 759-PAK[SF]) | Pakistan | Education | 1996-10-31 | Better sequencing of the project components could have averted the consequences of delayed establishment of educational facilities (Institute for the Promotion of Science Education and Training (IPSET), and Science Education Centers). Under the changed circumstances of the project after start-up, it might have been better to have reverted to the existing institutional framework to begin implementation of the software and training components. The process of identifying and hiring staff for teacher training and curriculum revision as well as sending selected personnel abroad for training should have preceded the setting up of educational facilities. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Management information system Capacity Development: Capacity building Capacity Development: Human resources management Capacity Development: Institutional analysis Capacity Development: Technology/Technology transfer Sector Related Issues: Education Education projects that add new institutions to an existing, very complex network of educational institutions need to ensure the unambiguous placement of the additions in the existing line of authority. The main intended function of The Institute for the Promotion of Science Education and Training (IPSET) was the creation and implementation of a new science curriculum and related textbooks. Yet, it was a multiplicity of other parallel bodies which actually retained the power under legislative acts to determine matters for curricula and textbooks. This particular example of a separation of function from administrative responsibility is a result of the complex, in many ways duplicative and ambiguous, institutional framework for the education sector. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Education Policy & Reform: Policy reforms/framework In general, future education projects should deemphasize hardware components in favor of software components. Funding for teacher training and teaching aids quality improvement should be assigned high priority. Quantification of employment benefits, which arise as a result of the improvement in the quality and relevance of secondary science education, could focus project implementation management on education quality and achievement targets, rather than on physical output targets. The Post-Evaluation Mission recommends using a measure of wage- or employment-related benefits for monitoring project objectives. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Capacity building Crosscutting Issues/Themes: Employment Sector Related Issues: Education Methodologies/Approaches: Targeting Integration of newly set up project institutions needs to be accomplished on the budgetary side as well, so that there is no repetition of the experience of the project where the newly set up institution is still getting a lump sum grant to maintain operations at less than minimum level required after project completion or is barely operating without a regular source of funding. Repair workshops for science equipment are not of much use when science equipment still partly lies idle, or where there is no budget for distributing the equipment among the schools, as well as collecting it for repair by the workshops. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/science-education-secondary-schools-sector-project-loan-759-paksf
Faisalabad Water Supply, Sewerage and Drainage Project (Loan 331-PAK[SF]) | Pakistan | Water and Other Urban Infrastructure and Services | 1996-04-30 | A utility needs to be able to focus on activities essential to its business for autonomous operation on a financially self-sufficient basis to meet customers' demand. ADB leverage to facilitate capacity building should be exerted early in a project because its effectiveness decreases as a loan approaches its closing. ADB should be ready to pay and work for improving the project's quality and capacity upgrading. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building The core of demand-based planning is a commitment to draw beneficiaries into the planning process by assessing their willingness to pay for selected technological options and related costs, thereby allowing the prediction of the degree of financial autonomy and sustainability of a project and thus the extent of possible subsidization. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Without improvement of customer satisfaction, the prospects of long-term payment of tariff and the utility's financial soundness are limited. Once confidence in a utility's ability and commitment to extend quality service is lost, restoring and ensuring tariff payment become difficult even when services improve. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Capacity Development: Ownership Policy & Reform: Reform | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/faisalabad-water-supply-sewerage-and-drainage-project-loan-331-paksf
Bank Operations in the Gas Sector in Pakistan | Pakistan | Energy | 1995-12-31 | Financial covenants are of limited effectiveness without appropriate changes in government policy. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial management Loan Agreement: Covenants Policy & Reform: Policy reforms/framework Low prices are generally not an effective means of targeting assistance to the poor. Except in particular circumstances, the major beneficiaries of such low prices are likely to be higher income groups. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Market analysis The policy environment is important if the full potential of projects is to be realized. Distortions in the policy environment make it difficult for managers to make correct decisions and frequently inhibit investment. project cycle stage: Feasibility Lesson Topics: | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/bank-operations-gas-sector-pakistan
Load Despatch and Transmission Project (Loan 505-PAK[SF]) | Pakistan | Energy | 1995-09-30 | Implementation experience has shown that the formulation and appraisal of similar (energy) projects should be carried out within the framework of a long-term power program that includes information about government policies as well as data and analyses of power systems. The assessment of the power sector should also be linked to the overall macroeconomic development plan of the country to ensure project quality and sustainability and prevent the ad hoc changes that result from short-term assessments. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Data collection and management Project Design: Appraisal Sector Related Issues: Energy planning/management Policy & Reform: Policy reforms/framework Prior to commercial operations of the load despatch system (LDS), training was conducted to prepare the executing agency personnel to operate the LDS. However, given the dynamic nature of technology and systems used in the project, an ongoing training program should be formulated so that the training needs of personnel are anticipated, defined, and implemented. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Sector Related Issues: Energy planning/management While the actions taken by ADB and the executing agency after loan approval were generally responsive to the changing needs of the project, slow decision making on the part of the executing agency and the government resulted in significant delays and cost overruns. Although improvements have occurred, there remains room to strengthen project implementation procedures and arrangements in the government and the executing agency. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/load-despatch-and-transmission-project-loan-505-paksf
Second Telecommunications Project (Loan 761-PAK) | Pakistan | Information and Communication Technology | 1995-02-28 | Project experience highlights the importance of detailed cost accounting systems and procedures to be in place to allow for investment programs to be undertaken which are funded from numerous sources. The existence of a proper cost accounting system is a prerequisite for efficient tariff design particularly where a more competitive environment is evolving. Conversely, it may be argued that unless the executing agency devotes greater effort to its cost accounting systems, it will not maximize its gains from its recent investment program. Similarly, it will not be able to clearly define its future policies regarding tariff cross-subsidization and more generally pursue social equity objectives on behalf of the government, particularly with regard to rural telecommunications. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Executing/Implementing agencies Project Management: Management information system Sector Related Issues: Rural development Whilst it is often recognized by segments of telecommunications markets that tariffs could be significantly higher (as supported by transport cost savings to particular users), country-specific surveys are required to reliably estimate 'willingness to pay' (WTP) estimates, by consumer groups, for new telecommunications projects. It is important that market data are available prior to and at the completion of project implementation to indicate how consumers value the provision of access to telephone services for the first time and how the improved quality of service to existing users is valued, in domestic prices. Similarly, it is important to be able to identify the correct supply/demand responses from the implementation of telecommunications projects and to estimate, on that basis, the prices for services. By underestimating the economic benefits to communities of telecommunications projects, particularly in rural areas, lower EIRRs will continue to be generated and future investment signals to the sector will remain distorted. project cycle stage: Feasibility Completion Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Management information system Sector Related Issues: Rural development | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-telecommunications-project-loan-761-pak
Facilitating Public-Private Partnerships: Technical Assistance Completion Report | Papua New Guinea | Public sector management | 2016-05-01 | TA (technical assistance) that is supporting sensitive reform areas in the Pacific takes substantial time to implement. The original time period for TA implementation of 24 months was highly optimistic given the country context and political economy issues, given the nature of the reforms. The challenging and slow progress, despite the availability of resources under this TA (and the additional support through PSDI or Pacific Private Sector Development Initiative), demonstrate the challenges of advancing a PPP program in the Pacific. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/png-facilitating-ppp-tcr
Major Bridges Study: Technical Assistance Completion Report | Papua New Guinea | Transport | 2015-07-01 | Despite the delays in the recruitments, the consultant was able to complete the assignment on time and submitted high quality report. This was mainly due to the 90:10 selection method and lump sum contract as was jointly expressed by the consultant and DOW (Department of Works). Lump sum contract enabled the consultant to work at their own pace given the flexibility in managing their resources and staging their inputs. Moreover, the consultant was actively pursuing for the feedbacks and comments on their deliverables which resulted timely payments. Project cycle stage: Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/png-major-bridges-study-tcr
Road Maintenance and Upgrading (Sector) Project: Validation of Completion Report | Papua New Guinea | Transport | 2015-01-30 | The PCR (project completion report) identified a few important lessons. One lesson was the need for frequent reviews and close supervision and monitoring of procurement processes. Another lesson pointed out that counterpart funding allocation into project accounts should be made a condition of ADB disbursement. The next lesson cited the need to ensure that subproject preparation should, at least, reach 90% completion at the time of project preparatory technical assistance and 100% before loan effectiveness. The last suggested a rigorous assessment of the executing agency's capacity to undertake technical, financial, economic, safeguards, and governance evaluation of subprojects, which should be done during project formulation. This validation finds these lessons appropriate and has no additional lesson to offer. project cycle stage: Design, Implementation | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/papua-new-guinea-road-maintenance-and-upgrading-sector-project
Community Water Transport Project: Project Completion Report | Papua New Guinea | Transport | 2014-08-01 | The project demonstrated that subsidized community water transport services can be viable delivery mechanism that can provide improved access for marginalized and remote maritime and river-based communities so they can access health, education, and other government services. Improved maritime services can also increase production of market produce and goods, increase community earnings, and reduce poverty, particularly when linking franchise shipping service provision and infrastructure improvement in future project design so that synergistic effects can be expected to increase the number of passengers. While the issue of delays to project mobilization were recognized in the lessons learned at appraisal, the project failed to ensure such delays did not occur. Future projects need to plan for timely advance procurement of consultants and ensure advance commitment to institutional and financing arrangements prior to loan approval. Where trust funds are part of project design, institutional and operating rules need to be agreed and trust deeds formulated and agreed, if not formally signed prior to loan approval. Advance appointment of fund managers should be considered. In the Papua New Guinea context, arrangements to avoid or fast-track the Central Supply and Tenders Board/National Executive Council procurement process need to be considered for incorporation in project loan agreements. The project encountered considerable delays and significant cost escalations in the design and tendering of the remote water transport infrastructure restoration component as a consequence of the switch from restoring existing structures to building new structures and introducing equitable distribution of project structures among maritime provinces. Future projects should examine the relevance, design, and cost implications and determine the project scope and design resource needs, avoiding the need for scope changes. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/png-community-water-transport-project-pcr
Road Maintenance and Upgrading (Sector) Project | Papua New Guinea | Transport | 2013-10-01 | 1. The initial delays due to the lack of consistent and timely project review and oversight from ADB during the first 3 years of the project could not be corrected for a long period, during which time civil works progress fell behind completion targets and disbursement was constantly below expectations. In order to mitigate this, frequent review and close supervision and closely monitoring for in-country procurement processes will be required. 2. Expedite Withdrawal Application processing by reducing processing time and involving ADB in checking the claim before the Engineer issues the payment certificate. One way of overcoming this issue is to ensure that counterpart funding allocation into the project account needs to be made as conditions for ADB's disbursement. 3. Government counterpart funding for similar projects needs to be secured upfront, at least for the initial years with firmer guarantees for subsequent years, and paid into a separate project account. Subprojects need to be duly appraised, estimates prepared and approved, at least prior to Loan Effectiveness. Subproject preparations must reach 90% completion at the time of project preparatory technical assistance and 100% prior to loan effectiveness. This could be made as ï¿½effectiveness' criteria. 4. A rigorous assessment of an Executing Agency's capacity to undertake technical, financial, economic, safeguards and governance evaluation of subprojects needs to be conducted during project formulation. Project preparatory technical assistance report is to include a section or appendix on the Executing Agency capacity assessment and Report and Recommendations of the President is to propose measures to gap the capacity constraints. 5. To facilitate project implementation, Executing Agency need to encourage and apply advanced procurement where possible to engage consultants and initiate procurement activities for subproject contracts early to minimize delays which otherwise result in price escalations. Advance action for procurement and consultant recruitment is made compulsory with the assistance of ADB staff in guiding the Executing Agency's staff. 6. To ensure efficient contractor performance, local contractor ability and capacity needs to be assessed in advance to determine appropriate contract packaging and apply single step procurement procedures. Project preparatory technical assistance report shall include a section or appendix on the local contracting and consultant capacity assessment and Report and Recommendations of the President is to propose measures to gap the capacity constraints. 7. Most importantly, the government, Department of Works and the development partners need to agree on adequate levels of maintenance funding necessary for the sector and ensure that they are provided into a separate account at the beginning of the year to implement a properly designed maintenance program. The amount to be committed by the Government/ Department of Works needs to be clearly mentioned in the Report and Recommendations of the President and covenanted in the loan agreement. 8. To avoid implementation delays, project management units need to be established in advance, with appropriate personnel and advance capacity training provided to such personnel. Establishment of project management unit and the engagement at least 90% of the project management unit full time staff is made as condition for loan effectiveness. 9. Separating the engineering consultant roles between (i) design and supervision and (ii) implementation support needs to be carefully assessed during project design. When such division of responsibility is included in the project design, the design and supervision consultants need to be appointed first to avoid the project performance problems. 10. All civil works project loans need to be delegated to ADB's country resident mission at the earliest date, to ensure closer monitoring, so that where necessary, monthly review meetings can be held with Executing Agency to monitor performance against monthly agreed targets set at prior monthly meetings. This monthly monitoring approach should be mandatory for projects experiencing significant implementation and disbursement delays. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/road-maintenance-and-upgrading-sector-project-pcr
Papua New Guinea: Financial Management Project | Papua New Guinea |  | 2011-10-31 | 1. The risks associated with a change in scope (in this case the inadequate capacity of the executing/implementing institution) needs to be fully considered to prevent project failure. For example, experience with the Financial Management Project in Papua New Guinea (PNG) pointed to the importance of ensuring that institutional capacity exists carrying out changes, i.e., technical aspects of the project design. The decision to combine components 1 and 2 during its third year of implementation, and to fund the development of an integrated software package that could cover all activities under these two components introduced a huge risk to the project. The use of an integrated system for public sector financial management was rare even in developed countries, and required technical sophistication in the development and operations phase that was nonexistent in PNG. This change in design led to implementation delays, and adversely affected project outputs and outcomes. It also reduced the relevance of the project. [Main text, paras. 10, 20] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity development | Validation of Project/Program Completion Report | Unsuccessful | http://www.adb.org/documents/papua-new-guinea-financial-management-project
Microfinance and Employment Project | Papua New Guinea | Finance | 2011-09-01 | Realistic design key in conditions of uncertainty. When a project seeks to develop a nascent industry in a challenging environment, outputs need to be realistic. The project design relied on assumptions about the state of and potential for development in the microfinance industry that proved to be unrealistic. The project redesign highlights the need to be flexible in adapting the project to emerging realities and experiences in the industry. Efficient reporting and data collection essential. The project implementing unit (PIU) did not allocate sufficient time to reporting and data collection during implementation, which impacted negatively on the ability of ADB and the microfinance steering committee to administer the project effectively. Not housing the PIU within the executing agency reduced oversight and transparency. Timely reviews, earlier solutions, lower costs. A major project redesign followed a midterm review. While the changes contributed significantly to the success of the project, this review occurred came fairly lateï¿½in 2005, compared with the original closing date of 2006. Had this review taken place earlier, the project might have been able to achieve its outcomes earlier and at lower cost. Match ADB staff skills to specific project needs. When supporting the development of a new industry in a challenging environment, project administration needs to be particularly vigilant and carried out by ADB officers with strong expertise in the area. Stakeholders noted that the performance of ADB improved when staff had expertise in the microfinance sector and were actively involved in the implementation of the project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/microfinance-and-employment-project
Papua New Guinea: Rehabilitation of the Maritime Navigation Aids System Project | Papua New Guinea | Transport | 2011-07-31 | 1. Resident missions can play a pivotal role in rigorous project supervision by ensuring project implementation is on track and that ADB loan funds are fully used for the intended purposes within the planned loan closing date. Although the Papua New Guinea Resident Mission (PNRM) was formally established in 2003, which was almost midway in the implementation of Papua New Guinea's Rehabilitation of the Maritime Navigation Aids System Project, project completion report does not indicate whether PNRM support was sought for project supervision. Such support would have been helpful in expediting the consultant selection approval process, the award of contracts, and completion of the training program. [Main text, page 10] project cycle stage: Implementation Lesson Topics: 1. Resident missions can play a pivotal role in rigorous project supervision by ensuring project implementation is on track and that ADB loan funds are fully used for the intended purposes within the planned loan closing date. Although the Papua New Guinea Resident Mission (PNRM) was formally established in 2003, which was almost midway in the implementation of Papua New Guinea's Rehabilitation of the Maritime Navigation Aids System Project, project completion report does not indicate whether PNRM support was sought for project supervision. Such support would have been helpful in expediting the consultant selection approval process, the award of contracts, and completion of the training program. [Main text, page 10] project cycle stage: Implementation Lesson Topics: | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/papua-new-guinea-rehabilitation-maritime-navigation-aids-system-project
Financial Management Project | Papua New Guinea |  | 2010-09-01 | Executing agencies, ADB project officers, project consultants, and others must very carefully examine and assess the full range of possible impacts from a change of scope. Technically correct, evidence-based positions must prevail. ADB project supervision and guidance should match a project's complexity and challenges, especially in response to projects at risk. Particularly for a technically complex and nuanced area such as public financial management, ADB project officers should have strong relevant technical backgrounds. A project modality may not be the best approach to a process issue such as fostering improvements in a public financial management system. A combination of technical assistance (TA) and program lending or a sector development program may have been a more appropriate approach in bringing about improvements. If a project modality is used, financing plans should reflect the nature of the project inputs being financed. Although the project mobilized almost $25 million in grant parallel cofinancing, many of the international consultants were financed from the loan. | Project/Program Completion Reports (PCR) | Unsuccessful | http://wcm.adb.org/projects/documents/financial-management-project
Provincial Towns Water Supply and Sanitation Project | Papua New Guinea | Water and other urban infrastructure and services | 2010-09-01 | Inadequate project design undermines project implementation. Good project design is a basic requirement for project success, and inadequate design can prevent project success. In this case, design did not demonstrate adequate technical understanding of the availability of suitable water or the feasibility of its use for water supply and sanitation (WSS) projects in four of the six provincial towns. The cost estimates at appraisal, based on project preparatory technical assistance (PPTA), were too low, as actual costs were almost 225% higher than the appraisal estimate for the Wabag water supply subproject and 650% higher for the Madang sewerage subproject. The risk of the Australian Agency for International Development (AusAID) grant not being approved was not identified, and this curtailed capacity building in the Waterboard. Only priority sites should be surveyed at project design. Identifying a short list, not a long list, of priority sites before PPTA starts is good practice. Frequently, executing agencies in Papua New Guinea (PNG) do not identify priority sites or undertake preliminary analysis, citing their lack of preparatory budgets or skills. This does not foster ownership and passes on responsibility to consultants. In this case, PPTA consultants were asked to survey 12 provincial towns, out of which only 2 were ultimately developed. Inadequate preparatory work was done prior to project approval, causing high cost overruns and the need for re-design during implementation. ADB did not have the capacity to verify results from so many sites. Commitment from citizens in the form of willingness to pay and from governments in the form of investment, maintenance, and protecting assets from vandalism should be regarded as a part of future Waterboard investment decisions. The Waterboard should require an enforceable contract with provincial governments prior to new town investments. Targeting poor families with grant funds and low-cost technology makes good sense. The low cost sanitation and community awareness and health education (LC-CAHE) component was the most successful part of the project, despite cost overruns and reduced impact compared with the original targets. It combined low-cost infrastructure improvements with vitally needed information to improve awareness and understanding of the need for greater cleanliness and modern sanitation to improve public health. It also involved working with poor communities in a participatory manner to build commitment. It is a model that can be replicated at minimal cost in PNG and elsewhere in the Pacific. Lower-cost technologies have significant potential to improve public health. The very high cost of servicing small and isolated towns in PNG through reticulated WSS systems means that lower-cost alternatives should be considered. Water prices have risen and will rise further with the Independent Consumer and Competition Commission's (ICCC) regulatory contract with the Waterboard. This improves the commercial environment for the Waterboard, which it may be able to exploit if it can provide improved services more efficiently. However, water prices are unlikely to increase enough, even in the medium to long term, to financially justify reticulated WSS systems throughout urban PNG. Alternative models for providing WSS services should be considered that aim to alleviate capital constraints on reaching customers. The actual costs of reaching urban customers e.g., approximately $3,900 per user for the sewerage upgrade under the loan project in Madang, compared with $212 per user for septic tanks in Madang or $150 per user for ventilated improved pit latrines in the LCS-CAHE Program is evidence that far cheaper solutions are available. Alternative providers of these services, in competition with the Waterboard, should be encouraged if the Waterboard is unable to offer lower-cost alternatives. In Wabag, the investment cost of $6.3 million to serve 6,000 beneficiaries, at $1,050 per person, may be sustainable if all water supplied is paid for. Currently, only 29% of consumers pay their bills, a figure that is expected to significantly increase as the user-pays principle becomes established in Wabag. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/provincial-towns-water-supply-and-sanitation-project
Employment-Oriented Skills Development Project | Papua New Guinea |  | 2008-12-18 | 1. Major changes in implementation arrangements midway through project implementation had a destabilizing and delaying impact on the Project. Changes may be unavoidable, especially if they result from Government institutional restructuring. But implementation arrangements for such a challenging project as this, must be thoroughly considered and designed well in advance by completing policy dialogue on institutional arrangements (e.g., establishment of well represented steering/coordination committee) before a project commences than during implementation. [Main text, paras. 20, 28, 30, 43(i-ii)] project cycle stage: Design Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration 2. A detailed, well-considered sustainability plan is particularly important for institutionally complex projects such as this. A sustainability plan, prepared and adopted well before project completion, could help facilitate adequate funding and effective management of service delivery. The plan prepared under this skills development project, however, has yet to be approved. [Main text, paras. 38, 46(iii)] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Project management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/employment-oriented-skills-development-project
Public Service Program | Papua New Guinea |  | 2006-11-15 | It is difficult to get an appropriate balance between what is achievable as outputs and how they lead to broader impacts. Even if most specific loan conditions, performance indicators, and reporting requirements are relevant and satisfactorily met, the principles underlying their design may not be readily embraced. In part, this may simply be a question of time. Public sector reform is a complex and long-term undertaking. It depends on changing not only the rulesof the game and the systems that operate, but also the attitudes of stakeholders. Project experience demonstrated that it is unrealistic to expect for reforms to be embedded sufficiently in PNG's systems after only a year or two of serious reform effort. What was missing from the Public Service Program was a mechanism to continue to advocate for the principles underlying the tranche conditions after the tranche was withheld and the loan finally closed. [Main text, paras. 38-40, 46-47] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Loan Agreement: Covenants Monitoring & Evaluation: Indicators Project Design: Project design Project Management: Project reporting Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/public-service-program
Health Sector Development Program | Papua New Guinea | Health | 2004-10-15 | Alternate staffing arrangements should be introduced in project implementing units (PIUs), in cases when the project manager or project coordinators go on long leave, to ensure smooth project implementation. Alternates should have hands-on experience in administering projects, specifically those funded by ADB. project cycle stage: Design Lesson Topics: Project Management: Project administration Project Management: Project management Capacity Development: Human resources management Capacity building through the use of consultants varied largely depending on the area. The major problem was the availability of local counterparts and the continuity of their presence during the job. Too often they were transferred to other sectors after being trained. While this modality was very effective with the health health management information system (HMIS), due to the stability and leadership within themonitoring and research branch, the transfer of the senior finance officer trained in the Health Sector Development Program (HSDP) secretariat to another sector puts at risk the capacity built in this area by the attached technical assistance. project cycle stage: Appraisal Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Management information system Project Management: Risks/Risk management Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Health and sanitation management The choice of a quick-disbursing approach, with release of two large tranches was not adequate for the kind of reforms and support envisaged in the Health Sector Development Program (HSDP). This approach resulted in major difficulties between the Department of Treasury (DOT) and the National Department of Health (NDOH), with the latter not releasing funds as scheduled. The approach also did not allow ADB's close monitoring of the progress made during the program's entire life, as any leverage disappeared after the release of the second tranche. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management Policy & Reform: Reform The Health Sector Development Program (HSDP) established early on a policy of producing and disseminating information on as broad a basis as possible. The attention given to transparency and resolving issues raised through the monitoring process also served to underscore the importance of the monitoring and information process. The useful application of information in the management process is acquired through practice. Only when managers have acquired this skill is the costly exercise of producing information justified. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness The reform process underway in the National Department of Health (NDOH), with the assistance of an international accounting firm, also needs to be sustained. The progress to date is substantial, but a change in public service culture will require continued assistance and the progressive and active involvement of the relevant government support agencies, including the Auditor General's Office, Department of Finance, Department of Intergovernment Relations, Department of Personnel Management, and others. A public service culture change cannot occur in a sustainable manner in one government department alone. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Capacity Development: Capacity development Sector Related Issues: Health and sanitation management Policy & Reform: Public sector reform Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/health-sector-development-program-5
Fisheries Development Project | Papua New Guinea |  | 2003-12-15 | High-level political support is essential for successful institutional reform, but it isdifficult to secure. project cycle stage: Appraisal Lesson Topics: Capacity Development: Capacity development Capacity Development: Ownership Policy & Reform: Policy reforms/framework Institutional strengthening is a process, and should be reinforced periodically. Incorporation of funds to cover retrenchment costs is crucial in the successful implementation of institutional strengthening. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building Policy & Reform: Public sector reform Keep implementation arrangements simple. Project implementation must be flexible. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Project administration Project Management: Project management Methodologies/Approaches: Process approach When policy components are included, the process envisaged for incorporatingthe outcome of studies into policy development and introduction should be clear. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/fisheries-development-project
Third Urban Water Supply | Papua New Guinea | Water and Other Urban Infrastructure and Services | 2003-12-15 | 1. Readiness of essential cofinancing should be confirmed at project appraisal or loan negotiation to avoid implementation delays. project cycle stage: Appraisal Lesson Topics: 2. Land acquisition remains difficult and should be avoided or minimized. Whereland acquisition is required, the acquisition process - including compulsoryaction - should be initiated as early as possible. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Procurement 3. Comprehensive water connection programs should be developed and shouldinclude poorly served areas, businesses, and poor households. The programsneed maintenance, compliance and enforcement. An associated communityeducation and awareness program should be conducted to improve communityunderstanding of the benefits, availability of lifeline block supplies, value inunderstandable terms to them (e.g. a day's fishing or sales at the market),payment methods, and penalties on illegal connection. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Water resource management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Community approach 4. The government's initiative in developing a comprehensive Management Information System (MIS) will help continue to improve the Waterboard's operations and management. To achieve its potential and ensure its positive effect, however, the MIS needs to ensure that operational data and performance indicators are accurate and available in a timely manner to allow district managers to make necessary adjustments in O&M, connection programs, and local administration. project cycle stage: Implementation, Completion Operation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Project Management: Management information system Project Management: Operation and maintenance 5. A strong PMO and active involvement of Waterboard management was key to the project's success and should be incorporated into future projects. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project management Sector Related Issues: Water resource management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-urban-water-supply
Country Assistance Program Evaluation for Papua New Guinea (2003) | Papua New Guinea |  | 2003-09-30 | Country strategies were weak in translating the stated goals into an operational program. As a result, projects were often developed without keeping a strong link to the country-level goals, resulting in a piecemeal approach, where composite parts of essentially complementary program elements took place in isolation and without consideration to timing and sequencing. Choices made within sectors did not seem to follow strategic plans even though they were presented as sector strategies in country program papers. In turn, sector strategies (in country strategy documents) tended to summarize objectives of ongoing projects or those in the immediate pipeline. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Project Design: Problem identification Project Design: Project design Policy & Reform: Policy reforms/framework New approaches in project design and implementation are encouraging, although it is too early to assess how effective they may be. These changes include moving (i) from an insufficient understanding of local end-users' needs to greater end-user orientation; (ii) from generic ownership, based on national or sector policies, to stronger ownership by selecting project locations where commitment from provincial governments could be obtained; (iii) from providing physical infrastructure to a broader focus on sector reform and service delivery; (iv) from working through the public service, supply-side, to identifying alternative service providers; and (v) from assuming recurrent expenditure would be met from regular budget allocations to experimenting with alternative long-term funding arrangements. project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Capacity Development: Ownership Sector Related Issues: Private sector Sector Related Issues: Public-private partnership Policy & Reform: Reform Methodologies/Approaches: Civil Society Participation Sector choices seemed appropriate (matching country goals), although assisting with the reform of the machinery of government could have been recognized earlier as a key area for ADB involvement. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Public governance Modality: Program Policy & Reform: Public sector reform | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-papua-new-guinea-2003
Higher Education Project | Papua New Guinea | Education | 2002-12-13 | A monitoring mechanism together with baseline data must be identified duringproject appraisal to assess the project's progress and success. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Given the pivotal importance of the roles and preparedness of the executing agency, assessing the executing agency's capacity to implement a project is particularly important. The establishment of the Project Implementation Unit (PIU) and the appointment of the project manager and accountant must be made a condition of loan effectiveness. project cycle stage: Feasibility, Appraisal Lesson Topics: Loan Agreement: Loan Agreement Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Human resources management In the design of education projects for small nations such as island nations, thelikelihood of inadequate institutional capacity, political interference, weakmanagement, budgetary cuts, and longer implementation periods must be takeninto account. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design Capacity Development: Capacity assessment Sector Related Issues: Education The availability of counterpart staff for the project should be determined duringproject appraisal and suitable people should be identified to avoid delays andensure the transfer of technology. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Technology/Technology transfer The incorporation of more frequent reviews, including quarterly and midtermreviews by both the government and ADB, seems to be critical in situations wherethe availability of counterpart funds and staff is likely to be limited. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Human resources management The number of consultants should match the availability of counterpart staff andthe country's absorptive capacity. A large number of short-term consultantsimposes a heavy administrative, logistical, and counterpart staff burden on aninexperienced Project Implementation Unit (PIU). Long-term consultants are better placed to provide continuityin ideas and assistance to counterpart staff, who would then be required insmaller and more manageable numbers and be available for a longer period tohelp digest reports. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Human resources management The provision of a long-term consultant team leader to coordinate the inputs andoutputs of a large number of consultants is vital to assure continuity andcoordination and preserve institutional memory. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Consultants Methodologies/Approaches: Consultation/Participation The timely provision of counterpart funds is critical for the speedy implementationof any project. Ways must be found to ensure that adequate funds are set asideunder the project. project cycle stage: Appraisal Lesson Topics: Unlike construction and consultancy components, which are administered in thecountry and can therefore be more easily monitored and coordinated, overseasstaff development programs do not lend themselves to easy monitoring andcoordination because they involve people with careers, families, and financialresponsibilities who have to adjust to the educational, cultural, and otherdemands of foreign universities. About 30% more time should be added to theperiod for studies abroad compared to studies in the home country. project cycle stage: Feasibility, Appraisal Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants Capacity Development: Capacity building Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/higher-education-project
Transport Infrastructure Development Project | Papua New Guinea | Transport | 2002-12-13 | Flexibility of scope changes or loan extensions during implementation can behelpful, but in the face of persistent failure to meet targets, firm action should beconsidered. Unless the causes of failure can be resolved promptly, the projectshould be reviewed thoroughly and, if warranted, fundamentally redesigned. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project administration Methodologies/Approaches: Process approach Methodologies/Approaches: Targeting It is best to limit the size and scope of a project to manageable proportions, taking into account the capacity and resources of the recipient government and executing agencies. To find the right match between needs and capabilities, it is also advisable to allow more time in designing future projects. It is better to err on the side of too much project preparation than too little. Project design ï¿½on the jobï¿½ may suffice if the engineer is knowledgeable and experienced, but the money saved can be lost many times over if, for example, the work done is washed away in the first flood. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Country Context: Emergency Systematic monitoring of the execution of routine maintenance is essential.There is a need for independent inspectors to perform technical audits ofmaintenance, and there should be a financial audit to make sure that physicaloutputs are commensurate with the inputs. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting Monitoring & Evaluation: Monitoring and evaluation Project Management: Operation and maintenance There are no shortcuts in project monitoring. Active project administration and close monitoring should be stressed. Field visits to inspect the physical progress are essential, not optional. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration When there are problems in maintaining existing infrastructure, lending money for projects that add to the maintenance load without first addressing existing problems must be thoroughly reviewed and debated. Loans to cover recurrent costs are not a good practice. Serious consideration should therefore be given to lending money for routine maintenance, or indeedfor all maintenance, including rehabilitation. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Problem identification Project Design: Project design Project Management: Operation and maintenance | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/transport-infrastructure-development-project
Population and Family Planning Project | Papua New Guinea | Health | 2002-07-15 | Outcomes depend a lot on the performance of consultants. This has been obviousduring the project, but it is often difficult to evaluate before recruitment. Progress has to bemade in linking performance to remuneration. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Capacity Development: Human resources management The accounting function is chronically weak in the public sector in Papua New Guinea. As a result, project design should routinely provide for a private accountant. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial reporting Project Design: Project design Project Management: Executing/Implementing agencies The complexity built into the project has been a major obstacle to its implementation.The manageability of projects must be carefully assessed at the design stage. Given the limitedcapacity of executing agencies, the lesson is to avoid involvement inmultidonor/multiagency projects. Practically, the executing agency has moved toward the sector-wide approachwith the first step taken by the Health Sector Development Program. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity assessment Sector Related Issues: Health and sanitation management Methodologies/Approaches: Sectoral approach The impact of the project could have been much more significant had the appropriategovernment counterparts been identified in the design and stayed in place throughout the life ofthe project. This encompasses the overseas training provided under the project, as takinggovernment personnel away from their posts for extended periods which exacerbates operationaldifficulties experienced when officers are absent from their duty stations. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Impact evaluation Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/population-and-family-planning-project
Agriculture Sector Program (Loans 997[SF]/998-PNG) | Papua New Guinea | Agriculture, Natural Resources, and Rural Development | 2001-07-31 | Most inadequacies of the program stem from design. Lack of a program preparatory TA and detailed sector analysis or analytical study of policy reform impacts resulted in a program inadequately tailored to the needs of the sector. Hence, the program promoted, by and large, continued existing or planned policies and programs of government that were well known to have been ineffective. The output and recommendations of the related TAs ideally should have been available at or soon after the design stage. The program should have had a much longer implementation period, accompanied by three tranches rather than two, and should have been stipulated to achieve institutional change in a country with known poor implementation and absorptive capacity. The more recent ADB-financed Smallholder Support Services Pilot Project builds more fully on experience with the program by having a longer implementation period, explicitly involving decentralized institutions, and trying a new approach to extension services. project cycle stage: Feasibility Lesson Topics: Modality: Program Modality: Technical Assistance Monitoring & Evaluation: Impact evaluation Project Design: Project design Capacity Development: Capacity development Country Context: Decentralization Sector Related Issues: Extension service Policy & Reform: Policy reforms/framework There was little effort during the program design period to build a sense of local ownership through consultations with the primary stakeholders, smallholder treecrop farmers. The multiple objectives of the program may also have affected the feeling of local ownership. Due to the financial crisis at the time, the inflow of foreign exchange was the main concern of the nominated implementing agencies. Their main interest was in expediting disbursement. It is also notable that ADB ceased supervision after the release of the second tranche, although the program provided for program benefit monitoring and evaluation during 1989-1996. Annual benefit monitoring and evaluation reports, if any, could not be found. The large number of activities supported by the counterpart funds would have made it impractical for ADB supervision staff to effectively monitor them. The effectiveness of the institutional strengthening elements of the program depended on the implementing agency (Department of Agriculture and Livestock), which appears to have had little involvement in design, other than planning the Public InvestmentProgram (PIP) projects to be supported by counterpart funds. This may have contributed in particular to the ineffectiveness of the TAs. A program with a narrower focus and involving less implementing agencies would have permitted better management and supervision. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Counterpart funds Modality: Technical Assistance Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project Management: Project management Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Ownership Country Context: Crisis/Post-crisis Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Program Approach | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/agriculture-sector-program-loans-997sf-998-png
East New Britain Smallholder Development Project (Loans 852/853[SF]-PNG) | Papua New Guinea | Agriculture, Natural Resources, and Rural Development | 1999-09-30 | ADB should have had a better assessment and knowledge of the limited capacity of the implementing agencies to coordinate and manage the project as designed. The EA's capability to implement the project needs to be established at appraisal so as to avoid implementation delay. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Capacity Development: Institutional analysis Although there was no social assessment at appraisal, the simple project design turned out to fit in well with the sociocultural conditions of the local community (farmers). However, the project confirms the need to conduct a detailed social assessment at the project preparatory stage in accordance with ADB requirements before deciding on the appropriate project design and approach. project cycle stage: Feasibility Lesson Topics: Project Design: Appraisal Project Design: Project design Country Context: Cultural constraints In the absence of clear guidelines on the criteria for project beneficiary selection at the time of appraisal, the project management committee had a free hand in the selection process. Thus, the beneficiaries selected may not have been the most needy farmers. The criteria for project beneficiary selection should be mandatory for allprojects. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Sector Related Issues: Rural development | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/east-new-britain-smallholder-development-project-loans-852853sf-png
West New Britain Smallholder Development Project (Loans 784[SF]/785-PNG) | Papua New Guinea | Agriculture, Natural Resources, and Rural Development | 1999-09-30 | A more extensive examination of the social environment in the project area at appraisal will ensure that all affected people are considered and problems arising from social conflicts, particularly settlement problems, could be averted if not eliminated. Although the project design fitted well into the sociocultural conditions of the communities without carrying out a social assessment, this confirms the importance of requiring social assessment at the formulation stage. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Country Context: Cultural constraints Project experience underscored the need for private sector support in the areas of processing and marketing for smallholder oil palm development. In cases where government support services are weak and where smallholder credit is not readily available, participation of the private sector nucleus estates is key to ensure that the project is successful and that project benefits are optimized and sustained. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Sector Related Issues: Extension service Sector Related Issues: Private sector Sector Related Issues: Rural development Project experience underscored the need to conduct a detailed assessment of the EA s capacity to implement the project. In cases where the EA is weak, institutional strengthening measures should be carried out to ensure that the project commences as scheduled and that the EA staff are familiar with the ADB s tendering and procurement procedures to avoid undue delay during the project start-up phase. project cycle stage: Design, Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity assessment Capacity Development: Capacity building The decision to transfer project management from the executing agency (EA) to another government agency following an assessment early on during implementation that the EA exhibited weaknesses in its administrative setup, proved to be an appropriate and beneficial move for the project. The ability of project management to shift emphasis to oil palm planting by village farmers and to convince the nucleus estates to supplement and to provide credit for new oil palm planting contributed to the success of the project. Flexibility in project management is a major factor for effective implementation. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity assessment Sector Related Issues: Rural development Methodologies/Approaches: Process approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/west-new-britain-smallholder-development-project-loans-784sf785-png
Fourth Road Improvement (Sector) Project (Loans 690/691-PNG [SF]) | Papua New Guinea | Transport | 1998-01-31 | Project appraisal teams should carefully review implementation schedules to ensure they are realistic. In this case, the project implementation schedule at appraisal was not realistic, and this was exacerbated by the poor performance of the EAs. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies The failure of the government to enforce axle load and vehicle dimensions can seriously affect the sustainability of the project roads. ADB needs to review how it can enforce compliance with important loan covenants that have a direct and important impact on the likely success of the project. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Loan Agreement: Covenants Project Design: Project design Sector Related Issues: Roading The need remains for a more systematic approach to assessing the environment for capacity building prior to providing technical assistance. The capacity of EAs for timely handling of procurement and submissions of audited accounts needs to be carefully assessed at the time of project appraisal. In addition to procedural advice on procurement, ADB needs to support the improvement of the national tender process and conduct additional procurement workshops on ADB guidelines for the guidance of future processing efforts. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Capacity Development: Capacity building Capacity Development: Institutional analysis | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/fourth-road-improvement-sector-project-loans-690691-png-sf
Ports Development Project (Loan 738-PNG) | Papua New Guinea | Transport | 1997-09-30 | The benefits of packaging comparatively small projects at a number of different ports into a contract size that will attract international bidders need to be considered in the context of the potential delays that can result in the construction program at one port due to delays at another. project cycle stage: Feasibility Lesson Topics: Project Management: Procurement Sector Related Issues: Transport planning The difficulties encountered with the Port MIS illustrate the importance of having adequate management training and postdevelopment technical support in TAs involving computer systems. project cycle stage: Operation Lesson Topics: Modality: Technical Assistance Project Management: Management information system Capacity Development: Capacity building The need to mobilize construction equipment, labor, and materials to remote ports makes project cost estimation difficult. Higher than usual contingency amounts may be allowed in such circumstances. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Transport planning The success of the Port Moresby component of the project demonstrates the importance of matching yard capacity to berth capacity and the significant increases in capacity that can be achieved through a relatively modest investment in yard facilities when there is a shortfall in these. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/ports-development-project-loan-738-png
Institutional Strengthening of Agriculture Bank of Papua New Guinea | Papua New Guinea | Industry and Trade | 1996-12-31 | The importance of having the resolve and commitment of the government to a TA and its findings emerged from this TA. At the time the TA was being formulated, it would have been appropriate to have had some indication from the government that it was indeed prepared to provide greater autonomy to the executing agency, to undertake the necessary financial restructuring, and to liberalize interest rates. project cycle stage: Feasibility, Implementation, Operation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Ownership Policy & Reform: Reform | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/institutional-strengthening-agriculture-bank-papua-new-guinea
Advisory Technical Assistance to Selected Development Finance Institutions in Pacific Developing Member Countries | Papua New Guinea, Samoa, Vanuatu | Finance | 2001-12-31 | Governments should maintain existing or envisioned critical institutional arrangements to ensure that the capacity built by TAs is put to good use to sustain benefits. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Capacity Development: Capacity building TA designs should be flexible to permit midcourse adjustments in scope and implementation arrangements to enhance efficiency of TA implementation and optimize outputs. project cycle stage: Design, Implementation Lesson Topics: Modality: Technical Assistance Methodologies/Approaches: Process approach There is a need for upfront government commitment or action on required policy changes as a condition of TA approval where the problems of a DFI are well known and where their resolution depends on such action. Relatedly, TA outputs conditioned on or leading to policy change should be produced at an early stage of TA implementation. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Appraisal Project Management: Executing/Implementing agencies Policy & Reform: Policy reforms/framework | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/advisory-technical-assistance-selected-development-finance-institutions-pacific-developing
Rural Community-Based Renewable Energy Development in Mindanao: Technical Assistance Completion Report | Philippines | Energy, Finance | 2016-05-01 | As per project experience, the role of the LGUs (local government units) was very significant during implementation but which was not identified at the initial concept stage of the TA (technical assistance). LGUs' roles were fundamental and essential to the overall TA implementation such as processing of permits, certifications, clearance for security, National Commission on Indigenous Peoples (NCIP) related processes and the turnover of the project. It is therefore imperative to identify a key agency to take the lead in implementing projects at the initial stage. Project cycle stage: Concept, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/phi-rural-community-based-renewable-energy-dev-mindanao-tcr
Strategic Policy Actions for Successful Structural Transformation and Inclusive Growth: Technical Assistance Completion Report | Philippines | Industry and trade | 2015-07-01 | The TA (technical assistance) had strong implementation links to a prior technical assistance, but the approach was not flexible enough to allow for changes in TA team leadership, since the output desired was of a highly technical and specific nature. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/strategic-policy-actions-successful-structural-transformation-and-inclusive-growth-tcr
Philippine Energy Efficiency Project: Completion Report | Philippines | Energy | 2015-06-26 | Stakeholder analysis and detailed consultation are very important for pioneering projects like this one. Ownership by stakeholders is at risk if project implementation requirements are insufficiently analyzed, and if the institutional environment and human resource capacity is inadequate. This was the first ADB loan to be implemented by DOE (Department of Energy), and it became apparent early on that it was not familiar with ADB procedures, especially on procurement matters and engagement of consultants, which led to project delays. project cycle stage: Design, Implementation Projects implemented in a period when a change in government is foreseeable will undergo reevaluation and review by the new administration. If the core PMU (project management unit) team has a strong foundation and capacity to implement the project, and is seen to be politically impartial, the risk of changes to leadership and possibly even decisions can be mitigated. To have an efficient PMU, project monitoring needs to be programmed and reviewed regularly during implementation to ensure that the executing agency has sufficient staff and counterpart budget. project cycle stage: Design, Appraisal, Implementation Project cost estimates need to factor in all duties and taxes, not only on machinery and equipment but also on service providers. Assessments of banking rules and the government's budget implementation process are also needed. project cycle stage: Feasibility, Appraisal, Implementation Market development of efficient lighting was very fast. Midway through the distribution of CFLs (compact fluorescent lamp) (subcomponent 1.2) the scale had to be pared back because market penetration of the technology had greatly improved. project cycle stage: Implementation In projects of this kind, the technical complexities of the equipment and the specialized nature of the works or services to be procured need to be considered when estimating the procurement period. project cycle stage: Design, Implementation The time provided to establish and operationalize the Super ESCO (energy service company) was not sufficient. The existing policy environment, particularly for government budgeting and accounting, does not support the ESCO concept of an energy performance contract (EPC). The environment needs to be adjusted first to enable implementation of ESCO projects in the public sector. project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/philippine-energy-efficiency-project-pcr
Design of a Pilot Project to Improve Environmental Conditions of Estero de Paco: Technical Assistance Completion Report | Philippines | Water and Other Urban Infrastructure and Services | 2015-06-01 | The ToR (terms of reference) formulation was adequate and pilot Project implementation inclusion on the TA (technical assistance) a success. Data and information delivered by some stakeholders was however contradictory due to institutional conflict of interests. Governance remains a challenge, policies establishment, inter-agencies' monitoring and coordination should be improved. project cycle stage: Design, Implementation, Operation The Pilot project fulfilled five conditions: it (i) included significant unconnected/improperly connected households with sewage reaching the estero; (ii) showed the proposed solution replicability; (iii) had a manageable construction cost and low maintenance cost; (iv) was built in an area where structures were consistent with PRRC (Pasig River Rehabilitation Commission) and Local Government Unit (LGU) plans and (v) proper construction aftercare implemented to avoid sewers clogging. project cycle stage: Implementation, Completion, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/design-pilot-project-improve-environmental-conditions-estero-de-paco-tcr
Davao Sustainable Urban Transport Project: Technical Assistance Completion Report | Philippines | Transport | 2015-05-01 | The relationship of central and local government could have been better. It was difficult to ensure central government participation at key events during the meetings in the city. The role and agreement of the Mayor was of vital importance in this case. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/davao-sustainable-urban-transport-project-tcr
Consumer Protection in a Competitive Electricity Market with Open Access: Technical Assistance Completion Report | Philippines | Energy | 2015-04-01 | The TA (technical assistance) preceded the RCOA (retail competition with open access) which commenced in June 2013 and thus addressed only the first step of RCOA implementation covering about 909 large customers with electricity demand of at least 1 MW. ERC (Energy Regulatory Commission) has yet to announce the next steps for customer thresholds of 750 kWh to 1 MW and RCOA to residential customers is unlikely to happen before 2017. The large consumers were not the intended beneficiaries of the TA. The consumer groups engaged under this TA which represented the small residential consumers were interested to engage in the wider debate about EPIRA (Philippine Electric Power Industry Reform Act ), which was outside the scope of the TA. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/consumer-protection-competitive-electricity-market-with-open-access-tcr
Health Sector Development Program | Philippines | Health | 2014-08-01 | Health Sector Development Program supported the entire Health Sector Reform Agenda, with six reform areas, a large number of stakeholders, multiple levels, and intervening policy alterations, making it a complex undertaking. However, the government reported that ADB's support for the entire reform program helped advance reforms. Nevertheless, careful consideration should be given to the scope of program support. A high on-lending rate prevented the targeted provinces from participating. At appraisal, careful consideration needs to be given to the project's financial feasibility. Limited project funds could finance only about 30% of required investments in targeted health facilities. Although additional funding was mobilized to complete upgrading of these facilities, more detailed advanced planning could mitigate financing risks. Design flaws resulted from the rehabilitation of existing facilities. Budget constraints may have led to the use of substandard materials. Some equipment was purchased that did not meet technical specifications. Further improvements can be made by improving specifications, adequately budgeting for works and equipment, and ensuring proper commissioning. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/health-sector-development-program-pcr
Local Government Financing and Budget Reform Program Cluster | Philippines | Public Sector Management | 2013-03-01 | Local government reform is a complex undertaking, involving major changes in the regulatory framework, institutional arrangements, supporting infrastructure, and human capacity. It also requires a long-term perspective in both design and implementation. Thus, the government?s continuous commitment to reform, its ownership of the program, and collaborative support by the donor community are all necessary elements in designing local government reform through a programmatic approach. The Local Government Financing and Budget Reform program cluster shows that ADB, through continuous dialogue with the government and collaborative financing with other donors, was able to develop a well-designed program that is sufficiently demand driven. Substantial reforms were accomplished, which laid a stronger foundation for achieving the program's objective of more effective delivery of key government services at the local level. The program's success and likely sustainability can be attributed also to the technical assistance activities undertaken during implementation, which have strengthened the capacity of local officials in carrying out reforms. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/local-government-financing-and-budget-reform-program-cluster-pcr
Financial Market Regulation and Intermediation Program | Philippines | Finance | 2013-02-09 | 1. Programs and technical assistance should not depend on passage of law in countries where legislative processes are slow and cumbersome. In this case, reforms to the bank resolution process, such as the authorization of bridge banking powers for Philippine Deposit Insurance Corporation, rely on the passage of legislation, and are still pending. The administrative increase in minimum capital requirements for the insurance subsector was embroiled in controversy and delay, but now appears to be required by law, but only following a 7-year delay. Therefore, where legal amendments are necessary or can make reforms more sustainable, programs and technical assistance should support drafting of legislation, but also enhance the regulatory framework that complements legislative changes. project cycle stage: Lesson Topics: 2. There should be strong and widespread political will. For example, the Capital Market Development Plan was initiated unilaterally by the Securities and Exchange Commission and clearly was not reflective of industry sentiment and therefore did not enjoy widespread support. In the case of the Office of the Insurance Commission, pressure from the industry to postpone higher required capitalization contributed to a change in the Insurance Commissioner and a reduction in political will in support of reform. However, the pace of program implementation and reforms accelerated significantly under the new government. A new capital market development plan was launched, under the close leadership of the Ministry of Finance (MOF), which benefited from widespread stakeholder consultations and support. Likewise, increased capital standards have been applied legislatively to the insurance sector with strong MOF support. project cycle stage: Lesson Topics: 3. Program design should focus on mplementing reforms not only where commitment is strong, but where resources and external factors are adequate to ensure successful implementation. In the case of the Securities and Exchange Commission (SEC), a persistent and chronic shortage of funding initially compromised its ability to provide effective surveillance and supervision to the capital markets. Additional budget increases still appear necessary to bring Office of the Insurance Commission and SEC remuneration in line with the Bangko Sentral ng Pilipinas, as mandated by Republic Act No. 8799 and Republic Act No. 9829. Further, until enforcement officials are sufficiently protected from frivolous and intimidating lawsuits, expectations of strong enforcement actions may be unrealistic. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/financial-market-regulation-and-intermediation-program-philippines-pcr
Philippines: Technical Education and Skills Development Project and Fund for Technical Education and Skills Development | Philippines | Education | 2012-12-27 | Aid agencies need to make the criteria for their support clear to the government counterpart, while understanding why the government is seeking assistance in the first place. In the case of Danish International Development Agency (Danida), they held the funding as they wanted Technical Education and Skills Development Authority (TESDA) to (i) receive an adequate budget allocation, and (ii) seek reimbursement from Danida after spending their own budgetary resources. However, the government had a budget problem. Danida spent 2 years trying to encourage the budget allocation for TESDA, but that did not happen. Danida eventually canceled their portion after 2 years. [Main text, para. 29] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Harmonization Finance & Financial Aspects: Counterpart funds Loan Agreement: Covenants Loan Agreement: Loan Agreement | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/philippines-technical-education-and-skills-development-project-and-fund-technical-educatio
Philippines: Power Sector Development Program | Philippines | Energy | 2012-12-17 | While cluster program designs provide the benefit of flexibility (i.e., deferring subprograms wherein the program design cannot be fully defined at appraisal), care must be taken to maximize the achievement of critical objectives even if ongoing subprograms are canceled. [Main text, para. 23] project cycle stage: Design Lesson Topics: | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/philippines-power-sector-development-program
Infrastructure for Rural Productivity Enhancement Sector Project | Philippines | Agriculture, natural resources and rural development | 2012-11-01 | The project demonstrated that successful local government unit (LGU)-led, demand-driven, decentralized implementation is a viable delivery mechanism for the planning, development, and management of rural infrastructure. Examination of the reasons for the delayed start yield valuable lessons for future projects. The primary lesson is that advance action needs to be commenced prior to loan approval as regards (i) shared understanding that Guidelines on the Use of Consultants by ADB and Its Borrowers must be followed for ADB-funded consulting engagements; (ii) commitment and establishment of the project management framework, including recruitment of key personnel; (iii) agreement and commitment at all levels to an effective funds disbursement mechanism; (iv) familiarization with project management actions and procedures; and (v) preparation of a long list of LGU identified subprojects. Advance preparation of subproject long lists will assist in evaluating LGU capabilities and capacity to participate in future projects. In preparing subproject lists for future projects, consideration should be given to agribusiness development zones as a basis for future planning, such that infrastructure and value chain improvements are designed on a regional basis rather than being geographically scattered. Future projects should consider sizing project area coverage in relation to executing agency resources. Consideration should be given also to advance preparation of broader-scale agricultural intensification plans (AIPs). Placing support teams, including consultants, in the regions and zonal project offices is critical to providing LGUs guidance and technical assistance when and where needed. Careful consideration is required regarding the relative mix between executing agency personnel and consultants to ensure the executing agencies are adequately resourced with the appropriate technical skills so as to retain project experience within the agency after a project is completed. Slow funds liquidation results in inadequate funds availability, slowing implementation. Future projects should ensure that seamless, efficient, and simple funds disbursement processes are established that satisfy appropriate procurement and financial audit requirements. Future projects should consider (i) direct payment of contractors by ADB; (ii) making imprest account levels appropriate to the funds flows anticipated; and (iii) simplified disbursement procedures and documentation requirements, preferably through the executing agency. The project has highlighted the need to provide ongoing operation and maintenance (O&M) capacity building support and to monitor actual O&M implementation after loan closure. Future projects should incorporate provision for executing agencies to establish O&M technical support teams conducting biannual infrastructure O&M inspections and providing ongoing training to LGUs on O&M practices after project completion. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/infrastructure-rural-productivity-enhancement-sector-project-pcr
Electricity Market and Transmission Development Project | Philippines | Energy | 2012-03-01 | 1. As the wholesale electricity spot market (WESM) is new in the Philippines, the market operator should have worked earlier to develop training programs to educate the market participants in the operation of WESM, as the success of the WESM depends on the readiness of all the market participants. The market operator should have taken proactive measures as to the training needs of the market participants - avoiding unnecessary delays in the launching of the WESM. project cycle stage: Lesson Topics: 2. The protracted procurement process for the transmission line and substation components was one of the main reasons for the delay in the completion of this part. If there had been closer consultation between ADB and Transco, issues could have been addressed as early as possible to avoid delays. ADB could have regularly monitored with Transco the progress and issues encountered during the procurement stage. This would have triggered Transco's actions, in a timely manner, on the issues encountered. Transco should have assigned dedicated full-time staff to handle bid evaluations and could have shortened its approval process. project cycle stage: Lesson Topics: 3. The separate procurements for the supply (funded by Japan Bank for International Cooperation) and installation (funded by Transco) of the substation equipment for the Mindanao substation expansion delayed its implementation. Turnkey contracts could have reduced the implementation delays of this component, as there would have been only one procurement package. project cycle stage: Lesson Topics: 4. Right-of-way (ROW) acquisition was another main cause of delay in the completion of Part B. The project's ROW staff should have dedicatedly followed the project implementation schedule. Transco committed to ADB that the ROW for the transmission lines would be acquired and paid for prior to the commencement of works, but this did not fully happen. The works were stopped because of ROW issues and some project-affected families allege that they have yet to receive complete payment. project cycle stage: Lesson Topics: 5. The social engineering group which undertook the meetings and consultations with the affected people should have conducted initial assessment of strategies used in improving affected people's awareness on matters of compensation and resettlement. Improvements could have minimized the instances of claims on lack of knowledge of the process of property valuation. An affected person who understands what the impact of the project will be and knows the willingness of the project proponent to mitigate adverse impacts will result to increased level of his/her cooperation and acceptance. project cycle stage: Lesson Topics: 6. While ADB policy as well as the LARP clearly outlined the steps to take in cases of complaints, actual setting up of the institutional arrangements was overlooked. Disputes on inventory and valuation of property lost indeed slowed down implementation of compensation and resettlement. A strong and working grievance redress committee results to quicker resolution of issues brought up by the affected people. The social engineering and right-of-way clearing units following due diligence in conflict resolution will be credited for the timely receipt of assistance of affected people. project cycle stage: Lesson Topics: 7. Affected people knew that their property and livelihood will be affected because of transmission towers and lines that will be set-up. However, the broader project objective of propelling progress and development (through more energy supplied in the region) if communicated effectively can result to better appreciation of the project. The few affected people who have expressed apprehension, as well as those local government units which still refused to cooperate may in the end offer more positive attitude in doing their share to achieve the goals of the project. project cycle stage: Lesson Topics: 8. While the project as stated in the land acquisition and resettlement plan recognizes the importance of active participation of the different local stakeholders, the municipal, and barangay local government units (LGUs) have largely been credited only on organizing consultation meetings between Transco and the affected people. LGUs could have been likewise tapped as information disseminators and the ?first line of troubleshooters? in instances of grievance. When Transco completed the project and left the project area, it is after all the LGU that is left and is expected to continually address the needs of affected people. project cycle stage: Lesson Topics: 9. The external monitoring group may have to be on board early on the land acquisition and resettlement plan (LARP) implementation. This is to allow sufficient time for the group doing the electricity market to understand the project and the LARP. Due to the highly specialized task of external monitoring group, it is true that not many groups such as those in the academe or non-government organization have actual experience doing the task. The group would need more time to study the issues, and come up with recommendations that can still be incorporated in the on-going process of assisting affected people. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/electricity-market-and-transmission-development-project
Philippines: Bukidnon Integrated Area Development Project | Philippines | Agriculture, Natural Resources, and Rural Development | 2011-12-01 | 1. The financial impact of projects on local governments needs to be ascertained at project preparation to ensure that these can meet their financial obligations. For example, it would have been clear that the Bukidnon Integrated Area Development Project in the Philippines could not have met the financial requirements of the projectï¿½to invest $12 million of its own resources, and to pay high interest on $14 million borrowed from Mindanao Development Fund. Unless viable options are found to fund local investments, a project of this type should not proceed. [Main text, para. 23] project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Country Context: political economy factors | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/philippines-bukidnon-integrated-area-development-project
Philippines: Secondary Education Development and Improvement Project | Philippines | Education | 2011-12-01 | 1. More innovative cost sharing arrangements need to be developed so that poor local government units (LGUs) are not hindered from participating in programs that require counterpart equity. Under the Secondary Education Development and Improvement Project in the Philippines, LGU involvement was incorporated into the school building program to promote partnership with local stakeholders. The program required LGUs to provide 25% of the construction costs for the required school facilities. Unfortunately, most participating LGUs found it difficult to provide equity funds which led to postponed construction. [PVR Main text, para. 21; see also PCR Main text, para. 21] project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Counterpart funds Sector Related Issues: Education | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/philippines-secondary-education-development-and-improvement-project
Countercyclical Support | Philippines | Public sector management | 2011-10-01 | Based on this performance evaluation there are three lessons. First, efficient public financial management (PFM) systems are important to ensure timely disbursements. While the Philippines has made progress in PFM reform, it clearly needs to do much more to address the low disbursement rates typical in the first semester of each year. Measures implemented in 2009 helped to improve disbursements. The government is addressing these and in February 2011 announced its PFM roadmap. Second, the Philippines budget does not have automatic stabilizers that would allow for stronger countercyclical spending. The Conditional Cash Transfer (CCT) program could become an automatic stabilizer. The Comprehensive Livelihood and Emergency Employment Program (CLEEP) was successful in boosting temporary employment in 2009. However, it is unknown to what extent CLEEP displaced workers. The government should consider reviewing lessons learned from CLEEP and look at the feasibility of converting it into a minimum employment guarantee scheme (MEGS) that could be scaled up in subnational regions during economic and or natural disasters. Third, the fiscal stimulus package was successful because it included a mix of measuresï¿½social spending and labor intensive, small- scale infrastructure projectsï¿½and because effective and regular monitoring and reporting mechanisms were in place. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/countercyclical-support
Southern Philippines Irrigation Sector Project | Philippines | Agriculture, natural resources and rural development | 2011-10-01 | Participation of beneficiaries at an early stage of subproject preparation will enhance the chance of success where beneficiaries are to assume control of operation and maintenance (O&M). Beneficiary contributions must be set at a level that reflects their capacity to pay, and it is considered inappropriate to overload farmers with higher costs where poverty remains an issue. Quality subproject feasibility and detailed engineering designs, based on solid geological and topographic surveys, are necessary prerequisites to successful irrigation and road subprojects. Without these, unachievable targets will be established that cause subprojects to be assessed less successful. The role of local government units must be understood, given their limited resources and their primary function as a political institution. While they remain an important inclusion from a lobbying perspective, they cannot adopt roles beyond the level for which they have human and financial resource capacity. Further capacity building must be undertaken in procurement and bid evaluation if provincial and regional procurement is to be continued in similar future projects. While there is a certain autonomy in regional centers, the central government and ADB should adopt a stronger procurement monitoring role, if only to prevent repetition of previous mistakes. A realistic evaluation of institutional capacities is needed during project preparation for the tasks expected of them. This is particularly important with the proposed downsizing of the NIA that is currently taking place. Stronger links with technical support and input supplies such as credit should be part of the training of irrigator associations during subproject implementation. While attempts at coordinating technical support were envisaged, much of this came down to personal relationships, and that varied widely between subprojects. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/southern-philippines-irrigation-sector-project
Philippines: Mindanao Basic Urban Services Sector Project | Philippines | Transport, Water and Other Urban Infrastructure and Services | 2011-09-30 | 1. There is a need for improved and expeditious processing of approvals both within ADB business processes and within the government to avoid delays to approval of variation requests and other procurement matters. project cycle stage: Appraisal Implementation Lesson Topics: Capacity Development: Capacity development Capacity Development: Institutional analysis | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/philippines-mindanao-basic-urban-services-sector-project
Philippines: Metropolitan Waterworks and Sewerage System New Water Source Development Project | Philippines | Water and Other Urban Infrastructure and Services | 2011-07-31 | 1. To identify potential sector programming issues, ADB needs to actively engage with other development partners' on their investment plans prior to or in the early stage of loan implementation and match its own comparative advantage in offering assistance to a DMC. In the case of the Angat Water Utilization and Aqueduct Improvement Project in the Philippines where, instead of pursuing the ADB multitranche financing facility, the government opted for a loan from the Government of the People's Republic of China. The government deal with many official development assistance partners, and there are grants and loans with better conditions than ADB loans. While the project team insists that the government decision to change its funding source was unexpected, through project documents, the validation report did not find significant evidence suggesting that ADB actively explored other development partners' investment plans in the sector, prior to or in the early stage of the loan implementation, nor did it assess its own comparative advantage in offering its assistance to the Philippine development assistance environment in the water sector. A master plan for water resource development in each river basin including careful assessment of conflicting responsibilities for regulation, extraction, and approval in the sector is needed for future ADB engagement. [Main text, page 5] project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Sector Related Issues: Water resource management | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/philippines-metropolitan-waterworks-and-sewerage-system-new-water-source-development-proje
Development of Poor Urban Communities Sector Project | Philippines | Water and other urban infrastructure and services | 2011-02-05 | 1. Local government units (LGUs) are important as facilitators of housing projects, but should not be overburdened with housing production or housing loans. LGU-driven projects are important and strategic for targeting the urban poor. LGUs can have a crucial role in provision of land, particularly land that has been proclaimed by the President of the Philippines for social housing purposes. However, there needs to be additional innovation to make the urban poor bankable. Home Development Mutual Fund (HDMF) lending needs to open up to LGU-initiated socialized housing projects, even if they are for nonHDMF members. In order to serve the urban poor, LGUs need to innovate and provide guarantee funds (guaranteed by the internal revenue allotment or other forms of collateral) for HDMF lending operations to the urban poor. In addition, the implementation of socialized housing projects needs to make use of microfinance institution collection practices. project cycle stage: Lesson Topics: 2. Private sector developers need to be motivated to prefinance and build social housing schemes. The private sector modality does work if established in tandem with a take-out mechanism from Home Development Mutual Fund (HDMF). While the private sector will only require short-term loans during the construction period (until a scheme is fully sold), it relies on a separate financing mechanism through HMDF or similar other arrangements. project cycle stage: Lesson Topics: 3. A bigger role for nongovernment organizations (NGOs) can be envisaged. NGOs can borrow from the Developnment Bank of the Philippines if they have sufficient collateral at their disposal. However, few NGOs may have land available for housing, and may consequently rely on partnerships with other stakeholders, such as the local government units or the private sector, to access land for their projects. project cycle stage: Lesson Topics: 4. Microfinance for housing should be encouraged. Housing microfinance is an important long-term development instrument. Microfinance institutions that have clienteles with good reputation as borrowers are best suited to implement such housing microfinance loans. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/development-poor-urban-communities-sector-project
Development Policy Support Program Cluster | Philippines | Public sector management | 2010-12-01 | A program cluster approach with prior expected actions enveloped by a medium-term framework with flexibility built into its design is an effective approach to supporting government reforms. It promotes continuous dialogue with the government on reforms and allows for program changes to effectively and efficiently respond to new or worsening risks to the economy and shifts in government policy priorities. This was demonstrated in subprogram 3, with the introduction of new measures to address heightened macroeconomic risks to the economy and help the government effectively provide a fiscal stimulus package in 2009. Using numerical targets such as the tax revenue-to-gross domestic product (GDP) ratio as triggers, as initially done in subprogram 2, should be cautiously approached. Ambitious numerical targets that are not supported by a realistic reform timetable are likely to fail. If necessary, triggers should be supported by technical assistance (TA), as were the subprogram 2 and 3 public financial management (PFM) triggers. During the review of subprogram 2 policy triggers, the government and ADB identified gaps in government budget execution, internal audit and controls, and reporting, acerbated by the underdevelopment of the government's computerized accounts system. The government asked ADB for longer-term integrated TA to strengthen its PFM framework. A program should have a well-defined exit strategy. This program was designed for implementation over 3 years with specified medium-term targets. It successfully closed upon completing subprogram 3. Without an exit strategy, the program risks reform fatigue and may encourage lax compliance with policy reforms. Introducing the post-program partnership framework during subprogram 3 proved to be effective in ensuring the sustainability of key reforms. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/development-policy-support-program-cluster
Mindanao Basic Urban Services Sector Project | Philippines | Transport, Water and other urban infrastructure and services | 2010-11-01 | Participating local government units (LGUs) obtained several benefits. The project generated strong interest among LGUs. Most LGUs appreciated the loan terms (particularly the fixed long-term nature of ADB funds) and the assistance and services provided by the Land Bank of the Philippines (LBP) and the Department of Interior and Local Government (DILG). LGUs also appreciated receiving assistance in modernized governance systems, including assistance in rationalized planning (comprehensive development plans), property tax administration, and revenue enhancement. The assistance was transforming for some LGUs as it allowed them to handle big projects involving loan financing for the first time. The project also increased LGU awareness of urban development priorities and opportunities for future investments. Revenue-earning subprojects were favored. Many of the implemented subprojects e.g. public markets, public transport terminals, and water supply schemes are good revenue earners or have the potential to be good revenue earners. These subprojects provide essential economic and environmental benefits that will have long-lasting positive impacts. It is expected that most of these investments will be sustainable and will lead to further related investments to expand infrastructure networks. Notably, public markets and transport terminals were the most popular choices of subprojects, while water supply systems were the third most popular. Sanitation, flood control, and solid waste management subprojects, perceived by LGUs as low revenue earners, were not implemented. This indicates that LGUs fail to understand or appreciate the benefits of improving the local environment, and that incentives (like capital grants from the DILG) have not been effectively used to direct LGU investment choices. Building town or municipal halls or gymnasiums are of questionable relevance compared with water supply, sanitation, and solid waste management. Municipal buildings may not generate large revenues, but data suggest that they can contribute to improved revenue collection since tax payers appreciate improved quality of town halls and demonstrate more aptitude to pay their taxes there. More strategic and participatory planning is desirable. LGU chief executive officers (CEOs) often selected subprojects and made investment decisions on their own rather than on the basis of strategic local development plans. Although the project assisted some LGUs in formulating comprehensive land use plans, it did not succeed in ensuring that such plans are standard tools for investment planning despite an LBP requirement mandating that LGUs possess annual development plans to qualify for loan approval. The absence of participatory strategic development plans could result in future LGU administrations backtracking on established development priorities and arbitrarily choosing new priorities. Allowing CEOs to choose subprojects creates a risk that cost recovery mechanisms will not be implemented, as political expedience may lead future CEOs to provide services at below-cost levels. Decentralized projects call for a better PPMS. The scattered nature of investments throughout Mindanao created substantial management challenges of reporting and data management. The disparity and decentralized nature of the subprojects should have made it imperative that the project implement a web-based project performance monitoring system (PPMS) instead of employing traditional narrative reporting methods. A web-based PPMS would have facilitated management and supervision. It proved advantageous that LBP had offices in many LGUs or in their subregions, and that the DILG had local officers in all LGUs and was thus able to offer hands-on support for subproject implementation, but did little to support central data management. Collaboration between local DILG officers and LBP lending center staff varied. Capital grants are attractive, but should only be given as a reward for good performance. In the first years of the project the DILG offered capital grants for eligible subprojects. These were discontinued in 2005 after the cancellation of the DILG's grant source. After that, many LGUs stopped subproject preparation work because of the (perceived high) costs of ADB loans. The commitment and buy-in of LGUs was weak at times. Many LGUs were more oriented toward grants than the lending facility. It raises the question of whether the mixed grant-loan scheme was a good concept to start with, considering that it tried to compete with operations of the Municipal Development Fund Office (MDFO) of the Department of Finance (DOF). The concept of capital grants, also part of the national government-local government cost sharing policy, might require some reformulation. Ex-post performance-based grants might have been more appropriate than upfront capital grants, which often distorted LGU perceptions of the project as a lending facility. LGUs see banking requirements as too tedious. Despite various introductory workshops, some LGUs kept complaining about the documentation requirements. The assistance of DILG and its consultants has helped ease their concerns, but LGUs reported that at times they felt like they were being forced into compliance with procedures that other official development assistance (ODA) providers (like Japan Bank for International Cooperation) had already relaxed. Both ADB and LBP procedures could have been simplified to better bond LGU customers with the project. The value of capacity development. Although not easily measurable in terms of monetary impacts and outcomes, capacity development support made an important contribution to the project. The investment of $6 million through an Nordic Development Fund (NDF) loan to the DILG was an unprecedented engagement in favor of LGUs; this amount was augmented with a substantial in-kind operational counterpart contribution by the DILG. However, the true value of the NDF-funded capacity development program can only be assessed in terms of the sustainability of the urban services financed under the project. LGUs reported that without the capacity building they would not have been able to effectively implement the infrastructure investments. Several LGUs stated that cost-free capacity building for their staff was the most attractive aspect of the project even more attractive than the loans especially as it prepared their staff to possibly participate in future ODA projects. A single executing agency could have simplified implementation. The report and recommendation of the president (RRP) and the loan agreement both established an unnecessary overlap of functions between LBP and the DILG. This could have been avoided through a more straightforward and functional separation of roles: LBP to implement Part A, and the DILG to limit its role to Part B. The existence of two executing agencies under the project should have been avoided. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/mindanao-basic-urban-services-sector-project
Small and Medium Enterprise Development Support Project | Philippines | Industry and trade | 2010-10-01 | A credit line operation can be efficiently conducted through a sound operating financial institution focused on sector development. Small Business Guarantee and Finance Corporation's (SB Corporation) healthy institutional and operational structure (supported by the associated technical assistance or TA), coupled with clear, effective laws , have helped it conduct lending operations efficiently and effectively. In other words, vibrant small and medium-sized enterprise (SME) lending operations must be supported by effective policy and institutional arrangements. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/small-and-medium-enterprise-development-support-project-0
Power Sector Development Program | Philippines | Energy | 2010-08-01 | The design of the Power Sector Development Program (PSDP) took into account the lessons learned from previous ADB operations in the power sector. In particular, the preparation of the PSDP benefited from the sector assistance program evaluation of ADB's assistance to the Philippine power sector. On this basis, the PSDP envisaged two subprograms with 2-year time horizons, covering 2007- 2008 and tentatively 2009-2010. Target dates were set only for subprogram 1 to allow flexibility in the overall implementation schedule. The government chose not to pursue subprogram 2 mainly because of the better-than-expected progress of the privatization program, with private sector investments being made without the assistance foreseen under subprogram 2. However, without subprogram 2, the government was able to defer a key policy action that was required for the implementation of the subprogram the introduction of universal charges for stranded debt and cost. As a consequence, the Power Sector Assets and Liabilities Management Corporation (PSALM) could not achieve a debt service coverage ratio (DSCR) of 1.0 in 2009 as required in the policy matrix. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/power-sector-development-program
Bukidnon Integrated Area Development Project | Philippines |  | 2010-05-01 | Many of the administrative lessons learned have been addressed and taken into account in the design of later projects through recent improvements in ADB project-processing methodologies such as the review of project concept papers, the use of project readiness filters, and harmonization of ADB and country procedures for procurement. However, many of the technical lessons learned point to the need for greater attention to design issues at the project formulation stage. They are as follows. (i) Greater care should be taken when recommending the introduction of new technology such as drip irrigation, which had not been practiced on a large scale in the Philippines. (ii) More resources should have been allocated prior to appraisal for the preparation of the feasibility study to verify that the project was both technically and economically viable. The small-scale feasibility study did not provide sufficient time or resources to collect important design data such as rainfall records, land tenure status, crop budgets (including realistic figures on crop inputs), yields, and prices for the with- and without-project situations. This additional information would have enabled the appraisal report to provide a more informed assessment of major project risks. (iii) The feasibility study should have included a detailed value-chain analysis to trace the flow of produce from the farm to its final use and to identify all risks involved at different stages. Effective, feasible remedies should be recommended at each stage. A critical oversight in assessing risks was linking the investment project to the purchase of tomatoes by the tomato-processing factory. (iv) The project should have supported a detailed market study to identify the demand for various high-value crops in different markets at various times of the year. This information could have been made available to farmers to guide them in their timing and choice of planting different crops. A market information system, linking farmers with major buyers for their commodities, could also have been provided to ensure that farmers receive the best prices for their crops. (v) The high cost of providing water to crops, such as tomatoes, using drip irrigation can only be justified in situations where there is assurance of high yields and prices for farm produce. In the project design, insufficient attention was paid to ensuring that the farmers would be able to secure the resources to fund the purchase of high levels of farm inputs or that the marketing arrangements would remain in place for them to obtain high prices. (vi) The water availability for the irrigation schemes appears to have been underestimated at the design stage. In particular, it was found that the Sagayon communal irrigation system or CIS (if implemented) would have been able to provide irrigation water to less than 35% of the area planned. (vii) Procedures for project implementation at the local level need to be established at an early stage. More attention needs to be given to establishing an ongoing dialogue among ADB, national-level government agencies, and the provincial- level executing agency (EA) and implementing agencies (IAs) on the documentation required for the smooth flow of funds. More attention should have been given to capacity building of the EA and IAs in the early stages of project implementation. (viii) Greater attention should have been given to the impact of the project on the budget resources of the province. Although the project was reduced in size from $66.0 million in the initial design to $37.3 million at appraisal, not enough consideration was taken of the province's financial capacity, its revenue, or its budget commitments, which in the end became a key consideration in the provincial government's decision to cancel the loan (principally the irrigation and rural roads components) so that it could channel more of its discretionary budgetary resources into higher priority investments, which turned out to be health care, education, and water supply, and which part of the project did support. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/bukidnon-integrated-area-development-project
Pasig River Environmental Management and Rehabilitation Sector Development Program | Philippines | Agriculture, Natural Resources, and Rural Development, Water and other urban infrastructure and services | 2010-01-12 | 1. The program was overly ambitious in its scope and in its implementation structure. Only after modification of the scope and implementation arrangements was progress made. This could have been avoided, had a proper risk assessment and risk mitigation plan been prepared, based on the lessons learned from the previous program. Although the Pasig River Development Plan provided a good framework for the implementation of environmental improvement projects, more and longer-term assistance is required to establish the institutional setting for its effective implementation. project cycle stage: Lesson Topics: 2. The program required the cooperation of a large number of government agencies, while responsibility for implementation was given to the newly established Pasig River Rehabilitation Commission, without a well-established mandate or political influence. Without high-level political support, coordination became difficult and program outcomes were not achieved. When the responsibility for project implementation was delegated to sector agencies, it became more effective. The program could have been more effective if a more delegated approach had been followed from the beginning, clearly identifying the subprojects to be implemented by respective agencies, based on established mandates, and with subsidiary loan agreements with the Department of Finance. project cycle stage: Lesson Topics: 3. The program assumed that by implementing the policy framework the government would have the tools and capacity to implement the full Pasig River Development Plan (PRDP), leading to the overall objective of improving the Pasig River water quality to class C level by 2014. However, the outputs of the policy loan covered only part of the implementation activities of the PRDP, and therefore it should have been clear from the start that the overall objective was not attainable. Better realignment of the policy and investment loan outcomes and overall impact could have led to a better understanding of the program by the participating utilities. project cycle stage: Lesson Topics: 4. The technical assistance contributed substantially to achieving the policy reforms envisaged under the policy loan, but longer-term and more focused assistance will be required since: (i) as a new agency, the PRRC has limited capacity to drive policy reforms; (ii) policy change requires skills, effective institutional incentives and culture change; (iii) the program is ambitious and multi-faceted, encompassing a wide range of stakeholders with a variety of interests, not necessarily linked to the policy agenda. project cycle stage: Lesson Topics: 5. Because the government had already purchased most of the housing prior to ADB loan approval, it could not be financed by the loan. ADB funds were therefore directed toward facilities. If ADB had not been involved in the project, the host communities would have received these community facilities much later and they would probably have been of a lower quality. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/pasig-river-environmental-management-and-rehabilitation-sector-development-prog-0
Technical Education and Skills Development Project and Fund for Technical Education and Skills Development | Philippines | Education | 2009-11-27 | 1. While mainstreaming arrangements in future projects can improve sustainability, the resourcing plan should recognize the additional workload and coordination the project will require. The mainstreamed approach of this project has been very important for ownership, capability development, and integration with regular programs. The project's complexity and diversity required that significant coordination be undertaken from the outset. This did not occur until the midterm review, after which coordination was strengthened. Project workload was substantial and in many cases it came in addition to the regular work program of the implementing agency, thereby, affecting project efficiency. [Main text, paras. 48-49,81] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Ownership 2. Both ADB and executing agencies needs to ensure that an adequate project management structure with sufficient resources should be in place before the project starts. Some of the initial delays in project implementation were caused by the delayed staffing of the project management office (PMO). In addition, the initial lack of staff with experience in procurement, especially in handling bidding, slowed implementation. The total workload of staff involved in the project should also be considered. The PMO staff faced heavy demands from several other projects receiving foreign assistance that were undertaken concurrently with this project. In many cases, the project workload was in addition to other work required of subcomponent focal points and their teams. [Main text, paras. 63,82] project cycle stage: Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management 3. It is important to collect baseline data at project commencement and perform monitoring during implementation. The failure to establish baseline data and information for impact and outcome levels at the start of the project made it difficult to determine the actual project achievements in some areas, e.g., number of women and rural populations completing informal skills training at the start of the project. Data collection for indicators should be included in the project plan. [Main text, paras. 76,78,83] project cycle stage: Design, Implementation Lesson Topics: Monitoring &amp; Evaluation: Baseline data Monitoring &amp; Evaluation: Data collection and management Monitoring &amp; Evaluation: Monitoring and evaluation 4. Consideration should be given to providing additional support or attention to project activities that are not core functions of the implementing agency. Sub-outputs that are well aligned with the mandate of the Technical Education and Skills Development Authority (TESDA) and the expertise of its staff were mainly successful. For instance, the competency assessment and certification program is a TESDA flagship program, and TESDA commitment, expertise and ownership with respect to this activity are strong. However, those sub-outputs that are not aligned with its mandate, and in which TESDA lacked expertise, encountered greater problems, were cancelled or did not proceed well. These included the student loan fund and distance education. [Main text, paras. 7,18,34,49,77,84] project cycle stage: Design, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Ownership 5. To assist project startup and implementation, the following ideas could be considered: (i) the design stage should focus more on project implementation, (ii) ADB should actively engage with the executing agency to set up the project management unit and systems prior to loan effectiveness, and (iii) a small advance should be released from loan proceeds to finance startup project management activities. The complexity and diversity of the project constituted a risk that was recognized in the design, but this risk was underestimated. While it was expected that two sub-outputs would be managed by Development Bank of the Philippines and Land Bank of the Philippines, little or no notice was given to the significant and constant management and coordination required for the remaining numerous suboutputs. Complete staffing of the PMO at the start of the project would have helped improve coordination in the first half of the project. [Main text, para. 7,49,63,85] project cycle stage: Design Appraisal Implementation Lesson Topics: Project Management: Project administration Project Management: Project management 6. Instructors from private institutions provided a valuable contribution to the development of the training regulations. The partnership with the private sector is very important, because the majority of TESD students are trained in the private sector. The private sector needs to be improved to provide a higher-quality learning environment (e.g., improved physical facilities and better trained teachers). However, continuing education for instructors in private institutions was a challenge. The staff development target for private instructors was not met as they could not be released at the time of the scheduled programs. Consultations should be held with private institutions to identify how their instructors can be provided with training. Training could be conducted on a voluntary basis on weekends or during term breaks, with instructors paid to attend. Training could also be provided during terms, with replacement instructors paid to cover the absence of the regular instructor. [Main text, paras. 35, 68,86 ] project cycle stage: Implementation Lesson Topics: Sector Related Issues: Private sector Methodologies/Approaches: Consultation/Participation 7. It is critical to involve each implementing agency early in loan preparation to enhance project operations. The Development Bank of the Philippines (DBP), identified as the lending institution to manage funds for financing private technical education and skills development (TESD) providers, was not involved in the preparation of the project until close to the loan negotiation stage. During implementation, when the loan uptake proved low, DBP realized they should have been involved in the preparation stage. For similar future DBP-administered loans, DBP field officers who are familiar with problems encountered in lending to specific target groups should be consulted. Had been DBP more involved, the project's targets would have been scaled back for smaller schools and provided grant-funded technical assistance (TA) to support smaller TESD providers needing significant assistance and counselling. The TA could have helped formulate innovative ways to mitigate the potential risks associated with small borrowers. [Main text, paras. 32,50,64,87] project cycle stage: Design, Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/technical-education-and-skills-development-project-and-fund-technical-education-a
MWSS New Water Source Development Project | Philippines | Water and Other Urban Infrastructure and Services | 2009-07-01 | 1. In future projects, ADB may recommend the use of advance procurement action to get consulting services started quickly. The consulting services for the Laiban Dam Project (LDP) preparation was canceled because the Metropolitan Waterworks and Sewerage System (MWSS) considered direct consultant selection necessary for quick progress in developing new water sources (although no such urgency was indicated at the time the loan was designed). MWSS therefore decided instead to implement the studies with funds from the private concessionaires. [Main text, paras. 10, 30] project cycle stage: Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/mwss-new-water-source-development-project
Secondary Education Development and Improvement Project | Philippines | Education | 2009-03-31 | 1. The Project highlighted the importance of employing a holistic approach to education development. Project interventions aiming to improve teaching and learning focused on teacher capacity building, availability of learning resources, improvements in physical environment, and remediation have shown some short-term progress and led to limited progress regarding student achievement. Designing interventions aimed directly at improving student achievement need to be more holistic. For instance, the Dropout Reduction Program could have improved the quality of its interventions specifically for at-risk students by complementing distance education materials with open highschool system and other school based initiatives customized to the needs of students at risk of dropping out. [Main text, paras. 25-29, 80] project cycle stage: Design Lesson Topics: Project Design: Project design Methodologies/Approaches: Holistic approach 2. Demand-driven approach to project implementation in an education is a good approach in promoting partnerships with local stakeholders as it directly addresses their needs. ADB and the concerned government agency designed the Project to give priority to schools that previously received no interventions for improvement. In many instances, the allocations proved appropriate and met local needs. This type of resource allocation promoted partnerships between school and community stakeholders (e.g., LGUs and parent associations). [Main text, paras. 31, 60, 81] project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Partnerships Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach 3. The Project highlighted the importance of taking a systemic, holistic approach to education planning and management that promotes decentralization. The Project demonstrated that partnership between and among school heads and division-level management is feasible under a devolved system. Likewise, partnerships between division-level and regional management were also made possible. The Project underscored the critical role of division and regional offices in continuously providing technical assistance and guidance to school heads. [Main text, paras. 63-64, 82] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Country Context: Decentralization Methodologies/Approaches: Holistic approach 4. The project could have benefited from adequate assessment of the capacity of the executing agency to implement multiple projects. The Secondary Education Development and Improvement Project (SEDIP) and the World Bank-funded Third Elementary Education Project (TEEP) were designed as a package to cover elementary and secondary education in the same divisions - thereby achieve synergies in implementation and amplify project impacts. This did happen to a large extent, but implementation difficulties arose because the divisions lacked the human, physical, and financial resources to deal with two large projects at once. As TEEP started a year before SEDIP, this negative impact was felt most by SEDIP. The initial capacity and financial assessments were carried out separately for each project and did not adequately predict the combined demands of both projects upon the divisions. [Main text, para. 83] project cycle stage: Design Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-education-development-and-improvement-project-pcr
Country Assistance Program Evaluation for the Philippines: Increasing Strategic Focus for Better Results (2008) | Philippines |  | 2008-06-30 | 1. Building selectivity into the country program by focusing on key constraints, in particular fiscal management, that were mutually understood and agreed between the Government and ADB has paid off in terms of clearer, more substantial, and earlier results and portfolio improvement. The combination of portfolio cleanup and timely use of program lending resulted in a restoration of net transfers, closed ineffective investment projects, and helped address the Government's fiscal burden from underperforming operations. However, bureaucratic inertia in key revenue collection agencies, misaligned institutional incentives, and vested interests have hampered progress on deepening revenue gains and highlighting the need for continued, focused engagement. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Program Project Design: Project design Country Context: Prioritization Methodologies/Approaches: Consultation/Participation 10. Progressing fiscal reforms is crucial for maintaining macroeconomic stability and improving public expenditure management to facilitate growth and poverty reduction. In the event of a global and domestic economy slowdown, maintaining fiscal discipline will continue to be needed. Continued operational focus is needed on fiscal reforms including revenue efforts and improving budget allocations for priority sector development (infrastructure, education, health, agriculture, and rural development). To progress expenditure efficiency and improve local service delivery, support is needed for systematic capacity development to improve public expenditure management and service delivery. Increasing support for local capacity development in country systems-based planning, management, and internal audit is needed and requires consideration of alternative modalities to expand systematic institutional capacity development. Wider consideration is needed for human resource development and incentive structures, especially at the local government level. Given the ongoing national agency rationalization process, a focus on national agencies and local government units that support or are responsible for the provision of local goods and services is needed. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Poverty reduction Capacity Development: Capacity development Capacity Development: Human resources management Country Context: Decentralization Country Context: Prioritization Policy & Reform: Reform Methodologies/Approaches: Program Approach 11. ADB support through the Secondary Education Development Improvement Project highlights the need for mutual understanding of the project design at the outset to avoid delays. In cases of frequent changes in heads of department, especially at the Secretary level, close dialogue is needed to identify the risks to the project and to aid ADB decision making on the possible need for changes in scope or cancellation where covenants are fundamentally compromised. Even in cases where technical assistance recommendations are initially rejected, maintaining a policy dialogue can result in the possibility of future acceptance. Where ADB's assistance in a sector is a relatively small contribution to overall Government efforts, the emphasis should be on demonstration effects. Falling Millenium Development Goals performance in education, private sector concerns over education standards, and the still tenuous budget allocations to the sector suggest that ADB's engagement in the sector should be a priority. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Policy dialogue Methodologies/Approaches: Sectoral approach 12. Fostering privatization and competition in the power subsector takes time and proceeds in an incremental fashion. Substantial reform efforts have addressed power supply uncertainties, but this has yet to translate into markedly lower tariffs, due to the need to reduce the fiscal burden of tariff subsidies and to repay the long-term maturity debt needed to develop energy assets. To sustain the positive reform progress, it is essential to ensure that private sector entry to the sector leads to deeper competition, operating efficiencies, gains for consumers; and enhanced access to reliable power supplies in rural areas. To minimize the possibility of a repeat of the power shortages of the 1990s, private sector investors need reassurance on government commitment to sector reforms, the independence and transparency of the regulatory regime, effective operation of the spot market, and existence of a competitive market. Reform momentum can be maintained through continued assistance in financing key privatization projects, promotion of competition, and improved regulation, and moreover, to address the large unmet demand for rural electrification. To address current high oil prices and global warming, expanded support for energy efficiency and renewable energy is needed. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Capacity Development: Ownership Sector Related Issues: Private sector Policy & Reform: Privatization Policy & Reform: Public sector reform Policy & Reform: Reform 13. Transport infrastructure is a key constraint to private sector development and growth, and transport development is an area of ADB's core corporate competence deserving significant attention. At the operational level, careful evaluation is needed of land acquisition and resettlement (LAR) issues to ensure an accurate, agreed, and costed LAR plan prepared in advance of appraisal and to ensure that ADB policies are clearly understood and included in the Loan Agreement. To avoid major changes in design, optimistic implementation schedules place additional burdens on EAs and ADB. Clear roles and responsibilities of regional and local project management offices are needed. At the strategic level, development partners including ADB have provided substantial support for transport planning and attention needs to turn obstacles to implementation of plans. This needs ADB to systematically assess where and how it can best contribute to sector's needs. To foster public-private partnerships in transport, greater coordination is needed among regulatory agencies and support is needed for infrastructure implementation. ADB needs to continue to address areas such as transport policy; transparent procurement; and improving the prospects for public private partnerships, including needs for areas such as mass transit in Metro Manila and roll-on-roll-off ferry systems to promote trade through and beyond the archipelago. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Private sector Sector Related Issues: Public-private partnership Policy & Reform: Policy reforms/framework 14. Urban development was seen as having the potential to address poverty reduction, social inclusion and service access, and environmental problems. However, urban development is hampered by a wide range of contextual factors, which must be considered in project design. ADB's urban development projects also suffered from multiple institutional layers, fiscal constraints, 3-year mayoral tenure cycles, bureaucratic inefficiencies including complicated multi-agency mandates and project management unit arrangements, and a series of difficult land acquisition issues. Hence, a more thorough assessment of local institutions and risks is needed at the design and appraisal stages. In the case of sector projects, a rigorous assessment of institutional capacity is needed prior to committing new subprojects. Moreover, success factors and good practices between project and nonproject municipalities can provide insights on design and implementation issues between municipalities. The mixed results in the urban development sector suggests a need for assistance approaches that foster widespread participation in design and implementation, combined with designs for operations that can more effectively anticipate and address complex cross-sector concerns. There is also a need to spur greater private sector participation in urban infrastructure and services through strengthening of public private partnerships. project cycle stage: Design, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Project design Project Design: Subprojects Project Management: Project management Project Management: Risks/Risk management Capacity Development: Capacity assessment Sector Related Issues: Private sector Sector Related Issues: Public-private partnership Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach Methodologies/Approaches: Sectoral approach 2. Strong agreement and coordination by Government oversight agencies has improved the design and implementation of critical macroeconomic reforms. Independent analysis and advocacy by the private sector, academe, and civil society stakeholders together with coordinated consultation with the Government helped to improve the understanding and management of the political economy for fiscal and energy sector reforms that complemented fiscal management improvements. project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Project Design: Project design Project Management: Project administration Capacity Development: Ownership Policy & Reform: Reform Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach 3. The introduction of a medium-term development policy support approach (DPSP) to fiscal reforms has avoided previous problems with prior conditionality and facilitated more continuous policy dialogue and positioning for next stage reforms. Sequenced and combined use of program lending, public project finance, private sector finance, and technical assistance (TA) for capacity building in regulation has helped energy sector reforms and development. The development of needed institutional infrastructure in the nonbank financial subsector took time, as well as lending and nonlending support. Here, the lesson is that reforms involving institutional strengthening should take a medium- to long-term perspective. The Health Sector Development Program (HSDP) provides good practice examples of the use of sector-wide, programmatic approaches using existing ADB modalities, and the DPSP provides a good practice example of engaging in difficult reforms over the medium term. project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Modality: Lending modality Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Methodologies/Approaches: Policy dialogue Methodologies/Approaches: Program Approach Methodologies/Approaches: Sectoral approach 4. Support for fiscal, energy, nonbank finance reforms contributed to improving the private sector enabling environment. The North Luzon expressway public-private partnership .is an example of both involving the private sector in infrastructure development and lowering travel costs between economic centers. However, new support for transport and water infrastructure has not been forthcoming as planned. Concerns over handling of right-of-way issues requiring resettlement, lack of competitiveness with other bilateral development partners, and perceived high transaction costs of ADB-administered projects have limited ADB s contribution. ADB has demonstrated readiness to be involved in public private partnerships such as the Maynilad water consortium, but this did not prosper due to management problems with the original concessionaire. project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Resettlement Sector Related Issues: Private sector Sector Related Issues: Public-private partnership Policy & Reform: Reform 5. ADB has supported investment climate assessment and advocacy helping to spotlight the need to reform competitiveness more broadly if the country is to sustain growth and generate the employment and incomes necessary to address exclusion and income poverty. Projects can address corruption issues within their boundaries, but their impact on wider governance problems is inherently limited. Support for fiscal management and budget realignment has opened a promising avenue for ADB's contribution to addressing corruption systemically through initiatives such as more transparent procurement in public projects. Policy based lending and related technical support is better placed to address systemic governance issues. Inadequacies in the judicial system and rule of law have been deterrents to investments. The fact that the leadership of the judiciary was prepared to be engaged is a good start. Successes in capital market reforms shows that avoidance of corruption requires a sector focus with well-defined rules and a good regulatory framework. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Corruption Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Public governance Modality: Policy-based lending Modality: Technical Assistance Project Management: Procurement Policy & Reform: Public sector reform Policy & Reform: Reform 6. While relevant, overlapping roles and responsibilities of many agencies, lack of access by LGUs to development finance, wide geographic dispersion and complex operational designs, and in some instances, insufficient follow-through in any one location have hampered support for the rural and urban agenda. However, rural and urban development projects have provided positive local livelihood impacts and useful project cycle capacity building for participating LGUs that complements recent initiatives to strengthen provincial planning and expenditure management systems. Reform support for local government finance is a key step to systematically re-engaging the Government on decentralization, and links to the fiscal management agenda, but requires more intense and systematic support for capacity development. project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Funding Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development Country Context: Decentralization Sector Related Issues: Rural development Sector Related Issues: Urban sector/development Policy & Reform: Reform 7. A focus on the southern Philippines, and particularly Mindanao, has presented an opportunity to build a synergy between agricultural development, small and medium-sized enterprisedevelopment, and regional cooperation through BIMP-EAGA. This is accompanied by an unplanned but highly relevant opportunity for developing rural value chains, backward linking to areas with high rural poverty, and clarifying public and private sector roles in the process. This is having the unanticipated effect of increasing the income impact of agriculture projects. Planned advisory activity such as quarantine, immigration, customs, and security will strengthen synergies, and has the potential to develop into a structured strategy. The canceled support for regional airport infrastructure development was a missed opportunity to further integrate such linkages. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Regional cooperation Modality: Technical Assistance Sector Related Issues: Rural development Methodologies/Approaches: Targeting 8. Support to the ARMM has had limited effectiveness, and for lending operations became a factor in delaying the implementation of some projects. This suggests that the current lending operational designs and approach are not relevant or effective in meeting the critical needs of the ARMM. Support for Islamic finance through regional technical support to, for example ASEAN, had a potential application in the ARMM, but ADB has not yet explored this link. project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Poverty reduction Capacity Development: Capacity development Capacity Development: Human resources management Country Context: Decentralization Country Context: Prioritization Policy & Reform: Reform Methodologies/Approaches: Program Approach Methodologies/Approaches: Targeting 9. The analysis of the political economy of reforms reveals several points across and within sector reforms. The fiscal reforms were central to progressing reforms in other sectors. However, progress on fiscal consolidation was contingent on prior progress in energy sector reforms, especially progress in privatizing assets of the National Power Corporation (NPC). The political constituency for energy and tax reforms was a turning point for overall fiscal consolidation. This provided a foundation for increasing overall public resources needed to progress reforms to raise spending on basic social services such as health and education. The analysis also shows that strengthened institutions are critical to deepening and sustaining reforms. project cycle stage: Country Partnership Strategy Lesson Topics: Project Design: Problem identification Capacity Development: Capacity development Country Context: political economy factors Policy & Reform: Privatization Policy & Reform: Reform Methodologies/Approaches: Program Approach | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-philippines-increasing-strategic-focus-better
Women's Health and Safe Motherhood Project in the Philippines (Loan 1331-PHI[SF]) | Philippines | Health | 2007-07-31 | 1. Effective inter-local health zones can help provide better public health services underthe devolved health systems. The local government units were able to provide better health services under thedevolved health system when they planned, coordinated, and shared resources withneighboring municipalities. This approach can be an efficient and cost-effective system in thelong term, although it may require substantial support initially for developing and establishingthe required institutional capacity. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity development Capacity Development: Human resources management Country Context: Decentralization Sector Related Issues: Health and sanitation management 2. Empowering provincial and municipal health officers by enhancing their skills in health sector management and promoting greater ownership could serve as an effective entry point for improving the provision of health services. The provincial health officers are the main personnel overseeing and implementing health policies for the provinces, while municipal health officers have similar roles for municipalities. The key informant interviews indicated that health officers with strong commitment and experience in public health were able to secure additional funds from local government units for the required physical capital, human resources, and consumables. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Capacity Development: Capacity development Capacity Development: Ownership Country Context: Decentralization Sector Related Issues: Health and sanitation management 3. Future programs on women s health and safe motherhood should include interventions that address issues of abortion and unwanted pregnancy. The most recent National Demographic and Health Survey affirmed that the population growth target could be better achieved if such unwanted pregnancies were avoided. Induced abortion, which is a significantunderlying cause of maternal mortality, could also be eliminated. In addition, inclusion of family planning advocacy in future programs could contribute towards reduced maternal mortality, as high fertility and maternal mortality are correlated. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Project Design: Project design Sector Related Issues: Health and sanitation management A strong and well-functioning PMO managed by the executing agency is essential for improving the overall coordination and control of project activities. The PMO should have an adequate number of well trained staff and should be well integrated within the institutional framework of the executing agency. It is also desirable to assess the potential effects of alternative project implementation arrangements on the long-term capacity of the executing agency. More resources should be invested in ensuring institutional capacity for enhancing project sustainability and effectiveness. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management An assessment of the procurement and disbursement system of the executing agency needs to beundertaken, with concrete steps taken to improve the situation. This requires streamlining andmodernizing the system, ensuring staff are adequately trained, and establishing clear guidelinesto ensure timeliness of procurement and disbursement. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Project Management: Executing/Implementing agencies Project Management: Procurement Capacity Development: Capacity building Capacity Development: Human resources management For effective outcome and impact, project investment should not be spread too thinly nor be so ambitious in scope as to become unmanageable. Given contextual factors and equity issues, strategic investment choices need to be made when deciding geographical coverage. project cycle stage: Feasibility, Appraisal Lesson Topics: Increased contact with health centers and formally trained health professionals does notnecessarily lead to behavioral change towards delivering babies at health facilities. Most of thedeliveries continue to be assisted by hilots at home. With additional training, hilots can continueto play an important role and complement the facility-based approach in providing improvedmaternal care. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Health and sanitation management The combination of interventions provided in the project facilities upgrading, referral systems improvement, IEC, and program management could serve as a model for future programs. Suitable scaling-up strategies are needed to generate impact on a broader scale. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/womens-health-and-safe-motherhood-project-philippines-loan-1331-phisf
Integrated Community Health Services Project | Philippines | Health | 2006-11-15 | Better pay clearly accounts for lower staff turnover rates. This has an immediate budget impact, but elevating the provincial civil service classification has positive benefits in terms of recruiting and retaining quality staff. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Capacity Development: Human resources management Decentralization can work to attain better health outcomes if local government units (LGUs) are willing to coordinate with one another, unify their plans, harmonize their efforts, and share resources and expertise. Despite formidable obstacles brought about by decentralization, LGUs can work together to address common health problems. This is possible if the local chief executives are highly committed to reforms in their respective localities and are willing to look to the national health agency (Department of Health or DOH) for policy direction and technical guidance. project cycle stage: Feasibility, Implementation Lesson Topics: Country Context: Decentralization Sector Related Issues: Health and sanitation management Policy & Reform: Public sector reform Health management systems are essential for the delivery of comprehensive health services. However, the development and installation of systems per se, no matter how technically sound, cannot generate reform without the corresponding commitment of the stakeholders, sense of ownership by the system users, constant follow-up on the utilization and application of systems, and allocation of resources to sustain the system. Project interventions must complement other components and be implemented in a synchronized manner to obtain maximum results. For example, health facilities will not function without the minimum number of staff required, equipment cannot be operated without proper technicians, and the services ofBarangay Health Worker (BHW) midwives may not be maximized if they are not hired to function as midwives. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Ownership Sector Related Issues: Health and sanitation management Policy & Reform: Public sector reform The visible impacts of health sector reforms take time to materialize. Reforms also incur costs, so judicious prioritization of resource use is essential. External funds are necessary for long-term investments, but local government units (LGUs) must provide the necessary counterpart staff and budgets to sustain gains brought about by the project. project cycle stage: Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Capacity Development: Human resources management Country Context: Prioritization Sector Related Issues: Health and sanitation management Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/integrated-community-health-services-project
Nonbank Financial Governance Program II | Philippines |  | 2006-09-15 | 1. Further reforms to enhance sustainable growth of mutual fund and pre-need plans depend on enactment of legislative reforms. While the program focused on key reform initiatives that were under the control of the executive branch, objectives focused on facilitating mobilization of domestic savings which require legislative action. Although relevant bills were submitted and technical working groups organized to discuss, and public hearings conducted on these bills, it appears that neither adoption of a new pre-need code nor amendment of the Investment Company Act is a Congressional priority. [Main text, paras. 49, 58-59] project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Policy & Reform: Reform 2. While it is acknowledged that funding for government agencies remains limited, key reform initiatives require adequate resources to strengthen regulatory capacity, especially in the area of surveillance and enforcement. Likewise, until the Securities and Exchange Commission (SEC) staff are sufficiently protected from frivolous and intimidating lawsuits, it may be unrealistic to expect strong enforcement actions. [Main text, paras. 48, 53, 60] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Policy & Reform: Reform 3. In addition to focusing on legislative measures, it may be more effective to help the Securities and Exchance Commission (SEC) review other regulatory tools to achieve greater compliance. For example, greater use of information and communication technology (ICT) to monitor compliance with regulatory requirements by both the SEC and Philippine Stock Exchange (PSE) could free up much-needed staff resources and provide timely review of compliance, although initial costs may be substantial. The government has demonstrated strong ownership of financial reporting reforms, where compliance can also be monitored by market professionals through the SEC's new i-Report system. [Main text, paras. 23, 61] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Management: Management information system Capacity Development: Human resources management Capacity Development: Ownership Policy & Reform: Reform 4. In the future, program designs should focus on areas where there is strong commitment and adequate resources available to successfully implement reforms. Ongoing domination of the financial sector by banks will continue in the absence of a concerted government policy to promote regulatory and tax parity among bank and nonbank investment products. Moreover, simply changing a law or regulation will not change behavior in the absence of strong enforcement and sustained (long term) commitment to the reform agenda. [Main text, para. 49, 56, 62] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Modality: Program Project Design: Project design Capacity Development: Ownership Policy & Reform: Reform 5. The Second Nonbank Financial Governance Program was developed prior to adoption of the Results-Based Framework by ADB, which shifts the orientation of country programming from resource transfers to development outcomes. Future projects thus need to focus on more concrete outcomes linked to tangible medium- and longer-term results. [Main text, para. 63] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Modality: Program Project Design: Project design | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/nonbank-financial-governance-program-ii
Clark Area Municipal Development Project | Philippines |  | 2006-08-15 | At the time of project approval, there was little experience of borrowing by smaller local government units (LGUs), and hence the project provided a good means of testing the system. Financing from the Municipal Development Fund Office (MDFO) and government financial institutions (GFIs) are good alternatives to direct budget support for LGUs and support the government's objective of reducing fiscal pressure by encouraging LGUs to raise revenue, improve financial management and invest in priority ventures through borrowing and equity. The government and ADB's investment in promising but high risk interventions is acceptable as long as the risks and associated costs are clearly identified for worst case scenarios and decision points to terminate the project, once valuable lessons have emerged , are clear to all parties. This can then form the basis for improvements in service delivery and strengthen the rationale for future investments. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Project Design: Project design Project Management: Risks/Risk management Country Context: Decentralization Choice of financing modalities and improved fundflow processes need to be provided. Although financing from both the Municipal Development Fund Office (MDFO) and government financial institutions (GFIs) is accessible to all local government units (LGUs), MDFO is more attractive to fifth- and sixth-class LGUs, which can receive up to 70% concessional financing from MDFO. Limiting the financing window under the project to MDFO, when six of the eightLGUs were classified as first-class and clearly had alternatives available turned out to be a flaw in project design. Three first-class LGUs out of the eight LGUs dropped from the project and availed GFI financing, due to the faster processing time, albeit they too received funds through the budget. Moreover, an important aspect of loans seems to be the creation of processes for making timely payments to credit worthy LGUs (without having to route small loans through the lengthy budgetary process,). More efficient fundflow processes need not compromise fiduciary safeguards or avoid accountability mechanisms. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Modality: Lending modality Project Design: Project design Country Context: Decentralization It is important to thoroughly assess the adequacy and timeliness of budget support. One of the principal reasons for the project's poor performance is that the design process did not include a through assessment of likely budget support. While the project design recognized that timely and adequate budget support might not be forthcoming, the mitigating measure i.e. a thorough assessment of the borrowing capacity of the local government units, did little to address the issue of delayed budget support which was necessary for timely mobilization of project management support (PMS) consultants, thus slowing implementation. In fact, the project (CAMDP) was clearly a low priority project during times of fiscal tightening and was placed in the ï¿½unprogrammed ï¿½category of the budget, along with other projects with funding being contingent on the government meeting certain revenue targets. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Project Design: Project design Project Management: Consultants Project Management: Project management Capacity Development: Capacity assessment Country Context: Decentralization It is necessary to develop mechanisms that encourage LGUs to follow through with commitments. Despite extensive participatory processes undertaken in the design and selection of subprojects, these proved to be at risk of being cancelled and or changed due to a change in the local government unit's (LGU's) political leadership. Part of capacity building is to have LGUs think hard before they commit to borrowing for certain subprojects. If they withdraw due to a change in priorities (which in itself is ironic) they should do so considering the negative implications this would entail, such as financial or reputational, or a downgrading of credit worthiness. New policies now require the local Legislative Councils to approve subprojects on the basis of a medium-term LGU investment plan. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Project design Project Design: Subprojects Capacity Development: Capacity building Capacity Development: Ownership Country Context: Decentralization Country Context: Prioritization Land acquisition issues need to be resolved before signing subloan agreements. The failure of the government and ADB to agree on the terms of land acquisition for a bridge and a landfill led to the cancellation of these subprojects, after considerable resources had been invested in preparing resettlement action plans and assessing the costs of land acquisition. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Loan Agreement: Loan Agreement Project Design: Subprojects Project implementation could have been strengthened with the timely provision of consultant support at both the PMO and PIU level through a grant TA from ADB. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Consultants Project Management: Project management Capacity Development: Capacity building Time for potential delays needs to be built in. The project's original implementation schedule did not allow time for potential delays in loan effectiveness and for delays arising from the lack of budget cover. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/clark-area-municipal-development-project
Power Transmission Reinforcement Project | Philippines | Energy | 2006-08-15 | 1. Closer consultation between ADB and the Borrower (National Power Corporation) at each step of the procurement, particularly on the issue of project scope, could have avoided a change in the financing arrangements and consequent delay. The major change in the financing arrangements for Part A delayed the completion of the Leyte-Cebu interconnection uprating by about 5 years. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Procurement Sector Related Issues: Energy planning/management Methodologies/Approaches: Consultation/Participation 2. Before loan approval, ADB should have assessed thoroughly National Transmission Corporation (Transco) capacity to deal with right of way (ROW) issues. The project schedule at appraisal was unrealistic, because it did not take into account the long time needed for Transco to comply with the procedures to secure ROW. At the time of the project completion report Mission, 302 affected households and owners (i.e., 13% of the total) had not received compensation. These issues led to long implementation delays for Part B. Transco could have mitigated many of the delays with forward planning and effective project management. ADB's review mission could have included a resettlement specialist to advise and assist Transco in addressing ROW issues. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Appraisal Project Design: Project design Project Management: Project management Project Management: Project supervision Capacity Development: Capacity assessment Capacity Development: Human resources management 3. In accordance with the arrangements agreed at appraisal, ADB's loan financed the supply and delivery of substation and transmission line equipment, while the executing agency financed the civil works and erection contracts. This arrangement required two procurement processes, and different contractors for the implementation of the same project components. Turnkey contracts could have reduced the implementation delays caused by the use of separate supply contracts (financed by ADB) and civil works and erection contracts. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Loan Agreement Project Design: Appraisal Project Management: Procurement Sector Related Issues: Energy planning/management The demand forecasts made at appraisal were overly optimistic, because the methodology used was based on the projected gross domestic product and constant elasticity coefficients. Such an econometric approach failed to capture the impact of the Asian financial crisis that slowed the country's economic growth and suppressed electricity demand. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Appraisal Country Context: Crisis/Post-crisis Sector Related Issues: Energy planning/management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/power-transmission-reinforcement-project
Rural Microenterprise Finance Project in the Philippines (Loan 1435-PHI[SF]) | Philippines | Finance | 2006-07-31 | 1. Covenants on regulation need to be more sensitive to the laws and standards practiced in the financial sector. In particular, the covenant to regulate deposit mobilization of nongovernment organizations (NGOs) and formulate an appropriate law (if necessary) was difficult to comply with. NGOs are outside the authority of any regulatory agency, unless they transform themselves into regulated financial institutions. The Agricultural Sectors (Divisions), which initiated ADB s microfinance programs in the past, might have inadvertently overlooked the vital nuances of the covenant and implications for the financial system. As a subsector of the financial system, microfinance should conform to the rigors of that system. [Main text, para. 83] project cycle stage: Design Appraisal Lesson Topics: 2. Any efforts to target the poor must (i) clearly define the target group; (ii) identify the barriers to their market entry; and (iii) include interventions and/or mechanisms to break these barriers in the project design to ensure the target group s participation. The ultra poor the bottom 30% of the rural population were the main target of the project design. However, the ultra poor were not defined clearly, which prevented targeting from being more focused and concrete. Likewise, barriers to this target group accessing the institutional credit market were not identified well. Further, given the difficulty of estimating incomes in rural areas, the participation of the bottom 30% of the rural population in the Project cannot be assessed reliably. [Main text, para. 84] project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Project Design: Problem identification Methodologies/Approaches: Targeting 3. Microfinance is not effective in reaching large numbers of the ultra poor on a sustainable basis. The ultra poor and destitute have a different set of needs that can be addressed more effectively by other forms of social development inputs. Safety net programs, such as guaranteed employment, food aid, and skills training, are some examples. Over time, these interventions could help them graduate to credit-taking capability and become full-fledged microfinance clients. [Main text, para. 85] project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Sustainability Methodologies/Approaches: Targeting 4. The project brought microfinance into the mainstream of the formal financial system. This was accomplished by facilitating the participation of rural banks, cooperative banks, and thrift banks that have emerged as major providers of microfinance. The critical factors that contributed to this achievement were (i) the availability of project funds that catalyzed the expansion in the supply of microfinance services, (ii) the favorable policy and legal environment provided by the Central Bank and the passage of a social reform and poverty alleviation act, and (iii) the flexibility of ADB and the executing agency to adjust and respond to changing market demand conditions. [Main text, para. 86] project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Capacity Development: Partnerships Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/rural-microenterprise-finance-project-philippines-loan-1435-phisf
Rural Water Supply and Sanitation Sector Project | Philippines | Water and Other Urban Infrastructure and Services | 2006-07-14 | The combined activities of constructing a building, supplying equipment, and training technical staff are insufficient to establish an operational water quality laboratory. More assistance is required, such as (i) providing the laboratories with water supply and electricity; (ii) training the medical technicians to operate the supplied equipment, which may be different from the equipment used during formal training; (iii) training new technical staff to replace departing staff; (iv) establishing rates for the services offered; and (v) formulating a business plan. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management The organizational structure should be in place before implementation starts. In the case of new management structures, it should be anticipated that this will take time, and adequate resources should be allocated. A functional monitoring system should be established to manage large numbers of subprojects effectively. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Project management The project proved to be very ambitious. It required cooperation among at least three government agencies at three levels and communities in 20 different provinces. Implementation required strong management skills and capacity from the executing agency (EA), implementing agencies (IAs), and local government units (LGUs). project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity assessment Country Context: Decentralization | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/rural-water-supply-and-sanitation-sector-project
Cordillera Highland Agricultural Resource Management | Philippines | Agriculture, Natural Resources, and Rural Development | 2006-05-15 | 1. Using the new (participatory) approach to the project, it is necessary to train government officials and project staff properly at the very beginning of the project. The project was the first ADB-funded project in the Philippines to use a participatory process to mobilize and empower local communities to bring them into the development stream. It also strengthened the capacity of government institutions with responsibility for delivering a range of services. Although the participation of community members was largely confined to the planning stage, with implementation undertaken by the line agencies using conventional means, valuable experience was gained that will be relevant to similar projects. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity building Methodologies/Approaches: Participatory approach 2. In the participatory process, early and quick mobilization of the planning facilitator is the key to success of the project. The 2-year delay in completing the contractual arrangements and mobilizing the locally-based NGOs led to delays in initiating the participatory process and resulted in a compressed time frame and delayed implementation, which should be avoided in future projects. NGO involvement in the formulation of the Barangay Natural Resource Management Plan (BNRMP) was very useful since the NGO was familiar with the participatory approach, the Cordillera Administrative Region, and indigenous peoples. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Capacity Development: Capacity development Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Participatory approach 3. For the establishment of a new project implementation office, the secondment of staff from the participating agencies, rather than hiring contractual staff, contributed to human resource development and enabled institutional knowledge to be retained within the implementing agencies, which will be useful for similar projects in the future. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Human resources management 4. Support for the ï¿½Cordillera Highland Agricultural Resource Managemet (CHARM) on the Airï¿½ radio program provided market information and increased awareness on the project. Due to strong support from listeners, the radio program has attracted private sector support since completion of the project, which is an ideal way of sustaining project activities. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Information dissemination/Public awareness 5. The expansion of the Integrated Pest Management ( IPM) program through farmers' field schools to cover other activities such as livestock, agro-forestry and child nutrition was successful and beneficial. This methodology may be applied to other agricultural activities. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Rural development 6. Due to the sense of ownership generated by the implementation arrangements under the project, the construction of roads by the provincial engineering office was more effective than using the national roads agency or the Department of Public Works and Highways (which had been used as the implementing agency for the previous Highland Agricultural Development Project). project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Roading 7. Incorporation of indigenous peoples knowledge to the project design makes the project more implementable and easy to be understood by the people. The project incorporated indigenous forest management practices called lapat. It may prove to be a model for the use of other indigenous knowledge and institutions in the management of other sectors - e.g., water, agriculture, and health. Such indigenous knowledge should be drawn on for future projects. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/cordillera-highland-agricultural-resource-management
Regional Municipal Development Project | Philippines |  | 2006-05-15 | 1. Flexibility in project design could have facilitated adjustments required during project implementation; hence addressed reduction in geographical coverage and limited scope of the project. The project loan approach was too rigid. It did not offer the executing agency and IAs the possibility of replacing cities or subprojects. A more flexible approach (e.g., sector loan) would have reduced the government's commitment fees, while enabling more cities to be accommodated and equally worthy subprojects to be considered. A major change of project scope could have allowed the replacement or redefinition of subprojects, or the replacement of cities that dropped out of the project. However, this was not pursued due to the lengthy processing time required. The loan amounts per city were considered too small relative to the transaction costs involved. [Main text, paras. 51, 63(i)] project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Modality: Lending modality Modality: Program Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies 2. There should be greater attention to risks, including political risks which could disrupt project implementation. The project completion report has noted that changes in local administrations resulted in delays in subrpoject implementation. Project designs should consider the 3-year terms of local governments, and insist on longer-tem commitments. Advocacy is needed to ensure project sustainability. [Main text, paras. 53, 63(ii)] project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Risks/Risk management Country Context: Decentralization Policy & Reform: Information dissemination/Public awareness 3. Thorough technical reviews, or a second technical opinion, should be sought for important and environmentally sensitive projects (such as the Puerto Princesa landfill). For the sanitary landfill in Puerto Princesa, the failure of the design to consider all possible technical details, such as the provision of geo-textile membrane for anchoring of the isolation materials, proved costly. The detailed engineering design did not anticipate significant excavation works of underlying wastes since necessary soil investigations were not conducted. [Main text, paras. 43, 63(iv)] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design 4. The assessment of local government unit (LGU) borrowing capacity should consider all information that could affect an LGU's ability to borrow funds. The failure to consider Legaspi City's plan to float municipal bonds overrated its borrowing capacity, which eventually led to its decision to withdraw from the project. All cities declared that they had more capacity to borrow than the executing agency/loan administrator recognized. Further, they stated they would have liked additional loan funding for, among other things, investments in (a) drainage and storm water control, (b) improvement/maintenance of the road network (asphalt batching), (c) water resource management, and (d) sewerage treatment. All LGUs would agree to provide collateral in the form of city assets or their budgeted internal revenue allocations (IRA). [Main text, paras. 6, 11, 63(v)] project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Sector Related Issues: Roading Sector Related Issues: Water resource management 5. Future ADB support should consider more flexible and responsive fund channels for local government units (LGUs). Cities found the documentary requirements of the Municipal Development Fund Office (MDFO) cumbersome and the process time-consuming. They also found transacting business with MDFO in Manila to be more costly than with other financial institutions with branches in the cities. Processing paperwork at MDFO was considered too time-consuming and centralized. In contrast, working with the Development Bank of the Philippines or Land Bank of the Philippines is considered easier since they have local branches in the participating cities. The cities would like to have direct loan agreements with ADB, or to have access to a municipal financing facility that is flexible and responsive to their requirements. [Main text, paras. 63(vi)] project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Finance & Financial Aspects: Financing Loan Agreement: Loan Agreement 6. Resettlement of displaced familties (as the case was for the Iligan drainage subproject) to distant sites requires mitigation measures that would address transport costs, lack of income opportunities, and shortage of water supply and electricity. The project completion report noted that about 20% of resettled families moved back to the city given the challenges of living in distant relocation sites. Considering the additional costs, LGUs will incur to address these concerns, support of other funding agencies need to be sought. [Main text, paras. 60, 63(viii)] project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Financing Country Context: Decentralization Crosscutting Issues/Themes: Employment 7. More frequent review missions could have helped to avert some of the loan cancellations, or to introduce a major change in scope of the project in time, as the implementing agencies desired. ADB staff conducted only five loan review missions, two special loan review missions, two loan administration missions, and a midterm review mission. While the missions were able to highlight urgent issues affecting project implementation, and helped facilitate execution through their recommendations, ADB failed to provide adequate backstopping, and has not been proactive in addressing or providing guidance on cancellations. [Main text, paras. 50, 63(ix)] project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Environmentally sensitive projects require Environmental Impact Statement (EIS) and Environmental Clearance Certificate (ECC). Proponents should be made aware that the processing of ECCs takes time. Tests and documentary requirements should be prepared in advance. If the proposed sites for the project are risky, alternatives should be identified. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Project Design: Project design The combination of loan and grant financing is well received. All participating cities considered ADB funds expensive. The combination of the AusAID-funded capacity building assistance with ADB-financed support for infrastructure subprojects has been widely appreciated as a successful and attractive model that provides added value to the recipients as well as to the executing agency and the funding agencies involved. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Lending modality Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Capacity building Country Context: Decentralization | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/regional-municipal-development-project
Small Towns Water Supply Sector Project | Philippines | Water and Other Urban Infrastructure and Services | 2006-04-08 | 1. The major issue affecting implementation of the project was the unavailability of national counterpart funding, which was beyond the control of the executing agency. The government had given assurance that adequate funds for the project would be allocated and released within the implementation schedule. Possible lack of counterpart funds was identified as a risk in project design and mitigating measures should have been identified so options were readily available when problems occured during implementation. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management 2. The larger water districts seem to be able to implement projects efficiently, financed by a combination of their own equity, internally generated funds, and loans. This opens the possibility of direct subsovereign lending. project cycle stage: Concept Feasibility Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Modality: Lending modality Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management 3. As far as exploitation of new water sources is concerned, firmer assurances on their availability should have been obtained before completion of detailed engineering design. This was particularly true for the eight large or medium-sized subprojects in the province of Bulacan that were relying on the Bulacan bulk water supply scheme. The cancellation of this scheme led to the cancellation of the eight subprojects after much work had been undertaken. project cycle stage: Design Lesson Topics: Project Design: Project design Project Design: Subprojects Sector Related Issues: Water resource management 4. The project performance monitoring system (PPMS) was initially planned to be a management tool to allow the executing agency to undertake efficient monitoring of the implementation status of all ongoing subprojects. The completion of the system should have been prioritized in the first part of the project to ensure that it would be available and operational during project implementation and not just an output after project completion. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project management Country Context: Prioritization The executing agency should have provided additional institutional and capability building support to newly established and small water districts to ensure the viability and sustainability of the investments. There is a need to further strengthen the small water districts' capacity to operate their water systems. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management The objective of providing water to low-income populations by providing public stand pipes appears to run counter to the objective of the water districts becoming financially viable. This was the reason given by the water districts for not including public stand pipes in the design of their water supply systems. The requirements to involve NGOs and to set specific targets for the number of beneficiaries living below the poverty line, appear to have been unrealistic in water districts whose first priority is to achieve financial viability. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Targeting When project components are transferred to other projects or programs, financed by external parties or the executing agency (EA) itself, the EA should be obliged to report on the output of these project components, since these form an essential input in achieving the project outcome. project cycle stage: Implementation, Completion Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project reporting | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/small-towns-water-supply-sector-project
Airport Development Project | Philippines | Transport | 2005-12-15 | Advanced action and periodic supervision remains the most important avenue available to ADB to ensure proper and timely land acquisition and resettlement (LAR) implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Project supervision Effective land acquisition and resettlement (LAR) requires that the Borrower assumes the ultimate responsibility on LAR financing and administration (in the case reviewed, responsibility was left to Davao City). project cycle stage: Feasibility, Implementation Lesson Topics: In areas with developed real-estate markets a sound compensation policy needs to include provisions fitting the local house-financing practices to ensure adequate compensation in line with market prices. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Industry and Trade Safety and security are important elements of airport design/layout and operations. To make sure that the relevant installations will be effective and efficient it is imperative that they are well planned and designed, and that the completed facilities are maintained in good working condition. The fence deserves particular attention, and must be kept clear of vegetation, so that patrol must be able to control its indemnity without difficulty. Monitoring of safety compliance should become a standard element of ADB's review missions. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Operation and maintenance Project Management: Project supervision Sector Related Issues: Transport planning Since loan covenants sometimes relate to long-term issues such as financial sustainability or maintenance of the facilities, it is necessary to have continued policy dialogue on pending issues, through portfolio reviews and future interventions, as an incentive for the Borrower to comply with the covenants beyond project completion. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Loan Agreement: Covenants Project Design: Problem identification Project Management: Operation and maintenance Policy & Reform: Policy matrix Sound land acquisition and resettlement (LAR) planning inclusive of systematic compensation policies and clear compensation rates agreed by the affected families (AFs) before project implementation is essential to prevent project delays and ensure equity in compensation. project cycle stage: Feasibility Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/airport-development-project
Local Government Unit Private Infrastructure Project Development Facility | Philippines |  | 2005-06-15 | A thorough demand analysis of local government units (LGUs) should have been conducted to ascertain target LGUs' willingness to participate in the project. To strengthen commitment, participatory approach during the design of such projects is absolutely necessary. The financial capacity of the identified LGUs to enter into loan agreements of several million pesos for preparation of feasibility studies and tender documents, which might or might not transform into actual LGU infrastructure, should have been examined first. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Loan Agreement: Loan Agreement Project Design: Project design Capacity Development: Capacity assessment Country Context: Decentralization Methodologies/Approaches: Participatory approach ADB could have insisted on an earlier project termination, when implementation progress was low and few potential subprojects had materialized. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Project management Project Management: Project supervision Coordination between the executing agency (Land Bank of the Philippines or LBP) and the other executing agency for Part A of the project (Build-Operate-Transfer Center or BOT) during project implementation left much to be desired. Although the BOT Center was quite proactive in producing marketing materials and conducting orientation seminars for local government officials, its activities had limited impact as its staff and offices are located only in the national capital (Manila). In contrast, although the executing agency has a far broader reach through its regional lending centers, which had been provided training, the level of interest and understanding at the executing agency-regional level remained low. The executing agency regional representatives could have enhanced their capacities to market the product to local government units (LGUs) by attending the training conducted by the BOT Center. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Private sector Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation Local executing agency (Land Bank of the Philippines or LBP) branches were usually the first agencies that the local government units (LGUs) approached when seeking funds for development projects. LBP loans include the cost of a feasibility study, so LGUs prefer to use government financial institutions (GFIs). Thus, LBP's role as a financial conduit should be carefully reviewed to minimize conflicts of interest. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Country Context: Decentralization The facility had limited focus in terms of activity and project eligibility. First, the facility offered loans only to finance feasibility studies and tender documents; it gave no funding for the ensuing project. Second, financing was restricted only for private sector projects and local government units (LGUs) were not fully keen nor familiar or comfortable with bidding projects out. The interest of LGUs would probably have been higher if the facility had allowed financing for LGUs to develop local government infrastructure. There were also problems with the terms of lending in terms of higher interest rate and the lack of understanding of the advantages of fixed-rate borrowing. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Procurement Country Context: Decentralization Sector Related Issues: Private sector The project design should have reflected a basic understanding of the dynamics of political cycles. Local leadership changed every 3 years, and the project selection process lay in the hands of the incumbent or newly elected local executives. More often than not, newly elected officials shelved projects that the former local executives initiated, especially if the officials belonged to different parties. Mitigating measures to alleviate the effects of political changes could have been included in the project design. For example, the project design could have minimized the risk of political interference by following the established division of work among government agencies, which designates the Department of Interior and local governments to assist in local government unit (LGU) infrastructure development. Furthermore, measures to alleviate negative effects of political changes could have been built into the design by adjusting the project schedule to mayoral terms. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Country Context: Decentralization | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/local-government-unit-private-infrastructure-project-development-facility
Rural Microenterprise Finance Project | Philippines | Finance | 2005-02-15 | A simple loan structure and minimum reporting requirements would minimize operational costs. In the future, ADB loans could be lent directly to the Land Bank of the Philippines (as for the World Bank Countryside Loan Facility, which provides funding for onlending over the limit of the Rural Microenterprise Finance Project, channeled through People's Credit and Finance Corporation or PCFC). The early delays in implementation could have been eased if the statement of expenditure (SOE-2) form were not required. A large amount of end-borrowers' information does not help in effective project monitoring, which largely relies on field verification conducted by PCFC and ADB missions. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Close coordination with a reliable executing agency and implementing agencies and quick responses to any required changes in loan conditions and microfinance institutions (MFI) accreditation are keys to success. ADB's interaction with the executing agency to modify the loan conditions in response to market needs significantly enhanced project implementation. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation Management information systems (MIS) development should take a tailor-made approach to the needs of individual microfinance institutions (MFIs), rather than providing a generic model which does not reflect the diversity of types of operations, the size of the institution, its operational focus, its geographic location and the local market demand. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Management information system The Rural Microenterprise Finance Project (RMFP) offered a uniform lending rate of 12% per annum to any accredited microfinance institutions (MFI). However, a more flexible means of setting interest rates to reflect the credit standing of individual MFIs may have to be considered. This would keep the RMFP investment credit facility attractive to those MFIs that have a higher credit status and access to alternative funding sources. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Rural development | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/rural-microenterprise-finance-project
Manila South Water Distribution Project | Philippines | Water and Other Urban Infrastructure and Services | 2004-10-15 | All three projects - Angat Water Supply Optimization Project (AWSOP), Manila South Water Distribution Project (MSWDP), and Umiray-Angat Transbasin Project (UATP) - were implemented by the same executing agency, and affected by the same issues, mainly delays resulting from the legal dispute about fiberglass pipes and the impact of privatization. They were also complex and, except UATP, involved several funding agencies. During implementation, the impact of one project was not always reflected in the planning of the other projects, which could have been mitigated by improved program management, and one senior person in charge of critical path monitoring, and risk management. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Risks/Risk management Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Policy & Reform: Privatization The failure to meet the projected nonrevenue water (NRW) reduction targets has greatly affected project benefits envisaged at appraisal. Considerable investment in water supply improvements has not resulted in the expected timely reduction of NRW, including in the project area of Manila South Water Distribution Project (MSWDP). It appears, that NRW reduction is far more complex and difficult than initially assumed. Projections for NRW reduction have major impact on the calculation of project benefits, and assumptions should therefore be conservative to avoid overestimation of project benefits at appraisal. Besides investing in system improvements, the utility must take responsibility for NRW reduction as an ongoing operational activity. Project design should make use of experiences gathered and lessons learned in NRW reduction from successful and efficient water utilities in the region. project cycle stage: Design, Feasibility, Appraisal, Implementation, Operation Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Health and sanitation management Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/manila-south-water-distribution-project
Umiray-Angat Transbasin Project | Philippines | Water and Other Urban Infrastructure and Services | 2004-10-15 | In cases where several, independent projects are implemented and serve a similar purpose, it is advisable to have one senior person responsible for program management, critical path monitoring, and risk management. Supervising the interrelationship of various components can facilitate decision making, especially limiting the damage caused by delays. Outsourcing of project management should be considered if there is a risk that the size or complexity of interrelated projects could exceed the capacity of the executing agency. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Human resources management Nonrevenue water (NRW) reduction is a more complex and difficult task than it initially appears. Projections of NRW reduction need to be conservatively estimated at appraisal to avoid overestimating project benefits. A project approach alone is not sufficient to reduce NRW. The utility must take responsibility for NRW reduction in terms of a routine operational activity. Experience shows that covenanting NRW reduction should be done with caution, as drivers for NRW are often difficult to get under control. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Design: Appraisal Project Management: Operation and maintenance Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/umiray-angat-transbasin-project
Angat Water Supply Optimization Project | Philippines | Water and Other Urban Infrastructure and Services | 2004-09-15 | Nonrevenue water (NRW) reduction is more complex and difficult than it initially appears. Appraisal projections of NRW reduction need to be conservatively estimated in line with the Project Design, to avoid over estimation of project benefits. One project is not sufficient to reduce NRW. The water utility must take responsibility for NRW reduction in terms of a routine operational activity while targeting at the same time 24-hour coverage with piped water. Experience shows that covenanting NRW reduction should be done with caution, as drivers for NRW are often difficult to get under control. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Design: Appraisal Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Health and sanitation management To avoid issues like the fiberglass pipe dispute and the leaking Aqueduct No. 5, provisions should be made to hire an independent technical panel of experts to provide advice regarding contentious problems. It is recommended to have one senior person responsible for program management, critical path monitoring, and risk management particularly for complex projects and those involving several funding sources. Seeing the interrelationship of various components can facilitate decision-making, especially limiting the damage caused by delays. project cycle stage: Design Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Management: Procurement Project Management: Project management Project Management: Risks/Risk management Capacity Development: Human resources management Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/angat-water-supply-optimization-project
Subic Bay Area Municipal Development Project | Philippines |  | 2004-09-15 | ADB could have insisted that the project be closed in late 2000, when very little implementation progress had beenachieved and many subprojects were canceled. At loan closing in June 2003, 38% of the loan funds disbursed were for interest during construction and commitment charges. An earlier termination of the project would have prevented this distressing outcome and the unnecessarily high costs for the government. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Project Design: Subprojects Project Management: Project supervision Coordination among the three executing agencies during project implementation was not satisfactory. Project implementation would have benefited from having one executing agency and one project management office (PMO) with full responsibility and accountability. The Department of Interior and Local Government (DILG) should have been the executing agency since it is the agency designated to assist local government units' (LGUs') development under the 1991 Local Government Code. SBMA, a government-owned and -controlled corporation, could have assisted project implementation as a member of Project Supervisory Committee (PSC). project cycle stage: Design, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Country Context: Decentralization Methodologies/Approaches: Consultation/Participation During project preparation, political risks should have been carefully reviewed. When the local political leadership that initiated the project changed during implementation, the project faltered. Project design could have minimized the risk of political interference by following the established division of work among government agencies, which designates the Department of Interior and Local Government (DILG) to assist local government units' (LGUs') infrastructure development. Further, mitigation measures against political changes could have been built into the design by adjusting the project schedule to mayoral terms. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Country Context: Decentralization Generally, local government units (LGUs) do not follow their own development plans consistently and development priorities tend to change. Recognizing this reality, the project should have built in more flexibility to accommodate additional LGUs and their components by adopting a sector loan approach. The drastic cancellation of loan funds requested during implementation could have been avoided if a sector loan approach had been chosen. In addition, the project should have examined more carefully each LGU's willingness to participate. If a project loan approach had to be chosen, appraisal of subprojects should be completed during loan processing, allowing procurement to begin upon loan effectiveness. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Lending modality Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Procurement Country Context: Decentralization Local branches of Development Bank of the Philippines and Land Bank of the Philippines apply their own appraisal methods, which are less strict than those of the Municipal Development Fund Office (MDFO). These government financial institutions (GFIs) also process loans more quickly than the MDFO. Local government units (LGUs), therefore, prefer to use GFIs. MDFO's role as a financial conduit should be carefully reconsidered. In recent projects, ADB has already used GFIs for channeling loan proceeds to LGUs. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Country Context: Decentralization Project design could have followed the procedures established by the Bureau of Local Government Finance (BLGF) in assessing the local government units' (LGUs') borrowing capacity. If other procedures were considered more appropriate for the project, the concerned government agencies should have been consulted on the use of those procedures. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Country Context: Decentralization When evaluating the capacity of selected local government units (LGUs) and water districts (WDs) to provide required counterpart funds, the project should consider only funds from sources that the LGUs can generate, collect, and allocate. At appraisal, the estimates of counterpart funds included allocations from Special Economic Zone Fund (SEZF) and Countryside Development Fund( CDF), which the LGUs did not control. Allocations from these funds were provided either very late or not at all, which prompted the cancellation of several subprojects. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Appraisal Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Country Context: Decentralization Sector Related Issues: Health and sanitation management While capacity building (Part B) was generally successful, the local government units' (LGUs') capacity for infrastructure development needs strengthening. None of the LGUs implemented civil works subprojects within the project period, except for Morong's market subproject. Their capacity to supervise engineering consultants and contractors has been limited. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Subprojects Project Management: Consultants Project Management: Project supervision Capacity Development: Capacity building Country Context: Decentralization While urban development can cover various types of infrastructure, projects should limit the number of components to keep implementation arrangements simple. Local Water Utilities Administration (LWUA) and its water supply component could have been covered by another ADB-financed water supply project. Inclusion of a water supply component, with LWUA as additional executing agency, unnecessarily complicated implementation arrangements. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/subic-bay-area-municipal-development-project
Kabulnan Irrigation and Area Development Project | Philippines | Agriculture, Natural Resources, and Rural Development, Education, Health, Transport, Water and Other Urban Infrastructure and Services, Multisector | 2004-08-13 | Future project design should emphasize agricultural extension, institutionaldevelopment, and credit for farmers. Consideration should also be given tofinancing of routine O&M costs during initial years of operation, while farmerslearn to manage new technology, and new irrigation facilities. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity development Capacity Development: Technology/Technology transfer Sector Related Issues: Irrigation management Sector Related Issues: Rural development The complementary activities under the project for watershed protection;provision of health, water supply, sanitation, and education facilities; andpromotion of women-in-development activities were highly relevant in achievingoverall development in the project area. A similar multisectoral approach shouldbe considered in future project designs. Use of nongovernment organizations (NGOs) for some of these activitieswas highly successful. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Gender Project Design: Project design Sector Related Issues: Education Sector Related Issues: Health and sanitation management Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Holistic approach The project's inability to meet the irrigation service area predicted at appraisalhas not only reduced the anticipated (and perhaps, overly optimistic) benefits inthe initial years of operation, but highlights the need to provide ongoing supportto complete on-farm facilities after project completion. The estimate of the designarea at project appraisal should be more realistic, giving consideration tocontinuation of funding to firm up the design service area after civil works arecompleted. project cycle stage: Appraisal Operation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development The rural roads component was highly instrumental in opening the project areafor development, and should be considered, seriously, in future irrigationprojects. The Project Completion Report (PCR) Mission noted that flexibility in adjusting the planned networkto meet local needs during project implementation has positive outcomes, andmight be replicated in future projects. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Process approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/kabulnan-irrigation-and-area-development-project
Power Sector Retstructuring Program | Philippines |  | 2004-07-15 | In Asia, the Philippines has been one of the first countries to encourage greater private sector participation in its power sector, as evident from its experience with independent power producers (IPPs) in the 1990s and recognition of introducing wholesale electricity spot market (WESM). However, the reforms pursued have yet to restore legislative and public confidence as the economic efficiency of state power utilities is low and electric tariffs remain one of the highest in the region. In wake of this, and given the legislative sentiments associated with the sale of transmission assets, developing consensus for the transfer of transmission franchise bill has been difficult. In designing power sector reforms and restructuring, it is important to consider political constraint as well as involve stakeholders to ensure buy-in of reforms. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Modality: Program Capacity Development: Ownership Sector Related Issues: Energy planning/management Sector Related Issues: Private sector Policy & Reform: Public sector reform Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation The Philippines is among the first developing member countries to implement fundamental power sector restructuring, requiring substantive privatization of generation assets and entering into concessionaire agreement with private parties for operating transmission assets, with the objective of achieving full competition. This is an ambitious and complex task given the prevailing economic environment and involves coordinated actions on legislative, regulatory, and policy measures spread over a reasonable long period of time. With hindsight, a more appropriate modality for fundamental power sector restructuring of the magnitude targeted under the Power Sector Restructuring Program would have been a cluster approach, where the reform actions are prioritized and sequenced in phases more realistically. In the first phase, the program could have concentrated on establishing a sound policy, legal, and regulatory framework for introducing new competitive markets, and laying the ground for transfer of assets, privatization, and absorption of stranded debt in subsequent phases. Therefore, power sector restructuring in developing countries is a long process and, as such, the design of policy reforms should recognize the need for a steady approach with a phased and realistic implementation schedule. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Modality: Cluster operations Modality: Lending modality Modality: Program Country Context: Prioritization Sector Related Issues: Energy planning/management Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Public sector reform Policy & Reform: Reform The program included 60 policy actions to be implemented. Though most of these actions have been complied with, some of the key objectives were not achieved. This is more an action-oriented program than an objective-oriented program. Program loans should be designed with fewer conditionalities, following the recommended cluster approach. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Modality: Cluster operations Modality: Program Policy & Reform: Policy matrix The program, as designed, underestimated the complexities of the prevailing investment climate, both judicial and regulatory, which plays a significant role in privatization of power entities. The legislative branch in the Philippines has some unique characteristics that render any key decision a lengthy process. The investment climate has been further affected by the judiciary overruling Energy Regulatory Commission (ERC) rulings and weak contract enforcement as manifested in case of some private sector deals involving public utilities. As such, ensuring adequate independence of regulator and broader improvements in governance of judicial system are critical for power reforms to move ahead in a timely manner. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Modality: Program Sector Related Issues: Energy planning/management Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Reform Theoretically, timely privatization of generation and transmission ought to help alleviate financial difficulties of public sector power utilities and ease government budget pressure. However, the program underestimated the nexus between the public sector liabilities and high fiscal deficit which impacts the ability to restructure the power sector. Over the last few years, inefficiencies of government owned corporations have perpetuated the fiscal deficit and eroded government's ability to upfront finance costs of structural adjustment of power entities, the settlements of which are critical to facilitating the privatization and restoring power sector's financial sustainability. As such, future power sector operations should recognize the nexus and complexities of debt resolution of state enterprises at a time of high and unsustainable fiscal deficits. In the Philippines, the fiscal deficit will continue to impede the prospects of an early absorption of National Power Corporation's (NPC's) stranded debt, which in turn affect the ability of NPC/Power Sector Assets and Liabilities Management Corporation (PSALM) to raise resources at competitive prices. Moreover, the restructuring cost should take into account the possible timing mismatch between cash inflows from the expected revenues of privatization and cash outflows, particularly in the initial years when key milestones of the privatization process are being passed. In such cases, provision of partial credit guarantee (PCG) is appropriate to support the government to keep the reform program on track and maintain momentum until the process is completed. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Modality: Program Sector Related Issues: Energy planning/management Policy & Reform: Privatization Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/power-sector-retstructuring-program
Rural Infrastructure Development Project | Philippines | Multisector | 2004-07-15 | Due to the lack of management knowledge among cooperative members and severe competition with private sectors, development of cooperatives is a slow process and requires proper monitoring and follow-on support to ensure their long-term sustainability. project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity building Sector Related Issues: Extension service Sector Related Issues: Private sector In addition to monitoring the physical and financial progress, the project management information system should also provide for collection of baseline information and periodic assessment of project intervention impact. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Management: Management information system The lack of peace and order may fail to attract qualified contractors from outside the project area, and awarding contracts to local contractors beyond their capacity will harm work progress and quality. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Capacity Development: Capacity assessment Country Context: Emergency With the timely technical and financial support from the central government, provincial and municipal governments can be highly effective in implementing development programs. A sense of local ownership enhances success and sustainability of development. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Capacity Development: Ownership Country Context: Decentralization | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-infrastructure-development-project-0
Women's Health and Safe Motherhood Project | Philippines | Health | 2004-06-15 | A Project Management Office (PMO) anchored in an appropriate organic unit of the executing agency is more effective than a stand-alone structure. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Clear and detailed terms of reference, essential qualifications, technical competency, and relevant experience should be specified for consultants. Technical and managerial capacities for consulting firms should be clearly defined. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Effective monitoring and evaluation requires that a simple set of indicators and guidelines for collection be designed at appraisal and made operational at the beginning of project implementation. The number of indicators selected at appraisal was too large, assumed data sources were inappropriate, and major surveys were left to government financing (subject to availability of budget). Baseline data was made partly available only after the midterm review. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Preparation of a complex and large-scale project, particularly in the context of devolution of health services and associated institutional reforms should entail more in-depth analysis of the potential risks affecting implementation. Project design should envisage adjustment to emerging needs, making projects more relevant, efficient, and effective. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Country Context: Decentralization Sector Related Issues: Health and sanitation management Policy & Reform: Reform Project coverage extending to one half of the country was too ambitious. This resulted in thin spreading of resources and capacities. Reduced project coverage, coupled with more extensive and comprehensive support within a project province, could have created the critical mass of health facilities for a better functioning, sustainable referral system. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Sector Related Issues: Health and sanitation management Top management support is critical to implementation. This was clearly the case during the latter part of implementation. A system of accountability must be clearly defined for all parties involved and effective mechanisms should be in place to ensure compliance. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corruption Project Management: Executing/Implementing agencies Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/womens-health-and-safe-motherhood-project
Forestry Sector Project | Philippines | Agriculture, Natural Resources, and Rural Development | 2003-11-14 | Consultants under the technical assistance (TA) on community-based, small-scale forest industriesshould have been fielded when comprehensive site development (CSD) was completed and people's organizationswere ready to pursue their recommendations. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Technical Assistance Project Management: Consultants Sector Related Issues: Industry and Trade Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach Delays in project implementation could have been minimized if the project relied on the executing agency's technical expertise and experience in survey, mapping, and planning (SMP) instead of relying on private survey firms that were unfamiliar with forest surveys and boundaries. Even though the loan agreement specified contractual arrangements for SMPs, ADB and the executing agency should have taken early steps to overcome the delays caused by incapability of private firms to carry out SMP. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Loan Agreement: Loan Agreement Monitoring & Evaluation: Data collection and management Project Management: Executing/Implementing agencies Sector Related Issues: Private sector Fund provision should have been made specifically for silvicultural treatment(weeding, thinning) 3-5 years after subproject site planting under cost-sharingarrangements with the relevant people's organizations. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Methodologies/Approaches: Civil Society Participation Loan consultants should have been recruited and fielded in the first year ofimplementation, and the appraisal of subprojects could have been carried out assurvey, mapping, and planning (SMP) work was being completed. project cycle stage: Implementation Lesson Topics: Project Design: Appraisal Project Design: Subprojects Project Management: Consultants Nongovernment organizations (NGOs) should have been screened more rigorously.The success of people's organizations in implementing comprehensive site development (CSD) and in developingthemselves into viable organizations depended heavily on assistance provided by the executing agency, particularly during the first 2 years of the subprojects. The people's organizations made earnest attempts to pursue livelihood projects; however, they lacked technical expertise and skills in marketing that would have enabled themto expand their projects into truly viable ventures. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Subprojects Project Management: Executing/Implementing agencies Capacity Development: Capacity building Capacity Development: Capacity development Crosscutting Issues/Themes: Employment Methodologies/Approaches: Civil Society Participation The project design was too ambitious, as the executing agency did not have the capacity, bothat national and regional level, to implement such a large-scale sector investment.It would be more feasible to undertake reforestation projects on a smaller-scalewithin a contiguous area, rather than as a sector investment with a nationwidegeographical coverage. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Lending modality Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment The subproject sites were spread out across remote areas and their sizes weretoo small to justify the construction of access roads and other infrastructure.Monitoring of activities in such areas was much more difficult and less effectivethan it would have been if larger and contiguous planting sites had been used. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/forestry-sector-project-1
Municipal Water Supply Project | Philippines | Water and Other Urban Infrastructure and Services | 2003-09-15 | A large amount of loan funds was canceled, including the unused contingency of$4.7 million. The contingency was estimated at more than 18% of the base costfor both foreign and local currency costs. To reduce unnecessary commitmentcharges, the contingency for foreign currency cost should be carefully estimated. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Foreign exchange Development plans of water supply networks should be gradual and carefullyscheduled to be sustainable. The institutional capacity in Calbayog City and GeneralSantos City could not keep pace with the rapid physical expansion of servicenetworks. A master plan matching institutional capacity with service expansion is needed. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Policy & Reform: Policy reforms/framework During construction, a public awareness campaign on the merits of piped waterand a calibrated marketing campaign to attract new customers are essential tooptimize construction schedules and cost recovery. In most cases, distributionlines and service connections were installed separately because customers hadnot decided to subscribe to the service when distribution lines were laid. It would be more efficient to install distribution lines and service connections at the same time to avoid repeated excavation and restoration works. For this purpose, eachwater district's (WD's) marketing team should work closely with its construction team. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Health and sanitation management Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation In general, the executing agency (Local Water Utilities Administration or LWUA) and the water districts (WDs) need to enhance their capabilities to supervise contractors. During bidding and construction, LWUA and the WDs were misledby the contractors' alternative proposals for different materials and construction methods from the original specifications. Sometimes the alternatives turned out to be of poor quality, resulting in a delay to secure the necessary quality. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project supervision Capacity Development: Capacity building Sector Related Issues: Health and sanitation management In scheduling construction works, upstream water source development should besynchronized with installation of downstream distribution lines. This is essentialto expedite cost recovery. In Calamba, the distribution lines installed(downstream) stayed unused for a long time waiting for water sourcedevelopment works (upstream) to be completed. Gaps in the constructionschedule increase the interest paid by water districts (WDs). project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Sector Related Issues: Health and sanitation management Some construction works were delayed waiting for the executing agency's (Local Water Utilities Administration's) approval of variation orders. Some decisions should be delegated to the lower levels of the organization. In particular, resident engineers could be given greater authority to make decisions since they are in a position to directly observe constructionworks. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Country Context: Decentralization Some contractors tried to install second-hand equipment that was rejected by thewater district (WD) on site, resulting in a delay while new equipment was delivered. To avoidthis, the executing agency (Local Water Utilities Administration or LWUA) and the water districts (WDs) should vigilantly review a contractor's proposal for selected equipment prior to delivery. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Health and sanitation management To avoid engaging financially weak contractors, more stringent evaluation of their financial capacity is necessary during bid evaluation. Further, the executing agency (Local Water Utilities Administration or LWUA) may consider increasing the percentage of performance security against the contractfrom the current 10% to discourage financially weak contractors from bidding. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Water demand forecasts should be realistic. For two water districts (WDs), demand was overestimated and they currently have an over supply of water. Piped water is a value-added substitute to which people will switch if they are convinced about the additional value for the price paid. In particular, the price elasticity of demand should be carefully considered in making demand projections. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/municipal-water-supply-project
Nonformal Education Project | Philippines | Education | 2003-09-15 | A weak government budgetary commitment prevented nonformal education (NFE) to be fully institutionalized nationwide and to make the project sustainable. Without adequate budgetary allocation of the government, project impacts cannotbecome sustainable. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Counterpart funds Sector Related Issues: Education Essential data, e.g., baseline literacy rates, and systematic operational guidelines for functional education and literacy program (FELP) and nonformal education (NFE) accreditation and equivalency (A&E), should guide implementation and evaluation of NFE projects. The importance of a simple management information system (MIS) cannot be underestimated. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Project evaluation Project Management: Management information system Project Management: Project management Sector Related Issues: Education Project design should incorporate adequate horizontal and verticalcommunication involving many stakeholders at different levels to maximize thequality of project implementation. Project designs should envisage adjustment to address any shortcomings at the early stage of implementation, which will make projects more relevant, efficient, and effective. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Process approach Project design was too ambitious and complex to be completed in five years. This resulted in weak institutional arrangements for project implementation. Future intervention should adequately assess the capacity of the executing agency and implementing agencies upfront for projects of this nature. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment The inclusion of four nongovernment organization (NGO) umbrella organizations gave them a major role in nonformal education (NFE)delivery and helped speed up implementation. However, the experience gainedcould not be transferred to other NGOs at grassroot level thus limiting thecapacity building impact at NGO level. project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity building Sector Related Issues: Education Methodologies/Approaches: Civil Society Participation To augment a demand driven approach to delivery of service, the project designshould be based on a more comprehensive analysis of institutional, social, andeconomic demands. Without employment opportunities, livelihood skills acquiredthrough nonformal education (NFE) do not lead to higher income. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/nonformal-education-project
Capital Market Development Program (Loan 1363-PHI) | Philippines | Finance | 2003-08-31 | Development of a new market structure and associated institutions is time consuming and the program loan modality though used for this purpose should not have a quick-disbursing nature when applied to an overall sector development agenda. Instead, multitranche loans spread over a longer time horizon associated with key components of the program or a cluster program approach is preferable. project cycle stage: Appraisal Lesson Topics: Modality: Cluster operations Modality: Program Project Design: Project design Policy & Reform: Reform Given that institutional development is a continuing process that needs continuing monitoring, short-term technical assistance (TA) modality that enables international consultants to only provide recommendations may not be the most suitable way to address this continuing capacity building. Instead of TA grants, which are limited to short-term small infusion of funds from ADB, longer term TA loans, sector development programs, or cofinancing arrangements with other institutions may be more appropriate for such capacity-building initiatives. These TAs should be geared to clearly identifying capacity-building needs and should include sufficient funds and duration, not only to derive recommendations but also to implement them. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Capacity Development: Capacity assessment Capacity Development: Capacity building In undertaking financial reforms, the need for interaction between the component submarkets must be recognized. Therefore, an explicit overall holistic capital market reform agenda has to be formulated carefully and painstakingly considering the unique features of the economy and issues confronting it. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Policy & Reform: Reform Methodologies/Approaches: Holistic approach The creation of new laws does not guarantee meaningful reforms and the desired development. To achieve the desired development, many other conditions have to be fulfilled. First, the intended legislation needs to correspond with the final form of the law, and this is not always true especially if the passage of the law is delayed over many years. In addition, the relevant institutions must also have the capacity to enforce the new provisions of law, and finally private sector participants should be willing to abide by the new legal framework. Therefore, it is important that prior to the enactment of legislation, a new set of dynamics is set in motion in the form of administrative measures and memoranda of understanding through a participatory dialogue. By doing so, in effect, the implied actions of the proposed law can be put into place at the same time the law is passed. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Loan Agreement: Covenants Capacity Development: Capacity assessment Sector Related Issues: Private sector Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation The legislative process is designed to take time to ensure that all concerns from various stakeholders can be raised and to prevent the possible abuse of dominant institutional parties. The long delays associated with passage of law have been evident in implementing many of the approved program loans. Therefore, the passage of a law could be a program condition in a cluster program loan approach where its passage may be a precondition for the next phase of the program. This could be a useful way of promoting legislative reforms without undermining the ongoing program to the prolonged and unpredictable process. In addition, if improvements to regulations are required, alternatives to legislation through rules and administrative orders should be explored prior to formulating legislative action as program conditions. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Loan Agreement: Covenants Modality: Cluster operations Modality: Program Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation The overall capital market agenda works best if it is designed through the collective voice of stakeholders. Not only should there be active and formal discussion among stakeholders, but the means for reform must emanate from a visible high-level entity that is seen as representing the spectrum of interests in the capital market. This is not only an issue of participation but also that of transparency in the ownership of ideas and delegating responsibility for specific endeavors. In the Philippines, this was attempted through the Capital Market Development Council (CMDC), which helped in crafting a reform agenda agreed by consensus between the regulators and the regulated, speaking in a collective voice while trying to dissipate both political sensitivities and potentially conflicting interests among stakeholders. Based on the positive impetus created by CMDC, a lesson could be learned about establishing and finding a means to sustain such forums during the development of capital markets in any country. While the establishment of such markets could initially be funded by grants for demonstrative effect, it may be possible to generate a long-term fund through a levy imposed on the members of CMDC when the importance and the usefulness of the forum become evident. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Ownership Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/capital-market-development-program-loan-1363-phi
Nonbank Financial Governance Program | Philippines |  | 2003-08-15 | A main focus of the program has been on supporting institutional change and capacitybuilding. Its emphasis on developing a strong capital market regulator with adequate powersand capacity is of fundamental importance for sound and sustainable capital marketdevelopment. However, it should be recognized that parallel reforms of the primary andsecondary market are also crucial. Given the significant structural change advocated for the Philippine Stock Exchange (PSE), which has long been dominated by small brokers, it has taken longer to transform the exchange.Fundamental governance reforms of the stock exchange require extensive stakeholderconsultation and agreement, and once this has been realized, the technical process ofdemutualization requires appropriate planning and conducive market conditions. Both Phase Iand II of the program provide support for this and the process will need to be closely monitoredgiven pressures from vested interests to delay the process of change. project cycle stage: Concept Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Program Capacity Development: Capacity building Capacity Development: Capacity development Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Sound capital market development also depends on parallel reforms aimed atstrengthening governance at the corporate level. The program design included appropriatesupport for strengthening corporate governance through increasing the number of independentdirectors on the boards of listed companies and strengthening financial disclosure requirements.To strengthen impact in this area, a proactive stance by the Securities and Exchange Commission (SEC) and the Philippine Stock Exchange (PSE) is critical to ensure thatcompanies effectively implement corporate governance standards. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Modality: Program Policy & Reform: Reform The Asian financial crisis highlighted underlying structural weaknesses in the financialsector and their economy wide implications, and a major trading scandal in 2000 drew particularattention to the need to strengthen capital market governance. Recognition of this helpedcatalyze fundamental reforms and the draft Securities Regulation Code (SRC), which had been pending in Congress, wasreviewed comprehensively and enacted with broad support from the legislators as well asmarket participants. Crisis provided an opportunity to move forward with difficult reforms, andADB's longstanding involvement in the sector through technical assistance (TA) and policy dialogue helped ensurethat reforms were appropriately considered and designed. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Modality: Technical Assistance Country Context: Crisis/Post-crisis Policy & Reform: Policy matrix Policy & Reform: Reform The implementation experience of the program reinforces the findings of ADB's 1999 review of its program lending policies - namely, that flexibility is important when designing programs that address second-generation challenges whose reform trajectories are uncertain. The program's single tranche/cluster approach allowed for enhancement of the Phase II agenda to take account of changed circumstances, evolving government priorities, and additional reform opportunities. While the tranche release under Nonbank Financial Governance Program (NFGP) was a one-time event in 2001, it was effectively anchored on extensive policy and analytical work carried out in the nonbank financial sector between 1998-2001 and provided direction for further reforms during 2002-2003 supported by technical assistance (TA) and policy dialogue. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Modality: Cluster operations Modality: Lending modality Modality: Program Modality: Technical Assistance Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/nonbank-financial-governance-program
Low-Income Upland Communities Project | Philippines | Agriculture, Natural Resources, and Rural Development | 2003-07-15 | Project facilitation by community organizing could have been further enhanced, ifthe roles of all implementers, particularly nongovernment organizations (NGOs), were better defined at thecommencement of the project. More rigorous screening of NGOs is critical. project cycle stage: Design Lesson Topics: Project Design: Project design Methodologies/Approaches: Civil Society Participation Sustainable environmental management is possible only when accompanied bysustainable economic development of communities. The project provides a goodmodel for reaching the poorest of the poor through viable economic developmentand sustainable environmental management. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Project Design: Project design The local application of sloping agricultural land technology (SALT) failed. To ensure sustainability, any farming system to be introduced to indigenous peoples must be adjusted to local conditions andshould have a relatively low maintenance cost. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Crosscutting Issues/Themes: Vulnerable groups Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Rural development The project's success reaffirms the validity of using a holistic approach thataccommodates various priority needs of the people and adopting a participatoryprocess in its planning, design, and implementation. Winning theconfidence of some sections of the Mangyan communities in regard to projectgoals and objectives was a slow process, but they ultimately contributed to theproject's successful implementation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Vulnerable groups Methodologies/Approaches: Holistic approach Methodologies/Approaches: Participatory approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/low-income-upland-communities-project
Country Assistance Program Evaluation for the Philippines (2003) | Philippines |  | 2003-01-31 | Political and macroeconomic stability is a critical factor behind the success of a development assistance program. ADB support in programs and projects has been more successful when they have been implemented in the context of a stable political and macroeconomic environment. In the last 2 decades or so, the Philippine program was often interrupted and accordingly modified in the face of internal and external shocks that hit the economy. This disruption in the smooth implementation of projects and programs had a major adverse impact on their final outcome and success. project cycle stage: Implementation Lesson Topics: Project Management: Project administration Country Context: Crisis/Post-crisis Project design should be relatively simple. Project designs that are too complex and impose excessive demands on the organizational capabilities of the implementing agencies are likely to fail. Lending to the Philippines in the early part of ADB history, which was characterized by small, simple loans that made modest demands on the organizational capacity of EAs, was relatively successful. Subsequently, as ADB substantially increased the average loan size as well as the complexity in design, there was a corresponding increase in the incidence of failures. Unless there is rapid improvement in the institutional capacity of LGUs, recent evidence suggest that devolution might lead to a further increase in the incidence of failures. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Institutional analysis Country Context: Decentralization Project success requires careful project preparation. An important cause of project failures in the Philippines has been the lack of careful project preparation. Careful project preparation should include detailed analytical work such as site investigations and diagnostic assessments of macroeconomic and market conditions, geological and environmental conditions, demand growth potential, input availability, risk factors, policy environment, and institutional capabilities. In addition, quality of investments and sustainability of impact require that beneficiaries should actively participate in the design and implementation of projects. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Institutional analysis Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation Success of the assistance program depends on its ability to nurture institutional development. Weak institutions have often been cited as a principal cause of failures in the development assistance program in the Philippines. Strengthening these weak institutions would entail improving organizational structures, streamlining procedures, reforming incentive systems, and training both implementers and project clientele. ADB TAs can make an important contribution to nurturing institutional development. To improve management of development assistance activities, there is a need to further streamline government systems and procedures related to project administration and conduct sector studies that identify emerging needs and challenges that sectoral agencies are likely to encounter in the medium term. project cycle stage: Design, Operation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Public governance Crosscutting Issues/Themes: Sustainability Modality: Program Modality: Technical Assistance Project Management: Project administration Capacity Development: Capacity building Capacity Development: Capacity development Sustaining development impact requires close monitoring during implementation and after project completion. The Philippine experience strongly suggests that the quality of project monitoring has an important bearing on project success. To improve project monitoring, some institutional innovations are warranted. Past efforts at capacity building in benefits monitoring and evaluation have been largely ineffective as the responsibility was located in the project management unit, and not integrated into the mainstream activities of agencies. Moreover, these monitoring and evaluation efforts were largely limited to developing survey instruments and manuals rather than to institutionalizing the system, as noted in an impact evaluation study. Although there is widespread recognition of the importance of monitoring and evaluation, this recognition has not translated into strong commitment to these activities. This lack of strong commitment, and ownership, at a sufficiently high level of the government is often reflected in insufficient budget and staff allocation. In addition, these activities also suffer from a lack of status within the institutional hierarchy, absence of 'champions for evaluation,' and lack of participation of key stakeholders in the process. project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Counterpart funds Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-philippines-2003
Metropolitan Cebu Water Supply Project (Loans 1056-PHI[SF]/1057-PHI) | Philippines | Water and Other Urban Infrastructure and Services | 2002-12-31 | Because of lack of quantifiable and measurable targets with regard to project beneficiaries and inadequate monitoring, it is not apparent that the targeted 30% proportion of the poor has been reached. However, communal water association can be an appropriate intermediate delivery program for water supply to the poorer population until they can obtain individual connections. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Water resource management Despite the higher than average tariffs in the project area than in the rest of the country, the residents are willing to pay for good-quality water and a reliable service. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management Inaccessibility of the wells built in the late 1980s demonstrates the need for extensive public consultations with the potentially affected people. Insufficient attention was given to the preparation of proper environmental and social impact studies and dissemination of the results. Consequently, the well field and the transmission pipes financed under the project have not been used effectively. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation The project delays due to problems with producing the filter media for the infiltration basin show the importance of procedures for evaluating consultants and contractors. Had quality- and cost-based selection methods been used, the 4-year delay in building the infiltration basin could have been avoided. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Project Management: Procurement Sector Related Issues: Health and sanitation management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/metropolitan-cebu-water-supply-project-loans-1056-1057-phi
Second Palawan Integrated Area Development Project (Loans 1033-PHI[SF]/1034-PHI) | Philippines | Agriculture, Natural Resources, and Rural Development | 2002-12-31 | A village-level benchmark survey could be combined with community mobilization in a village at the commencement of a subproject. project cycle stage: Implementation Lesson Topics: Project Design: Subprojects Capacity Development: Capacity development Capacity building for local governments and social preparation for the poor should be conducted prior to physical investment. Since these activities are time consuming, technical assistance from aid agencies could be used to build up local capacity prior to the design of loan projects. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity building In line with decentralization, integrated area development projects are better implemented by local governments, which are more attuned to the needs of their voters and the delivery of project benefits. National line agencies could participate as contractors to provide services based on client demand. project cycle stage: Design, Feasibility Lesson Topics: Investment in extension or training centers needs to consider the real value of such centers as well as factors that may reduce the expected outcome such as shortage of staff and operational budgets after project completion. In most cases, the key constraint to agricultural extension is not a lack of buildings or training venues but shortage of staff and travel budget. project cycle stage: Feasibility Lesson Topics: Project Management: Operation and maintenance Project Management: Risks/Risk management Multiple interventions are needed for rural development and poverty reduction. To achieve real synergies, integration of project activities should be based on client demand and conducted at the village level instead of letting different line agencies independently implement different project components. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach Project benefit monitoring will be most effective and efficient if local governments and communities are provided with strong incentives to monitor. Proportionate sharing of cash investment cost and allocation of project budget to local governments may be useful for this purpose. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Benefit monitoring and evaluation Project monitoring should focus on project benefits rather than physical targets so as to draw the attention of project staff to the purpose of public investment. The newly introduced results-oriented monitoring is a step in the right direction. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration Public investment in comunal irrigation systems (CISs) tends to be overdesigned. This leads to inefficiencies and poor sustainability. Due to their small size, most communal irrigation systems (CISs) benefit a small number of the better-off groups instead of the poor. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Irrigation management Sector Related Issues: Private sector Regulations need to be developed to ensure exclusive use of the fund for emergency purposes. This measure will help screen out subprojects with poor sustainability, as local governments and beneficiaries that are unable or unwilling to contribute to the fund will likely be unable or unwilling to take care of the facilities after construction. project cycle stage: Feasibility Lesson Topics: The top-down approach of designing a subproject by consultants with beneficiaries being informed of the investment decision leads to weak ownership of the subproject and poor sustainability. A better alternative is to let beneficiaries participate in subproject decisions, and share a proportionate cash investment. project cycle stage: Design Lesson Topics: Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation When expanding a regular government program, its strengths and weaknesses need to be carefully studied. Under the project, the livestock program distributed animals to farmers free of charge in the name of helping the poor, but ended up benefiting a small number of the better-off groups at a high cost to the government. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Sector Related Issues: Rural development | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-palawan-integrated-area-development-project-loans-1033-1034-phi
Power Transmission Project | Philippines | Energy | 2002-12-13 | Although the project's transmission components were generally implemented as conceived at appraisal, implementation delays became a major concern to ADB, and raised local costs significantly. The executing agency (National Power Corporation or NPC) could have mitigated many of the delays with forward planning and effective project management. NPC's management style was generally reactive, with little anticipation of emerging problems. The project would also have benefited if more activities such as separate administration of supply and install contracts in Mindanao had been carriedout in parallel. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Local currency Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Sector Related Issues: Energy planning/management Parts C, D, and E of the project were not closely integrated with parts A and B. Part C was envisaged to be financed by the ADB loan, but ADB agreed to its cancellation. The Report and Recommendation of the President (RRP)did not detail the objectives and scope of parts D and E, nor their financing arrangements. ADB review missions did not monitor or supervise these two parts because the World Bank and USAID financed them, through different projects. Closer coordination with those agencies would have helped assure ADB that project objectives were met. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Project design Project Management: Project supervision The project schedule at appraisal was unrealistic because it did not include adequate time (i) for the executing agency to comply with the covenants in the loan agreement, which were conditions for loan effectiveness, (ii) for arrangement of cofinancing, even though there were no firm cofinancing commitments when the ADB loan was approved, or (iii) for the evaluation and award of contracts, given the complexity of the executing agency's internal contracting procedures and the need for ADB approval before contract award. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-transmission-project
Sixteenth Power (Masinloc Thermal Power) Project (Loan 1042-PHI) | Philippines | Energy | 2002-10-31 | Despite the initial delays, project construction was relatively smooth and within the revised schedule. This was largely due to the adoption of a single turnkey contract for all project components. It is likely that the turnkey approach, compared with multicontract packaging, resulted in cost savings as well as a shortened construction period, perhaps by as much as a year. A downside of the turnkey approach as used in this case was that all the payments were made in foreign currency. project cycle stage: Appraisal Lesson Topics: The project suffered from a major front-end delay of about 3.5 years. It may be preferable for projects of this type to acquire the necessary land and rights-of-way before loan approval. Regarding resettlement, the following is essential: preparation of a comprehensive resettlement program by a team of experts from diverse disciplines, a separate environmental impact statement for the resettlement site, and a feasibility study of livelihood programs; engagement of a full-time community organization and relations officer to assist project-affected family (PAFs) in their adjustments; and participation of PAFs in the design and implementation of the livelihood programs. In short, resettlement should be based on a time-bound action plan of documented measures, be founded on a sound legal basis and a cogent assessment of the pre project socioeconomic situation, and be fully communicated to all PAFs. This would facilitate its acceptance by PAFs and allow a clear comparison of what was intended and what was actually achieved. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Civil society Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Resettlement Monitoring & Evaluation: Impact evaluation Project Design: Appraisal Project Design: Project design Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/sixteenth-power-masinloc-thermal-power-project-loan-1042-phi
Forestry Sector Program (Loans 889[SF]/890-PHI) | Philippines | Agriculture, Natural Resources, and Rural Development | 2001-12-31 | A part of the investment program was to provide long-term plantation forest resources to sustain wood-based industry and to avoid the import of wood and wood products at a high cost to the economy. The private sector contributed to the investment during the period of the project but has done little more than replant in existing plantations since. The design of much of the government sector planting has not been with a view to future timber harvests but for protection of forest resources against degradation only. Therefore, the onus of meeting the future needs of the country falls on the private sector. The inability of the government to generate adequate income from the areas that it planted under the project provides a further reason to turn over as much as possible to the private sector, including community groups, for exploitation so as to generate the revenues required for the long-term protection of the forests. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Sector Related Issues: Private sector Methodologies/Approaches: Community approach Components of a forest management and conservation program should directly address the basic cause of forest degradation, namely, poverty and landlessness. Greater emphasis should be placed on the people rather than the natural resources if the benefits of the project are to be sustained. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Human resources management Sector Related Issues: Rural development NGOs such as farmer cooperatives and community groups are far better than city-based organizations in effectively implementing reforestation projects. The most successful groups are those resident in the area. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach Policy changes need to be accompanied by enabling legislation. The key impediment to real policy reform is the outdated Presidential Decree 705 (Revised Forestry Code). Constant changes of policy through the issuance of department administrative orders raise perceived risks for the private sector and discourage further investment. The number of requirements to be complied with in order to plant or harvest industrial tree plantations (ITPs) and community-based forest management agreement (CBFMAs) creates a burden that will discourage all but the most committed of tree planters. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Legal system Project Management: Risks/Risk management Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework The most common difficulty experienced by people involved in actual implementation in the field was insufficient lead time to do necessary planning, NGO screening, and community organizing. The investment component should have been spread over eight years rather than five. project cycle stage: Design Lesson Topics: Project Design: Project design Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach The project was too focused on physical outputs, and long-term qualitative outcomes in the forestry sector were not given sufficient emphasis. A program design that allows for rolling (multiyear) targets, consciously considers quality and outcomes (as against outputs), and incorporates community participation processes may be more appropriate for complex types of programs. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Modality: Program Project Design: Project design Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/forestry-sector-program-loans-889sf-890-phi
Fisheries Sector Program (Loans 971[SF]/972-PHI) | Philippines | Agriculture, Natural Resources, and Rural Development | 1999-12-31 | A time-bound action plan should be based on realistic assumptions of both the implementation capacity of the executing agencies and other exogenous factors. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Institutional analysis Development of sustainable alternative livelihood projects is particularly difficult in coastal and rural areas. There is need to devise an innovative microcredit component to link with these projects to ensure their sustainability. The existing livelihood of the fisherfolk is closely interlinked with their cultural practices. New approaches need to be developed, and adequate time should be provided for social preparation of the target beneficiaries. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Country Context: Cultural constraints Crosscutting Issues/Themes: Employment Sector Related Issues: Rural development Program design should take into account the country's political structure and legal system; they may impose constraints on the pace of policy reforms and investment activities. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Project design Policy & Reform: Policy reforms/framework Methodologies/Approaches: Program Approach Programs that are broad in scope and have complex and dynamic parameters should be designed using a phased development (or process) approach to allow for progressive understanding of changing conditions in the program area. A process approach provides a basis for designing project activities for the succeeding phases, and allows interim evaluation of the project components already initiated. This, in turn, allows necessary changes/modifications for subsequent phases to be identified. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Methodologies/Approaches: Process approach Methodologies/Approaches: Program Approach The availability of capable locally based NGOs or people's organizations at project sites is often overestimated. Future programs/projects requiring NGOs should emphasize the importance of (i) reviewing the existence of capable locally based NGOs prior to finalizing project design; and (ii) selecting potential project sites based on the availability of capable NGOs. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity assessment Country Context: Prioritization Methodologies/Approaches: Civil Society Participation When formulating policy reforms, a comprehensive review and analysis of the sector, followed by continuing policy dialogue over an extended period, are important. Attention must also be given to the appropriateness and timing of targets for the attainment of policy goals and objectives. Many policy reforms and associated investment activities require time to have demonstrable impact. The design of projects with a policy reform component should (i) incorporate measures to help attain policy objectives (e.g., information and education campaign); and (ii) allot sufficient time for the social and technical preparation of those who will be affected by, or involved in, policy implementation. Political will must also be strengthened, and an active constituency based on sustainable development and resource management ensured. A longer time frame is needed for a sector development program. ADB needs to pay greater attention to sector issues and sector development programs, and establish a pragmatic time frame for policy reforms to have an impact. project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Methodologies/Approaches: Program Approach Methodologies/Approaches: Targeting With devolution, the planning, design, and implementation of fisheries programs/projects should involve the local government with jurisdiction for the proposed activity. Local government involvement during the early stages of program planning and design will encourage and strengthen local government support of program activities, and provide a mechanism for determining and delineating responsibilities during program implementation. Such a strategy will also enhance the effectiveness and efficiency of program/project execution. This will result in maximum benefits as a result of better coordination and cooperation of the national agencies and local government units. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Problem identification Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Institutional analysis Country Context: Decentralization Methodologies/Approaches: Consultation/Participation | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/fisheries-sector-program-loans-971sf972-phi
Third Development Bank of the Philippines Project (Loan 1088-PHI) | Philippines | Finance | 1999-12-31 | Access to credit, both working capital and investment capital, rather than its availability constrains SME development. This accessibility problem stems partly from lack of information flow about the SMEs and lack of marketing and management facilities. In designing a project that addresses only one of the constraints for SME development, ADB should, through a policy dialogue with the government, ensure that other constraints are separately addressed as well. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy matrix Separating SME lending programs from those that also cater to large-scale clients for SME lending may be more effective.The extent and the nature of the demand for credit should be assessed separately for SMEs, and the terms and conditions of the loan and its ability to fulfill the needs of SMEs must be carefully reviewed. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Some eligibility criteria involved environmental regulations and other aspects that drove the participating financial institutions to ensure compliance. Specification of eligibility criteria based on development impacts such as regional development, employment generation, and saving foreign exchange and using them as monitorable indicators may provide a better incentive for concerned parties to pay serious attention to expected development impacts. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Finance & Financial Aspects: Financing Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design The project fell short of achieving the developmental objectives of ADB due to its broad formulation and design focusing on the credit needs of SMEs as well as accommodating larger enterprises under a common credit facility. ADB needs to be careful not to compromise its developmental objectives when accommodating clients requests to finance larger enterprises. project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design The TA accompanying the loan trained executing agency staff to assess eligible and viable subprojects. The TA would have been more effective if the staff members trained in SME lending (especially in rural areas) had been in place and performing before the participating financial institution (PFI) received the credit influx. As the TA was a prerequisite on which the project s success depended and was only partly funded by ADB, it was necessary for ADB to follow-up to find out whether adequate funding was available to achieve all of the TA objectives. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity building | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/third-development-bank-philippines-project-loan-1088-phi
Highland Agriculture Development Project (Loan 802-PHI) | Philippines | Agriculture, Natural Resources, and Rural Development | 1998-06-30 | Beneficiary participation in the planning and design of project components can improve the relevance of project-supplied facilities to the needs of the beneficiaries. Continual assessment of the design assumptions during implementation, and flexibility in responding to new information, can further improve a project. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation Project Design: Project design Methodologies/Approaches: Consultation/Participation Improved road access can lead to a large and rapid expansion in the area planted to crops, increasing the risk of deforestation and erosion. Careful study of proposals for new roads so as to avoid such problems appears warranted. Such studies should assess the environmental impacts and mitigation measures and formulate proper environmental management from the early phases of project preparation. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Project Design: Appraisal Sector Related Issues: Roading Integrated pest management under the project embodied more than just the control of pests and was able to encourage improved fertilizer and crop management practices with benefits other than just pest control. Farmers appear willing to adopt integrated pest management , although in the project area, this was probably a reflection of the high expenditure on agricultural chemicals by vegetable farmers. project cycle stage: Feasibility Lesson Topics: Sector Related Issues: Extension service Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach The development of beneficiary associations to effectively manage facilities such as a Communal Irrigation System and credit funds is a lengthy process requiring more inputs than those provided under the project. The provision of long-term support for building groups must be balanced by the need to avoid developing a dependency within the groups on outside support. project cycle stage: Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Capacity Development: Capacity development Sector Related Issues: Irrigation management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/highland-agriculture-development-project-loan-802-phi
Bank Operations in the Road Sector in the Philippines | Philippines | Transport | 1997-12-31 | ADB's past road project appraisal and postcompletion reporting and monitoring procedures have not been entirely successful in warning of the potential effects of indifferent project implementation standards. With the use of more modern Highway Design and Maintenance Standards Models, more rigorous definitions of the without-project situation, which are crucial in the definition of project benefits, should be clearly described in the Appraisal Reports. In view of the importance of the assumption that reductions in road user charges are passed on to users of road transport services, much greater emphasis should be placed on monitoring real changes in road transport rates in response to road improvements. ADB and other foreign sources will have to monitor more closely and be involved on a continuing basis in network-wide expenditure prioritization, planning, and programming within the core executive institution of the road sector. Aid agencies also need to pay greater attention to the network as a whole (e.g., total network data quality) and not just on each individual agency's 'project' concerns. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Appraisal Project Design: Project design Sector Related Issues: Roading Inadequate road maintenance, particularly the periodic or preventive maintenance, has been a continuous source of concern to all foreign funding agencies involved with the road sector. Experience from the road projects has indicated that the economic costs resulting from a failure to maintain what are probably the nation's most valuable infrastructure assets have been high. The results of inadequate maintenance have been more severe than in other countries because of the variable standards of implementing roadworks. Part of the problem has been attributed to constrained budgets and the other significant part has been the absence of a 'maintenance culture' within the institutions administering the nation's road networks. To address this problem, consideration should be given to replace the Equivalent Maintenance Kilometer system by a totally new maintenance, planning and budgeting system based on reliable information on road and bridge conditions and maintenance costs. In addition, the new system should take into account the maintenance of nonnational roads in view of decentralization policies. project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Operation and maintenance Country Context: Decentralization Sector Related Issues: Roading Many of the shortcomings in the present management and financing of the road network can be attributed to the traditonal institutional and budgetary framework. Roads are administered more like a social service rather than managed like a quasi commercial enterprise. The financial resources for expenditure on roads come from general taxation, domestic borrowing, and foreign assistance. The locally financed component suffers from the vagaries of the highly politicized annual budget process. There is no necessary connection between tax revenue raised from road users and the expenditure requirements of the road network. Radical new initiatives for the reform of the financing and management of highway networks have been considered and the most successful efforts combine a major institutional reform with a reform of highway financing based on benign earmarking of funds for the highway sector. The key concept underlying both is commercialization. project cycle stage: Feasibility Operation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Sector Related Issues: Roading Policy & Reform: Reform The funding community has potentially a key role to play in encouraging and assisting necessary institutional and financial reforms for the road sector, and ensuring their success, but only if aid agencies agree on objectives and the means of attaining them. They can support the reform process by providing well-targeted assistance and support, particularly technical assistance, and avoiding adoption of conflicting policies and contradictory forms of assistance based solely on their individual preferences. A first step in the commitment to meaningful reform would be to make future assistance conditional on strong evidence of improved performance of the core executive institution of the road sector in maintaining the national road network and on government success in implementing the policy reforms proposed so far. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Operation and maintenance Sector Related Issues: Roading Policy & Reform: Policy reforms/framework The standards to which road improvements are designed should reflect a realistic assessment of the future utilization of the roads, taking into account the various physical, environmental, and cost aspects of the problem. The most appropriate design for a given situation will be the one that contributes to the minimization of total road life cycle costs and takes full account of potential budgetary constraints. The argument that pavement design standards must be raised to take account of the widespread overloading of trucks seems strange in that higher than necessary road rehabilitation and improvement costs have to be incurred to solve the problem of controlling axle loads, which, other things being equal, should cost only a fraction of the higher pavement costs. Traditionally, axle load enforcement has failed, as enforcers, usually the police, are not given the resources or training to do the job properly. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Roading There is no adequate system for ensuring that investments in road maintenance, rehabilitation, and improvement are allocated according to priorities based on an analysis of needs. The road information collection and storage system reflects this to the extent that there appears to be no readily available up-to-date summary of information on national road conditions by pavement type. It also reflects the absence of a central highway database storing information required for modern highway expenditure prioritization and planning. This reflects a lack of urgency in institutional response to a highly necessary reform of the management of the main road network. project cycle stage: Feasibility Operation Lesson Topics: Monitoring & Evaluation: Data collection and management Project Management: Management information system Project Management: Operation and maintenance Capacity Development: Ownership Country Context: Prioritization Sector Related Issues: Roading Policy & Reform: Reform | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/bank-operations-road-sector-philippines
Forestry Development Project (Loan 677-PHI) | Philippines | Agriculture, Natural Resources, and Rural Development | 1997-07-31 | Forestry development activities should be implemented using a business approach taking into consideration the investment process (production of goods and services) and the marketing aspects (pricing, markets, and distribution channels) to maximize returns. The process should be conducted under a conducive institutional framework with adequate technical support. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Plantation forestry relies heavily on regular tree growth monitoring and updating of forest descriptions. Without these tools, it is very difficult, if not impossible, to make the necessary management decisions to achieve optimum results. Regular monitoring of tree growth and performance should be part of forestry management inputs. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Sector Related Issues: Rural development The project was implemented using the sole criterion of the plant survival rate as the indicator of success. As a result, project staff neglected to monitor the quality aspects of project performance. A project monitoring system with clearly defined performance indicators should be established from the time of project commencement. The system should provide the central agency with adequate feedback at regular intervals so that remedial actions can be taken to realign project activities toward achieving the objectives. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation The venture into a pioneering, large-scale, forest plantations with the adoption of a dominantly single-species technology entailed potentially high risks and uncertainties. Great caution should be exercised in embarking on large-scale project activities that are experimental in nature. Activities should be on a pilot basis and accompanied by a strong research and development program. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Rural development Methodologies/Approaches: Pilot project | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/forestry-development-project-loan-677-phi
Philippine National Oil Company Energy Project (Loan 726-PHI) | Philippines | Energy | 1997-05-31 | The government benefited greatly from the privatization of one of the EA's subsidiary. Proceeds from the sale of a 60 percent equity stake helped to reduce its budget deficit, secured a reliable and steady source of crude oil supply, and ensured private sector financing of the subsidiary's future rehabilitation and expansion plans. The transfer of mining rights of some of the EA's coal mines to the private sector, the closure of others, and the disposal of a large number of shipping vessels also contributed to the financial health of the EA directly, and to the goverment indirectly. Although not part of the project, the experience with privatization has been a positive one and indicates that expanding the private sector's involvement, at least in the nonpower energy subsector, should be seriously considered as part of any future loans in this subsector in other DMCs. project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Sector Related Issues: Private sector Policy & Reform: Privatization There does not seem to have been sufficient justification to dispense with proper project preparation in order to expedite the processing of the project loan given the country's nearly whole dependence on imported oil for commercial energy needs, and the threat of political and economic difficulties including foreign exchange shortages to restrict government's access to the oil market. Parts B and C of the project were not well conceived and, on hindsight, probably should not have been included in the project. More thorough and careful project preparation would have uncovered important aspects of the EA's coal mining and shipping operations that would likely have excluded these components. Sufficient time for proper project preparation should therefore be mandatory, whether a country is in economic difficulties or not. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Country Context: Crisis/Post-crisis Sector Related Issues: Energy planning/management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/philippine-national-oil-company-energy
Manila Water Supply Rehabilitation Projects 1 and 2 (Loans 645/947-PHI) | Philippines | Water and Other Urban Infrastructure and Services | 1997-04-30 | ADB's assistance in water supply and rehabilitation projects in the past have not resulted in any improvement in the NRW losses. ADB's experience indicated that projects in which the prime objective is the reduction of NRW, could not be realized through funding rehabilitation work alone. A partial and piecemeal approach will not be effective in NRW reduction. There is a need to understand all the root causes and undertake a systemwide approach to effectively reduce NRW. project cycle stage: Feasibility Lesson Topics: Prior to imposing the covenant, which requires the reduction of O&M expenditure per unit output, ADB should ensure that present levels of expenditure are more than sufficient to maintain the agency's assets and operations, and are significantly above the norm for similar agencies operating successfully in other cities. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Management: Operation and maintenance | Project/Program Performance Evaluation Report (PPER) |  | http://www.adb.org/documents/manila-water-supply-rehabilitation-projects-1-and-2-loans-645947-phi
Small and Medium Industry Project (Loan 944/945-PHI[SF]) | Philippines | Industry and trade | 1996-11-30 | Project experience indicates that the interest rate incentive was not effective in encouraging financial institutions to provide lending to projects to promote socioeconomic development in less-developed provinces where high risks were perceived. The credit facilities should be provided together with adequate industrial, social, and marketing infrastructure in promoting SMEs in less-developed regions. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Industry and Trade Sector Related Issues: Rural development Rapid and full utilization of funds and good financial performance of the subprojects are due to the use of the financial institutions with sound financial and managerial capabilities as the conduit of ADB funds. The requirement for the financial institutions to bear the risk of loan defaults makes them more prudent in selecting subprojects for financing. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Project Design: Subprojects The project demonstrates that (i) SMEs seek long-term loans to finance permanent working capital in addition to fixed assets; (ii) there is strong demand for credit by SMEs at the market-based lending rates; (iii) compliance with loan covenants regarding the use of ADB funds under credit line projects must be monitored and enforced, and (iv) existing arrangements are inadequate to ensure compliance with environmental laws by SMEs. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Finance & Financial Aspects: Financing Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Industry and Trade The project highlights that it is difficult for credit projects to achieve commercial and developmental objectives simultaneously. Without proper targeting instruments and close monitoring of subloan approval, it is difficult to ensure that subprojects financed would lead to desirable social and economic development impacts. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Methodologies/Approaches: Targeting | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/small-and-medium-industry-project-loan-944945-phisf
Impact Evaluation Study of the Bank's Benefit Monitoring and Evaluation Assistance to the Agriculture and Social Sectors in the Philippines | Philippines | Agriculture, Natural Resources, and Rural Development, Education, Health | 1995-12-31 | ADB support for BME activities could have been made more effective if an agency-wide BME system had been developed rather than systems for individual projects. Tailoring BME systems to the information needs of executing agencies, thus streamlining systems and limiting their resource intensity, will be a first step in reducing their financial requirements. An additional incentive may be created if BME systems/information can demonstrate their contribution to cost savings. project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Management information system Contributions to sustainability may be achieved if (i) BME assistance is provided at the right level of the institutional structure; (ii) there is transfer of technology from consultants to local counterparts, from contractual staff to regular staff (or the former is absorbed as regular staff for BME type of activities), and between regional and central levels; (iii) BME systems and methodologies developed by the project are integrated into the BME system of the executing agency, with adequate inputs and support provided to ensure such internalization; and (iv) the BME data base/information system is integrated with the central MIS system, assuming that the latter exists and is operational. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Technology/Technology transfer Integrating project-related BME into the regular structure of executing agencies will make a positive contribution to capacity building. Designing capacity building assistance must be based on detailed analyses of BME capacities. Time should be given to institutionalize systems developed by consultants. Donor coordination is needed to contribute positively to capacity building by congregating resources on effective systems and reducing time and resources to operate them. Executing agency's commitment and allocation of resources for supporting BME are critical and also need to be enhanced. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity assessment Capacity Development: Capacity building Capacity Development: Ownership Ownership of BME systems needs to be fostered. Being developed for a particular project, located in a coterminous project office, and having the main purpose of reporting to ADB on project impact, project-based BME systems are not perceived or treated as part of the executing agency's structure or system. Closer integration of ADB assistance and requirements with the regular BME structure of executing agencies may help in overcoming the ownership problem as well as in enhancing the impact of ADB assistance in terms of ensuring management support. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Project management Capacity Development: Ownership To become functional, BME systems will have to be designed on the basis of an appreciation of which information is needed by whom, at which time, and for what purpose. BME must not be performed for compliance purposes only. The amount and degree of data collated in such a way do not necessarily correspond with the information needs at higher levels, Thus, much of the information is meaningless or is not generated and compiled in a useful manner, which is one of the reasons for nonutilization of BME information (thus lack of feedback) and leads to frustration of potential users. project cycle stage: Design, Feasibility Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Management: Management information system | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-study-banks-benefit-monitoring-and-evaluation-assistance-agriculture-and
Study on Vehicular Emission Control Planning in Metro Manila in the Philippines | Philippines | Transport | 1995-10-31 | The TA has shown the importance of a project's approach on its outcome. A clear differentiation is required between direct advisory services, i.e., where consultants are recruited to carry out a survey and provide recommendations for follow-up action, and capacity-building projects. The earlier approach should be chosen only if the readiness and ability to take requisite decisions and implement them exist. Capacity-building targets should be set on the basis of institutional analysis and capacities anticipated to exist at the end of the project should be explicitly defined. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Management: Consultants Capacity Development: Capacity building Capacity Development: Institutional analysis | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/study-vehicular-emission-control-planning-metro-manila-philippines
Island Provinces Rural Water Supply Sector Project (Loan 812-PHI) | Philippines | Water and Other Urban Infrastructure and Services | 1995-05-31 | Formation of water user groups and the commitment of their members to pay necessary fees should be a precondition for approving a subproject. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Subprojects Project Management: Operation and maintenance Capacity Development: Ownership Health benefits are the main justification for rural water supply projects, but unless water quality is properly monitored and controlled, the provision of such facilities may not significantly reduce the incidence of mortality and morbidity. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Procurement Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management Protecting the investment and the quality of water through proper O&M is an urgent requirement. Institutions for the collection of water charges need to be established and they should remain active to ensure cost recovery and proper O&M. Water sources may be contaminated because of poor drainage around point sources and poor water users' habits. project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Financial management Capacity Development: Capacity building Sector Related Issues: Water resource management The capacity of an executing agency to meet the requirements of a sector loan including the selection and appraisal of subprojects requires more careful analysis. Where such capacity is considered insufficient or doubtful, assistance to enhance such capacity should be provided together with the loan. project cycle stage: Feasibility Lesson Topics: Loan Agreement: Covenants Project Design: Subprojects Project Management: Executing/Implementing agencies The design criteria, once established, should be reflected in subproject selection and appraisal criteria and the appraisal of subprojects. The criterion for the distance from households to point sources is particularly important as it determines the number of point sources to be constructed, the magnitude of investment needed, travel time for fetching water, and the level of water consumption. While the present criterion requires a maximum distance of 250 meters, the average actual distance to the point sources constructed was only around 50 meters. This suggests that the point sources may have been provided at closer intervals than intended. The selection of the sites for point sources should attempt to provide them primarily to those households beyond the optimum distance from the point sources with a view to maximizing cost-effectiveness. project cycle stage: Feasibility Lesson Topics: Project Design: Subprojects Sector Related Issues: Water resource management The process also needs to take into consideration community plans to obtain alternative sources of water to avoid developing several different water facilities in an area. Where available, more springs should be developed, and the watershed areas need to be protected. Extension of spring development to communal standpipes or house connection is something that people appreciate and are ready to pay for and should be promoted wherever practicable. project cycle stage: Feasibility Lesson Topics: The responsibilities assigned to the concerned agencies at the central and provincial levels should be clarified; adequate personnel and other resources should be provided; and a system of accountability must be established. This will also have to involve the reeducation of the beneficiaries on the status of ownership of the facilities. Training for testing the quality of water and for organizing water user groups needs to be strengthened and sustained. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Sector Related Issues: Water resource management | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/island-provinces-rural-water-supply-sector-project-loan-812-phi
Road and Road Transport Sector Program Loan (Loan 1046[SF]/1047-PHI) | Philippines | Transport | 1995-02-28 | In the future, an optimal targeting of program lending, with emphasis on sustaining reform measures, should be undertaken and a working group approach to screening study bases for their sufficiency to support policy interventions should be adopted. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Program Project Design: Appraisal Policy & Reform: Policy reforms/framework Program lending is not generically exempt from technical performance or benefit monitoring and every effort should be made by ADB to ensure that financial, economic, social, or indicator-based monitoring of impacts is carried out for all such assistance. project cycle stage: Implementation Lesson Topics: Modality: Program Monitoring & Evaluation: Benefit monitoring and evaluation To include ancillary or subsidiary technical assistance studies funded by ADB in the loan policy base (matrix) when their purpose or thrust is not directly supporting the program focus nor conditional on follow-on actions can be misleading and should generally be avoided. Such technical assistance work should be discussed and presented in a separate annex. project cycle stage: Appraisal Lesson Topics: Modality: Policy-based lending Modality: Technical Assistance | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/road-and-road-transport-sector-program-loan-loan-1046sf1047-phi
Promoting Economic Use of Customary Land, Phase II: Technical Assistance Completion Report | Samoa | Public sector management | 2015-07-01 | While the use of customary land is of economic importance for the people of Samoa, it is culturally sensitive, and this requires community consultations. As government continues in its reform plans, the public will need to be continuously consulted, and investors and landholders made aware of the opportunities as they become available. The use of Samoan national consultants on the TA (technical assistance) has helped with the community consultations and given stakeholders assurance and confidence about the objectives of the TA. Political will to push on with the reforms is of great importance. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/sam-promoting-economic-use-of-customary-land-phase2-tcr
Economic Recovery Support Program - Subprograms 1 and 2: Validation of Completion Report | Samoa | Education, Energy, Information and Communication Technology, Public Sector Management, Water and Other Urban Infrastructure and Services | 2015-01-30 | The PCR (program completion report) section on lessons provided useful lessons on the inherent challenges for the Pacific member countries to undertake long-term structural adjustments, such as SOE (state-owned enterprise) reforms, and changes to land tenure and trade regime. This is mainly from a political economy perspective. Any long-term structural adjustments would need sustained negotiations with the government and the support of all the major development partners. This validation concurs with this finding. project cycle stage: Implementation This validation adds that targets and indicators in the DMF (design and monitoring framework) of program loans such as this need to be extremely conscious of exogenous factors. There is also a need for ADB program to assign focus areas for policy coordination and monitoring among ADB and other development partners so that respective contributions to policy dialogue under the different program components can be traced. project cycle stage: Design, Implementation | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/samoa-economic-recovery-support-program-subprograms-1-and-2
Economic Recovery Support Program - Subprograms 1 and 2 | Samoa | Education, Energy, Information and communication technology, Public sector management, Water and other urban infrastructure and services | 2014-03-01 | All Pacific developing member countries, including Samoa, experience great difficulty implementing long-term structural adjustment policies. While demand-side, short-term price stabilization policies may be more readily implemented, longer-term changes to land tenure and state-owned enterprises and efforts to liberalize trade and investment regimes confront a very difficult political economy environment in the Pacific islands. Governments are comfortable with short-term price reforms that pose less of a challenge to the political economy. Reform programs that include structural adjustment policy require careful, if not tough, negotiation. This negotiation requires the buy-in of government, support of all major development partners, and support of senior ADB management. Consideration should have been given in program design to greater consultation between the government and ADB project analysts for improved program management and policy analysis, impact assessment, redesign where appropriate (for example, in the transition stage between subprograms 1 and 2), and implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/samoa-economic-recovery-support-program-subprograms-1-and-2-pcr
Sanitation and Drainage Project | Samoa | Water and other urban infrastructure and services | 2012-01-06 | Inadequate preparation at appraisal and readiness at approval caused the problems encountered during implementation. An urban development master plan and more importantly a detailed feasibility study to fully assess costs and alternatives was not in place prior to appraisal. As a result, the project required (i) further detailed studies during an extended initial implementation phase, and (ii) supplementary financing. Because a comprehensive feasibility study was lacking, the project implementation assistance consultants had to undertake a significant number of feasibility options analyses prior to development of the preliminary designs and bid documents, which led to delays in the project's initial implementation phase. From the initial cost estimate of $10 million, the actual project cost increased to $17.8 million, requiring supplemental financing and resulting in further implementation delays. [Main text, para. 53] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/sanitation-and-drainage-project-pcr
Samoa: Small Business Development Project [Loan 1785(SF)] | Samoa | Industry and trade | 2011-07-31 | 1. A project design based on a sound and thorough assessment of institutional constraints and market conditions would have ensured smoother implementation and improved loan performance. In the context of Samoa where the financial market is relatively underdeveloped, the collateral framework is weak, and institutions have limited capacity a more simple and focused project design would have been more appropriate. Some of the subcomponents such as the venture capital fund, credit bureau and chattels registry were totally new activities which made the design more complex and difficult to implement. Also, clearly a modest project like this would not be the best vehicle for addressing a fundamental political issue like land ownership. Those preparing the project design could have placed greater focus on creating an enabling environment for the financing and growth of micro and small enterprises. This would have involved developing the policy and legal environment for the sector (which to some extent was achieved by the project), and building institutions to service the sector. [Main text, paras. 17,25,32,70] project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design 2. Early identification of the constraints to implementation, and development of clear strategies to address these constraints would have made project implementation more effective and efficient. Findings from project supervision could have also been consistently used to adjust project in light of experience. The capacity constraints of implementing agencies were not clearly defined early on in implementation, especially the credit components. No clear strategies were developed to address constraints in the social and cultural environment and in market conditions that affect the policy component. Both ADB and the government could have taken into account these constraints in the project design or addressed at the implementation stage. As a result, project benefits were limited by deficiencies in design, delays and problems in implementation, and the institutional constraints of implementing and participating institutions. [Main text, paras. 32,39,60-62,71] project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Capacity assessment Country Context: Cultural constraints 3. Support for capacity building should be geared towards promoting the long-term sustainability of institutions. While ADB's technical assistance in the form of logistical support, advisory assistance (through consultant inputs), study tours, and training help to improve project capabilities, they do not necessarily address long-term sustainability of institutions. Efforts towards promoting sustainability, such as for the Small Business Enterprise Centre, should include developing appropriate and effective financial systems, installing an effective management information system, institutionalizing good governance and management structure, and strengthening risk assessment, loan appraisal, and monitoring skills. [Main text, paras. 12,72] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Monitoring and evaluation Project Management: Management information system Project Management: Risks/Risk management Capacity Development: Capacity development 4. Enterprise finance projects need to have a clear exit strategy at completion to ensure sustainability. The project had no clear strategy on how the Small Business Enterprise Centre (SBEC) should be supported beyond the life of the project. The SBEC was left with a huge loan guarantee portfolio at the end of the project and no long-term means to sustain its operations. [Main text, paras. 13,73] project cycle stage: Completion Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/samoa-small-business-development-project-loan-1785sf
Samoa: Small Business Development Project | Samoa | Industry and Trade | 2011-01-31 | 1. To improve the prospects for successful project implementation, achieving the desired outcomes and outputs, and maintaining sustainability in the medium term: (i) the focus and selection of project components must consider the developmental context of the country and its absorptive capacity; and (ii) preparedness and viability of proposed component, including likelihood of their adoption by obtaining firm upfront commitments from the parties that champion their promotion, must be ascertained. Under the Small Business Development Project in Samoa, the latter does not appear to have been done on one of its components, Venture Capital Fund (VCF). The report and recommendation of the president was more of a description of what the proposed VCF would look like. Many loose ends, including critical issues such as shareholder contributions, choice of the fund manager and key staff, and tax liability, were left to be sorted out during implementation which took time for resolution, and the VCF was closed without doing any business after determining that it was unlikely to be financially viable. [Main text, pages 7-8] project cycle stage: Implementation, Completion Operation Lesson Topics: Project Design: Project design Project Management: Project management | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/samoa-small-business-development-project
Education Sector Project | Samoa |  | 2007-12-24 | 1. More analysis should have been done to assess the feasibility of large community contributions to the ESP. Although a long-standing tradition of the community is to provide the school facilities and maintain them, the cost of doing so in the past was largely in kind and relatively low. Under the ESP, these costs were higher and more frequent as rapidly depreciating equipment such as computers are included. Techniques such as contingent valuation should be used to test the beneficiary willingness to pay for previously free or low-cost services. All such techniques produce results with uncertainties attached and these uncertainties should be factored into the project design. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis 2. The timing and phasing of technical assistance (TA) inputs in relation to the loan project are critical in situations where absorptive capacity has yet to be proven. The TA should have preceded the start of the project so that the preparatory work with counterparts could have been completed before the construction and teacher training stages. This sequencing would have lessened the extent of initial on-the-job training and would have provided a greater (and more sustainable) capacity in Ministry of Education, Sports and Culture. Failure to observe that may reflect some uncertainty as to the relative importance of capacity building on the one hand and speed of implementation on the other. project cycle stage: Design, Implementation Lesson Topics: Modality: Project Modality: Technical Assistance Capacity Development: Capacity development 3. Apia serves as a ï¿½boardinghouseï¿½ for the children of relatives all over Samoa and in 2006, 57% of the total population of Apia's urban areas were enrolled in schools. The situation will not change significantly until the other schools are able to demonstrate improved performance. In this context, the enrollment caps at Malifa were unrealistic. Apia's schools at Malifa have long been seen as offering the best education in Samoa and this perception will remain until such time as the other schools begin to show similar results. It will take much more than a few years to demonstrate this outcome; hence, it was unrealistic to set such ambitious targets for the enrollment caps. project cycle stage: Design Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Sector Related Issues: Education Methodologies/Approaches: Targeting 4. Establishment of new specialist facilities and equipment in schools requires significant school-based training and support. New equipment is often not used because teachers are unfamiliar with it. New specialist facilities are often not utilized due to teachers' lack of knowledge and experience. The effectiveness of the project could have been increased by more technical assistance support for school-based implementation in association with upgraded libraries, science laboratories, design and technology laboratories, and food and textile laboratories. project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Capacity development Sector Related Issues: Education There is always likely to be a trade-off between capacity building on the one hand and rapid implementation of civil works and procurement of goods and services on the other. Early in the design phase, there needs to be a decision as to where the priority is to be placed, and that decision should then drive the project schedule. All consultants and the staff of the executing agency, implmenting agency, and ADB engaged in a project should be well-briefed on where this priority lies to maintain the focus throughout the project. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/education-sector-project
Power Sector Improvement Project | Samoa |  | 2007-12-18 | 1. Inadequate resources for due diligence during project preparation and underestimation of risks associated with the augmentation of the Afulilo project were key contributing factors to the implementation delays and cost increases, beyond the initial delays associated with loan effectiveness. More careful preparation of cost estimates is warranted. As the feasibility of the gravity-fed canal was not confirmed at appraisal, this uncertainty should have been reflected in the physical contingencies. Given the capacity constraints of the Electric Power Corporation, project preparation did not adequately address risks associated with implementation, including the engagement of an experienced project manager, oversight of project implementation activities, and reporting arrangements. Project preparation should also have identified the risk of a delay associated with loan effectiveness and introduced mitigation measures. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity development 2. At the time of appraisal, consideration should have been given to individual contracts for civil works associated with augmenting the Afulilo project, supply and install contracts for mechanical and electrical works associated with upgrades of the transmission line and telemetry system, and for the 2-megawatt generator. Once the gravity-fed canal was found inappropriate, a review of the contract packaging would have been appropriate. If the project had been packaged into separate contracts, much of the delays could have been avoided and all investment components except for the gravity-fed canal could have been achieved. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Management: Procurement 3. Insufficient resources were spent to prepare the environmental impact assessment. No effective measures were put in place to mitigate the identified social concerns about the water quality from villages located downstream from the Afulilo Hydropower Project. Furthermore, a short land acquisition and resettlement plan and an initial environmental assessment for the south and north coast transmission line components should have been prepared prior to ADB approval of the project. project cycle stage: Design Lesson Topics: 4. While project preparation identified and addressed significant issues related to the financial performance of the Electric Power Corporation (EPC) and project financial sustainability, implementation failed to recognize and address the deterioration of EPC's financial performance. Policy dialogue with the Government, particularly with regard to EPC's deteriorating collection performance and lack of implementation of the automatic tariff adjustment mechanism, appears not to have taken place until October 2005 during project reappraisal. The ADB review missions did not appear to have the required expertise to conduct a policy dialogue on EPC's financial performance. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Project management Methodologies/Approaches: Policy dialogue 5. The Electric Power Corporation's (EPC's) project management and implementation capacity were weak. Further consideration needs to be given during project preparation to identifying and addressing risks associated with the implementation capacity of EPC. The externally recruited project manager, although not included under the financing of the project, was not sufficiently experienced in project management. Involvement of EPC staff in the project was also very limited. project cycle stage: Design Lesson Topics: Project Design: Project design Capacity Development: Capacity development | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/power-sector-improvement-project-0
Financial Sector Program | Samoa |  | 2004-10-15 | A strong governance framework was a program highlight. This is reflected in numerous laws drafted and pushed to enactment. But some significant legislation like the Companies Act 2000 and its amendments have not yet been announced and implemented. Schedules to the Public Bodies Performance and Accountability Act 2001 are in place, and two more are being drafted. In other cases, further amendments for effective implementation have been, or are being made. These shortcomings imply that some legislation was passed with little scrutiny or reflection. Once bills are completed, the next crucial phase is a learning exercise in educating users about workings of relevant acts. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Public governance Modality: Program Policy & Reform: Information dissemination/Public awareness The program encouraged and instilled the value of stakeholder consultation, particularly with the private sector, and of the participation process to strengthen support for, and broad ownership of, reform initiatives. The consultation process gave stakeholders an opportunity to understand, monitor, and reassess their goals; and to adjust to conform with the government's reform program. The flow-on effect is seen in the effective contributions of the private sector and civil society to formulation of Samoa's development strategy. Also, the Samoan Government was right in targeting first reforms at the financial sector, before embarking on wider initiatives for public sector reform. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Ownership Sector Related Issues: Private sector Policy & Reform: Public sector reform Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach Methodologies/Approaches: Targeting Waivers of tranche conditions are not encouraged, unless for strong and valid reasons. But in this case, the policy condition to expressly identify eight state-owned enterprises ( SOEs) for privatization during the design phase was too ambitious and optimistic, considering the process by past experiences. The government had still not completely resolved the privatization and divestment of three of the eight SOEs by September 2004, when this report was written. project cycle stage: Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Policy & Reform: Privatization Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/financial-sector-program
Second Road Improvement (Sector) Project: Completion Report | Solomon Islands | Transport | 2015-09-18 | Achieving sustainability requires a consistent and long term approach. The sustainability of project outcomes is greatly dependent on an ongoing commitment by the government to road maintenance, rehabilitation and asset management. Significant steps have been taken to harmonize donor assistance to the transport sector in support of a sector-wide approach. The ongoing Transport Sector Development Project and its support to MID (Ministry of Infrastructure Development) provides a predictable medium-term source of financing through NTF (National Transport Fund). CPIU (Central project implementation unit) already uses government systems, 'topped up' as required, for procurement and other technical and safeguard procedures, and policies for planning, implementing, and maintaining transport assets within the framework of the NTP (National Transport Plan). project cycle stage: Implementation, Operation Sound technical and economic safeguard procedures are required to support NTP (National Transport Plan) implementation. All such procedures are essential for translation of the NTP into worthwhile and fully supported investments on the ground. Appropriate engagement and communication with stakeholders is essential to ensure these processes are fully understood as well as the reasons for particular technical decisions. A stronger country safeguards system, including guidelines on obtaining land for transport projects, is essential. ADB is assisting the government to strengthen its safeguards system in the transport sector, including developing guidelines on environment and land acquisition, and building capacity within MID (Ministry of Infrastructure Development), Ministry of Lands, Housing and Survey, and Ministry of Environment, Climate Change, Disaster Management and Meteorology. project cycle stage: Appraisal, Implementation Climate change adaptation. The project implemented several measures to mitigate impacts from climate change. At present, these measures are effective and efficient. Continuous monitoring and maintenance of improved assets is needed to ensure sustainability of the adaptation measures. project cycle stage: Implementation, Operation Community liaison. Effective and efficient community liaison by experienced persons is important to resolving conflicts between the community and workforce, and between expatriate and local labor. Greater capacity will be required in MID (Ministry of Infrastructure Development) to manage community liaison, identify affected people, and manage the process of compensation to avoid community dissatisfaction. project cycle stage: Implementation Imprest accounts. The project received financing from various sources at different time intervals through grant agreements 0175, 0176, 0177, 0207, 0210 and recipient's contribution through government annual budget and the NTF (National Transport Fund). The disbursement of funds was carried out through direct payment and reimbursement procedures by maintaining three first generation and five second generation accounts. Even though PMCBU (project management and capacity building unit) managed these accounts satisfactorily, substantial delay occurred at the end of the project due to cumbersome nature in reconciling and winding up the accounts. project cycle stage: Design, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/sol-second-road-improvement-sector-project-pcr
Strengthening Country Safeguard Systems in the Transport Sector: Technical Assistance Completion Report | Solomon Islands | Transport | 2015-07-01 | A major lesson was the importance of keeping the focal points and other staff participating from each of the three ministries sufficiently engaged over the course of the TA (technical assistance). Recruiting LALSU (Landowners' Advocacy and Legal Support Unit) to roll-out the awareness raising workshops worked well; this is an activity and approach? engaging with a well-grounded civil society organization as stakeholder conduit?that can be promoted on other TAs and projects. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/sol-strengthening-country-safeguard-systems-in-the-transport-sector-tcr
Economic and Financial Reform Program: Completion Report | Solomon Islands | Public Sector Management | 2015-05-07 | Country ownership. Country ownership is critical to successful implementation of the EFRP. The effectiveness of the EFRP (Economic and Financial Reform Program) and the CEWG (core economic working group) mechanism has reflected the strong leadership of the minister of finance and his permanent secretary; support from the prime minister, other ministers, and senior government officials; and the commitment of development partners to support these processes. project cycle stage: Implementation, Country Partnership Strategy Use of country systems. The CEWG (core economic working group) process has helped to channel a growing share of development partner assistance through government systems and as a result reduce transaction costs over a narrow front of activity, and make greater use of country systems in line with development partner commitments. In 2009 - 2013, the portion of recurrent and development expenditures through budget support increased. Recurrent budget grants comprised 5.2% of total revenue and grants in 2009 and rose to 9.6% in 2013. project cycle stage: Country Partnership Strategy Benefits of dialogue and tight focus. The tight focus of the EFRP (Economic and Financial Reform Program) and the ADB policy matrix has helped to strengthen ownership by the government. The CEWG (core economic working group) policy dialogue contains three main elements: (i) discussions on the design and implementation of the EFRP policy matrix, (ii) regular CEWG meetings, and (iii) the annual joint review missions. Policy dialogue was anchored on the EFRP matrix with its objectives of strengthened PFM, budget reform, and economic growth. The CEWG has made an important contribution to harmonizing dialogue around a narrow set of issues and reducing transaction costs. project cycle stage: Implementation, Operation Progress fairly steady but slow. Implementation of the EFRP (Economic and Financial Reform Program) has been satisfactory but has often taken longer than anticipated, particularly in the area of legislative reform. The number of policy actions and reforms monitored through the EFRP has varied greatly each year - 49 in 2010, 31 in 2011, 77 in 2012, and 29 in 2013. While reform actions were initially evenly divided between PFM (public financial management) and budget reform on the one hand and economic growth on the other, the clear focus in later years has been on public expenditure and financial management. The joint review mission assessment each year has typically shown that more than one-half of the actions planned have been completed. The performance on actions related to economic growth and the business environment seem to have been stronger in most years than performance on those related to public expenditure and financial management. With the exception of 2011, the share of total actions considered to be off track - i.e., no progress - has been less than 10%. However, almost all legislation has been several years behind the intended timetables and therefore EFRP policy actions that include legislative reform need to have realistic timelines. project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/economic-and-financial-reform-program-pcr
Road Improvement (Sector) Project | Solomon Islands | Transport | 2014-04-01 | Achieving sustainability requires a consistent and long-term approach. Significant steps have been taken to harmonize development partner assistance in the transport sector to support a sector-wide approach. The Transport Sector Development Project and its support to Ministry of Infrastructure Development (MID) through the central project implementation unit provides a predictable medium-term source of finance (via the National Transport Fund) and ensures the use of government systems for procurement and other technical and safeguard procedures, as well as policies for planning, implementing, and maintaining all transport improvements within the framework of the agreed National Transport Plan. A wide range of measures will be needed to sustain government ownership, engage stakeholders, enhance MID's access to competent staff, and institutionalize procedures for planning, implementation, maintenance, and monitoring into daily MID processes. Sustained improvements in transport-related organizational capacity will require continued consultant support with early and continuous client engagement to ensure relevance. Obstacles can be overcome and the impact of capacity building can be improved by high-level client involvement as early as subproject preparation and execution. Selective external capacity building support focused on high-priority needs such as (i) feasibility study; (ii) contract management; (iii) labor-based, equipment-supported maintenance program preparation, procurement, and supervision; and (iv) application of safeguards rather than across-the-board capacity building is likely to be beneficial. While constraints on transport agency performance may occur as a result of weakness in other areas of government, a proactive and competent transport agency would be better able to call for essential improvements. Need for sound technical, economic, social, and environmental procedures. They are essential for translating the National Transport Plan into worthwhile and fully supported investments. Proper engagement and communication with stakeholders is vital to ensure that the rationale and the processes are fully understood. A stronger country safeguard system, including guidelines on obtaining customary land for transport projects, is essential. Stronger internal procedures ensure maintenance quality and probity. Quality control remains a weakness. Funding must be provided to support critical maintenance-related activities - progressive improvement of performance-based contracts, timely and appropriate supervision of maintenance contracts, and asset management planning to ensure proper forward planning of maintenance needs. Sound fiduciary procedures are needed to ensure that the quality and quantity of civil works, and the purchase of goods and services, are matched by proper financial records and approvals. Adequate travel budgets and efficient mechanisms at MID and the Ministry of Finance and Treasury are required to ensure MID staff regularly travel to outer islands to inspect ongoing maintenance contracts. Creating a contracting industry by motivating local communities. This can help maintain roads in good condition while representing value for money and providing positive social outcomes, but it requires adequate resources for effective supervision by engendering accountability of central and provincial governments. Greater capacity is needed by the government to manage community relations and negotiate compensation for land and resources utilized. Land acquisition for the Makira subproject was minimal and managed in accordance with ADB's safeguard policy. In the future, greater government capacity will be needed to manage community liaison, identify affected persons, and manage the process of compensation to avoid community dissatisfaction. Cost overruns due to exchange rate fluctuations may be managed by an improved methodology for determining price contingencies. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/road-improvement-sector-project-pcr
Economic Recovery Support Program - Subprograms 1 and 2 | Solomon Islands | Education, Health, Public Sector Management, Transport | 2012-03-09 | 1. The overall design contributed to promoting country ownership through the following qualities: (i) relatively simple scope with realistic and achievable goals, (ii) long-term perspective and commitment, and (iii) strong development partner collaboration. These are also consistent with lessons from ADB's special evaluation on promoting good governance in the Pacific. [Main text, para. 45] project cycle stage: Lesson Topics: 2. Development partners' coordinated technical and capacity support to the government was critical to achieving the reform in a timely manner. A comprehensive economic and fiscal reform program needs to be backed by a common understanding of both the budget and the strengths and weaknesses of the development strategy, budget processes, and approaches. Setting policy priorities requires careful review, analysis, and implementation by capable government agencies. [Main text, para. 46] project cycle stage: Lesson Topics: 3. It is important that development partners remain united on key policy messages and policy actions. The creation of a government-multidonor core economic working group (CEWG) was transformational. The main strengths of the CEWG were its focus, the extent of aid coordination, the regularity of its operations, and the lower transaction costs for the government. [Main text, para. 47] project cycle stage: Lesson Topics: 4. Progress in implementation of policy actions needs to be jointly assessed by government and all relevant development partners. This ensures a consistent base for release of funds. The decision to track the program's reforms as part of the quarterly core economic working group dialogue and annual review process reduced the compliance burden on the government and contributed to a shared understanding of progress made among the partners. [Main text, para. 48] project cycle stage: Lesson Topics: 5. Policy dialogue requires on-the-ground support from ADB. Establishment of the ADB-World Bank joint development coordination office in October 2008 played a key role in forging successful policy dialogue. [Main text, para. 49] project cycle stage: Lesson Topics: 6. Including measures for state-owned enterprise (SOE) and transport policy reform under the program provided an added incentive to the government to implement agreed reforms on a fixed time schedule. It is uncertain whether SOE reforms would have progressed as rapidly if they had been supported by advisory technical assistance alone without the complementary milestones for SOE reform under the program. [Main text, para. 50] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/economic-recovery-support-program-subprograms-1-and-2-pcr
Emergency Assistance Project | Solomon Islands | Agriculture, natural resources and rural development, Transport | 2011-10-01 | Implementation issues. The long front-end implementation delays from the project serve as a major lesson. The expectations in implementing the project under an emergency modality over 18 months as a sector project over remotely located subproject sites, given the low absorptive capacity of Ministry of Infrastructure Development (MID), may have been unrealistic. For remote subprojects, higher mobilization and demobilization costs should be factored into cost estimates. Preparing feasibility studies for emergency projects. An accelerated approach to preparing feasibility studies and selecting subprojects could be developed for future emergency projects. The process to identify, define, and prioritize the long list of subprojects, prepare and review full feasibility studies, prepare engineering designs, and bid the civil works was time-consuming and prevented early commencement of physical implementation. Stakeholder consultations. Consultations with landowners and stakeholders should be held and Memoranda of Understanding signed prior to award of contract and physical implementation. During the contract for the rehabilitation of coastal infrastructure, it was only discovered that one of the proposed wharfs was located on customary land after the contract was awarded. The timely completion of the contract was therefore at risk, although the situation was eventually resolved. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/emergency-assistance-project
Solomon Islands: Post-Conflict Emergency Rehabilitation Project | Solomon Islands | Education, Health, Water and Other Urban Infrastructure and Services | 2011-07-11 | 1. In the case of countries with potential debt service payment risks, incorporating a debt sustainability analysis in the risk and vulnerability assessment of the project can help anticipate the potential risks to ADB. In the Post-conflict Emergency Rehabilitation Project, the country's severe budgetary constraint in early 2000 meant the government will be unable to finance any reconstruction work in the short term. ADB could have identified this potential debt payment issue by doing a simple debt sustainability analysis and instituted necessary mitigation measures to avoid 3-year delay in project implementation. [PVR Main text, pages 6-7; see also PCR Main text, para. 5] project cycle stage: Design Appraisal Lesson Topics: Project Design: Appraisal Country Context: Conflict/Post-conflict Country Context: Emergency | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/solomon-islands-post-conflict-emergency-rehabilitation-project
Public Sector Reform Program | Solomon Islands |  | 2002-12-13 | Careful country analysis and diagnosis of issues are essential to identify and prioritize ADB interventions and to design programs. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Country Context: Prioritization Downsizing of the public service and restructuring of public enterprises are more likely to succeed in a favorable macroeconomic environment, where the government has financial strength and alternative employment opportunities are available. The Economic and Public Sector Reform Program (EPSRP) was designed and undertaken at a time of substantial economic uncertainty, a declining domestic currency exchange rate, rapidly increasing domestic prices, few employment opportunities, and the loss of the Tonga Trust Fund. Such an adverse environment made a large cut in public sector employment politically, socially, and culturally unacceptable. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Governance Project Design: Project design Crosscutting Issues/Themes: Employment Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform The complexity and long-term process of the economic and public sector reform need to be recognized. One short-duration program loan cannot achieve lofty goals involving gross domestic product (GDP) growth, inflation rate, fiscal balance, efficient and effective use of resources by public enterprises, and improved public services. When designing reform programs, outputs, objectives, and development goals need to be more realistically linked with policy conditionality. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Program Project Design: Project design Policy & Reform: Public sector reform The program lending modality has limitations in its ability to bring about structural changes. To ensure successful implementation of a program, adequate attention has to be paid to the implementability of the policy conditions. This, however, has to be done, very often, by focusing on specific actions rather than on underlying incentives or institutional capacities. For instance, the Economic and Public Sector Reform Program (EPSRP) required actions like corporatization, but had to leave corporate governance unaddressed. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Corporate governance Modality: Program Project Design: Appraisal Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/public-sector-reform-program
Support for Planning and Policy Formulation, Phase 1: Technical Assistance Completion Report | Sri Lanka | Public sector management | 2015-09-01 | The flexibility in design allowed ADB to accommodate a wide range of policy-related activities and respond quickly to government requests. However the outputs differed from what was anticipated during the design stage. A stronger commitment from government on the type of activities to support at design stage, at least for a larger component of funds, would have been helpful to design the performance indicators for the TA (technical assistance) more effectively. Some components, such as the training on PPPs (public-private partnerships) and the presentation on the PPP pipeline, should have had clearer paths for sustainability, either by linking to larger projects or further technical assistance. A tighter scope of the TA and streamlined set of players would have avoided much of the slippages in terms of time, however this must be balanced against the responsiveness factors noted above. The TA would also have benefited from closer involvement of topic experts, sector focal persons from ADB, industry representatives and experts from centers of excellence providing more practical orientation for technical aspects. Project cycle stage: Concept, Design | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/sri-support-for-planning-and-policy-formulation-phase1-tcr
Capacity Development for Non-Revenue Water Reduction: Technical Assistance Completion Report | Sri Lanka |  | 2015-08-01 | Updated and verified details of Colombo city water supply distribution network would have assisted the consultants in the redesign of the DMA (District Metered Area) with greater precision. A fully isolated and discrete supply zone with permanent boundaries should be established for the accurate measurement of baseline NRW (non-revenue water) figures and water balance assessments, through securing the hydraulic boundary and improving system input metering. The investment program has addressed these issues further. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/capacity-development-non-revenue-water-reduction-tcr
Colombo Port Efficiency and Expansion Project: Completion Report | Sri Lanka | Transport | 2015-07-29 | The project experienced substantial delays. These were mainly contributed by difficulties in securing sufficient public sector funding and approvals by various government agencies on the SHDP business plan and BOT concession agreement. However, ADB exercised flexibility in extending the TA loan, providing continued assistance to the government to implement the large-scale PPP project. Implementation delays was also attributed by the loan covenants on the ports sector reforms that could not be achieved as planned. Nevertheless, the spirit of these original loan covenants was fulfilled, which was beneficial in improving the operational efficiency at JCT. Although the ports regulator could not be established as planned, this was instead achieved by establishing an advisory committee to act as a grievance redress mechanism for such issues. For similar projects in the future, it may be beneficial to require reforms to be demonstrated as a project readiness criterion before project approval and implementation. Alternatively, if included in loan covenants, such institutional and regulatory reforms could be defined at a higher level - rather than as specific outputs - to allow the government more flexibility during implementation. project cycle stage: Feasibility, Appraisal, Implementation, Completion, Operation The decision to suspend the services of the MSC (main services consultant) from September 2005 to July 2006 with the consent of the MSC and approval from ADB was noteworthy. This approach not only resulted in financial savings, it ensured the success of the TA loan. Given that this is the first large-scale PPP project in the transport sector, the TA loan was effective in providing continuous support to government agencies, allowing them to carry out the necessary preparations for the PPP, including preparation of the procurement documents, bid evaluation, and BOT concession agreement negotiations. To minimize professional liability, the MSC was subsequently single-sourced to act as construction supervision consultants for the ensuing loan to implement the HIW works. project cycle stage: Appraisal, Implementation To mitigate the risk of lack of private sector participation, the selection of a private sector BOT concessionaire was a loan effectiveness condition for the ensuing loan. This ensured the selection of a credible private sector party to implement the BOT concession. project cycle stage: Appraisal The government had explored the possibility of setting up a special purpose vehicle to construct the breakwater using private sector financing, but this was found to be problematic for the following reasons: (i) the breakwater would not generate revenue, (ii) the construction skills required for building breakwaters and terminals are very different, (iii) revenues would only be generated from the operations of the container terminal, and (iv) it would be difficult to attract private sector investment for the breakwater. Hence the PPP landlord model was used, where SLPA (Sri Lanka Ports Authority) would be the landlord, and the breakwater implemented as a public sector component. project cycle stage: Feasibility, Implementation Although the completion of the TA loan was delayed by 6 years, the TA loan is still considered a success given its significant contribution in facilitating the development of the first large-scale PPP transport infrastructure project in Sri Lanka. The extensions in completion time allowed adjustments to be made to ensure successful of implementation. project cycle stage: Implementation, Completion, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/sri-colombo-port-efficiency-and-expansion-project-pcr
Colombo Port Expansion Project: Completion Report | Sri Lanka | Transport | 2015-07-27 | Project structuring. A key consideration was to draw an optimal balance of public and private sector participation. The government applied a PPP landlord port model whereby the public sector would deliver the basic breakwater infrastructure and private sector deliver two of the three container terminal facilities to be accommodated by the new breakwater. This approach has not only brought about significant efficiencies in delivery, it also resulted in tremendous financial leverage. project cycle stage: Design, Implementation Procurement. The project is very large scale and complex in nature, so it was important to bring in quality consultants and contractors. Continuation of services from the main design consultants to provide construction supervision not only reduced the time for procurement but also resulted in minimizing liability risks and disclaimers of responsibility. project cycle stage: Design Civil works packaging. Since the works were interrelated, the HIW (harbor infrastructure works) was packaged as a single contract. The large size of the contract attracted good quality and experienced contractors. project cycle stage: Design, Feasibility Loan effectiveness. Realization of the full project benefits was contingent upon the public and private sector components being well coordinated and implemented as planned. Implementation of the private sector component - and especially selection of the private concessionaire for the first container terminal - initially presented a major risk. This was mitigated by linking the progress of selecting a successful bidder for private concessionaire with implementation of the breakwater infrastructure (public sector component) as a condition of loan effectiveness. Although the loan effectiveness condition had to be amended to accommodate the commencement of breakwater construction and allow more time for selecting the private concessionaire, the condition ensured risk mitigation. project cycle stage: Appraisal, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/colombo-port-expansion-project-pcr
Southern Transport Development Project | Sri Lanka | Transport | 2014-08-01 | The success of the project can be attributed to a combination of solid government ownership and strategic vision; the long-term partnership between the government, ADB, and a number of development partners; the high level of advocacy of civil society groups; and a series of well-targeted technical assistance projects that bridged existing knowledge gaps. The Southern Transport Development Project is an invaluable source of lessons for mega road project planning and implementation. Planning and preparing a mega greenfield road project requires adequate allocation of resources and time to allow for timely and efficient commencement of civil works. The project implementation essentially focused on the concept finalization and detailed engineering in the first 4 years. For a country with no prior experience of expressway development, direct support from ADB on project conceptualization and detailed formulation is necessary to ensure project quality and final success. Even with such support, the finalization of engineering design took twice as much time as planned at project appraisal. ADB's lending instruments are now more diversified than they were in 1999. A recommended model is to use a technical assistance loan or a project design advance to assist the government in finalizing the engineering before the project loan proposal is submitted to the ADB Board. The impact of the lead time between the initial conceptualization and the commencement of services can be significant enough to change the feasibility of project alternatives and may result in a different preference. It was already envisaged in 1999 that the Southern Expressway would ultimately be a six-lane, high-capacity, limited-access express highway, and a stage-wise construction approach was adopted. However, the fast social and economic development in the southern region demanded a high-capacity highway earlier than the projection. The government, cofinanciers and ADB demonstrated great patience and flexibility to allow the further development of project concept during the early stage of project implementation, and finally ensured the relevance of project outputs. Managing the public relationship is an important part of successful project management. Even with the best ever compensation package in Sri Lanka, strong public protests were faced at the beginning of the project with regard to the land acquisition and compensation process. A proper project communication plan was not prepared during the project formulation and early implementation stage. To manage the public relationship, the Road Development Authority established a project communication plan in 2005 and ran a number of public awareness campaigns. Finally, the Road Development Authority gained strong support from stakeholders. Lastly, the implementation of mega projects can provide good opportunities for improving safeguard systems. Under the Southern Transport Development Project resettlement implementation plan, the mechanism of land acquisition and resettlement committee system was introduced to Sri Lanka for the first time. These committees were very popular among affected people as they played a very constructive role in redressing grievances. This mechanism managed a large number of cases which would otherwise have resulted in legal procedures, and thus significantly reduced implementation delays. The government also adopted the land acquisition and resettlement committee system in others sectors. It was also learned that the grievance redress system needed to be established as early as possible and stakeholders made aware of it. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/southern-transport-development-project-pcr
North East Community Restoration and Development Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development, Education, Finance, Health, Industry and Trade, Water and other urban infrastructure and services | 2013-11-11 | 1. The North East Community Restoration and Development implementation structure, including the delegation of responsibility to a provincial project management unit and the inclusion of all stakeholders in the provincial project coordination committee subproject selection process, was effective in implementing restoration activities. It provided a model for coordination between central, provincial, district, divisional, and local government, and encouraged cooperation with other agencies and minimized duplication of agencies' work. project cycle stage: Lesson Topics: 2. Implementation is difficult in the fluid security conditions of conflicts and their aftermath. However, staff members were motivated by the evident need for their services, as well as by pressure from both sides in the conflict to address basic infrastructure in all areas. project cycle stage: Lesson Topics: 3. Most contracts were relatively small and within the competence levels of local contractors, especially relevant in the difficult conditions for access and supply that applied during and after the conflicts. Use of local contractors, instead of outside companies, strengthened local ownership and avoided aggravating community and ethnic tensions. project cycle stage: Lesson Topics: 4. Baseline data are important. During conflicts, data change: infrastructure is destroyed and people are displaced. Monitoring surveys are difficult to conduct because of restricted access. The project management unit failed to expand the management information system to assess subproject impacts, the absence of which made postproject evaluation difficult. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-east-community-restoration-and-development-project-pcr
Small and Medium Enterprise Regional Development Project | Sri Lanka | Industry and Trade | 2013-01-08 | 1. ADB's Financial Sector Operational Plan supports the market-based pricing approach and stipulates that projects involving credit lines need to be designed to strengthen the capacity of financial institutions intermediating the credits and such a project should comply with the Operations Manual (D6) to avoid undermining the commercial incentive for the participating financial institutions to competitively mobilize finances and distorting the credit and interbank market. As such, it is the norm to adopt the average weighted deposit rate (AWDR) as a local anchor for determining subloan interest rates for ADB financial intermediary loans. Adopting the AWDR is considered generally consistent with best practices. However, adopting a local interest rate anchor is not widely practiced by other development partners, which in many cases adopt fixed interest rates, often lower than prevailing market rates. There may be a need to promote a standard local anchor for interest rates, as it will bring assistance from development partners into conformity with the local environment and avoid market distortions. Project formulation missions need to be mindful of consistency with other projects with financial intermediary loans. If a significant discrepancy in the interest rate exists with projects funded by other development partners, there will likely be implications for disbursement. 2. Small and medium enterprises (SMEs) generally suffer capacity constraints and lack skills in business development, marketing, planning, human resource management, and other business skills, which makes them less bankable. Had it been done, the capacity development technical assistance would have provided necessary skills training and improved the capacity of borrowing SMEs. Sri Lanka's Credit Information Bureau also covers SMEs. Participating commercial bank (PCBs) reported that they accessed the bureau's credit information report to appraise the SME subloans to be financed under the project. Despite the existence of fairly adequate institutions for SME risk assessment, PCBs emphasized the need for stronger support institutions, including training institutions for SMEs, and reliable funding sources for SMEs. 3. Delay in ADB's internal business processes, including the disbursement of withdrawal applications, often frustrates smooth implementation progress. Timely disbursement is critical, especially for financial intermediation loans, because financial institutions set the subloan interest rate based on the relending rate from the government and approve subloans to final borrowers only after they receive refinance from the government. Project administration requires closer attention to efficient and timely disbursement and other internal business processes. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/small-and-medium-enterprise-regional-development-project-pcr
Fiscal Management Reform Program | Sri Lanka | Public sector management | 2012-11-01 | A sequence to reforms. A key consideration in sequencing is that legislative and regulatory reforms require changes in the capacity of institutions (policy and rules), organizations charged with implementation, and the competencies of responsible government officers to change their management practices. This cascade of legislation-institutions-organizations-people provides a strategic sequence for reforms. However, in practice this is not a linear sequence. Rather, people (officials and stakeholders) are involved from the outset of the reform process. As policy reforms are an iterative, negotiated process, attention needs to be given to developing and maintaining a broad consensus for reform, as this is one of the most difficult and important challenges in sustaining change management processes. It is important to note that developing and maintaining a broad consensus for reform was one of the hallmarks of the Fiscal Management Reform Program (FMRP) that ensured unwavering government commitment to the programï¿½s strong legislative and regulatory reform content. Capacity constraints and project complexity. In addition to appropriate reform sequencing, ambitious and complex programs and projects are more likely to succeed if significant attention is given to building the capability and ownership of a broad range of stakeholders. As a sector development program, the FMRP successfully tackled a wide range of issues within a short time frame, while also contributing significantly to human development in several key implementation agencies. Advisory services to government under the project were also effective in keeping the program on track, especially in technical areas where previous experience was limited. Developing ï¿½softï¿½ capacities. Institutionalizing change management practices among those charged with implementing reformsï¿½such as the efforts undertaken in the program to provide staff with technical skills to implement systems and procedures at the Ministry of Finance and Planning (MOFP) and the key revenue departmentsï¿½requires upgrading of technical and change management competency. It is necessary to enable government to sustain capacity development programs beyond the life of a program (for example, by providing training experts, particularly to develop soft capacities). | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/fiscal-management-reform-program-pcr
Tsunami-Affected Areas Rebuilding Project | Sri Lanka | Finance, Public sector management, Transport, Water and other urban infrastructure and services | 2012-11-01 | Reestablishing the identity papers and legal documentation of disaster victims is an essential and urgent necessity, and ADB's support to the government's program improved its delivery and effectiveness by ensuring sufficient funds. As highlighted in the performance audit, the mobile clinics facilitated legal documentation and proved to be an efficient mechanism for emergency situations. This can be adopted as a good practice for future interventions. For components B, E, and H, substantial time was required to mobilize community- based organizations and implementing-partner nongovernment organizations (NGOs) to reach hundreds of villages to be served under major disaster reconstruction programs. This resulted in delays at the start of implementing activities under these components, and support from NGOs was required. To avoid underutilization of newly built facilities, equipment, staff, and operations budgets should be identified and allocated by the responsible government agencies for activities involving rehabilitation and expansion of buildings and hospitals. The success of the women's rural development societies (WRDSs) involved in components B and H, and earlier in the North East Community Restoration and Development Project (NECORD) and NECCDEP (North East Coastal Community Development Project) projects, demonstrated that community-based organizations contribute to a sustainable mechanism for improving economic activities at the local community level while concurrently achieving aspects of the gender action plan by empowering women through increased income, confidence, and quality of life. Implementing ADB's requirement to incorporate strengthened building standards into the design of buildings and structures was not possible. It took the government 3 years to develop the revised standards, by which time most structures had been designed and many constructed. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/tsunami-affected-areas-rebuilding-project-pcr
Conflict-Affected Area Rehabilitation Project: Project Completion Report | Sri Lanka | Agriculture, natural resources and rural development, Education, Energy, Health, Public sector management, Transport | 2012-10-01 | At appraisal it was estimated that the project would be implemented over 4 years and be completed by December 2007. Due to the conflict, works could not be undertaken in the time envisaged, thus Loan 2043 was extended four times, to 31 March 2011, and Loan 2044 twice, to 31 December 2010. ADB needs to allow adequate time for planning, design, tendering, and construction of projects where a conflict is involved, as the incidence of security issues severely hampered the implementation of the project. Loan extensions cause extra work for the implementing agencies and ADB staff, and tend to discourage government agencies as they feel that their project is always behind schedule. In future, for similar projects under emergency or conflict situations, ADB needs to ensure that timetables are realistic. The appraisal estimate for component A was that 500 km of roads could be rehabilitated with double-bitumen surface treatment. As a result of the government's decision on national highways, the road surface was changed from double bitumen to asphalt concrete. This led to numerous contract variations and extensions. Therefore, rehabilitation of 500 km was reduced to 198 km. As for component B (power and electrification), it was fortunate that the Government of Norway agreed to cofinance it and that Japan Bank for International Cooperation (JBIC) agreed to undertake the Vavuniya-Kilinochchi transmission line, because otherwise the project would have had difficulty in meeting its objectives. In a major change in scope in 2006, funds released from component B thanks to the external assistance from Norway and JBIC were reallocated to component A. However, the scope of component A was reduced from 500 km to 300 km due to cost increases. Eventually, only 198 km of road could be completed. ADB needs to ensure that financial details, including cofinancing and assistance from other donors, are already in place at appraisal, as otherwise the possibility of not achieving project objectives becomes too high. The executing agencies did not always submit their project completion reports on time, and not always in the format requested by ADB. The reports also did not contain sufficient information on government counterpart funds, which forced the project completion review mission (PCRM) to spend considerable time on obtaining the data from each executing agency. In the case of Ceylon Electricity Board (CEB), this proved extremely difficult, as the agency did not have adequate records dating back to the start of the project. This has been a common problem in several previous projects, where the executing agencies did not seem to be aware of how much was spent from government funds to the level of detail necessary to undertake a project completion report. ADB needs to ensure that the executing agencies for ADB projects collect and supply all data required in the project completion report; otherwise a PCRM spends too much time chasing such information. In a project that involves several executing and implementing agencies, coordination between all agencies is of the utmost importance. While the national and provincial project coordinating committees (PCCs) did all that was possible to implement the project successfully, a more central unit for coordinating project activities would have improved implementation. The establishment of a dedicated project management unit (PMU) to facilitate the implementation and coordination with different government agencies should be considered for future projects of a similar nature, especially when they involve multiple sectors, multiple layers of governments, vast geographical areas, and other development partners. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/conflict-affected-area-rehabilitation-project-pcr
Secondary Education Modernization Project II | Sri Lanka | Education | 2012-02-07 | 1. Investment in information and communication technology (ICT) infrastructure requires additional resources and training to ensure that the facilities are adequately and appropriately utilized and maintained. These include (i) training for the school principal and ICT teacher on the effective use of ICT, (ii) a robust mechanism for providing funding to cover operating expenses such as electricity bills and internet access, (iii) a mechanism that would provide resources to schools (through provincial institutions) to maintain and update hardware and software as needed, (iv) improvement of the curriculum to integrate computer-assisted learning into the teaching of different subjects, and (v) parental education and involvement in encouraging students to enroll in ICT options at O- and A-level. The school visits conducted as part of the project completion report mission confirmed that the resources provided under the project are available in schools but are not being fully utilized, except where a particularly motivated school principal or ICT teacher is involved. Further, ICT infrastructure provided under various initiatives over the years (regardless of financing source) has become obsolete, and even when the hardware is still in working condition, the software has been rendered ineffective by viruses. [Main text, para. 61] project cycle stage: Lesson Topics: 2. Stronger monitoring and support from zonal facilitators is essential for ensuring effective use of interventions made in quality of learning. Although the project developed several good training modules on Program for School Improvement, school-based assessment, teaching learning methodologies and teaching learning resource development and use, the effective use of these modules cannot be sustained unless supported in schools and classrooms by a committed zonal facilitator. This individual is required to visit each school on a regular basis (at least once per month) to ensure that teachers and principals are supported in adopting new management and teaching techniques. With only four facilitators per zone, covering over 100 schools and many subjects in each, coverage is inadequate. It is important to ensure that a sufficient number of zonal facilitators are made available. Strengthening their role within the system and monitoring their performance to ensure delivery will be a key enabler for implementing future projects in school education. [Main text, para. 62] project cycle stage: Lesson Topics: 3. A general lesson learnt is that the sustainability of initiatives beyond the lifetime of the project rests heavily on the level of reinforcement provided by the Ministry of Education (MOE), in the form of circulars, training, and regular follow up by provincial and zonal staff. For example, initiatives such as school-based assessment and Program for School Improvement, which were supported and reinforced by the MOE (e.g. through circulars) have had better success than initiatives such as teaching learning methodologies and teaching learning resource development and useU, which did not enjoy the same level of support. Hence, in order for future projects and programs to be successful, ADB would have to closely align these with the government's Education Sector Development Framework and Program to ensure greater institutional ownership and support. [Main text, para. 63] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-education-modernization-project-ii-pcr
North East Coastal Community Development Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 2012-01-08 | 1. A strong project management unit with qualified staff under a competent project director who remained throughout the project enabled implementation despite disruption from a tsunami and renewed conflict. [Main text, para. 63] project cycle stage: Lesson Topics: 2. The Gender Action Plan (GAP) provided a framework for gender-balanced activities but a project management unit gender specialist should have been included in the project design to manage the plan. Implementing the GAP separately through the rural development societies and the women's rural development societies gave women space for involvement but reduced opportunities for fully gender-balanced operations. [Main text, para. 64] project cycle stage: Lesson Topics: 3. Providing initial training for the government field staff, which had been weakened by the civil conflict, would have helped implementation. The capacities of the implementing partner nongovernment organizations were overestimated at the design stage and the project management unit spent a lot of time on guidance and training. [Main text, para. 65] project cycle stage: Lesson Topics: 4. No legal precedents for the special area management planning safeguards existed and no single agency was empowered to handle legal aspects of coastal resource planning. Implementation of coastal planning needed better interagency coordination and the Coast Conservation Department should have been included in the design as the implementing agency for component C to give a greater sense of ownership. [Main text, para. 66] project cycle stage: Lesson Topics: 5. Channeling credit through community organizations rather than individuals could reduce defaults through peer group pressure and lower administration costs. Credit lending terms should be consistent with the prevailing local microfinance conditions. [Main text, para. 67] project cycle stage: Lesson Topics: 6. Inclusion of an innovative process monitoring system enabled the correction of processes during implementation. This was especially important given the volatile and uncertain security conditions. Process monitoring helped in assessing the work of nongovernment organizations and modifying village planning, livelihood enterprise development services, and microfinance processes. [Main text, para. 68] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-east-coastal-community-development-project-pcr
Rural Finance Sector Development Program | Sri Lanka | Finance | 2012-01-05 | 1. Overly ambitious and complex projects are less likely to be successful. The Program objectives had a strong rationale and the design was technically sound. However, in view of the weak implementation capacity of the executing agency and the implementing agencies, the Program would likely have yielded better results with a more focused and prioritized set of policy actions and project activities. Moreover, the Rural Financial Sector Development Program was approved only three months prior to the April 2004 parliamentary election. While the election outcome and subsequent policy direction could not have been fully anticipated at the time, there was sufficient uncertainty regarding continued political support to warrant reconsideration of the timing of Board consideration. project cycle stage: Lesson Topics: 2. The program loan tranches were front-loaded, with $35 million of the total program amount of $50 million programmed for the first two tranches. The first two tranches were largely preparatory measures and intermediate steps. Had the program been back-loaded with relatively larger amounts allocated to the third and fourth tranches, it is possible that the authorities would have been more inclined to implement some of the more difficult reform measures. project cycle stage: Lesson Topics: 3. Timely project completion report (PCR) is important for maintaining policy dialogue and assessing the need for follow-up actions and future assistance. Project Administration Instruction No. 6.07A recommends that the PCR be prepared between 1-2 years after project completion. In the case of Rural Financial Sector Development Program (RFSDP) program loan, the second (and final) tranche was released in February 2006. The bulk of activities under Project 1 and Project 2 were completed in 2008. Given that considerable time has lapsed since Program implementation ended, and significant staff turnover in the executing agency and implementing agencies since, the authorities were not able to contribute meaningfully to Program assessment. PCR preparation would have benefited from the insights of officials directly involved in program implementation. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/rural-finance-sector-development-program-7
Sri Lanka: Road Sector Development Project (1986-SRI[SF]) | Sri Lanka | Transport | 2011-12-16 | 1. A sound and scientific methodology on road project selection (including expected social development impact as a criterion) reduces the exposure of the selection process to political influences. Further, having the necessary data (traffic counts and road condition) facilitates arriving at sound decision during the road project selection process. Evaluation noted the mechanics of the final screening and decision making of the implementing agency were not clear, nor was the relevance of the selected provincial roads to the objectives of the project. Selection of some road projects appeared to have been based more on political rather than economic and social considerations. [Main text, paras. 2,22,47-49,82] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Transport planning 2. More careful monitoring and supervision would have been required to review the progress of the program, to understand its key issues, and to propose alternative approaches where necessary. The design of the Reform Program with its numerous components was complex, so efforts on monitoring and guidance should have been made during project implementation. This was not done by ADB. Many targets of the Reform Program were not achieved, and neither ADB nor the implementing agencies reviewed the issues that prevented achievement. Almost all memoranda of understanding between the government and ADB, as well as monthly progress reports prepared by the consultants during project implementation, were not comprehensive and did not cover all targets of the Reform Program. Hence, the project completion reports of ADB, the Road Development Authority and the Ministry of Local Government and Provincial Councils (MLGPC) could not evaluate all the activities of the Reform Program. The main consultant was based in Colombo at the MLGPC and as such did not have much direct interaction with the four provincial road administrations, resulting in less effective monitoring of progress. With careful monitoring and attention, the number of successful targets and the quality of capacity building could have been greater and activities of the Reform Program could have been more user-oriented. [Main text, paras. 55,86] project cycle stage: Implementation, Completion Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project supervision Sector Related Issues: Roading Sector Related Issues: Transport planning Policy & Reform: Reform 3. The requirements, key issues, terms of reference, selection criteria including qualification of consultants, implementation structure, and understanding and ownership of the technical assistance (TA) by the implementing agencies should have been described carefully according to the requirements of technical assistance. If poor performance was observed, prompt action would have been required to minimize the loss of time and funds. The consultancy services for the detailed engineering design of national highways and TA 4075-SRI were incomplete due to poor performance by the consultants and did not provide significant outputs. The Road Development Authority also should have developed a well-maintained performance recording system. [Main text, paras. 3,19,76,87] project cycle stage: Implementation Lesson Topics: Project Management: Consultants Sector Related Issues: Roading Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/sri-lanka-road-sector-development-project-1986-srisf
Aquatic Resource Development and Quality Improvement Project | Sri Lanka | Agriculture, natural resources and rural development, Finance | 2011-12-01 | A single sector approach aids simplicity and a project's effectiveness. The strong project management office (PMO) with qualified staff and single project director effectively progressed the project, even if subsidiary implementing agencies lacked capacity. Key elements were seconding the implementing agency's staff, absorbing personnel contracted for the project to the PMO, and detaching the PMO from the executing agency's offices. For this project, engaging and training in-house or contracted staff of the implementing agency for social mobilization was more sustainable than recruiting outside nongovernment organizations (NGOs). Longer lead times (up to 2 years) should be allowed for the complex legal and administrative processes required to amend Acts of Parliament. Similarly, completing major civil works within 1-1/2 years is unrealistic. Regular review and updating of the DMF would have aided monitoring and evaluation. A design and monitoring framework (DMF) needs to follow ADB's standard format yet be dynamic. Credit line design needs to be based on studies of market demand. Given a profitable and properly regulated enterprise like culture-based fisheries, community-based organizations (CBOs) can be developed into sustainable, profitable businesses. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/aquatic-resource-development-and-quality-improvement-project
Distance Education Modernization Project | Sri Lanka | Education | 2011-12-01 | The project involved the establishment of an entirely new platform of learning, with investments in hardware and software and including creation of partnerships with institutions that were to develop their course content into online distance learning format. This constituted a major step toward a new concept of learning. There is a risk that the system will eventually collapse unless it is put on a sound business and strategic footing in the near future. In addition to the risk of dilapidation of equipment (which for now is still relevant and state-of-the- art), staff capacity that was sourced, developed, and placed to keep National Online Distance Education Service (NODES) and network access centers (NACs) operational risks being eroded as the highly skilled people begin to find alternative work in the market. One major lesson is that longer-term support could have been built into project design to enable more time for preparing a sustainability plan with concrete milestones, including adequate transition arrangements followed by approval of an institutional framework for the successor organization. Another lesson arises from the novelty and innovation of the projectï¿½a higher priority should have been placed on social marketing and awareness raising among potential partner institutions and students, to ensure broad-based demand and a strong supply of market- oriented courses. There is great potential for self-sustainability in this model if its management is outsourced or it is transformed into a corporate entity, but inclusion of social marketing will be key to its success. Also, mobilization of the private sector requires effective communication and a credible monitoring mechanism to ensure that matching grants are used effectively. An important lesson regards the nature of the courses that were offered and if they were the most appropriate ones for an online distance-learning platform. While the project was designed to create access to postsecondary (degree-level) programs for those A-level achievers who would not have an opportunity to enroll in traditional university programs, it may not have been suitable for students newly transitioning from secondary to tertiary education for whom distance learning was less desirable or appropriate, given the strong preference for more traditional modes of post-secondary education. Such a system may be of more relevance and therefore better used if it focuses on non-degree courses to supplement formal education, especially courses that help the employed broaden their skills or the unemployed making themselves more employable. This has deep implications for the future of NODES, as the ?new management? or policymakers consider how they want to develop and use it. Finally, an important institutional lesson arises from the need for better planning and coordination between all ministries and agencies that have a potential stake in a project's outputs. In the case of this project, NODES can be of relevance and use to the training and education programs offered and governed by various ministries and agenciesï¿½e.g., Ministry of Education, Vocational Training Authority. Already, several of these courses relate to vocational areas (hotel management; computer studies and/or software development; food and beverages; etc.) and their thrust is aligned with the government's priority goal of developing information technology (IT) and tourism as focus areas for investment in technical education and vocational training, supported by public-private partnership and an information and communications technology (ICT) platformï¿½all of which NODES offers. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/distance-education-modernization-project
Sri Lanka: Forest Resources Management Sector Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 2011-12-01 | 1. Projects, which include enactment of legislations, should be provided ample implementation timeframes. The difficulty of enacting legislation in support of a project activity and within the timeframe of a project is often underestimated. The estimated implementation time of the Forest Resources Management Sector Project in Sri Lanka project should have considered possible difficulties faced by line agencies in pushing for the component legislation through the national parliament. [Main text, paras. 21, 24] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/sri-lanka-forest-resources-management-sector-project
Financial Markets Program for Private Sector Development | Sri Lanka | Finance | 2011-10-01 | The timing of a program is crucial to the effectiveness of its outputs and outcomes. Difficulties to obtain approvals of the numerous legislative actions in this program could be traced to the change of government (and the fact that the government did not hold a majority of seats in the Parliament). The program's achievements of performance targets benefited from the eventual improvement of the political and economic landscape from 2009 onwards. Therefore, to ensure the effective and pragmatic design of similar programs in the future, it is imperative that ADB be cognizant of potential changes in the country's political environment as well as factor in important variables (such as the internal conflict in this case) that could impact program implementation. Furthermore, it is prudent to minimize the number of legislative actions to ensure effective program implementation. The program had an excessive number of legislative actions that contributed to program implementation delays. In addition, a salient feature of this program is the transparent and effective approach to monitoring the restructuring of a bank. This feature can be applied to other similar entities. The key performance indicators that were embedded in People's Bank Strategic Plan 2009-2014 were rigorously reviewed on a biannual basis to ensure that the bank restructuring was on track. These key performance indicators were comprehensive and broad-based and encompassed major aspects of operational activities such as capacity adequacy, asset quality, management, earning, and liquidity. Finally, a key success of a reform program is the relevant design that incentivizes strong government ownership on institutional strengthening, in this case, by improving bank's operational management: supporting profitable business lines such as pawning, tightening credit reviews and recoveries to reduce nonperforming loans (NPL), and controlling overhead costs such as reducing headcounts to improve performance on a per employee basis. The fact that People's Bank continued restructuring and committed itself to performance indicators to improve bank operations over and beyond what was agreed to under the program underscored the success and sustainability of the ADB support. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/financial-markets-program-private-sector-development
Asian Development Bank's Assistance for Low-Income Housing Finance in Sri Lanka | Sri Lanka | Finance, Water and Other Urban Infrastructure and Services | 2011-08-31 | 1. Targeting poorer households could make the project welfare impacts more robust requiring flexible loan procedures and requirements. The project targeted households with incomes below the 55th income percentile (low income). As households were required to meet conventional standards of creditworthiness, including having loan collateral, the project was in effect not available to the very poor. Hence, most project beneficiaries were near middle-income households, whose labor force participation, school enrollment, and health conditions were already high. [Main text, paras. 60-63,66,68,72,76] project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Methodologies/Approaches: Targeting 2. For similar projects in the future, the design team can encourage flexibility in loan terms. The Impact Evaluation Study showed that in several cases, the impacts were larger and more significant in the case of longer-term loans. This supports the hypothesis that longer loan terms, with lighter repayment burdens, could increase household welfare. [Main text, paras. 53,60,78] project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/asian-development-banks-assistance-low-income-housing-finance-sri-lanka
Sri Lanka: Country Partnership Strategy 2009-2011 - Final Review Validation | Sri Lanka |  | 2011-08-28 | 1. The political economy of Sri Lanka required a more comprehensive understanding of the implementation time frame and greater appreciation of the need to inject policy reforms on a phased basis. The expectations of some of the interventions (e.g., restructuring of institutions, Aquatic Resources Development and Quality Improvement Project, Secondary Towns and Rural Community-based Water Supply and Sanitation Project, and fiscal and tariff reforms) were somewhat misplaced, not having been carefully planned in a phased manner with more realistic time frames to suit local conditions. Further, the design of some projects (e.g., Small and Medium Enterprises Regional Development Project and Forest Resources Management Sector Project) did not provide for strategic adaptations in respect of interventions such as credit components. project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Design: Project design Country Context: political economy factors Policy & Reform: Policy reforms/framework 2. Policy dialogue in the context of emerging economies beset with domestic complications is a long and arduous process that requires persistence, follow-up, and commitment to the achievement of end results. Policy-based lending encountered many constraints such as inadequate stakeholder partnership, political and trade union opposition, and absence of a comprehensive approach to policy dialogue by ADB, which would have necessitated a phased and programmatic approach to discussion of policy and sector reforms. project cycle stage: Implementation Lesson Topics: Modality: Policy-based lending Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Policy dialogue 3. Capacity development is a long and sustained undertaking that requires ownership, understanding, and support from within the country and should emerge in response to demand to develop and strengthen institutions for better delivery of services. Institutional capacity limitations were known and remedial measures were adopted through accompanying and stand-alone advisory TA to strengthen capacity. A total of 29 capacity development TA operations were approved during this period, but field visits suggested that more preparatory work should have been done before TA operations were approved, including consultations with stakeholders. The Umbrella Capacity Development Fund initiative for which TA was approved did not get off the ground despite the resident mission's interest and efforts. project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Capacity development Capacity Development: Ownership Other: Resident Mission 4. To ensure that outputs and outcomes can be continued, sufficient funding for maintenance, including policy level commitment for enhanced funding support, is crucial. This becomes all the more pronounced when civil conflict endangers people's participation and involvement. Insufficient funding for maintenance, such as in the case of the Road Maintenance Trust Fund, Ceylon Electricity Board, and National Water Supply and Drainage Board, and multiple agencies handling sector functions, such as in the transport and information and communication technology sector, led to lack of consistency in the approach to operation and maintenance. project cycle stage: Implementation Lesson Topics: | Country Partnership Strategy Final Review |  | http://www.adb.org/documents/sri-lanka-country-partnership-strategy-2009-2011-final-review-validation
Coastal Resource Management Project | Sri Lanka | Agriculture, natural resources and rural development | 2010-12-01 | One key lesson is the need to involve communities in project activities from inception to completion. Law enforcement alone cannot safeguard the environment. To ensure communities benefit, their involvement is important even in large infrastructure development and rehabilitation projects. Social awareness programs are important throughout project implementation and beyond to encourage community ownership of their resources. Even at the institutional level, a sense of ownership has to be developed early in the project. This can prevent delays during implementation and ensure continued operation and maintenance. Communication among stakeholders should be strengthened to convey correct messages and prevent misunderstandings. The project trained coastal communities in alternative livelihoods to prevent their over- exploitation of coastal resources. To ensure the sustainability of the alternative livelihoods, they should link to markets to generate income. If not, communities may return to their traditional activities. Delays in implementation ensue when components are clustered in a project. Further, clustering discourages ownership of project outputs. Combining harbor development with coastal conservation delayed project implementation considerably because the activities are not complementary. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/coastal-resource-management-project-pcr
Plantation Development Project | Sri Lanka | Agriculture, natural resources and rural development | 2010-12-01 | First, delays were avoidable if the project preparatory technical assistance (PPTA) financing percentages had been retained. During the loan appraisal and negotiation phase, the recommended financing percentages of the PPTA of 70% ADB-30% regional plantation company (RPC) for social amenities and 90% ADB-10% RPC for the social development programs were adjusted to 50% ADB-50% RPC, resulting in RPCs not participating. Given the weak balance sheets and the lack of profitability, the desire for greater ownership through increased financial contribution was inconsistent. The subsequent increase in ADB financing overcame the issues, and implementation proceeded rapidly over 3 years. Second, there was unnecessary design complexity and add-ons. The core project components relating to investment and social objectives were coherent and achievable. The inclusion of additional inputs for the development of Tea Association of Sri Lanka (TASL), marketing alliances, and demand-based public research were not client-driven nor demanded, lacked appreciation of the commercial and proprietary rights attached to market relationships, and research findings as contributing factors for achieving competitive advantage. Further, there were insufficient financial and governance benefits to merit insistence on an international fund manager when the size of the fund was extremely limited and the duration of funds available for investment short. In addition, project outcome and impact indicators were poorly defined in terms of sustainability and what this represented. There was inadequate consideration of sector financial risks, including wage inflation, and political risks relating to price escalation in the sector. A major cost item, the inflation adjustment formula for RPC leases, was not reflected in the institutional nor design framework. The use of a credit line was an effective implementation modality. Significant advantages from longer loan periods, grace periods, and fixed interest rates during a period of high and rising interest rates and markedly lower capital availability supplied a definite demand. The use of fixed interest rates during the current period of declining interest rates has, however, increased the requests for early repayment. THe Development Finance Corporation of Ceylon (DFCC), the Ministry of Finance, and Ministry of Plantation Industries (MPI) should consider the option of interest rate adjustment to outstanding loans. Similarly, the apex body agreement did not adequately cover for the recycling of early repayments, and, as such, interest earned and loan repayments can be retained by the apex body. Participating financial institutions (PFIs) are required to pass early repayments back to the apex body. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/plantation-development-project
Protected Area Management and Wildlife Conservation Project | Sri Lanka | Agriculture, natural resources and rural development | 2010-11-01 | Reference to international nongovernment organizations (NGOs) and public-private partnerships in the report and recommendation of the president (RRP) provoked local wildlife activists and politicians, resulting in project delays. This could have been avoided by wider pre-project public relations efforts. Launching a complex project through the Department of Wildlife Conservation (DWC), a small organization faced with structural reform, was overambitious. A two-phased approach (phase 1: capacity- building and restructuring; phase 2: implementation) would have been more appropriate. Loan covenant time frames underestimated the time required for the government procedures to amend the Fauna and Flora Protection Ordinance (FFPO) and for institutional reform. Heading the project management unit (PMU) with someone from outside the DWC was detrimental to engaging the department staff. Introducing large numbers of technical assistance (TA) consultants into the DWC that was understaffed resulted in inefficient use of consultancy expertise. Regular review and updating of the project framework would have aided monitoring and evaluation. The outreach program was made more sustainable by being implemented by the executing agency's own staff than it would have been by recruiting outside NGOs, who would have left when the project closed. Delegation of powers to the field enhanced pilot protected area (PPA) management but it also increased the importance of self-motivated PPA leadership. It was unreasonable to expect government officers to engage in commercial links and marketing initiatives with private enterprise in such a short time. A formal monitoring system should have been established by the DWC at the start of the project. Training for all PPA ranks and public awareness-raising were positive factors in improving conservation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/protected-area-management-and-wildlife-conservation-project
Sri Lanka: North East Community Restoration and Development Project | Sri Lanka | Public Sector Management | 2010-09-30 | It is noted that the project worked well with both sides in the conflict, and was well accepted in conflict-affected areas. Developing this type of rapport is important, and reflects well on the project implementers. The lessons should be relevant in other conflict or post-conflict situations.[Main text, page 8, section E(ii)] project cycle stage: Implementation Lesson Topics: | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/sri-lanka-north-east-community-restoration-and-development-project
Forest Resources Management Sector Project | Sri Lanka | Agriculture, natural resources and rural development | 2010-09-01 | Monitoring of production-related activities. A wide range of production activities were financed under the project new woodlots, the maintenance of old woodlots, clear-felling, and the replanting of mature plantations, for example. Detailed physical and financial information was not maintained at the individual enterprise level, however. This would have been best collected through regular stock assessments to estimate growth rates more clearly. The resulting information would have been valuable in two ways. It would have made it possible to more accurately determine the financial returns to beneficiaries at the household level. At the state plantation level, it would have informed policy decisions on investment in the sector. Institutional change process. The magnitude of loss in potential revenue because of its delay in introducing open competition in state plantation timber harvesting was demonstrated analytically to the government through a comprehensive plantation measurement and valuation system. This led to an increase in stumpage rates and provided an incentive for the Forest Department to take steps to review the mandate of the State Timber Corporation and make it more cost efficient. But much still needs to be done to enhance competitiveness in the sector. The process of achieving sustainable institutional change and strengthening organizations demands time, rigorous analysis, informed policy dialogue, and active engagement. Public response to project activities. Consultations, mass media campaigns, awareness workshops, and beneficiary involvement in conflict resolution meetings all contributed to a greater understanding of project interventions by key stakeholders. Implementation activities did not appear to have created significant public protest and generated no critical news reports, public interest litigation, or petitions. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/forest-resources-management-sector-project
Power Sector Development Program | Sri Lanka | Energy | 2010-01-12 | 1. A strong sector development program (policy and investment) entails a design that properly links and demarcates expected impacts, outcomes, and outputs. The Power Sector Development Program (PSDP) failed to coherently set out the objectives between its policy and investment components. Consequently, the lack of clarity between the two components in the PSDP framework contributed to the sector program's underperformance and poor design made it difficult to evaluate. Thus, in designing of such programs, proponents need to properly articulate linkage of impact, outcomes and outputs in various project documents. [Main text, paras. 40,69] project cycle stage: Design, Implementation Lesson Topics: 2. Advance procurement actions and decisiveness on the end of the Ceylon Electricity Board and ADB could have prevented procurement delays. The project completion report noted that the project was extended by 24 months to accommodate delays in procurement. [Main text, paras. 20, 71] project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/power-sector-development-program-0
Southern Province Rural Economic Advancement Project | Sri Lanka | Finance, Transport | 2010-01-12 | 1. The project was particularly effective in meeting the needs of the government. The project responded very effectively by repairing the damaged rural gravel roads and pedestrian bridges after the May 2003 floods. As requested by the government, the project also responded positively by changing its scope from gravel roads to paved surface roads. The responsiveness and flexibility demonstrated by the project was laudable, and the project provided a worthy example for the design and management of future projects. project cycle stage: Lesson Topics: 2. Since the project had two implementing agencies supervised by different agencies, project coordination was difficult. A more suitable arrangement involving dual implementation agencies may be through a region-based apex financial institution, which is also assigned responsibility for establishment and operation of enterprise development service support activities and works closely with the regional organization responsible for sustaining the enabling environment. During the design stage, project implementation arrangements and responsibilities of each agency should be clearly explained in the project administration memorandum. project cycle stage: Lesson Topics: 3. Future projects need to address issues associated with the financial capacity of pradeshiya sabhas to develop and maintain rural infrastructure through closer monitoring, obtaining greater commitments from provincial and local organizations, and the use of soft loans for capital works tied to user-pay financial plans for civil works such as rural markets, where a financing charges mechanism already exists. project cycle stage: Lesson Topics: 4. Future projects designed to address rural gravel road maintenance issues need to be more carefully designed through (i) identification of project roads during appraisal; (ii) identification of suitable gravel sources in proximity of the project roads; and (iii) prior commitment from each pradeshiya sabha to participate in the project, including prior establishment and commitment of funds to a road maintenance account. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/southern-province-rural-economic-advancement-project
Third Water Supply and Sanitation Sector Project | Sri Lanka |  | 2009-01-11 | 1. Demand-driven, community-based development requires a flexible design to accommodate community preferences. Accordingly, the project design team needs to ensure that sufficient time is alloted to overcome initial hesitation by communities. In this project, the overall success of delivering the investments can be attributed to sound planning and flexible design processes, particularly in mobilizing community participation in the initial stages of the Project. Participatory planning is an effective tool under the demand responsive approach to enable users to express their demands. [Main text, paras.7,43,52(i)] project cycle stage: Design Lesson Topics: Project Design: Project design Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation 2. Requiring cash and labor contributions and giving operation and maintenance responsibility to communities enhances commitment and ownership. project cycle stage: Implementation, Operation Lesson Topics: Project Management: Operation and maintenance Capacity Development: Ownership Methodologies/Approaches: Community approach 3. Handover of water supply to local communities requires continued support during the transition and follow-up periods. Ongoing capacity development efforts need to include operation and maintenance and financial management training. project cycle stage: Implementation, Completion Operation Lesson Topics: Capacity Development: Capacity development Sector Related Issues: Water resource management 4. Conducting groundwater investigations over a period of time sufficient to determine variations in yield and recharge rates can prevent water shortages. In future projects, shortages in groundwater experienced in some rural areas need to be identified as early as the feasibility stage planning. In Sri Lanka, depletion of the groundwater table is a common issue in dry-zone areas. Closely located agrowells were identified as a major cause of this, in addition to other natural and manmade hazards. Hence, in cases where groundwater was selected as the water source for pipe schemes, a safety factor was introduced to the actual possible yield from the well in calculating the probable extraction of water to allow for recharge and to avoid overextraction. In a small number of schemes, the implementing agency constructed additional boreholes or connected to nearby piped schemes to assist villages faced with shortages. [Main text, para. 52(iv), Appendix 9] project cycle stage: Feasibility, Implementation Lesson Topics: 5. Policy reforms, to be more effective, require a more careful assessment of political risks and upfront consultation with government leadership and various stakeholders. By project completion, expected sector reforms have been noted to be less satisfactory and only partially completed. For instance, a national water resources policy and act, included as one of the project covenants, was not achieved largely due to lack of political support. Government leadership and a more process oriented consultations are therefore critical in the policy formulation and broader stakeholder acceptance. [Main text, paras. 20-23,52(v)] project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Ownership Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation 6. Project preparatory activies needs to include an up-front capacity assessment of national procurement regulations and practices to avoid unnecessary delays. Accordingly, this needs to be reflected in the comprehensive procurement plan for new projects and used as a monitoring tool during implementation. Delays in procurement occurred due to government procedures in processing and approving contracts. After ADB intervention though, procurement procedures were improved by the Government. [Main text, paras. 34,52(vi)] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Procurement Capacity Development: Capacity assessment 7. Loan covenants for land acquisition needs to be strengthened to include provisions for preparing safeguard documents in case ADB's involuntary resettlement policy is triggered. Safeguards monitoring and reporting if not carried out effectively will lead to issues not addressed in time and appropriately. In this case, land acquisition has caused delays in some urban subprojects. Evaluation further noted that even after project completion, land compensation has yet to be completed for nine parcels of land. [Main text, paras. 15,32,52(vii); Appendix 10] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-water-supply-and-sanitation-sector-project
Secondary Education Modernization Project | Sri Lanka | Education | 2008-11-14 | 1. Implementation of the Project has shown that schools that are well managed implement project activities more effectively and efficiently. This strengthens the importance of champions for the success of any new initiative. Champions can be both identified and developed. [Main text, para. 72] project cycle stage: Implementation Lesson Topics: 2. Any project that attempts to bring about substantial systemic changes needs to be realistic about the goals including the timeframe for such changes. Due consideration for the sequencing and interdependence of project components as well as buy-in from stakeholders are essential in this process. As bringing about systemic change is an incremental and time-consuming process, continued support is crucial to its sustainability. The project completion report noted the lack of progress in career guidance, development of public-private partnership and school based management due to inadequate support from various stakeholders. [Main text, paras. 5, 21, 26-27, 64, 73] project cycle stage: Lesson Topics: Project Design: Project design Capacity Development: Ownership Capacity Development: Partnerships Policy & Reform: Reform 3. To bring about and sustain change, government ownership is crucially important. As a result of strong government ownership, many project components remain successful, or remain on the agenda for implementation. [Main text, paras. 59, 67, 74] project cycle stage: Concept Design Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Ownership 4. The potential of project activities cannot be maximized without effective monitoring and the commitment of officials trained in monitoring and evaluation. Project experience noted lack of attention given to monitoring and evaluation. Up until 2005 (almost five years into implementation), the project lacked systematic monitoring of its components and outcomes . [Main text, paras. 31, 76] project cycle stage: Implementation Lesson Topics: 5. The first computer procurement experience indicates that bidding documents need to always clearly specify instructions and requirements. Should there be doubts on the authenticity or completeness of bidders' submissions, the government needs to directly verify information with manufacturers. As noted in this education project, vague instructions in the bidding documents had caused misunderstanding on deliverables of contractors and this continued to be an outstanding issue at project completion. Lessons from this experience were incorporated in the succeeding contract awards. [Main text, paras. 48, 51, 53, 77] project cycle stage: Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/secondary-education-modernization-project
Tea Development Project | Sri Lanka | Agriculture and Natural Resources | 2008-03-03 | 1. The outcome of several project interventions was affected by changes in government policy during project implementation. The success of institutional reforms is closely linked to consistency in government policies. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Risks/Risk management Policy & Reform: Policy reforms/framework 2. To ensure implementation of institutional reforms, an agency or unit that has adequate mandate and power should be involved. A project management unit lacks the power to put pressure on the Government to enact policy reforms. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Institutional analysis Policy & Reform: Policy reforms/framework 3. A voluntary staff separation package program for streamlining an institution should use staff performance as an eligibility criterion. The voluntary early separationprogram under the Project did not achieve the expected results because it was not linked to staff performance indicators. project cycle stage: Design, Implementation Lesson Topics: 4. A plan for institutional reforms should be designed with due consideration for the effectiveness of the proposed actions. The reconstitution of the boards of the tea-related institutions was a reform intended to ensure the perspectives of the private sector and the tea smallholders were heard with respect to management decisions. Although the boards were reconstituted, their effectiveness did not increase as the role of the boards did not change, despite the inclusion of the new members. project cycle stage: Appraisal Implementation Lesson Topics: Capacity Development: Capacity assessment Capacity Development: Institutional analysis Sector Related Issues: Public-private partnership Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform Policy & Reform: Reform Methodologies/Approaches: Participatory approach 5. A mechanism to continue and replicate successful activities after a project ends needs to be established prior to project completion. Despite the potential for continuity of the homestead development component, all activities ceased at the end of the Project and the increase in capacity relating to homestead development is not being utilized. project cycle stage: Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Crosscutting Issues/Themes: Sustainability Capacity Development: Capacity development 6. Consideration should be given to institutional sustainability after the project period, including coordination among related agencies and M&E of project benefits. Temporary arrangements for project implementation, such as the PMU and a steering committee, cannot continue their activities once a project closes. The stimulus for successful activities tends to disappear quickly upon project closure. project cycle stage: Completion, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Institutional analysis Project management should be given flexibility in modifying staff positions, especially for key technical positions. project cycle stage: Implementation Lesson Topics: Project Management: Project management Capacity Development: Human resources management The capacity of the entity that will be responsible for operation and maintenance of project facilities should be assessed carefully at appraisal. project cycle stage: Lesson Topics: Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity assessment Capacity Development: Institutional analysis The executing agency's firm commitment is essential to promote participation by the private sector in activities that could potentially be undertaken by public sector agencies. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Sector Related Issues: Private sector Sector Related Issues: Public-private partnership The record of fund utilization segregated by project activities is essential information for M&E, and adequate arrangements for financial management should be established early in a project, particularly when multiple implementing agencies are involved. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies The time and resources needed to finalize project accounts should be considered in preparing project implementation arrangements. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financial reporting Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/tea-development-project
Second Perennial Crops Development Project | Sri Lanka |  | 2008-02-05 | 1. The experience of the pilot activity under the Project shows that potential exists in Sri Lanka for a gradual introduction of a fee-levying private extension service among commercial farmers with a better ability to pay, leaving scarce government resources to serve the poor and subsistence level groups of farmers more effectively. Commercial farmers need different kinds of services, including farm planning and budgeting, financial management, and post-harvest operations, in addition to the more traditional advice on production technology. They require need-based extension services with which they could reduce cost of production. Furthermore, user-pay services are accountable, collectively and individually stimulating service providers' performance and commitment related to demand. However, the process of introducing private sector service providers requires a clear policy framework and an effective framework for cooperation between the Government and private sector stakeholders. project cycle stage: Design, Feasibility, Appraisal Lesson Topics: Project Design: Project design Sector Related Issues: Extension service Sector Related Issues: Public-private partnership Policy & Reform: Policy reforms/framework Methodologies/Approaches: Pilot project 2. To be profitable, private sector extension services need to be integrated into other commercial operations, such as sale of farm inputs. A company set up solely to provide extension services may not be viable in the long term. This is seen in the less than optimal scale of operations of the three service contractors. Contractors expressed views that (i) the financial benefits of input sales as setting off any operational losses in providing extension services, and (ii) the establishment of a reliable network of high-quality producers as of sufficient benefit to offset its operational losses in providing advisory services. Without such externalities, the operation may not be attractive. In fact, one of the contractors did not benefit from either input sales or output marketing. project cycle stage: Lesson Topics: Project Design: Project design Sector Related Issues: Extension service 3. An executing agency's firm commitment is essential to promote private sector participation in activities that could potentially be undertaken by public sector agencies, as government tends to be reluctant to take actions that broadly diminish its power and enhances the influence of the private sector. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Ownership Capacity Development: Partnerships Sector Related Issues: Private sector Sector Related Issues: Public-private partnership 4. The plan to use a short-term international consultant for M&E appeared to be inappropriate. When an assignment for consultants in a socioeconomic field is short term, national consultants are more appropriate than international consultants. project cycle stage: Design Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Consultants Capacity Development: Capacity development Capacity Development: Ownership After completion of projects, executing agencies do not have procedures and systems in place to build upon the knowledge gained by implementing the projects. This results in inadequate transfer of project knowledge to government institutions and staff. project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Project Management: Executing/Implementing agencies Capacity Development: Capacity development Government institutions are in general not geared to working with the private sector and therefore have inadequate mechanisms to interface with it. project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity development Capacity Development: Institutional analysis Capacity Development: Partnerships Sector Related Issues: Public-private partnership Introducing new approaches requires public awareness campaigns at a project's outset to obtain stakeholders' support. Public understanding of proposed changes' rationale and expected outcomes can facilitate introducing new interventions. project cycle stage: Lesson Topics: Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach The multiplicity of government ministries and agencies involved in the agricultural sector poses serious challenges for coordination and synergy. project cycle stage: Lesson Topics: Crosscutting Issues/Themes: Public governance Project Management: Project management Capacity Development: Capacity assessment Capacity Development: Institutional analysis The outcome of project interventions was affected by changes in the direction of government policies during project implementation. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Policy & Reform: Policy reforms/framework When procuring goods and services involves multiple agencies, each of them forms its own tender committee. Having several committees for procurement is extremely cumbersome. Despite the Government's having more flexible procurement guidelines for donor-funded projects, the executing agencies do not follow them. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Without specific activities for the most isolated rural areas, project investments remained biased towards suburban, more developed districts. project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Sector Related Issues: Rural development Sector Related Issues: Urban sector/development Methodologies/Approaches: Targeting | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-perennial-crops-development-project
Skills Development Project | Sri Lanka | Education | 2008-01-30 | 1. Adding an additional component to a completed loan design requires thorough analysis to ensure congruence with the project goals, objectives, and methods. If additional input is required, the new requirements should be integrated into existing components in the original project design. project cycle stage: Design Appraisal Lesson Topics: Project Design: Project design Project Design: Subprojects 2. Complex projects involving multiple funding agencies, government agencies, institutions, and stakeholders require additional time at early implementation to establish operational policies and procedures. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Project administration Methodologies/Approaches: Consultation/Participation 3. The sequencing of various implementation activities such as policy reforms, civil works, consultancy deployment, and equipment procurement must be logical and carefully planned to realize maximum investment efficiency and effectiveness. When project implementation relies heavily on policy change, the essential policy adjustments should be completed prior to consultant deployment. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement Project Management: Project administration Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/skills-development-project-1
Country Assistance Program Evaluation for Sri Lanka: Inclusive Development and Conflict Resolution: Major Challenges in the Future (2007) | Sri Lanka |  | 2007-08-31 | 1. Change management calls for an understanding of the reasons for resistance, and ways of overcoming impediments. Moreover, continuing efforts are needed to arrest the decline in the capacity of sector institutions to implement projects, mainly due to problems with recruiting and retaining qualified staff. An improvement in the incentive and reward system isimportant. project cycle stage: Feasibility, Implementation Lesson Topics: Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Human resources management 2. Policy-based lending requires a careful assessment of the reform environment and reform readiness. Country ownership and political will are fundamental. Policy reforms that are built on an apolitical process and a lack of understanding of the country's history are bound to fail. Policymaking is often complicated by elections. Certain calls for economic reforms may not be heeded, particularly during the rise to power of political coalitions that have differing agendas. A balance must be achieved between setting the pace of reforms and ensuring social and political stability. Thus, the vulnerability and sensitivity of policy reform must be understood in program design and implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Policy-based lending Project Design: Project design Project Management: Project management Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform A community-based approach to rural water supply systems can be effective in enhancing customer roles in project planning and implementation and in promoting greater ownership. Least-cost options for planning water supplyand sanitation projects should consider an integrated approach, including supply and demandfactors, to achieve more sustainable resource use. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Market analysis Project Design: Project design Project Management: Project management Capacity Development: Ownership Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Sector Related Issues: Water resource management Methodologies/Approaches: Community approach Methodologies/Approaches: Holistic approach A good understanding of political and legislative processes, including policy and regulatory environments, is a key requisite in project preparation and implementation. Monitoring changes in the macro context influencing a key sector is necessary, particularly the incentive environment for private sector participation. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project administration Project Management: Project management Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Assessing the institutional and management capacity of executing agencies is extremely important. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Benchmarking can be an effective tool for improving the operational performance of water supply service providers. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Sector Related Issues: Health and sanitation management Continued stakeholder support for policy reforms is essential to sustain the reform process. project cycle stage: Feasibility, Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Developing a project management and information system should be prioritized for effective project implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Project Management: Management information system Project Management: Project management For vocational training graduates, support services must complement the provision of loans for self employment, and more tracer studies of graduates must be conducted for future planning. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Education Handover of management of water schemes to local authorities and community-based organizations requires continued support during the transition and follow-up periods to enhance the sustainability of such schemes. project cycle stage: Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Sector Related Issues: Water resource management Methodologies/Approaches: Civil Society Participation In distance learning, more awareness programs are necessary to promote readiness for online learning as well as to expedite the participation of nonstate agencies. A revolving fund will enable participants from non-affluent families to acquirecomputers for distance learning. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Executing/Implementing agencies Sector Related Issues: Education Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation In technical education and vocational training, more social marketing programs are necessary to change the negative attitudes of private sector employers, parents, and students toward state-run technical education and vocationaltraining institutions. While education policies have been gender sensitive, concomitant motivation programs to encourage women to enroll in technical training programs are crucial. Across the education subsectors, results-based monitoring andevaluation must be promoted to track achievements over time. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Managing for Development Results Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Human resources management Sector Related Issues: Education Sector Related Issues: Private sector In the context of sector reforms, country ownership and political will for implementing the reformagenda are requisites for which ADB assistance cannot serve as a substitute. Advancing policyand institutional changes requires champions and coherent support from within the country.Policy initiatives can take a long time to materialize, and such initiatives require sustainedsupport. project cycle stage: Feasibility, Implementation Lesson Topics: Capacity Development: Ownership Policy & Reform: Policy reforms/framework Policy & Reform: Reform Investing in awareness campaigns to improve beneficiary participation is vital. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation Power sector restructuring is a dynamic and complex process with enormous challenges. It calls for a deep understanding of the political economy; broad-based ownership of reforms; a comprehensive sector road map that recognizes pressing needs, such as least-cost power generation, other than reforms; and measures to knit reforms into a broader articulation of public interest. Conveying the costs and benefits of the reforms versus alternative measures isimportant. Work is necessary on all fronts, not only in putting in place a legal framework or animproved market structure, but also in building constituencies for reform. Where public andpolitical resistance is likely to hinder reform implementation, provision should be made forincreasing public awareness of the reform agenda and reaching a consensus on the means forachieving objectives. project cycle stage: Design, Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Project design Capacity Development: Ownership Sector Related Issues: Energy planning/management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform The complexity and diversity of a sector should be matched by flexible and robust projectdesigns that can meet evolving needs. project cycle stage: Design, Feasibility Lesson Topics: The rapid divestment of state-owned enterprises tended to sacrifice transparency and due diligence. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Policy & Reform: Privatization Policy & Reform: Public sector reform Without continuing commitment from the government, ensuring cost recovery and financial viability through ADB's loancovenants can be effective to some extent only. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Loan Agreement: Covenants Capacity Development: Ownership | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-sri-lanka-inclusive-development-and-conflict
Water Resources Management Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 2007-01-11 | 1. During project preparation and implementation, there was overemphasis on achieving a product - a new policy and a new organization - but there was little time and insufficient resources to deal with the processes, the sociopolitical issues involved, and the overall institutional implications. The TA studies implemented prior to the Project analyzed the project environment with sufficient accuracy, but could not fully assess the political risks involved in establishing the National Water Resource Authority (NWRA) in place of the Water Resources Secretariat - creating a perceived threat within existing water sector agencies. Therefore, comprehensive analysis is needed on how the end product could be successfully achieved or a more process-oriented methodology could have been initiated during project preparation, including assessments of the risks associated with the establishment of NWRA, and resources required for the implementation of part A of the Project. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 2. Projects designed to support national policy, legislation, and sector reforms - including institutional development - should not be mixed with infrastructure development in selected geographic areas. Such diverse objectives, which require a complex mix of project staff and expertise, should have not been combined in a single project to avoid delays in project implementation. project cycle stage: Design Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform 3. In this Project, an attempt had been made to prepare and obtain approval of a comprehensive National Water Resources Policy that had too many contentious details, such as pricing of water, private sector participation, and regulation of groundwater. Since some political parties, even within the Government, had very different views on these aspects, the proposals reform attracted criticism at the outset. Only key elements of the policy (e.g., enabling the creation of a national agency with a mandate for overseeing water resources management and the key principles according to which water resources will be managed) were needed initially. The remaining policy elements could have been developed once the implementing agency was created and operational. Inclusion, without prior broad consultations, of complex issues - such as water rights, groundwater regulation, and water pricing - in the policy document eventually stalled the process. The policy could have been developed in a gradual manner, enabling wider consultations, to ensure acceptance by all stakeholders. Government leadership is critical in the policy formulation and consultation processes. project cycle stage: Implementation Lesson Topics: Sector Related Issues: Water resource management Policy & Reform: Policy reforms/framework Policy & Reform: Reform 4. Although the Project was designed to involve key stakeholders in a consultative process, the eventual effect was not favorable. The consultation activities have not been effective, as they could not reach grassroots stakeholders or they were not sufficient to present effectively the facts justifying the need for a National Water Resources Policy in Sri Lanka. Policy development and institutional reforms can be effective only when partner organizations and other stakeholders are all equally aware of their responsibilities and benefits. It is also essential that the proposed reform programs are clearly understood and eventually owned by all stakeholders. A strong political will to proceed with such reforms is a product of public confidence and the common acceptance of the proposed reforms. Adequate mechanisms are needed to produce that level of public awareness, confidence, and acceptance - initially by absorbing views of diverse interest groups and analyzing them in terms of program objectives, and finally adjusting the design of the programs to suit the majority views. project cycle stage: Design, Implementation Lesson Topics: Sector Related Issues: Water resource management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Unsuccessful | http://www.adb.org/projects/documents/water-resources-management-project
Upper Watershed Management Project | Sri Lanka |  | 2006-11-13 | 1. Project frameworks need to be dynamic, adopt standard procedures, and be constantly reviewed if they are to serve monitoring and evaluation needs. The Report & Recommendation of the President (RRP) framework was weak and was neither used nor updated. Having more than one outcome has also led to confusion during implementation. [Main text, paras. 9, 66(i)] project cycle stage: Feasibility Lesson Topics: 2. All land users should have been involved, as required by a holistic approach to watershed management. Tea estates were excluded despite their contribution to soil erosion. [Main text, paras. 9, 66(ii)] project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach 3. Translating policy into practice takes longer than the duration of a project. The National Watershed Management Policy (NWMP) has yet to be internalized within the government. Proposals to establish provincial watershed management units (WMUs) to continue the project approach, although welcomed at the local level, failed to materialize for lack of an overall institutional support agency. [Main text, paras. 50, 66(iii)] project cycle stage: Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Capacity Development: Capacity development Sector Related Issues: Water resource management Policy & Reform: Policy reforms/framework 4. A high degree of local community participation and contribution can lead to greater project efficiency. This was achieved in the Upper Watershed Management Project through the use of social mobilizers (SMs). The project management office directly engaged SMs as the interface between communities and implementing agencies. Community involvement in planning, implementing, managing, and maintaining field activities created greater transparency and ownership. This led to greater efficiency in procuring materials, construction, and ensuring plantation quality. [Main text, paras. 53, 66 (iv); Appendix 6, paras. 39-44] project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Project Management: Project management Sector Related Issues: Rural development Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach 5. Given the major task of establishing coordination among many implementing agencies, devolved and not, an initial 12-month planning and preparation period should have been included. Pressure to commence field activities and meet targets adversely affected start-up operations and training. [Main text, paras. 26, 66(v)] project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Targeting 6. To facilitate assessment of effectiveness, systems to monitor and evaluate project benefits should be built into the implementing agencies' (IAs) systems. In this project, a computer-based system was designed but not applied nor adopted by the IAs. There was no midterm socioeconomic assessment undertaken. The project management office relied on less formal means of monitoring and depended on consultants for final evaluations. [Main text, paras. 45, 66(vi)] project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management 7. Sustainability of project benefits could have been increased by focusing on existing community based organizations (CBOs), registering new ones with the divisional secretariat, and giving CBOs full responsibility for use of their funds. The subsidy-dependent syndrome that remains engrained among beneficiaries will need to be reversed to self-reliance if participatory approaches are to become truly self-sustaining. [Main text, paras. 55, 66(iv)] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Methodologies/Approaches: Community approach Methodologies/Approaches: Participatory approach Management through a Project Management Office (PMO) engendered departmental independence and facilitated coordination of multiple implementing agencies (IAs), but the stimulus ceased on closure. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Project Management: Project management Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/upper-watershed-management-project
Private Sector Development Program Loan | Sri Lanka |  | 2006-06-15 | 1. Some measures, such as voluntary retirement schemes (VRS) for the involuntary termination of workers for state-owned enterprises (SOEs) that are to be divested, have significant budgetary implications. When including such measures in the policy matrix, it is important to ensure that the fiscal situation can support such measures and the necessary budget allocations are made. project cycle stage: Design Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Capacity Development: Human resources management Policy & Reform: Policy matrix Policy & Reform: Privatization Policy & Reform: Public sector reform In order to provide adequate flexibility, a program cluster should be designed as a set of single tranche subprograms, with each subprogram comprising clearly defined policy actions that are calibrated to be achievable within a relatively short time frame. project cycle stage: Appraisal Lesson Topics: Modality: Cluster operations Modality: Program Project Design: Project design Policy & Reform: Policy reforms/framework Proceeds received from the sale of state-owned enterprises (SOEs) are dependent on the economic environment and market conditions. A predetermined mandatory program for privatizations - with a quantified net asset value within a specified period to meet tranche release conditions - may not always optimize proceeds. Instead, it could result in underpricing of shares as demonstrated in the sale of Sri Lanka Telecom Ltd. and Sri Lanka Insurance Corporation Ltd., both of which were sold in order to meet tranche release conditions when the stock markets were plummeting worldwide and the Sri Lanka market was at a relatively low level. In addition, the regulatory authority must be operational to properly regulate the industry (i.e., Insurance Board of Sri Lanka) before a privatization takes place. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Market analysis Modality: Program Policy & Reform: Privatization Policy & Reform: Public sector reform Under the program cluster approach, other multilateral institutions may finance programs originally proposed to be included in future subprograms of the cluster loan. The Private Sector Development Program's (PSDP's) subprogram 1 and proposed follow-on (subprogram 2) were put in place before the World Bank's Poverty Reduction Strategy Credit was developed. The World Bank program overlaps some of the focus areas of PSDP's subprogram 2. Organizational restructuring within ADB also shifted responsibility for many of the components that were originally envisioned to be included in subprogram 2 to other departments, which are implementing them. Although the PSDP was structured as a cluster, only 1 of the 15 areas considered in the preparatory work for subprogram 2 were actually included in subprogram 2. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Cluster operations Modality: Program Sector Related Issues: Private sector | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/private-sector-development-program-loan-0
Science and Technology Personnel Development Project | Sri Lanka |  | 2006-06-15 | 1. The project was highly ambitious and complex, involving 16 semi-autonomous institutions, 4 different ministries; and activities that would take time to complete before they would have an impact. Therefore, the implementation period of 5 years was unrealistic. There was little room for flexibility in project implementation; with a longer-term view, and more of ï¿½processï¿½ approach, the project could have started at a smaller scale and gradually expanded as experience was gained and lessons were learned. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education Methodologies/Approaches: Process approach 2. One problem that will remain in terms of upgrading the qualification of academic staff is that some staff who go abroad for postgraduate studies, for example to the US or Australia, may not return, since they can there earn in a month what they would earn in a year at a university in Sri Lanka. Since Sri Lanka will need to continue to send science and technology and R&D staff abroad for higher science and technology qualifications, an option may be to send them to universities in the region in the first instance, and only to send them outside if the region cannot provide the required degree,. project cycle stage: Feasibility Lesson Topics: Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Education 3. Underutilization of facilities has been and continues to be a problem in ADB-supported projects. Future projects need to assess carefully the needs and plans for such investments. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design 4. Gender aspects need more attention and action needs to be taken to increase female enrollment in undergraduate science and technology courses traditionally dominated by men. The obstacles women face undertaking graduate and postgraduate studies need to be analyzed. Support for gender studies, workshops for faculty at institutes, career guidance for women, and opportunities to meet successful female role models should be considered. In the case of the project, provision of a higher number of scholarship awards to females for postgraduate studies was the only input to promote gender equity. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Gender Project Design: Project design Sector Related Issues: Education 5. Setting up a comprehensive scheme of accreditation, with continuous monitoring and periodic evaluation to maintain standards, is a long process, but a very important one if the required standards in response to global trends are to be maintained. In the case of the project, program quality at the 10 universities varies. The project provided inputs for accreditation of courses. Only a few courses received foreign accreditation, and no attempts were made to establish a local professional body for accreditation. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/science-and-technology-personnel-development-project
North Central Province Rural Development Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 2006-05-15 | 1. Integrated Rural Development Projects (IRDPs), by nature, are multisectoral undertakings. Limited project preparation resources are therefore spread more thinly as the complexity of the design grows. It is therefore better to focus project activities on a core program, rather than trying to cover a wide array of potential activities. Extra care should be taken when including relatively new arrangements for line agencies, such as the devolution of powers to the Provincial Irrigation Departments (PIDs) and the Provincial Road Development Authorities (PRDAs). A period for building capacity through technical assistance may be required before the project, or, alternatively, special provisions may need to be made to ensure long-term institutional capacity building during the project. IRDPs require careful planning and coordination among all project partners. project cycle stage: Design, Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Irrigation management Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation 2. Projects that aim to expand emerging enterprises or help the establishment of new enterprises should provide more than credit. There is a need to support managerial, planning, record keeping, and marketing skills. Capacity building by qualified service providers (e.g., NGOs) or microfinance institutions is desirable. Proper targeting of beneficiaries at the design phase will help to determine the right microfinance option and to target poor beneficiaries who are often risk averse and cannot obtain credit from participating credit institutions (PCIs). The microcredit component of this integrated rural development project had very little impact on the poor (i.e., it has failed to target the poor, instead it has successfully encouraged entrepreneurship through training and/or credit provision among already established enterprises). [Main text, paras. 14-16, 62] project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Industry and Trade Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Targeting 3. The overall project objective was to reduce poverty in the province. The poorest of the poor might have benefited if the following approaches had been adopted: (i) the provision of microcredit and skill and employment training (rather than only the enterprise development approach that was finally adopted for the credit program); (ii) creative financing schemes to facilitate access to drinking water and rural electrification under the Village Advancement Program or VAP (e.g., through links to NGOs or microfinance institutions as is already being done elsewhere in Sri Lanka); and (iii) greater use of qualified NGOs that have the capacity to target and work with the poorest of the poor. This need not have required an overhaul of the Project Design, but could have been achieved with only minor enhancements. [Main text, para. 63] project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity building Crosscutting Issues/Themes: Employment Sector Related Issues: Health and sanitation management Sector Related Issues: Rural development Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Targeting 4. Better implementation planning would have ensured better phasing of project activities: (i) establishing the PMO office (staff, facilities, equipment, consultants); (ii) creating and integrating line agency capacities; (iii) a controlled pilot phase to introduce and learn from initial project works; and (iv) a scaling up of activities after a careful assessment of lessons learned from the initial pilot phase. BME is a critical part of planning and implementation, and should be established within the first year of the project. In the case of this integrated rural development project, poor planning has resulted to lack of cost control, poor quality work, and lack of program integration, among others. [Main text, paras. 26, 64] project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Management: Project management Methodologies/Approaches: Pilot project 5. To foster greater ownership by local government, participation of local leaders and line agencies should be sought (i) in project preparation, and (ii) through routine and periodic planning throughout project implementation. The project did not achieve much transference to the provincial government or line agencies. It achieved little integration and significantly lacked involvement in and ownership of the project by the provincial government which threatens the likelihood of the project's sustainability. [Main text, paras. 52, 56, 60, 66] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Ownership Country Context: Decentralization Methodologies/Approaches: Consultation/Participation 6. Strengthening operation and maintenance (O&M) and looking into innovative mechanisms for participatory O&M should be a priority to ensure likelihood of project sustainability. Realistic post-project strategies, plans and budgets should be incorporated into the project for each sector. Serious attention to O&M issues at the design stage, and, where appropriate, a phased project implementation approach, with clear beneficiary understanding and formal commitment of the requirements for O&M is needed. If local government resources are limited, projects that require intensive O&M need particular attention in the country strategy and program and during the project design stage. One of the shortcomings in the project preparation of the integrated rural development project is the failure to incorporate enhancing O&M capabilities as a major component seriously reducing its relevance and likelihood of sustainability. [Main text, paras. 36, 60, 67] project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Cluster operations Project Design: Project design Project Management: Operation and maintenance Country Context: Decentralization Country Context: Prioritization Methodologies/Approaches: Participatory approach A participatory approach is critical throughout implementation of rural development projects and must be a high-profile activity. project cycle stage: Implementation Lesson Topics: Sector Related Issues: Rural development Methodologies/Approaches: Participatory approach Technical and resource limitations should be documented when institutions are assessed in project preparation and programs prepared to overcome these. If the limitations cannot be addressed in project preparation, the components should be dropped, and the remaining implementation arrangements simplified. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Institutional analysis | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/north-central-province-rural-development-project
Southern Provincial Roads Improvement Project | Sri Lanka | Transport | 2005-09-15 | Any reassessment of a project is problematic where only limited field investigation has been carried out. A BME database management system must be set up for each project, right at the start of implementation. Using well-established scientific principles and techniques of experimental design would put BME for provincial roads on a more solid footing. Areas for improvement in future projects were identified, including: patchiness in both data collection and information safekeeping for BME since the time of appraisal; BME has often to be restrained and based upon a relatively small sample of road sections which needs to strike a balance between social and other demographic features; BME requires statistical coherence in the material collected and consolidated during the course of the project and in the years beyond; and road condition surveys should be geared towards the provision of consistent network-wide estimates of international roughness index (IRI), in particular, on all roads surveyed. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Design: Appraisal Project Management: Management information system Sector Related Issues: Roading Better consultation, coordination, and cooperation between public authorities would help reduce the incidence of problems related to relocation of utility services along roadways. The public service authorities were generally too slow to act on requests to relocate infrastructure that obstructed the project's road rehabilitation work although funds for such relocation were available through the project. When preparing projects in the future, other arrangements should be earnestly sought to ensure the timely relocation of such service infrastructure. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation Similar road projects in the future might more usefully be designed around local network effects than road classification. Existing and potential public transport routes, irrespective of the class of road used, might be a more appropriate starting point for design rather than a collection of dispersed short road segments, selected only because they fall within the purview of a single government authority. For the project, it was realized during appraisal that one of the risks was connected with the possible failure of the government to fully implement its plans to develop and maintain the primary road network serving the project area (Southern Province). Even now, after the project, some project roads are functionally connected to major class-B roads that are still in an indifferent state of repair. Where evident, this situation has tended to blunt the efficacy of the project. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Roading Sustainable road maintenance requires a continuing focus on the potential benefits available from effective and consistent budget allocation and expenditure. Funds must be allocated by the government to maintain infrastructure properly, and maintenance must be efficiently executed to obtain maximum benefit. Both of these requirements must be met as either one without the other will result in a deterioration of services. The project has contributed effectively towards ensuring that the latter requirement is met to the fullest extent, but the imbalance so far evidenced in the accomplishment of these two requirements, and the deleterious effects of this imbalance, should continue to be of major concern as a potential risk when preparing similar projects in the future. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Operation and maintenance Project Management: Risks/Risk management Sector Related Issues: Roading There are assured benefits to be gained by shortening as much as possible the response time between project preparation and implementation. Additional design and maintenance costs could be avoided, and economic performance and efficiency would improve. Borrowers and ADB together must ensure that the overall process is speeded up to the fullest extent possible. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Operation and maintenance | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/southern-provincial-roads-improvement-project
Plantation Reform Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 2004-12-15 | Labor should be considered an investment, rather than a cost, and human capital and social development should be integral parts of regional plantation companies' (RPCs') corporate development strategies if the plantation sector is to be profitable. To be successful, social development programs should have a strong commitment at the management level and shouldbe driven by stakeholder demand. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Market analysis Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Industry and Trade Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Project experience underscores the commitment and political will required to implement policy reforms, such as privatization and market liberalization. This was the underlying factor in the privatization of 20 regional plantation companies (RPCs) during the project period's first half. The commitment and political will, however, did not last. When the privatization procedures were changed, the controlling interests in three of the 20 RPCs were bought by government entities. ADB did not consider the three RPCs privatized, and they were therefore not eligible for project funding. The three RPCs were eventually privatized, being sold to private entities. At project completion, another three RPCs were not yet privatized. Also, Janatha Estates Development Board (JEDB) and Sri Lanka State Plantation Corporation (SLSPC) estates and warehouses were not restructured and privatized. With continued political intervention on wages and the restrictions on marketing, an enabling environment was not created for the RPCs to improve their profitability, and, hence, achieve the full potential for long-term sustainability. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Capacity Development: Ownership Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Reform Success in privatization required a private sector willing and able to finance the acquisition of regional plantation companies (RPCs). Sri Lanka's financial system is well able to provide short-term funding for working capital purposes, but the limited development of sources of long-term loan funds would have prevented investors from using any gearing to achieve an acceptable cost of funds, forcing them to rely on equity alone. In the absence of Part A's long-term credit, there would have been no such funds available, and the pace and success of privatization would have been constrained. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Privatization The project's good performance was facilitated by the flexibility allowed in the non-credit component. This enabled the project to develop activities such as the tea sector strategy study and other programs to meet the industry's evolving needs. For example, the project provided regional plantation companies (RPCs) with training equipment, although this was not envisaged during appraisal. The training equipment provided was well used and served as an incentive for the expansion of field-level training. project cycle stage: Implementation Lesson Topics: Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/plantation-reform-project
Third Road Improvement Project | Sri Lanka |  | 2004-10-15 | Significant implementation delays were caused by the complex procurement procedures of the government. Improvements in government procurement procedures and the delegation of more authority to executing agencies need to be made. The lack of institutional capacity in the executing agency (Road Development Authority) for preconstruction processes, including land acquisition and relocation of utilities, also led to delays. Even though advance action wasapproved in December 1993, this action did not alleviate delays. As in previous projects, inadequate project maintenance was noted by the PCR Mission for the existing project roads. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Procurement Capacity Development: Capacity assessment Capacity Development: Capacity building Country Context: Decentralization Sector Related Issues: Roading The government has difficulty complying with covenants related to broader budget allocation for road maintenance. The inconsistent management of the executing agency (Road Development Authority) is a serious problem and inhibits decision making. Due to these factors, ADB should focus on strengthening RDA and its project implementation capability. Although the project tried to develop the lack of capacity and inexperience of the domestic private sector in road construction and engineering and related services, considerable work still needs to be done. The broader lack of maintenance issues for the sector needs to be addressed through a reform program to improve the planning, execution, and financing of road maintenance. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Program Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity building Sector Related Issues: Private sector Sector Related Issues: Roading Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-road-improvement-project
Second Power System Expansion (Sector) Project | Sri Lanka | Energy | 2004-09-15 | Implementation delays due mostly to the government's complex procurement procedures became a major concern to ADB. Procurement procedures need to be improved, and more authority should be delegated to the executing agencies. Similarly, to avoid public opposition to future projects, and the resulting delays in project implementation, involuntary resettlement should be addressed, and the affected people should be consulted, as early as possible. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Management: Executing/Implementing agencies Project Management: Procurement Methodologies/Approaches: Consultation/Participation The executing agency (Ceylon Electricity Board or CEB) should be given greater autonomy, and electricity tariffs should be set based on commercial, not political, grounds. Ideally, an independent regulatory body should set tariffs. If this cannot be achieved, tariffs should be raised according to a predetermined schedule. project cycle stage: Design Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Management: Executing/Implementing agencies Sector Related Issues: Energy planning/management Policy & Reform: Public sector reform The executing agency's (Ceylon Electricity Board's) compliance with loan covenants was not satisfactory, particularly in achieving an 8% rate of return. Based on CEB's performance, achieving this rate of return will be difficult.Loan covenants on rates of return should be set realistically in view of past performance. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Loan Agreement: Covenants Project Management: Executing/Implementing agencies | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-power-system-expansion-sector-project
Southern Province Rural Development Project | Sri Lanka | Multisector | 2004-03-15 | If an environmental assessment study was done for at least one saltwater exclusion and drainage (SWED) scheme during project preparation, the SWED implementation could have been launched earlier. This project highlights the importance of preparing a technically rigorous environmental assessment early in the business process. That would allow (i) the integration of safeguards into subProject Design, (ii) the appropriation of funds, and (iii) the provision of adequate institutional support as needed. ADB's suspension of SWED works until the Central Environmental Authority (CEA) approved the technical studies demonstrates the importance of monitoring safeguard compliance during project implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Capacity Development: Capacity building Sector Related Issues: Irrigation management In terms of closure and continuity, the project and other Integrated Rural Development Projects (IRDPs) typically employ an independent project management unit to coordinate activities and budgets during implementation. Upon completion, officers and staff frequently transfer and the project civil works are delegated - often to line agencies with inadequate O&M programs and budgets. The sense of continuity, commitment, and follow-through of the IRDP are generally casualties. project cycle stage: Completion Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Management information system Project Management: Operation and maintenance Project Management: Project management Capacity Development: Human resources management Capacity Development: Ownership Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach The Project Benefit Monitoring and Evaluation (PBME) studies were partially satisfactory. The shortcomings were not necessarily in the execution of the PBME surveys by consultants. They were due partly to (i) inadequate ADB communication of its information and evaluation needs, and (ii) a lack of guidance to the local consultants conducting the surveys. To this end, more ADB contribution and guidance to these surveys is advisable if they are to provide useful input into ADB evaluations later. project cycle stage: Feasibility, Appraisal Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Post-evaluation Project Management: Consultants Project Management: Project supervision The project has not overcome the fact that lowland agriculture in the province generally is practiced on a subsistence basis, involving uneconomic-sized farms, land tenure and labor constraints, limited access to technology and inputs, and low levels of technical know-how. The project basically focused on upgrading infrastructure facilities. A more comprehensive approach to agriculture would include improving (i) farm practice and input use, (ii) input availability and product marketing, and (iii) crop diversification. This implies a higher profile for agricultural extension, farming systems, agribusiness and marketing, and policy assessment - areas less easily addressed in an integrated rural development approach. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Extension service Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework Methodologies/Approaches: Holistic approach The project's management demonstrated an ability to achieve substantial disbursements and physical outputs for the province. However, the numerous sectors, activities, and implementing agencies were spread over a large geographic area. As such, the project did not achieve the focus and synergy that might be expected for an Integrated Rural Development Project (IRDP). This geographic spread stretched project management and limited the ability to focus on strategic issues, such as capacity building in implementing agencies, strengthening O&M, and ensuring sustainability. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Disbursement Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Project Management: Project management Capacity Development: Capacity building Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach The requirement of 10% farmer contribution to irrigation works was an obstacle to implementation. While this rate might be workable in high-performance systems, the appropriateness must be carefully considered when applied to subsistence agriculture. An alternative proposal for the future was half pay or food for labor. Under that proposal, poor farmers would have something to bring home at the end of the day, while simultaneously contributing to the irrigation works. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Crosscutting Issues/Themes: Employment Sector Related Issues: Irrigation management Sector Related Issues: Rural development While the project and other Integrated Rural Development Projects (IRDPs) have achieved some increases in rural income and employment, they generally have not resulted in a self-sustaining process of income growth to break the cycle of rural poverty. The projects typically have not provided rural inhabitants with the alternative skills, resources, and employment avenues required to move to higher levels of productivity. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Sustainability Crosscutting Issues/Themes: Employment Sector Related Issues: Rural development Methodologies/Approaches: Holistic approach | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/southern-province-rural-development-project
Fisheries Sector Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 2003-11-14 | One reason for the delay in implementing harbor and anchorage subprojects wasthe appointment of a single local consulting firm to conduct the coastalengineering studies. During project preparation and at appraisal, localcapacity should be realistically assessed before fixing the procurement mode(which, in this case, was local competitive bidding). Alternatively, recognizing thelimitations in local capacity, implementation schedules should be more realistic. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Consultants Project Management: Procurement Capacity Development: Capacity assessment Sector Related Issues: Rural development Some facilities built through the social infrastructure subproject are notmaintained well, because funding is inadequate. To ensure the sustainability ofsuch assets, beneficiary consultation should include (a) providing awareness tothe beneficiaries of the need for periodic maintenance, and (b) obtaining the user community's commitment to the funding of operating and maintenance (O&M)costs. Selection and design of such facilities should be within the communities'capacities. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Project Management: Operation and maintenance Capacity Development: Capacity assessment Capacity Development: Ownership Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Consultation/Participation The benefit monitoring and evaluation (BME) interim evaluation noted that the Panadura site was not suitable technically, and that political considerations played a major role in the site selection. Although subproject selection is demand-driven, technical and financial or economic viability should be the overriding consideration in investment decisions. In addition, anadequate analysis should be made of risks and the robustness of assumptions. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project Design: Subprojects Project Management: Risks/Risk management The financial management consultants were appointed almost 38months into the project. The systems that the consultants recommended werenot implemented properly. Project data were not readily available. Data retrieval took time and effort, and was often incomplete. Project information systems should be set up within 6 months of implementation for efficient recording anddissemination of basic information. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Monitoring & Evaluation: Data collection and management Project Management: Consultants Project Management: Management information system Policy & Reform: Information dissemination/Public awareness | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/fisheries-sector-project-0
Fourth Development Finance Loan Project | Sri Lanka |  | 2002-10-15 | Project finance-oriented eligibility criteria such as financial internal rate of return (FIRR) and economic internal rate of return (EIRR) were not appropriate for lease applicants (mainly small and medium-sized enterprises or SMEs). A simpler return measure should be used. Owing to the revolving nature of short-term advances, overdrafts, and deposits, private domestic commercial banks (PDCBs) found the cash collection and debt service coverage ratios difficult to calculate. They should only be made applicable for term loan portfolios and term deposits and borrowings. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Sector Related Issues: Industry and Trade Protected industries should not be eligible for financing under future ADB credit lines to avoid, for example, nonperforming subloans and leases in textile manufacturing under the Fourth Development Finance Loan (DFL IV). Had appropriate economic pricing been applied in economic internal rate of return (EIRR) calculation, heavily protected subprojects would have been screened out. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Project design Project Design: Subprojects Sector Related Issues: Industry and Trade The participating financial institutions (PFIs) should be required to maintain a computerized system for subproject benefitmonitoring and evaluation, which would facilitate quarterly reporting to ADB and preparation by the PFIs of their own completion reports, required under the Fourth Development Finance Loan Project. Otherwise, data on subprojectswould be difficult to retrieve, especially on those funded by leases, which, being generally 3-4 years, became inactive sooner than term subloans. After certain leases were fully paid, no active files on them were maintained and the old files could not be located easily. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Design: Subprojects Project Management: Management information system The Third Development Finance Loan Project (DFL III) PCR was completed almost 3 years after the Fourth Development Finance Loan (DFL IV) was approved, which prevented ADB from reflecting on the lessons of DFL III during formulation of DFL IV. It could have given more attention and resources to setting up a monitoring system to track the progress of policy reforms and to obtain subproject and participating financial institution (PFI) data required by ADB. Budgetary or technical assistance (TA) resources could have been allocated to sustain training of PFI staff in using the subproject benefit monitoring and evaluation worksheet model and system review, and to refine the model to enhance its usefulness. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Design: Subprojects Capacity Development: Capacity building Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/fourth-development-finance-loan-project
North Western Province Water Resources Development Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development, Transport, Multisector | 2002-10-15 | A high level of efficiency, efficacy, and acceptance of credit lines can be achieved through client focus and specificity of the credit arrangements. However, this requires credit arrangements both to be worked out in sufficient detail with stakeholders and to be tested. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Pilot project Maintenance issues should have been more carefully analyzed during project formulation, as these were the reason for the rehabilitation. More attention should have been given to maintenance issues during the early stages of project implementation so that innovative arrangements could have been tested and proven to ensure their acceptability and sustainability. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Project Management: Operation and maintenance Methodologies/Approaches: Pilot project Success factors and risks need to be comprehensively analyzed. The project objective of crop diversification was not achieved on the intended scale. Provision of water, extension services, and roads was insufficient to achieve crop diversification under the conditions of gravity irrigation systems found in the project area. Other factors of technical andsocial complexities of water management under tank irrigation systems, traditions, and risks must also be addressed. As farmer organizations (FOs) or farmer groups must jointly decide on crop changes involving water management, group-based approaches to training and extension using FOs as facilitators would likely have been more effective. A methodology was lacking to properly identify and prioritize problems and constraints associated with the intended crop diversification. Theanalytical process of project framework preparation, in use at ADB at the time of project completion and including situation, problem, objectives, and stakeholder analysis, would have been useful. Project experience indicates that, in addition, the comprehensiveness of the analysis including the analysis of the importance and sensitivity of success factors can be ofparticular import,i.e., the relevance of key success factors and the likely importance and efficacy of each to achieve targets must be viewed together. During implementation, performance of these factors should be monitored. If required progress is not achieved, timely design changes should be made. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Risks/Risk management Capacity Development: Capacity building Country Context: Prioritization Sector Related Issues: Extension service Sector Related Issues: Irrigation management Sector Related Issues: Roading Sector Related Issues: Rural development The design of the institutional development component should have been based on a more thorough diagnostic study of performance gaps, which should have included an analysis of the potential role that private service providers could have played. Investments should have been based on strategic institutional development plans and limited to sustained needs. Similarly, the project's substantial training efforts could have been more effective if they had been based on a morethorough needs assessment and strategic training planning process. Earlier provision of the project's required temporary services from the private sector could have been more efficient. The technical assistance (TA) could have been more relevant and effective if its objectives and scope had been aligned with those of the project. The TA's supervision could have been more effective as well. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Capacity development Sector Related Issues: Private sector | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/north-western-province-water-resources-development-project
Selected Advisory Technical Assistance to Social Sectors | Sri Lanka | Health And Social Protection | 2001-10-31 | A TA has maximum development impact when the government (i) feels a strong need for the TA, (ii) is very clear about the desired outputs, and (iii) provides leadership during design and implementation. These conditions result in the government having a strong incentive to use the TA outputs and implement itsrecommendations. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Impact evaluation Project Management: Executing/Implementing agencies Capacity Development: Ownership Arrangements for know-how transfer should become a standard design requirement for advisory TAs to ensure that government officials will have the capacity to use the TA outputs and reduce their reliance on consultants in the long run. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants Capacity Development: Capacity building Capacity Development: Technology/Technology transfer Given limited resources and time, a focused TA has several advantages over one with broad coverage, providing clear insights into the key factors underlying issues identified, detailed measures for ready implementation of its recommendations, and testing of selected recommendations when appropriate. The testing, if successful, may generate strong interest within the government in favor of the TA recommendations and, therefore, enhance its sustainability. project cycle stage: Design, Feasibility Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Project Management: Executing/Implementing agencies Methodologies/Approaches: Pilot project Sufficient time and budget need to be allocated for the later stages of TA implementation to allow consultants not only to produce reports but also to conduct in-depth discussions with government officials on the policyimplications of their findings, develop follow-up actions, and guide the actual implementation oftheir recommendations when appropriate. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Management: Consultants To maximize a TA's impact on policy reforms, it is necessary to select an Executing Agency that not only has the ability to facilitate the required TA activities, but also the authority to implement the TA recommendations. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Policy & Reform: Policy reforms/framework Utilization of TA outputs should receive full attention in a TA design; whenever possible and appropriate, explicit arrangements for the dissemination of TA outputs to the general public and academic institutes should become a standard design requirement for advisory TAs. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Policy & Reform: Information dissemination/Public awareness | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/selected-advisory-technical-assistance-social-sectors
Kirindi Oya Irrigation and Settlement Project | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 2000-12-31 | ADB has a special responsibility in approving projects. It should ensure that the optimal investment option has been selected. It must be transparent in explaining why major changes are made at appraisal relative to feasibility study analysis and when major assumptions are revised in subsequent economic evaluations. Substantial changes should not be made to costs or benefits unless supported by rigorous analysis. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design ADB must be able to challenge underlying assumptions and require that the proposed design reflects circumstances found in the target area. It should not be hurried into making politically driven decisions. project cycle stage: Design Lesson Topics: Getting the design correct from the beginning, including institutional aspects, is a necessary condition for project success. This is particularly true because neither ADB nor a government has a specific capacity to withdraw from a project if its design proves to be flawed. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Capacity Development: Capacity development Good record keeping is essential for management as well as facilitating the understanding of past developments. In particular, all details of economic evaluation should be electronically stored for greater accountability and future reference. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Project Design: Project design Project Management: Management information system Particularly for schemes that are planned to utilize a significant proportion of total catchment water discharge, detailed analysis of catchment hydrology is essential, both at the time of design and thereafter at regular intervals. Improved stream gauging and rainfall recording may be required to support such analysis. Irrigation development must take a conservative view of future river flows, and recognize that water demand for all purposes is likely to increase over time. Schemes that use a high proportion of predicted seasonal or annual flow are inherently risky and should usually be avoided. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Settlement schemes can be highly charged politically. Major efforts are warranted to ensure that settlers move to their allotments to promote both social development and user management of irrigation and agricultural development. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Rural development Where irrigation schemes include areas of existing irrigation, it is important to clarify existing formal and informal water rights, and to ensure that water allocation between new and existing users is equitable. The needs of existing livestock owners must also be taken into account. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management | Project/Program Performance Evaluation Report (PPER) |  | http://www.adb.org/documents/kirindi-oya-irrigation-and-settlement-project
Second Road Improvement Project (Loan 864-SRI[SF]) | Sri Lanka | Transport | 2000-06-30 | ADB should respond quickly to resolve tendering problems so as to avoid situations such as the expiry of validity periods, which happened under the project. Where the tender rules directly and clearly address the problem, there should not be any delay on the part of ADB. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project administration Both the government and ADB should ensure that monitoring systems are established and data collected as expected at appraisal. project cycle stage: Appraisal Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal The experience of both the project and ADB s previous Trunk Roads Project highlights the difficulties in establishing quarries. Such difficulties may unnecessarily delay projects or cause contractors to submit higher tender prices because of the uncertainty raised. The problem of quarry establishment has been recognized, however, and the government now attempts to identify appropriate quarry sites and seek clearances prior to the opening of tenders. project cycle stage: Feasibility Lesson Topics: Project Management: Procurement Sector Related Issues: Roading The government recently acknowledged that it is inappropriate to rely upon its own Road Construction and Development Corporation (RCDC) to undertake all road maintenance works. Such an arrangement constrains road maintenance to the capacity of RCDC, which has recently reached its limit. Alternative arrangements that include force account operations by Road Development Authority and use of private contractors are now being used. The latter conforms to the original intent of the project. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Public governance Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Private sector Sector Related Issues: Roading The lack of success in the project s capacity-building efforts highlights two lessons. The first is that the design of capacity-building interventions should be based on real needs as defined by diagnostic studies. Such a review of the needs of the private road maintenance contracting industry would reveal the importance of continuity of work and access to working finance. Secondly, appropriate policies are required to support project capacity-building initiatives. When the government changed its policy concerning the implementation of road maintenance works, an important part of the project could no longer be achieved. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Private sector Sector Related Issues: Roading Policy & Reform: Policy reforms/framework The project suffered from a lack of realism in its formulation. Institutional capacities, the time needed for tendering and contract award, and postproject maintenance were substantially overestimated, whereas local currency price contingencies were grossly underestimated. While efforts have been made to improve the contract tendering and award process, such as through ADB-financed TA, projects will still need to consider the institutional constraints and high probability of inadequate postproject maintenance. The latter is of particular importance, and until maintenance planning, decision making, and funding are improved, both the design of roads and their evaluation should be done on the basis that maintenance will be inadequate. Local currency cost increases have historically exceeded those used in project appraisal, and more realistic estimates of price contingencies are also warranted. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Local currency Modality: Technical Assistance Project Design: Appraisal Project Design: Project design Project Management: Operation and maintenance Project Management: Procurement Capacity Development: Institutional analysis Sector Related Issues: Roading When preparing detailed designs for roads, greater consideration should be given to (i) hard surfacing road shoulders to save future maintenance expenditure rather than just graveling shoulders as done under the project; (ii) constructing bridges and culverts to the full width of the roadway, including shoulders; and (iii) providing road safety during construction. project cycle stage: Design Lesson Topics: Project Design: Project design Project Management: Operation and maintenance Sector Related Issues: Roading | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/second-road-improvement-project-loan-864-srisf
Second Water Supply and Sanitation Project | Sri Lanka | Water and Other Urban Infrastructure and Services, Multisector | 2000-01-08 | 1. To some extent, project facilities were expanded and repaired at the same time, adding significant benefits to the Project. In the interests of economy and efficiency, the Project should have been designed to cover less towns and to meet at least 10 years of demand so that expansion and rehabilitation works could have been further integrated. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 2. To avoid conflicts with other water users and to secure the water source, the availability of water should have been carefully examined, and its projected use coordinated with other users at the design stage. project cycle stage: Design Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 3. Inaccuracies in cost estimates for rehabilitation works contributed to the cost increase. Higher contingency funds should have been provided for such works. project cycle stage: Design Lesson Topics: 4. Unaccounted for water (UFW) could not be reduced on a sustainable basis only by repairing infrastructure. Institutional, managerial, and social measures were required in tandem with the rehabilitation works. As an institutional measure, a permanent operations unit was established in National Water Supply and Drainage Board (NWSDB) to carry out the program of reducing UFW in Greater Colombo and will continue the program even after the Project. The caretaker approach was adopted as a managerial measure. Standpost societies were mobilized to enhance ownership as a social measure, and metering and maintenance facilities were improved. project cycle stage: Implementation Lesson Topics: Capacity Development: Ownership Sector Related Issues: Water resource management 5. Tariff increases were effective in decreasing the water demand of high consumption households, but not enough to substantially reduce overall water demand. Other measures, such as public awareness, should be undertaken in parallel to control water demand. project cycle stage: Implementation, Operation Lesson Topics: Sector Related Issues: Water resource management Policy & Reform: Information dissemination/Public awareness 6. Before handing over the water supply distribution systems to local authorities, the Government and National Water Supply and Drainage Board (NWSDB) should allocate enough funds and staff to support local authorities in training staff and building capacity. project cycle stage: Operation Lesson Topics: Capacity Development: Capacity building Sector Related Issues: Water resource management 7. The involvement of beneficiaries in all aspects of development, implementation, and operation and maintenance can create a sense of ownership and improve the sustainability of the Project. The success of a community-based approach depends on local hydrogeological, socio-cultural, economic, and political conditions, and the capacities of local non-government organizations and community-based organizations. Therefore, a pilot project should be implemented to examine these conditions before introducing a full-scale project. project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Ownership Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation 8. To extend services for the urban poor, connection fee on concessionary terms and low lifeline tariff should be considered. project cycle stage: Operation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-water-supply-and-sanitation-project-0
Walawe Irrigation Improvement Project (Loan 695-SRI[SF]) | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 1999-12-31 | Experience with irrigation system rehabilitation indicates that a different approach to irrigation project formulation, design, implementation, and operation is necessary to avoid (i) costly cycles of repeat rehabilitation soon after completion, (ii) resulting benefit shortfalls, and (iii) lack of overall sustainability. The optimal approach is a gradual and progressive process that focuses on institutional upgrading and participation by all stakeholders. project cycle stage: Design, Feasibility, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Capacity development Sector Related Issues: Irrigation management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach Institutional support for participation at the highest levels in the implementing agency is essential if participation is to be institutionalized at the farm level. In some cases, participatory approaches may be seen as a challenge to traditional implementation methods and a threat to an institution's power base. Effort, therefore, is often needed to build support for participation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Policy & Reform: Reform Methodologies/Approaches: Participatory approach Mechanisms for beneficiary participation in the design of irrigation projects should be carefully planned; tackling participatory approaches on to a project during or after implementation is less effective. The involvement of farmers from the outset of irrigation system rehabilitation is needed to promote understanding of water management issues and general ownership of the irrigation system. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Capacity Development: Ownership Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Participatory approach Participatory approaches are essential if system deterioration is to be prevented or minimized. Under the current fiscal climate it is seldom possible for irrigation authorities to assume full responsibility for system maintenance. project cycle stage: Feasibility Operation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Sector Related Issues: Irrigation management Methodologies/Approaches: Participatory approach Pilot projects can help define the best approaches to develop beneficiary participation. Such approaches must be utilized rapidly or much of the skill and knowledge developed can be dissipated. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Pilot project Resistance to change is often demonstrated by smallholders. It has proved difficult to change long-established and wasteful irrigation practices. project cycle stage: Implementation Lesson Topics: The establishment of sustainable participatory management approaches is time consuming and not well-suited to short-term TA inputs. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Methodologies/Approaches: Participatory approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/walawe-irrigation-improvement-project-loan-695-srisf
Secondary Towns Power Distribution Project II (Loan 870-SRI[SF]) | Sri Lanka | Energy | 1998-10-31 | The Appraisal Report was comprehensive but contained substantive underestimates of rehabilitation requirements for meeting the project's targets, namely, reducing system losses to 10 percent while at the same time meeting load growth for the full economic life of the project. It is noted that prior to approval of the project, the scope of rehabilitation had been reduced as a result of budgetary constraints; however the original loss reduction target had been maintained. Where the achievement of project objectives is a direct function of the level of inputs, the implications of reducing the project scope should be carefully assessed. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Sector Related Issues: Energy planning/management Methodologies/Approaches: Targeting As experienced under the project, a level of resistance and public enquiry not envisaged at appraisal, hindered implementation. With projects of this type, the design should include provisions to promote public awareness of the project benefits. project cycle stage: Design Lesson Topics: Project Design: Appraisal Project Design: Project design Capacity Development: Ownership Policy & Reform: Information dissemination/Public awareness | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/secondary-towns-power-distribution-project-ii-loan-870-srisf
Impact Evaluation of Bank Assistance to the Industrial Crops and Agro-Industry Sector in Sri Lanka | Sri Lanka |  | 1996-07-31 | ADB's assistance for projects emphasized raising productivity by improving factory processing and cultivation practices, and in effect attacked symptoms rather than the cause. The modernization of tea factories improved operating efficiencies and maintained operating margins, but it did not lead to a significant expansion in national production. There remains considerable scope for improving management and production efficiencies at the present scale of operations. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Project management Sector Related Issues: Industry and Trade Policy & Reform: Policy reforms/framework The development of industries within the sector has been suppressed by inappropriate regulations and fiscal policies. Under this operating environment, the record of success of postevaluated projects relative to targets at appraisal for these projects has varied and the operating performance of the sector has lost its competitive advantage and generally remained unsatisfactory. This has pointed to a need for a more market-oriented approach and in-depth project preparation in the sector. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development Policy & Reform: Policy reforms/framework While many of ADB-financed projects improved technologies and cultivation practices, these improvements could not be sustained after completion of the projects, and the concepts introduced were not sustainable once the funds for projects had been utilized. For similar reasons, the factory modernization processes were not replicated or extended. An overriding constraint on development of the sector is the macroeconomic management of the economy. The government needs to focus on policies that further enhance the mobilization of capital, reduce inflation, minimize interest costs, and ensure more responsive exchange rate adjustments. There is a need for an analysis of the institutional framework, policy environment, and ecological implications of ADB's activities. project cycle stage: Feasibility Operation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Institutional analysis Capacity Development: Technology/Technology transfer Sector Related Issues: Industry and Trade Policy & Reform: Policy reforms/framework | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-bank-assistance-industrial-crops-and-agro-industry-sector-sri-lanka
Impact Evaluation Study of Bank Assistance in the Health and Population Sector in Sri Lanka | Sri Lanka | Health | 1995-12-31 | One of the reasons for the failed promotion of fuller integration of curative and preventive services is the apparent inclination of government doctors to devote more attention to hospital work (curative service) at the expense of preventive work, which also involves field visits. Hospital work serves to keep the doctors in touch with the types of services required in private practice. Alternatives to ensure that adequate medical personnel would be available for preventive health care will have to be studied to remedy the situation. project cycle stage: Feasibility Lesson Topics: The government needs to consider alternative financing strategies for health services as the increasing demand for these has not always been matched with increasing budget allocations. Given the welfare orientation of the government in regard to social services and the traditional political climate on such a sensitive sector as health, any cost recovery attempts may require considerable efforts. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Sector Related Issues: Health and sanitation management The installation of an appropriate BME system would have improved the efficiency of health care delivery system. In particular, it would have helped to monitor not only benefits during and after project implementation but would have also ensured that relevant benchmark data by which to quantify the impact of project intervention are compiled. It would have alleviated the data collection problems often encountered in any postproject assessment caused by transfers and nonavailability of relevant government officers who were intimately connected with the project and who could have provided reliable information. project cycle stage: Implementation, Operation Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Sector Related Issues: Health and sanitation management | Impact Evaluation Study (IES) |  | http://www.adb.org/documents/impact-evaluation-study-bank-assistance-health-and-population-sector-sri-lanka
Livestock Development Project (Loan 606-SRI[SF]) | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 1995-11-30 | Although not envisaged under the project, the use of private inseminators and financial incentives for inseminators in the area covered by the project demonstrates that these measures can increase significantly the effectiveness of the artificial insemination field services. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Sector Related Issues: Rural development Crossbreeding to upgrade the productivity of dairy cattle and buffalo is beneficial. Artificial insemination is acceptable to livestock owners and provides a viable mechanism for introducing exotic genetic material. project cycle stage: Feasibility Lesson Topics: The concentration on infrastructure to improve government support services, such as those for animal health, without commensurate efforts to upgrade the operating systems may not generate the expected benefits. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Extension service Sector Related Issues: Rural development The importation of live animals to establish breeding herds for production of improved animals for distribution is expensive and risky, particularly in the case of the Sahiwal, where the sources and number of stock for making a selection are limited. The importation of semen or small numbers of bulls appears preferable. project cycle stage: Feasibility Lesson Topics: Project Management: Risks/Risk management Sector Related Issues: Rural development The inclusion of an office within the management structure for the project to collect data for monitoring and evaluation does not guarantee that useful information will be collected. It may be necessary for ADB to give specific support to ensuring that the office has expertise in developing appropriate data collection and monitoring systems. The need for this assistance should be assessed at an early stage of implementation in order that data collection activities are planned, funded, and conducted. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project management The promotion of successful cooperative societies is a lengthy process, requiring a comprehensive, well-executed development program, and may not be achieved within the timeframe of a project. This is evident by the lack of cooperative spirit and inability of many of the societies to prevent mismanagement of their business. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Cluster operations Methodologies/Approaches: Holistic approach | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/livestock-development-project-loan-606-srisf
Aquaculture Development Project (Loan 648-SRI[SF]) | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 1995-08-31 | If preparatory work of the PPTA consulting team is poor, it is vital that ADB give greater emphasis on providing advisory input and guidance to the PPTA team to ensure that the project design is formulated in line with ADB's and the government's strategy frameworks, and that all detailed information is adequately presented for further analysis. This is especially important in projects involving the introduction of new technologies. Frequent monitoring and supervisory missions are needed. During the initial critical years of project implementation, ADB supervision needs to identify emerging problems at a much earlier stage and to react with appropriate assistance in a more timely fashion. Another important aspect is that review missions should carefully identify implementation constraints and review the appropriateness of project design and approach to ensure maximum flexibility to meet changing circumstances during implementation. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Project supervision Capacity Development: Technology/Technology transfer Policy & Reform: Policy reforms/framework In case of weak BME expertise both in the executing agency and local consultant capability, project design should give greater emphasis on designing a detailed BME program to enable the executing agency to execute the program. The BME program should specify key indicators by which the achievement of project objectives and the generation of outputs and provision of inputs are to be monitored. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Indicators Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Loan covenants should identify key milestones and ways to ensure that covenants are complied with in a timely manner. In this regard, implementation activities that can adversely affect the operational performance should not be allowed to proceed unless mitigating measures have been adopted in consultation with loan consultants and ADB supervisory staff. project cycle stage: Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Project Management: Consultants Project Management: Project supervision Project delay can be caused by inappropriate site identification because of water, land and/or soil constraints. Much time can be lost in finding alternative sites. Project preparatory teams should pay greater attention to devising appropriate site selection criteria and selecting suitable sites. In devising site selection criteria and subsequent site selection, detailed information pertaining to such factors as land availability and acquisition issues, soil suitability, beneficiary participation, and socioeconomic analysis of beneficiaries living around the proposed project sites should be collected as a basis for appraisal. Land availability and acquisition issues should be fully resolved prior to loan effectivity. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Methodologies/Approaches: Consultation/Participation That weak project management was not identified as a key issue in project preparation and appraisal contributed to the delay in staff and consultants recruitment. This and the cumbersome government procedures were the major reasons for the inefficient project implementation. Ineffective ADB supervision and failure to take firmer action to overcome the weak management during the early years of implementation also contributed to the major delay in implementation. Where weaknesses are identified in the executing agency, consideration should be given to the inclusion of advisory tehnical assistance to address these needs. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Modality: Technical Assistance Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Project supervision | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/aquaculture-development-project-loan-648-srisf
Sevanagala Sugar Development Project (Loan 369-SRI[SF]) | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 1995-08-31 | Projects representing complex ventures integrating field production, factory and distillery performance, and management of smallholders and estates requiring social services, all in an isolated environment, require innovative management inputs to succeed. In that connection, several tested sugar development strategies are available. That of an integrated and closely managed and controlled mode has proved to be inadequate in many countries, as smallholders are particularly difficult to direct. An alternative approach relies on market prices as incentives to smallholders. It would thus appear essential for success that development strategies be subjected to thorough scrutiny at appraisal in the same way technical parameters are generally considered. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial benefits Project Design: Appraisal Project Design: Project design Sector Related Issues: Rural development Since sugar prices have historically been low, it is a prerequisite that price projections and variability are analyzed with care in order to assess realistically the level and likelihood of risks at appraisal and regularly during implementation to reorient a project, as required. In this regard, it would be necessary to prepare likely scenarios, related action plans, and needed resources. The opportunity cost of irrigation projects in situations of competition for water should be reflected in economic analysis and in action plans throughout a project's life, since such costs can often be large relative to the benefits. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Irrigation management Where a prospective executing agency has a consistently poor record of past performance on similar projects, it is desirable to strengthen the institutional framework in conformity with the requirements of the project (through privatization, for example). project cycle stage: Feasibility Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Capacity building | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/sevanagala-sugar-development-project-loan-369-srisf
Plantation Sector Project (Loan 712-SRI[SF]) | Sri Lanka | Agriculture, Natural Resources, and Rural Development | 1995-02-28 | It should be necessary to assess the training needs of the project staff at different levels relating to accounting, auditing, reporting, and tendering. Training should be provided during the early stage of project implementation. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Procurement Project Management: Project reporting Capacity Development: Capacity assessment Capacity Development: Capacity building Projects that involve crops of long gestation periods and have longer-term benefits should consider the long-term interests of the participants, and rigorously assess the risks involved. The project design should provide for the periodic monitoring of government interventions and the macroeconomic environment affecting production and marketing. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Risks/Risk management Sector Related Issues: Rural development The design and implementation arrangements and plans for projects of the plantation sector-type dispersed throughout the country should consider the views and experience of the potential participants. In particular, where a large number of producing and processing units dispersed in the countryside are involved, the project should take a realistic view and provide for a longer implementation period. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation The plantation estates complement the smallholder sector. Projects for the two subsectors, even if processed independently, should be coordinated but responsibility for implementation can be clearly demarcated and defined. This will ensure interaction of the estate factories with the neighboring smallholders supplying green tea leaf or rubber latex to the estates for processing. In this symbiotic relationship, the estates could provide the smallholders with various services, technologies, and inputs. Such an arrangement will, inter alia, lead to estate-village integration and harmony in the plantation environment. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Rural development The strengths and weaknesses of state agencies owning and operating commercial enterprises should be examined in depth at the time of project appraisal. Project lending to them should proceed cautiously and include specific provisions to address problems that may be identified during implementation. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Capacity Development: Capacity assessment Capacity Development: Institutional analysis To be cost-effective, suitable, and maintainable, housing and other social welfare activities should have beneficiary participation in site selection, design and cost-sharing arrangements. project cycle stage: Design, Feasibility Lesson Topics: | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/plantation-sector-project-loan-712-srisf
Rural Development Project: Project Completion Report | Tajikistan | Agriculture, Natural Resources, and Rural Development, Finance, Transport | 2015-09-21 | Effective implementation is strongly linked to the quality of project management. Implementation suffered from poor leadership and a lack of focus on activities and outcomes by the first two project directors. This was reflected in the non-compliance with ADB's Guidelines on the use of Consultants and Procurement Guidelines, and the non-implementation of ADB- approved activity changes. These resulted in delays and reductions in project scope. project cycle stage: Implementation The large number of civil works contracts was an administrative burden on both the Ministry of Agriculture (MOA) and ADB. Given the similarity of some rural infrastructure subprojects (e.g., the village potable water supply schemes), it should have been possible to group subprojects into fewer contracts to be more manageable, allowing MOA to focus more on implementing the other components more directly related to enhancing agricultural performance. project cycle stage: Design, Implementation The project had too many DMF (design and monitoring framework) indicators, some of which were poorly defined and hence not properly measured, set too high for the activities to achieve, without clearly defined targets. Component 3 could only pilot technologies within the implementation period, hence the large-scale raion impacts could only be achieved many years after adoption. Project management did not have the capacity to prioritize the DMF indicators. project cycle stage: Concept Some payment delays occurred as a result of mistakes in withdrawal applications because of the complexities of cost sharing between the Global Environment Facility and Asian Development Fund grants. Simplified consistent arrangements should have been established. project cycle stage: Implementation The project benefited from involving women in the planning process of infrastructure projects. There was strong community ownership; the structures targeted community needs; and in many cases women led the operation and maintenance of structures. This contributes strongly to the investment's long-term sustainability. project cycle stage: Design, Operation Implementation of the credit line would have been more successful if (i) financial and integrity due diligence was conducted of financial intermediary and microfinance institutions at appraisal, and (ii) necessary project and subsidiary loan agreements were signed. Having signed agreements between MOF (Ministry of Finance), microfinance institutions, and ADB may have prevented MOF relinquishing its role as financial intermediary after project approval. project cycle stage: Concept, Implementation The project showed commendable flexibility in implementing new activities (e.g., establishing veterinary centers) in response to beneficiary needs. As a result, the project has strong community support and ownership (e.g., infrastructure, veterinary centers, PUSs [pasture user societies]). This should ensure sustainability. project cycle stage: Implementation, Operation At appraisal and during implementation, establishing demand-driven agricultural advisory centers and MIUs (market intelligence units) that were autonomous from government was seen as an essential project component. There was a desire for the organizations to be on a secure financial footing with farmers contracted to pay for advice they received. However, the transfer of project vehicles and equipment procured for them to government agencies, including MOA (Ministry of Agriculture), risks the centers' sustainability. At design or during implementation, steps need to be taken to clarify the future ownership of such assets. Alternatively, no attempt should be made to establish these types of organizations if it is possible they will operate only during implementation. project cycle stage: Design, Appraisal, Implementation, Operation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/taj-rural-development-project-pcr
Strengthening Public Resource Management Program: Completion Report | Tajikistan | Public Sector Management | 2015-09-17 | A program concentrating on a single area is much more likely to have a bigger impact than a program with several focuses project cycle stage: Design In order to have a meaningful and more sustainable impact, policy reforms should focus on areas in which ADB has been engaged and remains involved over a longer time period. project cycle stage: Operation Where country systems are weak, program monitoring could benefit from TA (technical assistance), as in Tajikistan. The TA could focus on expenditure tracking mechanisms, internal controls, and external audits; and be conducted in two stages. In the first stage, when monitoring capacity is still weak, experts could be engaged to monitor program-supported expenditures rather than relying on the government to submit monitoring reports. The second stage would focus on improving country systems to help the transition of monitoring tasks from external experts to government staff. project cycle stage: Implementation, Operation, Country Partnership Strategy In countries with capacity challenges, reforms take time as limited capacity results in implementation delays. This must be accounted for in design. project cycle stage: Implementation A multiple tranche design or program cluster design is useful, as it brings more balance to the program and helps keep up the government's commitment, even though such a design has high transaction costs for the government and ADB. Such designs also discourage the tendency for the government and ADB to include easier actions in the initial tranche and tougher ones in the later tranches, thereby unbalancing the program and leading to less than successful ratings. The incentive tranche kept ADB and the government engaged and kept the reforms on track. project cycle stage: Design Policy reforms invariably require a champion to steer and lead. The Minister of Labor and Social Protection, who had earlier been the Chairman of Amonatbank, was the key figure in promoting the plastic cards pilot program. Despite some issues (some of which may still linger), this remains a modern step in pension reform in the region. Similarly, the reforms in the Tax Committee had considerable government ownership and support. During the program, the President announced issuance of a new Tax Code, an action that was endorsed by the program. project cycle stage: Implementation, Operation Gender-related goals are generally easier to monitor if they are policy conditions instead of targets in the DMF (design and monitoring framework). project cycle stage: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-public-resource-management-program-pcr
Khatlon Province Flood Risk Management Project: Completion Report | Tajikistan | Agriculture, Natural Resources, and Rural Development | 2015-04-15 | Implementation arrangements. While foreign contractors were not attracted to the ICB (international competitive bidding) packages because of the location and limited time available to complete the rehabilitation works, national contractors were able to undertake civil work with a contract value of $1.5 million. Second, there was a high project administration burden associated with the large number of civil works contracts (there were 28 civil works contracts awarded through either NCB [national competitive bidding] or ICB, with an average contract amount of $0.7 million). If the civil works had been repackaged, with a value of $1.5 million per contract, the number of civil work contracts could have been reduced to 13. Third, involvement of PMO (project management office) staff - in the absence of the involvement of permanent executing agency and implementing agency staff with attractive salaries in the fields of procurement, economic and financial evaluations, social and environment safeguards, and financial management - will not improve institutional capacity of the executing agency and implementing agencies in these fields, and will perpetuate the need to establish a PMO for future projects. Fourth, although the project was the first ADB-financed flood-related project in Tajikistan implemented through three government agencies with an integrated approach and in partnership with the NGO (nongovernment organization) that implemented the JFPR (Japan Fund for Poverty Reduction) project, the integrated approach and good collaboration resulted in successful non-physical project outputs, for the project and successful community-level outputs for the JFPR project. In particular, it proved that community- level interventions can be carried out by NGO(s) if firm partnership mechanisms are developed during project preparation. project cycle stage: Design, Feasibility, Implementation Project design. The holistic flood risk management approach that combines physical, non-physical, and legal measures (as distinct from previous reactive infrastructure-oriented flood control measures) was quite effective in helping people address flood risks. Second, the specially designed spurs have been effective in stimulating sedimentation, with natural vegetation, inside the river channel, which could augment rehabilitated embankments for effective flood protection, and would reduce O&M (operation and maintenance) requirement. Third, the specified heavy equipment for the O&M activity was, in some cases, too small for flood protection works and not efficient. Fourth, while flood warning systems using radio communication were proposed and were procured under the project, these were largely obsolete because of the prevalent and more efficient use of mobile telephones in the project area. project cycle stage: Design, Implementation, Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/khatlon-province-flood-risk-management-project-pcr
Sustainable Cotton Subsector Project: Validation of Completion Report | Tajikistan | Agriculture, Natural Resources, and Rural Development, Finance | 2015-01-16 | This validation subscribes to the major lessons the PCR (project completion report) drew out for ADB operations. The PCR noted that the project's amended purpose and objectives, as well as the corresponding outputs needed to meet them, were clearly stated. At the same time, the PCR noted that many operational and management lapses could have been immediately and effectively averted if the executing agencies had a better appreciation of the processes, procedures, and requirements of the project and helped ensure government's commitment to project objectives. Baseline data and monitoring reports were not complied with. Required contractual agreements were only halfheartedly pursued. Clearly, the implementing institutions' earlier and closer guidance on the processes and procedures for procuring goods and services, and the timely selection of private partners could have avoided implementation slippage. Due diligence on the capacity and commitment of government partner institutions, like the MOA (Ministry of Agriculture), to implement components assigned to them should have been undertaken at appraisal to determine the risks and sustainability of involving them. project cycle stage: Implementation | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/tajikistan-sustainable-cotton-subsector-project
Sustainable Cotton Subsector Project | Tajikistan | Agriculture, Natural Resources, and Rural Development, Finance | 2014-03-01 | More detailed understanding of legal requirements for and better supervision of arrangements for the establishment and operation of project-financed assets by private- sector entities is necessary to remove the risk that such assets may not operate effectively or operate in ways not intended. Expecting farmer organizations to want to operate such facilities as seed cleaning plants, as the proposal of the major change in scope and implementation arrangements did, was overly optimistic. Moreover, proactively promoting expressions of interest solely from farmer organizations as opposed to other entities would have been a conflict of interest. More emphasis is required on the establishment and operation of project implementation and safeguards monitoring to ensure effective implementation and facilitate project evaluation. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/sustainable-cotton-subsector-project-pcr
Dushanbe - Kyrgyz Border Road Rehabilitation Project, Phase II | Tajikistan | Transport | 2013-03-06 | 1. A properly designed project can minimize the risk of changes in quantities and scope during implementation and can contribute to timely completion within budget. For this project, the geological nature and conditions were complex and fragile and no detailed study was carried out at appraisal. This caused several changes in the estimation of earthwork needed during implementation and made detailed geological studies in the middle of the process necessary. The entire project design and financing plans were affected. Such complex conditions should be carefully examined by conducting detailed studies during project preparation. project cycle stage: Lesson Topics: 2. More robust due diligence is needed during project design and formulation to enable the closest possible cost estimates and to set aside enough resources to cover contingencies. This can result in considerable time savings. The values of the works contracts were significantly higher than originally estimated. Further, the amounts had to be increased during implementation because of an unprecedented increase in material costs, besides the extra earthwork needed. At cost estimation, prices of materials should be examined carefully and in relation to neighboring markets, and also by looking at the unit costs of similar items in previously awarded contracts. A sufficient allowance should be kept under contingencies for any unexpected cost increases for construction material and/or changes in contract scope. project cycle stage: Lesson Topics: 3. Because the project road is now in better condition, vehicles travel faster than before. Existing road safety facilities are insufficient to minimize accidents. Future projects must include a road safety component to ensure that comprehensive road safety arrangements are in place, instead of relying on existing, insufficient facilities. project cycle stage: Lesson Topics: 4. The loan and grant were approved together, and the information and education campaign (IEC) activities under the grant were extended to people engaged in civil works financed by the loan. The IEC activities were managed by the health officials trained through the HIV/AIDS and Mitigation Program. Such synergetic (cross-sector) approaches may be applied to future transport projects, considering the worldwide HIV/AIDS prevalence. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/dushanbe-kyrgyz-border-road-rehabilitation-project-phase-ii-pcr
Tajikistan: Health Sector Reform Project | Tajikistan | Health | 2012-12-10 | Relative success of the project was facilitated by: (i) Installation of project management at a very high level with the President's office as executing agency and the deputy prime minister as project coordinator. With such high level management support, the adoption of key policy recommendations and implementation of essential reform packages had a much better chance of being acted upon more quickly than if it were anchored on a weak ministry that still needed reform and strengthening.; and (ii) ADB's having frequent review missions at the initial stage, active participation in technical discussions, and prompt action on project requests, were critical factors in ensuring that the project remained responsive to recurrent and emerging needs and that implementation was on track with the project timelines. [Main text, para. 32] project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/tajikistan-health-sector-reform-project
Irrigation Rehabilitation Project | Tajikistan | Agriculture, natural resources and rural development | 2012-11-01 | Partial rehabilitation of irrigation systems is less effective than complete rehabilitation. Two issues arose from the partial rehabilitation approach: (a) significant infrastructure constraints remained following the partial rehabilitation, limiting the effectiveness and efficiency of the investment; and (b) there were public misconceptions about the rehabilitation program, which contributed to the project complaints raised by nongovernment organizations (NGOs). Infrastructure rehabilitation projects dispersed over a broad geographic area are harder to implement and have higher administrative burdens and management costs than more regionally concentrated projects. There is a high project administration burden associated with a large number of civil works and equipment contracts. Improving on-farm agricultural productivity is important for project efficiency and sustainability. Access to irrigation water is not the only constraint on improving crop yields. Higher farm incomes from yield improvements due to productivity gains make it easier to pay water use fees and sustain operation and mainetnance (O&M) of irrigation infrastructure. The Ministry of Water Resources and Land Reclamation (MWRLR) did not have the expertise to deliver the output of improved agricultural technologies. An alternative implementing agency such as the Ministry of Agriculture and Rural Development may have had more success in delivering this output. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/irrigation-rehabilitation-project-pcr
Regional Customs Modernization and Infrastructure Development Project | Tajikistan | Industry and Trade | 2012-10-01 | The project scope proposed at appraisal (in this case with respect to border-post infrastructure) needs to be more carefully assessed, and cost estimates need to more closely reflect the real costs of project expenditures. As regards infrastructure, costs and project schedules should reflect the difficulty of access to project areas and the relatively short construction season in some project areas. Where a major project component (such as the unified automated information system or UAIS) is dependent on the performance of consultants (in this case with respect to UAIS procurement) and where the executing agency does not have the capacity to monitor consultants' progress, ADB should take greater responsibility for monitoring progress at an early stage to avoid problems that may later cause implementation delays. There is need for standard bidding documents allowing for the procurement of a single responsibility IT contract, including both software and hardware components. A project steering committee may not be necessary where the executing agency is able to coordinate directly with other government agencies to facilitate project implementation. Low levels of remuneration for project management staff can lead to high staff turnover with potentially negative consequences for project implementation. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/regional-customs-modernization-and-infrastructure-development-project-pcr
Republic of Tajikistan: Dushanbe-Kyrgyz Border Rehabilitation Project (Phase I) | Tajikistan | Transport | 2011-12-01 | 1. The approach used in calculating the economic internal rate of return at completion should be consistent with the approach adopted at appraisal. This will provide a realistic and reliable comparison of before and after project economic benefits. [Main text, paras. 16, 23] project cycle stage: Appraisal Completion Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Appraisal | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/republic-tajikistan-dushanbe-kyrgyz-border-rehabilitation-project
Tajikistan: Power Rehabilitation Project | Tajikistan | Energy | 2011-04-30 | 1. For lessons to be useful during project implementation, they need to be taken into account during the formulation and design stage. Listing lessons learned in the report and recommendation of the President is not enough. For example, the implementation of the Power Rehabilitation Project in Tajikistan would have benefited if at least some of the past lessons were taken into account during its formulation and design. Many of the implementation problems arose because of the executing agency's (Barki Tajik) unfamiliarity with ADB's procurement procedures, and the appraisal mission was well aware that such unfamiliarity has delayed the start of many projects in Central Asia. These problems would have been avoided had this been taken into account in the project's design and the executing agency provided the necessary familiarization training on ADB procurement procedures. [Main text, pages 4, 8] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Energy planning/management | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/tajikistan-power-rehabilitation-project
Tajikistan: Microfinance Systems Development Program [Loan 2000-2001-TAJ] | Tajikistan | Finance | 2010-12-06 | The Microfinance Systems Development Program experience underpins the need for adequate advisory services to help prepare required legal and regulatory changes to speed up program implementation. The program also shows the benefits of integrated approaches to microfinance development support that promote capacity development of microfinance institutions in conjunction with necessary reforms in the underlying policy environment. [Main text, page 9, section E(2)] project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Financing Methodologies/Approaches: Program Approach | Validation of Project/Program Completion Report | Highly successful | http://www.adb.org/documents/tajikistan-microfinance-systems-development-program-loan-2000-2001-taj
Agriculture Rehabilitation Project | Tajikistan | Agriculture, natural resources and rural development | 2010-12-01 | Engaging local expertise to undertake the survey and design of works expedites implementation, reduces costs associated with engaging international and national consultants for the purpose, provides the government with continuing access to project-relevant expertise, and builds national capacity for future projects. Where WUAs are expected to participate in designing irrigation and drainage schemes, it is important that they be established in advance of the design process to ensure ownership. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/agriculture-rehabilitation-project
Crisis Recovery Support Program | Tajikistan | Public sector management | 2010-12-01 | The program provides several lessons on structuring a crisis response operation. First, ADB has no modality for a financial crisis response operation for Asian Development Fund countries. The special program loan in the Program Lending Policy is limited to ordinary capital resources countries and can only used to address balance of payment crises. Likewise, emergency assistance under the Disaster and Emergency Assistance Policy (DEAP) does not include financial crisis response. As such, the program had to use the standard program grant modality and develop the design of program actions to allow quick processing and disbursement. While program preparation was shorter than for typical program grants and loans, preparation would have benefited from streamlined and abbreviated procedures similar to the countercyclical support facility and the DEAP, and would have been able to provide the support much earlier. Second, during crisis episodes, while policy reforms are important, the government has urgent needs to quickly stabilize the economy, such as, providing urgent fiscal support to counteract the financial crisis. As such, crisis response operations should focus more on immediate responses to the financial crisis, such as maintaining critical social and safety net expenditures. However, as crises open opportunities for reforms, policy dialogue can be initiated for follow-up operations. But this should not delay the financial crisis recovery support. Third, success of a financial crisis response operation is highly contingent on the government's ability to quickly put together its own anti-crisis plan, which could be financed by ADB after exercising due diligence. In the case of Tajikistan, the government had an anti-crisis action plan and a crisis budget. Readiness to implement is also important. Fourth, since the crisis response operations support government's crisis mitigation measures, program monitoring could also benefit from technical assistance where country systems are weak, as in Tajikistan. The technical assistance could focus on expenditure tracking mechanisms, internal controls, and external audits; and be conducted in two stages. At the first stage, when monitoring capacity is still weak, experts could be engaged to monitor program-supported expenditures rather than relying on the government to submit monitoring reports. The second stage would focus on improving country systems to help transition monitoring tasks from external experts to government staff. Fifth, the program provided lessons in allocating counterpart funds generated from program proceeds. Budget earmarking should only be considered if the government has adequate mechanisms to track expenditures. Otherwise, technical assistance is important to provide this capacity. Programs should also rethink strict budget earmarking. While placing strict conditions on how a government spends the funds seems desirable, implementation could be difficult when budget precision is low. In the case of the program, the government could not fully execute the strictly allocated utility expenditures because it had already maximized its spending below the budget allocation. A better solution might be to provide governments with sufficient flexibility in spending across several identified items. Also, the scope and coverage of independent audits of special accounts to fund specific items should be very clear and precise if they are to be useful. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/crisis-recovery-support-program-0
Education Sector Reform Project | Tajikistan | Education | 2010-12-01 | Holistic approach. The project design, which simultaneously strengthens three pillars of support the line ministry (MInistry of Education or MOE), the school, and the community proved to be a good model for future education projects. Complementary project inputs. The combination of the Education Sector Reform Project (ESRP) and the Japan Fund for Poverty Reduction (JFPR) School Improvement Project was a demonstration of successful coordination of projects pursuing related objectives within the same organization. Transparency and fairness in resource allocation. The use of objective, transparent (poverty index), and fair criteria in allocating assistance funds elicits trust and a positive response from the community. Application of training to real situations. The in-service training provided participants with new ideas and skills. Combined with the provision of new textbooks and teachers' manuals written in line wit the methodological training, this has provided teachers with concrete opportunities to practice and develop their skills further. Sense of ownership at the higher level. Developing a strong sense of ownership at the higher level of the hierarchy is as important as developing it at the ground level. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/education-sector-reform-project
Health Sector Reform Project | Tajikistan | Health | 2010-12-01 | The project experience: (i) confirms that rationalization of PHC institutions and provision of adequate health financing should go 'hand in hand'. Thus, the restructuring of health institutions should be accompanied by trained primary health care (PHC) staff, sufficient coverage of PHC facilities, adequate supplies of essential drugs and medical commodities, and health reform; (ii) illustrates the value of conducting a comprehensive needs assessment before drawing up civil works and equipment lists, to ensure that the right inputs are made in the right places; (iii) demonstrates the need for advance recruitment of consultants to assist with planning and review, pre-implementation preparations, and legal support to ensure that project implementation is not delayed; (iv) indicates the need for intensive information campaigns to ensure a high degree of community participation in PHC management, sourcing of financing, co-sharing, contributions in kind, and other expressions of support that help to sustain health reform projects. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/health-sector-reform-project
Dushanbe-Kyrgyz Border Road Rehabilitation Project (Phase 1) | Tajikistan | Transport | 2010-08-01 | The technical assistance (TA) for preparing the project was inadequate. Project preparatory TA was designed and implemented similarly for all countries in terms of budget, scope, and expertise. However, Tajikistan needs more technical support from ADB, especially in engineering aspects. Due to inadequate engineering survey and design, as well as little involvement of government officials, numerous changes in quantity and methodology were required during implementation. ADB should provide suitable technical assistance according to need (which will differ from country from country) and select suitable consultants. The project was the second ADB-financed road project in Tajikistan. Therefore, the Ministry of Transport and Communication (MOTC) and project implementation unit (PIU) need to be familiarized with ADB's policies and procedures. However, the familiarization effort was inadequate. ADB should continue to train MOTC on its policies and procedures and PIU staff for existing and future projects. In addition, frequent changes in ADB project officers caused discontinuity in project administration. The transfer of project administration from ADB headquarters to the Tajikistan Resident Mission occurred almost at the end of the project (2008), and this made it difficult for the resident mission to take over. Transfer of the project at a late stage of implementation should be carefully considered. Frequent replacement of ADB project officers should be avoided. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/dushanbe-kyrgyz-border-road-rehabilitation-project-phase-1
Power Rehabilitation Project | Tajikistan | Energy | 2009-12-28 | 1. Although the project components were completed successfully, there were serious cost overruns and implementation delays. ADB and its consultants need to be aware of the risk of high construction costs in Tajikistan, and to review whether this is a persistent problem or if it has diminished with the more settled political conditions now. The implementation delays also point to the need for significant levels of assistance from international consultants in project implementation, and to the establishment of a PIU that is not subject to political interference. [Main text, paras. 30,35,62,69] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Project management Project Management: Risks/Risk management 2. Collection of appropriate data is essential in monitoring and measuring project benefits and outcomes. During the PCR mission, Barki Tojik had problems providing certain data to quantify the project's direct and indirect incremental effects on income and poverty reduction as well as improved standards of living. Hence in the preparation and implementation of the next project, ADB needs to ensure that the executing agency and project implementation unit would place more attention in monitoring the collection of such information. [Main text, paras. 61,64,70] project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Monitoring and evaluation 3. ADB needs to be more careful in reviewing the compliance of Barki Tojik with loan and project covenants that require cost recovery and financial performance, improved accounting procedures, and the annual submission of corporate and financial accounts in English to ADB. These agreements are standard ADB covenants which Barki Tojik failed to comply with as the latter's accounting and financial performance were unsatisfactory. [Main text, paras. 37-41,71,74] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-rehabilitation-project
Road Rehabilitation Project | Tajikistan | Transport | 2008-07-31 | Project implementation could have improved with intensive trainings on ADB policies and procedures and by ensuring staff continuity. Advance contracting and retroactive financing would have shortened the time between appraisal and the start of works, and between design, tendering, and contract award. Evaluation noted numerous changes in the road rehabilitation method from that indicated in the drawings caused substantial engineering changes and raised the bidding price. The scope of the improvement works also increased substantially between appraisal and the start of actual works. On top of this, frequent changes in ADB project officers have caused discontinuity in project preparation and administration. [Main text, paras. 20, 39, 58] project cycle stage: Design Appraisal Implementation Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project administration Project Management: Project management Project Management: Project supervision Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/road-rehabilitation-project-3
Emergency Baipaza Landslide Stabilization Project | Tajikistan |  | 2006-04-14 | 1. Rigorous administration, close supervision, timely implementation of corrective measures, and frequent review missions are important, particularly when the executing and implementing agencies are not familiar with ADB procedures. [Main text, paras. 34, 46(i)] project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project supervision 2. Strong government ownership facilitated project implementation as it ensured timely provision of counterpart funds. It has also allowed the project to be completed without disputes or unexpected claims among contractors, suppliers and consultants. The high level of government ownership was demonstrated with its frequent project steering committee meetings, visits by the deputy prime minister to the project site, efficient management of imprest accounts, and timely provision of adequate counterpart funds. [Main text, paras. 31-33, 46(ii)] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Management: Consultants Project Management: Procurement Capacity Development: Ownership | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/emergency-baipaza-landslide-stabilization-project
Social Sector Rehabilitation | Tajikistan |  | 2005-09-15 | Continual on-the-job training of executing agencies and project implementation staff should be conducted during implementation. Training of the project team in financial management and accounting - and the use of financial and accounting software systems - significantly increased the effectiveness and speed of project implementation. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Executing/Implementing agencies Project Management: Management information system Project Management: Project management Capacity Development: Capacity building The civil works highlighted the importance of timely coordination between civil works and procurement of equipment and supplies. Civil work contractors should be prequalified to ensure adequate quality of the works. Local level technical supervision over the civil works contributed tothe quality and efficiency of the works. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project supervision Methodologies/Approaches: Consultation/Participation The discretionary grant fund (DGF) component demonstrated the value of local community involvement in rehabilitation of community facilities and development of community-level projects. The DGF-funded microprojects helped to create employment, promoted entrepreneurship, provided local communities with long-term sources of income, and confirmed that local community mobilizationhas strong potential to support development activities. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Capacity Development: Capacity development Crosscutting Issues/Themes: Employment Methodologies/Approaches: Community approach The government did not utilize fully the project steering committee (PSC) as a strategic and coordinating institution. The project stakeholders missed an opportunity to use the PSC meetings for proactive multilateral dialogue, coordination, and cooperation. Project implementation issues were resolved through informal bilateral contacts between the project management unit (PMU) and the concerned ministries. This highlighted the trade-off between the role of PSC as an institution for strategic planning, interagency coordination, and policy dialogue; and PSC as an additional level of project management. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Policy & Reform: Policy matrix Methodologies/Approaches: Consultation/Participation The project underscored the importance of interagency coordination. Donor coordination and information sharing in future projects should be ensured through mechanismssuch as roundtables, workshops, and conferences. These would bring together international aid agencies working in the country's social sector development. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation The project was the first ADB loan project in Tajikistan. At the start of implementation, the executing agency, project management unit (PMU), project implementation units (PIUs), and other counterparts were unfamiliar with ADB's operation procedures and guidelines. In addition to providing on-the-job training, the international consultants played an important role in developing staff capacity in the PMU and PIUs. The consultants contributed significantly to increasing the efficiency of project implementation. Moreover, they developed adequate technical specifications for equipment and supplies, and streamlined distribution of pharmaceuticals to rehabilitated health care facilities. project cycle stage: Feasibility, Appraisal Lesson Topics: Sector Related Issues: Health and sanitation management Policy & Reform: Transition economies To allow ADB to respond to the urgent social sector rehabilitation needs in post-civil war Tajikistan, the project was designed quickly in an insecure environment. For these reasons, the project appraisal had three major shortcomings: (i) inadequate assessment of infrastructure rehabilitation needs, (ii) underestimated project costs, and (iii) inadequate assessment of implementation arrangements. The shortcomings in appraisal work contributed to implementation delays and other problems that had to be resolved during implementation. Despite those shortcomings, the timely and broad nature of the project catalyzed efforts to address the challenges in the country's social sector. When processing similar projects in the future, recognition of possible trade-offs between timely processing, quality Project Design, and effective implementation will be important. Circumstances permitting, adequate assessment of implementation issues and arrangements is also critical. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Project management Country Context: Emergency Sector Related Issues: Education Sector Related Issues: Health and sanitation management Sector Related Issues: Urban sector/development | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/social-sector-rehabilitation
Emergency Flood Rehabilitation | Tajikistan |  | 2004-06-15 | Materials should not have been procured separately and should have been included in the respective civil works, mechanical and electrical works contracts. The large number of contracts with materials to be supplied by other suppliers made the use of materials difficult to monitor and supervise. The implementing agency (Center for Liquidation of the Consequences of Natural Disasters or CLCND) could not verify exact consumption of fuel, cement, and bitumen for each contract. WB cancelled its loan due to misprocurement, because material bids came from nonexistent companies. It would have been better to have had fewer contractors (even if there were many sites), with the contractors responsible for procuring the materials. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project supervision The loan should have included plans and covenants to stimulate the government to finance maintenance of the rehabilitated/repaired structures, such as roads, levees, andschools. Only 3 years after the original repair, the embankments again need repair - but no funds are available. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Management: Operation and maintenance Sector Related Issues: Education Sector Related Issues: Roading Sector Related Issues: Water resource management The project would have benefited from a full-time international consultant particularly during the first year of implementation to train and supervise the project implementation staff, domestic designers, and supervisors. ADTA 3319-TAJ, which was to provide those required services during five 1-month disaster management expert (DME) field visits, failed to do that. Implementing agency personnel and supervisors needed training - even in office technology. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Capacity building Capacity Development: Human resources management Country Context: Emergency Capacity Development: Technology/Technology transfer The Tajik procurement systems and designs were used in civil works. The project was divided into unnecessarily small contracts: 87 civil works and 61 materials procurement contracts. Design and management of so many contracts suffered because the number of supervisors was limited and the implementing agency (IA) was inexperienced and weak, and the sites were scattered across Tajikistan which rendered effective supervision difficult. project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project supervision | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/emergency-flood-rehabilitation
Emergency Restoration of Yavan Water Conveyance System Project | Tajikistan |  | 2004-05-14 | A higher imprest fund ceiling is necessary for short-duration projects to avoid implementation delays. However, this must be linked to strong financial management. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financial management A well-designed associated advisory TA with strong links to the investment project can greatly enhance capacity building and sustainability of the project benefits. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance Capacity Development: Capacity building Credible NGOs carry out socioeconomic surveys and information campaigns more effectively and efficiently than consultants. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Data collection and management Project Management: Consultants Policy & Reform: Information dissemination/Public awareness Methodologies/Approaches: Civil Society Participation Environmental monitoring programs tend to get neglected under pressing needs to rehabilitate project systems in the shortest possible time. Review missions need to pay particular attention to environmental monitoring activities specified in the summary initial environment examination. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Environmental management Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Management: Project supervision Rigorous project administration and timely implementation of corrective measures are key to the timely completion of a short-duration project, particularly when the executing agency is not familiar with the ADB procedures. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Serious review by ADB of the resettlement plan is key to its timely and proper implementation. project cycle stage: Appraisal Lesson Topics: Since ADB staff resources might not be sufficient, suitable provisions should be made for international consultants, particularly if the executing agency is not familiar with ADB procedures. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project administration Capacity Development: Human resources management Strong ownership of the project by the government facilitates the timely release of counterpart funds in appropriate amounts, allowing for the completion of a project on schedule. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Capacity Development: Ownership The capacity of government auditors should be assessed at appraisal, and if found to be inadequate, external auditors should be provided. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Capacity Development: Capacity assessment The Project Steering Committee (PSC) can facilitate smooth implementation and timely completion of a project through frequent meetings and rigorous implementation review. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/emergency-restoration-yavan-water-conveyance-system-project
Postconflict Infrastructure Program | Tajikistan |  | 2002-12-13 | ADB needs to take into account the government's capacity to implement substantial policy reforms in crucial sectors, particularly in light of the country's economic and political situation. ADB should not design an overly ambitious policyreform agenda for program loans, since such an agenda will likely require modification in thefuture and does not increase the likelihood that reforms will be implemented. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Capacity Development: Capacity assessment Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/postconflict-infrastructure-program
Capital Market Development Program: Completion Report | Thailand | Finance | 2015-06-18 | Strong coordination. The CMDWC (Capital Market Development Working Committee) and its sub-committee provided a platform for strong coordination among regulators and with market institutions. The Capital Market Development Master Plan was drafted by the sub-committee and endorsed by the committee through a highly consultative process, which greatly helped in fostering a sense of ownership. project cycle stage: Design, Implementation Long-term perspective. The master plan - with a medium-term vision and strategies for capital market development - provided the government and regulators with a set of long-term objectives to guide and shape policy design and implementation. project cycle stage: Design, Implementation Technical assistance (TA) resources. Under the program, the government and regulators adopted legal and policy measures and introduced new products, many of which were relatively new, complicated concepts that required extensive coordination and consultation to build understanding and acceptance by stakeholders. Through resourceful TA support, the program's policy actions were all successfully complied with, and most post-program partnership follow-up actions were also implemented. Individual consultants were selected on the basis of both technical merit and their perceived ability to work well as a team. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/capital-market-development-program-pcr
Thailand Intercity Motorway Project: Technical Assistance Completion Report | Thailand | Transport | 2015-04-01 | One of the important lessons gained during the course of TA (technical assistance) implementation is the active involvement of ADB in providing technical guidance to the TA consultant and offering professional advice to EA/IA (executing/implementing agency) to facilitate TA implementation. The EA/IA regarded ADB's active participation valuable in terms of illustrating ADB's technical know-how and sharing knowledge with the government counterparts. Consultants Qualification Selection (CQS) for the TA is considered an appropriate method for selecting the consultants given that the TA requires specialized expertise in PPP (public-private partnership) transaction advisory. In this regard, another lesson learned through the TA implementation is that the need for closely discussing with the government to determine the specialized expertise in PPP transaction and correspondingly tailoring detailed terms of reference to specify consultants' expertise to facilitate CQS. Additional time required for this process should be taken into consideration when designing the overall TA duration for similar future TA projects. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/thailand-intercity-motorway-project-tcr
Thailand: Country Partnership Strategy, 2007 - 2011 Final Review Validation | Thailand |  | 2013-06-25 | 1. Success was greatest when ADB support was focused in areas where there was strong government buy-in, capable sector officials, a strong desire to catch-up with performance in neighboring countries, and little likelihood that reform would generate political controversy or require extended parliamentary debate. [Executive Summary, page iii; Main text, para. 103(i)] project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity building Capacity Development: Ownership 2. Many government agencies are responsible for decision making. The combination of political instability and fragmented institutional responsibilities has meant that decision making can be complex and often requires a considerable amount of consensus building to move forward. [Executive Summary, page iii; Main text, para. 103(ii)] project cycle stage: Implementation Lesson Topics: 3. Differences exist between country systems in procurement, environmental management, and involuntary resettlement and those that the international financial institutions (IFIs) use. The Greater Mekong Subregion Highway Expansion Project experience demonstrates that project readiness is important, as is working toward compliance between country standards and IFI requirements in procurement and safeguards. [Executive Summary, page iii; Main text, para. 103(iii)] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Resettlement Project Management: Procurement 4. Efforts made to plan, program, and prepare new public sector loans have met with a low level of success because the government has access to sufficient liquidity in the domestic financial market and is reluctant to borrow from international financial institutions. Borrowing uncertainty has made it difficult to plan and manage for the delivery of development results. By contrast, efforts made to help the government identify and chart reforms, as demonstrated in the capital markets area, have generally been sufficient to catalyze a process of positive change. [Executive Summary, page iii; Main text, para. 103(iv)] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Policy & Reform: Public sector reform Policy & Reform: Reform 5. Climatic conditions have become increasingly severe and volatile. Thailand suffered extensive damages from the recent severe floods in 2011 and it was estimated that the floods caused economic losses of close to $46 billion. The severe and prolonged effects of the floods showed that adequate and sustained disaster risk reduction programs are necessary, in addition to the focus on relief and recovery. [Executive Summary, pages iii-iv; Main text, para. 103(v)] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Country Context: Crisis/Post-crisis | Country Partnership Strategy Final Review |  | http://www.adb.org/documents/thailand-country-partnership-strategy-2007-2011-final-review-validation
Higher Education Development Project | Thailand |  | 2006-09-15 | 1. Opportunities for project staff to learn about ADB's guidelines, as well as government regulations, on or before the start of a project are critically important for smooth implementation of the project. In this project, procurement was delayed initially because subproject implementation units were mandated to follow several guidelines and procedures at the same time - government regulations, administrative regulations and commonly accepted practices in project universities and faculties, and ADB's guidelines and procedures - most of which were new to them. The principles of the different regulations were not in conflict, however, each regulation required different documentation, communication, and approval process, creating confusion and requiring longer processing time. The lack of a focal person with ample experience in different procurement styles and proficiency in English to handle the bidding process might have been another reason for the delay. To resolve this issue, active use of retroactive financing under the loan and a component under the project preparatory technical assistance for this purpose might merit consideration. [Main text, paras. 25, 59] project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Appraisal Project Management: Procurement Project Management: Project administration Project Management: Project management Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/higher-education-development-project
Restructuring of Specialized Financial Institutions | Thailand |  | 2005-12-15 | ADB's sustained experience in Thailand in the aftermath of the 1997 crisis highlights the importance of understanding the national contexts for policy making. The recent economics literature explains that the complex interaction between national stakeholders frequently involves conflicts of interest that introduce uncertainty into the final outcomes of reform processes. The different interests of the stakeholders give rise to common agency problems. Thus, coordination issues become important and cannot be taken for granted. The principal implication for project design is the recognition of two factors. First, the domestic political process will determine outcomes. Second, project design will need to be adjusted during implementation to reflect this process. The complexity of national contexts for economic policy making raises the issue that country ownership is thus central. Further, where the government takes commitment and ownership, ADB's role - no matter how highly valued - will involve less ï¿½additionality.ï¿½ A trade-off is inevitable. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Country Context: Crisis/Post-crisis Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Complex issues such as governance reforms cannot be promoted effectively with consulting firm support, as the outputs cannot be specified fully in advance. ADB staff involvement is needed in conjunction with individual consultants to adjust the programs during implementation to meet the needs of the government effectively. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Program Project Management: Consultants Project Management: Project supervision Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/restructuring-specialized-financial-institutions-0
Bangkok Urban Transport Project in Thailand (Loan 1195-THA) | Thailand | Transport | 2005-11-30 | In projects with a large advisory component, when advice on various issues is clustered, the risk that some will not be acted upon increases, especially if the relevant government agency is small. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Legal action by households affected by a project should be avoided as much as possible by engaging those households in resettlement planning early, and by determining the compensation and relocation options. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Resettlement Methodologies/Approaches: Consultation/Participation Projects that mix infrastructure investments for certain agencies with large institutional development components for other agencies would work better if ADB were to devote sufficient staff resources to project administration. Resettlement and capacity building components need specialized support from ADB to optimize their effects. One of the risks is that administration will focus on the direct and pressing problems of procurement and construction supervision. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Project Management: Procurement Project Management: Project administration Project Management: Risks/Risk management Capacity Development: Capacity building Capacity Development: Human resources management Projects with a large advisory component should space the advice carefully to enable the government to absorb the outputs at its own pace. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design The potential adverse effects of new roads on environment and traffic accidents are less dependent on road expansion per se than on specific measures taken to mitigate these effects. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Sector Related Issues: Roading Sector Related Issues: Transport planning To optimize the benefits of projects, primary road construction in urban areas must be assessed carefully in the context of needed supporting distributor roads and comprehensive land use management. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Sector Related Issues: Roading Sector Related Issues: Transport planning Sector Related Issues: Urban sector/development Urban highway investments focusing on missing links can help create opportunities, thereby reducing poverty by saving time for bus passengers in the city. The size of the effect depends on the number of buses and vans relative to the total number of vehicles on the road. Equally important are bus ticket prices and the number of poor people traveling by bus. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Sector Related Issues: Transport planning Sector Related Issues: Urban sector/development | Project/Program Performance Evaluation Report (PPER) | Highly successful | http://www.adb.org/documents/bangkok-urban-transport-project-thailand-loan-1195-tha
Rural Enterprise Credit Project in Thailand (Loan 1540-THA) | Thailand | Finance | 2004-10-31 | A variable local benchmark, transparently determined, should be used asreference for re-lending and onlending interest rates. project cycle stage: Feasibility Lesson Topics: Appropriate credit appraisal system for all loans and competent staff is necessary to implement the system to ensure a quality loan portfolio and lead to more sustainable lending. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Finance & Financial Aspects: Financing Factors affecting availability of internal resources and demandfor credit need to be assessed during appraisal. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Appraisal Insurance against unanticipated financial crises needs to be in place to protect development finance institution loans. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Risks/Risk management Country Context: Crisis/Post-crisis Linkage and coordination with other lending agencies on policy reforms should be included in the loan covenant. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Policy & Reform: Policy reforms/framework Nonperforming loans require higher loan-loss provisioning so they don t adversely affect financial performance. project cycle stage: Appraisal Lesson Topics: The predominance of short-term lending can increase volatility. A more balanced asset structure, with a larger share of medium- to long-term lending, is necessary to reduce volatility. This would require careful monitoring to avoid maturity mismatch. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Monitoring & Evaluation: Monitoring and evaluation The use of full or partial guarantees and other instruments along with credit lines must be consistent with the country s financial sector development. project cycle stage: Feasibility Lesson Topics: There is a need to require development finance institutions to hedge foreign exchange positionswith expertise provided along with the ADB loan. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Finance & Financial Aspects: Foreign exchange | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/rural-enterprise-credit-project-thailand-loan-1540-tha
Regional Roads (Sector) Project and Second Regional Roads (Sector) Project | Thailand | Transport | 2004-10-15 | Covenant compliance, especially with regard to submission of audited accounts, and adequate maintenance of project facilities, needs to be enforced thoroughly during implementation. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Loan Agreement: Covenants Project Management: Operation and maintenance The most important problem encountered by the project was undoubtedly the 1997 financial crisis, which affected most contractors, resulting not only in cash flow and financial problems but also in a flow-on effect to site personnel and, in some cases, affecting contractors' management of construction. Cash-flow problems were the single biggest cause of civil works' delays, affecting supply of construction plant and materials, and payment of site personnel. Bidders should have sufficient financial resources during prequalification. Procurement was delayed by the executing agency's (Department of Highway's) unfamiliarity with ADB's standard bidding documents and by need for Cabinet approval of contracts. Adequate management capability is essential to avoid these delays. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management Country Context: Crisis/Post-crisis The project did not have a coordination or implementation unit, which made coordinating the various subcomponents difficult. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Project management Covenant compliance, especially with regard to submission of audited accounts, and adequate maintenance of project facilities, needs to be enforced thoroughly during implementation. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financial reporting Loan Agreement: Covenants Project Management: Operation and maintenance The most important problem encountered by the project was undoubtedly the 1997 financial crisis, which affected most Thai contractors, resulting not only in cash flow and financial problems but also in a flow-on effect to site personnel and, in some cases, affecting contractors' management of construction. Cash-flow problems were the single biggest cause of civil works' delays, affecting supply of construction plant and materials, and payment of site personnel. Bidders should have sufficient financial resources during prequalification. Procurement was delayed by the executing agency's (Department of Highway's) unfamiliarity with ADB's standard bidding documents and by need for Cabinet approval of contracts. Adequate management capability is essential to avoid these delays. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project management Country Context: Crisis/Post-crisis Too many components under the project complicated project administration and involved too many executing agencies. The project did not have a coordination or implementation unit, which made coordinating the various subcomponents difficult. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/regional-roads-sector-project-and-second-regional-roads-sector-project
Agriculture Sector Program | Thailand |  | 2003-12-15 | Due to the complexity of the program, joint supervision and monitoringby the government and ADB on specific project activities financed with counterpart funds could have been carried out more frequently. This was particularly important during program implementation to increase a sense of accountability among implementing agencies. Program Management Office's (PMO's) resources for conducting field verifications of a large number of project activities scattered around the country were limited. A shortage of budgetary resources also constrained capacity building activities that needed to be carried out in parallel with the institutional changes and decentralization proposed under the program. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Management: Executing/Implementing agencies Project Management: Project management Project Management: Project supervision Capacity Development: Capacity building Country Context: Decentralization In view of ADB's long absence from the agriculture sector in Thailand (except for rural finance), a more comprehensive sector analysis would have been useful at the time of program formulation, along with longer periods for the program negotiations and policy dialogue. This would have allowed the implementing agencies to enhance their understanding and ownership of the policy matrix. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Rural development Policy & Reform: Policy matrix The difficulties encountered by the government in resolving medium- to long-termsector issues under a fast-disbursing loan during a crisis period needs to be fullyconsidered for future operations. For instance, the introduction of a decentralized system foragricultural planning and management requires better local capacity and awareness. Properplanning and sequencing are needed to support effective institutionalization. The use of a quick-disbursingemergency loan might carry certain risks and the possibility of adverse impacts. Thechoice of an appropriate operational modality needs to be carefully assessed. project cycle stage: Appraisal Lesson Topics: Modality: Lending modality Project Management: Risks/Risk management Capacity Development: Capacity building Country Context: Crisis/Post-crisis Country Context: Decentralization Country Context: Emergency Sector Related Issues: Rural development Policy & Reform: Information dissemination/Public awareness The program involved a large number of detailed actions, many ofwhich were relatively complex and time-bound. It also called for major changes in deeply rootedpractices and approaches. A more focused approach, with fewer major policy and institutionalissues, could have been effective in establishing a clear understanding of program measuresand required actions. For complex programs involving several agencies and many actions, it isimportant to be realistic about the expected pace of reforms and to ensure that the programperiod includes a sensible allowance for delays in government processes. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Management: Executing/Implementing agencies Policy & Reform: Reform Transparency during program preparation and implementation was critical in obtaining constructive inputs from key stakeholders including nongovernment organizations (NGOs), keeping them reassured, and seeking their support, ownership, and participation. Awareness about the long-term benefits of efficient use of water resources could have been promoted more widely to mobilize political support. Such information dissemination was particularly important for the pilot schemes that require contributions from farmers' groups. Greater emphasis on proactive public relations throughout the program period would have been useful. The benefit of ensuring that all versions of the policy matrix are produced in the Thai language at the beginning of program formulation is also an important consideration. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Modality: Program Capacity Development: Ownership Sector Related Issues: Water resource management Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy matrix Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Pilot project | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/agriculture-sector-program-0
Third Rural Telecommunications (Sector) Project | Thailand | Information and Communication Technology | 2003-12-15 | Contract packages need to be broken into manageable sizes. Under the Second Rural Telecommunications Project a single, turnkey contract was awarded to supply and install equipment, a method that had coordination and supervision difficulties. Under this project, 58 provinces were divided into three zones with works undertaken by different suppliers in each zone. In some cases, the zones were not internally contiguous, causing difficulties for the suppliers. On the downside, three different suppliers with their own design, components, and maintenance requirements provided the technology. This arrangement should be avoided. Thailand already had a large number of time division multiple access (TDMA) stations of the same design, so it might have been more time and cost efficient to repeat orders from the original supplier. The installation suppliers could have competed for wireless local loop (WLL) supply and other tender components. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Management information system Project Management: Procurement Project Management: Project supervision Capacity Development: Technology/Technology transfer Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation Internal political/bureaucratic considerations can cause considerable difficulties. Thetenders for the three zones should not have been issued until Post andTelegraph Department (PTD) had approved frequency allocations. Telephone Organization of Thailand or TOT (the executing agency) got into an international conflict that substantially delayed procurement when itassumed that the necessary frequencies would be available. Significant, internal governmentproblems should be resolved before external commitments are made or implied. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Public governance Project Management: Executing/Implementing agencies Project Management: Procurement | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/third-rural-telecommunications-sector-project
Financial Markets Reform Program | Thailand | Finance | 2003-10-15 | Continuity and flexibility of the program's administration would have been helpful in ensuring effective implementation that was compatible with legislative procedures and the long-standing tradition of interagency consultation for policy formulation. At the time of the program's launch, it was important to maintain a broad-based policy framework to accommodate unexpected events and crisis developments. The needs and desires of the Borrower also outgrew the original policy framework as the progress of market reforms and the economic recovery moved far ahead of the initial expectations. However, loan administration remained focused mainly on the compliance with all specific policy conditions, some of which became outdated or fell short of concrete time-bound action plans for further progress. Thus, the loan administration was unable to address new issues or reassess alternative options during the implementation period. project cycle stage: Lesson Topics: Crosscutting Issues/Themes: Legal system Modality: Policy-based lending Modality: Program Project Management: Project administration Country Context: Crisis/Post-crisis Policy & Reform: Policy reforms/framework Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach In times of crisis, a program loan can benefit enormously fromspeedy processing and disbursement. To provide timely support and enhance the effectivenessof the program, ADB shortened the timeframe for the loan approval and disbursement processby waiving some of the loan processing requirements, such as the formal management reviewand the staff review committee. Unfortunately, however, crisis assistance entails higher risks butless scrutiny on loan conditions and covenants at the time of disbursement. Based onexperience in the Republic of Korea and Thailand, ADB institutionalized a special program loanmodality with shorter maturity and grace period and higher risk premiums. While the benefitsof the significant front-loading cannot be ignored, reasonable risk premiums aligned with market prices and suitable loan structure would enhance efficiency of the crisis management whileminimizing moral hazard. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Loan Agreement: Covenants Modality: Lending modality Modality: Program Project Design: Appraisal Project Management: Risks/Risk management Country Context: Crisis/Post-crisis The financial crisis stemmed from more fundamental problems in the real sector. Lending booms and inflated asset prices prior to the crisis were not only symptoms of structural weaknesses in the financial system, but also a reflection of low productivity of the real sector. To avoid a recurrence of such a crisis, more comprehensive economic reforms should take place to strengthen the competitiveness of the real sector and enhance productivity. The effectiveness of capital market reforms also will depend on the successful completion of corporate restructuring and the recovery of productivity. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Financing Modality: Program Country Context: Crisis/Post-crisis Policy & Reform: Reform The modality of a cluster loan may enable the reassessment ofchanged environments and new issues through rigorous analyses of the fundamental causes ofa crisis as the urgency of the crisis wears off. While a crisis situation requires decisive andimmediate action in the short term, reform principles should reflect more medium- and long-termstructural adjustments to support and strengthen the recovering economy and avoid arecurrence. However, the nature of the emergency, combined with unbridled market insecurity,makes it difficult to map out many details for the longer-term adjustments, let alone judge theextent and length of the crisis management. A relatively long program without a formula formodifications to reflect the changing economic and market environment also seemsinappropriate for crisis management. Since ADB assistance during the crisis pursued twodistinct goals - restoring macroeconomic and financial stability and setting out long-termstructural adjustment to underpin the economic recovery and growth - a single loan (especiallywith a single tranche) might lack the flexibility to effectively implement reform initiatives inresponse to the unfolding crisis and post-crisis recovery. In hindsight, ADB support could havebeen more effective if the initiatives aimed at economic stabilization and immediate correction inthe early stages of the crisis had been followed by detailed technical support and advice. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Market analysis Modality: Cluster operations Modality: Lending modality Modality: Program Modality: Technical Assistance Country Context: Crisis/Post-crisis Country Context: Emergency Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/financial-markets-reform-program
Skills Development Project | Thailand | Education | 2003-10-15 | Initial procurement delays were caused by (i) the Project Implementation Unit's (PIU's) interpretation of ADB procurement procedures for conformity with government regulations; and (ii) the lack of a focal person who had ample experience in different procurement styles and was proficient in English to handle the bidding process. ADB approved additional procurement specialists during implementation to help carry out procurement for 22 project institutes and centers. During preparation, it is useful to assess potential risks of procedural conflict in procurement. Procurement specialists could be considered, particularly in countries where English is less commonly spoken. project cycle stage: Appraisal Lesson Topics: Project Management: Procurement Project Management: Project management Project Management: Risks/Risk management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/skills-development-project-6
Bangkok Urban Transport Project | Thailand | Transport | 2002-12-13 | ADB needs to ensure that the project executing agency (EA) has adequate resources to implement the project on schedule. In this project, the executing agency (EA) was not diligent due to lack of resources and motivation. It should have coordinated with ADB and the consultants more closely, streamlined approvals, and followed ADB guidelines and procedures from the outset. It only communicated when ADB requested information and then only after considerable delay. Advice offered by ADB was often disregarded. Civil works procurement was delayed due to the EA modifying the bidding documents after they were approved by ADB, which made appointing contractors even more difficult. Lastly, the EA ignored the loan covenants. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Loan Agreement: Covenants Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Methodologies/Approaches: Consultation/Participation Only the Canadian International Development Agency (CIDA) grant was provided to the Bangkok Regional Structure Plan. The Inception Mission only visited the National Economic and Social Development Board (NESDB) in 1993 to review progress on the component. NESDB and ADB did not coordinate with each other although the component was successfullycompleted. A component without ADB loans and grants should not be incorporated into future projects. CIDA and ADB did not coordinate with each other. The cofinanciers should haveperiodically discussed the project's status during implementation. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Methodologies/Approaches: Consultation/Participation The Asian economic crisis caused one contractor to seriously delay the project. Careful attention should be paid during the prequalification exercise to ensure that bidders have sufficient financial resources. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Project Management: Procurement Country Context: Crisis/Post-crisis The executing agency selected the construction supervision consultants locally without reference to ADB's Guidelines on the Use of Consultants. As the loan did not include funding for the consulting services, ADB had difficulty controlling the consultants. To avoid the same kinds of delay and difficulty, the construction supervision consultants should be financed from the loan and selected in accordance with ADB's guidelines. The consultants of each section of the project road were different, which required additional coordination. For example, one consultant made a requested project completion report, but another did not. More than one consulting service contract for construction supervision was unnecessary. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Project Management: Project supervision Sector Related Issues: Roading Methodologies/Approaches: Consultation/Participation Three executing agencies (EAs) oversaw four project components, complicating project administration. All the components achieved their objectives, but independently. The EAs coordinated only in thetraining component. A project coordinator should have been appointed from the government. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Capacity Development: Capacity building Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/bangkok-urban-transport-project
Social Sector Program | Thailand |  | 2002-11-15 | Proper information dissemination during program preparation and implementation is critical for obtaining inputs from civil society, keeping them reassured, and seeking their support and participation. Misinformation about the reform process canhinder the pace of implementation and weaken political support. Preparation of program loans requires extensive sector analysis, policy diagnosis, and assessment of institutional performance. It is important to consult a wide group of stakeholders in carrying out these assessments. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Program Capacity Development: Capacity assessment Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation The delay in the release of the second tranche of the loan was partly due to the delay in the government's processes for approval of policy conditions. For complex programs involving several sectors, it is important to be realistic about the expected pace of government approval of reforms and to ensure that program timeframes include a sensible allowance for bureaucratic delays. Unrealistic timeframes can create excessively high expectations and dissatisfaction with the results of the program. project cycle stage: Appraisal Lesson Topics: Modality: Policy-based lending Modality: Program Policy & Reform: Reform The monitoring of sector development programs is complex and requires considerable resources. The program shows that high-level political involvement through the Program Coordinating and Monitoring Committee (PCMC) chaired by the deputy prime minister was critical for monitoring and implementation. Many of ADB's developing member governments may not be able to implement or sustain such monitoring and evaluation activities. Therefore, strong capacity-building efforts and government commitment to comprehensive monitoring and evaluation should be a prerequisite for such complex programs. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity building Capacity Development: Ownership | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/social-sector-program-0
Third Power Transmission (Sector) Project and Fourth Power Transmission (Sector) Project (Loans 1170/1245-THA) | Thailand | Energy | 2002-09-30 | From the viewpoint of ADB s operations as a whole, there is the need for flexibility in the timing of implementation of projects such as these, designed to fund an ongoing and evolving development program. This flexibility needs to recognize the desirability of project deferrals if the need arises. With transmission and distribution projects, this is generally possible because of their relatively short lead times. project cycle stage: Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Energy planning/management The sector lending approach has resulted in highly successful power projects. Clear ownership of the projects, matched with satisfactory institutional capacity of the executing agency, is crucial for achieving this kind of success in other developing member countries. project cycle stage: Design, Feasibility, Appraisal Implementation Lesson Topics: Modality: Lending modality Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Ownership | Project/Program Performance Evaluation Report (PPER) | Highly successful | http://www.adb.org/documents/third-power-transmission-sector-project-and-fourth-power-transmission-sector-project
Chonburi Water Supply Project | Thailand | Water and Other Urban Infrastructure and Services | 2002-03-15 | If the need to replace pipelines in the distribution system had been assessed indetail at the design stage, the nonrevenue water (NRW) program could have started earlier and hadgreater scope by using canceled loan funds rather than limited local funds. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design Sector Related Issues: Health and sanitation management Nonrevenue water (NRW) could not be sustainably reduced by repairing infrastructure alone.Institutional and managerial measures were required in tandem with therehabilitation works. As an institutional measure, a permanent operations unitwas established in the executing agency (Provincial Waterworks Authority) to carry out the program to reduce NRW and willcontinue the program even after the project. A proposed consultant should havebeen recruited to adopt a zoning approach. The executing agency's capacity and the cancelationof recruitment of consultants for NRW reduction should have been carefullyexamined during the project. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity development Sector Related Issues: Health and sanitation management Policy dialogue between ADB, the government, and the executing agency, and ADB technical assistance (TA) contributed to institutional development and policy reform, which strengthenedthe executing agency's operations, accelerated privatization of water supply operations, andestablished a regulatory body. project cycle stage: Appraisal Implementation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity development Sector Related Issues: Health and sanitation management Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Policy & Reform: Privatization The current water shortage in the project area could have been predicted earliersince demand for water is higher than Bang Phra Reservoir's (BPR's) capacity to supply it. Raw watersupply for the water treatment plant (WTPs) should have been carefully monitored and appropriatemeasures taken to prevent water shortages for WTPs and other water users inthe project area. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/chonburi-water-supply-project
Rural Enterprise Credit Project | Thailand | Finance | 2001-12-14 | Along with credit lines, guarantees (either full or partial) and other instrumentsconsistent with the stage of the development of the financial sector in theparticular country, should be considered. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Assessment of the factors that could affect availability of internal resources anddemand for credit should be undertaken during loan appraisal. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Project Design: Appraisal Development finance institutions should be required to hedge foreign exchangepositions, the expertise for which should be provided along with the ADB loan. ADB'sLIBOR-based lending modality facilitates hedging foreign exchange risks. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Foreign exchange Modality: Lending modality Project Management: Risks/Risk management Policy reforms, in addition to being covenanted, should also be linked andcoordinated with the reforms being promoted by other lending agencies. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Policy & Reform: Policy reforms/framework The anchor for relending and on-lending interest rates should be a variable localbenchmark that is transparently determined. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Financing Project Design: Project design | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/rural-enterprise-credit-project
Second Erawan Gas Transmission Project (Loan 1276-THA) | Thailand | Energy | 2001-06-30 | More thorough verification of bidding firms technical expertise and experience in operating in the particular physical environment is essential. The delay in constructing the onshore pipelines was due largely to the contractor s lack of experience in operating on soft marshy land. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Procurement Project Management: Project administration Sector Related Issues: Energy planning/management The only unrealized project component was the studies and training related to the executing agency's (EA's) corporate restructuring and institutional strengthening because they overlapped with the EA's various ongoing efforts. A thorough examination of past and ongoing efforts before deciding on new initiatives during project formulation is advisable. project cycle stage: Feasibility Lesson Topics: The project demonstrates, in a positive manner, that a strong sense of ownership by the government and the executing agency is crucial for the project s success. In this case, both the government and the executing agency viewed the project as a key step to achieve their long-term strategic and business goals. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Policy & Reform: Policy reforms/framework | Project/Program Performance Evaluation Report (PPER) | Highly successful | http://www.adb.org/documents/second-erawan-gas-transmission-project-loan-1276-tha
Second Rural Telecommunications Project (Loan 1239-THA) | Thailand | Information and Communication Technology | 2001-06-30 | Deregulation of the telecommunications sector and the introduction of a mobile telephone service has had a profound effect on rural telecommunications. The mobile telephone service industry has grown rapidly in the rural areas since the mid-1990s as prices of mobile telephone handsets fell. Thus, mobile telephones offer an alternate mode of voice communication in rural areas and compete with the executing agency's fixed-line service. Mobile telephone companies have demonstrated that they are willing and able to provide telephone services in rural areas and at a lower cost than the EA. In the future, rural telecommunications should be left to the least-cost provider. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Reform The scope for making the rural telephone service more profitable is limited as cost recovery for basic rural telephone service will likely be only partial and some form of subsidy will be necessary. However, cross-subsidization by other consumers is not efficient; implicit cross-subsidies also make privatization more difficult and put rural telephone operations at risk during cost reduction exercises. If the public sector needs to provide rural telecommunications, it would be preferable for it to provide an explicit government subsidy to the company providing the rural telephone service. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Private sector Sector Related Issues: Rural development Policy & Reform: Privatization | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/second-rural-telecommunications-project-loan-1239-tha
Privatization in the Power, Gas and Water Sectors in the Kingdom of Thailand | Thailand | Multisector | 1999-05-31 | Design of future TA studies should (i) ensure that the study rationale is appropriate so that TORs do not overlook financial implications and important areas for assessment, and (ii) address more closely the intended objectives for counterpart staff to assure effective transfer of technical knowledge. In addition, where advisory study recommendations are likely to face skepticism or resistance (a) allow adequate time for processing comments and reaching a consensus on consultant recommendations, (b) encourage consultants to allocate initial time to presentations on concepts and issues that may not be understood or accepted, (c) include study tours for involved government officials and employee representatives to see how systems are working in other countries, and (d) strengthen the mechanism for bringing study recommendations to the attention of government to ensure follow-up directives. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Management: Consultants | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/privatization-power-gas-and-water-sectors-kingdom-thailand
Bongkot Gas Transmission Project (Loan 1169-THA) | Thailand | Energy | 1997-07-31 | ADB missed an opportunity to build upon the project's efforts to promote environmentally sound development of hydrocarbon resources by not following up on the results of one of the EA's TA on Environmental Standards and Regulations when it processed the Second Erawan Gas Transmission Project in 1993. This new pipeline project offered ADB an opportunity to support the implementation of draft environmental regulations either through further TA support or through targeted loan covenants. This experience underscores the importance of advisory TAs as more than simply add-ons to projects, but as key elements in project design and as useful tools to establish the continuity of institution-strengthening objectives across projects. project cycle stage: Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Sustainability Loan Agreement: Covenants Modality: Cluster operations Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity building Sector Related Issues: Energy planning/management Policy & Reform: Policy reforms/framework TA success demonstrates the importance of (i) designing a realistic TA based on a thorough review of the EA's staff resources and ability to implement study recommendations; (ii) employing a logical framework, which would have helped identify steps leading to attainment of objectives, e.g., adoption of national standards; and (iii) providing for closer ADB supervision, particularly with respect to the practical usefulness of the final product. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Project Management: Project supervision Capacity Development: Capacity assessment The success of the project demonstrates the importance of (i) sound project formulation and a high degree of ownership by the EA; (ii) engaging qualified consultants and contractors in areas where considerable specialization and experience are required; and (iii) close attention to prior lessons learned, specifically the certification of gas reserves by third party experts to minimize project risk. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Ownership | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/bongkot-gas-transmission-project-loan-1169-tha
Sixth Power Distribution (Sector Loan) Project (Loan 903-THA) | Thailand | Energy | 1996-12-31 | As long as ADB is satisfied with the overall sector development plan, major sector policies, and the institutional strength of the executing agencies concerned, the use of a sector loan approach should be positively considered. project cycle stage: Appraisal Lesson Topics: Modality: Lending modality Project Management: Executing/Implementing agencies Capacity Development: Institutional analysis Sector Related Issues: Energy planning/management Policy & Reform: Policy reforms/framework Institutional building is a continuous process and can be achieved gradually over time. As demonstrated by ADB's assistance to the executing agency in establishing computerized systems, a sustained and systematic approach in institutional capacity building will be effective. project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Cluster operations Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/sixth-power-distribution-project-903-THA
Shelter Sector Project (Loan 736-THA) | Thailand |  | 1995-09-30 | Changes in project scope, particularly those affecting the underlying concept during implementation must be clearly documented, and the implications of such changes for the project beneficiaries, as well as justification of such changes, should be analyzed. This is particularly important to ascertain the relevance of the revised project, and for project benefit monitoring and evaluation. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Project Design: Project design Project experience highlights the importance of government agencies involved with low-income housing to be fully aware of the consumer preferences of potential buyers/tenants. The planning and design function must be supported by comprehensive market research activities which monitor changes in the preferences, financial standing, and affordability of the buyers. In particular, income and price elasticities for low-income housing units need to be estimated carefully, in relation to alternative private sector options which may be offered. It is also necessary to rationalize the social objectives of a public sector housing development program vis-a-vis the commercial viability of such programs. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Market analysis Project Management: Executing/Implementing agencies Sector Related Issues: Private sector Sector Related Issues: Urban sector/development | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/shelter-sector-project-loan-736-tha
Strengthening Major Public Investments: Technical Assistance Completion Report | Timor-Leste | Public sector management | 2015-09-01 | TA (technical assistance) can be useful, relevant and effective in rapidly changing institutional settings provided that ADB is able to respond with a reasonable degree of flexibility in implementation. Changed outputs can contribute equally to the outcome in many cases, particularly when demand driven. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-major-public-investments-tcr
Microfinance Development Project | Timor-Leste | Finance | 2005-10-14 | A considerable amount of technical assistance is needed over an extended period to build a strong and sustainable microfinance bank (MFB) in a post-conflict situation similar to Timor-Leste. project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Cluster operations Modality: Technical Assistance Country Context: Conflict/Post-conflict An appropriate policy, legal, and regulatory framework should be in place before sustainable microfinance bank (MFB) operations can begin. In post-conflict countries, developing financial infrastructure and viable local institutions takes much longer than in normal situations. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Capacity Development: Capacity development Country Context: Conflict/Post-conflict Policy & Reform: Policy reforms/framework Establishing a regulated microfinance bank (MFB) through grants is a sound strategy. However, it is important to have a very clear road map for an ownership structure from the start. Further, the local staff and institutional capacity should not be overestimated because, in the case of Timor-Leste, a large number of qualified Timorese left the country because of civil unrest and the project and the country faced a severe shortage of skilled labor in all sectors, including microfinance. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Lending modality Capacity Development: Capacity assessment Capacity Development: Ownership Country Context: Conflict/Post-conflict In post-conflict countries such as Timor-Leste, microfinance is an effective development tool for poverty reduction. It enables poor and conflict-affected communities to improve economic security quickly. The capacity of poor households to borrow and save should not be underestimated, even in the most difficult environments. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financing Capacity Development: Capacity assessment Country Context: Conflict/Post-conflict To establish a successful microfinance bank, it is essential to recruit a qualified practical banker (rather than a general microfinance specialist) with extensive field experience in managing similar banks. In the case of Instituicao de Microfinancas de Timor-Leste (IMFTL), it is one of the success factors. project cycle stage: Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Capacity Development: Human resources management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/microfinance-development-project
Water Supply and Sanitation Rehabilitation Projects Phase I and Phase II | Timor-Leste | Agriculture, Natural Resources, and Rural Development | 2004-10-15 | A strong partnership between the project management unit (PMU) and ADB, coupled with close monitoring of the projects, was effective in solving problems. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project management Capacity Development: Partnerships A strong sector organization and competent staff are needed to implement and sustain water supply and sanitation (WS&S) sector development plans and projects. For effective human resource capacity building, the organization must be well structured and function properly. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Capacity Development: Capacity building Capacity Development: Human resources management Sector Related Issues: Health and sanitation management Flexibility is required when designing sector programs in a post-conflict country such as Timor-Leste. Implementing projects takes longer when the institutional capacities are uncertain. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Design: Project design Capacity Development: Capacity assessment Country Context: Conflict/Post-conflict Non-government organizations (NGOs) can be effective partners of the government and the communities in implementing community-managed water supply and sanitation (WS&S) projects by providing technical and institutional assistance. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Capacity Development: Partnerships Sector Related Issues: Health and sanitation management Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Community approach Officials at the national, district, and community levels should become involved early in projects, and should be encouraged to give people a sense of ownership and responsibility for the success and sustainability of projects. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Capacity Development: Ownership Country Context: Decentralization Sanitation is a necessary component along with health and hygiene education for maximizing health benefits from water supply projects. However, sanitation is not given enough attention, as the low coverage and small number of projectsimplemented demonstrated. project cycle stage: Feasibility Lesson Topics: Project Design: Problem identification Project Design: Project design Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/water-supply-and-sanitation-rehabilitation-projects-phase-i-and-phase-ii
Hera Port Fisheries Facilities Rehabilitation Project | Timor-Leste | Agriculture, Natural Resources, and Rural Development | 2004-07-15 | In hindsight, if ADB had supported early work related to formulating fisheries legislation, Hera port might today be a very busy place experiencing rapid growth. But, legislation should not be a rushed attempt as ownership by government is key to adoption of any legislation, and an elected government was not in place at the start of the project. A more pragmatic justification at appraisal for Hera port's upgrade, such as the justification for rehabilitation of public roads or electricity facilities, being more in line with emergency rehabilitation, would probably have been more correct. As Hera port is Timor-Leste's only fishing port, it will eventually be used, but not necessarily with the vessel types or numbers envisaged at appraisal. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Project Design: Appraisal Capacity Development: Ownership Country Context: Emergency Sector Related Issues: Rural development Sector Related Issues: Transport planning Policy & Reform: Policy reforms/framework | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/hera-port-fisheries-facilities-rehabilitation-project-timor-leste-pcr
Integrated Urban Development Sector Project: Completion Report | Tonga | Transport, Water and Other Urban Infrastructure and Services | 2015-09-18 | One of the significant lessons from the project is the positive impact of early fielding of PIA (project implementation assistance) consultants. During project preparation, the capacity of the executing agency, MOW (Ministry of Works), was assessed as insufficient, particularly for detailed design, construction supervision, and overall project planning, monitoring, and reporting. The project design therefore provided for PIA consultants to assist and support MOW. Recognizing the importance of the PIA team and its own unfamiliarity with ADB procedures for selecting consultants, MOW requested advance action and ADB's assistance for the recruitment. This is believed to have significantly reduced the risk of delays in recruiting the PIA consultants - which typically would result in slow project start-up and late implementation - and allowed for fielding of consultants within weeks of grant effectiveness. The project was implemented largely on time and on budget. project cycle stage: Design, Implementation Under a sector modality, core subprojects should only be included at project appraisal if detailed feasibility studies have shown them to be implementable. Under this grant project, a core subproject (Sopu drainage channel) had to be dropped in the implementation phase when detailed design and feasibility studies revealed huge and unfeasible land acquisition needs. project cycle stage: Design, Feasibility, Appraisal, Implementation ADB provided guidance and support throughout the project with frequent project review missions. Regular communication between MOW (Ministry of Works), PIA (project implementation assistance) consultants, and ADB allowed for continuous assessment of the direction toward attainment of the project's immediate objectives; review of institutional, administrative, organizational, technical, environmental, social, economic, and financial aspects of the project; assessment of the need to restructure or reformulate the project; and updates to the project's design and monitoring framework when necessary. Such regular tripartite interaction also allowed for good planning and implementation of additional, non-core subprojects to realize the benefits of savings from other project components, and also achieve completion of additional works within the fund utilization period. Although MOW went through a reform process during project implementation, close coordination between it and ADB prevented any major disruption to the project. project cycle stage: Appraisal, Implementation For projects where machinery and equipment are to be purchased from project funding, it should be ascertained during project design that the executing agency is making sufficient allocations to the operational budget in the year targeted for the procurement of the equipment, and the years to follow. Otherwise, the equipment is not used effectively for lack of operational budget in the first year. project cycle stage: Design, Implementation, Operation Allowing some NCB (national competitive bidding) packages in any project gives an opportunity to engage and test the ability of reputable local contractors. In this project it was noted that the local contractors for smaller NCB packages offered some very competitive rates and, with close supervision from the project team, were able to complete and deliver components in a timely manner. However, not every local contractor may be in the best position to handle larger ICB (international competitive bidding) contracts, as was seen in the poor performance displayed under an ICB contract won by a local contractor in joint venture with an overseas partner. The PMU (project management unit) acted swiftly to resolve the issues caused by the poor performance, and all activities under the component could be completed within the grant implementation period. project cycle stage: Implementation Proper engagement and communication with stakeholders is vital to ensure that the rationale and the objectives of the project are fully understood, and this helps during project implementation by speeding up important decisions. The good interaction between MOW (Ministry of Works), the PSC (project steering committee), and the PIA (project implementation assistance) consultants proved highly beneficial in completing this project on time. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/ton-integrated-urban-devt-sector-project-pcr
Strengthening Public Financial Management Program | Tonga | Public Sector Management | 2014-08-01 | Single-tranche program. A single-tranche program operation can encourage up-front delivery of important reforms, particularly if launched as part of a programmatic, multiyear, policy reform effort where ongoing reforms are supported by several partners. This ensures reform sustainability. Limited but meaningful policy actions. In a single-tranche operation, those reforms selected for development-partner support should be few in number but large in potential impact. Technical assistance support should be available at program commencement. They should be clearly defined, widely owned, and have time-bound milestones that trigger financial support, either by ADB or by other partners supporting the government-led reform effort. A single, government-led policy matrix can enhance coordination and collaboration amongst development partners. The Joint Policy Reform Matrix has evolved into a highly consultative process around which development partners coordinate their budget support and technical assistance for reform. This process has helped the partners speak with one voice to the government and has created a situation in which line ministries actively compete to have reforms listed in the Joint Policy Reform Matrix. The Pacific Islands Forum Secretariat has identified the Joint Policy Reform Matrix as an international best practice in supporting government-led reform. Reforming large state-owned enterprises and complex regulatory reform. The impact of political sensitivities need to be factored into reform programs for major SOEs, particularly public utilities. Moreover, there may not be much legitimate appetite for foreign investment into distressed state-owned enterprises. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/tonga-strengthening-public-financial-management-program-pcr
Outer Islands Agriculture Development in Tonga (Loan 1412-TON) | Tonga | Agriculture, Natural Resources, and Rural Development | 2006-07-31 | 1. As restructuring took much longer than anticipated, long-term resident consultants would have been more effective in maintaining progress than intermittent inputs. Since capacity constraints are significant in microstates, ADB must be sensitive to the need for ongoing support at times of significant change if it plans to encourage implementing agency restructuring. [Main text, paras. 61, 95] project cycle stage: Implementation Lesson Topics: Project Management: Consultants Capacity Development: Capacity assessment Capacity Development: Capacity building Policy & Reform: Reform 2. The scale of a technical assistance (TA) must recognize the size and strength of the recipient institution, and ensure general political support for the TA. Without such support, successful institutional change is impossible. The experience with the Tonga Trade TA exemplifies the difficulties of applying large-scale assistance to small and new organizations. Tonga Trade did not have the staff or financial resources to use the TA effectively, especially the training component, when it was provided. In addition, the continuing understaffing of Tonga Trade, as well as its subsequent changes in orientation, suggests that support for the organization s direction and role as specified in the RRP was not universal at higher levels of Government. [Main text, paras. 94, 96] project cycle stage: Design Appraisal Implementation Lesson Topics: Modality: Technical Assistance Project Management: Executing/Implementing agencies Capacity Development: Capacity development Capacity Development: Ownership 3. When using commercially orientated organizations to achieve non-commercial objectives, ADB and the government should acknowledge possible conflicts and gear financial arrangements to realistic assessments of commercial outcomes. The telecommunications component was implemented efficiently, and has improved the target population s communications with the outside world. However, this phone system will be a cash drain to Tonga Telecommunications Corporation (TTC) for some time. Although TTC has contributed to the achievement of important development goals, its weak financial performance might conflict with its new corporate status. The new telephone system is connected only tenuously with the project objectives to increase agriculture productivity on the outer islands, reduce income disparities between households on different island groups, and stimulate agriculture exports. [Main text, paras. 73, 98] project cycle stage: Design, Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Project Management: Executing/Implementing agencies Beneficiaries have appreciated the provision of agriculture access roads which have produced social and economic benefits. The provision of roads might be the most efficient way to stimulate economic growth in areas with agricultural land not served by roads. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Roading Sector Related Issues: Rural development The goal of privatizing within a short period was unrealistic. It did not reflect the limited size and strength of the agriculture export sector, which was expected to assume the major role in financing and directing the organization to be privatized. The expectations of the private sector far exceeded its ability to deliver. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Market analysis Sector Related Issues: Private sector Policy & Reform: Privatization | Project/Program Performance Evaluation Report (PPER) | Unsuccessful | http://www.adb.org/documents/outer-islands-agriculture-development-tonga-loan-1412-ton
Economic and Public Sector Reform Program | Tonga |  | 2005-09-15 | Especially in situations where the government's capacity is poor, the design of the reform measures should be kept simple and extensive conditionalities should be avoided. The timeframe of the reform program should be realistic in balancing the government's need to rapidly establish a track record in relation to the external funding community and the broader public on the one hand, and the program's technical and political feasibility on the other. Moreover, providing sufficient resources for complementary institutionalchange and capacity building is indispensable. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Program Capacity Development: Capacity assessment Capacity Development: Capacity building Policy & Reform: Reform Measures that promise relatively rapid progress should be prioritized to facilitateeffective communication of success stories to the public. Effective communication of the reformprogram's rationale, objectives, and achievements is essential for maintaining public support,especially where an institutionalized participation mechanism does not exist. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Program Country Context: Prioritization Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Participatory approach The gap between domestic capabilities and skills requirements may be widened by theimportation of inappropriate techniques and technologies, so that reforms may not provedurable. At the same time, the involvement of strong, committed local consultants caneffectively help expand the government's capacities to manage and coordinate the reformprocess. project cycle stage: Implementation Lesson Topics: Modality: Program Project Management: Consultants Capacity Development: Capacity assessment Capacity Development: Capacity development Capacity Development: Technology/Technology transfer Policy & Reform: Reform The program has shown that strong government ownership of and commitment to aprogram with well-focused conditions can effectively support the reform process. By contrast,the program has also demonstrated the vulnerability of reform programs to the politicalenvironment, especially in conflict situations. This suggests that the level of commitment to aprogram loan is determined not only by the commitment of the government in power, but also byits ability to manage vested interests that wish to maintain the status quo (reform resistors) andthe overall political aspects of the reforms (for instance, displaced workers). Therefore, givensuch situations, carefully assessing and closely monitoring the political environment isimportant, including all supporting and resisting forces and the risks of a politically motivated interruption of the reform process, as well as assessing the capacity of the civil service and itsability to continue a reform program despite political upheavals. Extensive consultations amongpolitical factions and the broader public, including at the provincial level, are indispensable toensuring broadly based support for any reform program. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Program Monitoring & Evaluation: Monitoring and evaluation Project Management: Risks/Risk management Capacity Development: Capacity assessment Capacity Development: Ownership Country Context: Conflict/Post-conflict Policy & Reform: Information dissemination/Public awareness Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/economic-and-public-sector-reform-program
Strengthened Public Financial Management Program | Tuvalu | Public sector management | 2014-08-01 | Ownership and continuity. Government leadership was strong in formulating the policy reform matrix, in coordinating policy dialogue, in mobilizing external budget support, and in formulating the program. Program reforms were championed by the Finance Minister, the permanent secretaries for Cabinet and Ministry of Finance and Economic Development, and the Australian-funded budget advisor. Their support was crucial to ensure that reforms were complete before the date that ADB's Board of Directors was to approve the grant. Follow-through on agreed reforms was frustrated, however, by the untimely death of the Finance Minister, three changes in finance secretary, the departure in 2013 of the Australian-funded budget advisor, and the 2013 change in government. This points to the need to ensure bipartisan support for reforms, so that their implementation is not adversely affected by changes in government or key officials. A communications strategy should be included as part of the program to create shared understanding and ownership of the reforms. A single, government-led, policy matrix can enhance coordination and collaboration amongst development partners. The policy reform matrix has evolved into a highly consultative process around which development partners coordinate their budget support and technical assistance for reform. This process has helped the partners speak with one voice to the government and has created a situation in which line ministries actively compete to have reforms listed in the policy reform matrix. Medium-term policy engagement. While a single-tranche modality was selected for ADB's operation, this was embedded in a programmatic, multiyear, policy reform effort with ongoing reforms contained in the policy reform matrix supported by several partners. The reforms selected were few in number but large in potential impact. They were clearly defined, widely owned, and had time-bound milestones that triggered financial and technical support, either by ADB or by other partners supporting the government-led reform effort. Furthermore, Government and partners have moved towards adoption of a programmatic approach to budget support to operationalize the coordinated, multi-donor, medium-term, programmatic dialogue already underway. Complementary TA support. Capacity-building technical assistance support should be closely linked to policy reform matrix implementation. Capacity constraints hamper the government's ability to follow through on agreed reforms. Even though the program reform agenda was carefully prioritized and focused, the government had other policy reform matrix reforms and routine government administrative matters to attend to. Three rounds of supplementary financing were provided for the Institutional Strengthening of the Ministry of Finance and Economic Development Technical Assistance to help authorities follow up on agreed reforms. In retrospect, programing technical assistance resources to assist the authorities define, secure approval, and implement agreed reforms at the start would have been more efficient. Public enterprise reforms. In small economies like Tuvalu, there will be constraints on efforts to sell state assets and encourage new private investment as economies and markets are simply too small to attract sufficient private interest. Pragmatic and flexible approaches, likely involving some measure of experimentation, need to be adopted in order to ensure that services are not disrupted, that losses are curtailed, and that performance improvements are realized. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/tuvalu-strengthened-public-financial-management-program-pcr
Improved Financial Management Program | Tuvalu | Public Sector Management | 2012-01-10 | 1. The scope of the program needs to be kept as simple as possible to reflect the country's capacity. [Main text, para. 30] project cycle stage: Lesson Topics: 2. Policy conditions for the release of tranches should be appropriate and achievable by the government and executing agency. In the case of Tuvalu, the requirement that Parliament adopt the regulatory framework for banking supervision as a condition for tranche release was out of the direct control of the government, and therefore constitutes a high risk to program success. [Main text, para. 30] project cycle stage: Lesson Topics: 3. Conditions need to be achievable and realistic so that they can be implemented in a timely manner. The requirement to have a legal framework in place for the supervision and monitoring of banking activities, compatible with the Basel Principles of Banking and Supervision, proved challenging and potentially too ambitious for such an administration as small as Tuvalu yet this is an important element if there is to be private sector involvement in banking in Tuvalu. The country has limited technical capacity to implement such a legal framework and continuing assistance will be required. [Main text, para. 30] project cycle stage: Lesson Topics: 4. Consultants may need to spend more time in country (depending on the technicality of the conditions) to deal with issues as they arise and support the timely delivery of outputs and outcomes. [Main text, para. 30] project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/improved-financial-management-program-pcr
Maritime Training Project | Tuvalu | Education | 2011-09-01 | A key lesson from this project comes from ADB's underestimation of the potential effects of the weakness of implementation capacity in Tuvalu. Professional services are limited domestically and the logistic problems are significant. A realistic and comprehensive assessment of capacity should have been conducted during project preparation. Transfer of skills alone may not be sufficient to overcome this problem because of the difficulty in identifying qualified counterparts and the fact that those who qualify may often not be in a position to commit all of their time to the project. In such cases, project activities need to be outsourced. This approach requires close oversight and monitoring. Close involvement of ADB staff in project implementation is also essential and the resources for this need to be provided. Fundamental changes in procurement methods may offer a procedural and administrative solution when a tendering process is stalled because of lack of competition or bids above the available budget. But these changes can also cause implementation problems, especially when the implementation capacity of the recipient is weak. Seafaring is one of the few non-government opportunities for income for young Tuvaluans. It has significant effects on the wealth and well-being of a large section of the population, including the poor. Yet this project did not get the support and attention from the government that its strategic importance warranted and required. This was mainly due to a high turnover of government and project staff, which compounded the weak implementing capacity. In addition, consideration and planning of similar future projects should note that accountability and governance frameworks are poorly developed in small Pacific island developing member countries such as Tuvalu. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/maritime-training-project-0
Island Development Program | Tuvalu |  | 2003-01-15 | Some in government feel that the success of the Tuvalu Trust Fund was influenced by the technical assistance (TA) that supported its corporate governance. This TA includes funding of the Tuvalu Trust Fund Advisory Committee (TTFAC) and the Board members, including representatives of the governments of Australia, New Zealand, and the United Kingdom. The logical extension of this view is that TA and advice from external parties are essential to the long-term success of the Falekaupule Trust Fund (FTF). Capacity constraints are significant in the microstates, so this has implications for ADB's Pacific strategy to encourage the use of trust funds as a tool for development assistance. Long-term advice isneeded to strengthen governance and maximize the likelihood of success in the use of trust funds. project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Modality: Technical Assistance Capacity Development: Capacity assessment Capacity Development: Capacity development Policy & Reform: Policy reforms/framework The need for counterpart staff has often been identified as crucial forthe success of projects. Island Development Program (IDP) was handicapped by a lack of staff in Ministry of Home Affairs and Rural Development (MHARD), the executing agency, because many staff were overseas for long-term training. Often, adequate transfer ofskills was not possible because of the difficulty in identifying counterparts, and competingdemands for their time. Complicating this problem was the Ministry's ability to retain staffbecause of a perceived lack of prestige. These issues should be considered before initiatingfuture projects, or stronger constraints should be placed on the executing agencies to ensurethe availability of adequate counterpart staff. But it is recognized that every project will havefactors beyond the control of its designers. project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Loan Agreement: Covenants Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Human resources management Capacity Development: Technology/Technology transfer Tranche conditions for fund release could be more tightly focusedto address program objectives. Conditions such as improving government paymentprocedures, introduction of output budgeting, and corporatizing the maritime training school arenot directly relevant to the loan's objectives. Fewer and more verifiable conditions that aredirectly related to the loan's objectives would bring more long-term benefits to the islandcommunities. An example of such a condition is a requirement that the government maintainsits financial support to the local governments after introduction of the Falekaupule Trust Fund (FTF). project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Loan Agreement: Covenants Modality: Program Country Context: Decentralization Translation of crucial documents is essential when dealing with island communities.Budgets should be provided for translation, through loans or technical assistance (TA). Allowances should be made fordelays associated with translation. The language problem can partly explain the disputes aboutdistribution. The Falekaupule Trust Fund (FTF) Deed was written in English, without translation. This issue was resolvedat the Island Leaders Conference, but it was agreed that it should be reviewed in 2005 afteranother 3 years of operation. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Modality: Technical Assistance | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/island-development-program
CAREC Corridor 2 Road Investment Program - Tranche 1: Completion Report | Uzbekistan | Transport | 2015-09-22 | Integrated projects planning for economic corridors and regional economic impacts. The newly built 50 km section of the A380 highway is located along CAREC (Central Asia Regional Economic Cooperation) Corridor 2 which has two border-crossing points (i) Termez at the Afghanistan border and (ii) Daut-ata at the Kazakhstan border. The remaining sections of the A380 highway are being improved under ongoing projects and future projects planned by the government. Due to better road conditions and increased road capacity, the travel time on the project road has been reduced by over 60%, from 90 minutes to only 35 minutes and overall on the corridor it has impacted 20% travel time reduction and annual average daily traffic increase five folds within last 5 years. Future projects should also be planned similarly for integrated road sections on a corridor to achieve optimum regional economic impacts, instead of developing only isolated part of a corridor. project cycle stage: Design, Completion Realistic estimation of project and contract duration. In future, project schedules should carefully take into account (a) actual construction period available in a year considering the potential inclement weather conditions; (b) delays in contractor mobilization; (c) longer-than- expected time spent by government agencies in procurement matters due to their limited capacity or lengthy internal approval procedures; and (d) possible flaws in the initial designs that may require additional surveys and increase the scope of the contract. Existing practice of about 18 months of construction period needs to be reviewed by the government considering that most of the completed and ongoing projects had to be extended in view of the above-mentioned issues. project cycle stage: Design, Feasibility Maximizing gender benefits. The gender training subcomponent, which benefited from the synergy with RETA (regional technical assistance) 7563 grant, showed overwhelmingly successful results achieving extensive gender benefits. This included improved community knowledge of basic health, sanitation, and reproductive health by providing facilities and improving mobility; and group formation and development of livelihood skills for local women through training a selected group of Sarimoy women in business skills development. These trainings improved their knowledge of taxation and business planning, which increased their self-confidence and capability in both their public and private lives. Considering the enormous benefits, future projects should include gender training components and small entrepreneur or business loan and mentorship programs, through which microloans and financial and business management training could be provided to local communities. project cycle stage: Implementation, Operation Uzavtoyul to implement RAMS (road asset management system) directly. Future RAMS components should be implemented directly by the end user Uzavtoyul rather than through the PMU (project management unit) to ensure better coordination between the consultant and the end user. This implementation strategy will maximize long-term sustainability and provide the end user with full planning and implementation control and ownership of the outcomes. project cycle stage: Design, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/carec-corridor-2-road-investment-program-t1-pcr
CAREC Regional Road Project: Completion Report | Uzbekistan | Transport | 2015-09-21 | Need for including all related works in the scope of work for civil works contractors. For the road development component, earthworks and the construction of the subbase were excluded from scope of work of the international contractors. This reduced the efficiency of the construction works, because the national contractors were unable to complete works of acceptable quality as designed and it took considerable time to rectify the defects. These works should have been integrated within the overall scope of the civil works. project cycle stage: Design, Implementation Need for timely taking over of completed project sections by the government. At completion, the taking over of section 1 by Uzavtoyul was delayed due to administrative problems within the government. This contributed to poor maintenance after the defects liability period. This issue was resolved in 2014. Future taking over of completed road sections needs to be conducted in a timely manner by the government. project cycle stage: Completion, Operation Need for careful assessment of project management and construction supervision consultant's qualification. The PMCS (project management and construction supervision) consultant's performance was found to be generally satisfactory. However, the team leader was replaced three times during implementation, which affected the progress of civil works. In future, CVs (curriculum vitae) of the candidates should be assessed carefully to ensure highly qualified and experienced experts are selected, with a preference for permanent staff of the consulting firm. project cycle stage: Implementation Need for minimizing staff turnover in the executing agency during implementation. The PIU's (project implementation unit's) project director was changed frequently affecting the project management efficiency. Such frequent changes of the project director should be minimized. project cycle stage: Implementation Higher ADB financing for civil works components. The project completion review mission noted that ADB financing for these components was only 2.8% of the total civil works costs, against 14.9% at appraisal. This is rather marginal compared to the resources spent administering the project. For efficient use of ADB resources, ADB financing of civil works should be at least 50% of project costs for projects of this size. It is noted that for other components, ADB financing was 100%, which helped to resolve the disputes efficiently. project cycle stage: Design, Completion Regular assignment of the PIU's (project implementation unit's) representatives at the project sites. For future projects, it is recommended that the PIU assign a representative to the project site to monitor the civil works progress closely with the construction supervision consultants, which will help the PIU identify issues at early stage and take prompt actions for resolution. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/uzb-carec-regional-road-project-pcr
Second Small and Microfinance Development Project: Completion Report | Uzbekistan | Finance | 2015-09-18 | Promoting the success of MSE (micro and small enterprise) operations and helping PCBs (participating commercial banks) fulfill their greater developmental functions would address existing constraints. Access to finance is just one constraint hindering the development of MSEs. In a 2003 survey of SMEs (in Uzbekistan, the International Finance Corporation identified some of the negative factors hindering the operation of enterprises. These include administrative procedures, currency conversion, access to finance, taxation, and import and export restrictions. More effective consultation and dialogue among various market participants and government agencies regarding proposed reforms can limit inconsistencies between government policies and the formulation and implementation of rules and regulations. project cycle stage: Implementation, Operation Monitoring and analysis of the MSE (micro and small enterprise) sector would benefit from estimates of the credit gap to confirm additionality of ADB FILs (financial intermediation loans). This could also help ensure that private sector funds are not displaced given the features of sovereign loans. How FILs catalyze the entry of new funds into the market needs to be better documented, and FILs' ability to move participants to more market-based finance needs to be improved. project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/uzb-second-small-microfinance-devt-project-pcr
Amu Zang Irrigation Rehabilitation Project: Completion Report | Uzbekistan | Agriculture, Natural Resources, and Rural Development | 2015-06-30 | Preparation and approval of a national feasibility study after loan approval substantially delays loan effectiveness. project cycle stage: Feasibility The price of large contracts, particularly those involving heavy equipment expressed in different foreign currencies, may cause escalation of US dollar (loan currency) equivalent price and result in significant cost overruns. project cycle stage: Appraisal Policy reforms are difficult to implement when (a) packaged with an investment project; (b) overambitious in terms of scope and time frame; and (c) developed without due consideration of general government policies, people's capacity, and the historic context. project cycle stage: Design, Implementation The provision of consultant input and skill mix, and TA duration should match the scope of work. project cycle stage: Implementation Duplication of the loan and the related TA activities creates difficulties during implementation and should be avoided. project cycle stage: Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/amu-zang-irrigation-rehabilitation-project-pcr
Uzbekistan: Small and Microfinance Development Project | Uzbekistan | Finance | 2012-12-27 | 1. Poverty intervention projects such as the project need to be clear on the mechanisms for ensuring participation of the poor. [Main text, para. 32(i)] project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Industry and Trade Methodologies/Approaches: Participatory approach 2. The definition of microfinance at appraisal in the context of Uzbekistan should have been given upfront to provide overall guidance in the project design. [Main text, para. 32(ii)] project cycle stage: Design Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Project design Sector Related Issues: Industry and Trade 3. The use of credit lines is not adequate in meeting long-term development needs and constraints of the sector. [Main text, para. 32(iii)] project cycle stage: Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Industry and Trade 4. The selection of appropriate institutions is crucial in targeting poor and low-income households. Commercial banks are constrained to reach large numbers of poor households due to inherent rigidities of bank regulations and policies. [Main text, para. 32(iv)] project cycle stage: Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Sector Related Issues: Industry and Trade 5. Capacity building is needed in enabling institutions to reach the poor with demand driven products and services. [Main text, para. 32(v)] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Financing Capacity Development: Capacity building Sector Related Issues: Industry and Trade | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/uzbekistan-small-and-microfinance-development-project
Uzbekistan: Urban Water Supply Project | Uzbekistan | Water and Other Urban Infrastructure and Services | 2012-12-10 | If the executing agency's limited relevant experience of project design and implementation is known at the outset at the project design stage (i.e., as confirmed in the risk assessment), it is necessary to design appropriate mitigation strategies. These could include the following: (i) design smaller pilot projects to gain experience before larger projects are tackled; or (ii) make significant consultant support available in the early stages of implementation to strengthen capacity and ensure timely implementation. [Main text, para. 32] project cycle stage: Design Lesson Topics: | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/uzbekistan-urban-water-supply-project
Information and Communications Technology in Basic Education Project | Uzbekistan | Education, Information and communication technology | 2012-11-01 | Lessons learnt include the following: (i) The cluster leader school (CLS) model supported by a decentralized training cascade is an effective model for delivering continuous professional development training. (ii) E-learning is as important for teachers as it is for their students. Information and communications technology (ICT) is not a translation of textbook materials into electronic textbooks, but requires pedagogical skill in identifying how the technology strengthens student understanding of core concepts and encourages self-directed learning. It is a transition from teacher-centered to student-centered pedagogy. It also requires more creative e-learning materials. (iii) Assessment of the procurement capacity of the executing agency and ensuring development of adequate capacity of the PIU and executing agency would help implementation of the project and ensure efficient procurement and consultant engagement. (iv) The executing agency needs to monitor the project more closely. Without timely monitoring and evaluation, an opportunity to demonstrate improved sector performance was missed. Early mobilization of consultants is necessary for effective implementation of the project. Consideration could be given to a short, results-based consulancy to assist the executing agency and project implementation unit (PIU) agree on the baseline, commence procurement, and clarify any implementation issues, as well as short- to medium-term consultancies to implement specific project components. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/ict-basic-education-project-pcr
Woman and Child Health Development Project | Uzbekistan | Health | 2012-11-01 | The project illustrates the importance of (i) strong commitment by the government, (ii) close collaboration among development partners, and (iii) prompt response to changing client needs during implementation. The leadership provided by MOH and the project coordinator was a key to the project's achievements. The project was not a stand-alone WCH project, but a part of broader health sector reforms. Strong collaboration among partners (i.e., technical inputs were provided by the World Bank, United States Agency for International Development, World Health Organization, UNICEF, and the United Nations Population Fund) and responsiveness to actual needs was an important contributor to the success of the various programs. The knowledge and working practice of health professionals improved from the outset. Because other partners addressed some project activities, it was possible to reallocate resources and expand geographical coverage. This improved project achievement and increased the likelihood of sustainability. The project was somewhat overambitious in setting the timelines for achieving the reforms. The government was fully committed to the reforms, but progress depended on the progress of other projects. In this project, two loan covenants were partly complied with at the project completion due their complexity. If reforms are significant, it is useful to consider a phased approach, so that interim achievements can be captured within the project timeframe. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/woman-child-health-development-project-pcr
Uzbekistan: Second Textbook Development Project | Uzbekistan | Education | 2012-01-01 | 1. This validation emphasizes that institutional capacity building is critical in monitoring and evaluating the project. Policymakers need to be able to monitor the results and impact of the intervention in order to track the success of a reform project. ADB should continue working with the government to support the education sector reforms in Uzbekistan. [Main text, para. 24] project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Impact evaluation Capacity Development: Capacity development Sector Related Issues: Education Policy & Reform: Policy reforms/framework Policy & Reform: Reform 2. Another lesson from this project is that development of textbooks and related teaching aids needs to be meticulously synchronized with the new curriculum development in order to avoid any delays and lost time. [Main text, para. 24] project cycle stage: Implementation Lesson Topics: Project Management: Project supervision Sector Related Issues: Education | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/uzbekistan-second-textbook-development-project
Kashkadarya and Navoi Rural Water Supply and Sanitation Sector Project | Uzbekistan | Agriculture, natural resources and rural development | 2011-12-01 | Significant inflation during project implementation affected the project cost. The total project cost could have been less than that actually spent, if the initial 2-year delay in implementation had been avoided. Action should have been taken by all the parties concerned including ADB to ensure that the government was taking timely action. The project management unit (PMU) and project implementation units (PIUs) should be staffed and consultants recruited in a timely manner to carry out the necessary work at an early stage, such as the preparation of subproject appraisal reports (SARs), land acquisition and involuntary resettlement plans (LARPs), detailed designs, and bid documents; the selection of contractors; and coordination with government agencies and other stakeholders. The salaries of PMU and PIU staff should be comparable with prevailing market rates to prevent the high turnover of PMU and PIU staff. Adequate local counterpart funds should have been allocated to the PMU and the PIUs to enable them to undertake the basic socioeconomic survey at the start and end of the project. Highest priority should be given to international consultants that are qualified and familiar with local rules and regulations related to project implementation. The quality of civil works for watertight structures, such as the underground and elevated water reservoirs constructed under the project, achieved the required local standards. However, local civil works contractors need further training on technology and workmanship for the construction of water supply facilities, in particular, watertight structures to reach international standards. The inclusion of a resettlement specialist within consulting services is essential to ensure timely preparation of LARPs. The PPMS report was prepared but not comprehensive. The project performance monitoring system (PPMS) should include all the technical and socioeconomic indicators that are essential to monitor the project's outcome and impact. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/kashkadarya-and-navoi-rural-water-supply-and-sanitation-sector-project
Rural Basic Education Project | Uzbekistan | Education | 2011-12-01 | Competitive selection of beneficiaries. The competitive approach used in the selection of beneficiary schools (i) proved effective in identifying schools with committed management and supportive communities; (ii) fostered a strong sense of ownership among the school's stakeholders: and (iii) encouraged a cooperative effort among the school board, school management, teachers, and parents in identifying priority needs and corresponding improvement programs. Assessment of capacity of the executing agency. During project preparation a comprehensive assessment of the executing agency's procurement capacity should help identify possible challenges in project implementation. In case of weak capacity, technical assistance grants can help to strengthen procurement capacity, especially in projects where success is linked predominantly to fast- paced, transparent procurement involving international competitive bidding (ICB). Clear understanding of government and ADB policies, guidelines, and procedures. Lack of familiarity with and understanding of policies, guidelines, and procedures of the government and ADBï¿½particularly on procurement, accounting, and financial reportingï¿½is often a source of confusion and delays. It is important that project implementation unit (PIU) staff, especially new ones where staff turnover is high, be given adequate orientation and hands-on training. PIU budgets should contain allocations for staff training. Procurement reform. The government procurement policy of verifying price after finalizing a contract under ICB causes serious project implementation difficulties. This policy should be either discontinued or streamlined and made part of the bid evaluation process. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/rural-basic-education-project
Small and Microfinance Development Project | Uzbekistan | Finance | 2011-12-01 | Legal, regulatory, and institutional framework. Legal, regulatory, and institutional framework appropriate for microfinance is required for sustainable development and the successful implementation of projects. Prudential supervisory and regulatory infrastructure and capacity. Prudential supervisory and regulatory infrastructure for bank and nonbank finance institutions with capacity and commitment to reform is essential to maintaining a stable and efficient financial system, regardless of size. Government ownership. The success of any development program depends on strong government ownership and willingness to address key constraints. Microfinance market development. Savings and credit union (SCU) growth by more than a factor of 10 demonstrated the market potential for microfinance in Uzbekistan. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/small-and-microfinance-development-project
Uzbekistan: Ak Altin Agricultural Development Project | Uzbekistan | Agriculture, Natural Resources, and Rural Development | 2011-12-01 | 1. Success of reforms largely depend on support by recruited champions from all stakeholder groups (including the upper levels of government) to a defined reform roadmap. In the case of the Ak Altin Agricultural Development Project in Uzbekistan, donors were keen to free up agriculture, and while the government in principle agreed, it was nonetheless extremely cautious about reforms. The government continued to operate at its own pace, and was almost immune to international pressure, which affected the achievement of reforms. [Main text, para. 25] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform 2. In establishing viable private agricultural services institutions in transition economy, it is important that the target farmers' willingness to avail of these services (in the short and long term) and their capacity to pay are assessed and considered during project design and implementation. Under the Ak Altin Agricultural Development Project in Uzbekistan, the Rural Business Advisory Center (RBAC) and the Machinery and Tractor Pool (MTL) were intended to be self-sufficient by project end. This is unlikely to happen for the MTL as the institution's targeted small cash-strapped farmers are inherently the most challenged to make payments for availed services. Likewise, comments from target farmers indicate that demand for services from the RBAC are only confined during the early stages of the project. [PVR main text, paras. 16, 26; see also PCR Main text, paras. 11, 27] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Country Context: Transition | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/uzbekistan-ak-altin-agricultural-development-project
Western Uzbekistan Rural Water Supply Project | Uzbekistan | Agriculture, natural resources and rural development | 2011-12-01 | Initial implementation delays need to be reduced. To this end, more work should be completed during project preparation including (a) the preparation of a request for proposal for consulting services, (b) the approval of advance action for the procurement of consulting services and construction contracts, (c) the preparation of feasibility studies and their approval by the government, and (d) the preparation of tender documents for the first contract package. Consultants should be fielded early in the project implementation period. Market-level compensation is necessary to attract and retain competent staff at the PMU and PIUs. The midterm review should thoroughly review the project, including knowledge of ground realities, costs, and implementation progress, and come up with a revised project scope, if warranted, keeping in view the budgetary provisions, and a realistic implementation schedule. Uninterrupted power supply and assured raw water availability are critical to ensure the sustainability of investments. Such infrastructure constraints that are outside the control of a particular project may reduce the project's benefits as well as accelerate the depreciation of the assets created. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/western-uzbekistan-rural-water-supply-project
Country Assistance Program Evaluation for Uzbekistan (2011) | Uzbekistan |  | 2011-07-31 | 1. When starting a new country program, financing simple projects that are high government priorities and building a strong project implementation unit can help lay a strong foundation for future projects. The first railway project is a good model for ADB to follow when starting a new country program. The first railway project was among the first ADB-financed projects in Uzbekistan. The first railway project was implemented without major problems, despite the extra burdens of learning about ADB's policies, procedures, and requirements, for three reasons: (i) it was relatively simple (rehabilitation of an existing railway line, instead of building a new line); (ii) it was among the government's highest priorities, so the government was strongly committed to it; and (iii) the project implementation unit (PIU) in the executing agency was strong and capable. Consequently, the PIU even became a source of knowledge and advice for PIUs of other ADB-financed projects in Uzbekistan. [Main text, paras. 81,102,141] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Program Modality: Project Project Management: Project management Capacity Development: Capacity development Capacity Development: Ownership 2. Demonstration projects can be more effective by focusing on economically feasible innovations. In the Land Improvement Project and Grain Productivity Improvement Project, ADB has been introducing improved varieties, alternative rotation systems, better land improvement technologies, and other innovations in technology and farm management. The demonstrations may have convinced farmers that the innovations raise productivity, but their high cost puts them out of reach of many farmers. Innovations in demonstration projects would be more effective if their financial and economic viability were first established in the farm and market context. [Main text, paras. 99,142] project cycle stage: Implementation, Operation Lesson Topics: Project Design: Appraisal Project Design: Project design 3. Effective and consistent support for reforms needs updated sector analyses, and sector road maps based on the government's priorities and commitments. ADB successfully supported reforms in education (developing new textbooks), finance (insurance and microfinance), and railways (state railway enterprise). In each of these, the need for reform was strong and the government was firmly committed, so the window of opportunity for reform was wide open. ADB's experience in supporting reforms in Uzbekistan shows that progress is possible, but a consistent and successful program needs a sector analysis to identify the most needed reforms and a sector strategy based on the government's priorities and commitments, and the skills and experience of ADB. [Main text, paras. 143-145] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Capacity Development: Ownership Policy & Reform: Public sector reform Policy & Reform: Reform 4. The added cost of following ADB's guidelines in restricting procurement to its member countries needs to be considered during project preparation. For the two ADB-financed railway projects, non-ADB member countries were the least-cost source of rails. Limiting procurement to ADB member countries raised the cost of rails by more than 250%. Uzbekistan and other countries of Central Asia or the Caucasus still have significant economic ties to the Commonwealth of Independent States (CIS), and projects can benefit from being able to procure from all CIS countries. The membership restriction also hurts ADB, by putting it at a competitive disadvantage relative to other development partners like the World Bank and European Bank for Reconstruction and Development, which can finance procurement from all CIS countries. As long as ADB's guidelines restrict procurement to member countries, when ADB determines that project costs are significantly lower in nonmember countries, it can advise the borrower on how to ask ADB's Board for an exemption from the membership requirement. [Main text, paras. 95,146] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-uzbekistan-2011
Uzbekistan: Education Sector Development Program | Uzbekistan | Education | 2011-04-30 | 1. A strategy that can help avoid program implementation delays is the careful and realistic selection of policy interventions and to implement these in a phased manner. The Education Sector Development Program in Uzbekistan, being the first to be implemented in the country, encountered implementation delays because some of its aspects were too ambitious and should have been done sequentially. [Main text, pages 6, 8] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Education | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/uzbekistan-education-sector-development-program
Education Sector Development Project | Uzbekistan | Education | 2010-12-01 | ADB and the government should jointly ensure project readiness before approval (e.g., all relevant studies, including the local feasibility studies should be completed before the start of the project). Inadequate allocation and delayed release of counterpart funds can jeopardize project outputs. ADB should be more proactive to ensure full compliance with the loan agreement and adherence to ADB procedures relating to procurement of goods and consulting services. | Project/Program Completion Reports (PCR) | Partly/less than successful | http://wcm.adb.org/projects/documents/education-sector-development-project
Urban Water Supply Project | Uzbekistan | Water and other urban infrastructure and services | 2010-12-01 | Initial implementation delays can be reduced by completing more works during project preparation such as (a) preparation of request for proposal for consulting services, (b) approval of feasibility studies by the government, (c) preparation of tender documents for the first contract package; and (d) advance actions for the procurement of consulting services or construction contracts. More capacity building needs to be provided to the staff of project management units (PMUs) and project implementaiton units (PIUs), particularly during early stages of implementation. Consultants should be fielded early in project implementation. Specifications for operation and maintenance (O&M) equipment should be prepared in consultation with the relevant agencies. Local government counterpart funding should not be included in future projects because such funds were invariably delayed which resulted in implementation delays. Market-level compensation is necessary to attract and retain competent staff at PMU, PIUs, and vodokanals. For the sake of efficiency of resources, similar works should be packaged into bigger contracts suitable for international competitive bidding and more efforts is needed during the prequalification and bid evaluation stages to ensure that the selected contractors are fully familiar with the country norms and practices. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/urban-water-supply-project
Uzbekistan: Grain Productivity Improvement Project [Loan 2017-UZB] | Uzbekistan | Agriculture, Natural Resources, and Rural Development, Finance | 2010-09-30 | This validation notes that the lesson regarding policy reform failed to emphasize the need for all parties, particularly those at the provincial and district levels, to be fully committed to the reform agenda. Support for reform at the central level is not enough. [Main text, page 8, section E(ii)] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/uzbekistan-grain-productivity-improvement-project-loan-2017-uzb
Grain Productivity Improvement Project | Uzbekistan | Agriculture, natural resources and rural development, Finance | 2010-03-01 | In forming loan covenants regarding policy reforms, sector issues should be reviewed in total, as some reforms may be rendered ineffective by various distortions. The implementation period should be realistic, determined after a thorough analysis of activities and their inter-relations and sequence. As the design implementation period of the project was short, some targets, particularly those related to varietal development and testing, were ambitious. While involving a number of government institutions and building their capacity is desirable for sustainability, enough resources should be provided for effective coordination. For agriculture enterprise development to be successful, sufficient lead time and necessary information and data should be provided, preferably through demonstration farms, for farmers to be convinced of what types of machinery and equipment to procure; subloan procedures should be simplified and the processing time shortened. Participating financial institutions (PFIs) should be selected more thoroughly keeping in view their relevant experience, geographic coverage, staff, and other resources. It is important to provide suitable incentives to attract commercial seed growers, which is key to providing quality seed of new varieties to farmers, in addition to incentives for increasing the capacity of the breeding institutions to multiply high- quality foundation seed. Field trial-cum-demonstration farms are effective in introducing improved technologies to farmers. For water users' associations (WUAs) and other community-based organizations to be effective and sustainable, they should have a good source(s) of income and reasonable leverage to collect. Project management staff benefits should match with those of comparable private sector institutions to prevent high turnover that constrains project management. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/grain-productivity-improvement-project
Ak Altin Agricultural Development Project | Uzbekistan | Agriculture, Natural Resources, and Rural Development | 2010-01-12 | 1. Except for special circumstances, such as when a pilot project is small or the executing agency is experienced in project implementation, the project design should be simplified to ease implementation. Generally, the focus should be on a single sector with a minimum number of types of measures. Although the project focused on rural development and agriculture, it comprised different measures (rural business strengthening, irrigation and drainage system enhancement, and cotton and wheat quota system reform) as a result of incorporating most of the challenges encountered in the sector. Projects with a narrower focus are more likely to be implemented successfully. project cycle stage: Lesson Topics: 2. In general, something as substantial and sensitive as cotton and wheat (C&W) quota system reform cannot be completed within a short time frame and should be undertaken at the national level. Although the Ministry of Agriculture and Water Resources was responsible for implementing the C&W quota system, reform required inputs from other government departments. Such policy reforms are better accomplished through vehicles other than projects, and certainly not a single pilot investment project in one district or region. A need for a policy reform could be identified and clarified by a technical assistance. Then, implementation of the reform could be set up in ADB's country partnership strategy as the condition to be met before specific investments could be processed. Sensitive policy reform must be separated from physical investment: project design that is highly independent of at-risk assumptions such as policy reforms will ensure the economic viability and efficiency needed to achieve outcomes. It should be noted that Uzbekistan's policy reforms are being gradually implemented - a fact that should have been considered to ensure a more realistic project design. project cycle stage: Lesson Topics: 3. The project completion mission noted that some farmers interviewed were unaware of their obligations to the government for on-farm rehabilitation cost recovery, despite having signed a repayment agreement with each water users' association and the government before rehabilitation works. This suggests that farmers had limited awareness of the cost-recovery requirements and that the farmers who were not willing to pay for rehabilitation might have been included in on-farm irrigation and drainage (I&D) systems. If on-farm I&D rehabilitation had been limited to farmers willing to participate and well aware of their cost-recovery obligations, the contractor would have encountered less resistance from farmers. In this regard, (i) the cost-recovery requirements for farmers should have been better publicized; or (ii) a survey on willingness to pay should have been conducted by the government and the project preparatory technical assistance consultants during project preparation, to identify areas for improvement more clearly so that civil works could be conducted more smoothly. project cycle stage: Lesson Topics: 4. During project implementation, key project officers in ADB and the Ministry of Agriculture and Water Resources changed, contributing to delayed decision making and project implementation. A new project officer should take over the project administration and management with adequate time, and ADB should ensure that the previous project officer accompanies a new project officer on mission to ensure a seamless transition in project administration. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/ak-altin-agricultural-development-project
Second Textbook Development Project | Uzbekistan | Education | 2010-01-12 | 1. The text book rental scheme (TRS) can serve as one of the models on textbook provision for other countries in Central Asia given the efficiency and effectiveness by which it was implemented. Contributing to the successful implementation of this scheme is the government's commitment and the design's alignment to government's priorities. Resources were used efficiently to establish functional arrangements that ensured sustainability of funding and made available and affordable textbooks to students and teacher's guides to teachers. Countries struggling with textbook provision could be encouraged to study the TRS in Uzbekistan. In turn, study visits could further strengthen the TRS by encouraging educators and the government in Uzbekistan to further improve its implementation. [Main text, paras. 34-35, 40, 45] project cycle stage: Design, Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Project Design: Project design Capacity Development: Capacity building Capacity Development: Technology/Technology transfer 2. Designing an improved and more relevant curriculum that focuses on competency-based learning objectives and promotes high cognitive skills requires further support and commitment from the Ministry of Public Education. Expected project outputs related to improvements in the curriculum were only partially achieved. Curriculum development was also assessed as less efficient in achieving outputs due to delays in fielding consultants and differences in perceptions of curriculum by national education developers and international consultants. While movement towards a competency-based curriculum and student-centered learning will take a longer time to develop, monitoring of classroom teaching practices and the extent to which textbooks continue to define the school curriculum will assist in identifying the next steps in the curriculum review. [Main text, paras. 39,42,45] project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Capacity Development: Capacity development Capacity Development: Ownership 3. The teachers' guides could cost effectively support the timely roll out of student centered learning. Teachers' guides could be expanded to identify tools, provide additional referencing to learning materials for teachers, and promote greater use of school libraries. The student centered learning is one of the areas which educators in Uzbekistan need to discuss so that the government can move to a more efficient and cost-effective approach to provision of textbooks, workbooks and teachers' guides. [Main text, para. 45; Appendix 7, paras. 16-17] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Methodologies/Approaches: Process approach 4. Discussion and dialogue on language of instruction (LOI) for ethnic minorities remains a sensitive issue in most countries in the Commonwealth of Independent States. Any debate of change in LOIs should be widely discussed before implementation and aim at (i) improving ethnic minorities' chances to enter the best senior secondary and higher education institutions, and (ii) acquiring language skills necessary for better job opportunities while providing necessary support to maintain their identity. [Main text, paras. 8, 45] project cycle stage: Design, Implementation Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-textbook-development-project
Education Sector Development Program | Uzbekistan | Education | 2008-12-26 | 1. The design of policy loan could have benefited from a detailed assessment of the context and institutional capacity of Ministry of Public Education and Ministry of Higher and Secondary Specialized Education to undertake the additional workload and to formulate and implement new and market-oriented policies. Being the first reform program in the country, managing the education transition toward a democratic and market-oriented economy has been a challenge as it assumes the availability of adequate resources and local capacity which can have a significant impact on the outcome. [Main text, paras. 49, 55] project cycle stage: Design Lesson Topics: Project Design: Project design Capacity Development: Capacity assessment Capacity Development: Institutional analysis Country Context: Transition Sector Related Issues: Education Sector Related Issues: Education 2. As the policy loan is supported by the investment loan, the design could have been strengthened by clearly showing the links between the two. Separate policy matrices and design frameworks could have helped. The PCR of such programs should also be done simultaneously as both the policy and investment loans are intertwined in delivering the inputs and outputs and in achieving the outcomes and impact and assessing one without the other may not provide full picture of the intervention. [Main text, paras. 47, 57] project cycle stage: Design, Completion Lesson Topics: Modality: Policy-based lending Modality: Program Modality: Project Project Design: Project design Policy & Reform: Policy matrix | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/education-sector-development-program-0
Senior Secondary Education Project | Uzbekistan | Education | 2007-12-27 | 1. The essence of vocational education and skills training is relevant practical training and hands-on experience for students; however the new equipment procured under the Project for the 45 pilot schools was mostly used for demonstration purposes, rather than for practical training of students. Project monitoring focused on equipment procurement and installation at schools. Consequently, the impact of the new equipments will remain limited. Project monitoring efforts must include means to ensure that (i) new equipment is being fully integrated in lessons, (ii) suitable qualified teachers are available to conduct lessons as planned, and (iii) sufficient consumables and supporting tools/equipment are in place. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity development Sector Related Issues: Education 2. The project did not provide for systematic gathering and analysis of data on the project impact, including effectiveness of teaching and learning in schools before and after the intervention. For future projects, a system to collect and maintain data, and to monitor and analyze quantitative and qualitative outputs and impacts should be built into project design. project cycle stage: Design, Completion Operation Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation Monitoring & Evaluation: Reporting | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/senior-secondary-education-project
Rural Enterprise Development Project (Loan 1504-UZB) | Uzbekistan | Agriculture, Natural Resources, and Rural Development | 2006-12-31 | 1. It is important to fully understand the country and sector context, and the government capability for project decision making and implementation at the time of project processing and approval. There were issues such as (a) difficulty in accessing information for project processing, (b) slower-than-expected decision making by the Government, and (c) a less-than desired level of donor feedback. ADB did not sufficiently consider these, despite the Rural Enterprise Development Project being the country s first ADB project. Selection of modality and endorsement of fast-track loan processing were deemed not appropriate. [Executive Summary; Main text, paras. 12-13, 44, 83] project cycle stage: Design Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Subprojects Project Management: Executing/Implementing agencies 2. An assessment of the financial sector, executing agency's non banking activities, and government's influence over the executing agency's structure, regulation and governance, among others, should have preceded ADB's financing credit lines to state-controlled financial intermediatires especially in a transition economy. Active policy dialogue should be maintained throughout project implementation given the weaknesses in the financial sector and in all aspects of the policy, legal and regulatory framework and corporate governance, and the consequent risks for the targeted financial intermediary s operations. Considering the scope and depth of these issues, a line of credit was not appropriate as a first intervention in a country that was just beginning its transition to a market economy. Diligent application of the Guidelines on Development Finance Institutions [DFI]) which note that government policies and economic environment should be congenial to the satisfactory operations of a DFI is needed. [Main text, paras. 84-85] project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Legal system Finance & Financial Aspects: Financing Modality: Lending modality Project Design: Project design Project Management: Risks/Risk management Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Policy & Reform: Transition economies 3. In considering financial covenants for an intermediary of ADB financial intermediation loans (FILs), prudential guidelinesin the country, their enforcement status, and the intermediary s capacity to manage risk should be thoroughly reviewed during appraisal. Based on such review, ADB should identify financial covenants that complement the intermediary s risk management systems and the country s prudential guidelines. In the case of the project, ADB should have included a financial covenant that addressed the intermediary's inadequate loan-loss provisioning for state-guaranteed loans. [Main text, paras. 39-41, 45, 87] project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Design: Appraisal Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Capacity assessment 4. The small and medium-sized enterprises (SMEs) prepared only pro-forma business plans, in some cases merely for a loan application. These business plans are not under public scrutiny as SMEs are typically not listed on the stock exchange. As such, loan application documents are often not fully reliable. Hence, the at-entry eligibility clearance of subprojects needed to be complemented by frequent on-site inspections by the executing agency and ADB. A general weakness in SMEs corporate governance as well as the significant overvaluation of the national currency at project entry were clear indications that portfolio problems could be anticipated and that ADB should have allocated extra resources to monitoring subprojects. [Main text, paras. 38, 80, 88] project cycle stage: Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Monitoring & Evaluation: Monitoring and evaluation Project Design: Appraisal Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project supervision Sector Related Issues: Industry and Trade 5. The intermediary has little information on the subprojects operational performance and development impacts. Weak benefit monitoring and evaluation (BME) has been common among ADB s financial intermediation loan (FIL) operations. Experience underscores the need for ADB to consider an alternative approach to creating a functional monitoring framework that balances increased administrative costs with the need for, and use of, the data collected. One possibility is to specify the required data and timing of data collection in a loan/project agreement. Another option is to select sample subprojects in case their number is large. The project agreement stipulated that the project's financial intermediary 'shall assist ADB to monitor and evaluate the long-term benefits of a random sample of five qualified projects. However, ADB did not select such a sample and should have dealt more vigorously with the BME clause during project implementation. [Main text, paras. 9, 89] project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Loan Agreement Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Design: Subprojects Project Management: Executing/Implementing agencies Project Management: Project supervision The RRP assessed the potential of the agroprocessing industry, but its assessment of the intermediary (National Bank for Foreign Economic Activity of the Republic of Uzbekistan or NBU) and the financial sector was weak. The RRP should have assessed the magnitude of the intermediary's nonbanking activities and the government s influence over its credit allocation decisions, the structure, regulation and governance in the financial sector, and the implications for its commercial orientation and portfolio performance. Such an assessment should have preceded ADB s financing credit lines to state-controlled financial intermediaries, especially in a transition economy. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Sector Related Issues: Rural development Policy & Reform: Transition economies | Project/Program Performance Evaluation Report (PPER) | Partly/less than successful | http://www.adb.org/documents/rural-enterprise-development-project-loan-1504-uzb
Railway Rehabilitation Project | Uzbekistan |  | 2006-04-14 | 1. ADB's monitoring could be improved by ensuring, to the extent possible, continuity or overlap of ADB project officers and sector specialists throughout project implementation. It should be ensured that before a project is handed over to a resident mission under ADB's Resident Mission Policy, the particular resident mission has both the staff resources and institutional capacity to administer the loan efficiently together with adequate sector support from Manila. Uzbekistan Resident Mission has been developing its capacity for project implementation since this first project was delegated, particularly in terms of systems for project administration and developing local staff capacity. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project administration Capacity Development: Capacity assessment Capacity Development: Capacity development Capacity Development: Human resources management Other: Resident Mission The allocation of resources procured under the project to another project can significantly delay project implementation. The government, by instructing the executing agency to reallocate materials and equipment being used for track rehabilitation to another project, considerably delayed the rate of track rehabilitation for about 1 year. This eventually led to an extension of the loan closing date. project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Transport planning | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/railway-rehabilitation-project
Country Assistance Program Evaluation for Uzbekistan (2006) | Uzbekistan |  | 2006-01-31 | 1. In the ADB private sector development strategy, (i) the right policy environment is vital for the development and viability of the private; and (ii) sector assistance given through both public and private operations windows should achieve synergy. Fostering enabling business conditions, creating business opportunities, and catalyzing private investment are three major ways in which the strategy indicated ADB should assist. However, conditions have not been conducive for catalyzing private investment in Uzbekistan. It appears that ADB has tried to address enabling conditions in an ad hoc manner, responding to opportunistic requests. In addition, ADB has not managed to combine its public and private expertise in order to catalyze reform and finance.[Main text, paras. 81-82; Appendix 6] project cycle stage: Country Partnership Strategy Lesson Topics: Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework 2. There is a need to strengthen the link between the country strategy and the corresponding programs to ensure consistency and focus of ADB operations. Evaluation noted weaknesses in the strategic management of the program. There have been too many interventions which do not conform to the thrust of the strategy. Their inclusion was not supported by an in-depth comparison of their advantages over alternative priorities which fall within the mainstream of the strategy, or by justification for a significant strategic shift. As a consequence, the program became more diffused, less focused, and potentially more difficult to manage given the resource constraints of ADB and its Uzbekistan Resident Mission. [Main text, paras. 71-72, 205-207] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Alignment Country Context: Prioritization 3. Focus on a limited number of sectors and aligning ADB resources correspondingly is more likely to achieve development results than a superficial engagement in a large number of sectors. Analysis found that Uzbekistan (among other transition economies) had the least focused loan portfolios given that loans and TA projects and new sectors were added to the program without adequate justification. As a general proposition, it is likely that ADB would have a better portfolio if it focused on those sectors in which it has a proven track record. Other factors that can be considered in prioritization include government priorities, changing economic circumstances, the openness to reform, the emerging role of the private sector, and the programs and priorities of other donors must also be considered. The number of sectors that ADB can engage in is partly determined by the size of its program. Development needs exist in all sectors in a country. But the issue comes down to prioritization, taking into account ADB staffing and budgeting constraints. [Main text, paras. 208-211] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Alignment Country Context: Prioritization 4. The country strategy and program (CSP) should include a well-articulated approach to governance that (i) reflects the Government's priorities, (ii) identifies niche areas where the Government would welcome support from ADB, (iii) mainstreams governance issues in sectoral operations and at the macro level, and (iv) is consistent with ADB's areas of expertise and budget and staffing constraints. ADB strategy and operations did not include a well articulated strategy for governance, despite the strategy's view that institutional development was one of the biggest constraints to growth and development. Many of the binding constraints such as the need for capacity and institution building, identified in the country assistance program evaluation (CAPE) at the macro and sectoral level, and the need to build an enabling environment for the private sector could be broadly classified as governance issues. Given that governance is a broad and sensitive topic, ADB needs to select a strategic governance agenda in Uzbekistan carefully, based on an open and frank discussion with Government. A challenge will be to identify parts of the governance agenda in which the Government wishes to engage with ADB. [Executive summary; Main text, paras. 214-216] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Governance Capacity Development: Capacity assessment Capacity Development: Institutional analysis Policy & Reform: Reform 5. The next country strategy and program (CSP) needs to actively build on ADB's comparative advantages to develop synergies through geographic focus, consistently addressing strategic themes across operations, and developing stronger partnerships with other agencies. The selection of the geographic areas, strategic themes, and potential partnerships should reflect Government priorities, the programs of other international development partners, and ADB's capacity to provide high quality services over a sustained period of time. ADB's country strategy should be more than the sum of the parts. Evaluation found little evidence to suggest that the CSP and the subsequent management of ADB's program in Uzbekistan sought to identify and exploit potential synergies. [Main text, paras. 212-213] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Alignment Crosscutting Issues/Themes: Harmonization Capacity Development: Partnerships Country Context: Prioritization 6. Technical assistance (TA) has the potential to be an excellent way of positioning ADB to engage in policy dialogue and to support capacity building. Used skillfully, such support helps to achieve development results, sometimes at the strategic level. However, this would require improvement in the management of the TA program along with the results it intends to achieve. Evaluation noted that while there is evidence of client satisfaction and positive outcomes under some TA projects, weaknesses were also identified, raising questions about the usefulness, impact, and sustainability of some outputs. These include poor strategic TA program management, lack of local knowledge reflected in the design of TA projects, overambitious objectives and terms of reference, and lack of ADB supervision and follow-up to enable outputs to be turned into outcomes. The last particularly affected policy development and developing management capacities. [Executive summary; Main text, paras. 151-156, 217-219] project cycle stage: Country Partnership Strategy Lesson Topics: Modality: Lending modality Modality: Technical Assistance 7. Strengthening the Uzbekistan resident mission (URM) would allow it to play an optimal role in building ADB's reputation with the government as a more effective partner in policy dialogue and program management. Evaluation noted that while the URM has performed well in client management, donor coordination and portfolio management, it would have to be resourced properly (staff complement with appropriate expertise) to be able to play an optimal role in the following areas: government relations and identifying strategic areas for ADB involvement, economic analysis and monitoring, strategy formulation and programming, portfolio management, loan and TA supervision, and partnering with other development partners and civil society. [Executive summary; Main text, paras. 175, 179-180, 223-224] project cycle stage: Design, Feasibility, Implementation, Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Other: Resident Mission | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-uzbekistan-2006
Basic Education Textbook Development Project | Uzbekistan | Education | 2005-06-15 | A particular strength of the project was that the objectives were firmly based on Borrower's priorities and on stakeholder assessment conducted during the preparatory phase and considerable direct consultation with beneficiary groups. Related to this was the demonstrated strong government commitment to the purpose and objectives of the Basic Education Textbook Development Project. Project ownership was evident among the senior management of the executing agencies and helped resolve problems on implementation and ensure its success. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation A system to collect and maintain data, and to monitor and analyze quantitative and qualitative outputs and impacts should be built into project design. The Basic Education Textbook Development Project did not provide for the systematic gathering and analysis of data on the project impact, including effectiveness of teaching and learning in schools before and after the intervention. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Sector Related Issues: Education Project design should ensure accurate estimates of the need for foreign exchange and avoid unnecessary burdening of the government with foreign currency financing. At appraisal it was not foreseen that a large amount of paper would need to be imported using foreign exchange. In reality, about 50% of total costs of textbook production was attributable to the cost of imported paper. As a result, the government shared significant project funding in foreign currency. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Foreign exchange Project Design: Appraisal Project Design: Project design The introduction of student-centered learning (SCL) is a paradigm shift in Uzbekistan. Given the former rigid educational environment, which focused on learning facts rather than acquiring skills, the understandable skepticism among teachers and trainers about SCL and the relative inexperience of counterparts with hands-on experience on SCL are changing. Ideas of interactive learning methods discussed during in-service training sessions were far more often referred to by teachers than the actual improvement of selected syllabi as primary outcomes of the project. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Education | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/basic-education-textbook-development-project
Rural Enterprise Development Project | Uzbekistan | Agriculture, Natural Resources, and Rural Development | 2003-10-15 | ADB needs to set realistic, relevant, and objectively measurable financialcovenants both for financial institutions and subprojects. This will help avoid delays in loan implementation while facilitating subproject viability and financial soundness of the institution. This lesson was also incorporated into the design of Loan 1799. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Design: Subprojects Capacity building is necessary for financial institutions selected for ADB'sintermediation loans to ensure sound appraisal and supervision of subprojects,sound credit and risk management policies, and sound corporate governance andfinancial disclosure policies. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Corporate governance Finance & Financial Aspects: Financial reporting Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Subprojects Project Management: Project supervision Project Management: Risks/Risk management Capacity Development: Capacity building Policy dialogue with the government on regulatory and other impediments isnecessary while processing a sector (credit) loan. This lesson was incorporated into the design of Loan 1799. project cycle stage: Appraisal Lesson Topics: Modality: Lending modality Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework Subloans of less than $1 million, particularly those to smaller subborrowers, resulted in better quality and repayment. Rigorous analysis, supervision, and monitoring of subloan proposals and subproject operation both by ADB and the participating financial institution are necessary to ensure efficient subloan recovery and achievement of development objectives at the subproject level. At the participating financial institution level, the post disbursementloan monitoring could be more efficient if decentralized. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation Project Design: Subprojects Project Management: Project supervision Country Context: Decentralization | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-enterprise-development-project
State-Owned Enterprise Rationalization Program: TA Completion Report | Vanuatu | Public sector management | 2015-03-01 | TA (technical assistance) that is supporting sensitive reform areas in the Pacific takes substantial time to implement. The original time period for TA implementation of 23 months was optimistic given the country context. In addition, the outcome indicators in the design and monitoring framework were overly ambitious and did not adequately take into account the existing state of the SOE (state-owned enterprise) sector at the time of TA design. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/state-owned-enterprise-rationalization-program-tcr
Urban Infrastructure Project | Vanuatu |  | 2003-06-13 | Future infrastructure projects should limit their multifaceted nature, concentrate on a fewmain infrastructure modes, limit agency participants, ensure the inclusion of project financialcapacity, and give responsibility for Benefit Monitoring and Evaluation (BME) to the executing agency (EA) or the infrastructure operating agency.Vanuatu, with its limited institutional capacity and relative government instability, is better suited to projects that are less complex and diverse than this one. That would simplify implementationarrangements and O&M requirements. Future projects should incorporate capacity building, andtheir effectiveness should be monitored carefully. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity building Loan covenants should be limited to a few directly relevant and achievable conditionswith strong government commitment. The loan covenants in this project that related to O&Msustainability were too wide-ranging and indirect. An alternate approach, requiring acommitment for direct O&M budget funding or related capacity building, would have been moreeffective, because it would have been simpler to understand, and easier to comply with. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Loan Agreement: Covenants Project Management: Operation and maintenance Capacity Development: Capacity building Capacity Development: Ownership Reliance on complementary technical assistance (TA) from other agencies should be limited to noncriticalproject areas, and only if the continuity of funding is assured. The late withdrawal of some TAand institutional strengthening from Australian Agency for International Development (AusAID), and all of New Zealand Overseas Development Assistance (NZODA) assistance, significantlyweakened the project's capacity building and institutional strengthening. That, in turn,weakened the project's sustainability. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development The capacity and funding for O&M should be carefully assessed for all futureinfrastructure projects in Vanuatu, and direct mechanisms to ensure sustainability should beimplemented before the loan becomes effective. Project sustainability is a significant problem inVanuatu because of (i) the executing agency's (Public Works Department's) limited capacity in maintenance, and a virtual absence ofmaintenance capacity in other organizations; (ii) a reluctance of Ministry of Finance and Economic Management (MFEM) and the government toallow the use of ï¿½tiedï¿½ funds because of concerns that the funds will be misused; and (iii) thegovernment's reluctance to place O&M for the Luganville water supply under an entitydedicated to water services, as is done in Port Vila. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Operation and maintenance Capacity Development: Capacity assessment Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/urban-infrastructure-project-1
Comprehensive Reform Program | Vanuatu |  | 2002-12-13 | A strong governance framework has been one of the highlights of the program. This isreflected in the voluminous number of laws enacted. But severe capacity constraints mean thatthese laws were passed without much scrutiny. In most cases, further amendments were madeto enable effective implementation. project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Legal system Modality: Program Capacity Development: Capacity assessment A wide consultation and participation process entrenches support and broad ownership for any reform initiative. The consultation process carried out during preparation of the Comprehensive Reform Program (CRP) and still continuing provided an opportunity for stakeholders to understand, monitor, and reassess their goals and make adjustments. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Program Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Ownership Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation ADB should be committed to fund institutional strengthening programs of key centralagencies to ensure alignment of outputs with the intended reform objectives. Experience inVanuatu has shown that work driven by project milestones has frequently failed to take accountof governments' overall strategic reform agendas. Therefore, some of the outputs and capacitybuilding envisaged under the program have not been satisfactorily met on time. At the sametime the government should be assertive in its leadership role in managing the outputs ofvarious funding agencies. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building Capacity Development: Capacity development Policy & Reform: Reform Following the dissolution of the Development Bank of Vanuatu (DBV), access to credit has been a problem for the public atlarge. The ni-Vanuatu Business Center established to cater for the business interests of ni-Vanuatu was inadequately resourced but replete with bureaucratic procedures. Furtherinstitutional strengthening will be needed before the Center becomes productive. This is anexample of waste as ADB helped establish the former DBV, dissolved it, and created anothernew institution for which the intended objectives have not been met. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Capacity Development: Capacity building The program underestimated the severe capacity constraints within Vanuatu. Thereform initiatives created new systems and processes that are alien to Vanuatu's managementand local culture. Consequently, considerable frustrations, lethargy, and communicationbreakdown were experienced during implementation. project cycle stage: Feasibility Lesson Topics: Modality: Program Project Management: Risks/Risk management Capacity Development: Capacity assessment Country Context: Cultural constraints Policy & Reform: Reform The sequencing of reform was inadequately assessed at appraisal, without due consideration to the sustainability of the project. The Comprehensive Reform Program (CRP) was too ambitious and addressed three major sectors simultaneously (public, economic, and financial) instead of being more focused. A more logical approach would have been to develop a financial sector project loan separate from the program loan covering public sector reform. Similarly, the program assumed too much in expecting the private sector to step into the vacuum following the public service retrenchment program. Unfortunately, the framework needed to develop the private sector was absent. In addition, some reform initiatives, such as privatization of public enterprises and the creation of an environment that induces private sector investment, will take many more years than envisaged under the program. project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Legal system Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Program Project Design: Appraisal Sector Related Issues: Private sector Policy & Reform: Policy reforms/framework Policy & Reform: Privatization Policy & Reform: Public sector reform Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/comprehensive-reform-program
Santo Port Project (Loans 843/1080-VAN[SF]) | Vanuatu | Transport | 2002-05-31 | ADB took an excessive amount of time to approve evaluation of bids for the construction works and evaluation of consulting proposals for the remedial works, highlighting the need for decentralization within ADB. ADB has already taken action to solve this problem through its resident mission policy. project cycle stage: Appraisal Lesson Topics: Project Management: Procurement Other: Resident Mission Discrepancies in statistical data suggest that collecting, compiling, and analyzing data for future sector planning require strengthening. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Data collection Capacity Development: Capacity building The implementing agency has weak managerial, planning, and financial capacities. It would have been useful to attach a TA component during project implementation to strengthen the implementing agencywhich would have helped implement the action plan. project cycle stage: Appraisal Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity building The project management manual prepared by the TA consultant was never used and OEM did not find anyone in the executing agency aware of the manual s existence. The manual should have been prepared during TA implementation, followed by seminars and training. project cycle stage: Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building When formulating a TA and reviewing its implementation, ADB should ensure that the training requirements are assessed appropriately. In this particular case, the project manager was not in the same location as the consultant and a technical assistant was not appointed. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity building Capacity Development: Human resources management | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/santo-port-project-loans-843-1080-van-sf
Enhancing Financial Stability (Scoping): Technical Assistance Completion Report | Viet Nam | Finance | 2015-08-01 | For TAs (technical assistance) such as this one, the project team needed to take a one ADB approach by working with staff with expertise from other regional and non-operational departments. The pool of available consultants is very small for this type of TA so the project team should have started identifying potential experts at a very early stage, even straight after formal request from the Government. ADB acceptance of the TA request should have been conditional on identification of suitable consultants. Networks with other regional central banks also need to be leveraged through other resident missions and non-operational departments such as OREI (Office of Regional Economic Integration). Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/enhancing-financial-stability-scoping-tcr
Central Region Small and Medium Towns Development Project: Completion Report | Viet Nam | Water and Other Urban Infrastructure and Services | 2015-07-31 | Executing agencies' recruitment of consultants remains time-consuming and was the main reason for start-up delays. This problem is not specific to the project but is common in all ADB-financed projects in Viet Nam. Delays in recruiting consultants result in delay of such project activities as detailed design, resettlement planning, environmental management planning, and preparing bidding documents. The delays in bidding and contract awards caused total project costs to rise and held back delivery of the facilities to the final recipients. project cycle stage: Design, Implementation The project substantially achieved the targeted outputs despite the start-up delays caused by the prolonged process of recruiting consultants. This demonstrated that the executing agencies at provincial level have the capacity for project implementation and the decentralized approach to project preparation and implementation is appropriate. project cycle stage: Feasibility, Implementation, Operation The result of efforts to increase tariffs varies among project provinces. Some provinces showed strong commitments in implementing the reform agenda set by the project (for example, Binh Thuan, Dak Lak, and Khanh Hoa provinces). Meanwhile, other provinces were reluctant to raise the wastewater tariff and solid waste collection fee to the required levels (Ninh Thuan and Phu Yen provinces). project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/central-region-small-and-medium-towns-development-project-pcr
Upper Secondary and Professional Teacher Development Project: Completion Report | Viet Nam | Education | 2015-06-29 | Consistency in project documents between the government and ADB. Some inconsistencies and ambitious targets between the government's feasibility study report and the RRP (Report and Recommendation of the President) required discussions and formal agreements between the MOET (Ministry of Education and Training) and ADB, resulting in delays in project implementation. At the design stage, project targets should be more realistic and attainable. Intensive consultations among stakeholders are needed to avoid such discrepancies. project cycle stage: Design, Feasibility, Implementation Capacity of project management unit staff. Limited familiarity of PMU (project management unit) staff with ADB procurement and financial management guidelines and procedures contributed to delays in implementation, procurement of equipment, awarding of contracts of civil works, and disbursement. Moreover, PMU heads were nominated and approved by the MOET (Ministry of Education and Training) only after project approval, which further contributed to delays in project start-up. For future projects, the PMU and PIUs should be established before loan approval. Moreover, once these have been established, recruitment of PMU and PIU staff with prior experience in ADB projects should be immediately undertaken. Training of PMU and PIU staff by project preparatory TA start-up consultants, and by ADB if required, must be carried out and explicitly recommended in the loan covenants. project cycle stage: Design, Implementation Recruitment of consultants. The recruitment of consultants remains time consuming. This problem is not specific to the project but common in all ADB-financed projects in Viet Nam. Delays in consultant recruitment result in delays in implementing the entire project. In future, advance actions and project readiness filters should be applied to minimize start-up delays. project cycle stage: Feasibility, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/upper-secondary-and-professional-teacher-development-pcr
Preventive Health System Support Project: Completion Report | Viet Nam | Health | 2015-06-26 | Consideration of local government fiscal capacity. The project originally required participating provinces to provide funds to upgrade the PPMCs (provincial preventive medicine centers), including their laboratories. While local government commitment to preventive health care is significant in Viet Nam, the fiscal situation of some provinces does not allow investments of the scale that was needed. ADB needs to carefully consider the local costs of such infrastructure projects and the fiscal ability of local governments to meet them before committing to an investment. project cycle stage: Feasibility, Implementation Phased approach. Implementing the project across almost four dozen provinces and such a wide geographical area led to challenges both in providing laboratory equipment in a timely manner and in ensuring that training was provided in the use of this equipment. A phased approach prioritizing provinces with stronger technical capacities would ensure a closer link between the provision of equipment and training thus increase efficiency. project cycle stage: Design, Implementation Need for market-based remuneration. The government's cost norm is too low and not competitive. Because of this, recruiting experienced senior national consultants (with the exception of retired government employees) remains a challenge. Training allowances are also too low. This also applies to its training allowances, which discourages participation by staff who must travel from where they live and work to take part. Future projects should include a clause that allows remuneration for consultants and allowances for staff training to be market-based. project cycle stage: Design, Implementation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/preventive-health-system-support-project-pcr
Support for Public-Private Development of the O Mon Thermal Power Complex Project: Technical Assistance Completion Report | Viet Nam | Energy | 2015-06-01 | TA's (technical assistance) outcomes were achievable only with the condition that the gas sale and purchase contract can be materialized timely. However such a condition is an external factor to the TA and also beyond the controls of the TA executing and implementing agencies. In the TA's design, the 'inability to reach an agreement with gas supply partners and obtain economic gas supply agreement' was identified as a risk to the achievement of the outcome. However risk mitigation measures were not prepared. At the time it was considered that the likelihood of reaching gas sale and purchase agreement is very high given the intensive discussions and activities among the concerned stakeholders, and O Mon I was under construction. In the future design of a TA will have to take into consideration the factors that will have influences on the intended outcomes, such as fuel supply availability and correspondingly a list of measures to mitigate those risks will have to be prepared under the TA design. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/support-public-private-development-o-mon-thermal-power-complex-project-tcr
Water Resources Development in the Mid- and Northeast Red River Delta: Technical Assistance Completion Report | Viet Nam | Agriculture, natural resources and rural development | 2015-06-01 | A programmatic approach to these types of water infrastructure upgrading investments, based on rigorous water balance assessments, could have provided a framework for more strategic selectivity of investments. This could have been more efficient instead of appraising the design of scattered individual subprojects only to find out much later on that water availability would become constraints. The subproject scope should have gone beyond water delivery to support changes in the irrigation system, as well as modernization and diversification of agriculture, which requires increased control of water and water delivery within the irrigation schemes. These considerations earlier in the PPTA (project preparatory technical assistance) could have provided insight into how the loan design could respond to the differing water demand needs of producers within and across the command area and within the context of diversification and modernization of production systems. The PPTA process could have been better phased to carry out screening on economic viability earlier in the process. A good practice from a previous successful ADB PPTA in the water sector in Viet Nam was to field a small team of individual consultants in the early pre-feasibility phase to do the economic and technical screening of the proposed loan. Recruitment of a PPTA firm did not commence until ADB was satisfied that the project had a very strong chance of being found feasible. Having said this, the processing time pressure for TA (Technical Assistance) 7926 would have posed a challenge to using such a staggered approach. Therefore, a better balance needs to be struck between processing in a short duration and using the phased approach. Project cycle stage: Concept, Design, Implementation | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/water-resources-development-mid-and-northeast-red-river-delta-tcr
Developing the Market Readiness Proposal for a Domestic Carbon Market: Technical Assistance Completion Report | Viet Nam | Energy | 2015-03-01 | For implementation of future similar TA (technical assistance) on country MRP (market readiness proposal) development, we propose the following recommendations: (i) a strong emphasis on sector-wide consultation and consensus building mechanism around the proposed MRP components; (ii) Identify at the TA preparation stage one single leading agency, ideally the EA (executing agency); and (iii) Include in the TA package some individual consultancy to serve as technical advisor to the EA. The introduction of a carbon finance market does not follow the one-size-fits-all principle and considering that both MPI (Ministry of Planning and Investment) and MONRE (Ministry of Natural Resources and Environment) co-led this, a key lesson learnt is that not only is continuous dialogue enough but the comments and lessons learned from their outcome had to be reflected in the revised and final version of the MRP. With the number of stakeholders involved in the preparation of the final MRP, the importance of consensus-driven decisions to assess the strength of carbon pricing policies became highly evident. However it is recommended going for similar exercise, these types of efforts should not be co-led, rather there should one overall responsible agency. Also to promote stronger government ownership, hiring individual consultants to serve as advisors to the EA is beneficial. Another important lesson learnt is that there should be only one delivery partner for ease of efficiency since having two delivery partners implies more time for consultation and consensus building. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/vie-developing-market-readiness-proposal-domestic-carbon-market-tcr
Support for the National Target Program on Climate Change with a Focus on Energy and Transport: Technical Assistance Completion Report | Viet Nam | Energy | 2015-03-01 | In the future, project design should emphasize in scope and resources the importance of establishing a credible evidence base from the outset. This would require a greater emphasis on modelling, geographic information system, and field survey activities as well as training to technical stakeholders in simple geographic information system assessment and database management techniques. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-national-target-program-climate-change-focus-energy-and-transport-tcr
Third Financial Sector Program Loan: Program Completion Report | Viet Nam |  | 2014-09-30 | 1. Assessment of a program's success should be based on quantitative indicators and tangible results rather than whether policy actions have been met. Whileapproval of legislation and regulations can be considered a reform in the initial phase of a program, particularly subprogram 1, subsequent programs should assess the result of the implementation of the legislation and regulations. As an illustration of this, the issuance of circulars, which was heavily relied upon as having achieved the desired outcomes under the Third Financial Sector Program Loan, does not necessarily mean that the objectives of the circulars have been met, or even that the actions required by these circulars have indeed been carried out. Circulars are merely the medium through which the desired end results are to be achieved. Measurability of end results in the form of quantitative targets (including transitional targets) would significantly improve the grey assessment areas to the benefit of both ADB and the government. [Main text, para. 43(i)] project cycle stage: Completion Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Project evaluation 10. When a reform requires adoption of international standards, then both ADB and the government should communicate with the relevant international body responsible for the adoption of those standards. Where possible, a program specifically for Viet Nam can be designed and agreed. An example of this is the adoption of international financial reporting standards in close coordination with the international accounting standards board. [Main text, para. 43(x)] project cycle stage: Design Lesson Topics: Modality: Program Project Design: Project design Policy & Reform: Reform 2. Related to the point above, the design and monitoring framework should consist of indicators agreed between ADB and the government from the outset. These indicators should either already be present in the government's strategy or blueprint or, if they are not, then they should be included and approved by the highest level of authority of a particular organization. This would strengthen government ownership and accountability. These indicators then should be measured by both ADB and the government at the end of each year of the program. When the indicators fall short, corrective measures should be agreed on and included as a reform in the following year. [Main text, para. 43(ii)] project cycle stage: Design Lesson Topics: 3. These indicators should be linked to the policy matrix, as reforms should contribute to the achievement of these indicators. When a particular reform is delayed, then additional technical assistance resources will need to be provided to address the problem. When policy actions are not completely achieved orwhen they are assessed as either satisfactory or ongoing (as in the case of the two actions for the tranche 2 release of the Third Financial Sector Program Loan), then the subsequent subprogram should immediately focus on these actions at the design stage, so that they do not fall through the cracks between subprograms or even between clusters. The post-program partnership framework is important to maintain dialogue between program clusters. While the policy matrix and the design and monitoring framework are separate documents in form, they should be connected through a cause and effect relationship. [Main text, para. 43(iii)] project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Indicators Policy & Reform: Policy matrix Policy & Reform: Reform 4. Given the challenges of coordination in Viet Nam and the financial sector generally, when a policy action requires coordination between two or more agencies, ADB and the government must first ensure that the coordination mechanism and institutional infrastructure have been established and areworking as envisioned. In the initial stage, ADB staff, including those from the Resident Mission, should participate in meetings and discussions. This is to prevent the existence of a coordination mechanism only on paper. [Main text, para. 43(iv)] project cycle stage: Implementation Lesson Topics: 5. ADB and the government need to recognize that financial sector reforms are complex, have a medium- to long-term gestation period, and require proper sequencing that follows a step-by-step approach. This is especially important when new institutions, legal and regulatory frameworks, or standards are being introduced. Such a focused and phased approach may better accommodate capacity constraints, avoid delays, and enable a more accurate measurement of outcome and impact. [Main text, para. 43(v)] project cycle stage: Implementation Lesson Topics: Policy & Reform: Policy reforms/framework Policy & Reform: Reform 6. Program loans should be focused and consist of targeted high impact policy actions in a few selected areas, which cumulatively lead to the desired outcome. This will increase government ownership of the program and thus avoid delays in implementation of the reforms. [Main text, para. 43(vi)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Program Capacity Development: Ownership Policy & Reform: Reform 7. There needs to be a balance between flexibility and achievement of results. A program cluster modality has in-built flexibility, particularly when designing indicative actions such as for subprogram 2. However, this flexibility is not a carte blanche for changes and should not be used to substitute uncompleted reforms just because they are difficult to implement. When making revisions or substituting policy actions, a careful assessment should be made as to how these revisions or substitutions will affect the achievement of outputs and ultimately the outcome of the program. In the case of Third Financial Sector Program Loan, the policy actions that were reformulated during subprogram 2 should be reassessed as part of future programs. [Main text, para. 43(vii)] project cycle stage: Design Lesson Topics: Modality: Program Project Design: Project design Policy & Reform: Reform 8. Financial sector reforms must be supported by sufficient technical assistance (TA) resources. The design of financial sector TA should be undertaken in close coordination with the relevant executing and implementing agencies and aligned to their work plan. TA projects should be focused, and targeted particularly at reforms that have been substantially delayed. [Main text, para. 43(viii)] project cycle stage: Design Lesson Topics: Modality: Technical Assistance Project Design: Project design Policy & Reform: Reform 9. For capacity building, technical assistance grants are likely to be insufficient. An ad hoc approach to training is insufficient and can be counterproductive. Instead, ADB and the government should discuss the possibility of either a project loan to support capacity building or of Ministry of Finance earmarking a portion of the program loan to fund the capacity building initiatives of a structured medium-term program through the government budget process. Given its importance, this can be considered as a policy action in the policy matrix. [Main text, para. 43(ix)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Program Modality: Project Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development Policy & Reform: Policy matrix | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/viet-nam-third-financial-sector-program-loan-pcr
Agriculture Science and Technology Project: Completion Report | Viet Nam | Agriculture, natural resources and rural development | 2014-09-01 | Ambitious project design including diverse technical and geographic coverage combined with innovative project procedures can delay implementation until all implementing agencies fully understand the process. Competitive bidding for agricultural research based on clear selection criteria that prioritize marginal areas and are formulated jointly by researchers and extension workers can lead to more user-responsive and demand-driven research, which also can be immediately extended to poor farmers. Preliminary impacts reveal more efficient use and more equitable distribution of public research funds. Competitive bidding for extension contracts based on demand-driven proposals generated at field level through a participatory process involving the poor can have a significant impact on (a) the timeliness and transparency of decision making, (b) the variety of extension messages delivered, and (c) the number and range of institutions and organizations providing extension services. Inadequate assessment during project preparation of implementing agencies' financial and human resources capacity, especially when introducing innovative implementation mechanisms, can lead to delays in project implementation. Unrealistic estimates of the time required for students to complete PhD programs can result in having to extend the project closing date. Insufficient or inappropriate design of consulting services, and delays in recruiting them, can cause problems early in project implementation and a failure to provide adequate support for key project activities in which project management has limited experience. Requiring the collection of gender-disaggregated data for all project activities is an effective means to improve gender mainstreaming in project implementation. Monitoring of and regular reporting on the participation of indigenous people in project activities can also lead to better awareness of special measures required for indigenous people. The lack of an effective project performance monitoring system risks undermining the success of a project by failing to properly report project outputs and outcomes. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/agriculture-science-and-technology-project-pcr
Viet Nam: Vocational and Technical Education Project | Viet Nam | Education | 2013-04-26 | 1. Management of vocational and technical education requires extensive coordination among different stakeholders. For the project, there was little collaboration and sharing of lessons among donors. There were also overlapping responsibilities for technical and professional education between the Ministry of Labor, Invalids, and Social Affairs and the Ministry of Education and Training. [Executive Summary, page iv; Main text, para. 86] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Harmonization Sector Related Issues: Education 2. Outcomes need to be integrated with the national system for them to be effectively utilized and sustained. The General Department of Vocational Training adopted the new curriculum development method and implemented it nationwide. In contrast, the labor market information system, production units at key schools, and school industry partnership have become rather inactive as sustaining these outputs requires a lot of resources. [Executive Summary, page iv; Main text, para. 87] project cycle stage: Implementation Lesson Topics: 3. Strong management capacity should be a prerequisite to project implementation. The General Department of Vocational Training (GDVT) lacked experience and capacity to effectively implement the project. The GDVT is overwhelmed with an increasing number of vocational institutions, which may explain the delay in implementing the program accreditation system and technical certification system nationwide. [Executive Summary, page iv; Main text, para. 86] project cycle stage: Implementation Lesson Topics: Project Management: Project management Capacity Development: Capacity development Sector Related Issues: Education 4. Establishing a market-driven vocational and technical education (VTE) system is a long process and requires macro-level links with industry. Public vocational institutions are still financially and strategically dependent on the government. School industry relations remain adhoc. Many of the VTE graduates obtained jobs that were not in the same field as the training they received. The percentage of nonmatching jobs ranges from 10% to 45% across years and degrees. [Executive Summary, page iv; Main text, para. 88] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: 5. The quality of vocational and technical education (VTE) can be improved with more and broader participation of students. University degrees are still preferred over VTE. Many students who enter vocational institutions are low-performing and unmotivated. At the same time, access to vocational education can be more equitable. The system attracts relatively few disadvantaged students such as women, ethnic minorities, and the poor. [Executive Summary, page iv; Main text, para. 89] project cycle stage: Implementation Lesson Topics: Sector Related Issues: Education Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/viet-nam-vocational-and-technical-education-project
Support the Implementation of the Poverty Reduction Programs IV and V | Viet Nam |  | 2013-02-09 | 1. A program cluster approach with prior expected actions enveloped by a medium-term framework with flexibility built into its design is an effective approach to supporting government reforms. It promotes continuous dialogue with the government on reforms and allows for program changes to effectively and efficiently respond to new or worsening risks to the economy and shifts in government policy priorities. project cycle stage: Lesson Topics: 2. The breadth of the reform undertaking and linkages among policy actions across sectors called for a comprehensive approach to dialogue and support by development partners. Several development partners withdrew or reduced their development assistance to Viet Nam, in accordance with their aid practices for middle-income countries. The number of cofinanciers peaked at 11 for Poverty Reduction Support Credits (PRSCs) 6 and 7 and has fallen since, with some impact on the total level of financing under the PRSCs. Some switched their focus to more specialized policy-based operations as deeper reforms were identified in the PRSC policy dialogue. Development partners provided additional funding for budget support while providing technical assistance to the government to support the policy dialogue in highly technical and complex areas. This dialogue, in turn, helped strengthen the institutional capacity of the ministries or agencies concerned. project cycle stage: Lesson Topics: 3. The new series of programmatic development policy lending is taking this broad lesson into account, driven by a new Socioeconomic Development Plan report (2011-2015). Though focused on two of the four pillars of the last Poverty Reduction Support Credit series, policy coordination that reflects linkages in policy areas requires a strong analytical foundation to inform directions and specific decisions. Dedicated and adequate resources for analytical work and short-term technical assistance should enable the government and its partners to assess the potential impacts of related policy actions and help refine the proposals. project cycle stage: Lesson Topics: 4. The Poverty Reduction Support Credit (PRSC) series served as an effective framework for policy dialogue and interactions between the government and donors. The PRSC exercise also served as a common forum for donors to raise concerns with the government and provided the donors with broad access to a large number of ministries and agencies. The role of cofinanciers under the PRSC evolved from providers of financing to partners engaged in policy dialogue and the preparation of operations. Information flows from the government expanded as trust with the partners deepened, which reduced the transaction costs for the government ministries and agencies. project cycle stage: Lesson Topics: 5. In Viet Nam legislation is often comprehensive but implementation weak. Implementation required close monitoring on an annual basis and ensured continued relevance to the government's reform progress. While the Poverty Reduction Support Credit operations provided financial support for implementing the whole Socioeconomic Development Plan (SEDP), they disbursed against the upfront completion of a number of specific reform measures identified within the SEDP agenda by consultation between partners and the government, led by the World Bank. Implementation was also linked to supporting government systems, including synchronized timing to feed into the formal budget cycle. Lack of understanding of the effectiveness of policy implementation makes it difficult to link the impact of policy reforms to the SEDP indicators in the design, monitoring, and framework of this program. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/support-implementation-poverty-reduction-programs-4-and-5-pcr
Central Region Transport Networks Improvement Sector Project | Viet Nam | Transport | 2013-01-10 | 1. The consultant's undertaking preparatory work for phases 1 and 2 were not the same as the construction supervision consultant's for all three phases who were also responsible for preparing Phase 3 subprojects. The construction supervision consultant's thus did not have any responsibility for the design of subprojects under phases 1 and 2. This became an issue after the consultant's that had done the preparatory work for phases 1 and 2 had completed their contract and left Viet Nam. Changed site conditions made it impossible for the contractors to follow the approved design, and so delays occurred. To ensure continuity, only one consultant both for supervision and design should have been selected. project cycle stage: Lesson Topics: 2. It was noted at appraisal: ï¿½preparation of documentation and commencement of civil works for phases 2 and 3 will follow sequentially as individual tasks are completed under Phase 1.ï¿½ This meant that delays and changes in some subprojects in phases 1 and 2, led to delays in subsequent Phase 3 subprojects. In future, this kind of conditionality should be avoided to prevent delays in implementation. project cycle stage: Lesson Topics: 3. In Phase 3, a total of three provinces were delegated full authority to implement subprojects in their provinces. This delegation included negotiations and signing of civil works contracts, approval of variation orders, changes to technical design, and approval of payments to the contractors. The time spent in solving changes in technical design and deciding on variations was significantly reduced, much to the benefit of the project. There was a feeling of local ownership to the subprojects in the delegated provinces. Delegated authority implied increased responsibility, which effectively put pressure on the provincial project management units to solve issues fast that otherwise could hamper the progress and/or negatively affect the quality of the subprojects. Delegation to more provinces could have improved the implementation of the project and avoided some delays. ADB should consider more delegation in future similar projects if provinces have sufficient capacity to handle ADB procedures. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-region-transport-networks-improvement-sector-project-viet-nam-pcr
Central Region Water Resources Project | Viet Nam | Agriculture, Natural Resources, and Rural Development | 2013-01-10 | 1. When policies and views diverge, constructive dialogue is often more rewarding than confrontation. When Decree 115 was promulgated by the government, it directly impacted the loan agreement. While the ADB project team could have invoked the agreement and demanded that either the decree be withdrawn or the project suspended, it chose to conduct constructive dialogue, resulting in a workable compromise. This allowed the physical completion of the project works with its associated benefits. project cycle stage: Lesson Topics: 2. Participation in key decisions can have a major impact on the ownership of policies and institutional changes. Once proposed changes to the irrigation management companies and water user groups (WUGs) had been revised to take stakeholder views into account, they were enthusiastically taken up by government agencies, local administrations, and the intended beneficiaries themselves. The degree of ownership for the revamped institutions was tangible during field visits and interviews. This type of enthusiasm can only come from a participatory approach and a willingness to take into account all points of view as well as the actual field conditions. If an attempt had been made to push through the original revisions of the WUGs, results would have been far less promising. project cycle stage: Lesson Topics: 3. One of the project's major technical problems was the appearance of cracks in the Khe Ngang reservoir dam. This serious issue could have jeopardized a significant part of the project and could also have had further safety repercussions. The problem was resolved when the Ministry of Agriculture and Rural Development, with ADB assistance, mobilized a senior engineering team to inspect the dam and come up with an acceptable and viable technical resolution. This positive and cooperative reaction by ADB allowed the works to be successfully completed with only a slight delay in the implementation schedule. project cycle stage: Lesson Topics: 4. Critical decisions on project investments must be informed, careful, and judicious. At the time of the mid-term review mission in May 2009, contract awards were 8% of the total loan amount and disbursements were 5%. On the basis of such apparent poor performance it would have been possible to cancel the loan and shut down the project at that time. However, a full analysis by the review mission indicated that delays had been caused more by procedural problems than deficiencies in the capacity of the executing agency and that implementation was at the point of finally taking off. The adoption of a comprehensive analysis of the problems facing the project and the decision to continue with implementation allowed the project to be successfully completed. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-region-water-resources-project-viet-nam-pcr
HIV/AIDS Prevention among Youth Project | Viet Nam | Health | 2013-01-10 | 1. Evaluation of the two nongovernment organization-implemented voluntary counseling and testing services demonstrated that population mapping, coordination between government agencies and the recruitment of suitable peers improved service targeting (particularly vulnerable populations). Setting optimistic testing targets that encouraged broad-brush recruitment of clients adversely affected testing results. project cycle stage: Lesson Topics: 2. Projects should be responsive to change; as the media environment altered, the project design should have been adjusted. project cycle stage: Lesson Topics: 3. Behavioral change communication, whether through mass media or interpersonal communication, is complex and specialized, and requires specialized expertise; a chief technical adviser should be provided throughout project implementation. project cycle stage: Lesson Topics: 4. Low cost norms made it difficult to attract competent, full-time staff for the central project management unit, resulting in project delays. There is a need to ensure proper staffing of the central project management unit. project cycle stage: Lesson Topics: 5. Project delays were mostly caused by lengthy administrative processes resulting from complex ADB and government procedures. project cycle stage: Lesson Topics: 6. Project monitoring was not systematic. An indicator list was prepared during the project's early stages, but the indicators were not adjusted and routinely reported as a result of weak monitoring capacity. project cycle stage: Lesson Topics: 7. A lack of exit planning resulted in no proper plan for continuation of activities and future use of information, education, and communication materials, including websites, interpersonal communication and training materials. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/hiv-aids-prevention-among-youth-project-viet-nam-pcr
Housing Finance Project | Viet Nam | Finance | 2013-01-10 | 1. Careful poverty analysis, a proper demand and supply analysis for housing, better selection criteria, as well as more pro-poor loan procedures and flexibility in the loan size, term, and use would have enhanced the inclusiveness and beneficial impacts of the project. Given the targeted low-income segment and limited institutional capacity, such projects should not be overly complex in design and difficult to implement. Having a variable interest rate on the loan did not help. Fixed interest rates are more appropriate and preferred by low-income and poor borrowers. The spread levied by some of the participating financial institutions (PFIs) over their borrowing rate from the State Bank of Viet Nam (Housing Finance Facility) was high. The project's capacity building component provided for development of hedging instruments to enable PFIs to offer fixed-rate housing subloans. Hedging is practically nonexistent in Viet Nam. Further, given the weak institutional capacity, consulting support should be properly phased out over the implementation period of the project. Because consulting support ceased in 2006, component C was not fully utilized. More flexible instruments and such product design innovations as graduated-payment mortgages, flexible repayment arrangements, and multipurpose loans might be considered to suit such type of borrowers. In parallel, encouraging financial discipline among low-income borrowers is also important. project cycle stage: Lesson Topics: 2. There are perceptions among some government agencies in Viet Nam that the interest rate should be much lower than market rates and be subsidized. Rather than focusing solely on the financing side, the complex issue of housing for the urban poor also needs to be looked at from the viewpoint of supply side constraints and the willingness of lenders to consider this an appropriate business line. Targeted subsidies that are separate from financing also need to be considered. Again, access to credit is more important than is providing interest rate subsidies. In every part of the developed and developing world, housing for low-income and poor people includes subsidies in some form as part of national social policy. Such schemes together with interest rate subsidies are plausible so long as the lending institutions continue to receive subsidies from the government. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/housing-finance-project-viet-nam-pcr
Second Lower Secondary Education Development Project | Viet Nam | Education | 2013-01-10 | 1. The recruitment of consultants by executing agencies remains time-consuming. This problem is not specific to the project, but common in all ADB-financed projects in Viet Nam. Delays in consultant recruitment result in delays in implementing the entire project. In the future, advance actions and project readiness filters should be applied to minimize start-up delays. project cycle stage: Lesson Topics: 2. The procurement capacity of the executing and implementing agencies, as well as the context of the project, needs to be considered when determining procurement methods. Their procurement capacity needs to be developed in order for them to implement procurement methods and accurately follow procedures and guidelines. Tracking of project implementation becomes difficult if procurement documentation does not follow requirements. project cycle stage: Lesson Topics: 3. The design of capacity building activities needs to be better structured with a model defining how knowledge and skills will be transferred and including pre- and post-training assessments to measure impact. Without a structure, capacity building activities are reduced to the number of persons trained. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-lower-secondary-education-development-project-viet-nam-pcr
Upper Secondary Education Development Project | Viet Nam | Education | 2013-01-10 | 1. There was some concern that the feasibility study report prepared by Ministry of Education and Training (MOET), which was the official appraisal document on the government side, was not sufficiently consistent with the report and recommendation of the President. Considerable discrepancies between the two key documents, due to limited communication between MOET and the project preparatory technical assistance (TA) consultants, were observed. As government agencies, including the state treasury, preferred to use the feasibility study report in reviewing and processing documents submitted by the national project implementation unit, the inconsistencies often hindered timely implementation. TA consultants should be formally required to work out issues with the government before submitting any report to avoid such discrepancies. project cycle stage: Lesson Topics: 2. The project could have avoided some implementation difficulties had the project manager been appointed earlier and assisted with the design of project details. Compared with the size of the project, the consultant services package was too small. The national project implementation unit (NPIU) had to take on too much of the work. While this helped in its Capacity Development, the NPIU was observed at times to have difficulty finding technically qualified staff to implement project activities that were not fully supported by the loan implementation consultants because of their limited contracts. This problem was pointed out to the government and the latter has agreed to a larger consulting service input for recently approved loan projects to ensure their timely and high-quality implementation. The NPIU must also be structured better so that suitably qualified staff are identified and appointed earlier in the process and the timing of external consulting support is better matched with project timelines. project cycle stage: Lesson Topics: 3. Positive outcomes in terms of cost and quality were associated with using market prices in cost estimates for civil works and involving local communities in the management of works. This fact was appreciated by the government, which valued ADB's flexibility in this aspect of the project's operation. Escalation of civil works costs has been a major delaying factor in numerous ADB-funded projects in Viet Nam. In this project, however, Ministry of Education and Training and ADB had agreed from the start to use market prices in the cost estimates for construction contracts, so the national project implementation unit never encountered any unexpected overrun in civil works costs. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/upper-secondary-education-development-project-viet-nam-pcr
Central Region Urban Environmental Improvement Project | Viet Nam | Water and other urban infrastructure and services | 2013-01-04 | 1. The recruitment of consultants by executing agencies remains time-consuming. This problem is not specific to the project, but common in all ADB-financed projects in Viet Nam. Delays in consultant recruitment result in delays of the entire associated project. In the future, advance actions and project readiness filters should be applied to minimize start-up delays. project cycle stage: Lesson Topics: 2. The loan covenants required compliance with most financial covenants within a certain number of months from the loan effectiveness date. It would be better to link the achievement of such covenants to the delivery date of project assets instead of the loan effectiveness date. project cycle stage: Lesson Topics: 3. Sanitation coverage indicators should be simplified by using nominal targets rather than ratios. Monitoring of coverage ratios requires that two independent parameters - physical outputs and population growth - be known. This is complicated by the continuing growth of the service areas under the control of the concerned utilities. project cycle stage: Lesson Topics: 4. The project provided sufficient resources to implement gender-focused design features. The provision of adequate resources is critical to both successful design and effective implementation of the gender action plan. The project was an excellent example of how attention to gender equality through a comprehensive and well-targeted gender action plan can lead to practical and strategic gender equality results. project cycle stage: Lesson Topics: 5. The calculation of the economic and financial internal rates of return at appraisal should be made in a manner that facilitates their re-evaluation at project completion. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-region-urban-environmental-improvement-project-pcr
Viet Nam: Small and Medium-Sized Enterprise Development Program Cluster (Subprograms 1 and 2) | Viet Nam | Industry and Trade | 2012-12-17 | One significant lesson is the importance of monitoring the results of reform programs even after the financial closure of the program, ensuring that the government and its various implementing agencies develop a strong sense of ownership for the reform initiatives. As pointed out in para. 19, these types of small and medium enterprise reform measures would usually take much longer time to achieve real outcomes on the ground. [Main text, para. 37] project cycle stage: Implementation Lesson Topics: Monitoring &amp; Evaluation: Monitoring and evaluation Sector Related Issues: Industry and Trade | Validation of Project/Program Completion Report | Partly/less than successful | http://www.adb.org/documents/viet-nam-small-and-medium-sized-enterprise-development-program-cluster-subprograms-1-and-2
Viet Nam: Agriculture Sector Development Program | Viet Nam | Agriculture, Natural Resources, and Rural Development | 2012-12-10 | Program experience demonstrates that accompanying investment projects in a sector development program loan matter. ADB, in selecting the sector lending modality as a broad-based lending instrument, should give careful consideration to the choice of accompanying projects intrinsically linked with the sector performance in all its dimensions. In this instance, greater benefits could have accrued by linking research and extension to some of the allied institutions such as land tenure, land use, land distribution and classification, marketing, agricultural credit, more extensive extension training, and human resource development than to small and medium enterprises, which in the end focused substantially on nonagricultural activities. [Main text, para. 27] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Harmonization Modality: Lending modality | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/viet-nam-agriculture-sector-development-program
Viet Nam: Teacher Training Project | Viet Nam | Education | 2012-12-10 | Synergies between lower secondary education (LSE) curriculum development and LSE teacher training projects are important, as the new teacher training curriculum should be consistent with the LSE curriculum. [Main text, para. 30] project cycle stage: Design Lesson Topics: Capacity Development: Capacity development Sector Related Issues: Education | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/viet-nam-teacher-training-project
Emergency Rehabilitation of Calamity Damage Project | Viet Nam | Agriculture, natural resources and rural development, Transport | 2012-10-01 | Project start-up. A look at previous and ongoing projects implemented by the Ministry of Agriculture and Rural Development (MARD) in Viet Nam shows a common pattern: slow initial start-up accompanied by delays, slow progress, and confusion followed by an intense pace of implementation from about the midterm of the project period, followed in turn by successful completion of the project scope, often at a higher level of coverage or output than originally conceived (see for example the project completion reports or PCRs for the Rural Infrastructure Sector Project or RISP and the Second Red River Basin Sector Project). This project has followed the same pattern. The obvious lesson from this experience is that the MARD and the provincial departments of agriculture and rural development are capable of implementing medium- to large-scale rural infrastructure projects, but there are some structural or institutional factors that constrain project start-up and initial implementation. As it is likely that the MARD will continue to be an executing agency supported by ADB in the future, it would seem worthwhile to expend some effort in determining what these factors are and identifying means to overcome or mitigate them. It is noted that since the PCR was completed, an effort has been launched by the resident mission and the MARD to try to reduce start-up delays by removing constraints to the government use of ADB's advance action procedures. ADB's disaster and emergency policy. A further lesson learned or at least hinted at by the experience of implementing this project is that, given the realities of the type of investment ADB is best adapted to support in view of its funding modalities, consultant recruitment procedures, and procurement regulations (i.e., generally capital-intensive infrastructure rehabilitation) and the level of supervision possible at field level (i.e., generally less intense than bilateral agencies or United Nations organizations), ADB's current policy on disasters and emergency assistance may be too restrictive. A preparation period of only 3 months may be inadequate to allow a full damage assessment and the design of rehabilitation and remedial measures. Moreover, if the disaster is weather related, rebuilding service infrastructure without improved design standards and protection from future severe weather is likely to be a waste of effort because the rebuilt infrastructure will still be vulnerable to future floods, typhoons, or storm surges. This will entail a longer period than the 2-year implementation period currently prescribed in the policy and in the operations manual. Provincially delegated projects. For projects that entail the delegation of design and implementation to provincial authorities, it is important to ensure that provincial implementation staff are fully briefed and trained on ADB safeguard requirements such as land acquisition and resettlement. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/emergency-rehabilitation-calamity-damage-project-pcr
Ho Chi Minh City-Long Thanh-Dau Giay Expressway Technical Assistance Project | Viet Nam | Transport | 2012-10-01 | The local governments and parties concerned should have streamlined their decision- making process in a timely manner to avoid delays. In order to avoid delays, the project should have been planned more carefully. If so, there may not have been a need to change the scope during the project implementation. International consulting firms should have obtained ample information on potential difficulties in setting up the project office and other legal requirements on such issues. They should also have been informed in advance that unless they register the project office with local authorities, the executing agency will be unable to make payments. International consulting firms should have been made aware of the appraisal and approval procedures for the design documents, particularly when appraisal is carried out by a third party. It can be a time-consuming process, thus delaying payments to the design consultants. It is advisable to start procurement of an appraisal consultant (if required) early so that he or she is ready to be recruited as soon as the design work has started. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/ho-chi-minh-city-long-thanh-dau-giay-expressway-technical-assistance-project-pcr
Northern Power Transmission Sector Project | Viet Nam | Energy | 2012-10-01 | ADB's appraisal of Component B of the project was inadequate. This oversight eventually delayed loan closing and caused the underutilization of the ADB loan. ADB should not approve funding for projects without independent evaluation and diligent review. The transmission and substation subprojects that had not been appraised prior to loan presentation took longer to process than planned and call into question the justification for the sector loan approach. All but one subproject had been identified during implementation, and problems that could have been tackled prior to approval led to significant delays and increased administrative effort during project implementation. ADB should closely review the use of sector loans to ensure that problems that could be addressed during project preparation are not being deferred for the sake of expediency. The delegation of loan administration to the Viet Nam Resident Mission improved ADB's ability to monitor project progress by allowing for more regular and informal meetings with project management staff in order to obtain information firsthand, rather than relying on quarterly reports, which were sometimes late and/or inadequate. The parallel cofinancing of part A with Agence Franc?aise de De?veloppement (AFD) worked well. The underlying reason was AFD acceptance of ADB rules and procedures for equipment procurement, which enabled consistent processing of ADB and AFD procurement packages. The leveraging of ADB's participation greatly assisted completion of the national power sector development program and the arrangements could be used in similar circumstances elsewhere. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/northern-power-transmission-sector-project-pcr
Health Care in the Central Highlands Project | Viet Nam | Health | 2012-03-01 | 1. The selection of adjoining provinces in the Central Highlands had several benefits. First, these provinces have a large number of poor ethnic minorities and other residents with low health status and limited access to health services. As such, these areas align with both the government's policy of supporting disadvantaged groups and ADB's overarching objectives of tackling poverty. Ethnic minorities needed continuous targeting as their health status and sociocultural adverse health behaviour warranted project interventions. Second, the selection of adjoining provinces reduced travel times and administrative overheads for project monitoring and supervision. Third, selection of these provinces avoided overlap with other major development partners in the country. On the other hand, the lack of allocative criteria led to unequitable resource distribution among the provinces, though no significant variation in performance was found, as provinces used funding according to their internal technical and absorptive capacity. project cycle stage: Lesson Topics: 2. The Joint Annual Health Review, 2010 notes that a shortage of human resources continues in several fields, including preventive medicine, public health, pediatrics, infectious diseases, mental illness, forensics, pathology, tuberculosis and leprosy, food safety and hygiene inspection, medical technology, engineers specialized in medical equipment, health statistics, and hospital management. The provincial health departments identified postgraduate training in health specializations as a major project benefit, leading to more available district staff and specializations. However, lack of staff in the project areas continues to be a major constraint for service delivery and requires future support. The Ministry of Health has developed policies and has been actively supporting methods to develop training in disadvantaged regions, including direct recruitment of students for training without entrance exams35 using specific contracts between health institutions and training facilities. project cycle stage: Lesson Topics: 3. The considerable delays in implementation were due to complicated procurement regulations of both ADB and the government. These delays and price inflation resulted in the quality of civil works being compromised in some locations and some facilities deviating from the design. Delays in equipment procurement led to the purchase of inappropriate and out-dated equipment. Limited district administrative capacity resulted in delays in imprest accounts being replenished, which constrained progress. Current government per diem allowances for training courses are very low; this limited participation. Delays in procuring consultants, especially for the Health Care Fund for the Poor, delayed disbursement. project cycle stage: Lesson Topics: 4. Investment in civil works and equipment has recurrent budget implications. Monitoring of whether provinces are allocating greater resources to recurrent budgets is difficult as financial tracking is complicated in a devolved financial management system. User fees may help support the ongoing expenditure support for buildings and equipment in the curative sector, but the preventive system has limited capacity to mobilize resources outside of the state budget. Given these constraints, future projects must have investment allocations that reflect the limited capacity for increasing recurrent expenditure, and use appropriate technology that has manageable cost implications. project cycle stage: Lesson Topics: 5. The central project management unit and provincial project management units have monitored financial flows and activity progress as part of routine quarterly reporting. Limited attention was paid to project outcomes in the project framework; outcomes were not changed during the project. Similarly, measurement of the outcomes of the training programs appears to have been limited. Given ADB's results-based approach to Project Management, both the Ministry of Health and ADB should have given a greater focus to monitoring and evaluation. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/health-care-central-highlands-project
Second Red River Basin Sector Project | Viet Nam | Agriculture, Natural Resources, and Rural Development | 2012-03-01 | 1. Project success almost always depends on simplicity of design and it is usually counterproductive to include superfluous components no matter how much they may reflect current development thinking or theories. project cycle stage: Lesson Topics: 2. Whenever possible, project design should target contiguous or proximate project areas with similar physical and environmental characteristics. project cycle stage: Lesson Topics: 3. To the extent possible and unless necessary, it is best to avoid making the implementation of one component of a project contingent on achievements of another component. project cycle stage: Lesson Topics: 4. Pursuing long-term institutional reforms through investment projects aimed at infrastructure development needs careful design and the full ownership of the borrower. project cycle stage: Lesson Topics: 5. Shortcomings in project and technical assistance design should be identified and acted upon early in implementation to avoid undue expense and a delayed accrual of benefits. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-red-river-basin-sector-project
Rural Health Project | Viet Nam | Health | 2011-12-01 | Priorities for health sector development. One issue with health projects in Viet Nam is that the Ministry of Health (MOH) and the provinces typically give priority to upgrading facilities and staff. Provinces may be less focused on sector reforms and improving outcomes, perhaps as this is not seen as a role of projects, and the results are less understood and tangible. Provinces need to focus more on improving the quality of services and maintaining assets. Piloting reforms. While government ownership of project formulation was strong, proposed pilots were too ambitious given MOH constraints and the lack of detailed plans or technical support. On the other hand, the project flexibly responded to several policy changes and national developments by adjusting its scope, which counterparts appreciated. Demand-led programming improved project impact. Targeting. The project improved services for the poor and had a substantial focus on maternal care but provided less targeted support for ethnic minorities. Several of the interventions for ethnic minorities didn't materialize. The project evaluation study showed that the poor in general and ethnic minorities in particular benefited from the government support for commune health stations (CHSs) and health insurance, while ADB funding provided more general public support. More could have been achieved with better targeting for minorities, assuming MOH concurrence. Lengthy administrative processes. Implementation delays were largely caused by lengthy procurement and financial control procedures at all levels. While the project management unit (PMU) and provincial project management unit (PPMU) capacity was also an issue, the government's administrative procedures were time consuming. ADB administration was considered relatively efficient. Monitoring and evaluation. Data were regularly collected, and efforts were made not to create a separate monitoring system but use existing information. However, project monitoring was incomplete and insufficiently used as a management tool to achieve results. Substantive project evaluation was very useful. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/rural-health-project
Third Provincial Towns Water Supply and Sanitation Project | Viet Nam | Water and other urban infrastructure and services | 2011-10-01 | Appropriate monitoring indicators are required. A project framework or design monitoring framework should list SMART (i.e., specific, measurable, acceptable, relevant and time-bound) indicators that, as much as possible, are part of the specified agenciesï¿½ established monitoring program, such as number of connections, water produced etc. Introducing new indicators should be accompanied by a strong support program because if agencies do not see the benefit of monitoring certain indicators, they will be unwilling to pay for collecting the data, such as the health indicators in this case. Indicators should be specific as to what output, outcome, and impact is being measured, when this will be done, and by whom. The lack of sufficient resources and guidance has affected the quality of the public health awareness program's (PHAP) monitoring, and the absence of specific drainage indicators prevented assessing that outcome. Water supply and sanitation coverage indicators need to be simplified. Monitoring coverage ratios requires the monitoring of two independent parameters: physical outputs and population growth. Sometimes this is complicated by a change in delineating the service area of the utilities. Nominal targets are therefore easier to monitor than ratios and are equally functional for assessing achievements. Nonrevenue water (NRW) reduction indicators need to be versified. Expressing the NRW levels in liters lost per connection per day, demonstrates a large variation in results. The best performing systems in terms of NRW ratios--NRW reduction targets are defined as the ratio of unbilled production versus total input capacity in m3/day--are not necessarily the lowest in absolute terms. To get a fundamental idea on actual performance, NRW results should at least be reported in ratios and absolute terms. Sanitation credit scheme requires an exit strategy. The project foresaw the establishment of a sanitation credit scheme, financed by the project through a grant from the central government. However, it did not address what should happen with the grant money and potential revenues once the project was completed. This lack of clarity has made Provincial Viet Nam Womenï¿½s Unions (PVWUs) reluctant to continue the program by revolving the first batch of repaid credits and expanding it to other communities outside the original project area. In all provinces, the provincial peopleï¿½s committee (PPC) issued specific orders that PVWUs are in charge of the funds. The program may be continued after loan closing and initiatives may be extended outside the original project area. PVWU experience sharing is beneficial to effective implementation. Although guidelines were provided for the sanitation revolving fund, each PVWU had the flexibility to implement it differently. Sharing of experiences, especially at the beginning stages, could have contributed to a more streamlined and effective implementation of the community environmental sanitation improvement (CESI) program. Project outcome and outputs need resource allocation. The identification and procurement of small-scale sanitation improvements was not carried out through community participation as intended, but directly by provincial project management units (PPMUs). The strong investment focus and the PPMUsï¿½ lack of knowledge about community-based approaches should have been identified as risks and mitigated by the project design through resource allocation. Likewise, the introduction and enforcement of local regulations on sanitation and environment protection was not supported by the project nor included as a covenant. Although the introduction was still achievable, enforcement would need support from the project. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/third-provincial-towns-water-supply-and-sanitation-project
Provincial Roads Improvement Sector Project | Viet Nam | Transport | 2011-01-08 | 1. The bid value of the project consultant was found to be at lower side. Road design should have been the sole responsibility of the project consultant and he should not have been subcontracted and fully passed the task on to a less experienced and capable provincial consulting firms with low subcontract value. This resulted in poor quality of surveys and detailed design works and a need to correct the design during implementation but also in substandard designs at certain locations. Inadequate payment by the project consultant to provincial consulting firm meant that the proper and necessary engineering surveys were not done at all locations. project cycle stage: Lesson Topics: 2. The views of the provinces on requirements in the road classification and design - for instance, their preference for paved shoulders over earthen shoulders to better accommodate larger, two-way traffic - should have been adequately addressed at project conceptualization and or at project design and formulation stage. project cycle stage: Lesson Topics: 3. The project encouraged the involvement of small contractors but they lacked resources and expertise and their participation should not have come at a cost in quality and delays. While their involvement in construction was required because they were familiar with local conditions, they needed proper technical and financial support. project cycle stage: Lesson Topics: 4. Repackaging the road contracts to make them larger and more financially attractive to bidders was successful and made contract management easier for the provinces. project cycle stage: Lesson Topics: 5. The executing and implementing agencies believed that implementation of the EMDP should not have been their responsibility, was outside their area of expertise, and interfered with project implementation. They said that it should have been carried out through other more suitable agencies, such provincial committees on ethnic minorities or women's unions. project cycle stage: Lesson Topics: 6. Frequent ADB missions throughout the implementation period, particularly visits to provinces, had a positive effect and facilitated timely decision making. project cycle stage: Lesson Topics: 7. The traffic projections at the project preparation stage did not anticipate that heavy vehicle traffic would greatly increase on the project roads once they were improved. The result was an inadequate design, roads not built to withstand such heavy truck use, and greater than anticipated damage to some upgraded sections where this traffic has grown. This problem should be foreseen in future similar projects and tackled during design. project cycle stage: Lesson Topics: 8. The absence of official records on land ownership made it difficult and time consuming to pay compensation to and rehabilitate people affected by the project. The PDOTs should approach the responsible local administrations well in advance of this kind of project either themselves or through specialized agencies to ensure that records are available to implement resettlement when construction begins. project cycle stage: Lesson Topics: 9. The division of projects into many phases consumes additional time and resources and causes delays in project implementation. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/provincial-roads-improvement-sector-project
Kunming-Haiphong Transport Corridor-Noi Bai-Lao Cai Highway Technical Assistance Project | Viet Nam | Transport | 2010-11-01 | The use of a technical assistance (TA) loan for project preparation rather than including project preparation in the investment loans is fully justified because (i) it enabled project costs, revenues, and social and environmental impacts to be more accurately assessed before preparation and signing of the investment loan; and (ii) it reduced the borrower's commitment charges caused by implementation delays of 20 months. The multitranche financing facility (MFF) mode was mainstreamed into ADB's financial operations in July 2008. (The MFF was introduced in August 2005.) TA and investment loans can be combined in an MFF as separate tranches. However, use of an MFF should not be recommended for large and complex projects such as the project highway because there is high risk of project cost overrun. The estimated total cost increased from $620 million at the TA loan appraisal to $1,216 million at the investment loan appraisal. The project cost would have considerably exceeded the maximum financing amount if an MFF had been used. However, if an MFF had been used the borrower could have benefited from the flexibility in timing of ADB financing and ADB's early commitment to the investment loans without incurring the commitment charges. Senior staff of both the Vietnam Expressway Corporation (VEC) and Ministry of Transport (MOT) had significant experience in implementing large- scale road development projects. Both agencies had sufficient capacity to carry out the project, and the capacity was further enhanced through the project. The delays in resettlement planning were mainly caused by low capacity of project provinces and districts but not of the executing or implementing agencies. The project provinces and districts should be involved from the early phases of resettlement and ethnic minority development plan (REMDP) preparation. Terms of reference for the consultant should be more realistic in predicting the project period, particularly for new infrastructure projects with considerable social and resettlement impacts, and multiple works procurements. In any project implementation, it is much more efficient to identify and correct problems in the initial part of the project period. The frequency of ADB review missions in the initial phase of the project achieved this efficiency and did a great deal to prevent further delays. The lesson is to have a higher frequency of review missions in the early phase of project implementation. In a fixed-fee services contract, inclusion of the value of the project contingency in calculation of the advanced payment should be carefully explained in the request for proposals. Similarly, the regulations applied to value-added tax (VAT) duties on national subconsultancy services should be clearly stated. The status of completion should be carefully examined before loan closure. In the event that there are outstanding activities, the contractual arrangements for completion should be carefully defined and committed before loan closure. It is a risk to assume that completion can take place under another loan with an unknown time frame and be dependent on a third-party consultant. Preparation of detailed design and bidding documents for the equipment packages should not have been included in the scope of the TA loan. The employment of an independent design appraisal consultant has been expedient and has avoided delays. Consideration should be given to the inclusion of an independent appraisal consultant in future large and complex design preparation projects with an underresourced implementing agency. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/kunming-haiphong-transport-corridor-noi-bai-lao-cai-highway-technical-assistance-
Vocational and Technical Education Project | Viet Nam | Education | 2008-12-26 | 1. An adequate project management structure should be in place before the Project starts to minimize/avoid implementation delays. A key issue was the weak delegation of management and budget responsibility to the implementing agency and project implementing unit (PIU). It proved difficult to mobilize capable project staff before project effectiveness. Initial delays in project implementation were largely caused by the inexperience of executing/implementing agencies in Project Management, in spite of the advisory technical assistance for capacity building. The executing/implementing agencies were not fully involved in project preparation and therefore faced tremendous capacity constraints once the responsibility was transferred to them. The insufficient delegation of authority to the implementing agency, as well as to the PIU, made the submission of withdrawal applications to ADB very time consuming. The initial lack of staff experienced in procurement, especially in handling bidding at the PIU and sub-PIUs at key schools, might have been another reason for these delays. [Main text, paras. 24-26, 44] project cycle stage: Appraisal Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project management Capacity Development: Capacity building 2. The scope of project coordination work needs to be in line with the capacity of the implementing agency. The Project was cofinanced with three agencies - AFD (Agence Francaise de Developpement), JICA (Japan International Cooperation Agency), and NDF (Nordic Development Fund) - on a parallel basis, which made project coordination difficult. The administration of key schools belonging to different ministries and provincial governments required extra coordination, compounding the complexity of project management and implementation. It would have been better to limit the number of funding agencies and government agencies to match the capacity of the implementing agency and the project implementation unit (PIU). Despite initial difficulties in coordination and managing the subprojects under cofinancing, the PIU took corrective measures such as streamlining procurement procedures under the AFD-financed project. The implementing agency, on its end, is developing a new organizational structure to better manage donor-funded projects. [Main text, para. 45] project cycle stage: Design, Implementation Lesson Topics: 3. Future projects may consider setting aside an endowment from the loan and counterpart funds from government and employers for the operation and maintenance of school equipments and facilities. Schools should also be encouraged to generate additional funds to support their recurrent activities. In the Vocational and Technical Education Project in Vietnam, the lack of funds for repair and maintenance of equipment and buildings was a common concern among schools. [Main text, paras. 13, 46] project cycle stage: Operation Lesson Topics: Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Funding Project Management: Operation and maintenance | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/vocational-and-technical-education-project
Teacher Training Project | Viet Nam | Education | 2008-01-12 | The project implementation unit (PIU) could have performed better had its composition included both technical and academic experts to effectively manage the logistics and establish a solid implementation framework and had there been information sharing from the project management unit of the project preparatory techical assistance. The project completion report of the Teacher Training Project in Viet Nam noted the PIU's weak implementation capacity due to its members' lack of involvement in designing the project and limited experience in project management. [Main text, paras. 57, 75(i,iv)] project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management When loan projects do not include advisory technical assistance projects for project implementation unit (PIU) capacity building, having a full-time, qualified staff for key positions (i.e., full-time project manager, financial and procurement unit heads) can facilitate implementation of project activities. The project's self- assessment has indicated the lack of full time qualified staff that contributed to its slow progress during the first half of the implementation period. [Main text, paras. 58, 75(ii)] project cycle stage: Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/teacher-training-project
Lower Secondary Education Development Project | Viet Nam |  | 2007-11-23 | The improvement of lower secondary education quality involves several factors. Teachers require time and support to change teaching methods. The textbook replacement training has caused some teachers (especially those in the remote and ethnic minority areas) to improve their knowledge and skills in teaching aids and equipment. Modern teaching methods require greater access to learning resources than traditional methods. The methods of student assessment need to be adapted to the new curriculum and teaching methods. The quality improvement process therefore requires efforts from both students and teachers and it takes longer - beyond the project period. In order to deliver the outputs and attain the outcomes, together with improved school facilities, it is important to increase the number of teachers from ethnic minority background and improve the quality of teachers through annual in-service training or refresher courses. The Project created a student-friendly learning environment and it encouraged the participation of the community in building more classrooms and school facilities. It became an example of socialization of education. ADB support plays a catalyst role in mobilizing funds from the community for the education of their children. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/lower-secondary-education-development-project
Second Provincial Towns Water Supply and Sanitation Project | Viet Nam |  | 2006-12-15 | Advance action for land acquisition and resettlement should be required, as consultation and agreements with affected households can take a very long time. project cycle stage: Concept Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Methodologies/Approaches: Consultation/Participation Each procurement package should be established in such size that bidding will be competitive among qualified contractors, while also trying to minimize the number of contract packages to lessen the executing agency's workload for controlling contractors and suppliers. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Executing/Implementing agencies Project Management: Procurement Engaging two teams of consultants to manage implementation of a project is ineffective, even if project sites are geographically spread, as staffing will be duplicated in some positions (including that of team leader). project cycle stage: Implementation Lesson Topics: Project Management: Consultants Project Management: Project management Capacity Development: Human resources management The consultants, including foreign experts, should be retained until the entire system is in operation and commissioning tests have been completed so that they will be held responsible for assessing the final outcome, including the quality of works, and for proposing corrective measures for defective works or shortages, if any. project cycle stage: Implementation, Completion Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Consultants The project implementation schedule should be established taking fully into account the government's approval procedures that require approval of higher authorities for feasibility studies, project budgets, the bid plan, bidding documents, bid evaluation, and contract awards. At the time of project preparation, delegation of approval authorities for critical activities to the lower levels should be discussed and agreed. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project management Country Context: Decentralization The water supply companies (WSCs) that will be the end users of completed project facilities and responsible for repayment of the loan should be party to the contracts with contractors, such that the WSCs and provincial project implementation offices (PPIOs) are authorized to supervise or control the performance of the contractors and suppliers. project cycle stage: Implementation Lesson Topics: Project Management: Procurement Project Management: Project management Project Management: Project supervision Sector Related Issues: Health and sanitation management Sector Related Issues: Water resource management Training workshops prior to project implementation are needed to familiarize staff of project implementation offices at local level with ADB procedures for selecting consultants, procurement, and disbursement. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Project Management: Consultants Project Management: Procurement Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/second-provincial-towns-water-supply-and-sanitation-project
Rural Infrastructure Sector | Viet Nam |  | 2006-09-15 | 1. Collaboration among development partners through harmonization of processes and utilization of comparative advantages helped develop a comprehensive, strategic, and attainable reform agenda. The identification and sequencing of a comprehensive reform agenda covering a medium-term period requires strong analytical support. In Viet Nam's Poverty Reduction Support Credit (PRSC) program, this support was effectively provided by development partners in consultation with the government and relevant stakeholders (i.e., as evident, among others, in the joint analysis to identify appropriate policy actions and implementation arrangements for the first 5-year PRSC cycle and comprehensive analytical reports covering the three pillars of the Comprehensive Poverty Reduction and Growth Strategy such as the annual Vietnamese Development Reports). [Main text, paras. 7, 40] project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Harmonization Crosscutting Issues/Themes: Poverty reduction Modality: Program Modality: Technical Assistance Policy & Reform: Reform 2. The comprehensive nature of the Poverty Reduction Support Credit (PRSC) process led to a common realization among all stakeholders that progress in different sectors and among different measures within one reform agenda would be uneven. Under the commonly agreed comprehensive PRSC framework, development partners and policymakers have to harmonize their project process to identify and address those development areas requiring special attention. [Main text, para. 41] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Policy & Reform: Reform 3. The increasingly broad scope of the policy dialogue raises logistical challenges to the process hence requiring effective coordination mechanisms. Effective coordination mechanisms have continuously evolved over time in order for operations to be delivered on an annual basis. A high level of coordination and communication were required at various levels: among development partners, among government agencies, and between development partners and government agencies. Given the comprehensive nature of the reform process and the ever-growing number of cofinanciers, it became necessary to establish a unit responsible for coordination activities, to deal with the program agenda, including monitoring and reporting, awareness raising, capacity building and reform outcome dissemination. [Main text, paras. 25-27, 42] project cycle stage: Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Modality: Program Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting Project Design: Project design Capacity Development: Capacity building Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy matrix Policy & Reform: Reform Methodologies/Approaches: Consultation/Participation 4. Alignment of annual multisector programs (i.e., Poverty Reduction Support Credit or PRSC which outline development partners' framework) with the government's broader, medium-term socioeconomic development plan (SEDP) facilitates reform implementation and achievement of development goals. In Vietnam, this process required close donor coordination and common dialogue with the government focusing on the sequencing and timing of policy measures, instead of the policy measures themselves. By moving away from formal conditionality, PRSC operations became a tool for supporting the government in achieving its stated development goals and implementing its reform program. This coordinated approach reduced the transaction cost of both the government and development partners and enabled the latter to focus on their respective areas of expertise and comparative advantage. [Main text, para. 43] project cycle stage: Design, Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Alignment Crosscutting Issues/Themes: Harmonization Crosscutting Issues/Themes: Poverty reduction Modality: Program Policy & Reform: Policy matrix Policy & Reform: Policy reforms/framework 5. Program implementation would have been more efficient had the government's Comprehensive Poverty Reduction and Growth Strategy (CPRGS) and socioeconomic development plan (SEDP) been unified, as this would have eliminated the need for a dual reporting, monitoring, and implementing systems for the CPRGS and SEDP. The CPRGS was instead prepared in parallel to the SEDP 2001-2005, as the action plan to achieve development outcomes envisaged in the SEDP. The existence of CPRGS in parallel to the SEDP proved to be less efficient, as double reporting and monitoring tracks were unavoidable. [Main text, paras. 4, 44] project cycle stage: Feasibility, Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting 6. Future poverty reduction support credit projects (Poverty Reduction Support Credit) may require exploring a new lending modality more suited to the nature of the PRSC framework. The Support to the Implementation of Poverty Reduction Program (SIPRP) was processed using an innovative lending modality that departed from conventional conditionality-type program loans. The SIPRP followed a program-based approach that was designed to be disbursed in a single tranche. The loan was disbursed upon loan effectiveness, because the SIPRP was formulated based on actual performance or prior actions that were complied with. Although it was a single-tranche program, the SIPRP was in fact part of a continuum multiple-tranche program loan, with emphasis on the feasibility of policy measures. The SIPRP design faced unavoidable challenges as it had to be classified under the existing lending modalities. [Main text, paras. 3, 45] project cycle stage: Appraisal Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Disbursement Loan Agreement: Covenants Modality: Lending modality Modality: Program Policy & Reform: Policy reforms/framework Methodologies/Approaches: Program Approach 7. The Resident Mission (RM) needs to be adequately resourced, both in terms of both personnel and financial resources, to ensure the quality of country coordination, dialogue, and research. Both the processing and implementation of intensive policy dialogue and coordination were most appropriately undertaken by ADB's Resident Mission. The coordination process could not be achieved through occasional missions from headquarters. The internal coordination and communication among ADB staff of the headquarters and of the RM are also important. As program (Poverty Reduction Support Credit or PRSC) operations are comprehensive in nature, the program officer will require input from all relevant sector specialists, and at times, consultants. [Main text, paras. 28, 47] project cycle stage: Design, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Program Project Management: Consultants Capacity Development: Human resources management Other: Resident Mission Policy & Reform: Policy matrix Methodologies/Approaches: Consultation/Participation 8. The Poverty Reduction Support Credit (PRSC) process is comprehensive and policy-oriented, without explicit technical assistance projects attached to a series of program loans. The Support to Implementation of Poverty Reduction Programs (SIPRPs) complement, rather than replace, other ADB initiatives, including sector-specific program loans, technical assistance projects, and sector-specific projects. Technical assistance from specialists based in ADB headquarters is important if ADB is to achieve maximum leverage in its sectoral operations in Viet Nam. In difficult areas of reform (e.g. banking and SOE reforms), however, there is a need to engage in analytical work beyond the conventional scope of the PRSC framework, and to engage influential local think-tanks or research institutions in in-depth studies, with the findings disseminated to decision makers. Ensuring that the PRSC process is integrated with other processes, such as projects, programs, and technical assistance undertakings supported by specific development partners, is therefore critical for achieving targeted development outcomes. The PRSC inputs to reform areas that are lagging therefore call for a concomitant involvement of sector or thematic specialists in such areas. [Main text, para. 48] project cycle stage: Design, Feasibility, Appraisal, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Modality: Program Modality: Technical Assistance Policy & Reform: Policy reforms/framework Methodologies/Approaches: Holistic approach 9. Streamlining partnership group coordination by sector would improve the efficiency and effectiveness of donor harmonization efforts. There have been overlapping aid harmonization groups in Vietnam with multiple coordination groups by sector. For example, there are more than 20 sector-specific partnership groups that monitor Comprehensive Poverty Reduction and Growth Strategy (CPRGS) implementation, one of which is the partnership group of aid effectiveness (PGAE). Under PGAE, sector-specific subgroups duplicate the sector work carried out by some of the 20 PGAE-level partnership groups. There are also separate sector-specific groups within Poverty Reduction Support Credit (PRSC) operations. [Main text, para. 49] project cycle stage: Design, Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Capacity Development: Partnerships Methodologies/Approaches: Consultation/Participation | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-infrastructure-sector
Support to Implementation of Poverty Reduction Program | Viet Nam | Public Sector Management | 2006-09-15 | Advance recruitment of consultants can improve operational procedures and overall efficiency. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Procurement Capacity building is best affected by combining formal training and learning-by-doing in the presence of effective support from the central level. Further capacity building in construction monitoring and supervision is required to maintain the high quality of works. project cycle stage: Feasibility, Implementation Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Project Management: Project supervision Capacity Development: Capacity building Capacity building should be extended to public servants and private sector consultants when a project activity makes extensive use of outsourcing. Local consultant skills in the areas of social assessment, initial environmental assessments, and economic and financial analyses need to be further developed. project cycle stage: Feasibility, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Capacity Development: Capacity building Sector Related Issues: Private sector Counterpart contributions are difficult to collect in situations where a wide range of beneficiaries not necessarily from within the immediate impact area share project benefits. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Counterpart funds Project Design: Project design Flexibility in applying unit cost ranges is needed to accommodate situations where unit costs vary widely and depend on local conditions. project cycle stage: Implementation Lesson Topics: Implementation across several provinces (23 provinces) diminishes the support that a reasonably resourced central project management unit (CPMU) can realistically provide. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Project management Project procedural guidelines should be provided early during implementation and are particularly important where project management capacities are limited. project cycle stage: Implementation Lesson Topics: Project Management: Project administration Project Management: Project management Staff assigned to provincial project management unit (PPMUs) need to be seconded on a full-time basis, especially financial management and accounting personnel. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial management Project Management: Project management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/support-implementation-poverty-reduction-program
Central and Southern Viet Nam Power Distribution Project Completion Report | Viet Nam |  | 2006-07-14 | Both implementing agencies (power companies or PCs) significantly revised some targets in the project components. However, ADB staff who conducted six review missions (between 1999 and 2004) never updated the framework in their back-to-office reports (BTOR) and in the project performance report (PPR). The progress of each target in the framework was not properly monitored. Consequently, ADB and both PCs used different indicators in monitoring the project's progress. project cycle stage: Implementation Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project supervision Sector Related Issues: Energy planning/management Methodologies/Approaches: Targeting Lack of coordination between urban planning and the electricity network rehabilitation and extension also contributed to delays. For example, local authorities required changes in transmission line routes after changes in urban plans, even after the issuance of construction authorization and the near completion of pole foundations. These delays could have been avoided if the rehabilitation of the electricity distribution had been undertaken in parallel with urban planning. Lack of a standard national policy about the type of equipment to be installed on national networks proved a source of significant delay. Numerous technical specifications were drafted, corrected, amended, cancelled, and redrafted to satisfy many different designers. There were also numerous revisions to the detailed designs and delays in finalizing cost estimates and bills of quantity. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Project design Sector Related Issues: Energy planning/management Sector Related Issues: Urban sector/development Methodologies/Approaches: Consultation/Participation More flexibility with regard to project scope is needed. In the case of the project, it could have been expanded to include additional cities to utilize loan savings had it been structured as a sector project. However, this was not an option during project preparation because of the difficulties involved with finalizing the feasibility studies/technical designs for additional towns/cities in a timely manner. It was also noted that some of the delays could have been avoided had the approval process for technical designs and the bidding documents been more streamlined. The procurement documents had to be approved by many layers at the implementing, executing and Borrower levels. project cycle stage: Implementation Lesson Topics: Modality: Program Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Energy planning/management Methodologies/Approaches: Sectoral approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/central-and-southern-viet-nam-power-distribution-project-completion-report
Power Distribution Rehabilitation Project | Viet Nam | Energy | 2005-02-15 | Although the project implementation consultant (IC) finished working when the project was only 75% complete, the remaining work went ahead without the IC's involvement, with no apparent detrimental impact on the project's effectiveness. The utilities technical group had been, for some time, in the business of designing expansions to their medium-voltage and low-voltage systems, selecting construction contractors and implementing the work. The group picked up quickly on the improved standards of design for the systems introduced to them by the consultants. The effectiveness of the consultants apparently ended when the designs of the 110 kV (transmission lines and 110/medium-voltage substations) were complete and when procurement of the equipment and material for the project was complete. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Procurement Sector Related Issues: Energy planning/management It is necessary to allow sufficient flexibility in the project design to cope with unforeseen circumstances. Significant aspects of the environment within which the project had to be implemented changed during the course of the project. Such aspects as the establishment of Electricity of Viet Nam (EVN) in 1995, revision of PC 1's (executing agency's) role with the presence of EVN, and the decision to remove Hanoi Power Company (HPC) and Hai Phong Power Company (HPPC) from PC 1 complicated and encumbered the approval process in a way that was not fully appreciated at the outset of the project. The difficulties with the compensation and resettlement aspects of the project were also not foreseen. These led to a significant delay in implementation. The unprecedented load growth in certain areas and the rapid urban development not foreseen at the design stage also affected the project implementation. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Resettlement Project Design: Project design Sector Related Issues: Energy planning/management Sector Related Issues: Urban sector/development Future projects should incorporate some form of amortization of up-front costs over a 12-month period (as in the Northern Area Rural Power Distribution Project in 2003). The cost of connection to the electric system for rural households was too high (ranged from $80-100) and resulted in fewer connections than envisaged at appraisal. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Sector Related Issues: Energy planning/management Sector Related Issues: Rural development If loan covenants are to be set, they need to be set realistically and on the basis of past performance. The executing agency could not comply with any of its financial loan covenants until the fifth year of project implementation. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Project Management: Executing/Implementing agencies Implementation delays could have been avoided if the executing agency and the consultants were familiar with ADB procurement procedures. Particularly, by using ADB's advance procurement procedures on recruitment of consultants, the executing agency and consultants can commence survey and design work soon after loan effectiveness, which could reduce the front-end period substantially. project cycle stage: Appraisal Lesson Topics: Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/power-distribution-rehabilitation-project
State-Owned Enterprise Reform and Corporate Governance Program | Viet Nam |  | 2004-12-15 | Clear understanding of the program by all stakeholders was essential. Successful and timely implementation of the policy decisions depended on the government's understanding and acceptance of the perspectives and approach that ADB envisioned under each condition. Program implementation showed that miscommunication and misinterpretation of the design and expected outputs of policy actions could delay implementation. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Loan Agreement: Covenants Modality: Program Project Design: Project design Policy & Reform: Information dissemination/Public awareness Policy & Reform: Policy matrix Program implementation reinforced the notion that the expected impact of a program loan is long term, particularly when the program scope and objectives are as broad and ambitious as that of the State-Owned Enterprise Reform and Corporate Governance Program. In Viet Nam, policy reform involves substantial learning and capacity building. It is difficult to predict the length of this process. Due to the large program scope, most policy actions were in areas over which the executing agency (State Bank of Vietnam) had no direct control. Therefore, the program depended highly on the performance of implementing agencies. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Modality: Program Project Management: Executing/Implementing agencies Capacity Development: Capacity building Policy & Reform: Policy reforms/framework Policy & Reform: Public sector reform State-owned enterprise (SOE) restructuring is a sensitive area that requires political and institutional consensus on reform values, as well as acceptance of the resulting changes. Commitment from the government agencies in charge and SOEs themselves was necessary. SOEs' accurate understanding and acceptance of those policy decisions was critical to the program's success, particularly in Viet Nam, where SOEs continue the traditional domination in the industrial sector. project cycle stage: Feasibility, Appraisal Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Project Management: Executing/Implementing agencies Capacity Development: Ownership Sector Related Issues: Industry and Trade Policy & Reform: Policy matrix Policy & Reform: Public sector reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/state-owned-enterprise-reform-and-corporate-governance-program
Population and Family Health Project | Viet Nam | Health | 2004-11-15 | Cofinanciers should harmonize their requirements in advance, to the extent possible. project cycle stage: Appraisal Lesson Topics: Project design would have benefited from more preparatory sector work, including updated information on key indicators and detailed understanding of issues at field level. This would have allowed the planning of second generation reproductive health (RH) activities upfront. project cycle stage: Feasibility Lesson Topics: Monitoring & Evaluation: Indicators Project Design: Project design Sector Related Issues: Health and sanitation management Project impact cannot be assumed based on a broad design, reflecting all major elements of the health system. Rather, it depends on participatory planning and strategy adjustments based on changes in health behavior and quality of care. The National Committee for Population and Family Planning (NCPFP) demonstrated flexibility to adjust the project as required. project cycle stage: Feasibility, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Health and sanitation management Methodologies/Approaches: Participatory approach The construction and maintenance of health centers was much better in locations where communities participated strongly. Communities should be involved in the planning of health centers, and agree with the authorities on the maintenance of the facility. The issue of medical waste should be addressed early in project preparation, included in loan covenants, and followed up during reviews. Health projects should provide clear guidelines, regular inspection,staff training, and community involvement for the handling of medical waste. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Environmental management Loan Agreement: Covenants Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Health and sanitation management Methodologies/Approaches: Community approach The management structure made establishing a link to field performance difficult. However, the project demonstrated valuable lessons for good Project Management, including clear assignment of responsibilities, intensive coordination, and flexibility in implementation. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Project management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Process approach | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/population-and-family-health-project
Fisheries Infrastructure Improvement Project | Viet Nam | Agriculture, Natural Resources, and Rural Development | 2004-10-15 | Covenants should be relevant and easy to implement in a localcontext. The Loan Agreement contained some ambitious covenants that couldnot be implemented. project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Design should cater to future growth in demand, including phaseddevelopment, if necessary. Port design should be undertaken in discussion withintended users. Provisions should be made for small fishers, to the extentpermitted by efficient port operation. Equipment requirements should be moreclosely analyzed and related to specific needs. project cycle stage: Design Lesson Topics: Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Transport planning Methodologies/Approaches: Consultation/Participation Fisheries infrastructure projects need to ensure thatadequate processes are in place or established to monitor fisheries resourcestatus and exploitation. The project did endeavor to do this through establishingenvironment and resource management units (ERMUs), but this aspect of the project was modified due to the existence of aparallel project that, however, has not yet provided adequate data. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Environmental management Monitoring & Evaluation: Monitoring and evaluation Sector Related Issues: Rural development Sector Related Issues: Transport planning Fully effective waste management systems should beintegral to modern fishing port design. project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Environmental management Project Design: Project design Sector Related Issues: Transport planning Port selection should be based on detailed analysis of demand. Anadequate feasibility study on an individual port would, at the least, examine portrequirements over time, consider options, and assess economic and financialperformance. project cycle stage: Feasibility Lesson Topics: Finance & Financial Aspects: Financial analysis Finance & Financial Aspects: Market analysis Project Design: Project design Sector Related Issues: Transport planning The difficulty of effecting change needs to be accountedfor in project design. At present, the provincial authorities do not appear to havemuch interest in introducing modern port management systems. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity development Sector Related Issues: Transport planning Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/fisheries-infrastructure-improvement-project
Ho Chi Minh City Water Supply and Sanitation Project | Viet Nam | Water and Other Urban Infrastructure and Services | 2004-07-15 | Bidding documents specifications should be explicit, with provision of specific values and quantities that the contractors shall follow, to facilitate the authority to supervise the works. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Procurement Project Management: Project supervision Government project staff members should be given training prior to the implementation of a project, to familiarize them with various ADB guidelines and procedures for project implementation. project cycle stage: Design Lesson Topics: Project Management: Project administration Capacity Development: Capacity building Capacity Development: Human resources management Project implementation periods should be carefully examined and determined during appraisal, taking into account government regulations for preparation of detailed design and bidding, bid evaluation, and scope changes. project cycle stage: Appraisal Lesson Topics: Project Design: Appraisal Project Design: Project design Project Management: Procurement Qualified consulting firm and staff member selection are the keys for successful project implementation, and high priority should be given to the selection of consultants who are familiar with local rules and regulations related to project implementation. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Project administration Country Context: Prioritization Unaccounted for water (UFW) projection at 30% by December 1998, covenanted in the Loan Agreement, was too ambitious, given the increased water pressure after the project and the limited inputs to the improvement of distribution networks (rehabilitation of 65 kilometers of pipelines against a total length of over 1,800 kilometers). project cycle stage: Appraisal Lesson Topics: Loan Agreement: Covenants Loan Agreement: Loan Agreement Sector Related Issues: Health and sanitation management | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/ho-chi-minh-city-water-supply-and-sanitation-project
Irrigation and Flood Protection Rehabilitation Project | Viet Nam | Agriculture, Natural Resources, and Rural Development | 2004-07-15 | Greater attention needs to be given to project preparation. ADB should have ensured, before loan approval, that the executing agency's implementation procedures were compatible with ADB's and that probable sources of delay were eliminated through mutual agreement. ADB also missed an excellent opportunity to provide capacity-building technical assistance (TA) to the executing agency. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Capacity Development: Capacity building Loan savings use, to carry out flood damage repairs in subprojects outside the originalproject area, was not cost-effective. The irrigation extension subprojects did not have clearobjectives or adequate needs and options assessments, and their selection criteria were notsufficiently rigorous to eliminate unsuitable schemes or works. These subprojects areconsidered unsuccessful, and they detract from the project's otherwise successful rating. project cycle stage: Implementation Lesson Topics: Project Design: Project design Project Design: Subprojects Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Many project implementation delays and performance-related difficulties can be tracedto the executing agency's lack of familiarity with ADB's project implementation guidelines and procedures. TheEA's need for capacity building should have been more carefully examined during projectpreparation, and appropriate technical assistance (TA) should have been included to complement physical works.Central Project Office's (CPO's) implementing capacity is limited, due to its low status within the executing agency (Ministry of Agriculture and Rural Development or MARD). CPO's role and status should therefore be strengthened, and CPO should be more effectively integrated into MARD. project cycle stage: Feasibility Lesson Topics: Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Project Management: Project administration Project Management: Project management Capacity Development: Capacity building O&M continues to be less than that needed to ensure the schemes' integrity. Irrigation management companies (IMCs)retained the practice of not providing maintenance to new infrastructure for a period of 3-5 years, thus setting the stage for ongoing cycles of capital reinvestment that water user fees do not cover. Currently, water fees pay for routine O&M but do not provide reserves for capital reinvestment. IMCs showed themselves to be effective implementers, but their capacity tomanage irrigation systems should be strengthened in all future projects. Most IMCs do not have O&M or business plans on which water fees and scheme performance can be based. A need also exists for greater accountability within IMCs for scheme performance. project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Governance Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial management Project Management: Operation and maintenance Capacity Development: Capacity building Sector Related Issues: Irrigation management The amount for resettlement required under the project far exceeded the appraisalestimate. Although the executing agency managed to resettle most affected people and compensate thosewho lost assets in a manner that increased well-being and produced little discontent, the lack ofa resettlement plan caused significant delays and increased counterpart fund requirements. Inaddition, project-gained experience was not applied to the irrigation extension subprojects.Resettlement planning should be integral to project preparation, including that for projectextensions. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Resettlement Finance & Financial Aspects: Counterpart funds Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Project design Project Design: Subprojects Project Management: Executing/Implementing agencies Sector Related Issues: Irrigation management The executing agency did not understand the potential value of effective Benefit Monitoring and Evaluation (BME), and monitoring and evaluation during implementation were therefore sporadic. At project completion, no permanentBME unit existed for Hanoi dike or the irrigation subprojects. All future projects should give closeattention to establishing effective monitoring and evaluation functions, and making thesefunctions consistent with the Project Performance Management System and operational prior tocommencement of any construction activities. Attention should also be paid to the terms ofreference for monitoring and evaluation, to ensure that control areas are included and that theseare consistent with project-impacted areas. project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Monitoring and evaluation Project Design: Subprojects Project Management: Executing/Implementing agencies Sector Related Issues: Irrigation management The predominantly engineering approach failed to address constraints facing waterusers in irrigated agriculture. A wider systems approach that builds water user and water resource institution involvement would provide a more complete project formulation that is capable of achieving the stated goals. Future projects should include more effective involvement of primary stakeholders [farmer beneficiaries, water management groups, and irrigation (and drainage) management companies] in project design. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation The relief wells for the Hanoi dike subproject were a completely new technique in VietNam, and their design should have been based on detailed geological investigations carried outas part of project preparation. The technical difficulties, however, proved too challenging forsome local contractors. As a result, the number of installed relief wells fell short ofspecifications, and some wells have low efficiency. When new technical solutions areintroduced, greater care is needed to engage suitably qualified and experienced consultantsand contractors. project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Design: Subprojects Project Management: Consultants Project Management: Procurement Capacity Development: Technology/Technology transfer Sector Related Issues: Irrigation management | Project/Program Completion Reports (PCR) | Partly/less than successful | http://www.adb.org/projects/documents/irrigation-and-flood-protection-rehabilitation-project
Second Road Improvement Project | Viet Nam | Transport | 2003-11-14 | Many roads under the rural road component (RRC) did not meet the assumption at appraisal that they carry littletraffic. A tight budget also imposed limitations on the rehabilitation cost per kilometer, leading tounderdesigned rehabilitation work on some roads. The selection procedure should either haveensured selection of roads with low traffic volumes, or some of the excess funds should havebeen reallocated to the RRC to enable higher standards on roads with heavy traffic. Thereshould have been more interaction between ADB, the executing agency, and the consultant torespond to changing circumstances. project cycle stage: Appraisal Implementation Lesson Topics: Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Project Management: Consultants Project Management: Executing/Implementing agencies Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Consultation/Participation Significant savings were realized in the course of project implementation, primarilybecause local contractors undertook construction rather than international contractors as wasexpected at appraisal. The savings enabled realization of additional project components thathad previously been abandoned for budgetary reasons. This has significantly improved theproject and contributes to long-term sustainability. The lesson learned is that flexibility isimportant during project implementation to ensure that opportunities for improvement can beseized. A flexible approach to unit cost constraints on the rural roads component (RRC) would have improved thesustainability of rural roads with heavy traffic. project cycle stage: Feasibility, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financial analysis Project Design: Appraisal Project Design: Project design Project Management: Procurement Sector Related Issues: Roading Sector Related Issues: Rural development Methodologies/Approaches: Process approach Small local contractors worked on the rural roads. Although these contractors hadtrouble finishing work on time, and required close supervision from Project Management Unit (PMU)-1 and the supervisionconsultant, the outcome was generally satisfactory. The lesson learned is that untested localcontractors can perform adequately, but ample time must be given to allow for the steeplearning curve and the many constraints facing such contractors. project cycle stage: Appraisal Implementation Lesson Topics: Project Management: Consultants Project Management: Procurement Project Management: Project supervision Sector Related Issues: Roading Sector Related Issues: Rural development Viet Nam's bid evaluation process is complicated and time-consuming. For contracts above a certain size, the evaluationhas to be approved by the Ministry of Planning and Investment, and finally by the Prime Minister. The usage of advance procurement ensured that the contract with the supervision consultant and the four initial civil works contracts for the national highway component (NHC) were signed within 5 months of loan effectiveness, causing no major delays to implementation. Although initial project approval was lengthy, the executing agency acted swiftly thereafter, as seen in the floating of contracts for various project extensions. Until the systemic causes for initial delay are overcome, advanceprocurement action should always be considered for projects in Viet Nam. project cycle stage: Appraisal Lesson Topics: Project Management: Consultants Project Management: Executing/Implementing agencies Project Management: Procurement Sector Related Issues: Roading | Project/Program Completion Reports (PCR) | Highly successful | http://www.adb.org/projects/documents/second-road-improvement-project-0
Rural Credit Project | Viet Nam | Finance | 2003-09-15 | Institutional and policy reforms will be more effectively implemented if agreement between the implementing agencies (Vietnam Bank for Agriculture and Rural Development and Central Credit Fund) and the government is obtained at the start of the project. A time-bound action plan for implementing these reforms should be clearly described and agreed to, and the actions should be conditions for disbursement of the loan funds. project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Disbursement Loan Agreement: Covenants Project Management: Executing/Implementing agencies Policy & Reform: Policy reforms/framework Methodologies/Approaches: Consultation/Participation Subject to appropriate loan appraisal and processing, there should be areasonable ceiling on the size of individual loans. It is impractical tospecify a subloan size of ï¿½up to $100ï¿½ for poor members. Also, specifying thatsubloans by People's Credit Funds (PCFs) should be short-term is inappropriate, as the objective is tofoster investment that would promote development. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Design: Appraisal Project Design: Subprojects The amount of the imprest fund to be established under the loan should bespecified for each executing agency and the use of the fund should includefinancing of subloans. The ultimate objective of the imprest fund is to providequick access to funds for financing eligible expenditures. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing Project Design: Subprojects Project Management: Executing/Implementing agencies The application of commercial interest on relending for noncredit components(i.e., strengthening of financial institutions), discouraged the People's Credit Funds (PCFs) from using the funds for institutional strengthening. Soft components such as training and software development should be provided at a concessional rate. project cycle stage: Appraisal Lesson Topics: Finance & Financial Aspects: Financing Project Management: Executing/Implementing agencies Project Management: Management information system Capacity Development: Capacity building | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/rural-credit-project-0
Saigon Port Project (Loan 1354-VIE[SF]) | Viet Nam | Transport | 2003-03-31 | Developing member countries still in the nascent stages of administering ADB projects would benefit from more proactive project monitoring by ADB, strengthened particularly at the resident mission level. project cycle stage: Implementation Lesson Topics: Monitoring &amp; Evaluation: Monitoring and evaluation Project Management: Project administration Capacity Development: Capacity building Other: Resident Mission The approach of separating business planning from strategic development functions in the port sector adopted by the government, may also be appropriate for ADB's other developing member countries. project cycle stage: Feasibility Lesson Topics: Project Design: Project design Sector Related Issues: Transport planning | Project/Program Performance Evaluation Report (PPER) | Successful/Generally successful | http://www.adb.org/documents/saigon-port-project-loan-1354-vie-sf
Red River Delta Water Resources Sector Project | Viet Nam | Agriculture, Natural Resources, and Rural Development | 2002-12-13 | Although the project's Benefit Monitoring and Evaluation (BME) program is being implemented successfully, it highlights (i) the desirability of commencing BME at an early stage of project implementation, (ii) the needto monitor control areas as well as benefiting areas, and (iii) the desirability of maximizing theuse of secondary data. It is important for future projects that BME is not seen as an end in itself,but rather as a valuable tool which can feed into the management of existing, and the design ofnew, subprojects. project cycle stage: Appraisal Implementation Lesson Topics: Monitoring & Evaluation: Benefit monitoring and evaluation Monitoring & Evaluation: Data collection and management Project Design: Project design Project Design: Subprojects Project Management: Project management For future projects, project planning should be based on a river basin development approach. It should also be undertaken within an overall system context and should address key constraints in an integrated manner. While the design of the project did not place any particular limit on the scale of subproject investments, in practice, central project office (CPO) and the design companies attempted to remain within the $3.0 million limit, above which subprojects had to be approved by ADB review missions. This resulted in a fragmented and truncated approach in the case of anumber of subprojects. Artificial cost limitations should not of themselves drive subproject selection. project cycle stage: Feasibility, Appraisal Lesson Topics: Project Design: Project design Project Design: Subprojects Project Management: Project supervision Sector Related Issues: Water resource management Methodologies/Approaches: Holistic approach Future projects need to ensure that parallel downstream investments required from provinces, cooperatives, or farmers are made in a timely manner. In several of the project's subproject areas, investments in the secondary and tertiary canal systems have been less than optimal, resulting in lowered system performance and an inability to fully capitalize on project investments. project cycle stage: Appraisal Implementation Lesson Topics: Project Design: Project design Project Design: Subprojects Sector Related Issues: Irrigation management Getting the design of subprojects right is the key to project performance and impact. The project employed a traditional approach to subProject Design, focusing almost entirely on primary infrastructure. A more participatory and holistic approach to design should result in improved outcomes. Future project designs therefore should include extensive consultation with the primary stakeholders (farmers, water management groups, and irrigation and drainage management companies [IDMCs]). Examples of contributions that these stakeholders can make to system design include identification of investment needs in secondary and tertiary drainage and irrigation systems, alignment and level of canals and drains, location of major structures, and placement of spoil from excavations. project cycle stage: Design Lesson Topics: Project Design: Project design Project Design: Subprojects Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Holistic approach Methodologies/Approaches: Participatory approach Since the management of most of the irrigation and drainage systems is under thejurisdiction of provincial governments, provincial stakeholders should take a lead role in upgrading and rehabilitating intraprovincial systems under future projects. Under the project, except for complex components such as large pump stations, and large outfall and intake sluices, implementation of several subproject components could have been delegated to the provinces with sufficient implementation capacity. project cycle stage: Design Appraisal Lesson Topics: Project Design: Project design Project Design: Subprojects Capacity Development: Capacity assessment Country Context: Decentralization Sector Related Issues: Irrigation management The project and the technical assistance (TA) were intended to assist in the development of Viet Nam's water resources institutions. In practice, their impact has been limited. The project and TA experiencehighlights the difficulties in encouraging institutions to adopt new approaches to planning andmanagement. A careful assessment is required during project and TA design of the agency'sreceptiveness to new institutional and operational concepts and the potential to operationalizethem. Furthermore, TA inputs should be planned in a phased manner so that in case ofinsufficient support and ownership on the part of the executing agency, the TA can bereformulated, rescheduled or, in the worst case, terminated. project cycle stage: Feasibility, Appraisal Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity assessment Capacity Development: Capacity development Capacity Development: Ownership Sector Related Issues: Water resource management The project has shown that physical interventions do not necessarily lead to improved irrigation fee collection - one of the project's objectives. Specific activities need to be integrated in the project design to address cost-recovery issues, taking into account the role of the provincial people's committees in setting irrigation and drainage fees, the performance of the irrigation and drainage management companies (IDMCs) in providing irrigation and drainage services, and the role of the cooperatives and their water management groups. In-system irrigation and drainage conflicts also need to be understood and addressed. For future projects, inclusion of reform measures to improve theperformance of water sector institutions should be considered, besides the physical interventions. project cycle stage: Feasibility, Appraisal Lesson Topics: Finance & Financial Aspects: Financial management Project Design: Project design Sector Related Issues: Irrigation management Sector Related Issues: Water resource management Policy & Reform: Reform | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/red-river-delta-water-resources-sector-project
Agriculture Sector Program (Loan 1340-VIE[SF]) | Viet Nam | Agriculture, Natural Resources, and Rural Development | 2002-09-30 | A greater focus on policy outcomes rather than policy actions may be more appropriate for a number of reasons. This leads to the conclusion that ADB needs to adopt a more strategic and flexible approach in its policy-based lending. For flexibility to be a practical option, monitoring and evaluation systems must function effectively to provide the information on which decisions can be made, and dialogue must be frequent and in-depth. Given the reality of staff constraints, the appointment of a senior policy consultant should be considered for program loans to provide intermittent inputs throughout program periods. Given their short duration, monitoring and evaluation systems for program loans and the required skills and resources should be in place by loan effectiveness. project cycle stage: Appraisal Lesson Topics: Modality: Policy-based lending Modality: Program Monitoring &amp; Evaluation: Monitoring and evaluation Project Management: Consultants Capacity Development: Human resources management Policy &amp; Reform: Policy reforms/framework ADB s flexibility in providing an additional technical assistance (TA) and modifying (two) policy conditions also contributed to program success. This TA and the relatively frequent dialogue by regular ADB missions ensured that problems were rapidly resolved and did not become entrenched. The planned TA support also provided a good base of information for policy work, and in the case of another TA, a compelling analysis of policy options and outcomes. project cycle stage: Implementation Lesson Topics: Modality: Policy-based lending Modality: Technical Assistance Project Management: Project supervision Policy &amp; Reform: Policy matrix Policy &amp; Reform: Policy reforms/framework In future programs, local currency proceeds (counterpart funds) should be used for purposes that are consistent with, and contribute to reform. While fungibility is an issue, the government should be encouraged to provide incremental funding for certain activities or meet clearly identified restructuring costs, both of which can be tracked through a review of budgetary allocations. ADB s Operations Manual provides the basis for obtaining expenditure commitments from the government. project cycle stage: Appraisal Lesson Topics: Finance &amp; Financial Aspects: Counterpart funds Policy &amp; Reform: Reform Restructuring of bad debt of a lending institution must be accompanied by policy changes to ensure that the problem does not reemerge. project cycle stage: Feasibility Lesson Topics: Finance &amp; Financial Aspects: Financing Modality: Technical Assistance Policy &amp; Reform: Policy reforms/framework Technical assistance (TA) support to improve institutional capability is likely to require a reallocation of recurrent expenditure if new developments such as the rice market model and land information system are to be sustained. This needs investigation during TA design. project cycle stage: Design Lesson Topics: Finance &amp; Financial Aspects: Financing Modality: Technical Assistance Project Management: Management information system Capacity Development: Capacity development The project was also successful because it did not include any significant departures from existing policy. Whether policy programs should involve a degree of additionality and thereby risk being only partly successful or should they have a high degree of fit with existing policy probably depends on the context. In the case of the project, the reform pace was rapid and it made sense to reward past efforts and consolidate the progress made rather than attempt to further increase the pace. When the pace of reform is slow, it may be sensible to provide incentives to accelerate and deepen the reform, even if this means the program may not fully achieve its objectives. project cycle stage: Feasibility Lesson Topics: Project Management: Risks/Risk management Policy &amp; Reform: Policy reforms/framework The project was successful primarily because of genuine commitment and support for the principles it embodied by those in government with power and influence to make it happen. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Project Management: Executing/Implementing agencies Capacity Development: Ownership The slow pace of achieving greater private sector involvement in agricultural trade is a concern. On the other hand, experience from the breakup of the former Soviet Union has shown that a too rapid privatization creates severe problems, which are very difficult to resolve. Viet Nam s steady approach has proven to be better although perhaps slower than necessary. What is clear is that the innovation and efficiency required to sustain agriculture sector growth and create off-farm employment through value-added activity will require a vibrant private sector operating at all levels. However, the private sector is unlikely to grow while a dominant state-owned enterprise sector retains competitive advantages. Measures are required to progressively withdraw state investment in commercial activities. project cycle stage: Feasibility Lesson Topics: Crosscutting Issues/Themes: Employment Sector Related Issues: Industry and Trade Sector Related Issues: Private sector Sector Related Issues: Rural development Policy &amp; Reform: Privatization Policy &amp; Reform: Public sector reform Policy &amp; Reform: Transition economies | Project/Program Performance Evaluation Report (PPER) |  | http://www.adb.org/documents/agriculture-sector-program-loan-1340-viesf
CAREC Midterm Review of the Transport and Trade Facilitation Strategy and Implementation Action Plan: Technical Assistance Completion Report |  | Transport | 2016-05-01 | (i) Need for core TA (technical assistance) funding to facilitate regional cooperation and project pipelining in the transport sector. Without the TA, the quality and the continuity of the strategic work in CAREC (Central Asia Regional Economic Cooperation) were not assured. CAREC is considered as one of the successful cases of regional cooperation. By extending the implementation period of the TA for a full two years following adoption of TTFS (Transport and Trade Facilitation Strategy) 2020, the TA was able to offer implementation support of the TTFS 2020 to CAREC countries. It thereby helped maintain the coherence and sustainability of the CAREC program as applied in the transport sector, which accounts for more than 80% of CAREC investments. (ii) Link between strategy and investment projects. The strategy effectively served as a regional master plan, and was linked to investment projects. The updated strategy offered an efficient vehicle for proper project identification and prioritization, in line with the objective of RCI (regional cooperation and integration). (iii) Importance of dialogue with countries. The ownership of the updated strategy was strong among all the CAREC member countries, with strengthened operational capacity of government authorities which are involved in implementation of TTFS. This basic philosophy was maintained through frequent dialogue with countries during the TA implementation. <!-- Project cycle stage: Concept, Implementation, Operation --> | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/carec-midterm-review-ttfs-and-implementation-action-plan-tcr
Development Partnership Program for South Asia: Technical Assistance Completion Report |  | Education, Public sector management | 2016-05-01 | Several major lessons can be learned from the implementation of this RETA (regional technical assistance): (i) evaluation of achievements is facilitated when benchmarking, performance management, and results frameworks are well-defined; (ii) subprojects that showed very good potential in the initial stage could have had more funding so that the reform process could have been more institutionalized; (iii) flexibility during RETA implementation allowed considerable opportunity to try to do things differently if there were obstacles, particularly in the RCI (regional cooperation and integration) subprojects; (iv) tailoring solutions to local conditions helped the RETA achieve more across the different themes; and (v) the ownership and commitment of DMCs (developing member countries) to the subprojects was critical in their success. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/development-partnership-program-for-south-asia-tcr
Technology Transfer for Disaster Resilient Infrastructure Project Development: Technical Assistance Completion Report |  | Energy, Transport, Water and other urban infrastructure and services | 2016-05-01 | Conducting country-based partnership forums prior to holding the regional Knowledge Partnership Week (KPW) would likely have improved the chances of brokering workable knowledge partnerships at the end of the KPW. A consensus on the roles and contributions of the different ADB units to support the COE (Center of Excellence) on Clean Energy would significantly improve interventions for Indonesia and make the One ADB approach more productive. Further collaboration among the relevant ADB units is needed for working with the private sector agencies as 'One ADB' to account for different perspectives, e.g., business opportunity, knowledge partnership, and cofinancing. Project cycle stage: Implementation, Country Partnership Strategy | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/technology-transfer-for-disaster-resilient-infrastructure-project-dev-tcr
Central Asia Regional Economic Cooperation Institute, 2009-2012: Technical Assistance Completion Report |  | Industry and trade, Public sector management, Transport | 2016-01-01 | The lessons learned include: (i) an implementation period of three years was overly ambitious for the TA (technical assistance) to address the capacity building needs of CAREC (Central Asia Regional Economic Cooperation) Program especially in absence of a detailed work program for the CI (CAREC Institute); (ii) strong interfaces with CAREC sector committees both during design and implementation are essential to ensure relevance and usefulness of the CI activities in terms of knowledge generation and dissemination; and (iii) sufficient flexibility in the TA design should be provided to accommodate the evolving needs of CAREC Program over the course of implementation. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/central-asia-regional-economic-cooperation-institute-2009-2012-tcr
Enhancing Knowledge on Climate Technology and Financing Mechanisms: Technical Assistance Completion Report |  | Energy, Industry and trade, Water and other urban infrastructure and services | 2016-01-01 | One lesson learned from the TA (technical assistance) concerns timing issues, that regardless of how strict one wants to follow an implementation schedule, it is still limited by factors not within the team's control, finding suitable and available experts in a still narrow field; and the speed of the GCF (Green Climate Fund) set-up and operationalization, which, however, could be overcome by increasing anticipation and foresight to the full extent possible, lessening its influence on the TA's timeline. Thus, patience, flexibility and aggressive follow-ups for administrative factors are key as not to diverge too much from the original TA implementation schedule. Another lesson from this TA is the lack of mechanism on how to measure continuous engagement of DMCs (developing member countries) in climate change issues, specifically on financing and technology. Project cycle stage: Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/enhancing-knowledge-on-climate-technology-and-financing-mechanisms-tcr
Policies for Industrial and Service Diversification in Asia in the 21st Century: Technical Assistance Completion Report |  | Industry and trade, Public sector management | 2016-01-01 | Problems were encountered with the co-publisher Edward Elgar on the quality of the editing, layout and printing. The publisher provided only a mediocre customer satisfaction, as dealing with its staff was very inefficient and many aspects of their services were below expectations. One of the many complaints is the sub-standard quality of the colored figures in the book. Given this, other publishing companies will be considered for future co-publishing arrangements. DER (Department of External Relations) was informed. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/policies-industrial-and-service-diversification-asia-21st-century-tcr
Attracting and Managing Foreign Direct Investments in the Transitional Economies of Southeast Asia: Technical Assistance Completion Report |  |  | 2015-12-01 | The selection of experts was critical in producing quality research work, while the selection of appropriate avenues for dissemination was crucial for publicizing research findings and reaching policymakers. ADB's participation in the preparation of Cambodia 2030 was particularly helpful in reaching the target audience and disseminating the SSTA's (small-scale technical assistance) policy recommendations. Project cycle stage: Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/attracting-and-managing-foreign-direct-investments-transitional-economies-southeast-asia-tcr
Improving Agricultural and Rural Statistics for Food Security: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development, Public sector management | 2015-12-01 | One of the lessons learned from this study is the need to provide technical assistance to DMCs (developing member countries) in the future to improve administrative data collection systems since sample surveys are expensive to implement. Another lesson is to promote the application of innovative data sources such as satellite data to improve precision of agricultural and rural statistics. To monitor the goal of increasing agricultural and rural statistics by 30%, it is recommended that ADB continue to coordinate with IAs (implementing agencies), partner organizations, and other major stakeholders through the Regional Steering Committee for Asia and the Pacific for the Global Strategy to Improve Agricultural and Rural Statistics by participating in the quarterly meetings, periodic review missions, and frequent email exchanges. Additionally, CARS (Community for Agricultural and Rural Statistics) website should continue to be utilized for other ongoing agricultural statistics work in the department. Finally, collaboration with regional departments is needed to get National Statistics Offices and Ministries of Agriculture to participate in the Global Strategy activities. Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/improving-agricultural-and-rural-statistics-food-security-tcr
Promoting Regional Infrastructure Development: Technical Assistance Completion Report |  | Transport | 2015-12-01 | Several lessons were derived from this TA (technical assistance), which include: (i) the design of a TA particularly when it involves key initiatives such as establishment of a regional PDF (Project Development Facility) needs strong justifications from broad-based consultation with external stakeholders particularly DMCs (developing member countries). (ii) Supporting regional infrastructure development involves work undertaken by all the operational departments. An adequate consultation and coordination/collaboration with all the related department particularly regional departments can help improve the TA design toward setting a more realistic target for more cost-effective and achievable intervention. (iii) Strong partnerships with other committed development partners are critical in studying/identifying optimal transport routes with achievable targets, as well as for sharing best practices in this area. (iv) The lack of an appropriate institutional arrangement within ADB with clear demarcation of responsibilities between the former OREI (Office of Regional Economic Integration) and the regional department (particularly when it involves intersubregional cooperation) was also partly responsible for the failure of the TA, which partly explains the lack of sufficient coordination/collaboration with the regional departments. And (v) from the administration point of view, an earlier closure of the TA would have achieved better cost efficiency, even though the TA's outputs as originally designed couldn't be achieved. Project cycle stage: Design, Implementation, Operation, Completion | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/promoting-regional-infrastructure-development-tcr
Sustainable Fuel Partnership Study - Exploring an Innovative Market Scheme to Advance Sustainable Transport and Fuel Security: Technical Assistance Completion Report |  | Transport | 2015-11-01 | The TA (technical assistance) confirmed the value of ADB working on knowledge partnerships with multilateral organizations (i.e. IEA or International Energy Agency) and leading academic institutions (i.e. Oxford University). In addition, the creation of an expert advisory panel to help oversee the technical direction of the project proved an effective instrument and should be considered for other ADB projects that involve subjects that are innovative and technically complex. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/sustainable-fuel-partnership-study-tcr
Asia-Pacific and Americas Proposed Customs Leaders' Partnership Dialogue - Efficient and Secure Trade for Shared Prosperity: Technical Assistance Completion Report |  | Industry and trade, Public sector management | 2015-10-01 | The Dialogue was held in Panama, a non ADB member country. ADB's financial contributions were sourced from three different TAs (technical assistance). Only SPD's (Strategy and Policy Department) TA secured a waiver of procurement restrictions which allowed financing in non-member countries including Panama, while the 2 TAs had the standard procurement restrictions. This posed tremendous financial management and coordination challenges to ADB offices involved in the Dialogue. As commented by some ADB offices during the review process for the draft TA paper, it must have been easier and faster if additional financing from SPD's TA was secured for a South-South cooperation event in a non-member country of ADB rather than processing new TA with the standard procurement restrictions which was only used for expenditures in ADB's member countries in addition to the TA with a waiver of procurement restrictions, but with a limited amount allocation. Project cycle stage: Concept, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/asia-pacific-americas-customs-leaders-partnership-dialogue-tcr
ADB-OECD Joint Study on Enhancing Financial Accessibility for SMEs: Technical Assistance Completion Report |  |  | 2015-09-01 | Doing a joint collaborative work with a center of excellence or external knowledge partner is a great way of exchanging views and issues on topics of interest which would benefit both institutions. It must be ensured though that there is clear division of work to guarantee smooth flow of work activities. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/adb-oecd-joint-study-enhancing-financial-accessibility-for-sme-tcr
Financial Regulatory Reforms in Asia: Technical Assistance Completion Report |  | Finance | 2015-09-01 | The topic of the TA (technical assistance) is very timely, it would be good to use the models discussed in the book in other countries to provide ideas how to determine the impact to their economy in the event of another round of financial crises. For the better implementation of the TA it needed to strengthen the contribution of ADB staff as co-authors. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/financial-regulatory-reforms-asia-tcr
Financial Sector Development in Central and West Asia: Technical Assistance Completion Report |  | Finance | 2015-09-01 | The contribution of the TA (technical assistance) to CWPF (Central and West Asia Department-Public Management, Financial Sector, and Trade Division) activities underscores the benefits of regional TAs which are focused on country needs and provides a good model for replicating in other sectors and regions. The TA could have been drafted to allow for greater flexibility in supporting the needs of countries and project teams in the design of TAs, projects and programs. Project cycle stage: Concept, Design, Country Partnership Strategy | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/financial-sector-development-central-and-west-asia-tcr
Fourth High-Level Forum on Aid Effectiveness: Technical Assistance Completion Report |  | Public sector management | 2015-09-01 | The TA (technical assistance) was highly successful due to a great team effort and dedication of its team members. Involving ADB RMs (resident missions) and DMCs (developing member countries) right from the start on global monitoring surveys and pre-discussions on the outcome documents was crucial in coming up with Asia-pacific regional perspectives that were country owned. Some activities, for example, management of donor funds were additional last minute activities, but these were managed well with the cooperation of other departments such as OCO (Office of Cofinancing Operations) and Treasury. ADB-wide support as well as keeping the ADB Board informed on the outcomes of the global events, is crucial. Project cycle stage: Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/fourth-high-level-forum-aid-effectiveness-tcr
Key Indicators for Asia and the Pacific 2012: Technical Assistance Completion Report |  | Public sector management | 2015-09-01 | The TA (technical assistance) was successful due to the dedication of the ERDI (Economics and Research Department-Development Indicators and Policy Research Division) staff to come up with the timely completion of Key Indicators. The cooperation of staff from ADB's regional departments, statistical partners, and other source agencies was also an important factor in publishing the Key Indicators. The timely sending of questionnaires, the extensive follow up, and clarification of queries to get data from partner statistical agencies on time and the use of the automated review greatly helped in a more efficient production of the Key Indicators. The collaboration with OIST (Office of Information Systems and Technology) to make sure that all database concerns were addressed is very vital for the review of the statistical tables. The support of the Department of External Relations and the Office of Administrative Services was also helpful for efficient production and dissemination of the publication. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/key-indicators-asia-and-pacific-2012-tcr
Knowledge Platform Development for the Asia Solar Energy Initiative: Technical Assistance Completion Report |  | Energy | 2015-09-01 | A consensus on all the implementation arrangements should be reached between ADB, DMCs (developing member countries) and the member agencies of RTF (Regional Task Force) and ASEF (Asia Solar Energy Forum) before the TA (technical assistance) is approved. This would minimize delays in the TA completion and smoothen project implementation. Furthermore, when a TA is part of the global efforts to mainstream renewable energy development, there are greater synergies between the TA and non-regional program being conducted by other agencies. Project cycle stage: Appraisal, Implementation, Operation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/knowledge-platform-development-asia-solar-energy-initiative-tcr
Project Preparation Support for the Cities Development Initiative for Asia: Technical Assistance Completion Report |  | Energy, Transport, Water and other urban infrastructure and services | 2015-09-01 | On the PFSs (pre-feasibility studies), specifically in linking to downstream financing would have been achieved if the selection of cities and potential projects were coordinated with ADB's operations departments. This should be a dimension of CDIA (Cities Development Initiative for Asia) operations which should be mainstreamed to its upcoming interventions for its activities to have more relevant impacts. In engaging consultants, the indefinite delivery contract (IDC) method used under the TA (technical assistance) for expediting recruitment of consulting firms for the preparation of PFSs is a good method to adopt for procurement of consultants on assignments involving repetitive types of outputs. Though UN-HABITAT, as implementation partner for this TA, was able to produce the agreed outputs and provide additional credibility to ADB's and CDIA's operations, there were some concerns on the administrative side that should be noted and considered if they will be engaged in future initiatives. There were substantial delays in the delivery of TA reports?not being a consulting firm their commitment to deliver the required deliverables was lax compared to a consulting firm running as a business. This should be carefully considered for future potential partnerships with UN-HABITAT. Project cycle stage: Feasibility, Appraisal, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/project-preparation-support-cities-development-initiative-asia-tcr
Provision of Environment Technical Services: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development, Public sector management, Transport, Water and other urban infrastructure and services | 2015-09-01 | The availability of technical experts from a world renowned agency to work on ADB projects is a significant benefit. As the LOI (Letter of Intent) provides for an in-kind contribution from the USEPA (Environmental Protection Agency of the United States of America), this is very cost effective as only travel and accommodation expenses are accrued by ADB. The demand for USEPA experts to provide technical inputs to projects was not as strong as envisaged and the interest in utilizing the experts varied from region to region. This was partly due to a large proportion of ADB projects not requiring the technical inputs or expertise provided by USEPA. Temporary budget restrictions on USEPA, in some cases, resulted in agency staff being unable to travel abroad to provide their expertise requested by ADB. A reasonable lead time is required for a project to utilize an expert as the agency had to first identify suitable personnel and then check on their availability. The long lead time was not always considered by project team leaders, therefore, in some instances it was not possible for the experts to travel to Asia on short notice. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/provision-of-environment-technical-services-tcr
Strategic Research for Sustainable Food and Nutrition Security in Asia: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-09-01 | A major lesson learned is that the administration of a large number of outputs and activities under one TA (technical assistance) that aims to achieve an ambitious goal is extremely challenging. Scattered outputs increased administrative burden, and yielded a long list of individual reports and records of many knowledge events. The TA could have disseminated the generated knowledge though the stakeholders and networks of ADB's relevant projects, so that the TA could have contributed directly to expanding ADB's food and nutrition engagement. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strategic-research-sustainable-food-and-nutrition-security-asia-tcr
Supporting Investments in Water-Related Disaster Management: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-09-01 | There were two important lessons should be considered: (i) Much greater emphasis should be placed on cementing and formalizing the relationship between an institutional partner (ICHARM or International Centre for Water Hazard and Risk Management) and the commercially-engaged consulting firm; and (ii) More robust approaches should be adopted to ensure the main activities have a clearer, more direct link to operations. This is a challenge for all regional technical assistance (TA) projects. In addition sound financial management helps early closure of any TA. In considering the financial management of the TA: (i) Final liquidation of the firm's out-of-pocket expenses were delayed until quite some time after TA completion; timely liquidation should remain a priority; and (ii) Issue of the certificate of turnover from the relevant government agency in Indonesia (responsible for minor equipment purchased under the TA) was delayed beyond TA closing: in future this requirement should be identified well in advance of TA completion. Project cycle stage: Design, Feasibility, Implementation, Operation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/supporting-investments-water-related-disaster-management-tcr
Free Trade Agreements in Asia: The Way Ahead: Technical Assistance Completion Report |  |  | 2015-08-01 | The lessons learned include: (i) The partnership between ADB and ADBI (ADB Institute) was productive and facilitated sharing of scarce financial resources, project management skills, and technical expertise within the ADB family. (ii) More time needs to be given for conducting firm-level surveys of this type and for data processing. Some interviews with firms had to be rescheduled due to last minute cancellations and data processing took longer than expected. (iii) From an administrative point of view, an early closure of the TA (technical assistance) would ensure early completion of more focused activities, as well as achieve more efficient and effective use of the TA funds. Project cycle stage: Implementation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/free-trade-agreements-asia-the-way-ahead-tcr
Global Supply Chains and Trade in Value Added: Technical Assistance Completion Report |  | Industry and trade | 2015-08-01 | (i) Close coordination and supervision of consultants by the ADB project team throughout the project ensured its smooth implementation and the quick resolution of minor issues whenever they arose; (ii) the use of advanced communication tools helped frequent communication with researchers distributed across three continents, while reducing project costs; and (iii) the midterm assessment of consultants, where the ADB team evaluated the consultants' outputs as per TOR (terms of reference), allowed the ADB team to swiftly address situations and take corrective action where necessary. Project cycle stage: Implementation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/global-supply-chains-and-trade-value-added-tcr
Promoting Gender Equality and Women's Empowerment: Technical Assistance Completion Report |  | Public sector management | 2015-08-01 | (i) The demand-driven approach that provided support when needed worked well to assist ADB's operations departments to strengthen the design and implementation of project GAPs (gender action plans); (ii) cross-regional lateral learning proved an effective mechanism for both gender capacity development of DMC (developing member country) officials, and for generating government ownership of project GAPs; (iii) timely consultant recruitment and fielding following subproject approval must be rigorously monitored to ensure timely startup, implementation and completion of subprojects managed by operations departments; (iv) development of a project performance reporting system is needed to alert the management of operations departments regarding the progress and performance of subprojects; and (v) more emphasis should be placed in scaling-up successful initiatives. Project cycle stage: Implementation, Operation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/promoting-gender-equality-and-womens-empowerment-tcr
Strengthening Economic Assessment Capacity for Asia and the Pacific Region: Technical Assistance Completion Report |  | Public sector management | 2015-08-01 | Although the TA (technical assistance) has taken the initial steps in developing macroeconomic assessment tools and helped strengthen the economic assessment capacity of member DMCs (developing member countries), there is a need to continue the works done at the country level. Data for some economies, i.e., Pacific and Central Asian economies are sparse and less frequent, hence, the difficulty in conducting economic monitoring activities and creating a much broader programming exercise. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-economic-assessment-capacity-asia-and-pacific-region-tcr
Support to the Pacific Pension Institute (PPI) in the Strengthening Pension Fund Industry in Asia-Pacific Region (Phase II): Technical Assistance Completion Report |  |  | 2015-08-01 | At the Asia Dialogue, the salient features of the Asian pension industry were highlighted. There was unanimity that implementation of international best practices related to the initial development of pension funds in the region's frontier markets must take into account the state of development of the pension funds industry volatility as well as regulatory constraints. This is important for helping them in fulfilling their fiduciary responsibilities and duties during periods of demographic shifts, economic and investment. In the next phase sustainable ways to fund the maintenance of the web-portal and data base, as well as enabling public- access needs to be explored so as to not rely perpetually on TA (technical assistance) funding. In addition, the needs assessment survey report recommended additional educational, professional development and knowledge-sharing activities to enhance the capacity of pension fund managers. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/support-ppi-strengthening-pension-fund-industry-asia-pacific-p2-tcr
Assessing the Socioeconomic Effects of the Greater Mekong Subregion Projects: Technical Assistance Completion Report |  | Public sector management | 2015-07-01 | It is necessary to understand the intrinsic difficulty of designing, implementing and evaluating regional cooperation projects, which (i) tend to be large relative to national projects in the same sector and (ii) require the agreement and cooperation of many different stakeholders (to the extent that enabling laws sometimes need to be ratified in the countries covered by the project). The socioeconomic impacts of these projects may take a longer period to be realized compared to site-specific projects; therefore, impact assessments should be conducted after sufficient time has elapsed?possibly more than 3 years after the project is completed. Furthermore, the collection of socioeconomic data and establishing necessary sampling and control mechanisms to capture attribution effects is methodologically difficult for regional cooperation projects. All of these factors need to be carefully considered when designing follow-up impact evaluation studies in the GMS (Greater Mekong Subregion). Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/assessing-socioeconomic-effects-gms-projects-tcr
Contribution to the Technical Assistance Facility of the Private Infrastructure Development Group: Technical Assistance Completion Report |  | Public sector management | 2015-07-01 | In designing a TA (technical assistance), the proposal must be carefully reviewed and evaluated to ensure focused scope and achievable goals during the expected period of TA implementation. In this case, the TA's outputs ranged from knowledge information (reports and workshops) to project development and support for partial guarantees. With limited resources available under the TA and short span of the TA duration, the scope should have been narrowed to only one or two focused outputs. When contributing to external trust funds, ADB should ensure clear and practical implementation guidelines and procedures related to fund administration, including selecting, approving, implementing, and monitoring of the projects supported during the TA implementation. The implementation guidelines and procedures of external trust funds contributed to by ADB should include a governance structure, project eligibility criteria and even a timeline for resource utilization. ADB's increased involvement will ensure efficient and effective implementation, and enhance further visibility of ADB contribution. Project cycle stage: Design, Feasibility, Implementation | Technical Assistance Completion Report | Unsuccessful | http://wcm.adb.org/projects/documents/contribution-ta-facility-private-infrastructure-development-group-tcr
Harmonization of Bond Standards and Market Practices in ASEAN+3 - Support for ASEAN+3 Bond Market Forum, Phase 2: Technical Assistance Completion Report |  | Finance | 2015-07-01 | Through the activities supported by this TA (technical assistance), key policy recommendations on AMBIF (ASEAN+3 Multi-currency Bond Issuance Framework) and bond transaction flows were identified, while actual policy actions for the recommendation will take time. For smooth implementation of policy recommendations, regular and close communication with regulators and central banks would be highly desirable. ABMF (ASEAN+3 Bond Market Forum) members acknowledged the need for continued support for the implementation of AMBIF in the case of SF1 (Sub-forum 1), and additional study to help standardize bond transaction flows and support AMBIF bond issuance and transactions in the case of SF2 (Sub-forum 2). Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/harmonization-bond-standards-market-practices-aseanplus3-support-bond-market-forum-phase2-tcr
Institutions for Regionalism: Enhancing Economic Cooperation and Integration in Asia and the Pacific: Technical Assistance Completion Report |  | Public sector management | 2015-07-01 | There are two major lessons from this TA (technical assistance). The first highlights the importance of working with experts who not only have the technical expertise necessary to produce quality research work, but also the stature to provide high-level policy and strategic advice to policymakers. The second lesson underscores the importance of finding appropriate avenues for disseminating research findings and reaching policymakers. Stakeholders gave positive feedback to the consultative approach taken during the dissemination seminars where key study findings were presented. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/institutions-regionalism-enhancing-economic-cooperation-and-integration-asia-and-pacific-tcr
Managing Water in Asia's River Basins: Charting Progress and Facilitating Investment : Technical Assistance Completion Report |  | Water and other urban infrastructure and services | 2015-07-01 | (i) Collaboration with NARBO (Network of Asian River Basin Organization) added significant value of the TA (technical assistance) in effective dissemination of IWRM (integrated water resources management) practice in regional meetings and capacity development program for basin practitioners across the region. The NARBO advisory service were applied to other DMCs (developing member countries) to provide guidance on various aspects of river basin management. This has led to the increased interest from other countries including Bangladesh, India and Nepal on similar activities and basin investment projects. (ii) Piloting of the RAS (roadmap advisory service) in the Baitarani river basin in India, which was shelved, incorporated the lessons learned from antecedent technical assistance which highlighted the stakeholder consultations as essential to acquire wider acknowledgement and mutual consensus among stakeholders in IWRM process. (iii) The senior water professionals from other river basins in the region delivered tangible contributions to RAS to serve as peer advisers, share experience in IWRM implementation and roadmap preparation, and dialogue closely with basin stakeholders. (iv) The project supported, catalyzed, and added value to parallel water initiatives. This made the TA strategically relevant, and kept it abreast on latest trends and challenges to water. Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/managing-water-asias-river-basins-charting-progress-and-facilitating-investment-tcr
Master Plan on ASEAN Connectivity Implementation: Technical Assistance Completion Report |  | Finance, Public sector management | 2015-07-01 | One lesson is on the administrative aspect of the TA (technical assistance). ADB needs to understand and factor in the multiple approvals for cofinancing from the JAIF (Japan-ASEAN [Association of Southeast Asian Nations] Integration Fund). While financing support for the TA from the JAIF was welcomed, its regulations and ASEAN requirements led to implementation delays. The external audit requirement also constrained the use of TA funds. Thus, the additional time and procedures associated with the JAIF cofinancing needs to be taken into account for future TAs. In addition, the under-utilization of TA funds was also due to consultants' lump sum contracts, as the consultants' actual claims were much lower than the contract amounts. At the project level, the Sumatra-Peninsular Malaysia High Voltage Direct Current Interconnection project experience indicates that considerable time and effort is required to build consensus among the stakeholders on such regional (multi-country) project. The consultation process is still ongoing, even after delivery of the TA outputs. Project cycle stage: Implementation, Operation, Completion | Technical Assistance Completion Report |  | http://wcm.adb.org/projects/documents/master-plan-asean-connectivity-implementation-tcr
Policy Support for Regional and Global Economic Cooperation: Technical Assistance Completion Report |  | Public sector management | 2015-07-01 | Outputs in relation to the first three sets of approved changes in implementation arrangements were completed on schedule. However, the scope of the final output from the fourth change in implementation arrangements was narrowed due to the inability of the national consultant to deliver his expected outputs. Despite several opportunities to complete his tasks, the national consultant was still unable to submit his complete report. Future cases like these could be handled more strictly to avoid unnecessary delays in TA (technical assistance) implementation. Project cycle stage: Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/policy-support-regional-and-global-economic-cooperation-tcr
Private Sector-Led Integration and Free Trade Agreements in South Asia: Technical Assistance Completion Report |  | Industry and trade | 2015-07-01 | Major lessons were as follows: (i) the close partnership with FICCI (Federation of Indian Chambers of Commerce and Industry, a critical private sector chamber in South Asia) contributed significantly to the successful conduct of the TA (technical assistance) activities. Being a knowledge unit in ADB, OREI (Office of Regional Economic Integration) had limited engagement with non-governmental stakeholders in South Asia and FICCI served as its gateway to key private sector organizations in the region. (ii) The TA's impact may have been enhanced if it were formally a part of ADB's country and regional technical assistance plans in South Asia. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/private-sector-led-integration-and-free-trade-agreements-south-asia-tcr
Public-Private Infrastructure Advisory Facility: Technical Assistance Completion Report |  | Finance | 2015-07-01 | The complicated structure and lengthy processing under the PPIAF (Public?Private Infrastructure Advisory Facility) have incurred delays in the implementation of the TA (technical assistance). In order to utilize remaining balance under this TA, ADB and World Bank have discussed various options for more than one year prior to arriving at a solution. ADB must ensure direct and efficient access to and administration of resources for timely processing, approval, and implementation of TA projects. There are two ways to remain an active member of PPIAF: the first is to provide a minimum membership contribution of $250,000 per year and the second is to provide equivalent funding through cofinancing of PPP (public-private partnership) activities. While the membership contribution goes to ADB's Non-Core Funds, which can be accessed by ADB project officers, the existing procedures for accessing these funds are quite cumbersome and inefficient. Thus, it is suggested that the second means of retaining active membership be pursued. Project cycle stage: Design, Appraisal, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-public-private-infrastructure-advisory-facility-tcr
Supporting Public Management through e-Government Capacity Development: Technical Assistance Completion Report |  | Public sector management | 2015-07-01 | The major challenges throughout the TA (technical assistance) implementation were related to the ambitious scope of the TA and the communication issues related to the capacity development programs. First, it was too ambitious that the TA included two different components (TAMIS [tax administration management information system] and SSAMIS [security administration management information system]) providing capacity development programs to multiple countries as well as developing a toolkit for each component. It caused a lot of challenges in scheduling workshops for multiple countries, preparing customized contents, and mobilizing resource people in timely manner. It is important to estimate realistic implementation time period at the design stage and it could be better if the TA would focus on a topic area rather than multiple topic areas. Second, there were some critical issues for toolkit development in terms of scope and quality. First of all, it was challenging to develop two e-government toolkits for both tax administration and social security program within a year under a $500K TA. Since there had been very few e-government toolkits across the world, it took a while to conceptualize how to develop toolkits. Ultimately, it was decided to focus on only a toolkit for TAMIS instead of two to make sure a reasonably good quality is produced. In addition, it was difficult to invite inputs and feedback from a broad range of stakeholders on the draft toolkit due to time constraints. Third, there is no such thing as a one-size-fits-all solution for capacity development program. So, it is critical to consider the local context in all stages of capacity development programs. In addition to the high level commitment, it is also important to get buy-ins from the participants in the capacity development programs. To achieve the expected outcome of the capacity development program, it is recommended to have enough discussions on the objectives and the way to conduct capacity development programs, and the qualification of the participants in advance. Fourth, given the limited budget of the TA, it was an excellent strategy to collaborate with other development partners such as MOPAS (Ministry of Public Administration and Security ), NIA (National Information Society Agency), and KEXIM (Korea Export-Import Bank) seeking their contributions to the TA. Not only was the partners' support helpful but their knowledge and experiences also contributed a lot to the capacity development programs. Project cycle stage: Concept, Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/supporting-public-mgt-through-e-government-capacity-development-tcr
Addressing the Pre- and Postharvest Challenges of the Rice Supply Chain: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-06-01 | International agriculture research centers like IRRI (International Rice Research Institute) are and will remain major sources of innovations for food and other resource-based commodities. As in the experience of this TA (technical assistance), they will need to transform into other business operating modalities such as consulting entities or partnerships with private sector to secure additional investments for R&D (research and development) endeavors. ADB needs to improve the consulting services mechanism with international agriculture research centers to streamline the selection process and for more efficient TA administration and results delivery. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/addressing-pre-and-postharvest-challenges-rice-supply-chain-tcr
Asia Regional Integration Center, Phase IV: Technical Assistance Completion Report |  | Finance, Industry and trade, Public sector management | 2015-06-01 | The transfer of ARIC (Asia Regional Integration Center) to the Economics Research and Regional Cooperation Department (ERCD) is a welcome development as research and knowledge generation and dissemination will benefit from synergies within ERCD. ARIC's specialization in tracking RCI (regional cooperation and integration) developments in the region will complement the varied research topics in ERCD, and its databases will likewise complement other economic indicators already embedded in ERCD. Continuous collaboration and coordination work with other regional and research institutions have played a significant role in disseminating the RCI knowledge work. Partnering with them proved to the most efficient way of organizing various seminars and conferences on RCI, particularly the AEIM (Asia Economic Integration Monitor) launches and seminars. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/asia-regional-integration-center-phase-iv-tcr
Asian Development Outlook 2013: Technical Assistance Completion Report |  | Public sector management | 2015-06-01 | The introduction of a two-year cycle for background research on issues relevant to the theme topic proved useful in advance planning, in-depth research, and wider consultations on the theme chapter topics. Also, by collaborating with an ADB Community of Practice or CoP (i.e., Energy CoP), the ADO (Asian Development Outlook) has greatly benefited from the stock of knowledge already existing within ADB, while at the same time being contributing to the continuous enhancement of the CoPs, through internal and external learning for CoP members, ADB, and its DMCs (developing member countries). Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/asian-development-outlook-2013-tcr
Assessment of Impediments and Actions Required for Achieving an ASEAN Economic Community by 2015: Technical Assistance Completion Report |  | Industry and trade, Public sector management | 2015-06-01 | There are three major lessons from this TA (technical assistance). The first highlights the importance of working with experts who not only have the technical expertise necessary to produce quality research work, but also the stature to provide high-level policy and strategic advice to policymakers. The second lesson underscores the importance of finding appropriate avenues for disseminating research findings and reaching policymakers. The third highlights the role of strong management support and an extensive consultation process, internally and with policy makers in the region, in significantly increasing the visibility and broadening the readership of the book. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/assessment-impediments-and-actions-required-achieving-aec-2015-tcr
Capacity Building for Regional Trade Integration and Facilitation: Technical Assistance Completion Report |  |  | 2015-06-01 | Lessons learned include (i) the need for on-going high-level and technical engagement with development partners (including the WTO or World Trade Organization and donors) to continually make the case for increased trade-related development assistance for the region amid diminishing aid budgets and competition from other regions for resources; and (ii) the need for sustained intensity to keep the private sector involved in the APTFF or Asia-Pacific Trade Facilitation Forum (or, rather, for making the APTFF consistently relevant for the private sector). The expansion and diversity of side events at APTFF on good practices in trade facilitation may be one way to do so. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/capacity-building-regional-trade-integration-and-facilitation-tcr
Drivers of Poverty Reduction in Asia and the Pacific: Technical Assistance Completion Report |  | Public sector management | 2015-06-01 | Despite the small budget of the TA (technical assistance), the efficient use of resources, close coordination between the research teams and the consultants and collaboration with various key organizations resulted in numerous high-quality and relevant knowledge products. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/drivers-poverty-reduction-asia-and-pacific-tcr
Greater Mekong Subregion Phnom Penh Plan for Development Management Phase V: Technical Assistance Completion Report |  | Public sector management | 2015-06-01 | It is difficult to ensure financial sustainability of capacity development activities for government officials in the GMS (Greater Mekong Subregion). The resources available to Governments and the lack of an established culture of continuing adult learning makes sustainability challenging. A major lesson is for training programs to be designed to supplement government-driven policies and initiatives so as to ensure ownership and 'demand-driven' instead of """"""""supply-driven"""""""" support. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/gms-phnom-penh-plan-development-management-phase-v-tcr
Institutional Development for Enhanced Subregional Cooperation in the aSEA Region: Technical Assistance Completion Report |  | Public sector management | 2015-06-01 | Important lessons learned include: (i) Designing and implementing TAs (technical assistance) for broad RCI (regional cooperation and integration) support in a flexible manner allowed ADB to adapt quickly to the rapidly changing RCI environment and respond efficiently to the needs and demands of member countries; (ii) Investing in development of subregional plans, identifying projects and building capacities of officials involved in RCI is a lengthy and costly process, but it is necessary to develop strong subregional and national secretariats and self-sustaining programs; and (iii) Partnering SERC (Southeast Asia Department - Regional Cooperation and Operations Coordination Division) with sector divisions, resident missions, knowledge departments and local institutions to organize activities was essential for providing high quality technical advice to the subregions. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/institutional-development-enhanced-subregional-cooperation-asea-region-tcr
Institutional Strengthening for Aviation Regulation: Technical Assistance Completion Report |  | Transport | 2015-06-01 | Although the provision of legal advising service was very useful for the member countries, a longer TA (technical assistance) duration was needed to realize the enactment of legislation and regulations in multiple countries. Administrative support to assist the countries in preparing and implementing legislation and regulations and budgeting might be helpful. Also, institutional development support to PASO (Pacific Aviation Safety Office) could be attached to the financial management support to ensure good financial management performance. The coordination with WB (World Bank) through participating in PASO Council Director's meetings was very effective to implement seamless support to PASO and the member countries. Project cycle stage: Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/institutional-strengthening-aviation-regulation-tcr
Regional Cooperation on Knowledge Management, Policy, and Institutional Support to the Coral Triangle Initiative: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-06-01 | Collaboration and resource sharing among the various players in the CTI or Coral Traingle Initiative (e.g., NCCs [national coordinating committees], IRS [interim regional secretariat], working groups, development partners and other collaborators) was a key approach in ensuring buy-in and maximizing impact of the TA (technical assistance) activities. Consistent with the key foundation of the CTI as a country-owned and country-driven program, the TA ensured that its activities were led and/or strengthened through the participation of and by capacitating the NCCs and the IRS through the engagement of knowledge integrators who assisted in addressing country-specific information gaps. This engendered strong country/institutional commitment and ownership and the institutional/financial sustainability of TA activities. On the flip side, working interdependently within the country processes and its institutions required more time and effort that resulted to implementation delays. However, the benefits from strong stakeholder participation outweighed these challenges. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/regional-cooperation-knowledge-management-policy-and-institutional-support-cti-tcr
Strengthening the Capacity of the ASEAN Secretariat in Regional Economic Integration and Policy Dialogue-Phase 2: Technical Assistance Completion Report |  | Public Sector Management | 2015-06-01 | The peculiar design of the TA (technical assistance) disbursing funds to ASEC (ASEAN Secretariat) in tranches with liquidation through SOEs (Statement of Expenditures) later made the TA one of the most costly TA in terms of administration. Tremendous efforts have been undertaken in clearing old files to liquidate long overdue ASEC expenditures instead of focusing on the substance. project cycle stage: Design, Implementation The actual capacity of ASEC (ASEAN Secretariat) should have been taken into consideration when designing the TA (technical assistance) including making the TA longer in validity so that numerous extensions could have been avoided. project cycle stage: Design, Implementation From the administration point of view, an earlier closure of the TA would ensure the completion of more focused activities as originally designed. project cycle stage: Design, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/strengthening-capacity-asean-secretariat-phase-2-tcr
Supporting Investments in Water Security in River Basins: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-06-01 | It is important to select a suitable partner agency for implementation of the technical assistance (TA). The partner agency of this TA, having rich knowledge and experiences as a practitioner of IWRM (integrated water resources management), enabled identification of key areas on water security and the appropriate delivery of technical inputs to support the river basin investment planning and capacity building program. The implementation agency took an advantage of existing relationships with counterpart agencies through NARBO (Network of Asian River Basin Organizations) to work closely with them in river basin investment planning. As a result, counterpart agencies enhanced ownership which is essential to successive actions of authorization and implementation of the investment plan. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/supporting-investments-water-security-river-basins-tcr
Ensuring Sustainability of Greater Mekong Subregion Regional Power Development: Technical Assistance Completion Report |  | Energy | 2015-05-01 | The TA (technical assistance) successfully introduced the SEA (Strategic Environment Assessment) in the GMS (Greater Mekong Subregion) power development planning on a regional level and generated a great deal of awareness among the GMS power sector planners. However, due to limited TA scope, country-level assistances were not sufficient under the TA to build the necessary capacity for all GMS countries to apply SEA into their PDP (Power Development Plan) on a national level, especially when each country had a different level of capacity in SEA and differing policies on RE (renewable energy) and EE (energy efficiency). Further, RE and EE are not typically seen as separate and exclusive strategies but are pursued jointly. Therefore, a more country-focused and integrated approach would have been more effective. The partnership with AFD was financially and technically beneficial to the project. However, it took some time for AFD (Agence Francaise de Developpement) to understand ADB's guidelines and procedures particularly related to consultant recruitment, which resulted in delaying AFD's endorsement on co-financing agreement. In the future, more regular communication between ADB and the partner agency can mitigate such risk. Project cycle stage: Implementation, Country Partnership Strategy | Technical Assistance Completion Report |  | http://wcm.adb.org/projects/documents/ensuring-sustainability-gms-regional-power-development-tcr
Information and Communication Technology-Based Inclusive Growth and Poverty Reduction in the Pacific: Technical Assistance Completion Report |  | Information and communication technology | 2015-05-01 | The TA (technical assistance) affirms that realizing the development potential of improved ICT (information and communications technology) connectivity requires more than investment in ICT infrastructure through (i) complementary investments in ICT applications and consideration of how to make the services more inclusive and accessible to the poor; (ii) developing capacity especially among frontline users on how to use these applications, and (iii) a coherent and conducive policy environment. The success of the TA implementation can be attributed to its flexible and demand-driven approach to meet the varying capacity gaps and needs in the Pacific. The TA tried to achieve a balance between responding to the demands of Pacific DMCs (developing member countries) and avoiding piecemeal support by ensuring that assistance is linked to ICT investments and applications in the country. Other major lessons include: (i) country ownership and cooperation were achieved through close consultation and by directly responding to country demands; (ii) a demand-driven TA requires wide dissemination to client countries to facilitate interest and avoid unutilized funds; and (iii) continuous updates and coordination with other development partners avoid duplication and provide for more strategic support. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/ict-based-inclusive-growth-and-poverty-reduction-pacific-tcr
Pacific Private Sector Development Initiative Phase II: Technical Assistance Completion Report |  | Finance, Public sector management | 2015-05-01 | PSDI (Private Sector Development Initiative) has been in operation since 2006 (with the approval of the first phase of PSDI, TA or Technical Assistance 6353-REG, on 21 November 2006) and a number of lessons have been able to be drawn from PLCO's (Pacific Liaison and Coordination Office) experience in implementing a large-scale regional TA over this period of time: (i) Promoting an enabling environment for the private sector in the Pacific remains a crucial challenge and requires a thorough analysis of the economic, political, and cultural issues and challenges facing Pacific developing member countries (DMCs). (ii) Reform in the Pacific region requires sound analysis, awareness building, and regular advocacy and outreach, involving policy makers, the private sector, the media, and civil society. Regional benchmarking is an effective advocacy tool and provides valuable information for monitoring progress. (iii) A regional (and multi-country) focus facilitates learning from experiences gained from undertaking similar reforms in other Pacific DMCs while ensuring that local needs, capacity, and conditions are reflected in proposed reforms. The approach used in PSDI has perpetuated demand-driven reforms, often with success in one country motivating others to follow suit. (iv) A rapid-response capability brings the flexibility to quickly mobilize expertise as reform opportunities arise, and to demobilize promptly when political commitment wanes, allocating resources where the demand is greatest and effectively supporting reformer governments and champions. (v) As reform initiatives often require several years to design and implement, and because relationships take time to build, long-term engagements are critical. (vi) It is important to sequence and prioritize reforms according to the level of political readiness and local capacities, and design reform measures to meet existing institutional capacity. (vii) Close collaboration and coordination among development partners is important to maximize impact, especially in small, fragile states. Harmonization of private sector development assistance through cofinancing has proved effective. Support was provided to the design of the Mekong Business Initiative drawing from these lessons. The Mekong Business Initiative is a policy advisory and advocacy facility to promote private sector development, business formalization, and growth in value chains in the Greater Mekong Subregion, with a focus on Cambodia, Lao People's Democratic Republic, Myanmar, and Viet Nam. ADB. 2014. Technical Assistance for the Mekong Business Initiative. Manila (TA 8785-REG, $10,500,000, approved on 3 December 2014, cofinanced by the Government of Australia). Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/pacific-private-sector-development-initiative-phase-2-tcr
Regional Strategic Response to Malaria and Other Communicable Diseases in Asia and the Pacific: Technical Assistance Completion Report |  | Health | 2015-05-01 | Implementing this TA (technical assistance) required political support from several countries which may be affected by changes of governments of these countries. The meeting to launch the APLMA (Asia Pacific Leaders Malaria Alliance) was cancelled when the new Australian government decided not to push through with the launch event meeting. Fortunately, the APLMA was still launched through a statement in the East Asian Summit declaration, which was strongly supported by the new Australian government. In the future, there is need to plan ahead on transition arrangement that should be undertaken when countries have changes of government. This plan could include briefings with the new government to ensure that prior commitments are sustained. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-strategic-response-malaria-and-other-communicable-diseases-asia-and-pacific-tcr
Sovereign Debt Crises in the US and the Eurozone - Potential Regional Impacts on Asia: Technical Assistance Completion Report |  | Public sector management | 2015-05-01 | The TA (technical assistance) underscored the importance of working with experts who not only have the technical expertise necessary to produce quality research work, but also the stature to provide high-level policy and strategic advice to policymakers. OREI's (Office of Regional Economic Integration) close collaboration with Dr. Sachs and the Advisory Panel provided overall research guidance and ensured the overall technical quality of the research outputs. Project cycle stage: Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/sovereign-debt-crises-us-and-eurozone-potential-regional-impacts-asia-tcr
Updating and Improving the Social Protection Index: Technical Assistance Completion Report |  | Public sector management | 2015-05-01 | To help address capacity constraints in DMCs (developing member countries) on monitoring social protection expenditures and impacts, the TA (technical assistance) supported capacity building at the regional and national level through pilots in three countries. The pilots attempted to integrate a social protection module in HIES (household income and expenditure surveys). Indonesia designed the social protection module for Socio-Economic Survey of Indonesia (SUSENAS) which is conducted annually. As a result, SUSENAS for 2015 will run with the social protection module included. For the Philippines, the social protection questions were incorporated in the Annual Poverty Indicators Survey (APIS) through consultations with major data users. In Sri Lanka, social protection questions were permanently integrated in their HIES. While the TA has ended, these concrete actions initiated by the NSOs (national statistics offices) will help ensure that going forward, these DMCs will have better source of data for social protection monitoring that can aid program design and policy-making. However, sustainability of these results will also depend on resources of DMCs to implement the surveys. The TA had to be extended by two years, therefore, the time provided for the TA implementation should be more realistic. Project cycle stage: Design, Implementation, Operation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/updating-and-improving-social-protection-index-tcr
Asian Bonds Online Website Project, Phase III: Technical Assistance Completion Report |  | Finance | 2015-04-01 | The TA (technical assistance) continued to improve and enhance existing deliverables from lessons learned in previous phases of the project. Quality of output is maintained with the careful selection of consultants and resource persons, under close supervision by and guidance from ADB staff. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/asian-bonds-online-website-project-phase-3-tcr
Geocoding of ADB's Projects: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-04-01 | Institutionalizing a new data reporting process requires not only a well-functioning tool but also a broad compliance with the new requirements by data reporters. For tasks where change in the perception of the people affected is a critical element of success, as was in the validation of the draft geocodes under the TA (technical assistance), it is important to ensure a sufficient allocation of resources and efforts in promoting awareness of the project objectives and benefits. For consultants newly engaged in ADB projects, adequate time should be allowed for knowledge transfer to familiarize them with ADB's strategic priorities, documentation and performance requirements, etc. Lack of knowledge about ADB-specific requirements can result in unexpected delay in implementation and waste of resources. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/geocoding-adbs-projects-tcr
Outreach for Good Governance and Development Effectiveness through the Accountability Mechanism: Technical Assistance Completion Report |  | Public sector management | 2015-04-01 | The TA (technical assistance) provided evidence of the need to tailor outreach to the particular culture of the DMC (developing member countries), particularly if outreach events are targeted towards APs (affected persons). Further, owing to the specialized message about the AM (accountability mechanism), it is also necessary to develop a multilevel communication strategy (i.e., for government, for private sector and for the AP/CBO [community-based organizations]/NGO [nongovernment organization] stakeholders) to address the information needs of the recipients of the AM outreach. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/outreach-good-governance-and-development-effectiveness-through-accountability-mechanism-tcr
Regional Economic Integration in Central Asia: Stocktaking and Experience Sharing (TCR) |  | Public sector management | 2015-04-01 | The TA (technical assistance) may have benefited more by consulting and coordinating closely with CWRD (Central and West Asia Department) early on in the implementation of the TA to provide more focus and greater depth on RCI (regional cooperation and integration) issues relevant for Central Asia. From an administration point of view, the TA implementation and subsequent closure process would have been facilitated better with a proper turnover from the original project officer prior to moving to a different department. Project cycle stage: Implementation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/regional-economic-integration-central-asia-stocktaking-and-experience-sharing-tcr
A Study of Bond Trading Costs Across Southeast Asia: Technical Assistance Completion Report |  | Finance | 2015-03-01 | Considerable variation exists across bond markets in Southeast Asia reflecting their informal 'over- the-counter nature'. This variation covers basic structure, mechanics, terms and the method of calculating levies, and gives rise to challenges in developing cross-country comparisons. TA (technical assistance) administered under such conditions should include adequate time and resources to prepare a uniform and comparative survey methodology prior to field visits. In addition, assessments of this type should require debriefs of the expert between field visits to individual countries. This would allow resets to survey methodology in real time to reflect the lessons learned. The additional time and cost would be easily justified by reducing the required follow-up and accelerating the completion of deliverables. Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/study-of-bond-trading-costs-across-southeast-asia-tcr
Communications Campaign for Prevention of HIV/AIDS: Technical Assistance Completion Report |  | Health | 2015-03-01 | ADB, through UNAIDS, will continue to monitor the: (i) commitments of partners, (ii) ongoing implementation of activities; and (iii) collaboration at the national/local level. The TA (technical assistance) demonstrated innovative modes of partnerships for broader collaboration on health. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/communications-campaign-for-prevention-of-hiv-aids-tcr
Developing Securitization Markets in ASEAN+3 Region: Technical Assistance Completion Report |  | Finance | 2015-03-01 | The study showed that Asian markets largely escaped the first round effects of the subprime crisis partly because they had not developed securitization markets to the extent seen in the US and Europe. Perhaps more importantly, Asian banks had not exposed much in the bonds backed by subprime assets. However, as Asian capital markets continue to develop so will their need for and the use of complex products such as securitization. To prevent staff from being overstretched in completing the activities during the implementation of TA, staff should provide progress reports within the division/department. Another key consideration could be to coordinate with regional departments particularly the finance divisions as well as with the Finance Sector Group. Project cycle stage: Implementation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/developing-securitization-markets-asean-3-region-tcr
Establishing the Asian International Economists Network: Technical Assistance Completion Report |  | Industry and trade | 2015-03-01 | First, the TA (technical assistance) was most ambitious in developing a web-based network without providing clear directions on content development. As a result, much resources and efforts were devoted to website contents, while less were done for other planned activities, even though the website gradually gained web traction from the requests received from various institutions. Second, there was somewhat mismatch of the AIEN (Asian International Economists Network) by its name with the actual activities focused (trade). This raised concern of duplication with the Asia-Pacific Research and Training Network on Trade of UNESCAP, which also focuses on trade issues. A closer coordination and collaboration with ADB's existing similar networks such as the Asian Think Tank initiative would have helped with a better focus area. Third, finding the right consultant for the project was a problem. AIEN did not have a team leader for most of the project duration, which affected the progress of some outputs. Thus, it would help if a better alternative to engage short-term international consultants with good contacts could have been considered from the beginning. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/establishing-asian-international-economists-network-tcr
Fighting HIV/AIDS in Asia and the Pacific: Technical Assistance Completion Report |  | Health | 2015-03-01 | The TA (technical assistance) showed that ADB can take an effective role in promoting HIV prevention as a regional public good, particularly in bringing together multi-sector stakeholders to pursue common goals. ADB's leadership in regional capacity building and implementation of multi-country projects is highly appreciated by governments and regional development agencies. Sustainable approaches require appropriate internal capacity in ADB, especially in programming HIV and other communicable diseases within the broader health development agenda. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/fighting-hiv-aids-asia-and-pacific-tcr
Implementing the Urban Operational Plan - Financing Investments in Environmental Infrastructure: Technical Assistance Completion Report |  | Energy, Transport, Water and other urban infrastructure and services | 2015-03-01 | Suggestions for improvement included: interactive sessions and round table discussions should be increased for the Urban Forum, leaving more time for networking and including more practical case studies. Most important, the Urban Forum should be held regularly to promote the UOP (Urban Operational Plan) in Asia and smooth the rapid urbanization. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/implementing-urban-operational-plan-financing-investments-environmental-infrastructure-tcr
Asian Bonds Online Website, Phase IV: Technical Assistance Completion Report |  | Finance | 2015-02-01 | Partnering with local institutions, as well as closely coordinating with DER (Department of External Relations) and resident missions, assisted in organizing the ABM (Asia Bond Monitor) launches and seminars, as well as in reaching out to wider relevant audience. On providing greater impact, other than conducting dissemination activities to promote local currency bond markets, developing the capacities of policymakers on these areas should also be pursued. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/asian-bonds-online-website-phase-4-tcr
Capacity Building and Institutional Strengthening of the Free Trade Agreement Units of Selected ASEAN Member Countries: Technical Assistance Completion Report |  |  | 2015-02-01 | Capacity building needs evolve over time. Thus, it is very important to have regular consultation with DMC (developing member country) officials. An example is the timely organization of a training course organized in Viet Nam in the middle of TPP (Trans-Pacific Partnership) negotiations that focused on investor-state dispute and service negative list, which was new to Viet Nam. It is also useful to involve participants' institutions or agencies to share in some of the costs. This is important to assess whether a training course is relevant for participants. It also provides funding options for ADB's future training designs. Capacity building and research are closely related. Policy challenges that DMC policy makers face cannot be tackled without relevant research. This, in turn, means that research that intends to contribute to capacity building should be widely disseminated. Given the number of policy oriented journals, publishing capacity building research in journals is very feasible. Close collaboration with DMC experts on research is necessary to deliver high quality research output. In fact, in this project, based on the initial report on the impact assessment of ASEAN-PRC (People's Republic of China) FTA (free trade agreement) on the Cambodian economy prepared by a local expert, a research article was jointly developed by the consultant and ADB staff to be published in a journal. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-capacity-building-institutional-strengthening-fta-units-selected-asean-member-countries-tcr
Enhancing the Capacity of Selected ASEAN+3 Countries for Assessing Financial Vulnerabilities: Technical Assistance Completion Report |  | Public sector management | 2015-02-01 | Very knowledgeable and experienced ADB staff readily available to provide technical inputs to ETWG (ASEAN+3 Technical Working Group on Economic and Financial Monitoring) meetings, conduct training workshops and other capacity building activities to member countries have played a vital role in transferring knowledge and skills to national surveillance units of the ASEAN+3 countries, with less reliance from external experts. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-enhancing-capacity-selected-asean-plus3-countries-assessing-financial-vulnerabilities-tcr
Quantifying the Costs and Benefits of Regional Economic Integration in Asia: Technical Assistance Completion Report |  |  | 2015-02-01 | The publication was the first attempt to quantify the costs and benefits of integration in Asia. Gaps remain when findings are not conclusive. More work remains to be done as questions continue to challenge and warrant a deeper, more extensive study. The appeal should also be wider than a mostly academic audience. Moreover, a media book launch as well as enhanced dissemination efforts (e.g., among ADB's RCI [Regional Cooperation and Integration] Thematic Group and subregional programs) could have expanded its reach to more and relevant readers. From the administration point of view, an earlier closure of the TA (technical assistance) would ensure the completion of more focused activities as originally designed. Project cycle stage: Design, Implementation, Completion | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-quantifying-costs-and-benefits-regional-economic-integration-in-asia-tcr
Solid Waste Management in the Pacific: Technical Assistance Completion Report |  | Water and other urban infrastructure and services | 2015-02-01 | Given the large number of consultants recruited under the TA (technical assistance), and the need to consolidate outputs into knowledge products suitable for publication, recruitment of consultants through a single firm could have reduced TA implementation delays and minimized the burden of administering a large number of consulting services contracts. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/solid-waste-management-pacific-tcr
Prevention and Control of Avian Influenza in Asia and the Pacific: Validation of Completion Report |  | Agriculture, Natural Resources, and Rural Development, Health | 2015-01-30 | ADB in-house expertise supported by a dedicated ADB team gave the leverage and made it possible to conduct dialogue with the technical and regional agencies to strengthen regional collaboration within and across the animal health and human health sectors. It provided the advantages of using a multisector approach in addressing the problems caused by emerging and reemerging infectious diseases in lieu of national and regional economic development benefits. project cycle stage: Implementation The PSC (project steering committee) provided prompt policy guidance and expedited decisions and actions. The needs of the countries were ascertained and their access to project resources was adequate. project cycle stage: Implementation The project's One Health concept emphasized the links between animal health and human health, and emerging animal and human diseases, which allowed a platform for unprecedented integration of animal, human, and ecosystem health issues to fight the threat of avian influenza. The systematic collaboration of technical agencies across disciplines, such as the FAO or Food and Agriculture Organization (veterinarians) and WHO or World Health Organization (medical doctors) and civil society organizations (community health workers), promoted this concept since the beginning of the project. ADB's financial and convening power and its high flexibility and responsiveness under the project helped build links and strengthen collaboration between WHO, the FAO, and the World Organization for Animal Health. project cycle stage: Implementation The urgent nature of the project due to the threat that avian influenza may become a pandemic, hampered the attempt in defining verifiable indicators for some outputs under the regional capacity building and regional coordination components. A project midterm review would have helped to review and update the DMF (design and monitoring framework). project cycle stage: Design This type of project faces the challenge of the early spread of the disease outpacing the gathering of scientific evidence essential in formulating containment policies. In the early days of the severe acute respiratory syndrome, the avian influenza, and the H1N1 pandemic, uncertainty stalled decision making, including the decisions on the timing of changing policy from containment to mitigation. project cycle stage: Implementation This validation adds another lesson related to the relevance of design and formulation. Assessment of relevance includes both the relevance of objectives and the relevance of design. The adequacy and appropriateness of project design have to be tailored to the project's ultimate objectives and complexities. The PCR (project completion report) provided weak justification of the relevance of the extension and the insufficiency of indicators. project cycle stage: Design | Validation of Project/Program Completion Report | Successful/Generally successful | http://www.adb.org/documents/regional-prevention-and-control-avian-influenza-asia-and-pacific
ASEAN+3 Regional Guarantee and Investment Mechanism (Phase 3): Technical Assistance Completion Report |  | Finance | 2015-01-01 | None Project cycle stage: | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-asean-plus3-regional-guarantee-and-investment-mechanism-phase3-tcr
Capturing Economic Benefits from Ecosystem Services: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-01-01 | Demonstrating the value of ecosystem services: Informational, institutional and economic forces ? and how these forces interact - influence how ecosystem service values are demonstrated and how PES (payments for ecosystem services) schemes evolve on the ground. Improvements in quantification of ecosystem services that have global significance (carbon, biodiversity) are helping spur initiatives to better demonstrate the values of ecosystem services that provide local or regional benefits, primarily watersheds. With better information, more coordinated policies, and improved governance structures, private entities are becoming more willing to support provision of ecosystem services through PES schemes. Monitoring, reporting and verification: PES payments, in principle, need to be performance-based to ensure payment is consistent with the desired results. However, very few of the PES schemes observed in Asia and the Pacific are performance-based, with beneficiaries typically receiving payment without any reference to the delivered services, such as quantity and quality of water flow, increase of forest cover and biodiversity. Evidence is weak on the presence of sanctions for non-compliance of both sellers and buyers. Ensuring equity: Among the dimensions of equity ? economic, political and cultural ? the PES schemes reviewed have paid most attention to the economic dimension. Political and cultural dimensions need further integration. Project cycle stage: Implementation, Operation | Technical Assistance Completion Report | Partly/less than successful | http://wcm.adb.org/projects/documents/capturing-economic-benefits-ecosystem-services-tcr
Collaborative Research and Advisory Services on Public Sector Management: Technical Assistance Completion Report |  | Public sector management | 2015-01-01 | The TA (technical assistance) experience netted the following lessons. Collaboration with academic institutions works, but requires trust and patient engagement; the transaction costs can be high to manage a relationship. Administrative arrangements could be improved by creating modalities better suited for cooperation/partnerships with centers of excellence. In a knowledge collaboration with an academic institution, there needs to be careful selection of researchers (i.e., those who have had prior practical experiences and are flexible in their approaches) to ensure that outputs are anchored on practical realities and considerations and useful to ADB and clients in DMCs (developing member countries). Project cycle stage: Design, Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-collaborative-research-and-advisory-services-on-public-sector-management-tcr
Energy Sector Strategy and Development: Technical Assistance Completion Report |  | Energy | 2015-01-01 | The RETA's (regional technical assistance) knowledge products highlight the magnitude and gravity of meeting the energy needs of Asia and the Pacific. The region's energy demand is to grow at 2.4% per year from 2005?2030, faster than the global rate of 1.5% per year. In the long-term, the DMCs (developing member countries) must address issues related to both energy security and climate change as they sustain economic growth. The DMCs must also deal with fossil fuel resource depletion, increasing global competition for fuels, the need to build new energy infrastructure, and finding the financial resources to meet future energy needs. In this light, the review and updating of the ADB's energy sector strategy is timely and appropriate. The external review of the draft energy sector strategy is valuable in making it based on best international practices and in engaging parties which are interested in and knowledgeable on what actually is happening in the DMCs' energy sector. The CEFPF (Clean Energy Financing Partnership Facility) provides a good model in engaging financing partners in increasing the use of clean energy technologies. The respectable attendance in the 2006 Clean Energy Week, and amount of external feedback on the review 1995 Energy Policy and the draft energy strategy paper show the eagerness of various stakeholders to participate in dialogues and be part of the solution to economically and sustainably meet Asia and the Pacific's energy needs. Project cycle stage: Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/energy-sector-strategy-and-development-tcr
Grid Integration of Renewable Energy Sources and Solar Energy Technologies: Technical Assistance Completion Report |  | Energy | 2015-01-01 | The quality and content of the training program were relevant, timely, and excellent. In particular, the field visits were considered invaluable by all participants, as it provided a good balance between the theoretical and actual practice of grid- integrated RE (renewable energy) systems. While the course objective focused on the integration problems in grids, a considerable part of participants raised interest regarding isolated, non-grid connected areas, and the possible solutions to address these concerns. The off grid renewable energy case studies were brought to discussion as much as possible having the perception that an extra dedicated effort to this topic would have been of general interests. Project cycle stage: Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/grid-integration-renewable-energy-sources-and-solar-energy-technologies-tcr
Improved Management of Water Resources in Central Asia: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-01-01 | In order to reach mutual agreements, commitment from all participating countries and the broader perspectives of political and economic relationships among the participating countries and their priorities are important. At the beginning of the RETA (regional technical assistance), careful consultations with each country should have been done. The RETA spent much time to make adjustments due to the different political concerns of each country to obtain their consensus. Additionally, different priorities among the countries caused significant delays on project implementations and limit results. Project cycle stage: Implementation | Technical Assistance Completion Report |  | http://wcm.adb.org/projects/documents/reg-improved-management-water-resources-central-asia-tcr
Support for the ASEAN+3 Integrated Food Security Framework: Technical Assistance Completion Report |  | Agriculture, natural resources and rural development | 2015-01-01 | A key lesson learned by the TA (technical assistance) implementation was that while ASEAN's regional public goods and services are aimed in the right direction, further strategic interventions are required over the long term to strengthen capacity and institutional building to take on the responsibility for regional actions as well as knowledge generation and market intelligence dissemination functions in order to boost the resilience of ASEAN member states to volatility in rice prices. These are the aspects that will be addressed by the ensuing TA. Project cycle stage: Implementation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/reg-support-for-asean-plus3-integrated-food-security-framework-tcr
Sustainable Energy Training Program: Technical Assistance Completion Report |  | Energy | 2015-01-01 | There are common issues in clean energy development, financing and technology and these could be addressed in the global scale with the end view that any gains from this level would trickle down and be applicable to the specific contexts of ADB DMCs (developing member countries) both in terms of maximizing the potential and recognizing the constraints of their resources, policy environment and technological advancement. What is important in these regional venues of learning and exchange is to give space and due regard to local dynamics in order for these venues to be truly relevant and sustainable to target participants. Project cycle stage: Operation | Technical Assistance Completion Report | Highly successful | http://wcm.adb.org/projects/documents/sustainable-energy-training-program-tcr
Sustainable Urban Transport: Technical Assistance Completion Report |  | Transport | 2015-01-01 | One important lesson gained during the course of TA (technical assistance) implementation is the effective support provided by the resident missions to the TA consultant teams and staff especially in facilitating inter-agency coordination in each of the pilot cities . Partnering with regional and international development agencies on regional events and meetings is a cost-effective way of disseminating ADB's work in the subsector. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | http://wcm.adb.org/projects/documents/reg-sustainable-urban-transport-tcr
Real-Time Evaluation of ADB's Initiatives to Support Access to Climate Finance |  |  | 2014-05-07 | 1. As ADB accumulates knowledge in specific areas in which many countries intend to transform their economies and societies, there may be opportunities for it to provide guidance to the Green Climate Fund (GCF) in the design and monitoring of its programs that aim to achieve transformational outcomes in areas to which developing countries accord high priority. In this way, ADB could position itself as being more than just one of the many implementing entities or financial intermediaries for the GCF. [Executive Summary, page xiv] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Knowledge Management Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design 2. ADB can provide support to meet viability gaps through the climate change transformation cycle for a range of adaptation and mitigation options, and it will be important for ADB to innovate with financial products, and to augment resources accessed from climate funds with leveraged finance from public and private sources. [Executive Summary, page xiv] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Modality: Lending modality 3. To scale up and mainstream adaptation and mitigation (beyond clean energy), it will be necessary for ADB to (i) increase nonsovereign and private sector operations in a wide range of adaptation and mitigation domains, and (ii) ensure that the various initiatives that have been pioneered largely by the knowledge departments are used purposefully by the operations departments. [Executive Summary, page xv] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental management Crosscutting Issues/Themes: Knowledge Management Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Sector Related Issues: Private sector | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/real-time-evaluation-adb-s-initiatives-support-access-climate-finance
Prevention and Control of Avian Influenza in Asia and the Pacific |  | Agriculture, Natural Resources, and Rural Development, Health | 2014-03-01 | ADB was able to use its convening power effectively because it had the necessary in-house technical expertise. Public health experts on ADB's staff with knowledge of emerging infectious diseases were involved in designing and implementing the project. This in-house expertise made the dialogue with the technical and regional agencies to strengthen regional collaboration within and across the animal health and human health sectors possible. This dialogue also highlighted the advantages of using a multisector approach to address the problem of emerging and reemerging infectious diseases to provide national and regional economic development benefits. For partnerships between ADB and technical agencies, ADB needs to have strong in-house technical capacity in the relevant areas. Equally important is to have a dedicated team to support the in-house experts in coordinating and monitoring the implementation of the regional activities. Given the range of technical and regional implementing partners involved, the project did well by fielding experts in key geographical areas (Bangkok and Almaty) to facilitate regional collaboration. ADB's high-level steering committee demonstrated ADB's institutional support, which enhanced coordination between development partners. The committee, comprising the heads of all regional departments and the Strategy and Policy Department and chaired by the director general of RSDD, provided prompt policy guidance and expedited decisions and actions. It also ensured that the needs of the countries were ascertained and that they had adequate access to project resources. The project supported the One Health concept, which emphasizes the links between animal health and human health and emerging animal and human diseases. One Health provided a platform for unprecedented integration of animal, human and ecosystem health issues to fight the threat of avian influenza. The systematic collaboration of technical agencies across disciplines, such as FAO (veterinarians) and WHO (medical doctors) and civil society organizations (community health workers) supported by the project has promoted this concept since the beginning of the project. ADB's financial and convening power and its high flexibility and responsiveness under the project helped build up links and strengthen collaboration between World Health Organization, the Food and Agriculture Organization of the United Nations, and World Organization for Animal Health. The rapid launch and accelerated implementation of the project made necessary by the threat that avian influenza would become a pandemic made it difficult to define verifiable indicators for a number of the outputs under the regional capacity building and regional coordination components. A mid-term review of the project would have facilitated a review and updating of the design and monitoring framework. Each new outbreak of disease confronts projects such as this one, as well as the implementing partners and global community, with a fresh challenge, because its early spread outpaces the gathering of scientific evidence needed to formulate containment policies. Each successive outbreak is followed by an initial opaque period characterized by a frustrating lack of scientific evidence on which to base policies and technical guidance. In the early days of severe acute respiratory syndrome, the avian influenza, and throughout the H1N1 pandemic, uncertainty hindered decision making, including the decisions on the timing of changing policy from containment to mitigation. | Project/Program Completion Reports (PCR) | Highly successful | http://wcm.adb.org/projects/documents/prevention-and-control-avian-influenza-asia-and-pacific-pcr
Thematic Evaluation Study on ADB Private Sector Operations: Contributions to Inclusive and Environmentally Sustainable Growth |  |  | 2013-08-19 | 1. A trade-off is not necessary between development impact and investment profitability. Private sector operations that contribute directly to inclusive growth can have similar commercial viability and financial returns as other types of investments. [Main text, para. 200(i)] project cycle stage: Implementation, Completion Operation Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Sector Related Issues: Private sector 2. Inclusive private investments were usually the result of the following drivers: (a) the private sponsor's business model targeting the poor, women, or rural populations as customers; (b) government contracts and policies requiring inclusion of the poor (e.g., connection targets for poor areas under a water concession, slum rehabilitation as a condition for converting parts of slum areas into high-end residential property); (c) complementary public sector investments (e.g., public rural electrification programs ensuring the inclusiveness of private power generation and transmission projects); and (d) the availability of development aid to finance community development and livelihood programs, outreach activities, as well as subsidies for poor consumers (e.g., the collaboration between a water concessionaire and GPOBA). Close cooperation between regional departments and the Private Sector Operations Department can facilitate the presence of the last three drivers. [Main text, para. 200(ii)] project cycle stage: Design, Implementation, Operation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Sector Related Issues: Private sector 3. Inclusive project designs often involve systematic targeting of underserved areas or customer groups, the provision of services and products that address special needs of such groups, the use of appropriate delivery channels, affordable pricing, or engagement of the poor and other disadvantaged groups as employees, suppliers and distributors. [Main text, para. 200(iii)] project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Vulnerable groups Project Design: Project design Methodologies/Approaches: Targeting 4. Compared with public sector operations, ADB has had less scope to influence the design of private sector operations (PSO) not only because of the very nature of private sector transactions, but also because the Private Sector Operations Department (PSOD) has not had the level of resources required for more proactive project development. Most infrastructure projects, in particular, have usually been developed by the private sponsor before being presented to ADB at the financing stage. In such cases, PSOD's project design inputs are generally limited to the financial structure, and risk-sharing and safeguard arrangements, although there might be some scope for affecting project features through the mobilization of funding for pertinent investment components or complementary investments. For financial market transactions, ADB tends to be one of several financiers, and at best, a minority shareholder. Unless ADB can also provide advisory services, its window for influencing approaches to financial institution lending is small and usually limited to specific lending or investment allocations and environmental and social management system specifications. Careful selection of sponsor proposals is therefore important to maximize the development impact of PSO allocations. [Main text, para. 200(iv)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Project Design: Project design Sector Related Issues: Private sector 5. More Private Sector Operations Department (PSOD) involvement in project development does not necessarily lead to superior development impact. Some of the few finance sector transactions initiated by PSOD (rather than by private sector sponsors) in response to government requests and/or with the aim of promoting certain development goals, misjudged underlying private sector demand leading to low uptake and disappointing business performance. Examples include a couple of private equity funds and guarantees for small and medium enterprise lending. [Main text, para. 200(v)] project cycle stage: Implementation, Operation Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Project Design: Project design Sector Related Issues: Private sector 6. Inclusion objectives unless supported by effective project targeting and transmission mechanisms and impact monitoring are unlikely to be realized. By the same token, inclusion can happen if transmission channels are in place, even if not recognized by stated project objectives. [Main text, para. 200(vi)] project cycle stage: Design, Implementation Lesson Topics: Monitoring & Evaluation: Impact evaluation Methodologies/Approaches: Targeting 7. Small and medium enterprise (SME)-focused private sector operations are not necessarily supportive of inclusive growth. To design relevant transactions, the method in which SMEs contribute to innovation, competition, entrepreneurship, and (self-) employment including, among others, of the poor, women, and rural populations, needs to be clearly established; as well as factors identified that impede their potential for larger contributions. [Main text, para. 200(vii)] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Vulnerable groups Sector Related Issues: Private sector Methodologies/Approaches: Targeting 8. Lack of funding has rarely been the key binding constraint to private investment, but lack of a conducive investment climate and inadequate policy and regulatory frameworks have. Any significant nonfinancial impediments need to be addressed in tandem. [Main text, para. 200(viii)] project cycle stage: Design, Implementation Lesson Topics: Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Policy & Reform: Policy reforms/framework Policy & Reform: Reform 9. Even inclusive investments usually do not reach the poorest, which is difficult without subsidies. Instead, targeting low-income segments at a higher tier of the income pyramid that have not had access to private sector goods or services can also be a valid approach to facilitate inclusion. [Main text, para. 200(ix)] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Poverty reduction Crosscutting Issues/Themes: Social protection Crosscutting Issues/Themes: Vulnerable groups Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding Methodologies/Approaches: Targeting | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/thematic-evaluation-study-adb-private-sector-operations-contributions-inclusive-and-enviro
Greater Mekong Subregion Regional Communicable Diseases Control Project |  | Health | 2013-01-10 | 1. The project was designed to target vulnerable groups, including the poor, women and children, and ethnic minorities. It mainly targeted poor provinces in border areas, including 7 provinces out of 20 with a predominantly ethnic minority population. The project interventions benefited poor women and children, who are more at risk of communicable diseases. However, based on ADB's results framework criteria, the project is rated unsatisfactory for gender equity. It only partially complied with gender and ethnic minority covenants. While the executing agencies were responsive to prioritizing the needs of women and ethnic groups, these groups were not specifically targeted in outbreak control. Disaggregated indicators could not be provided. Engagement of consulting services also takes time in government systems, and came too late to help integrate gender and ethnic concerns in project activities. The feasibility of indicators and monitoring targets, and the capacity of the executing agencies should be taken into consideration when preparing the project. project cycle stage: Lesson Topics: 2. The ministries have a strong tradition of top-down training programs to be implemented by the provinces, often in an ad hoc manner. Provincial capacity to plan and coordinate training activities is insufficient. Provinces also lack core capacities in teaching methodology and in monitoring staff performance. project cycle stage: Lesson Topics: 3. Participation in regional dialogues and other knowledge management activities has, through learning and sharing, made national and provincial communicable diseases control leaders more competent, cooperative, and competitive. However, participation in internet-based learning and sharing is still at a nascent stage. project cycle stage: Lesson Topics: 4. Carrying out project administration through existing structures helped speed up project implementation. Delegation of project activities to concerned departments and provinces facilitated implementation. Inclusion of project activities in national and provincial annual operational plans provided better integration of health services and funding. project cycle stage: Lesson Topics: 5. Financial management requires further improvement through training of provincial staff, timely approvals of annual operational plans, and timely liquidation of advances. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://www.adb.org/projects/documents/greater-mekong-subregion-regional-communicable-diseases-control-project-pcr
Real-Time Evaluation Study of the Multitranche Financing Facility |  |  | 2012-12-27 | 1. Where the development effectiveness of a specific multitranche financing facility (MFF) investment program is to be assessed, data and documents that shaped the MFF implementation need to be accessible. Such documents have been difficult to obtain for this evaluation. Such information will be needed at MFF closure, when an MFF completion report is to be prepared, as well as when a specific MFF investment program is to be independently evaluated. [Executive Summary, page xiv; Main text, para. 194] project cycle stage: Completion Lesson Topics: Finance & Financial Aspects: Funding Modality: Lending modality Monitoring & Evaluation: Data collection and management 2. Improved monitoring can serve to give early warnings on the performance of large and long-term multitranche financing facilities (MFFs). For instance, the facility-wide and tranche level design and monitoring frameworks (DMFs) can form a basis for tracking and reporting performance at the MFF and tranche levels by further improving the linkages between MFF and tranche-level DMFs. The scorecard system can also provide a better basis for gauging and comparing performance across MFFs when the performance rating system is improved. [Executive Summary, page xiv; Main text, para. 195] project cycle stage: Implementation Lesson Topics: Finance & Financial Aspects: Funding Modality: Lending modality Monitoring & Evaluation: Monitoring and evaluation 3. Where actual tranche approvals in a given year exceed the country financing envelope for that sector, the country strategies and rolling business plans are not a sufficient basis for advance multitranche financing facility (MFF)-related information to the Board. [Executive Summary, page xiv; Main text, para. 196] project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Funding Modality: Lending modality 4. Where capacity constraints exist, it is difficult to prepare credible strategies and road maps?or, if prepared, to ascertain client ownership and buy-in. It is also difficult to institute policy frameworks that encourage a judicious mix of commercial, financial, social, and equity objectives along with improving operational efficiency and minimizing the environmental footprint. Under such circumstances, the investment plans, financing plans, and undertakings cannot be considered firm, with the possible exception of certain types of investments (such as a long highway that can be financed through a series of tranches). In short, where institutional capacities are weak, the multitranche financing facility (MFF) prerequisites of the desired quality are not likely to be easily achieved (e.g., the energy sector MFF in Afghanistan). [Executive Summary, page xiv; Main text, para. 197] project cycle stage: Implementation, Completion Lesson Topics: Finance & Financial Aspects: Funding Modality: Lending modality Capacity Development: Capacity development Capacity Development: Ownership 5. The rigor of economic, technical, and safeguards due diligence is important. Equally important is the rigor of due diligence on legal, financial, regulatory, social, gender, governance, fiduciary oversight and other aspects. While the devolvement of tranche approval processes encourages flexibility in many ways, the achievements through the multitranche financing facility program may deviate significantly from what was stipulated in the Board-approved documentation upfront. [Executive Summary, page xiv; Main text, para. 198] project cycle stage: Design, Implementation, Completion Lesson Topics: Finance & Financial Aspects: Funding Modality: Lending modality Project Design: Appraisal 6. Where lending constraints are increasing, and the evidence for improved development effectiveness remains tentative, it would be useful for ADB to consider ways to be able to exercise the option, if necessary, of terminating or cancelling ongoing multitranche financing facilities in midstream. [Executive Summary, page xiv; Main text, para. 199] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Funding Modality: Lending modality | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/real-time-evaluation-study-multitranche-financing-facility
Special Evaluation Study on ADB's Knowledge Products and Services |  |  | 2012-11-20 | 1. Recent efforts to strengthen knowledge orientation have given impetus to the knowledge management (KM) agenda. There are signs, across many areas of ADB, and especially in 2012, of efforts and initiatives to improve the organization's knowledge orientation. This is manifest through a variety of forms, including interdepartmental realignment within the Vice President (Knowledge Management and Sustainable Development) group, realignment within the Regional and Sustainable Development Department to create the Knowledge Sharing and Services Center, greater focus on knowledge in some regional departments, revision and updating of policies and guidelines in some knowledge areas (such as publications), and efforts to better monitor and gauge knowledge issues among staff and stakeholders through ongoing surveys. However, what is lacking is systematic self-evaluation of what has worked and what has not, and the incorporation of feedback from clients?the primary audience of knowledge products and services. project cycle stage: Design, Implementation, Completion Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Project evaluation 2. Work program and budget frameworks (WPBFs) need to more clearly show budget allocations to knowledge activities. Recent corporate-level WPBFs show an insufficient relationship between them and the strategic priorities of Strategy 2020. In particular, the WPBFs have not demonstrated the envisaged proportions of budget allocation against the drivers of change presented in Strategy 2020, including knowledge solutions. Consequently, it is not possible to judge the effects of the magnitude of effort and investment on the knowledge management agenda. Moreover, the absence of a budget line for knowledge-related work and a fully rolled-out time recording system makes it difficult to assess progress and the level of effort made at the project, country, and regional levels. This highlights the need for the WPBF to more clearly show budget allocations to knowledge-related activities. project cycle stage: Design, Country Partnership Strategy Lesson Topics: | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/special-evaluation-study-adb-s-knowledge-products-and-services
Special Evaluation Study on ADB's Social Protection Strategy |  | Health | 2012-11-07 | 1. Sustained social protection policy dialogue and focused lending and nonlending support in noncrisis years is critical for the establishment of effective and efficient national social protection policies and systems. Sustained policy dialogue is needed to raise awareness of the importance of social protection and prioritize government initiatives towards achieving inclusive growth. [Main text, para. 157] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Social protection Methodologies/Approaches: Policy dialogue 2. ADB's social protection interventions generally lacked sufficient attention to monitoring and evaluation frameworks, and only one (Philippines CCT) supported a rigorous impact evaluation. Project evaluations of social protection support showed good performance in such areas as pensions TA and social protection knowledge work, and generally mixed performance in other areas. Lack of impact evaluations makes it difficult to demonstrate the development effectiveness of social protection support to either the ADB Board or Management or to potential clients in Asian and Pacific DMCs. [Main text, para. 158] project cycle stage: Design, Operation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Social protection Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation 3. A growing body of evidence shows that social protection, particularly safety nets targeted at the poor, reduces poverty; improves nutrition, health, and education; promotes greater equity; and is affordable. Some countries in the region have started to develop, expand, or reform social protection policies and programs within their development plans to support inclusive growth and/or as part of efforts to scale back unsustainable and regressive broad-based subsidies. The demand for ADB support can be expected to grow if ADB is able to provide the right expertise and policy dialogue at the right time. [Main text, para. 160] project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Social protection Policy & Reform: Policy reforms/framework Methodologies/Approaches: Policy dialogue | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/special-evaluation-study-adb-s-social-protection-strategy
Special Evaluation Study on ADB's Response to Natural Disasters and Disaster Risks |  |  | 2012-10-19 | 1. The increasing frequency of natural disasters in all areas of the Asia-Pacific region with large human losses and economic damage makes it imperative to recognize the risks to economic development from these disasters. This applies particularly to disasters related to extreme hydrometeorological events in densely populated areas, as well as to geophysical events in tectonically unstable areas. [Main text, page 65, section B(i)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Country Context: Crisis/Post-crisis Country Context: Emergency 10. Delegation to resident missions speeds up decision-making. Delegation of authority to the resident mission for procurement, financing, and accounting procedures is essential for the close monitoring and expediting of decision-making. [Main text, page 65, section C(v)] project cycle stage: Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Other: Resident Mission 11. Major infrastructure rehabilitation may be better off with large contracts. The design, procurement, and management of many small contracts can burden the limited number of supervisors and inexperienced implementing agencies. However, some small contracts may still be required to help implement well targeted livelihood restoration and foster community participation. [Main text, page 65, section C(vi)] project cycle stage: Lesson Topics: Project Design: Project design Project Management: Procurement Project Management: Project management Country Context: Crisis/Post-crisis Country Context: Emergency 2. It is necessary to raise the currently still low DMC awareness of disaster risk reduction measures and of the commonality of the disaster threat in the region. ADB does not regularly receive requests from member countries with respect to disaster risk reduction. Also, some parts of Asia-Pacific have initiated useful regional initiatives, such as by the Association of Southeast Asian Nations and in the Pacific on monitoring weather and volcanic activities. However, such common concerns have not been in evidence elsewhere. ADB staff could be more proactive in raising risk awareness through policy dialogue and could also show how to address such risks. [Main text, page 65, section B(ii)] project cycle stage: Country Partnership Strategy Lesson Topics: Country Context: Crisis/Post-crisis Country Context: Emergency Methodologies/Approaches: Policy dialogue 3. Continuous dialogue with relevant ministries on disaster risk reduction is important. ADB can improve results by proactively engaging in regular dialogue with key disaster risk reduction ministries, and by systematically linking capacity assessments with loan and TA component designs and targets. [Main text, page 65, section B(iii)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Capacity Development: Capacity assessment Country Context: Crisis/Post-crisis Country Context: Emergency Methodologies/Approaches: Policy dialogue 4. Sustainability of outputs and outcomes of ADB disaster prevention projects is an important area for ADB focus. This has proved to be a weak area in the past, perhaps in part due to many governments' perception that prevention is a luxury that needs to compete with more immediate priorities. [Main text, page 65, section B(iv)] project cycle stage: Completion Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Country Context: Crisis/Post-crisis Country Context: Emergency 5. Consolidation of knowledge support in disaster risk reduction is also important. In recent years, there have been local initiatives to monitor hazardous weather or geophysical conditions. Most of these focus on computer simulations, hazard mapping and planning support, and early warning systems. They are not part of any national policy or economic development platform. ADB TA in this field needs to be linked to existing natural disaster coordination platforms and strategies in countries across the region. RSDD needs to link the work of its climate change mitigation and adaptation unit to that of its DRM unit. [Main text, page 65, section B(v)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Country Context: Crisis/Post-crisis Country Context: Emergency 6. Compared with evolving international good practice, ADB's approach to disaster recovery has been limited to infrastructure rehabilitation and has not extended to major livelihood restoration frequently, although in some cases a more comprehensive approach has already been applied. ADB needs to make sure it gives special attention to the targeting of disaster victims and other disadvantaged groups. [Main text, page 65, section C(i)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Vulnerable groups Country Context: Crisis/Post-crisis Country Context: Emergency 7. Realistic assessment of the executing agency is crucial. A realistic understanding is needed during project design and assessment of the institutional capacities of executing agencies. For complex multisector projects, monitoring of implementation is vital through a central steering committee or similar entity at a relevant ministry. Regular interaction between the borrower and ADB through the steering committee can contribute greatly to the success of a project. [Main text, page 65, section C(ii)] project cycle stage: Design, Feasibility Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies 8. Involvement of the community is important to identify and prioritize project activities. Many projects highlighted the importance of community participation to foster ownership and to identify and prioritize project activities. [Main text, page 65, section C(iii)] project cycle stage: Design, Implementation Lesson Topics: Capacity Development: Ownership Methodologies/Approaches: Community approach Methodologies/Approaches: Consultation/Participation Methodologies/Approaches: Participatory approach 9. Explicit recognition should be made of gender in natural disasters. Recent major disasters in Asia have shown fatality rates for women that were substantially higher than those for men. Women are often more vulnerable due to lower access and control over key survival and recovery resources including shelter, functional transport, and food. [Main text, page 65, section C(iv)] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Gender Country Context: Crisis/Post-crisis Country Context: Emergency | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/special-evaluation-study-adbs-response-natural-disasters-and-disaster-risks
Microfinance Development Strategy 2000: Sector Performance and Client Welfare |  | Finance | 2012-09-10 | 1. Challenges to implementing microfinance projects were country specific. These included the lack of an enabling environment, limited technical capacity of institutions, limited capital base and financial sustainability of MFIs, and distortions in the market. The factors critical to project success were (i) creating a conducive environment for microfinance, (ii) good design and properly sequenced activities, (iii) loans accompanied by TA for capacity development of institutions, (iv) clear understanding of the market, and (v) government commitment. [Main text, para. 138] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Modality: Technical Assistance Project Design: Project design Capacity Development: Capacity development Policy & Reform: Policy reforms/framework 2. While the MDS was formulated within the overarching objective of poverty reduction, project designs were usually not clear on the mechanisms for ensuring participation of the poor in the financial system. Most projects had no baseline data or periodic monitoring data of income or poverty levels, or sex-disaggregated data of participating microfinance clients. In addition, there was no standard set of performance indicators (financial and social) for monitoring the quality of institutions supported by ADB projects. As a result, there was no readily available systematic way to check on the performance of ADB's microfinance portfolio. [Main text, para. 139] project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financing Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Indicators 3. The MDS was reasonably well thought out at the time it was formulated, and its five areas of strategic focus remain relevant. However, it needs refinement to account for recent development and opportunities in the sector. Staff surveyed recommended the creation of the financial inclusion strategy to provide guidance on how poor households could access a broader range of financial services, reduce their risks, and improve their quality of life. [Main text, para. 140] project cycle stage: Country Partnership Strategy Lesson Topics: | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/microfinance-development-strategy-2000-sector-performance-and-client-welfare
Asian Development Bank's Support for Promoting Good Governance in Pacific Developing Member Countries |  | Public Sector Management | 2011-11-01 | 1. More aid from more providers requires better coordination and capacity. While growing inflows of aid from more donors brings additional resources for development, it also leads to higher risk of poor coordination and fragmentation. Pacific developing member countries (DMCs) and their key development partners have made some efforts to improve coordination, but many consider this as still a major weakness. For ADB, a more congested development landscape will necessitate continued partnership building with traditional including possibly nontraditional ADB partners, more effective leveraging of its limited resources, and a sharper focus on areas where it has clear comparative advantages and a history of success. One area where ADB has a known comparative advantage, and where it has added value, has been in its conduct and publication of investigative studies into important development issues affecting the Pacific DMCs. Strategies to more effectively manage this knowledge and improve its visibility and usefulness in Pacific policy arenas can be considered. [Main text, paras.34-37,98] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Capacity Development: Capacity development Capacity Development: Partnerships 2. Follow-on support, less complexity, and project designs that incorporate nuances of local culture and political economy help effectiveness of projects. While the evaluation found ADB's support, overall, to be less effective, there were clear examples of projects achieving their objectives. Projects that were supported over an extended period, which were less complex, and which took into consideration local cultural and political-economy factors were generally more effective. Thematic or sectoral diagnostics helped those involved in design and implementation to identify and achieve project objectives, as did dissemination of information and follow-on technical assistance. [Main text, paras. 62-63,99] project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Project Design: Project design 3. Joint diagnostics are useful in promoting alignment of programs and processes among donors as well as governments. In the Pacific region, collaborative work with other development partners, through regional technical assistance and other modalities, promoted harmonization of country systems, improved coordination, and was found by the evaluation to be helpful in improving effectiveness. Collaboration within ADB was also found to be useful specifically in improving the procurement process and knowledge sharing for effective project implementation. [Main text, paras. 64,101] project cycle stage: Design, Implementation Lesson Topics: Modality: Lending modality Modality: Policy-based lending Modality: Program Modality: Project Modality: Technical Assistance | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/asian-development-banks-support-promoting-good-governance-pacific-developing-member
Special Evaluation Study on Managing for Development Results |  |  | 2011-10-31 | 1. After 7 years from the introduction of the Management for Development Results (MfDR) agenda, and 5 years since the approval of the first time-bound MfDR action plan, the Special Evaluation Study considers that mainstreaming of the MfDR agenda has progressed well to date, but that there are still enough areas that need attention to warrant the preparation of a new action plan by the Results Management Unit of the Strategy and Policy Department. The new action plan could emphasize more evaluation and learning from results in line with ADB's MfDR definition and internationally-recognized MfDR principles. It is recognized that the next phase of the implementation of the MfDR agenda may have substantial resource implications as well. [Main text, paras. 9,36,130] project cycle stage: Country Partnership Strategy Lesson Topics: 2. Over the course of the four Development Effectiveness Review (DefR) issues published during 2007?2011, the report has proven its worth as a valued corporate results reporting tool. The fact that the DEfR report has moved from being simply a public accountability tool to also being an important internal planning document, which is integrated into the ADB's high-level planning processes, is an additional factor demonstrating the utility of the tool. Given that other multilateral development banks such as World Bank and African Development Bank have followed ADB's lead in developing corporate results reports, the DEfR represents an international 'good practice.' [Main text, paras. 20,36,131] project cycle stage: Design, Operation Lesson Topics: Crosscutting Issues/Themes: Corporate governance Crosscutting Issues/Themes: Managing for Development Results Monitoring & Evaluation: Reporting 3. Using indicators with baseline data, improving staff accountability and incentives for results framework preparation and monitoring, and supporting the development of selected statistics for monitoring and evaluation are some possible solutions that could enhance results orientation of country partnership strategies (CPSs) and projects of ADB. The paucity of systematic data updating efforts has hampered the results orientation of ADB's CPSs and projects. Evaluation has noted lack of reliable data, including baselines, as a factor in project design and monitoring framework and CPS results framework quality. The challenge of identifying time-trend indicators that are regularly updated (preferably by in-country partners) has also been noted as a long-standing problem. [Main text, paras. 115,120,132] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Monitoring & Evaluation: Baseline data Monitoring & Evaluation: Data collection and management Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation 4. Reinforcing the monitoring of the various links of the results chain through better outcome and impact measurements would be a useful way of making the entire chain stronger and achieving greater results orientation at project, country, and corporate levels. As yet, there is insufficient evidence that the Managing for Development Results (MfDR) agenda has led to more outcome (and project impact) measurement. Current reporting tools used at various levels do not adequately stress the later results chain links, which inhibits focus on the achievement of results. To facilitate outcome orientation at the project level, the Independent Evaluation Department needs to revisit the weights accorded to the various evaluation criteria to put more importance on downstream results (e.g., effectiveness and sustainability criteria), and focus more on project outcome (and to the extent possible impact) reporting. Looking forward, ADB may consider additional ways to appropriately measure all the links of the results chain, with a view to making the chain stronger. [Main text, paras. 120,133] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting 5. Strategic approaches with government ownership at the center will be needed to successfully inculcate Managing for Development Results (MfDR) agenda in developing member countries (DMCs). DMC governments face a number of key challenges in increasing their understanding and use of MfDR, chief of which are absence of strong champions, lack of continuity due to political change, and lack of domestic demand for results-based management at different government levels. At DMC level, MfDR is not merely a technical or policy initiative, but a long-term and complex public sector reform process. It will encompass several administrative jurisdictions and political interests in matters such as accountability, participation and governance. The process also involves changing the attitudes of government staff and ideally fostering a results culture in the bureaucracy, and should be tailor-made to the given cultural, institutional, and political situation of each country. To align its MfDR strategy to DMC goals and objectives, ADB will need to be sensitive and respond to specific DMC needs, and to consider approaches to developing more comprehensive capacity development policies and tools. The Asia-Pacific Community of Practice on Managing for Development Results and DMC communities of practice could play a valuable supportive role in this regard. [Main text paras. 53,134] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Capacity Development: Ownership 6. Further improvement in the quality of project design and monitoring framework (DMF) can be achieved with significant attention from ADB on training, quality control as well as management emphasis on the instrument. The establishment of internal quality control mechanisms, training on project DMF preparation, and revisions to the DMF guidelines contributed to gradual improvements in the DMF quality. However, despite these undertakings, there appears to be continuing issues with DMF quality due to poorly formulated indicators, outputs, outcomes, and data sources. [Main text, paras. 61,120,135] project cycle stage: Design Lesson Topics: | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/special-evaluation-study-managing-development-results
Countercyclical Support |  |  | 2011-10-01 | A key lesson from the Viet Nam Countercyclical Support (VIE-CS) design and implementation process is the importance of the sustained dialogue between ADB and the government, as it ensured efficient program formulation. It also enabled good coordination between the Countercyclical Support Facility (CSF) and other policy lending operations already under implementation at the time. The existence of long-term, policy-based operations in Viet Nam that focus on macroeconomic management, public financial management, and social assistance greatly assisted the processing of the VIE-CS. Despite a shortened loan processing period, by the time the loan was eventually disbursed, most of the elements of the stimulus package were expiring. To the extent that loan processing could be further simplified and accelerated in the future, the potential impact of the CSF might be assisted. Not limited to the case of Viet Nam, the impact on gross domestic product (GDP) growth rates of the fiscal stimulus package shows the importance of a multidimensional strategy that allowed responding to the variety of challenges posed by the severe global financial crisis of the last few years. In Viet Nam, the strategy included tax cuts, large infrastructure spending, interest rate subsidies, and social welfare programs. However, the government should give consideration to the development of automatic macroeconomic stabilizers that provide an adequate social safety net. The macroeconomic instruments available to stimulate domestic demand were somewhat limited. As in other developing economies, Viet Nam lacks the kind of macroeconomic stabilizers such as unemployment and social security benefits that are triggered instantly as economic conditions worsen. The options used for the fiscal stimulus package included a range of instruments with varying potential for economic stimulus. Social spending may have yielded the most immediate results by increasing disposable income for domestic consumption, followed by employment generated by the implementation of infrastructure projects. On the other hand, onlending to domestic enterprises as a stimulus measure presents complex challenges. Adequate and transparent risk and cost benefit assessments, and detailed and individual project evaluation are required. In Viet Nam, projects financed through the onlending mechanism of the fiscal stimulus package included strategic sectors such as ship building, steel, cement, and the aircraft industry, in addition to light manufacturing (textiles, ceramics, etc.). The slower pace reported in disbursement of the onlending mechanism, in comparison to the quick implementation of other components of the stimulus package, should be an area for further analysis when establishing the relative efficiency of the fiscal stimulus components. The incremental capital output ratio in Viet Nam has increased over the last 10 years, and continued to increase after 2008. This suggests that the efficiency of the economy is falling. There is a strong view that the root cause of inefficiency is in public investments and the state-owned enterprise (SOE) sector. There is perceived little transparency or accountability on how large-scale public investments are selected and implemented, and little oversight of investment decisions. As it is the case with any policy-based lending, the impact and outcome of the VIE-CS loan was highly dependent on the quality of public financial management. Additional efforts in improving the efficiency and transparency of public financial management would allow even greater impact of similar fiscal stimulus programs. Key structural challenges of the Vietnamese economic system, such as the regular financing of SOEs by state-owned commercial banks, should remain a core area of analysis and reform, as such a structure may be limiting adequate market competition for available financial resources. Initiatives such as ADB's SOE Reform and Corporate Governance Facility, which supports the restructuring of state enterprises into more privately oriented institutions, are important steps in that direction. It will take time to discern the impact of the overall stimulus package. Recent fiscal data from the United States have corrected initial assessments of the depth of the economic and financial crisis and, with it, the impact of the stimulus package implemented. Similar trends could be at play not just in Viet Nam, but in other Asian economies that implemented stimulus programs. In that light, perhaps, program evaluation will be more adequately served with an assessment 3-4 years after loan disbursement. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/countercyclical-support-0
Countercyclical Support |  |  | 2011-08-01 | Based on this performance evaluation there are two lessons. First, efficient public financial management (PFM) systems are important to ensure timely disbursements. While Indonesia has made progress in PFM reform, it clearly needs to do much more to address the chronic problem of back-loaded spending in the fourth quarter of each fiscal year. Second, Indonesia's fiscal stimulus package was successful because it included a mix of measuresï¿½ including tax cuts, social spending, and labor-intensive small-scale infrastructure projectsï¿½and because effective and regular monitoring and reporting mechanisms were in place. The countercyclical support facility (CSF) loan would have been more timely if the facility itself was in place at the time the GFC (global financial crisis) began in the third quarter of 2008. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/countercyclical-support-1
Performance of the Asian Development Bank Institute: Research, Capacity Building and Training, and Outreach and Knowledge Management |  |  | 2011-07-31 | 1. Many midcourse corrections could have been made to sharpen Asian Development Bank Institute's (ADBI's) knowledge products and services through periodic self- assessment. In addition to the annual staff retreat, advice and recommendations given by the advisory council, and ADB Board discussions on ADBI's Three- Year Rolling Work Program and Budget taking place every December, this self-examination could be carried out every 3?4 years, particularly before a new dean is appointed. [Main text, para. 113] project cycle stage: Implementation, Completion Lesson Topics: 3. A well-formulated vision and mission statement is an important foundation for defining the direction of an institution. The Asian Development Bank Institute's (ADBI) vision and mission set the parameters for defining its functions of research, capacity building and training, and knowledge dissemination over a planned period such as the current 3-year rolling plan. Even more important, the vision and mission need to take into account the strategies and operations of ADB, the region's social and economic structure and institutions, the overall global environment, and the views of regional constituencies that eventually map out their policies and programs. In this connection, ADBI rightly indicates its 2008 alignment with ADB's Strategy 2020 in key documents such as ADBI's Year in Review and Three-Year Rolling Work Program and Budget. [Main text, paras. 14-15, 114] project cycle stage: Design Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Methodologies/Approaches: Targeting 4. ADBI's network could be strengthened by having more formal institutional links and networks based on a partnership framework. Because of its location and geographic advantages, institutional partnering with Japan-based partners is stronger than with developing member country (DMC)-based partners. For the most part, ADBI's partners in the DMCs are based more on individual relationships with representatives of their organizations (i.e., there is no clear institutionalized DMC-based partner organization). [Main text, paras. 19-21, 115] project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Capacity Development: Partnerships 5. A clear, long-term, strategic approach of selecting training themes would increase the likelihood that capacity building and training (CBT) courses will contribute in a sustainable manner to the capacity of developing member country (DMC) institutions. Similar to Asian Development Bank Institute's (ADBI's) research, CBT has been strategically programmed since 2008 according to the three priority themes of (i) inclusive and sustainable growth, (ii) regional cooperation and integration, and (iii) governance for policies and institutions. Those three priority themes are still too broad to provide much guidance for training topic selection. Given its limited resources, ADBI could consider a more programmatic approach of long-term strategic partnerships with a small number of selected DMC institutions, ADB headquarters, and international organizations, involving a series of interconnected events over the course of a multi-year period. [Main text, paras. 48, 116] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Capacity Development: Partnerships Methodologies/Approaches: Targeting 6. A more structured consultative process with top-level DMC officials could produce a capacity building and training plan that is more responsive and tailored to specific DMC development needs. The current system of conducting training needs assessment surveys does not fully deliver the data Asian Development Bank Institute (ADBI) needs for good course planning and discourages further direct consultations between ADBI and focal-point organizations. This system depends largely on ADB resident missions to distribute training needs assessment survey forms, and whether the forms are returned to ADBI depends mostly on these missions. Dialogue takes place between ADBI and developing member country (DMC) organizations on a sporadic basis. [Main text, paras. 51, 117] project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Capacity Development: Capacity assessment Capacity Development: Capacity development 7. Asian Development Bank Institute (ADBI) is constrained by the existing selection process and limited choices concerning the identity or seniority of the individuals that developing member country (DMC) governments and organizations choose to attend capacity building and training (CBT) programs. More control would enable ADBI to better direct and match course content and Modality, such as the policy dialogue format, to the kind of participants it intends to reach, which would ensure that CBT would be more successful in the long run. If selection nonetheless remains as the prerogative of DMC governments, ADBI should continue setting minimum standards for course participation and exercise its right not to accept a candidate who does not meet them when appropriate. As ADBI puts more importance on the policy dialogue seminar under the CBT program, CBT courses should be meant for senior-level and top- end of mid-level policy makers. [Main text, paras. 52-53, 118] project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Capacity Development: Capacity development Methodologies/Approaches: Policy dialogue | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/performance-asian-development-bank-institute-research-capacity-building-and-training-and
Real-time Evaluation of Asian Development Bank's Response to the Global Economic Crisis of 2008 - 2009 |  | Finance | 2011-06-30 | 1. Institutional readiness and greater flexibility are important in responding to crises. Timeliness is critical to crisis response; usually, the earlier the response, the more effective it is. Delayed response diminishes the value of ADB assistance to some extent. Institutional readiness to assist in future crises should place emphasis on (i) the need to have capital headroom for contingencies, and (ii) the timeliness of assistance. There will be a trade-off between ADB's crisis response operations and its normal operations unless ADB augments its risk-bearing capacity to mount a crisis response when a crisis is imminent. To stay prepared, ADB could evaluate the options for possible crisis response size, financing modalities and terms of such response, and their implication for normal lending operations as part of its medium-term planning. [Main text, paras. 20?25, 145, 147] project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Modality: Lending modality Capacity Development: Capacity assessment Capacity Development: Capacity development 10. A medium-term focus on building social protection systems in developing member countries (DMCs) collaboratively by development partners would enhance the DMCs' resilience to crises. Social protection programs are attractive crisis-mitigating instruments for two reasons: They have an inbuilt countercyclical bias and they protect the poor, who are the first to be affected by a crisis. If a country has an established social protection program?such as the conditional cash transfer program of Brazil or the employment guarantee program of India?it could be scaled up or down as required. In the presence of such programs, ADB's crisis support would be more effective and DMCs would become resilient to crises. However, social protection programs are often characterized by poor targeting, leakages, and waste. Thus, deeper knowledge about the operation and performance of such schemes is necessary if ADB is to rely on them in the future. In the medium term, ADB, jointly with other aid agencies, could develop comprehensive, well targeted social protection systems in the DMCs, keeping in mind a country's vulnerabilities, affordability, and administrative and political economy matters. [Main text, para. 156] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Crosscutting Issues/Themes: Social protection 2. Surveillance of more countries and regions would further enhance ADB's crisis response ability. ADB was better prepared institutionally to respond to this crisis than to the Asian crisis in 1997, in part due to the Office of Regional Economic Integration's assistance to surveillance in East and Southeast Asia. ADB could further strengthen the depth and frequency of its macroeconomic analysis of countries, and widen its surveillance capacity development and monitoring activities to regions outside East and Southeast Asia. A solid understanding of the macroeconomic situation in DMCs, and continuous monitoring of macroeconomic and finance sector developments, will enable ADB to assess the vulnerability of individual DMCs to future crises and to equip itself to respond more effectively. [Main text, paras. 30-41, 148] project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: 3. A crisis response facility for Asian Development Fund (ADF)-only countries would have been a useful crisis-response window during the period of the global economic crisis. While ADB successfully mobilized significant additional resources to help DMCs, the benefits of its response were unevenly distributed, to the disadvantage of severely affected countries. As a group, the countries most affected by the crisis received a lower share of additional ADB assistance than moderately and least-affected countries. This happened in part because a concessional crisis-response window that would exclusively help smaller and poorer countries was absent. ADB did try to boost its assistance to severely affected countries, but the rigidity of ADF allocation and the difficulties in the use of regular program and project loans for such countries constrained it. [Main text, paras. 43?45, 131, 149] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: 4. In a crisis situation, it is important to make more resources available to developing member countries (DMCs). For this, the focus of ADB should be on increasing disbursements. During crisis situations, ADB also needs to assess net resource transfers to DMCs from all official sources of development assistance. The evaluation found that a number of smaller DMCs, although most affected by the crisis, received negative net transfers from ADB during 2009?thereby inadvertently making ADB operations procyclical. This would not have occurred if the eligibility criteria that ADB used to allocate crisis-response resources to DMCs had taken into account the projected net resource transfer position from all funding sources, particularly for the most vulnerable countries. [Main text, paras. 46-48,150] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Disbursement Finance & Financial Aspects: Financing 5. Better internal coordination and collaboration at ADB among departments would have made the assistance during the global economic crisis even more efficient. ADB's response to the crisis would have resulted in a more optimal use of resources if there had been an arrangement (for example a committee of directors general) with one nodal lead to coordinate crisis-related responses of operations departments and knowledge departments. There was close interdepartmental coordination for preparing Plan B, which was ready in December 2008. However, asymmetry seen in the operational burden of this crisis on some departments and staff with requisite expertise could have been moderated through better coordination among operations departments. A coordinated and collaborative approach could have allowed crossdepartmental use of experienced and highly skilled staff, which could have further improved the quality of products and possibly reduced processing time, which was already compressed. [Main text, paras. 20, 40?41, 63, 151] project cycle stage: Implementation, Operation Lesson Topics: Capacity Development: Capacity development Capacity Development: Human resources management 6. The Countercyclical Support Facility (CSF) could be designated as a standby facility offering greater flexibility in disbursements. Blend countries would benefit from longer tenor where needed. The evaluation found the CSF to be a useful instrument for crisis response. However, it would be more effective if it offered more flexibility in loan size and tenor to fit the diverse needs of different countries. As found in the case of Bangladesh, which is not a middle income country, greater flexibility in withdrawing funds from the loan in the amounts and at the time needed by the government would have made the instrument more effective. Greater flexibility in disbursements, similar to the deferred drawdown facility offered by the World Bank, would have enhanced the CSF's responsiveness. Also, a fixed 5-year tenor for all countries makes the instrument less suitable for some poorer countries eligible for a blend of ADB's ordinary capital resources and Asian Development Fund (ADF) assistance?some could find it impractical, if not disruptive, to repay the loan in just 2 years in large biannual installments. A longer tenor (up to 8 years based on assessed need) would enhance the concessionality of the facility to the blend countries, which are unlikely to get access to the ADF crisis-response window. [Main text, paras. 69?70, 110?112, 152] project cycle stage: Country Partnership Strategy Lesson Topics: 7. A precautionary financing instrument (similar to the contingent loan provided to Indonesia) would be a useful tool to respond to future crises, particularly to help middle-income countries. To be effective, the facility would have to be provided rapidly and jointly by all participating agencies, since the intent of such an intervention is to give a strong signal to the markets. The contingent loan provided to Indonesia is akin to ADB's regular program loan in its tenor and processing approach. ADB should assess the implication of providing such a long tenor for crisis support loans on its headroom. If the Countercyclical Support Facility (CSF) is designed as a flexible instrument, the precautionary finance instrument could become a special case of the CSF. This would also allow fast-track processing of precautionary finance loans?a great advantage at a time of crisis. [Main text, paras. 74, 76, 110?111, 153] project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Modality: Lending modality 8. More rigorous assessment of vulnerability and coping abilities, and paying attention to net resource transfers, would have improved targeting. A further refinement of selection criteria?to include assessment of (i) the vulnerability of developing member countries via composite indexes based on information reflecting the fundamental strength of the policy regime and structural aspects of the economy, (ii) the ability of social protection systems to cope with a crisis, and (iii) net resource transfers from all official sources of development assistance?could ensure the flow of resources to countries that are more affected and in greater need. The criteria also need to include (i) triggers for Countercyclical Support Facility assistance, and (ii) principles for assessing the quantum of assistance required from ADB. [Main text, paras. 107?108, 154] project cycle stage: Implementation, Operation Lesson Topics: Crosscutting Issues/Themes: Social protection Modality: Lending modality Project Design: Project design Capacity Development: Capacity assessment 9. The Trade Finance Program (TFP) is a useful instrument during crises. The TFP is an excellent crisis-response instrument, particularly in Asia, where trade intensity is high; and for smaller developing member countries (DMCs) that rely on foreign trade and are more vulnerable to crises. Continuation of the program could help ADB stay engaged with local banks in DMCs and would enable it to scale up the facility in response to a crisis. It could potentially strengthen the banking sector in weaker DMCs, and fill persistent gaps in markets by helping smaller DMCs access trade finance. However, its actual performance in this regard will have to be assessed in greater depth. Therefore, it would be useful to study, at a later date, the relevance and effectiveness of the TFP at the subproject/borrower level from the point of view of development impact, ADB profitability, and ADB additionality. [Main text, paras. 119?129, 155] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Modality: Lending modality Modality: Program | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/real-time-evaluation-asian-development-banks-response-global-economic-crisis-2008-2009
Establishment of the Pacific Aviation Safety Office Project (Pacific Region) |  | Transport | 2011-06-01 | The project is unique among ADB interventions in the Pacific. It involved setting up a regional organization from scratch, using a regional loan guaranteed by four Pacific Aviation Safety Office (PASO) members. While the concept was innovative, the first lesson is that a regional project can raise a variety of new issues. Inception was delayed by lengthy procedures for parliamentary approval of two of the guarantees. As of 2011, there is a risk that the organization could eventually fail unless a secure funding basis can be established in the near future. Longer-term counterpart support needs to be built into the project design, so that short-term funding crises do not dominate operations and threaten the ability of the institution to offer technical services. Technical cooperation has required the use of best-practice systems and highly experienced professional staff from more developed countries. The development of regional expertise will take many years and require additional resources, if Pacific developing member countries (DMCs) expect to localize these positions. This environment requires flexibility in PASO staffing and structure to enable adjustments. A significant advantage of PASO, unlike the alternative of contracting other countries' inspection services, is that member countries receive dedicated professional advice and administrative backup to facilitate such improvements. Strong management and strategic thinking are prerequisites for establishing a sound and viable institution. The early management of PASO was weak. More support was needed to help it put necessary systems in place earlier in the project period. Some member states expressed the need to further improve financial management in terms of adequacy and transparency. The PASO council has the potential to provide needed support through its finance and technical committees but has not yet fully leveraged those capabilities. The introduction of new aviation systems into regional and national organizations needs to be subjected to in-depth systems analysis to ensure that the systems are appropriate to the environment. Also, it is necessary to provide sufficient, continued capacity development and training to retain the use of the system and improve it. The concept of regional cooperation in technically demanding sectors is sound. The project concept of developing the coordinated provision of technical services to small and poorly resourced states has been proven. The project has helped develop similar regional activities in Asia and Africa by demonstrating feasibility to the International Civil Aviation Organization (ICAO) and other international organizations. Institutional lessons arise from the need for cooperation on the part of governments, airlines, and international agencies in reforming and harmonizing the regulatory and legislative environment. ICAO has already recognized PASO as a legitimate international organization and will exercise quality control through the regular Universal Safety Oversight Audit Program and Universal Security Audit Program in each country. Governments need to ensure continuing cooperation between aviation ministries and other ministries responsible for drafting and enacting legislation and for providing finance. The benefits of harmonization are clear to airlines. | Project/Program Completion Reports (PCR) | Successful/Generally successful | http://wcm.adb.org/projects/documents/establishment-pacific-aviation-safety-office-project-pacific-region
Asian Development Bank Support for Gender and Development - Phase II: Results from Country Case Studies |  |  | 2010-12-31 | 1. Several specific factors contribute to successful gender mainstreaming of ADB support. These include: (i) projects are more successful when coherence is strong between upstream analytical work, downstream project design and implementation; (ii) project-specific gender analysis strengthens responsiveness, and provides a foundation for assessing potential an actual impacts; (iii) project documents that pay explicit attention to gender-related targets, output and outcome indicators can facilitate monitoring of implementation progress; (iv) provision of resources to implement gender-focused design features is critical to both successful design and effective implementation; and (v) capacity development of executing and implementing agencies and others responsible for project implementation to address gender-related issues in the sector and project is crucial to effective implementation of gender-related design features. [Main text, para. 82] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Gender Monitoring & Evaluation: Monitoring and evaluation Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Capacity development 2. Strengthening consultation and participation throughout the project cycle, and working with development partners and civil society organizations (CSOs) to improve coordination and collaboration around key issues, are important elements of strengthening country and project gender mainstreaming. The consultations with stakeholders, and notably development partners and CSOs, confirm that the different actors involved in gender mainstreaming projects bring important insights, experience, and perspectives to bear. ADB can support this through (i) engaging more fully with in-country gender working groups that provide opportunities to exchange ideas and share experience in gender mainstreaming; (ii) using in-country networks to develop and strengthen shared understandings of gender issues in developing member countries and to develop common approaches to addressing these issues; and (iii) working with partners to develop, in collaboration with government and civil society counterparts, approaches to tackling economic issues, including microfinance, private sector development and entrepreneurship, land tenure and rights, and approaches toward promoting women's empowerment as called for in Millennium Development Goal 3 on gender equality. [Executive summary; Main text, para. 83] project cycle stage: Design, Implementation, Completion, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Gender Crosscutting Issues/Themes: Knowledge Management Methodologies/Approaches: Civil Society Participation Methodologies/Approaches: Consultation/Participation | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/asian-development-bank-support-gender-and-development-phase-ii-results-country-case
Financing Partnership Facilities |  |  | 2010-12-31 | 1. There are potential benefits from consolidating trust funds outside the financing partnership facilities (FPFs) into the current FPFs. The potential advantages of this type of consolidation are twofold: (i) broadening the FPF partnership membership would diversify the sources of finance (and also increase the nonmonetary financing mechanisms provided), thereby improving both the relevance and the financial sustainability of the FPFs; and (ii) increased economies of scale in ADB's partnership financing would render the FPFs more efficient. [Main text, para. 127] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Finance & Financial Aspects: Financing Finance & Financial Aspects: Funding | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/financing-partnership-facilities
Asian Development Bank's Support to Fragile and Conflict-Affected Situations |  |  | 2010-10-31 | 1. Project designers and implementers may need to incorporate built in mechanisms for flexibility in adjusting outputs and components for as long as it is consistent with project outcomes. Adjustments and major change in scopes, with a few cases of cancellations, have proven to be highly probable during project implementation and efficiency has suffered as a result. Some quick disbursing emergency response instruments have been extended beyond the intended time period due to non-emergency issues. Reasons vary and include unanticipated security issues in post-conflict DMCs, nonresponsive executing agencies and weak institutions in small and isolated economies. [Main text, paras. 82?85,122] project cycle stage: Design, Implementation Lesson Topics: Country Context: Conflict/Post-conflict Country Context: Emergency Methodologies/Approaches: Targeting 2. In exited FCAS countries, the technical aspects of infrastructure projects overall are doing well. Problems that need to be addressed center on building capacities and institutions and effecting policy reforms. In Tajikistan, reporting, accounting, and monitoring procedures were inadequate. In the Lao PDR, the infrastructure component of an urban development project was considered a success, but the entity that was established to manage and maintain the facilities needs further institutional strengthening. In small Pacific island countries, infrastructure projects have had to contend with the logistical challenges of typhoon cycles and bringing equipment to widely dispersed smaller islands. In some, the infrastructure component is straightforward and simple (e.g., building training facilities) yet it is weak implementation capacities that hampers implementation (paras. 79?81, 123). project cycle stage: Implementation Lesson Topics: Capacity Development: Capacity building Capacity Development: Capacity development Country Context: Conflict/Post-conflict Policy & Reform: Policy reforms/framework 3. In small Pacific fragile and conflict-affected situations (FCAS) countries, commonality of issues and the small size of country-level support provide opportunities for pooling of resources across developing member countries (DMCs) to support common themes. For example, ADB and the Government of Australia co-financed regional technical assistance (TA) initiative for private sector development has been effective in strengthening the regulatory and legal environment for business in Pacific countries, including current Pacific FCAS countries. [Main text, paras. 33,124] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: 4. Private sector partnerships work with the right incentive. In Papua New Guinea, drawing on the expertise of the banking association to support microfinance has progressed well. The association has supported training for microfinance institutions and a reasonable fee was charged to sustain operation. Another example which is showing initial success is the partnership between civil society and a network of entrepreneurs to market and disseminate HIV/AIDS prevention and control in rural areas. [Main text, paras. 77?78,125] project cycle stage: Implementation Lesson Topics: 5. More important than large resource transfers to fragile and conflict-affected situations (FCAS) is the need to understand the country and the counterparts, to produce better, simpler designs, and to commit to work consistently over a medium-term horizon. The current (FCAS) countries are not performing quite as well as the DMCs that have left FCAS status. They have more pronounced problems with efficiency and achieving outcomes. The solution does not lie in simply relaxing business processes and procedures since this could lead to unintended governance issues. [Main text, paras. 34,40,82?83,126] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Country Context: Conflict/Post-conflict 6. In policy-based support, ADB must strengthen its efforts to follow-through on complex civil service reforms, achieve privatization of state-owned enterprises, and strengthen public financial accounting and reform in order to address sustainability concerns due to capacity constraints in fragile and conflict-affected situations (FCAS) countries. FCAS country institutions, by the nature of their capacity limitations, are constantly challenged by the lack of adequate and stable funding, and maintenance of the assets financed by ADB. For instance, cost recovery is a common problem for public utilities (failure to implement user charges). [Main text, paras. 58,105-106,127] project cycle stage: Completion Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Management: Operation and maintenance Country Context: Conflict/Post-conflict | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/asian-development-banks-support-fragile-and-conflict-affected-situations
Water Policy and Related Operations |  |  | 2010-10-31 | 1. At the strategic level, an effective policy needs to be firmly grounded in the core business of an enterprise. Successful policies need to be accompanied with clearly defined targets, required approach and resources, and a reliable monitoring mechanism with result indicators. Evaluation noted one of the principal weaknesses of ADB's water policy is the lack of realistic target results (outputs and outcomes) for water sector program performance, monitoring and evaluation framework for intended development results. The absence of monitorable outcome indicators at the sector and subsector levels under ADB's policy has also limited the assessment of its effectiveness. [Main text, para.85,128,168,170] project cycle stage: Design Lesson Topics: Monitoring & Evaluation: Indicators Monitoring & Evaluation: Monitoring and evaluation Policy & Reform: Policy matrix Methodologies/Approaches: Targeting 2. To improve overall success rate in water sector operations, both design and implementation of ADB-funded projects will have to improve, requiring change in the institutional mind-set and adoption of good practices and appropriate techniques/technology. ADB assistance has pursued some innovative approaches and good practices for improving efficiency (pricing, cost recovery, reducing non-revenue water). However, there is need for continued and significant effort in adopting and operationalizing innovative approaches and good practices given the continuing challenges in implementation including sustainability issues in various sector operations. [Main text, para. 129, Appendix 8] project cycle stage: Design, Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Project Design: Project design Capacity Development: Technology/Technology transfer Sector Related Issues: Water resource management 3. Implementation of the water policy requires a good design?integrated, community driven, institutionally robust, technically sound, and attentive to social and environmental values. Good design makes good financial sense because it minimizes financial risk. Project preparation requirements should be limited to aspects needed to assure due diligence, support sound decisions, and facilitate loan processing. Project preparation budgets should be commensurate with the project preparation requirements. [Main text, para. 131] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 4. Capacity Development, government commitment, community participation, monitoring, and good coordination are requisites of successful projects. Successful projects are characterized by strong stakeholder commitment, good leadership, and a capable executing agency. Despite successful implementation of some ADB projects, current efforts to build leadership and capabilities are not adequate to meet the challenges faced by DMCs. For instance, evaluation noted that institutional capacity among agencies remains weak. In addition, low level of community participation and lack of ownership and commitment among beneficiaries and concerned agencies were factors that continue to affect sustainability of ADB support. [Main text, paras. 124-126,132] project cycle stage: Implementation, Completion Lesson Topics: Monitoring & Evaluation: Monitoring and evaluation Capacity Development: Capacity development Capacity Development: Ownership Sector Related Issues: Water resource management Methodologies/Approaches: Consultation/Participation 5. For developing member countries, there is need for innovative and realistic business models, which recognize that water resources management is intensely political and requires the articulation of prioritized, sequenced, practical, and patient interventions. The interventions should support reformers and pay explicit attention during design and implementation to the political economy of reform. For instance, tariff reform and other conditions related to full cost recovery have most frequently been not complied or partly complied with. The extent to which covenants are met also provides insight into the suitability of design and partial and noncompliance represents a design factor that the client government considered unimplementable. [Main text, paras. 34,82,135,157-161] project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Sector Related Issues: Water resource management 6. To bridge investment gaps, ways need to be found to make investment in the sector more attractive to private business, particularly in rural areas with low densities of consumers. In this sense, the private sector can play a pivotal role in developing water supply and sanitation systems in the Asia Pacific region. However, within ADB, the provision of private sector support has been limited to construction contracts or concessions, with relatively low levels of direct investment (either foreign or local) in the sector. [Main text, para. 137, Appendix 6]. project cycle stage: Implementation Lesson Topics: Sector Related Issues: Private sector Sector Related Issues: Water resource management 7. Government agencies can be highly efficient in delivering services in the water sector. To optimize their role, ADB needs to identify champions in both managerial and political areas. Frequently quoted examples include Manila Water in the Philippines and Phnom Penh in Cambodia. In each case, a strong, principled, and long-serving head has managed to lead the institution from a nonviable state to a highly efficient supplier. [paras. 138,143-145,189] project cycle stage: Implementation, Operation Lesson Topics: | Thematic Evaluation Study (TES) |  | http://www.adb.org/documents/water-policy-and-related-operations
2010 Annual Evaluation Review |  |  | 2010-09-01 | 1. Sustainability needs to be discussed during the formulation of country strategies, in collaboration with other donors. Evaluations of almost all country strategies and sectors point out that projects financial sustainability and in a few cases, institutional sustainability continues to be a major problem. Consequently, evaluations typically recommend project-level remedial measures to mitigate the problem. ADB should encourage governments to carry out sustainability analysis during the formulation of country strategies. Investment sustainability needs to be assessed at the macro level using a medium-term fiscal framework to determine O&amp;M needs and affordability. Sustainability analysis will also help pinpoint institutional reforms that might improve the sustainability of investments, and determine which of those reforms could be incorporated in country strategies. [Main text, paras. 25,76] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring &amp; Evaluation: Monitoring and evaluation Monitoring &amp; Evaluation: Project evaluation Policy &amp; Reform: Reform 2. Midterm project reviews could be transformed into self-evaluative tools. Lack of clarity about outcomes during project implementation and absence of results focus in ADB operations (until recently) constrained the utility of midterm reviews as effective self-evaluation instruments. Carrying out evaluative midterm project reviews would help ADB strengthen project oversight and improve its ability to objectively assess project results. Indepth evaluative midterm reviews can provide real-time feedback on (i) project implementation issues, (ii) the likelihood of the project achieving its expected outputs and outcomes, (iii) the efficiency of resource use, and (iv) project sustainability. This will facilitate midcourse corrective actions to achieve intended project objectives. The introduction of results-oriented country portfolio reviews in June 2010 as well as quality improvements in the design and monitoring frameworks will make it feasible to assess project progress in terms of the likelihood of achieving stated outputs and outcomes. [Main text, paras. 61,78,80] project cycle stage: Implementation Lesson Topics: Crosscutting Issues/Themes: Sustainability Monitoring &amp; Evaluation: Project evaluation Project Management: Project management 3. Real-time evaluation of ongoing projects and programs requires developing member country (DMC) support. Success in this area will depend on (i) ADB improving the quality of design and monitoring frameworks (DMFs), (ii) a smooth transition to the new results-based country portfolio reviews, (iii) DMC government buy-in, (iv) DMC capabilities to track results at the project and sector levels, and (iv) greater harmonization of ADB's results-monitoring efforts with those of DMC governments and other development partners, and alignment of results monitoring with country monitoring systems. [Main text, para. 82] project cycle stage: Implementation Lesson Topics: Monitoring &amp; Evaluation: Monitoring and evaluation Monitoring &amp; Evaluation: Project evaluation Capacity Development: Ownership | Annual Evaluation Review (AER) |  | http://www.adb.org/documents/2010-annual-evaluation-review
South Asia: Validation of the Regional Cooperation Partnership Strategy (2006-2008) Completion Report |  |  | 2010-08-31 | Prospects for and awareness of benefits for all, geopolitical factors, and coordination across and within participating countries and institutions are key factors influencing the success of regional cooperation and integration activities. The influence of complex procedures and changing geopolitical factors on the preparation and implementation of regional projects suggest that the strategy and program should be realistic, and certainly not overambitious. [Main text, para. 34] project cycle stage: Design, Implementation Lesson Topics: 1. A strong central project management unit in the executing agency equipped with adequate technical staff would help to improve project implementation. project cycle stage: Design, Implementation Lesson Topics: Project Management: Project administration Project Management: Project management Project Management: Project supervision | Country Partnership Strategy Final Review |  | http://www.adb.org/documents/south-asia-validation-regional-cooperation-partnership-strategy-2006-2008-completion
Country Assistance Program Evaluation for the Socialist Republic of Viet Nam (2009) |  |  | 2009-08-31 | 1. Development partners can help influence government driven agenda by supporting pilot activities and knowledge sharing that would contribute to discussions on policy alternatives. Throughout Viet Nam's economic development, the government has demonstrated strong ownership and direction of the country's development agenda. Development partners are less likely to influence reforms where there is strong government ownership of the development agenda. Therefore, changes and reforms will not necessarily take place unless all concerned groups and decision makers are convinced of their benefits and political viability. [Executive Summary; Main text, para. 91,142] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Capacity Development: Ownership Policy &amp; Reform: Policy reforms/framework Policy &amp; Reform: Reform 2. Alignment with government plans and priorities facilitated the implementation of ADB's programs, particularly those supporting higher level reform. During the CAPE period, the development agenda was (and still is) strongly driven by the Government. Given the relatively small share of official development assistance in the total investment expenditure, the Government's commitment to its own development plan and planned reforms facilitated the achievement of development outcomes expected from ADB assistance, e.g., reforms in the nonbank financial and power sectors. ADB strategies had a continuing focus on growth as a key driver of poverty reduction, and sustained engagement in high priority sectors central to the Government's growth-driven poverty reduction strategy, including in transport, energy, education, and agriculture and natural resources. [Main text, paras. 140,143] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Alignment Crosscutting Issues/Themes: Harmonization 3. As the legal, policy, and institutional framework is constantly evolving, development partners need to be able to adjust to changing circumstances. ADB demonstrated flexibility and pragmatism in its support of reforms: ADB worked with the Government flexibly in its support for power sector reforms, while support for state-owned enterprise reform adapted to its slow pace. ADB was responsive to the considerable financing requirements of Viet Nam, particularly for large infrastructure projects, with the increased use of ordinary capital resources from 2004 and the application of ADB's innovative financing instrument, the multitranche financing facility. These helped address Viet Nam's large infrastructure requirements and provide greater funding certainty for large infrastructure projects. [Main text, paras 86-88,144] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Alignment Crosscutting Issues/Themes: Harmonization Finance &amp; Financial Aspects: Funding Policy &amp; Reform: Reform 4. Where an experimental approach to reform or changes was employed, demonstrating success facilitated their replication in other locations. As such, the approach can be continued or applied in future interventions as well. For instance, ADB support in urban services and water supply and sanitation, agriculture, and secondary education had demonstrated relevance to the needs and priorities of target beneficiaries. Hence, in the next phase or follow-on project, similar activities were also undertaken. [Main text, para. 145] project cycle stage: Design, Country Partnership Strategy Lesson Topics: 5. Coordination with development partners facilitates complementarities in assistance and greater aid effectiveness. ADB strategies and programs were coordinated with those of development partners. ADB often consulted widely with development partners in preparing and coordinating its programs, strategies, and projects, and was active in aid harmonization initiatives. These facilitated complementarities in sector support such as finance, education, transport, and urban services and water supply and sanitation. The partnerships are also helping to find solutions for common official development assistance implementation issues and greater aid effectiveness, particularly through the Six Banks Harmonization initiative. [Main text, paras. 50,85,94,146] project cycle stage: Design, Country Partnership Strategy Lesson Topics: 6. Improving implementation performance of ADB-supported projects requires, among other factors, building the implementation capacity of the concerned government agencies at subnational levels by taking into account their institutional capacities and procedures in project designs. While disbursement ratios were improving during the period 1999 2003, it retreated with the approval of large infrastructure projects from 2004. Designs of ADB projects in Viet Nam have not fully taken into consideration the complex government procedures and weak implementation capacity of some executing agencies, particularly at subnational levels. These have led to insufficient efforts to build implementation capacity during Project Design, preparation, and implementation. In addition, project designs or implementation arrangements were too complex for the national and provincial institutional capacities and procedures. As a result, the portfolio performance of the Viet Nam program is lagging behind the average for the rest of ADB, even if the Asian Development Fund portfolio were considered separately. [Main text, paras. 66,141,148,159] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Project Design: Project design Capacity Development: Capacity building Capacity Development: Capacity development 7. Considering that ADB technical assistance was less effective in building institutional capacity, new ways in delivering capacity building needs to be considered. Generic capacity building is less likely to be sustainable in the long term due to staff movement. Training should be linked to organizational and institutional needs, and not just the individual, for the institutions to benefit from capacity development programs. Sustained capacity development is required. [Main text, para. 149; Appendix 7] project cycle stage: Design, Implementation, Country Partnership Strategy Lesson Topics: Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Institutional analysis 8. The strategic focus on the Central Region does not seem to have led to any major economies of scale or synergies in implementation, in part, perhaps, because Viet Nam's planning and development systems act at the provincial rather than at a regional level. The Central Region's area of coverage was wide, and implementation requires more resources for day-to-day advice and support. project cycle stage: Design, Country Partnership Strategy Lesson Topics: | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-socialist-republic-viet-nam-2009
2009 Annual Evaluation Review |  |  | 2009-07-01 | 1. Guidance from IED would help strengthen RDs' self-evaluation capacity in preparing project completion reports (PCRs). Key weakness/issues faced in the self-evaluation process include inadequate/lack of (i) understanding of the criteria used under the project/program performance evaluation report (PPER), (ii) analytical skills, (iii) candid assessments and (iv) data to support the PCR ratings (as a result of unclear/incomplete DMF and weak M&amp;E system). Hence, clearer PPER guidelines on the coverage of various evaluation criteria and rating systems (e.g., relevance, effectiveness, efficiency, sustainability, impact, and borrower and ADB performance as well as the need to assess the quality of the project's design and monitoring DMF and M&amp;E system) would enhance RDs' understanding of the PPER criteria as applied to PCRs. A better DMF (with the right output, outcome, impact, and risk indicators as well as adequate baseline data) and M&amp;E system would also provide sufficient data at the time of PCR preparation. [Main text, 65-71, 109, 113(i-iii)] project cycle stage: Design, Completion Lesson Topics: Monitoring &amp; Evaluation: Baseline data Monitoring &amp; Evaluation: Monitoring and evaluation Monitoring &amp; Evaluation: Post-evaluation Project Design: Project design Capacity Development: Capacity development 2. Improving the quality of the validation of project completion report (PVR) requires a better template that is user friendly, less repetitive in some sections, and more complete. Evaluation noted that it took more consultant and IED staff time to do a PVR, and that the PVR template is difficult to format, is repetitive in some sections where relevance is assessed twice in sections C(i) and D(i), and does not reflect a PCR's lack of sufficient data as a criterion in judging its quality. [Main text, paras. 109, 113(iv)] project cycle stage: Completion Lesson Topics: 3. Strengthening the regional departments self-evaluation capacity in preparing technical assistance completion reports (TCRs) requires guidance from the Independent Evaluation Department on conducting objective evaluations supported by adequate data, being able to distinguish between technical assistance (TA) outputs and outcomes, and drawing useful lessons and recommendations based on the TA findings. In relation to these, TCRs would be more useful if a more detailed format is adopted where (i) TA outputs and outcomes are classified under different sections, (ii) assessment of and defining sustainability prospects are included; and (iii) relevant lessons and recommendations that are directly related to the TA findings are identified. These would be able to address the key concerns cited in this evaluation report, which include among, others, gaps in self and independent evaluation ratings, poor quality of lessons drawn, and inadequate analysis which poses difficulty in assessing quality of TCRs . [Main text 110, 114(i-ii)] project cycle stage: Completion Lesson Topics: Monitoring &amp; Evaluation: Post-evaluation Capacity Development: Capacity development 4. Guidance from the Independent Evaluation Department on improving country partnership strategy completion report (CPSCR) format and its timing of preparation would be useful in strengthening self evaluation capacity of regional departments. A more detailed format may include a bottom-up assessment of outcomes by sector, linked to CPS outcomes or pillars, and assessment of assistance approved before and implemented during the current CPS period. These would address the constraints posed by the format on depth of analyses. [Main text, paras. 111, 115 (i-ii)] project cycle stage: Completion, Country Partnership Strategy Lesson Topics: Monitoring &amp; Evaluation: Post-evaluation Capacity Development: Capacity development 5. Guidance from Regional Departments (RDs) [e.g., format to be used by developing member countries (DMCs) in doing project completion reports (PCRs), and how to follow the evaluation criteria required by the format] would help strengthen DMCs' self-evaluation capacity in preparing PCRs. The use of too broad format or no specific format in DMC's PCRs has led to too broad assessments or inadequate information for the preparation of RD's self evaluation. Increased attention from RD management would prompt RD staff to keep track of DMC's PCR . [Main text, para. 91-94, 112, 116 (i-iii)] project cycle stage: Completion Lesson Topics: Monitoring &amp; Evaluation: Post-evaluation Capacity Development: Capacity development | Annual Evaluation Review (AER) |  | http://www.adb.org/documents/2009-annual-evaluation-review
Annual Report on 2008 Portfolio Performance |  |  | 2009-07-01 | 1. Increasing levels of loan cancellations and cost overruns suggest that ADB needs to strengthen the preparation of project cost estimates and financing plans to ensure more accurate costing. The latter is likely to ensure more optimal utilization of the loan proceeds and result in fewer cancellations and also fewer projects with cost overrun issues. A more rigorous internal due diligence and review of project cost estimates and financing plans must be pursued. [Main text, para. 30-35, 40, 51] project cycle stage: Feasibility, Appraisal Lesson Topics: Finance &amp; Financial Aspects: Financial management Project Design: Appraisal 2. More than the procedural aspects, there is a need to evaluate the substantive aspects of TA knowledge products to provide a better defined and nuanced feedback for Management to monitor TA operations more effectively. The self-evaluation mechanism of technical assistance (TAs) and their knowledge products is rather general and does not do justice to either the role of TA operations or their variety. This seems to be the chronic deficiency of the TAs. Self-evaluation mechanism needs to be sharpened and more focused. [Main text, paras. 70, 72] project cycle stage: Implementation, Completion Lesson Topics: Modality: Technical Assistance Monitoring &amp; Evaluation: Project evaluation 3. The efforts of tying grant funds with economic variables like debt sustainability imply that allocation of grants may have to be calibrated periodically. Assessing and evaluating the impact of grant funds needs to be fleshed out in terms of its methodology as well as scope. project cycle stage: Completion Operation Lesson Topics: 4. In view of the growing emphasis on nonsovereign operations in ADB s Strategy 2020, the standard of evaluation in nonsovereign operations needs to be more thorough and transparent so that the lessons learned are broadcast and replicated swiftly. The long-term strategic framework has identified nonsovereign operations, i.e., private sector development and private sector operations, as the driver of change in the Asia-Pacific region and endorses infrastructure and the financial sector as the core sector of operations for nonsovereign operations. Over time, nonsovereign operations have been experiencing a healthy growth given the increase in the number of projects and total exposure. [Main text, paras. 82-94] project cycle stage: Implementation, Completion Lesson Topics: Monitoring &amp; Evaluation: Post-evaluation Monitoring &amp; Evaluation: Project evaluation | Annual Report on Portfolio Performance |  | http://www.adb.org/documents/annual-report-2008-portfolio-performance
2007 Annual Report on Acting on Recommendations |  |  | 2008-09-01 | 1. To monitor progress toward improved development effectiveness, it is crucial to track actions taken (quantitatively and qualitatively) on recommendations. The report, however, points out that even with the introduction of the Evaluation Information System (EVIS), ADB has no sufficiently functioning, integrated operating system for doing so. EVIS combines a database of lessons with another aimed at tracking (progress on) actions on recommendations, but Management and departments and offices concerned in ADB have not started using it. [Main text, para. 11] project cycle stage: Completion Lesson Topics: Crosscutting Issues/Themes: Managing for Development Results Monitoring &amp; Evaluation: Impact evaluation | Annual Evaluation Review (AER) |  | http://www.adb.org/documents/2007-annual-report-acting-recommendations
2008 Annual Evaluation Review |  |  | 2008-09-01 | 1. Long-term engagement is required to see the development outcomes of ADB's interventions. CAPEs find that success, as measured in terms of contribution to development outcomes, has been greatest when ADB has maintained a long-term involvement in a sector and has combined programs for institutional capacity building, policy reform, and investment support. CAPEs report that country strategies with a clear long-term commitment to progress in a limited number of sectors and thematic areas have had more coherence, realism, and a greater prospect for delivering development results. This also implies the need to have an exit strategy or a reexamination of operations in poorly performing sectors. [Main text, paras. 63, 127] project cycle stage: Country Partnership Strategy Lesson Topics: Capacity Development: Ownership Methodologies/Approaches: Holistic approach 10. ADB support for good governance, notably at the sector level, has had some success; but governance assistance needs more coherence, strategic direction, and supportive policy dialogue, particularly with respect to corruption risks at the sector and national levels. Progress is difficult to assess in governance programs because of a dearth of results indicators and the fact that many factors besides ADB assistance contribute to governance outcomes. In general, the CAPEs report that ADB support for good governance has been diffused and lacks strategic direction, particularly in the areas of rule-of-law and public policy reform. CAPEs also find that governance, including the need to control corruption, should be explicitly addressed in CPSs, and not just as a crosscutting theme. Moreover, the understanding of corruption and the risks that it has for ADB's operations remains superficial in CPSs. [Main text, paras. 87-89] project cycle stage: Country Partnership Strategy Lesson Topics: 11. Country strategies and programs should sufficiently incorporate the findings and recommendations of the country environmental assessment and should strategically position ADB to assist in environmental areas where it has a long-term sector commitment. CAPEs have found that environmental issues are highly relevant in most DMCs, and have become more so with high population densities and growing pressure on fragile resource bases. There are also several cross-border issues relating to environment, such as dust and sandstorms, water supply and water quality, air pollution, and a strong nexus of poverty environment issues. A number of CAPEs (Cambodia, Lao PDR, and PRC) find that ADB's awareness of regional sensitivities makes it well placed to maintain regional dialogue on sensitive trans-border resource management issues. [Main text, paras. 90-93] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Regional cooperation 12. More synergy is needed to harness potential benefits of ADB's public sector and private sector operations. CAPEs highlight a number of common themes related to support for private sector development: (i) the public and private sector sides of ADB did not work together effectively to develop niches and create synergies; (ii) the country programs did not have a clear strategy that positioned ADB to have a strategic impact in this area; (iii) while the regional departments undertook some activities to improve the enabling environment, these efforts were scattered across sectors, not systematic, and generally unrelated to the Private Sector Operations Department; and (iv) ADB's success in improving the business climate by supporting policy reforms and dialogue was mixed. [Executive summary; Main text, para. 94] project cycle stage: Country Partnership Strategy Lesson Topics: 13. Country and subregional partnership strategies and programs need more integration to boost returns from both country and regional support. The coverage of regional cooperation in the CAPEs reviewed is limited, given that (i) the first Regional Cooperation Strategy and Program was prepared in 2004 - viz., for the Greater Mekong Subregion; and (ii) the regional cooperation integration strategy was approved only in 2006. The latest CAPEs for Mongolia, Philippines, and PRC mention that the CPSs acknowledge the need to work in the area of regional cooperation but are not explicit in formulating a strategy that would coordinate the CPS with the subregional strategy. This is an area of focus for new CPSs under formulation since the regional cooperation integration strategy was approved in 2006. [Main text, para. 60] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Regional cooperation Crosscutting Issues/Themes: Donor coordination/harmonization 2. Focus and selectivity are essential to attain a critical mass and achieve sustainable results. The 10 most recent CAPEs are unanimous in stressing the need for greater sector selectivity. The CAPEs find that ADB resources often tend to be spread thinly across sectors, subsectors, and themes, often constituting one-off interventions that do not build synergies with other activities. Efforts to achieve multiple strategic goals and themes results in fragmented interventions, which ultimately harm performance at the project, sector, and program level. [Main text, paras. 64, 127] project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Sustainability Methodologies/Approaches: Targeting 3. ADB can be more effective in client responsiveness and service delivery if it delegates more responsibility and provides commensurate resources to its resident missions. The CAPEs note the tendency of a centralized structure to lead to longer response times (even for such routine services as procurement and disbursements); inadequate project supervision and troubleshooting due to distance, language, and cultural constraints; and reduced ability to stay attuned to market developments. Conversely, CAPEs have found that decentralization can dramatically improve the effectiveness of client services by shortening response times for core operational services (e.g., procurement and disbursements); expediting preparation of priority projects; providing better project supervision; and improving the relevance of policy advice. In addition, decentralization (i) increases the institution's visibility among important country constituents; (ii) promotes stronger links with other development partners; and (iii) sharpens understanding of the local scene, making it easier to fine-tune operational activities and undertake policy dialogue. [Main text, paras. 68, 127] project cycle stage: Country Partnership Strategy Lesson Topics: Project Management: Project supervision Country Context: Decentralization Other: Resident Mission 4. A general lesson from the CAPE surveys on client responsiveness is the need to streamline ADB policies, procedures, and practices to provide more efficient and responsive services. Common concerns reported in several CAPEs had to do with long time frames required for project preparation, insufficient supervision of the ongoing portfolio from headquarters staff, supply-driven TA, differences between ADB and national requirements for land acquisition and environmental impact assessment, and an overreliance on consultants for project preparation and policy advice. [Main text, paras. 69, 75, 93, 127] project cycle stage: Design, Feasibility, Appraisal, Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Alignment Crosscutting Issues/Themes: Environmental assessment Crosscutting Issues/Themes: Harmonization Crosscutting Issues/Themes: Resettlement Project Design: Project design Project Management: Consultants Project Management: Project supervision 5. Country ownership must be nurtured, risks carefully assessed, and the readiness of implementing agencies secured to ensure that the assistance program can be implemented effectively. Building strategic partnerships with other development agencies and with civil society can contribute to assistance systems conducive to enhancing country ownership, i.e., a more coherent assistance effort, development of national systems, and reduced transaction costs to the developing member countries. Country Assistance Performance Evaluations (CAPEs) have found that a failure of project designs to adequately assess risks early on and to recognize and address institutional weaknesses in implementing agencies, including a realistic assessment of recurrent financing capacity, leads to weak project performance and difficulty in sustaining project benefits. CAPEs report that weaknesses in portfolio performance are often attributed to a failure to take ownership, risks, and institutional readiness into account at the time of project design. [Main text, paras. 70-72, 127] project cycle stage: Implementation, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Harmonization Crosscutting Issues/Themes: Sustainability Project Management: Executing/Implementing agencies Project Management: Risks/Risk management Capacity Development: Capacity development Capacity Development: Ownership 6. Efforts to move to results-based Country Partnership Strategies (CPSs) are at the early stages and will require changes in institutional culture and incentives in both ADB and its developing member countries. The degree to which development impact is tracked has been identified in Country Assistance Performance Evaluations (CAPEs) as still weak, although more attention has been accorded to defining results and assisting governments in tracking results in recent years with the piloting of results-based CPSs. CAPEs have also noted that the lack of monitorable indicators and regular tracking of outcome indicators has made it difficult to evaluate past strategies. [Main text, paras. 73, 127] project cycle stage: Country Partnership Strategy Lesson Topics: Monitoring &amp; Evaluation: Impact evaluation Monitoring &amp; Evaluation: Indicators Monitoring &amp; Evaluation: Monitoring and evaluation 7. For capacity development to succeed, there are necessary conditions for both the government and ADB. Successful operations in capacity development were observed to have strong government ownership, long-term commitment, appropriate mix of ADB assistance modalities, supportive policy environment, better alignment of technical assistance (TA) resources to the country strategy, improved TA management, and enhancement of staff incentives for economic and sector work. [Executive summary; Main text, paras. 60, 74] project cycle stage: Country Partnership Strategy Lesson Topics: 8. Creating synergies between ADB's public and private sector operations can mobilize private sector resources to support socioeconomic development and poverty reduction in the Asia and Pacific region. ADB has yet to realize this potential through jointly planned country assistance operations as well as enhancing the enabling environment for the private sector. [Main text, paras. 52, 60, 77, 94, 125-126] project cycle stage: Country Partnership Strategy Lesson Topics: Sector Related Issues: Private sector Sector Related Issues: Public-private partnership Methodologies/Approaches: Sectoral approach 9. A key factor influencing long-term success in the social sectors has been the adequacy of recurrent budgetary support. Evaluations noted that support to education and health has been constrained by insufficient operation and maintenance funds and some project designs lacked plans for sustaining activities even after project completion. [Main text, para. 86] project cycle stage: Country Partnership Strategy Lesson Topics: Sector Related Issues: Education Sector Related Issues: Health and sanitation management | Annual Evaluation Review (AER) |  | http://www.adb.org/documents/2008-annual-evaluation-review
Annual Report on 2007 Portfolio Performance |  |  | 2008-09-01 | 1. Delays in Project Implementation. A comparison of expected and actual implementation periods suggests that delays in project implementation are the rule, rather than exception, for ADB s sovereign lending operations. Implementation periods planned and actual have hardly changed over time, suggesting that delays are predictable, which in turn should enable ADB and its PPR system to address the delay problem better. Underestimated implementation periods distort the results of economic analysis. In the current progress reporting system, underestimated implementation periods also trigger negative performance ratings, which then put undue pressure on the parties concerned with implementation.Based on an OED study, the range of causes of implementation delays is broad and not all can be foreseen and thereby prevented from occurring. However, delays were found to be sensitive to both country- and sector-specific parameters. Country parameters are perhaps more important. Project implementation is embedded in the governance regimes and the natural conditions of a country, and these may favor expeditious project implementation to varying degrees. Beyond making provisions for certain countries and sectors with proven track records, it may be expedient to factor in delays of one or another kind and extend the project duration; this could be seen as adding a time contingency to the schedule. The PPR may need to use standardized indicators to capture factors leading to delays in a better way. Many factors are already standardized one way or another, but some are not; these can be added when the PPR system is updated. project cycle stage: Implementation Lesson Topics: 2. Further Improvement to the PPR System. (a) Project Implementation Status Monitoring: Some improvements could be made with a renewed focus in training on PPR reporting of the project implementation status and more serious quality control. However, more objective establishment of the exact or even average progress of a project requires including the following in the PPR: (i) the original project work plan with milestones, and (ii) an annually updated work plan. The first is needed to keep track of original targets and would help determine the overall health of the project portfolio. The second would be an instrument for more detailed project supervision and the determination of the at risk status of the project. Weights should be assigned to the main activities of the project, so that the system can calculate progress objectively. Preferably, the new PPR should be web-based to allow executing agencies to be directly involved in work plan monitoring.(b) Covenant Monitoring: OED views regular checks on compliance with covenants through the PPR as an important way of improving due diligence in project management as well monitoring project-related governance in sectors, countries, and modalities. Relevant loan agreement schedules should be automatically downloaded into the PPR system via a smart template. A selection of ADB s loan or grant regulations could be similarly downloaded, or even be hard coded in it (i.e. be made part of the PPR form itself).(c) At Risk and Potential Problem Monitoring: This report recommends that a number of indicators in the PPR, currently often misunderstood or leaving opportunities for interpretation, are clarified in the Project Administration Instructions and current software module. A number of these ambiguous indicators should be refined and a few useful indicators should be added. The concept of the at risk status of individual projects should be maintained for the purposes of Project Management, so that weak projects are identified and resources directed to them through specific project action plans. project cycle stage: Implementation Lesson Topics: Loan Agreement: Covenants Monitoring &amp; Evaluation: Indicators Monitoring &amp; Evaluation: Reporting 3. The ratings for the design and monitoring frameworks (DMFs) for 2006-2007 operations are lower on average than those reported for DMFs of 2004 and 2005. The proportion of project and program DMFs approved in 2006 that OED rated satisfactory or better was 44%, and the share of those approved in 2007 was 58%. OED found problems in particular with the formulation of means of verification in DMFs, and the assumptions and risks. Furthermore, OED noted some confusion with respect to the levels of impacts and outcomes pursued in DMFs. Impacts and outcomes are often set at a level more suitable for country strategies and sector road maps. OED observed that the best DMFs were in the transport sector, water supply and sanitation sector, and education sector, where projects often follow a more standardized organization and had well-established rationales and more standard indicators.OED considers that much still can be improved in the completion of DMFs. Continued training of ADB s project processing staff is important. Even more important is quality improvement of DMFs within operations departments. While DMF quality in 2007 shows improvement over 2006, the DMF guidelines should be reviewed further (i) after changes in reporting have been made as a result of the P3M exercise, (ii) to align them with the recently introduced ADB-wide results framework and country level results framework; (iii) to make the DMF contribute to results monitoring during both project implementation and project operation, and (iv) to inform ADB s new country development effectiveness briefs and annual development effectiveness report. project cycle stage: Design Lesson Topics: 4. The attention for development results has increased but currently there is no regular and comprehensive monitoring of outputs and outcomes of ADB supported interventions after their completion. This report recommends that ADB consider promoting the monitoring of results of individual interventions for a period of 3 5 years after their completion. The findings could feed into management information systems and ADB s reporting systems. The availability of additional resources will be essential. Also in view of ADB s budget constraints, OED recommends that the approach is pilot tested first through a regional TA in selected DMCs such as those where ADB has a results-based country partnership strategy, large borrowers, and where ADB has been providing ADTA to help build results monitoring capacities. project cycle stage: Completion Lesson Topics: Monitoring &amp; Evaluation: Post-evaluation Monitoring &amp; Evaluation: Project evaluation | Annual Report on Portfolio Performance |  | http://www.adb.org/documents/annual-report-2007-portfolio-performance
Technical Assistance in Support of the Pacific Financial Technical Assistance Centre in the Pacific Island Countries |  | Finance | 2006-05-31 | 1. Clearly defined performance criteria are needed to be able to undertake a rigorous and objective evaluation. Evaluation has noted the absence of specific, qualified, and time-bound outcome measures for Pacific Financial Technical Assistance Centre (PFTAC). The challenge of defining outcomes beforehand in a demand-based technical assistance (TA) delivery system, where outcomes are shared with many funding agencies, has been highlighted. However, without such measures, a rigorous evaluation of performance is impossible. Further, PFTAC is deprived of useful management information for ongoing self-assessment, and to guide to the future direction of the project. IMF is proposing the preparation of a standard set of outcome measures for its regional TA centers. With these standards in place, and with the proposal in the 2005?2008 project document to include the outcomes of specific TA in the six-monthly reports, this situation should improve. [Main text, paras. 38, 61] project cycle stage: Design, Completion Lesson Topics: Monitoring & Evaluation: Impact evaluation Monitoring & Evaluation: Monitoring and evaluation Monitoring & Evaluation: Reporting 2. The regional approach and partnership arrangements that were incorporated into the Pacific Financial Technical Assistance Centre (PFTAC) 'experiment' have proved to be a successful model in the delivery of technical assistance in the region. Through support provided to PFTAC, ADB has leveraged greater results than would have been achieved through piecemeal allocation of the funds to activities in the financial and economic area. [Main text, paras. 7, 45, 62] project cycle stage: Design Lesson Topics: | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/technical-assistance-support-pacific-financial-technical-assistance-centre-pacific-island
Advisory Technical Assistance for Power Sector Institutional Strengthening in the Socialist Republic of Viet Nam |  | Energy | 2004-10-31 | ADB needs to find ways to support the management of counterpart organizations throughout technical assistance (TA) implementation. As a first step, ADB might consider asking EAs to undertake their own formal, documented evaluation of all TAs within 1 or 2 years of completion. The evaluation would assess the relevance of the TAs, their impact on the organization, and the extent to which recommendations were accepted and implemented. The aim of this exercise would be to increase the involvement of the recipient organization, and to help ensure that the design of subsequent ADB TA programs improves their chance of achieving the desired outcomes and impacts. project cycle stage: Design, Implementation, Operation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Post-evaluation Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation The executing agencies (EAs) lacked ownership and proactive involvement in the technical assistance projects (TAs). The TA outputs were regarded more as a source of reference for the future than an agreed course of action. During TA implementation, inputs from the EAs were often not substantial and substantive. After completion, the TA reports were not translated into the local language and disseminated throughout the organization. Other stakeholders and government agencies concerned were generally unaware of these TAs. When one of the EAs did not provide the required data after repeated attempts, more efficacious use of TA funds might have been considered, including discontinuing the TA-financed study, if necessary. project cycle stage: Implementation, Completion Operation Lesson Topics: Modality: Technical Assistance Monitoring & Evaluation: Data collection Project Management: Executing/Implementing agencies Capacity Development: Ownership Policy & Reform: Information dissemination/Public awareness The technical assistance (TAs) might have been better received had they focused on what was achievable, even if this was not necessarily optimal. When key recommendations are dismissed as irrelevant because they cannot be implemented readily, more useful recommendations tend to get overlooked as well. Consequently, the TA report loses its credibility. To avoid such problems, a three-way dialogue among the government, ADB, and the TA consultant is desirable throughout a TA. This allows misunderstandings to be resolved early, so the TA consultant can be redirected as necessary. project cycle stage: Design, Feasibility, Implementation, Completion Lesson Topics: Modality: Technical Assistance Methodologies/Approaches: Consultation/Participation | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/advisory-technical-assistance-power-sector-institutional-strengthening-socialist-republic
Selected Advisory Technical Assistance for Institutional Development and Capacity Building in the Water Supply and Sanitation Sector |  | Water and Other Urban Infrastructure and Services | 2003-02-28 | Coordination and timing between an advisory technical assistance (ADTA) and the associated project is also important. ADTAs should be implemented only when the new water supply infrastructure provided by the project is in place. If an ADTA is related to technical matters, it is more appropriate for it to be implemented before or at the beginning of the project so that project implementation may receive the greatest benefit from the ADTA. project cycle stage: Design, Feasibility, Implementation Lesson Topics: Finance & Financial Aspects: Financial management Modality: Technical Assistance For transition economies, coordination and timing are important for the effectiveness of advisory technical assistance (ADTAs). When an ADTA has several components that are interrelated, consultants' inputs should be arranged so that the outputs can be properly coordinated. project cycle stage: Design, Implementation Lesson Topics: The community health and hygiene programs, associated with water supply and sanitation projects, will be more effective when they can be implemented by a professional organization, which is already operating the same or similar types of activities. project cycle stage: Design, Operation Lesson Topics: Crosscutting Issues/Themes: Sustainability Modality: Technical Assistance When an institution is the recipient of a series of advisory technical assistance (ADTAs) over time, the effects can be cumulative and positive, even when the individual ADTAs may not have been, individually, very successful. project cycle stage: Design Lesson Topics: Modality: Cluster operations Modality: Technical Assistance | Technical Assistance Performance Evaluation (TPER) | Partly/less than successful | http://www.adb.org/documents/selected-advisory-technical-assistance-institutional-development-and-capacity-building
Country Assistance Program Evaluation for the Socialist Republic of Viet Nam (1999) |  |  | 1999-12-31 | Interagency and provincial-central level coordination in a country that values consensus building represents a serious constraint to expeditious project implementation. In such cases, projects that minimize across-boundary coordination should be preferred whenever possible. project cycle stage: Design, Implementation Lesson Topics: Project Design: Project design Project Management: Executing/Implementing agencies Methodologies/Approaches: Consultation/Participation It is unrealistic to expect that capacity building can quickly enhance the absorptive capacity of a transition economy. There is as much need to tailor ADB's business processes and country strategies to the country's administrative environment as there is for TAs to help the country to strengthen its capacity. project cycle stage: Design, Country Partnership Strategy Lesson Topics: Modality: Technical Assistance Project Management: Project administration Capacity Development: Capacity building Policy &amp; Reform: Transition economies The COS and CAP documents need to be designed to provide relevant operational guidance, particularly for project identification and processing. The strategy and program proposed should be focused and selective and should provide the basis for decision making including exclusion of specific areas of intervention. Priority areas need to be identified. project cycle stage: Concept Feasibility Lesson Topics: Project Design: Project design Country Context: Prioritization Policy &amp; Reform: Policy reforms/framework The failure to instill recipient ownership of lending and nonlending aid agency interventions is detrimental to their successful outcomes. Such a failure could arise from a lack of political or ideological commitment or conviction. Such issues are quite separate from fundamental problems of coordination and absorptive capacity and need to be resolved quite differently. project cycle stage: Feasibility Lesson Topics: Modality: Lending modality Modality: Technical Assistance Project Design: Project design Project Management: Executing/Implementing agencies Capacity Development: Ownership Methodologies/Approaches: Consultation/Participation The use of TA for capacity building and institutional strengthening can greatly assist the country in its reform process, but the TA operations need to have long-term strategic focus in terms of the institutions to be assisted, the synergy that can be tapped, and the timing and sequencing of the TAs to be implemented. project cycle stage: Appraisal, Country Partnership Strategy Lesson Topics: Modality: Cluster operations Modality: Technical Assistance Capacity Development: Capacity building Capacity Development: Capacity development Capacity Development: Institutional analysis Policy &amp; Reform: Reform | Country Assistance Performance Evaluation (CAPE) |  | http://www.adb.org/documents/country-assistance-program-evaluation-socialist-republic-viet-nam-1999
Capacity Building in the Financial Sector in the Socialist Republic of Viet Nam |  | Finance, Multisector | 1998-12-31 | In a transition economy where acquired techniques and skills applicable to a market-based economy may not be utilized immediately, greater concentration should be placed on training of trainers. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Transition economies In training programs, where the constraint of language and frequent change of interpreters poses a real hurdle, training courses need to be longer and interpreters with specific technical knowledge should be engaged. project cycle stage: Design Lesson Topics: Modality: Technical Assistance Capacity Development: Capacity development Policy & Reform: Transition economies | Technical Assistance Performance Evaluation (TPER) | Unsuccessful | http://www.adb.org/documents/capacity-building-financial-sector-socialist-republic-viet-nam
Development of Small-Scale Rural Credit Project in the Socialist Republic of Viet Nam |  |  | 1996-09-30 | The language difficulties and the cumbersome procurement procedures were underestimated. Language difficulties may be reduced bv having a longer lead time, but ensuring that consultants have the proper language facility would be more helpful, especially when technical terms are involved. Advance action may alleviate cumbersome procurement procedures but would not substitute for a thorough investigation of the procedures during TA formulation for possible alternative solutions. For more effective implementation of a TA involving training in a transition economy, the general background of the trainees should first be evaluated, and remedial action incorporated in the training to increase absorption of training benefits. project cycle stage: Feasibility, Implementation Lesson Topics: Modality: Technical Assistance Project Management: Consultants Project Management: Procurement Capacity Development: Capacity building Policy & Reform: Transition economies | Technical Assistance Performance Evaluation (TPER) | Successful/Generally successful | http://www.adb.org/documents/development-small-scale-rural-credit-project-socialist-republic-viet-nam