## Azerbaijan
AZERBAIJAN
REPORT NAME | SECTORS | DATE | LESSONS | REPORT TYPE | REPORT RATING | LINK
Power Transmission Enhancement Project: Completion Report | Energy | 2015-09-21 | The project demonstrated that Azerenergy is a capable implementing agency for power projects and that there is private sector capacity to undertake major construction projects related to augmentation and rehabilitation of power transmission and distribution networks. With proper planning, effective project monitoring mechanisms, and motivated and well-trained personnel, such projects can be successfully and expeditiously implemented. The government, with the assistance of ADB, should continue to upgrade and expand the transmission and distribution networks to ensure system losses are minimized, electricity supplies are reliable, and the growing demand for electricity in the country is met. project cycle stage: Design, Implementation There was some confusion in Azerenergy about the correct approach to use in calculating the debt - equity ratio and the DSCR (debt service coverage ratio). Financial ratios should be defined in loan covenants, particularly if they form part of the financial covenants of the loan. Moreover, ADB should more closely review these covenants during review missions to evaluate - and if needed initiate measures to ensure - compliance. project cycle stage: Design, Feasibility To enhance its operational and financial performance, Azerenergy is (i) streamlining its core business and transferring distribution networks assets and liabilities to Azerishiq, which will improve its financial performance and reduce administrative expenses; (ii) expanding power export to Georgia, Turkey and Russia; (iii) introducing enterprise resource planning, and enhancing internal audit and control to improve budgeting and planning functions; and (iv) accessing capital markets and diversifying financing channels (Azerenergy successfully obtained a corporate credit rating of BBB-/A-3 in February 2013). project cycle stage: Operation | Project/Program Completion Reports (PCR) | Successful/Generally successful | https://evaluation-lessons.org/report/power-transmission-enhancement-project-completion-report-2/
Road Network Development Program (Project 2) | Transport | 2013-02-09 | 1. More robust due diligence is needed during project design and formulation to enable the closest possible cost estimates and to set aside enough resources to cover contingencies. This can save considerable time. The scope of the ADB-financed East-West Highway Improvement Project, approved in 2005, included two sections of the east-west highway: Gazakh-Georgian border section and Ganja bypass road, forming part of Yevlakh-Ganja section. However, during implementation, the project experienced unprecedentedly sharp increases in prices for fuel, utilities, and major road construction materials, which significant increased the cost of construction. Consequently, the scope of the East-West Highway Improvement Project was revised to exclude the Ganja bypass road. This delayed improving the Ganja bypass road, which was a muchneeded alternative to the existing highway. At cost estimation, prices of materials should be examined carefully and in relation to neighboring markets and the unit costs of similar items in previously awarded contracts. Contingencies should also consider the exceptional cost increases during implementation. project cycle stage: Lesson Topics: 2. Realistic estimation of project and contract duration is important. Inclement weather seriously hampered physical progress in project implementation, especially from August 2011 to February 2012. The contractor had difficulty coping with it, which significantly delayed the completion of works. A more realistic timeframe for implementing a road project should be formulated allowing for unpredictable local weather conditions and other contingencies so that resources can be deployed effectively and efficiently. project cycle stage: Lesson Topics: 3. The project constructed a two-lane road. Subsequent to the start of the project, the government decided to widen the road to four lanes by constructing another two-lane road alongside the project road. The widening works are scheduled for completion by December 2013. The ADB-financed two-lane road was completed in December 2012. At appraisal, project design needs to be properly formulated through much broader consultation with line ministries and other stakeholders, keeping in view future requirements and government plans so that administrative and operational issues are not encountered during the implementation and the facility can be made ready for the users in a timely way. project cycle stage: Lesson Topics: 4. The project experienced start-up delays, because the contractor mobilized slowly and was unable to tie up with suitable local subcontractors. The contractor was also unfamiliar with conditions in the country at the start, which caused implementation delays. The subcontractors contributed significantly, and without them it would have been difficult for the contractor to successfully complete the project. For future projects, the criteria for qualifying the contractor - and the disclosure of information on subcontractors and the contractual provisions related to contractor performance, such as mobilization, staffing, and the deployment of equipment and funds - need to be strengthened to minimize the risk of poor contractor performance. Moreover, the previous performance of the contractor in the project country should be taken into account when evaluating bids. The Ministry of Transport and Azer Road Service need to provide bidders with adequate local information at pre-bidding meetings, and to publish on its website information on the cost of locally available inputs such as materials, equipment, and labor, to enable bidders to submit sensible bids and implement the project successfully. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Successful/Generally successful | https://evaluation-lessons.org/report/road-network-development-program-project-2/
Azerbaijan: Validation of the Final Review of Country Operations, 2000 - 2011 |  | 2012-11-06 | 1. A mechanism is required to secure government commitment to an ADB-supported forward program that is flexible in the context of shifting government priorities. ADB needs to adopt a flexible approach to its country program, in case the multi-tranche financing faciltiy (MFF) tranches do not materialize as envisaged. MFFs are generally approved for periods of up to 10 years, whereas country partnership strategies are approved for periods of 4 5 years. This flexibility could be either linked to updating the country operations business plan or defining a low-lending case or a base case scenario with results of support defined at entry for priority sectors. The evaluation period witnessed a shift in government's approach to economic growth from an early expeditious development of its oil and gas resources, to a more broad-based approach looking to long-term growth to reduce poverty and raise living standards. ADB initiated the shift in its strategic focus from direct support to internally displaced persons, agriculture and rural development, water supply and sanitation, and rural roads until 2006, to the transport, water supply and sanitation, and energy sectors starting from 2007. While ADB failed to secure commitment from the government for its planned full country and strategy program in 2006, it slowly and in an incremental manner developed its program in roads, water supply, and power. project cycle stage: Country Partnership Strategy Lesson Topics: Finance & Financial Aspects: Financing Country Context: Prioritization 2. A shift from investment program financing to provision of more knowledge services and technology facilitation is needed in upper middle-income country contexts. With the majority of the ADB-supported projects still ongoing, chances are high that most would be carried forward into the next country partnership strategy period. However, like Kazakhstan, another upper middle income country in the region, ADB needs to look beyond provision of investment program financing to knowledge services that add value. In the roads multitranche financing facility (MFF), efforts are ongoing to develop a study on a legal and regulatory framework and operational procedures for toll roads. Similarly, in the Urban Services MFF, a twinning arrangement is being finalized between Azersu, the executing agency and an international water utility for sustained institutional and organizational capacity development. ADB needs to build on these efforts to develop systematic policy advisory support and targeted capacity development in its sectors of engagement. Such an approach would enable continued ADB engagement in targeted sectors through a lowlending scenario, even if there were changes to the government's policy on external borrowing. project cycle stage: Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Finance & Financial Aspects: Financing 3. A focus on non-physical components, specifically Capacity Development, is essential to maximize the development effectiveness of investments in physical components. The capacity of the executing and implementing agencies has varied across ADB sectors of engagement, and capacity development efforts in the past have been part of ADB investments. Much of the previous focus has been on developing organizational capacity through, for example, preparation of manuals and training materials. In-country consultations highlighted that non-physical components, and especially Capacity Development, need to be given more attention through the forthcoming country partneship strategy period. The World Bank experience has included the use of funding pools earmarked for preparation and implementation of projects in priority sectors, in addition to individual capacity development components within sector investments. While, the former approach raises sustainability issues after closure of funding pool, the latter approach raises difficulties in reporting improvements at institutional, organizational, and individual levels. Predefined actionable indicators, which cover policy, regulatory issues (upstream), corporatization issues of service providers in the sector (mid-stream), and service delivery (downstream) are needed. project cycle stage: Design, Country Partnership Strategy Lesson Topics: | Country Partnership Strategy Final Review |  | https://evaluation-lessons.org/report/third-health-sector-development-project-validation-of-completion-report/
Urban Water Supply and Sanitation Project | Water and other urban infrastructure and services | 2011-12-01 | Understanding the sector environment in new member countries is important. When engaging in a new sector or country, understanding the key sector participants and their agendas, as well as developments in the sector is important. This will improve the project design and increase the likelihood that the project will have strong government support. Use phased reform programs. Radical reform programs, especially if they carry political risks, are likely to result in government resistance, unless the government strongly supports the concept. A phased long-term reform program is more likely to gain government support, especially if each stage is aligned with government objectives. Use conservative cost estimates and ensure sufficient funding. The funding allocation should be sufficient to cover project costs; if it is not, the project scope should be reduced or the funding allocation increased with no delay during implementation. Ensure the government understands the proposed project. Ensure that government agencies fully review and understand proposed projects. Reconfirmation with all relevant agencies is critical. | Project/Program Completion Reports (PCR) | Partly/less than successful | https://evaluation-lessons.org/report/urban-water-supply-and-sanitation-project-2/
East-West Highway Improvement Project | Transport | 2011-11-01 | The project was the first of the ADB-assisted road projects in Azerbaijan. Many lessons were learned during project preparation and implementation. The main lessons are summarized below: Azerbaijan experienced sharp increases in the prices of fuel, utilities, and major road construction materials between project appraisal and detailed design. These led to significant changes in the project scope and financing plan. In future road projects, greater due-diligence needs to be undertaken during project design and formulation, which includes carrying out adequate cost estimations, setting aside enough resources to cover contingencies, and shortening the interval between appraisal and implementation. The contractor for the Gazakh-Georgian border section was perhaps not familiar with the country's situation at the start, and this caused mobilization delays and difficulty in finding suitable local subcontractors. In future road projects, the Ministry of Transport (MOT) needs to provide bidders with adequate local information at pre-bidding meetings, and publish information on the cost of locally available inputs (materials, equipment, and labor) on its website to allow bidders to submit sensible bids. The project was cofinanced by several external aid agencies. This modality proved to be suitable for financing the rapid development of the road subsector. In future road projects financed by multiple aid agencies, the Azer Road Service Open Joint-Stock Company (ARS) needs to strengthen its project management capacity in the aspects of financial accounts, project scheduling, and quality control. At appraisal, the project was designed to cover two subsectors: roads and customs. Projects of this type, covering different administration sectors, need adequate guidance and coordination. A project coordination office may be established at the central government to coordinate project management and implementation activities between the concerned government agencies. The implementation delay for the local roads component resulted in the shifting of this component to subsequent ADB-assisted projects. As local road development can efficiently bring project benefits to rural areas, especially to the poor, in future road projects more attention should be paid to the development of local roads, an integral part of the country's road network. | Project/Program Completion Reports (PCR) | Successful/Generally successful | https://evaluation-lessons.org/report/east-west-highway-improvement-project/