## Georgia
GEORGIA
REPORT NAME | SECTORS | DATE | LESSONS | REPORT TYPE | REPORT RATING | LINK
Developing a Geospatial Urban Water Supply and Sanitation Utility Management System: Technical Assistance Completion Report | Water and other urban infrastructure and services | 2015-03-01 | The basic infrastructure asset mapping is essential and can be considered an integral part of urban planning while designing for any major urban infrastructure investments. It is better to adopt a holistic approach by advance identification of various utilities to be mapped and how the database can be used by various service providers. This would involve dialogue at various levels in different government departments before designing such initiative, and the consulting firm should be engaged only after clarity on such issues. It is equally important for the utility staff to understand importance of such exercise and engage from the beginning of the TA (technical assistance). This would help the staff to have clarity on the outputs, which would be required to be updated on continuous basis for its effective use, based on future investments in the assets creation or rehabilitation. Project cycle stage: Implementation | Technical Assistance Completion Report | Successful/Generally successful | https://evaluation-lessons.org/report/developing-a-geospatial-urban-water-supply-and-sanitation-utility-management-system-technical-assistance-completion-report/
Emergency Assistance for Post-Conflict Recovery | Finance, Health, Public sector management | 2010-12-01 | Lending Modality: Having an appropriate modality is critical. ADB's Disaster and Emergency Assistance Policy together with Achieving Development Effectiveness in Weakly Performing Countries provided a ready framework for Emergency Assistance for Post-Conflict Recovery (EAPCR). Monitoring and evaluation framework. The overall success of the EAPCR could have been greater had the DMF been better designed. The impact statement could have been closer to the outcome, and assumptions about investor and consumer confidence should have been more realistic. The impact statement could have focused on maintaining sustainable and inclusive public sector spending rather than to restore the Georgian economy to the pre-war trajectory of growth and social development. A more realistic assumption could have been formulated in line with the government's commitment to give priority to social expenditures. The output targets could have been defined according to existing data and definitions. | Technical Assistance Completion Report | Successful/Generally successful | https://evaluation-lessons.org/report/emergency-assistance-for-post-conflict-recovery/
Georgia Investment Forum: Technical Assistance Completion Report | Industry and trade | 2015-07-01 | More rigorous oversight of comparable surveys to ensure greater feedback should be undertaken for future events as the percentage of Forum attendees who responded to the Forum survey was only 10%. Visa restrictions introduced by the government of Georgia in 2014 hindered participation from several of ADB's developing member countries. While the government has revised visa regulations to streamline these processes going forward, this aspect requires close follow-up for future events. The quality of panel discussion during the Forum was linked in large part to advance planning and having skillful and articulate moderators. Participation of JICA (Japan International Cooperation Agency) in the Forum outreach activities was not planned during the design stage of the TA (technical assistance). However, JICA significantly contributed to the success of the Forum by identifying the Japanese companies interested to participate in the Forum and facilitating their travel and accommodation. Such partnerships will be valuable and should be actively sought. Project cycle stage: Implementation, Operation | Project/Program Completion Reports (PCR) | Unsuccessful | https://evaluation-lessons.org/report/georgia-investment-forum-technical-assistance-completion-report/
Georgia: Validation Report of the Final Review of Country Operations, 2008 - 2012 |  | 2013-11-14 | 1. Project designs and cost estimates should be carefully validated by ADB and the government. Projects are more appropriately designed and costed when there is close oversight of preparatory technical assistance outputs. Government participation in the early stages of project preparation is important because of the knowledge of local conditions, and it is essential that the government validates designs and cost estimates prepared by consultants during the project preparatory phase. This ensures that an adequate level of financing is allocated to the project, and cost overruns are avoided (particularly in large infrastructure investments). [Main text, para. 109; Executive Summary, page ii] project cycle stage: Design Lesson Topics: Project Design: Appraisal Project Design: Project design Methodologies/Approaches: Consultation/Participation 2. Project investment should be complemented by policy reforms. The interim operational strategy final review points out that ADB's policy reform, knowledge service, and innovative pilot project support were too limited compared with the size of the lending program. Investments undertaken so far have been implemented in an inadequate policy environment. Therefore, it is critical to augment project investment with policy reforms that address the broader spectrum of sector issues. [Main text, para. 110; Executive Summary, page ii] project cycle stage: Design, Country Partnership Strategy Lesson Topics: Crosscutting Issues/Themes: Knowledge Management Policy & Reform: Policy reforms/framework Policy & Reform: Reform 3. A stronger focus on inclusive growth is needed to ensure that rural population benefits from ADB support. Inclusive growth is crucial in a country with 50% of the population living in rural areas and high youth unemployment. A focus on economic growth, where investments are primarily geared to infrastructure, is insufficient to address the issues of poverty and unemployment in rural areas. [Main text, para. 111; Executive Summary, page ii] project cycle stage: Design, Country Partnership Strategy Lesson Topics: | Country Partnership Strategy Final Review |  | https://evaluation-lessons.org/report/avatiu-port-development-project-validation-of-completion-report/
Growth Recovery Support Program | Public sector management | 2010-12-01 | Socially responsible budget. Rapid disbursements into a budget that is socially responsible and sound in macroeconomic terms provide an efficient channel for supporting public spending, including social, infrastructure, and countercyclical stimulus. Lending Modality: The crisis in Georgia, triggered largely by exogenous shocks, has underscored the need for a suitable modality that will enable ADB to provide quick support. While ADB has a program lending policy, there is no special modality for a financial crisis response operation for Asian Development Fund countries. The special program loan in the program lending policy is limited to ordinary capital resources countries (OCR). ADB's Countercyclical Support Facility (CSF) helped disburse anti-crisis support quickly to OCR eligible countries. In 2008, ADB invoked its Disaster and Emergency Assistance Policy, together with Achieving Development Effectiveness in Weakly Performing Countries, to support Georgia through the Emergency Assistance for Post-Conflict Recovery Project. However, the approach adopted under the Growth Recovery Support Program has demonstrated that ADB can quickly mobilize support for its developing members countries (DMCs). Yet, somewhat protracted internal discussions over the application of the program lending policy slowed down ADB's response in the absence of clarity on the flexible application of that policy for crisis situations such as the one faced in Georgia. ADB business procedures. While program preparation was shorter than for typical program grants and loans, streamlined and abbreviated business procedures for processing crisis response programs could allow the response to be more timely. Monitoring and evaluation framework. The overall success of the program could have been greater had the design and monitoring framework (DMF) been better designed. The impact statement could have been closer to the outcome and assumptions about investor and consumer confidence more realistic. The impact statement could have focused on maintaining sustainable and inclusive public sector spending rather than to restore the Georgian economy to the pre-war trajectory of growth and social development. A more realistic assumption could have been formulated in line with the government's commitment to give priority to social expenditures. The output targets could have been defined according to existing data and definitions. | Project/Program Completion Reports (PCR) | Successful/Generally successful | https://evaluation-lessons.org/report/growth-recovery-support-program/
Municipal Services Development Project | Water and other urban infrastructure and services | 2012-10-01 | The Municipal Development Fund (MDF) consulted proactively with the municipal governments to ensure prompt selection of subprojects. It created a momentum that was kept during project implementation and contributed to physical completion ahead of schedule. The United Water Supply Company of Georgia (UWSCG) could not be fully involved in project implementation because it was created in 2010, after the project started. Since the facilities had already been completed when transferred to UWSCG, UWSCG could not be accountable for their design and construction. Similarly, MDF and the municipal governments are no longer accountable for the completed water supply and sanitation (WSS) facilities. Future projects should involve all the parties concerned from preconstruction to completion. The quality of civil works for road pavement and watertight structures, such as the underground water reservoirs, has achieved the required national standards. However, local civil works contractors need further training on technology and workmanship for cement concrete pavement and the construction of water supply facilities, in order to reach international standards. No consultant was engaged to address issues regarding legal and/or technical aspects of operation and maintenance (O&M) planning and funding, measures for cost recovery, tariff collection, and the metering system. This poses a risk associated with inadequate O&M of project WSS facilities. MDF has a management information system (MIS) installed under the World Bank assistance program. The MIS is efficient in providing all project information and data, which helped MDF monitor implementation of the project in a timely manner. The same system should be used for future and ongoing projects. Capacity development of municipal governments has been partly addressed through on-the-job training activities only and has not been as effective as actual training courses. | Project/Program Completion Reports (PCR) | Successful/Generally successful | https://evaluation-lessons.org/report/municipal-services-development-project/
Municipal Services Development Project - Phase 2 | Transport, Water and other urban infrastructure and services | 2013-03-06 | 1. Proactive consultation with municipal governments by the Municipal Development Fund to ensure prompt selection of subprojects created a momentum that was maintained during project implementation and contributed to completion of physical works ahead of schedule. project cycle stage: Lesson Topics: 2. Considering there were some shortfalls in the road subproject detailed design work (such as drainage and ditch cover, sidewalk, and traffic safety provision), Municipal Development Fund (MDF) technical staff, local consultants and contractors need training on technology and workmanship in order to reach international standards. MDF and ADB need to ensure timely recruitment of construction supervision. project cycle stage: Lesson Topics: 3. On-the-job training activities alone are less effective than actual training courses in terms of capacity development. The capacity of the municipal governments remains weak; all lack a filing and database system to store their asset inventories, which will be essential for planning, improvement and operation and maintenance of municipal infrastructure and services. project cycle stage: Lesson Topics: 4. Issues regarding legal and/or technical aspects of operation and maintenance (O&M) planning and funding, measures for cost recovery, tariff collection, and the metering system should be properly studied by consultants to mitigate the risk associated with inadequate O&M of project water supply system facilities. project cycle stage: Lesson Topics: 5. The management information system proved to be an efficient means to provide all project information and data and helped Municipal Development Fund monitor implementation of the project in a timely manner. The same system should be used other projects. project cycle stage: Lesson Topics: | Project/Program Completion Reports (PCR) | Highly successful | https://evaluation-lessons.org/report/municipal-services-development-project-phase-2/
Road Corridor Investment Program - Project 2: Project Completion Report | Transport | 2014-09-01 | Need for adequate resource allocation to preparatory works for new projects. The cost overrun of the civil works component was a primary reason for the cancellation, and was caused by inadequacies in the investment program appraisal with respect to safeguards, engineering design and the cost estimate. The project preparatory TA was conducted with very limited resources - only about $0.75 million was allocated to complete a comprehensive feasibility study for the investment program within 8 months, which was insufficient for a country that had become an ADB member country only one year before the TA's commencement, and for construction of roads in a greenfield site. The budget and implementation duration should have been carefully examined and discussed in depth with the government prior to the project preparatory TA's implementation. ADB currently has a different financial modality to provide project preparatory support to its developing member countries, called as project design advance, that involves more robust funding for needed studies and detailed advance design, with greater government ownership. Need for comprehensive due diligence in safeguards and technical aspects. The cost overrun had two major causes: (i) an insufficient safeguard assessment during appraisal, and (ii) an inaccurate cost estimate. A comprehensive safeguards impact assessment during appraisal could have avoided the later realignment. Detailed analysis of alternative alignments and their associated potential safeguards impacts, both of environmental and social, should have been conducted as well. The original alignment was to be located in the vicinity of the protected wetland area, which should have been examined together with the cost for environmental mitigation measures to be implemented. Several factors contributed to the inaccurate cost estimate, including market volatility. The estimates were prepared in 2009, when global construction activity was low. ADB has discussed with the government the need to minimize the risk of estimation errors or design changes in future projects. As a first step, the government and ADB agreed to plan robustly and execute preparatory work with more attention to detail, especially with regards to engineering designs, safeguards, procurement and cost estimation. The government will also explore value-engineering and non-traditional project delivery methods such as design-build to mitigate the risks the project encountered during implementation. Furthermore, the critical cost factors and the technical parameters of roads to be improved in future projects should be examined, with allowance for price and quantity adjustments for uncertainty, and including adequate contingencies to minimize the risk of cost overruns. Need for the government's continuous capacity enhancement in project preparation. The government should have conducted its own robust due diligence prior to processing new projects, particularly in terms of engineering and safeguards. Further, international financial institutions, including ADB, should continue providing technical support, including institutional and capacity development programs, to enable the executing and implementing agencies to independently prepare projects with sound technical inputs. | Project/Program Completion Reports (PCR) | Successful/Generally successful | https://evaluation-lessons.org/report/road-corridor-investment-program-project-2-project-completion-report/
Social Services Delivery Program | Education, Finance, Health, Public sector management | 2011-09-01 | Socially responsible budget. Rapid disbursements into a budget that is socially responsible and sound in macroeconomic terms provide an efficient channel for supporting sustainable and inclusive public spending, including social sector financing. Loan size determination. The projected budgetary financing requirement provides the rational for determining the loan size for budget support attached to a policy reform agenda, and it rests on unfunded fiscal ï¿½adjustmentï¿½ costs of reform, including both recurrent and capital expenditures. | Project/Program Completion Reports (PCR) | Successful/Generally successful | https://evaluation-lessons.org/report/social-services-delivery-program/