## Sheet1
Construction Year | School | Location | Project Description | Status | Type
2015
| Beacon Hill (1) | Beacon Ave S & 14th Ave S | Curb bulb, partial closure, curb ramps, marked crosswalks | Complete | Crossing Improvement
| Gatewood | Fauntleroy SW & SW Myrtle St | Curb bulb | Complete | Ramps
| Salmon Bay K-8 | NW 65th St and 18th Ave NW | Curb bulbs, ramps and crosswalks | Complete | Crossing Improvement
| O'Dea High School | Columbia St & Terry Ave | Curb ramps for the school crosswalks | Complete | Ramps
| West Woodland | NW 55th St & 3rd Ave NW | Street closure, curb bulbs, ramps | Contract Awarded | Crossing Improvement
| Wedgwood | NE 85th Street between 30th Ave NE and 28th Ave NE; 28th Ave NE between NE 85th and NE 83rd St | New sidewalk | Contract Advertised | Sidewalk
| Thornton Creek | NE 77th St - 39th to 40th | Sidewalk on one side of the street | Contract Awarded | Sidewalk
| University Child Development School | Roosevelt Way NE & NE 52nd St; Roosevelt Way NE & NE 53rd St | Curb bulbs | 100% Design | Crossing Improvement
| Greenwood | NW 80th St & 1st Ave NW | Curb bulb, RRFBs, signs | Contract Advertised | Ramps
| Mercer Middle School | 16th Ave S (vacated) | Mixed use trail between S Dakota St and S Spokane St | Contract Advertised | Sidewalk
| Sacajawea | 20th Ave NE - 95th to 92nd | Sidewalk on the east side of the street | Contract Awarded | Sidewalk
| South Shore K-8 | Rainier Ave S & 51th Ave S | Island and bulb | Contract Advertised | Crossing Improvement
| Viewlands | 3rd Ave NW - 105th to 107th | Sidewalk and curb on the west side of the street | Contract Awarded | Sidewalk
| Pinehurst K-8 | Pinehurst Way NE between Roosevelt Way NE and 15th Ave NE | Crosswalk improvements | 90% Design | Crossing Improvement
| Roxhill | Roxbury Street | Crosswalk improvements | 90% Design | Crossing Improvement
2016
| Blaine | 33rd Ave W & W Smith | Curb ramps, all-way stop | Final Design | Ramps
| Wedgwood | NE 83rd St between 28th Ave NE and 25th Ave NE | New sidewalk | 90% Design | Sidewalk
| Arbor Heights | 35th Ave SW - 100th to 104th | Sidewalk on the west side of the street | 90% Design | Sidewalk
| Coe | 7th Ave W and W McGraw St | Ramps on all corners, bulb on SWC | 30% Design | Ramps
| Montlake | E Lynn St and 19th Ave E | Intersection redesign - curb bulb, all way stop? | 90% Design | Ramps
| Sanislo | SW Orchard St & 18th Ave SW | Intersection redesign - curb bulb | 90% Design | Crossing Improvement
| Van Asselt / Wing Luke | S Cloverdale from Beacon Ave S to MLK; 37th Ave S from S Cloverdale to S Thistle | Sidewalk on north side of S Cloverdale; east side of 37th Ave S | 90% Design | Sidewalk
| BF Day | N 41st St and Fremont Ave N | Curb ramps, school crosswalk | 90% Design | Ramps
| Aki Kurose Middle School | 39th Ave S | Ramps and landings at 39th Ave S and S Juneau; between S Juneau and S Graham wheel stops; sidewalk repair on the west side | 30% Design | Ramps
2017
| Dearborn Park | S Orcas - Beacon Ave S to 32nd Ave S | Add curb and landscping, improve drainage on the north side of the street | 90% Design | Sidewalk
| Broadview-Thomson | Greenwood - N 136th to N 145th | Sidewalk | 30% Design | Sidewalk
| Whitman | MARY AVE NW BETWEEN NW HOLMAN ROAD & NW 92ND ST and NW 92ND ST BETWEEN MARY AVE NW AND 15TH AVE NW | New sidewalk | Conceptual design | Sidewalk
| Whitman | 15TH AVE NW BETWEEN NW 95TH ST AND NW 96TH ST | New sidewalk | Conceptual design | Sidewalk
| Addams/Rogers | NE 110th St - 39th to 40th | Sidewalk on the south side of the street | 90% Design | Sidewalk
| Addams/Rogers | NE 110th St between 35th Ave NE and 36th Ave NE | New sidewalk | Conceptual design | Sidewalk
| Addams/Rogers | NE 110TH ST BETWEEN 35TH AVE NE AND 34th AVE NE | New sidewalk | Conceptual design | Sidewalk
2018
| Hamilton Middle School | Stone Way N and N 41st St | Curb bulbs | Conceptual design | Crossing improvement
| Northgate | N 117TH ST BETWEEN MERIDIAN AVE N AND 1ST AVE NE | New sidewalk | Conceptual design | Sidewalk
| Amazing Grace /St Paul / Emerson | RENTON AVE S AND 59TH AVE S | Curb ramps and bulbs | Conceptual design | Ramps
| Amazing Grace /St Paul / Emerson | RENTON AVE S AND S RYAN ST" | Curb ramps and bulbs | Conceptual design | Ramps
| Pinehurst | 12TH AVENUE NE BETWEEN NE 117TH & PINEHURST PARK | New sidewalk | Conceptual design | Sidewalk
| Pinehurst | NE 115TH ST BETWEEN ROOSEVELT AND PINEHURST WAY NE | New sidewalk | Conceptual design | Sidewalk
| Rainier View | BEACON AVE S BETWEEN S AUGUSTA ST & 55TH AVE S | New curb, planting strip, raised crosswalk | Conceptual design | Sidewalk
| St Edward School | RAINIER AVE S AND S MEAD ST | New ped signal | Conceptual design | Signals
2019
| Bagley | STONE AVE N AND N 80TH ST / N 79TH ST | Curb ramps, bulbs | Conceptual design | Ramps
| Chief Sealth/Denny | SW Thistle St and 25th Ave S | Curb ramps and bulbs | Conceptual design | Ramps
| Ingraham | ASHWORTH AVE N AND N 130TH ST | New ped signal | Conceptual design | Signals
| Ingraham | N 135TH ST BETWEEN BURKE AVE N AND MERIDIAN AVE N and MERIDIAN SOUTH OF N 135TH | New sidewalk | Conceptual design | Sidewalk
| Mercer Middle School | S Columbian Way & 15th Avenue S | Intersection redesign, new crosswalks, signal improvements | Conceptual design