CHAPTER 3	Preparing to Build

3.1 Site investigation and associated issues

#### Review Task 1, p70

Identify the most important aspects that would need to be included in a site investigation report being undertaken by the building designer and contractor

|  | Survey Type | City centre site | Greenfield site | Designer/Contractor |
| --- | --- | --- | --- | --- |
| Ground conditions, including type of ground and if there is any ground contamination | DS | Will need to be assessed in detail; likely to be contamination, more so if on the site of an old industrial unit | Will need to be assessed in detail; unlikely to be contamination | D: Details of potential remediation must be taken into account in specifying the works C: Unforeseen remediation requirements could lead to cost and time overruns and may make the project unfeasible |
| Location of tipping facilities, distance to tip, tipping fee | D | Should be relatively nearby | Could be a long way to nearest facility | C: Tipping costs must be taken into account when submitting tenders |
| Are there any existing buildings that need to be demolished? | DS | Highly likely | Very unlikely | D: Selection of foundation solutions etc will be affected by building remains in the ground C: Demolition costs may need to be taken into account |
| Access | S | Difficult | Easy | D: Choice of frame systems/foundation solutions, etc., may be limited by restricted access for large components C: Deliveries of materials, etc., must be carefully considered as must the potential site layout |
| Location of the site | Ds | Deliveries should not have to be delivered from a long way away | Suppliers may be far away | D: Issues such as exposure of the site may be significant as will the vernacular styles, surrounding buildings C: Logistic aspects such as deliveries/ supplies/labour availability may be significant |
| Labour availability | D | Shouldn’t be too much of a problem | Could be a big problem | See above |
| Mains services | DS | Will be close to the site | Could be a long way from the site | D: Services must be specified or connected to and this must be considered in the design stage; there may be a need to provide local elements such as septic tanks, etc. C: Logistics of connection, phasing of connection, etc., must be taken into account and temporary supplies must be arranged if necessary |
| Vicinity of the site | S | Probably requires greater security | May require less security, but theft can still occur from more isolated sites due to the lack of people out of working hours | C: Security must be costed into the tender |

# 3.2 Overview of statutory control of buildings

Review Task 2, p80

What are the main implications of the requirements of Part L of the building regulations for multi-storey and large-span commercial and industrial buildings?

For non-domestic buildings emphasis is placed on the energy efficiency of the building envelope in terms of improved U values, and also on aspects of building design other than the building envelope. In particular, there is emphasis on:

### heating and hot water systems

### mechanical ventilation and air con.

### air tightness of buildings

### lighting efficiency

### thermal insulation for pipework, ducting and vessels

Air leakage and air tightness standards must comply with CIBSE standards and this could become an aspect of considerable concern in industrial and commercial buildings.

What are the duties of a client under the CDM regulations?

What are the implications of the CDM regulations for designers?

Brief summary of CDM Regulations 2007:

- the regulations apply to all construction work (except for domestic clients) that will last for more than 30 days or will involve more than 500 person days of work

- the Client is to appoint Designers, the CDM Coordinator (whose duties include the co-ordination of design work where relevant to H&S), and the main contractor (referred to as the Principal Contractor)

- responsibility for health and safety is shared between the client, the designers, the CDMC and Contractors, that is, by all Duty Holders.

- they require the need for the process of safety management to be considered as the design develops, be carried over to the site, and then on into the maintenance phases of the building

- they require that contractors are to take greater control of sites and greater responsibility for any failures in health and safety management

- the Principal Contractor is to establish a suitable Construction Phase (Health & Safety) Plan

Good design requires a balance of factors but, as design is an iterative process, different design decisions have to be made as each stage develops. As the design process unfolds from concept to detail design stage, so designers of buildings, whether new build or refurbishment, are constantly seeking technical solutions to design problems.

In making decisions throughout the design process, the designer will be constantly balancing issues of appearance, function and cost consistent with the client’s brief and budget. As the design develops, more information becomes available and this may give rise to technical problems or design choices that might have an impact on the financial viability of the project.

- Under the UK Construction (Design and Management) Regulations 2007 (CDM), designers have a statutory duty to avoid foreseeable risks to those involved in the construction and the future use of the completed structure.

The best way to achieve this is by considering the health and safety impact of design decisions right from the outset of a design and throughout its development. This will mean thinking about the risks attached to both concept stage decisions and decisions made during scheme and detail design.

When designers are unable to eliminate risk from their designs, UK legislation requires that this is stated in the pre-construction information pack which informs the contractor of residual design risks at the tendering stage, thereby enabling him to price for and develop safe working methods during the construction phase.

The CDM Regulations are currently under revision and the new Regulations are expected to come into effect in 2015.

3.3 Overview of Utilities and Infrastructure

#### Review Task 3, p88

Set out the possible ways in which ‘grey water’ can be recycled.

Grey water can be reused for a number of purposes but must not be utilised for any form of human consumption. Examples of the possible reuse of grey water may include: flushing of toilets, urinal, etc.; cooling water for certain processes, such as mechanical plant cooling, etc.; subject to strict treatments and controls to avoid possible contamination, it may be possible to use such water for cooling of internal spaces, etc.

Sketch a skeleton services distribution network for an eight storey building.

In order to do this, consider the following steps:

1:	Identify the types of services that must be accommodated: cabled services such as power distribution, data telecommunications and IT infrastructure; piped services such as water supplies, gas supplies, sprinkler systems etc; ducted services such as air handling, heating, ventilation/air-conditioning etc.

2:	Identify the end user positions for each of these: work stations for IT and power, etc.; heat emitters and taps for hot water; vent outlets for heating and A/C systems.

3: 	Identify the major pieces of supply plant and distribution equipment such as boilers, IT servers, calorifiers, etc.

4: 	Think about the distribution of the services from the supply points to the end user locations in terms of vertical and horizontal distribution.

5: 	Consider how the distribution network can be accommodated within the building fabric by ducts, risers, conduits, voids, etc.

Generate a simple table setting out the types of utilities serving a building and the uses to which they are put.

| Utility | Form | Use |
| --- | --- | --- |
| Gas | Piped service | Supply for space heating, process heating, etc. |
| Water | Piped service | Potable water supply for consumption Process supplies for manufacture, cooling, etc. Sanitary installations, flushing toilets, washing, cleaning, etc. Humidification in some A/C systems |
| Electricity | Cabled service | Power supplies for heating, lighting, A/C, process supplies, etc. |
| Drainage | Large piped service | Self-explanatory |
| Telecommunications & Data | Cabled service | Self-explanatory |

3.4 Ground Water Control

###### Review Task 4, p89

After studying the text and the diagrams, which do you believe is the most cost effective: having a shallow-sided excavation that requires more material to be excavated, or a steep-sided excavation that requires less excavation but allows more ground water to flow into the excavation (see Figure 3.17)?

This is a difficult question to answer without having actual excavation depths and areas. The cost implications for the shallow-sided excavation are the volume of excavated material that will have to be stored or disposed of and the cost of hiring an excavator for an extended length of time. A steep-sided excavation should therefore be cheaper because less material is excavated and the excavator will be required for less time, but there may be an additional cost in supporting the sides with sheet piles, which have a cost themselves and may need to be placed using a machine-based hammer.

Why might the steep-sided excavation with a form of groundwater control be the only suitable option?

If the site is restricted for space.

For each of the systems discussed, identify the positive and negative points from environmental impact and health and safety perspectives.

The answer given here should refer to the environmental impact of the materials used in each system, their impact on the environment once in place, and the environmental impact of their manufacture. Systems that require more excavation will have a greater impact on the environment than those with less, and any system that could cause seepage of chemicals into water courses should be avoided if at all possible. Systems that require machinery will create health and safety issues and therefore those that require less machine work will be safer. Any system that involves the use of chemicals will be more dangerous than those that do not.