Managing a branch closure programme: an exercise in planning and managing the process of change

Before reading Chapter 2, you might find it useful to think about managing change from the perspective of timing and the sequencing of actions. The Bank Closure Exercise explores some of the issues and choices that have to be considered when thinking about how best to introduce a change into an organization.

The aim of this activity is to explore the issues and choices involved in developing an overall strategy for large-scale change.

The scenario

A long-established bank is facing strong competition from new entrants into the retail banking market. The new entrants have acquired some high-street branches but specialize in the provision of mobile and internet banking services. Consequently, they have a lower cost base because they do not carry the overheads associated with a large branch network. The bank is also facing an additional threat. An increasing number of customers are using smartphones to transfer funds and pay bills and are visiting their local branch less frequently.

The operations board of the traditional bank is busy working on a number of important projects and does not seem to have recognized the potential impact of the new competition and of mobile banking on their market share and margins.

You are a member of the operations board and you have given a lot of thought to the problem. You believe that the only viable strategy is to reduce the size of the existing branch network in order to reduce overheads, but to do so in a way that will lead to an increase in net revenue per customer. At this stage, you have not thought through all the details of the strategy. For example, should the branches targeted for closure be city-centre branches occupying expensive properties, but providing services for high net worth customers who the bank would be reluctant to lose, or small rural branches occupying less expensive premises but with fewer customers of high net worth to the bank?

Step 1

You have brainstormed a list of possible actions that could provide the basis for a way forward. These are listed below in Table 1.1.

You are invited to review and revise this list of actions and use your experience to:

Delete any items that, on reflection, you feel are unimportant or irrelevant.

Add, in the space provided at the bottom of Table 1.1, any other actions that you feel should be included. You are allowed to add up to four additional actions.

Think about how the actions might be sequenced from start to finish. For each action, identify whether you think it should occur early or late in the change management process. You can record this view in the space provided on the right-hand side of the table. An interactive version of this table can be found at www.macmillanihe.com/Hayes-tpcm-5e. This might make it easier for you to experiment with different ways of sequencing the actions.

Table 1 Possible actions that will inform the strategy taken by the bank

|  |  | Early |  |  |  | Late |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Identify key stakeholders who might be affected by the change |  |  |  |  |  |
| 2 | Provide a counselling service and retraining for those who are to be displaced |  |  |  |  |  |
| 3 | Inform staff how they, personally, will be affected by the closure plan |  |  |  |  |  |
| 5 | Identify a project leader and set up a branch closure team |  |  |  |  |  |
| 6 | Announce the scope and scale of the closure plan to all staff |  |  |  |  |  |
| 7 | Brief key managers about the problem and win their support for the closure plan |  |  |  |  |  |
| 8 | Identify which branches are to be closed |  |  |  |  |  |
| 9 | Review the success (or otherwise) of the closure programme and disseminate throughout the organization any lessons learned about change management |  |  |  |  |  |
| 10 | Identify the information that will be required in order to decide the number and location of branches to be closed in order to achieve targeted benefits |  |  |  |  |  |
| 11 | Announce closure plan to existing customers |  |  |  |  |  |
| 12 | Train members of the branch closure team in change management skills |  |  |  |  |  |
| 13 | Identify (and quantify) benefits sought from closures |  |  |  |  |  |
| 14 | Develop a personnel package for displaced staff |  |  |  |  |  |
| 15 | Assess effects of the closures on other aspects of the bank’s functioning |  |  |  |  |  |
| 16 | Plan any training that may be required for staff who are to be reassigned to other work |  |  |  |  |  |
| 17 | Hold team meetings to brief staff about the closure plans and indicate when they will be informed about how they (personally) will be affected by the change |  |  |  |  |  |
| 18 | Identify what steps could be taken to retain high value customers affected by the closures |  |  |  |  |  |
| 19 | Provide training for managers and supervisors to help others and themselves to cope with the change |  |  |  |  |  |
| 20 | Issue newsletter outlining progress towards full implementation |  |  |  |  |  |
| 21 | Decide who should be involved in analysing the information relating to whether a closure plan will deliver sufficient benefits to justify the costs involved |  |  |  |  |  |
| 22 | Seek views of customers who might be affected by the closures about what issues should be given attention |  |  |  |  |  |
| 23 | Seek views of branch staff about the issues that will have to be given attention if the closure plan is to be successfully accomplished |  |  |  |  |  |
| 24 | Post-implementation, provide feedback to staff about how the change is affecting performance |  |  |  |  |  |
| 25 | Initiate programme to make properties suitable for disposal (e.g. remove vaults) |  |  |  |  |  |
| 26 | Celebrate successes and build on them in order to motivate people to continue working to improve the bank’s competitive position |  |  |  |  |  |
| 27 | Decide on date for first closures |  |  |  |  |  |
| 28 | Identify any personal gains or losses that might be perceived by those employees who will be affected by the closures |  |  |  |  |  |
| 29 | Specify timetable for implementing the closure plan |  |  |  |  |  |
| 30 | Consider what might be done to motivate employees to accept the change |  |  |  |  |  |
| 31 | Issue a press release about the closure plan |  |  |  |  |  |
| 32 | Monitor progress against timetable and anticipated benefits |  |  |  |  |  |
| 33 | Explore the best way of disposing of redundant properties |  |  |  |  |  |
| 34 | Identify social banking issues raised by the closures (e.g. what will happen to customers without transport when their local branch closes) |  |  |  |  |  |
| 35 | Plan what will happen to displaced staff (redeployment, early retirement, redundancy) |  |  |  |  |  |
| 36 | Arrange an awayday for members of the ops board to focus their thinking on emerging threats and opportunities and win their support for the change |  |  |  |  |  |
| 38 | Reflect on how well the change is progressing and discuss with colleagues what else could be done to ensure the change is successful |  |  |  |  |  |
| 39 | Decide who should be involved in identifying which branches are to be closed |  |  |  |  |  |

Step 2

Consider your list of action statements and assemble them into a plan:

Identify the sequence of actions from start to finish, recognizing that some actions may occur in parallel or be repeated.

Identify relationships between actions in your plan and consider how different actions might be grouped together to form separate steps or distinctive parts of your plan.

Summarize your plan as a flow diagram, including descriptive labels for the main aspects or stages of your plan.

- You might find it helpful to print out all the actions listed in table 1 on to separate post-its so that it will be easier to move them about and experiment with different ways of:

- Sequencing them

- Grouping them into categories that reflect the main steps in your approach to manage the change process

You might find it useful to compare the change model you developed here to manage the branch closures with the model presented at the end of Chapter 2. As you read the remaining chapters of this book, you might also find it helpful to reflect on how the content of each chapter might influence your approach to managing this kind of change.