## Blank Template
Company |  |  |  | YOUR COMPANY LOGO
Street Address, City, ZIP Code
Phone
Email
Project
| Project Status Report # |  | 0
Project Summary
Project Name |  | Date |  | Report #
Project Manager |  | PM Contact |  | Project Sponsor
Project Overview
| Status | Comments
Overall Project Health
Schedule
Budget
Issues
Project Completion
Start Date
Baseline End Date
Expected End Date
Variance | 0
Project Completion % | 30% | 70%
Budget
Total Budget |  | Comment
Budget to Date
Budget Left | 0
Milestones
Critical Milestones |  | Due date | Completed | Comment
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Issues
Key Issue |  | Status | Action Plan |  | Comment
INSERT YOUR GANTT CHART HERE
Developed by Mindiply.com
Try Mindiply Timeline, the PM tool that will automatically generate beautiful and clear reports. You'll save time, your clients will love them!

## Example
Company | Mindiply Ltd
Street Address, City, ZIP Code | Brighton, United Kingdom
Phone | +44 2034095596
Email | info@mindiply.com
Cats&Dogs App Project
| Project Status Report # 4 |  | 2020-08-01
Project Summary
Project Name | Cats&Dogs App | Date | 2020-08-01 | Report # | 4
Project Manager | John Doe | PM Contact | jdoe@mindiply.com | Project Sponsor | ACME
Project Overview
| Status | Comments
Overall Project Health | Amber | Currently, we are spending somewhat less than expected, but we are a bit behind with the schedule
Schedule | Red | User testing is taking more time than expected, activity will be completed in about two weeks
Budget | Green | Project is currently under budget
Issues | Amber | Some minor issues - see below
Project Completion
Start Date | 2020-05-10
Baseline End Date | 2020-10-20
Expected End Date | 2020-10-30
Variance | 10
Project Completion % | 40% | 60%
Budget
Total Budget | 200000 | Comment | We are currently under budget by 5K (80K instead of 85K expected)
Budget to Date | 80000
Budget Left | 120000
Milestones
Critical Milestones |  | Due date | Completed | Comment
Milestone 1 |  | 2020-06-15 | TRUE
Milestone 2 |  | 2020-07-20 | TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Issues
Key Issue |  | Status | Action Plan |  | Comment
Delays in Activity 4 (user testing): due to Covid-19 finding users for face-to-face sessions is harder than expected |  | Investigating | We are evaluating other ways to find testers and/or to run online sessions |  | We could use the extra budget for paying testers or an agency?
Developed by Mindiply.com
Try Mindiply Timeline, the PM tool that will automatically generate beautiful and clear reports. You'll save time, your clients will love them!

## hidden (hidden)
Red
Amber
Green