## Tasks
Plan name | Pre Signing Template
Task Name | Bucket Name
90 Launch Guide Tasks Assigned. | To do
Signing appointment arranged with prospect, confirming Joel/Michael/Chris is available. *Please allow a minimum of 72 hours for documentation to be prepared. | To do
Franchise Finals prepared and sent to Franchise Team, include all details for the addendum. | To do
Application approved or rejected by the Board of Directors. | To do
Prospect to register new company/ provide Franchise Team with the following; | To do
Approved Office Name List sent to prospect. | To do
Reference Calls conducted and uploaded to Franchise Applications group. | To do
Completed Franchise Application and Internal Form uploaded to Franchise Applications group for approval. | To do
Arrange for prospect to meet with a Director. | To do
Disclosure Documents and Franchise Application sent to prospect. | To do
Prospect folder created in SharePoint. | To do
Details provided to Franchise Team to prepare Disclosure Document, Prospective Franchisee Information Statement, Confidentiality Agreement, Protected Territory Certificate & Application through DocuSign. | To do
14-day Disclosure Period is satisfied and BGM advised. | To do
Franchise Team to prepare Franchise Agreement and Addendum and send to BGM for approval. | To do
Franchise Team to arrange invoice with Accounts for the Initial Franchise Fee. | To do
Franchise Team to prepare Induction agenda for Broker/Owner with Regional Team. | To do
Franchise Team to notify regional team. | To do
Franchise Team to email Broker/Owner before signing appointment. | To do
Franchise Team to prepare hard copy of documents for Signing Appointment. | To do
Franchise Team to prepare signing gift. | To do
BGM to arrange celebratory dinner with Broker/Owner for after signing appointment. Advise Franchise Team to make booking if required. | To do
Franchise Agreement signed. Franchise Team to email the following to the new Broker/Owner. | To do