## Tasks
Plan name | AUS New Franchise Template
Task Name | Bucket Name | Checklist Items | Labels
Health Check appointment arranged with Lenore Seiber. | TRAINING & MENTORING |  | After Launch
Marketing Team to conduct full marketing induction. | MARKETING | Precinct overview (Broker Dashboard);Discuss approved website providers;Social Media Guide to Broker and discuss available content;If applicable launch marketing campaign to be discussed | Before Launch
Marketing Team to confirm with Broker/Owner their solution with website. | MARKETING | Assist with any relevant introductions if required. | Before Launch
Marketing to email eStorm to set up compliant domain names. | MARKETING |  | Before Launch
Marketing Team to create launch material and upload to subsite. | MARKETING | Business Cards;Logos;Email Signature | Before Launch
Marketing Team to order any items included in the Addendum. | MARKETING | Letterhead;Presentation Folders;With Comps;DL Cards;EDM Header;Social Media Tile | Before Launch
Marketing team to request all signboard suppliers details and provide them with a Branding Guide and additional flag and directional templates. | MARKETING |  | Before Launch
Marketing Team to discuss Make-A-Wish association with Franchisee. If franchisee wishes to opt into the initiative, RE/MAX to provide collateral* Settlement program* Fundraisers. | MARKETING |  | Before Launch
BGM to notify Lyn of launch party date for a press release to be drafted. | MARKETING |  | Before Launch
Broker/Owner to set up Social Media Accounts as relevant. | MARKETING |  | Before Launch
Broker/Owner to liaise with Marketing Team for external signage and approval. | MARKETING |  | Before Launch
Broker/Owner to contact Marketing Team if publications do not have approved templates. | MARKETING |  | Before Launch
Public Relations to liaise with the Broker/Owner. | MARKETING | ongoing PR opportunities;New office announcement;available media release templates | Before Launch
Marketing Team to send out communication to network about office opening. | MARKETING |  | Launch Day
BGM to notify PR of launch date for a press release to be drafted. | OFFICE LAUNCH FUNCTION |  | Before Launch
Membership Team to ensure office is appearing on RE/MAX Australia website with correct address and contact information. | MEMBERSHIP |  | Launch Day
Franchise Team to email eStorm. | HEAD OFFICE | Request they contact Broker/Owner for training session;Add Broker to Broker Page on Precinct;Creat Subsite
Professional Development Manager to add Broker/Owner to the R4 attendee list (if applicable per their addendum). | TRAINING & MENTORING |  | Before Launch
Membership Team to train Broker/Owner in returns process. | MEMBERSHIP |  | After Launch
Membership Team to check office fee structure in the system. | MEMBERSHIP |  | Launch Day
Membership Team to confirm members have received Max Centre welcome email and registered their log in details. | MEMBERSHIP |  | Launch Day
Membership Team to chase any outstanding membership forms. | MEMBERSHIP |  | Launch Day
Membership Team to set up office in Pier Alpha. | MEMBERSHIP |  | Before Launch
Membership Team to add new office to Weekly Report. | MEMBERSHIP |  | Before Launch
Membership Team to process new Broker/Owner membership forms. | MEMBERSHIP |  | Before Launch
Franchise Team to email LLC and advise of office opening. | HEAD OFFICE |  | After Launch
BGM to conduct site inspection & location check of proposed office. Take 3 photos of proposed site (front/side/side) and send to marketing team. | OFFICE SPACE |  | Before Launch
Franchise Team to update Master Spreadsheet in Sharepoint. | HEAD OFFICE |  | Before Launch
Soft copy of Franchise Agreement emailed to Broker/Owner and Hard copy with welcome letter sent in mail. | FRANCHISE DOCUMENTATION |  | Before Launch
Franchise Team to notify Regional Team of new office and send copy of signed Addendum to appropriate staff members. | FRANCHISE DOCUMENTATION |  | Before Launch
Franchise Team to email signed Franchise Agreement to RE/MAX LLC. | FRANCHISE DOCUMENTATION |  | Before Launch
BGM to prepare Handover Brief and send to Franchise Team. | HEAD OFFICE |  | Before Launch
Franchise Team to contact Broker/Owner to arrange Business Plan & Smart Goals Session with BGM. | BUSINESS PLAN |  | Before Launch
Accounts to contact Broker/Owner to explain Integrapay for Direct Debit of franchise fees. | HEAD OFFICE |  | After Launch
Broker/Owner to join the Property & Asset Management Chapter. | TRAINING & MENTORING |  | Before Launch
Franchise Team to notify Pivotal Financial of new Franchisee. | PIVOTAL FINANCIAL |  | Before Launch
Pivotal to complete follow up call with Broker/Owner after induction day and discuss services. | PIVOTAL FINANCIAL |  | Before Launch
Pivotal to allocate a Broker to the office. | PIVOTAL FINANCIAL |  | Before Launch
Pivotal Financial to call Broker/Owner to congratulate them on opening day. | PIVOTAL FINANCIAL |  | Launch Day
Pivotal Financial to arrange date to meet Broker/Owner at office. | PIVOTAL FINANCIAL |  | After Launch
Franchise Team to set up relevant office folder in Sharepoint & create physical file in cupboard. | HEAD OFFICE |  | Before Launch
Partner Co-ordinator to send Broker/Owner details to all RE/MAX Partners. | HEAD OFFICE |  | Before Launch
Managing Director to phone new Broker/Owner and congratulate them on signing. | HEAD OFFICE |  | Before Launch
BGM to supply the Franchise Team with list of 5 surrounding suburbs for Suburb Statistic Reports to be generated for Business Planning Session. | BUSINESS PLAN |  | Before Launch
Franchise Team to generate Suburb Statistics Reports for surrounding suburbs ready for Business Planning Session. BGM to supply list. | BUSINESS PLAN |  | Before Launch
Office Administrator to discuss with the Broker/Owner the products for hire. Advise of booking process. | OFFICE LAUNCH FUNCTION |  | Before Launch
Franchise Team to add a recurring reminder in BGM, Franchise Director & Managing Director calendar for Broker Anniversary date. | HEAD OFFICE |  | Launch Day
Franchise Team to have Purchase Order signed off and order framed balloon poster from Frame Craft. | HEAD OFFICE |  | Before Launch
Franchise Team to arrange flowers to be sent to Broker/Owner on opening day. | HEAD OFFICE |  | Launch Day
Regional Team to call the office on opening day to congratulate them. | HEAD OFFICE |  | Launch Day
Franchise Team to send 'Look Who's Joined' email to BGM's via iRealty. | HEAD OFFICE |  | Launch Day
Managing Director to call Broker/Owner and congratulate them on opening day. | HEAD OFFICE |  | Launch Day
Professional Development Manager to book Broker into Broker/Owner Essentials Training. | TRAINING & MENTORING |  | Before Launch
Deposit & Fees Paid | FRANCHISE DOCUMENTATION |  | Before Launch
RE/MAX Australia to Register Business Name | REGISTER | Record of Registration sent to Broker/Owner | Before Launch